## Contents
GINR Activity: Apr 01, 2019 to Apr 30, 2019
Table of Contents
Disclaimer and References | Disclaimer on the use of this report, and references to associated ERCOT Binding Documents ***Please read***
Acronyms | A list of the various acronyms used throughout the report
Summary | Tables that provide project aggregate counts and megawatt capacities by GINR phase and fuel type
Project Commissioning Update | A table listing project commissioning approval milestones met for the month: energization, synchronization, and commercial operations approval
Project Cancellation Update | A table listing the projects cancelled for the month
Project Details | A table that lists project details; only includes projects for which a Full Interconnection Study has been requested
GINR Trends | Charts and tables that show historical and projected interconnection study trends.
Time of Report Run: May 1, 2019 8:00:32 AM

## Disclaimer and References
Generator Interconnection Status Report - Disclaimer
FOR PLANNING PURPOSES ONLY
This ERCOT Working Paper has been prepared for specific ERCOT and Market Participant purposes, and has been
developed from data provided by Interconnecting Entities and Transmission Service Providers that has been entered into the online GINR system.
The data may contain errors or be obsolete depending on when the data was entered. ERCOT MAKES NO WARRANTY, EXPRESS
OR IMPLIED,INCLUDING ANY WARRANTY OF MERCHANTABILITY OR FITNESS FOR ANY PARTICULAR PURPOSE,
AND DISCLAIMS ANY AND ALL LIABILITY WITH RESPECT TO THE ACCURACY OF SAME OR THE FITNESS OR
APPROPRIATENESS OF SAME FOR ANY PARTICULAR USE. THIS ERCOT WORKING PAPER IS SUPPLIED WITH ALL FAULTS.
References
The links below provide more information on the ERCOT interconnection process:
http://www.ercot.com/mktrules/guides/planning/current
http://www.ercot.com/services/rq/re/reg/Resource%20Interconnection%20Handbook.pdf

## Acronyms
Acronyms
GINR = Generation Interconnection or Change Request
COD = Commercial Operation Date
SS = Security Screening Study
FIS = Full Interconnection Study
IA = Interconnection Agreement; can be either of the following:
- Standard Generation Interconnection Agreement (SGIA)
- Public financially binding agreement
- An official letter from a Municipally Owned Utility or Electric Cooperative signifying developer intent to build and operate generation facilities and
interconnect with the MOU or EC
POI = Point of lnterconnection
INR = Interconnection Request Number
TSP = Transmission Service Provider
NtP = Notice-to-Proceed given to the TSP for interconnection construction
CDR = Capacity, Demand and Reserves Report
SFS = Sufficient Financial Security provided to the TSP for construction of the interconnection facilities
QSA = Quarterly Stability Assessment
Fuel Types | Technology Types
BIO = Biomass | BA = Battery Energy Storage
COA = Coal | CC = Combined-Cycle
GAS = Gas | CE = Compressed Air Energy Storage
GEO = Geothermal | CP = Concentrated Solar Power
HYD = Hydrogen | EN = Energy Storage
NUC = Nuclear | FC = Fuel Cell
OIL = Fuel Oil | GT = Combustion (gas) Turbine, but not part of a Combined-Cycle
OTH = Other | HY = Hydroelectric Turbine
PET = Petcoke | IC = Internal Combustion Engine, eg. Reciprocating
SOL = Solar | OT = Other
WAT = Water | PV = Photovoltaic Solar
WIN = Wind | ST = Steam Turbine other than Combined-Cycle
WT = Wind Turbine

## Summary
Summary |  |  | Major GINR Milestone Status by Fuel/Technology Type, MW
Currently tracking 527 generation interconnection or change requests as of Apr 30, 2019 |  |  | Includes only those projects for which a Security Screening Study (SS) has been requested.
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  |  | Fuel | Technology | SS Started | SS Started | SS Completed | SS Completed | SS Completed | SS Completed | SS Completed | TOTAL
Includes only those projects for which a Security Screening Study (SS) is underway |  |  | Type | Type | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | FIS Started | FIS Completed
[5 empty] | No IA | No IA | No IA | No IA | No IA | IA | IA
Status of SS, FIS, and IA | Project Count | % of Total | Gas | Combined-Cycle |  | 19 |  | 1262.5 |  | 1485.8 | 252 | 3019.3
SS Started, FIS Not Started, No IA | 38 | 7.28% | Gas | Combustion Turbine |  | 140 | 950 | 3782.3 | 317 | 968 | 318 | 6475.3
SS Started, FIS Started, No IA | 25 | 4.789% | Gas | Internal Combustion Engine
SS Completed, FIS Not Started, No IA | 79 | 15.13% | Gas | Compressed Air Energy Storage | 280 |  | 328 |  |  |  |  | 608
SS Completed, FIS Started, No IA | 235 | 44.83% | Gas | Steam Turbine
SS Completed, FIS Completed, No IA | 30 | 4.981% | Gas | Fuel Cell
SS Completed, FIS Started, IA | 43 | 8.238% | Gas | Total gas | 280 | 159 | 1278 | 5044.8 | 317 | 2453.8 | 570 | 10102.6
SS Completed, FIS Completed, IA | 77 | 14.75% | Coal |  |  |  |  | 45 |  |  |  | 45
Total Interconnection Requests | 527 |  | Wind |  | 1724.4 | 616.5 | 3130.6 | 15490.69 | 681.5 | 3989 | 10011.59 | 35644.28
Cancelled Studies (since last month) | 9 |  | Solar |  | 5770 | 3271.36 | 12433.5 | 25030.79 | 1051.7 | 4966.35 | 2131.75 | 54655.45
| Capacity, MW |  | Biomass
Total Capacity Under Study | 104248.57 |  | Other | Battery | 265.8 | 647.4 | 738.6 | 1354.44 |  | 495 |  | 3501.24
Interconnection Agreements Executed | 24617.49 |  | Other* |  |  |  | 300 |  |  |  |  | 300
Cancelled (since last month) | 2552.1 |  | TOTAL |  | 8040.2 | 4694.26 | 17880.7 | 46965.72 | 2050.2 | 11904.15 | 12713.34 | 104248.57
* Other includes petroleum coke (pet coke), hydroelectric, fuel oil, geothermal energy, other miscellaneous fuels reported by developers, and fuel cells that use fuels other than natural gas.

## Project Commissioning Update
Commissioning Approvals During April 2019
Commissioning Category | INR | Project Name | Fuel | County | Approval Date * | MW **
Synchronization Approved by ERCOT | 12INR0055 | S_Hills Wind | Wind | Baylor | 2019-04-19 | 30.24
Synchronization Approved by ERCOT | 11INR0062 | Shaffer | Wind | Nueces | 2019-04-05 | 226
Synchronization Approved by ERCOT | 18INR0033 | Oveja Wind | Wind | Irion | 2019-04-05 | 300
Energization Approved by ERCOT | 12INR0055 | S_Hills Wind | Wind | Baylor | 2019-04-11 | 30.24
Energization Approved by ERCOT | 19INR0029 | Phoebe Solar | Solar | Winkler | 2019-04-12 | 250
* For projects approved for commercial operations, the approval date is the Resource Commissioning Date defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a
Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative
values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.

## Project Cancellation Update
Projects Cancelled by the Developer during April 2019*
INR | Project Name | Fuel | County | Cancel Date | MW **
20INR0225 | Sugarland Power Plant | Gas | Brazoria | 2019-04-03 13:48 | 484
12INR0002a | Silver Canyon Wind A | Wind | Briscoe | 2019-04-09 11:08 | 200
13INR0010def | Scandia Wind DEF | Wind | Parmer | 2019-04-08 15:04 | 600.3
* Includes only those projects cancelled after the developer makes a Full Interconnection Study (FIS) request.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.

## Project Details
GINR Project Details
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study (FIS) has been requested are included. Because of legacy data issues,
certain projects that are in the FIS stage are reported as having no FIS Request date, but nevertheless have successfully completed an FIS application.
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GINR system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not been obtained or reported to ERCOT yet.
Project Attributes | [10 empty] | Changes from Last Report | GINR Project Milestone Dates
INR | Project Name | GINR Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | IA Signed |  | Air Permit | GHG Permit | Water Availability | Meets Planning | Meets All Planning |  | Construction Start | Construction End | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Change indicators: Proj Name, MW | [5 empty] | Financial Security |  |  |  | Guide Section 6.9(1) | Guide Section 6.9 | Meets Planning Guide
[11 empty] | Size , COD, SFS/NtP, FIS Request | [5 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[17 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[21 empty] | Models | Models
08INR0019b | Grandview 5 W | SS Completed, FIS Started, No IA | Eon | 79005 Railhead 345kV | Gray | PANHANDLE | 2020-12-15 | WIN | WT | 249 |  | 2006-07-21 | 2006-10-02 | 2006-07-21 |  |  | No | Not Required | Not Required | Not Required
11INR0054 | Midway Wind | SS Completed, FIS Completed, IA | Apex Clean | 8961 Whitepoint 138kV | San Patricio | COASTAL | 2019-04-05 | WIN | WT | 162.9 |  | 2009-02-26 | 2009-05-28 | 2009-11-30 | 2018-04-19 | 2017-11-05 | Yes | Not Required | Not Required | Not Required | 2018-04-24 | 2018-09-28 | 2018-05-01 |  |  | 2018-10-23 | 2018-12-04
11INR0062 | Shaffer | SS Completed, FIS Completed, IA | Clearway Energy | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2019-05-22 | WIN | WT | 226 |  | 2009-04-23 | 2009-06-16 | 2009-07-21 | 2018-06-13 | 2013-07-02 | Yes | Not Required | Not Required | Not Required | 2018-04-18 | 2018-09-28 | 2018-07-31 |  |  | 2019-03-27 | 2019-04-05
12INR0055 | S_Hills Wind | SS Completed, FIS Completed, IA | SEYMOUR HILLS WIND PROJECT, LLC | 33728 Mabelle 69kV | Baylor | WEST | 2019-05-30 | WIN | WT | 30.24 | COD | 2010-09-28 | 2010-12-20 | 2016-08-17 | 2018-06-19 | 2017-12-04 | Yes | Not Required | Not Required | Not Required | 2018-10-04 | 2018-10-04 | 2018-08-01 |  |  | 2019-04-11 | 2019-04-19
12INR0059b | HOVEY (Barilla Solar 1B) | SS Completed, FIS Completed, IA | First Solar | 60385 Solstice 138kV | Pecos | WEST | 2019-02-28 | SOL | PV | 7.4 |  | 2010-12-01 | 2011-02-25 | 2011-08-09 | 2014-01-16 | 2013-12-26 | Yes | Not Required | Not Required | Not Required
12INR0060 | Wilson Ranch | SS Completed, FIS Completed, IA | ENGIE | 76003 Big Hill 345kV | Schleicher | WEST | 2019-05-31 | WIN | WT | 199.5 |  | 2010-12-03 | 2014-03-21 | 2011-06-06 | 2018-05-31 | 2018-05-21 | Yes | Not Required | Not Required | Not Required | 2018-05-21 | 2018-09-28 | 2018-04-30 |  |  | 2018-10-11 | 2018-11-29
13INR0010a | Mariah Del Este | SS Completed, FIS Started, IA | Mariah Acquisition | 141765 Mariah 345kV | Parmer | PANHANDLE | 2020-10-30 | WIN | WT | 152.5 |  | 2009-06-29 | 2009-09-25 | 2010-03-26 |  | 2013-01-31 | Yes | Not Required | Not Required | Not Required | 2018-04-30 | 2018-04-30
13INR0025 | Northdraw Wind | SS Completed, FIS Started, IA | National Renewable Solutions | 79504 AJ Swope 345kV | Randall | PANHANDLE | 2020-08-01 | WIN | WT | 150 |  | 2010-06-15 | 2010-09-02 | 2011-03-01 |  | 2018-04-25 | No | Not Required | Not Required | Not Required
13INR0026 | Canadian Breaks Wind | SS Completed, FIS Completed, IA | Macquarie Cap | Tap 345kV 79502 Windmill - 79504 AJ Swope | Oldham | PANHANDLE | 2019-09-13 | WIN | WT | 210 |  | 2010-07-06 | 2010-10-04 | 2011-04-01 | 2017-03-16 | 2016-05-20 | Yes | Not Required | Not Required | Not Required | 2018-09-04 | 2018-10-30 | 2018-10-30
13INR0038 | Wildrose Wind | SS Completed, FIS Started, IA | S Power | 79501 Ogallala 345kV | Swisher | PANHANDLE | 2021-12-30 | WIN | WT | 302.5 |  | 2011-05-01 | 2011-05-26 | 2011-11-02 |  | 2015-09-06 | Yes | Not Required | Not Required | Not Required | 2017-05-04
14INR0009 | WKN Amadeus Wind | SS Completed, FIS Started, IA | WKN | tap 345kV 11305 Dermott - 60704 Kirchhof | Fisher | WEST | 2020-05-15 | WIN | WT | 245.9 |  | 2011-01-24 | 2011-03-18 | 2011-09-12 |  | 2018-03-15 | Yes | Not Required | Not Required | Not Required | 2019-03-07
14INR0030c | Panhandle Wind 3 | SS Completed, FIS Started, IA | Pattern Energy | 79005 Railhead 345kV | Carson | PANHANDLE | 2020-12-01 | WIN | WT | 248 |  | 2012-07-03 | 2012-08-17 | 2014-03-26 |  | 2014-08-25 | Yes | Not Required | Not Required | Not Required | Date Not Available
14INR0033 | Goodnight Wind | SS Completed, FIS Completed, IA | FGE Power | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | PANHANDLE | 2020-08-15 | WIN | WT | 504.4 |  | 2012-07-24 | 2012-09-19 | 2013-03-04 | 2017-09-25 | 2018-03-07 | No | Not Required | Not Required | Not Required
14INR0044 | West of Pecos Solar | SS Completed, FIS Completed, IA | Eon | 11083 Riverton 138kV | Reeves | WEST | 2019-12-15 | SOL | PV | 100 |  | 2013-01-21 | 2013-02-19 | 2013-06-12 | 2019-04-25 | 2019-02-05 | Yes | Not Required | Not Required | Not Required | 2017-05-04 | 2019-04-24 | 2019-04-24
14INR0045 | Torrecillas Wind | SS Completed, FIS Completed, IA | Nextera | 161252, 161301 Torrecillas 34.5kV | Webb | SOUTH | 2019-04-15 | WIN | WT | 300.5 |  | 2013-01-30 | 2013-03-14 | 2013-01-30 | 2018-05-14 | 2018-04-12 | Yes | Not Required | Not Required | Not Required | 2018-04-26 | 2018-04-26 | 2018-05-14 |  |  | 2018-11-09 | 2019-02-26
15INR0034 | El Algodon Alto W | SS Completed, FIS Started, No IA | Eon | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | COASTAL | 2020-12-31 | WIN | WT | 201 |  | 2013-02-04 | 2013-03-25 | 2013-08-16 |  |  | No | Not Required | Not Required | Not Required
15INR0044 | Corazon Solar | SS Completed, FIS Started, No IA | Enerverse | 80219 Lobo 345kV | Webb | SOUTH | 2019-12-31 | SOL | PV | 200 |  | 2013-09-06 | 2013-09-16 | 2013-08-20 |  |  | No | Not Required | Not Required | Not Required
15INR0051 | Tierra Blanca W | SS Completed, FIS Started, No IA | Eon | 79501 Ogallala 345kV | Randall | PANHANDLE | 2021-12-15 | WIN | WT | 200 |  | 2013-10-01 | 2013-10-18 | 2014-02-05 |  |  | No | Not Required | Not Required | Not Required
15INR0059 | Emerald Grove Solar | SS Completed, FIS Started, IA | Cypress Creek Renewables | 6601 Rio Pecos 138kV | Pecos | WEST | 2020-04-10 | SOL | PV | 108 |  | 2013-11-13 | 2013-12-23 | 2013-11-12 |  | 2018-06-27 | Yes | Not Required | Not Required | Not Required | Date Not Available | 2019-04-17
15INR0063 | Easter Wind | SS Completed, FIS Completed, IA | TriGlobal | 79502 Windmill 345kV | Castro | PANHANDLE | 2020-10-31 | WIN | WT | 307.5 |  | 2013-12-18 | 2014-02-27 | 2014-04-15 | 2017-12-06 | 2018-06-01 | No | Not Required | Not Required | Not Required
15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2019-12-13 | WIN | WT | 162.1 |  | 2013-11-27 | 2014-01-27 | 2014-04-15 | 2017-09-27 | 2018-05-30 | Yes | Not Required | Not Required | Not Required | 2018-05-30 | 2018-09-19 | 2019-01-22
15INR0090 | Pflugerville Solar | SS Completed, FIS Started, IA | RRE Solar | tap 138kV 7336 Gillie - 3650 Elgin | Travis | SOUTH | 2020-12-31 | SOL | PV | 144 | COD | 2015-04-28 | 2015-07-01 | 2015-09-30 |  | 2017-06-13 | No | Not Required | Not Required | Not Required
16INR0003 | LEVEE (Freeport LNG) | SS Completed, FIS Completed, IA | Freeport LNG | 43336 Oyster Cr 138kV | Brazoria | COASTAL | 2019-08-10 | GAS | GT | 11 |  | 2011-12-15 | 2012-02-15 | 2012-01-04 | 2018-01-22 | 2014-01-13 | Yes | 2014-07-16 | Not Required |  | 2018-10-09 | 2018-10-09 | 2018-10-09 |  |  | 2019-03-15
16INR0010 | FGE Texas 1 Gas | SS Completed, FIS Started, IA | FGE Power | Tap 345kV 1030 Morgan - 1025 Falcon | Mitchell | WEST | 2021-04-30 | GAS | CC | 742.9 |  | 2013-04-24 | 2013-05-29 | 2013-05-14 |  | 2016-08-31 | No | 2016-12-16 | 2016-12-12 | 2014-01-29
16INR0012 | Stella 2 Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 80076 Ajo - 80071 Zorillo | Kenedy | COASTAL | 2020-12-30 | WIN | WT | 201 |  | 2013-06-13 | 2013-03-15 | 2013-09-10 |  |  | No | Not Required | Not Required | Not Required
16INR0014 | Cattleman Wind A | SS Completed, FIS Started, No IA | Eon | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | PANHANDLE | 2021-09-01 | WIN | WT | 201.6 |  | 2013-10-01 | 2013-11-18 | 2014-02-10 |  |  | No | Not Required | Not Required | Not Required
16INR0014b | Cattleman Wind B | SS Completed, FIS Started, No IA | Eon | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | PANHANDLE | 2021-09-01 | WIN | WT | 201.6 |  | 2013-10-01 | 2013-11-18 | 2014-02-10 |  |  | No | Not Required | Not Required | Not Required
16INR0019 | BlueBell Solar | SS Completed, FIS Completed, IA | Nextera | 76090 Divide 345kV | Coke | WEST | 2019-04-15 | SOL | PV | 30 |  | 2013-11-15 | 2013-12-30 | 2013-11-07 | 2018-05-01 | 2015-08-19 | Yes | Not Required | Not Required | Not Required | 2018-05-01 | 2018-09-12 | 2018-05-01 |  |  | 2018-10-12 | 2018-10-25
16INR0033 | Hart Wind | SS Completed, FIS Completed, IA | Orion | 79501 Ogallala 345kV | Castro | PANHANDLE | 2020-12-31 | WIN | WT | 150 |  | 2014-02-10 | 2014-03-20 | 2014-10-27 | 2018-02-19 | 2018-08-06 | No | Not Required | Not Required | Not Required
16INR0037c | Pumpkin Farm Wind | SS Completed, FIS Completed, IA | Apex Clean | 79505 White River 345kV | Floyd | PANHANDLE | 2020-12-01 | WIN | WT | 280.9 |  | 2014-02-24 | 2014-04-08 | 2014-02-18 | 2018-01-12 | 2017-03-24 | Yes | Not Required | Not Required | Not Required | 2017-03-24 | 2018-09-19
16INR0044 | Halyard Wharton | SS Completed, FIS Started, IA | Halyard Energy | tap 345kV 9073 Holman - 44200 Hillje | Wharton | SOUTH | 2021-06-01 | GAS | GT | 484 |  | 2014-03-17 | 2014-04-28 | 2014-11-11 |  | 2016-01-26 | No | 2015-10-09 | Not Required | 2015-09-21
16INR0045 | Halyard Henderson | SS Completed, FIS Started, IA | Halyard Energy | tap 345kV 3109 Stryker - 3123 Trinidad | Henderson | NORTH | 2021-05-01 | GAS | GT | 484 |  | 2014-03-20 | 2014-04-15 | 2014-07-21 |  | 2016-04-01 | No | 2015-12-08 | Not Required | 2016-01-05
16INR0049 | Nazareth Solar | SS Completed, FIS Started, IA | Lendlease Energy | 79501 Ogallala 345kV | Castro | PANHANDLE | 2021-05-31 | SOL | PV | 201 | COD SFS/NtP | 2014-06-19 | 2014-07-25 | 2014-07-01 |  | 2018-05-10 | Yes | Not Required | Not Required | Not Required
16INR0054 | NA | SS Completed, FIS Completed, IA | NASA | 42970 Nasa 138kV | Harris | HOUSTON | 2018-09-01 | GAS | CC | 12 |  | 2015-03-10 | 2015-04-01 | 2015-03-10 | 2016-01-26 | 2016-10-27 | Yes | Not Required | Not Required |  | 2016-11-10 | 2018-09-28 |  |  |  |  | 2017-11-27
16INR0062b | Lockett Wind | SS Completed, FIS Completed, IA | Lincoln Clean | 141355-6 Electra 34.5kV | Wilbarger | WEST | 2019-09-30 | WIN | WT | 184 |  | 2014-09-15 | 2014-12-10 | 2014-12-05 | 2018-10-31 | 2015-03-31 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31
16INR0074 | Chocolate Bayou W | SS Completed, FIS Completed, No IA | Engie | tap 138kV 42109 Hudson - 42960 Mustang | Brazoria | COASTAL | 2020-12-01 | WIN | WT | 149.5 |  | 2014-12-08 | 2015-03-02 | 2014-12-04 | 2019-02-26 |  | No | Not Required | Not Required | Not Required
16INR0076 | Hudson (Ineos/Brazoria) | SS Completed, FIS Completed, IA | Ineos | 42100 Hudson 138kV | Brazoria | COASTAL | 2019-05-01 | GAS | GT | 96 |  | 2015-01-12 | 2015-03-19 | 2015-06-24 | 2017-08-24 | 2017-12-05 | Yes | 2017-02-10 | 2017-02-10 | 2018-01-10 | 2018-10-09 | 2019-02-12 | 2018-08-01 |  |  | 2019-02-12
16INR0081 | Mesteno Windpower | SS Completed, FIS Completed, IA | Mesteno Windpower, LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2020-03-01 | WIN | WT | 201.6 |  | 2014-12-30 | 2015-03-09 | 2014-12-30 | 2018-01-29 | 2018-04-25 | Yes | Not Required | Not Required | Not Required | 2018-04-25 | 2019-03-28 | 2019-04-01
16INR0085 | Priddy Wind | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1444 Brown – 3422 Killeen | Mills | NORTH | 2020-12-31 | WIN | WT | 300 |  | 2015-01-14 | 2015-02-10 | 2015-03-06 |  |  | No | Not Required | Not Required | Not Required
16INR0086 | Cactus Flats Wind | SS Completed, FIS Completed, IA | Southern Power Company | tap 138kV 6480 SAPS - 6365 Yellow Jacket | Concho | WEST | 2019-04-29 | WIN | WT | 148.4 | COD | 2015-02-02 | 2015-03-27 | 2015-02-02 | 2017-10-20 | 2017-03-15 | Yes | Not Required | Not Required | Not Required | Date Not Available | 2018-09-05 | 2017-11-01 |  |  | 2018-05-24 | 2018-06-11
16INR0097 | Morada Del Sol Solar | SS Completed, FIS Started, No IA | First Solar | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Upton | WEST | 2020-03-31 | SOL | PV | 245 |  | 2015-03-31 | 2015-06-23 | 2015-03-31 |  |  | No | Not Required | Not Required | Not Required
16INR0099 | Hecate Solar | SS Completed, FIS Started, No IA | Hecate Energy | tap 69kV 6653 Barilla - 6665 Alpine REA | Brewster | WEST | 2020-12-31 | SOL | PV | 33 |  | 2015-03-27 | 2015-05-14 | 2015-03-27 |  |  | No | Not Required | Not Required | Not Required
16INR0101 | Chatee Solar | SS Completed, FIS Started, No IA | Hecate Energy | 6641 Sun Valley 69kV | Pecos | WEST | 2020-12-31 | SOL | PV | 57 |  | 2015-04-07 | 2015-05-14 | 2015-04-07 |  |  | No | Not Required | Not Required | Not Required
16INR0102 | Owego Solar | SS Completed, FIS Started, No IA | Hecate Energy | 6601 Rio Pecos 138kV | Pecos | WEST | 2020-12-31 | SOL | PV | 74 |  | 2015-04-07 | 2015-05-14 | 2015-04-07 |  |  | No | Not Required | Not Required | Not Required
16INR0104 | Big Sampson Wind | SS Completed, FIS Completed, No IA | Infinity Renewables | 76005 Schneeman Draw 345kV | Crockett | WEST | 2019-12-01 | WIN | WT | 400 |  | 2015-05-11 | 2015-06-17 | 2015-05-11 | 2018-12-11 |  | No | Not Required | Not Required | Not Required
16INR0106 | Whatley Solar | SS Completed, FIS Started, No IA | Invenergy | 1281 Amoco Midland tap 69kV | Andrews | WEST | 2020-12-31 | SOL | PV | 150 |  | 2015-05-05 | 2015-05-26 | 2015-09-22 |  |  | No | Not Required | Not Required | Not Required
16INR0111 | Las Lomas Wind | SS Completed, FIS Started, IA | Enerverse | 8957 Lopeno 138kV | Starr | SOUTH | 2019-12-31 | WIN | WT | 200 |  | 2015-05-18 | 2015-06-25 | 2015-05-18 |  | 2018-12-22 | Yes | Not Required | Not Required | Not Required | 2019-01-29
16INR0112 | Loma Pinta Wind | SS Completed, FIS Completed, IA | Enerverse | 5705 Fowlerton 138kV | La Salle | SOUTH | 2019-11-30 | WIN | WT | 200 |  | 2015-05-18 | 2015-07-02 | 2015-05-18 | 2017-03-24 | 2017-12-13 | No | Not Required | Not Required | Not Required
16INR0114 | Upton Solar | SS Completed, FIS Started, IA | Clearway Energy | 76020 SONNE 138-kV | Upton | WEST | 2020-05-31 | SOL | PV | 104.56 |  | 2015-05-27 | 2015-07-02 | 2015-06-08 |  | 2015-12-04 | Yes | Not Required | Not Required | Not Required | 2018-12-14
16INR0117 | Tecovas 1 W | SS Completed, FIS Started, No IA | Engie | 79503 Tule Canyon 345kV | Briscoe | PANHANDLE | 2020-06-01 | WIN | WT | 200 |  | 2015-06-23 | 2015-07-06 | 2015-10-19 |  |  | No | Not Required | Not Required | Not Required
16INR0119 | Wake Solar | SS Completed, FIS Started, No IA | Invenergy | 59904 Cottonwood 345kV | Crosby | PANHANDLE | 2021-12-31 | SOL | PV | 150 |  | 2015-07-20 | 2015-07-27 | 2015-10-05 |  |  | No | Not Required | Not Required | Not Required
17INR0005 | Cabezon Wind | SS Completed, FIS Completed, IA | Longroad Energy | 80355 Del Sol 345kV | Starr | SOUTH | 2019-05-31 | WIN | WT | 237.6 | COD | 2013-09-17 | 2013-10-25 | 2013-09-06 | 2017-12-22 | 2017-08-03 | Yes | Not Required | Not Required | Not Required | 2017-12-08 | 2018-09-12 | 2018-02-01 |  |  | 2019-02-18 | 2019-03-14
17INR0010 | FGE Texas 2 Gas | SS Completed, FIS Started, IA | FGE Power | Tap 345kV 1030 Morgan – 1058 Longshore | Mitchell | WEST | 2022-05-25 | GAS | CC | 742.9 |  | 2014-02-11 | 2014-03-26 | 2014-02-19 |  | 2015-06-02 | No | 2016-12-16 | 2016-12-12
17INR0020a | RE Maplewood 2a Solar | SS Completed, FIS Started, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2020-05-31 | SOL | PV | 222 |  | 2014-10-17 | 2014-12-01 | 2014-10-22 |  | 2016-02-03 | Yes | Not Required | Not Required | Not Required | 2018-03-19
17INR0020b | RE Maplewood 2b Solar | SS Completed, FIS Started, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2020-12-31 | SOL | PV | 28 |  | 2014-10-17 | 2014-12-01 | 2014-10-22 |  | 2016-02-03 | Yes | Not Required | Not Required | Not Required | 2018-03-19
17INR0020c | RE Maplewood 2c Solar | SS Completed, FIS Started, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2021-06-01 | SOL | PV | 250 | COD | 2014-10-17 | 2014-12-01 | 2014-10-22 |  | 2016-02-03 | Yes | Not Required | Not Required | Not Required | 2018-03-19
17INR0022 | MIRAGE | SS Completed, FIS Completed, IA | Net Power | 111161 Mirage 13.8kV | Harris | HOUSTON | 2019-02-18 | GAS | GT | 11 |  | 2015-02-17 | 2015-05-01 | 2015-05-20 | 2016-09-13 | 2016-08-31 | Yes | 2015-05-08 | Not Required | 2017-10-12 | 2016-10-11 | 2018-09-28 |  |  |  | 2017-02-06
17INR0025 | Reloj Del Sol Wind | SS Completed, FIS Started, IA | EDP Renewables | 80220 Cenizo 345kV | Zapata | SOUTH | 2020-10-31 | WIN | WT | 202 |  | 2015-03-24 | 2015-05-05 | 2015-09-14 |  | 2018-12-21 | Yes | Not Required | Not Required | Not Required | 2019-03-04
17INR0027b | Coyote Wind | SS Completed, FIS Started, IA | Coyote Wind | 11305 Dermott 345kV | Scurry | WEST | 2020-06-03 | WIN | WT | 242.5 |  | 2015-04-22 | 2015-05-22 | 2015-06-11 |  | 2016-08-09 | Yes | Not Required | Not Required | Not Required | 2016-08-09
17INR0031 | Espiritu Wind | SS Completed, FIS Started, No IA | Acciona | Kelvin Station | Cameron | COASTAL | 2020-12-21 | WIN | WT | 148.5 |  | 2015-05-19 | 2015-06-22 | 2015-10-26 |  |  | No | Not Required | Not Required | Not Required
17INR0033 | Tecovas 2 W | SS Completed, FIS Started, No IA | Engie | 79503 Tule Canyon 345kV | Briscoe | PANHANDLE | 2020-06-01 | WIN | WT | 200 |  | 2015-06-23 | 2015-07-06 | 2015-10-19 |  |  | No | Not Required | Not Required | Not Required
17INR0035 | Las Majadas Wind | SS Completed, FIS Started, IA | EDF Renewable Energy | 8318 Rio Hondo 345kV plus 12.5mi gentie | Willacy | COASTAL | 2020-10-01 | WIN | WT | 272.8 |  | 2015-10-30 | 2015-12-14 | 2015-12-09 |  | 2018-04-13 | Yes | Not Required | Not Required | Not Required
17INR0036 | Grandview 4 Phase A Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 79000 Gray - 79006 Allen | Carson | PANHANDLE | 2020-05-29 | WIN | WT | 200.5 |  | 2015-11-25 | 2016-01-11 | 2016-01-21 |  |  | No | Not Required | Not Required | Not Required
17INR0037 | Palmas Altas Wind | SS Completed, FIS Completed, IA | Acciona | 5760 PALMAS 138 kV | Cameron | COASTAL | 2020-01-10 | WIN | WT | 144.9 |  | 2016-03-24 | 2016-05-06 | 2016-07-20 | 2018-08-07 | 2017-11-30 | Yes | Not Required | Not Required | Not Required | 2018-10-04 | 2018-10-04 | 2018-10-04
17INR0043 | Vaquero 1 Wind | SS Completed, FIS Started, No IA | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Zapata | SOUTH | 2020-12-31 | WIN | WT | 400 |  | 2016-04-01 | 2016-05-10 | 2016-04-01 |  |  | No | Not Required | Not Required | Not Required
17INR0045 | VictPort | SS Completed, FIS Completed, IA | Castleman Power | 8143 Dupont 138kV | Calhoun | COASTAL | 2019-05-03 | GAS | GT | 100 |  | 2016-04-20 | 2016-06-10 | 2017-01-10 | 2018-06-15 | 2018-03-06 | Yes | 2017-06-09 | Not Required | 2018-05-01 | 2017-03-06 | 2018-09-19 | Date Not Available
17INR0052 | Horse13 CallD repower | SS Completed, FIS Completed, No IA | Nextera | 6216 Bluff Creek 138kV | Taylor | WEST | 2018-11-01 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2018-04-10 |  | No | Not Required | Not Required | Not Required
17INR0053 | HHGT repower Horse13+CallD | SS Completed, FIS Completed, No IA | Nextera | 7046 Kendal 345kV | Taylor | WEST | 2018-11-01 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2017-07-06 |  | No | Not Required | Not Required | Not Required
17INR0054 | Capricorn I & III repower | SS Completed, FIS Completed, No IA | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WEST | 2018-11-01 | WIN | WT | 32 |  | 2017-03-09 | 2017-04-24 | 2017-03-09 | 2018-02-26 |  | No | Not Required | Not Required | Not Required
17INR0056 | Callahan repower | SS Completed, FIS Completed, No IA | Nextera |  | Taylor | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-07-19 | 2017-09-15 | 2017-07-19 | 2017-08-14 |  | No | Not Required | Not Required | Not Required
17INR0057 | Red Canyon repower | SS Completed, FIS Completed, No IA | Nextera | 729 ScurrySw 138kV | Garza | WEST | 2019-05-24 | WIN | WT | 0 | COD | 2017-07-21 | 2017-09-15 | 2017-07-21 | 2017-10-13 |  | No | Not Required | Not Required | Not Required
17INR0058 | Horse Hollow II repower | SS Completed, FIS Completed, No IA | Nextera | Bluff Creek 138kV | Taylor | WEST | 2019-03-01 | WIN | WT | 0 |  | 2017-07-28 | 2017-09-15 | 2017-07-28 | 2017-12-12 |  | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31
17INR0060 | Horse Hollow IV repower | SS Completed, FIS Completed, No IA | Nextera |  | Taylor | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-07-28 | 2017-09-15 | 2017-07-28 | 2017-12-12 |  | No | Not Required | Not Required | Not Required
17INR0061 | Capricorn IV repower | SS Completed, FIS Completed, No IA | Nextera |  | Sterling | WEST | 2018-11-01 | WIN | WT | 9 |  | 2017-08-23 | 2017-09-15 | 2017-08-23 | 2018-02-06 |  | No | Not Required | Not Required | Not Required
17INR0063 | Capricorn I repower | SS Completed, FIS Completed, No IA | Nextera |  | Sterling | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-08-16 | 2017-09-15 | 2017-08-16 | 2017-11-08 |  | No | Not Required | Not Required | Not Required
17INR0064 | Capricorn II repower | SS Completed, FIS Completed, No IA | Nextera |  | Sterling | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-08-16 | 2017-09-15 | 2017-08-16 | 2017-12-12 |  | No | Not Required | Not Required | Not Required
17INR0065 | Capricorn III repower | SS Completed, FIS Completed, No IA | Nextera |  | Sterling | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-08-16 | 2017-09-15 | 2017-08-16 | 2017-11-08 |  | No | Not Required | Not Required | Not Required
17INR0067 | Sweetwater 1 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2019-03-01 | WIN | WT | 0 |  | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-11 | Date Not Available | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31
17INR0068 | Sweetwater 2 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2019-03-01 | WIN | WT | 7.3 |  | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-11-10 | 2017-11-17 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2017-12-20
17INR0069 | Trent repower | SS Completed, FIS Completed, IA | Invenergy | 1338 Eskota 138kV | Nolan | WEST | 2019-03-01 | WIN | WT | 6.4 |  | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-03-01 | 2018-10-19 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 11:50 | 2018-10-31
17INR0070 | Desert Sky repower | SS Completed, FIS Completed, IA | Invenergy | two LCRA 138kV | Pecos | WEST | 2019-03-01 | WIN | WT | 7.2 |  | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-02-06 | 2018-10-18 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31
17INR0101 | Horse 1 repower | SS Completed, FIS Completed, No IA | Nextera |  | Taylor | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 |  | No | Not Required | Not Required | Not Required
17INR0103 | Horse 3 repower | SS Completed, FIS Completed, No IA | Nextera |  | Taylor | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 |  | No | Not Required | Not Required | Not Required
17INR0104 | Capricorn 4 repower | SS Completed, FIS Completed, IA | Nextera |  | Coke | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2018-05-01 | No | Not Required | Not Required | Not Required
18INR0009 | Eagle Pines Gas | SS Completed, FIS Started, No IA | FGE Power | tap 345kV 3109 Stryker - 3123 Trinidad | Cherokee | NORTH | 2021-02-15 | GAS | CC | 1173.5 |  | 2015-03-30 | 2015-06-23 | 2015-04-29 |  |  | No | 2017-02-14 | 2015-11-04
18INR0014 | Karankawa Wind | SS Completed, FIS Completed, IA | Avangrid | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | COASTAL | 2019-12-31 | WIN | WT | 206.64 |  | 2015-10-28 | 2015-11-11 | 2016-05-04 | 2018-08-03 | 2017-11-30 | Yes | Not Required | Not Required | Not Required | 2017-11-30 | 2019-01-18 | 2019-01-22
18INR0016 | RTS 2 Wind | SS Completed, FIS Completed, IA | RES Americas | 76006 Bow Wood 345kV | McCulloch | SOUTH | 2020-06-30 | WIN | WT | 179.91 |  | 2015-11-02 | 2015-12-07 | 2015-12-31 | 2019-01-16 | 2017-11-21 | Yes | Not Required | Not Required | Not Required
18INR0018 | Peyton Creek Wind | SS Completed, FIS Completed, IA | Eon | 42400 Refuge 345kV | Matagorda | COASTAL | 2019-12-01 | WIN | WT | 151.2 |  | 2015-11-25 | 2015-12-22 | 2016-06-22 | 2017-07-24 | 2018-03-19 | Yes | Not Required | Not Required | Not Required | 2018-03-19 | 2018-09-19 | 2019-04-24
18INR0023 | Darmstadt | SS Completed, FIS Completed, IA | RES Americas | 60708 Orsted 345kV - Big Hill | Schleicher | WEST | 2019-12-31 | WIN | WT | 200.9 |  | 2016-06-07 | 2016-09-04 | 2016-10-07 | 2018-07-23 | 2018-05-11 | No | Not Required | Not Required | Not Required
18INR0027 | Ponwar Solar Farm | SS Completed, FIS Started, No IA | 8minutenergy | tap 138kV 76032 N McCamey - 60361 Santa Rita | Upton | WEST | 2021-06-01 | SOL | PV | 180 |  | 2016-04-06 | 2016-05-27 | 2016-10-27 |  |  | No | Not Required | Not Required | Not Required
18INR0029 | Armstrong Wind | SS Completed, FIS Completed, IA | Big Sky Energy | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | PANHANDLE | 2020-03-31 | WIN | WT | 253 |  | 2016-05-10 | 2016-05-24 | 2016-07-25 | 2018-01-25 | 2018-08-31 | No | Not Required | Not Required | Not Required
18INR0030 | Canyon Wind | SS Completed, FIS Started, IA | TriGlobal | 11319 ScurryCounty 138kV | Scurry | WEST | 2020-06-30 | WIN | WT | 360 |  | 2016-05-09 | 2016-07-22 | 2017-03-02 |  | 2018-09-20 | No | Not Required | Not Required | Not Required
18INR0031 | Maryneal Windpower | SS Completed, FIS Started, No IA | Maryneal Windpower, LLC | 71050 Bitter Creek 345kV | Nolan | WEST | 2020-11-30 | WIN | WT | 182.4 |  | 2016-05-26 | 2016-07-21 | 2016-07-22 |  |  | No | Not Required | Not Required | Not Required
18INR0033 | Oveja Wind | SS Completed, FIS Completed, IA | Invenergy | 76005 Schneeman Draw 345kV | Irion | WEST | 2019-06-30 | WIN | WT | 300 |  | 2016-07-12 | 2016-09-07 | 2016-10-21 | 2018-07-11 | 2018-07-24 | Yes | Not Required | Not Required | Not Required | 2018-07-30 | 2018-09-28 | 2018-07-30 |  |  | 2019-03-28 | 2019-04-05
18INR0034 | Blanco Canyon Wind | SS Completed, FIS Started, No IA | Invenergy | 59904 Cottonwood 345kV | Crosby | PANHANDLE | 2021-12-31 | WIN | WT | 250.7 |  | 2016-07-21 | 2016-09-14 | 2017-03-22 |  |  | No | Not Required | Not Required | Not Required
18INR0035 | CityVict | SS Completed, FIS Completed, IA | Castleman Power | 8172 Victoria 138kV | Refugio | COASTAL | 2019-11-01 | GAS | GT | 100 |  | 2016-08-15 | 2016-09-27 | 2017-03-27 | 2018-07-25 | 2018-03-06 | Yes | 2017-06-15 | Not Required | 2018-04-26 | 2018-03-06 | 2018-09-19 | Date Not Available
18INR0038 | Barrow Ranch | SS Completed, FIS Completed, IA | Engie | 1134 Littman 138kV | Andrews | WEST | 2019-12-01 | WIN | WT | 160 |  | 2016-10-02 | 2016-12-12 | 2017-06-19 | 2018-05-09 | 2018-06-26 | Yes | Not Required | Not Required | Not Required | 2018-09-04
18INR0039 | Fowler Ranch | SS Completed, FIS Completed, IA | CED Crane Solar, LLC | tap 138kV 60014 Spudder - 76615 Crane | Crane | WEST | 2020-04-30 | SOL | PV | 150 |  | 2016-10-07 | 2016-11-08 | 2016-12-23 | 2019-01-30 | 2018-10-23 | No | Not Required | Not Required | Not Required
18INR0040 | Soda Lake Solar 1 | SS Completed, FIS Started, IA | Arrington Solar | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | WEST | 2020-12-31 | SOL | PV | 200 | COD | 2016-10-07 | 2016-11-08 | 2017-02-10 |  | 2018-08-20 | No | Not Required | Not Required | Not Required
18INR0042 | Kaiser Creek Wind | SS Completed, FIS Started, No IA | Calpine | Tap 138kV 6275 Abilene East – 6670 Putnam | Callahan | WEST | 2020-10-01 | WIN | WT | 100 |  | 2016-10-12 | 2016-12-01 | 2016-10-07 |  |  | No | Not Required | Not Required | Not Required
18INR0043 | Edmondson Ranch Wind | SS Completed, FIS Completed, IA | Wind Tex | 59903 Bearkat 345kV | Glasscock | WEST | 2020-06-26 | WIN | WT | 292.5 |  | 2016-10-26 | 2016-12-22 | 2017-02-01 | 2018-01-30 | 2017-10-04 | Yes | Not Required | Not Required | Not Required | Date Not Available | 2018-09-05
18INR0045 | Misae Solar | SS Completed, FIS Completed, IA | CIP | 60501 Tesla 345kV | Childress | PANHANDLE | 2019-11-29 | SOL | PV | 240.8 |  | 2016-10-20 | 2017-01-06 | 2016-10-20 | 2019-01-28 | 2018-07-18 | Yes | Not Required | Not Required | Not Required | 2019-01-28 | 2019-01-30 | 2019-01-31
18INR0049 | Santa Rita Solar | SS Completed, FIS Started, No IA | Invenergy | 76005 Schneeman Draw 345kV | Crockett | WEST | 2022-12-31 | SOL | PV | 400 |  | 2016-11-09 | 2016-12-19 | 2017-05-30 |  |  | No | Not Required | Not Required | Not Required
18INR0050 | Mustang Creek Solar | SS Completed, FIS Completed, IA | Sunchase Power | tap 138kV 5523 ETP - 78104 Ricebird new sub Galow | Jackson | SOUTH | 2020-04-15 | SOL | PV | 150 |  | 2016-11-16 | 2016-12-20 | 2017-03-22 | 2018-10-03 | 2019-01-04 | No | Not Required | Not Required | Not Required
18INR0053 | Fort Bend Solar | SS Completed, FIS Started, No IA | Fort Bend Solar LLC | tap 138kV 44541 Orchard - 44190 E Bernard | Fort Bend | HOUSTON | 2020-03-01 | SOL | PV | 240 |  | 2016-12-19 | 2017-02-15 | 2017-09-08 |  |  | No | Not Required | Not Required | Not Required
18INR0055 | Long Draw Solar | SS Completed, FIS Started, IA | ENGIE | 59900 Long Draw 345kV | Borden | WEST | 2020-06-30 | SOL | PV | 225 |  | 2016-12-15 | 2017-02-02 | 2017-02-28 |  | 2018-08-16 | Yes | Not Required | Not Required | Not Required | 2019-02-28
18INR0056 | Hallmark Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 69kV 1824 Neyland - 1826 Cadmil | Hunt | NORTH | 2020-12-15 | SOL | PV | 43 |  | 2016-12-15 | 2017-02-16 | 2017-02-21 |  |  | No | Not Required | Not Required | Not Required
18INR0058 | Texana Solar | SS Completed, FIS Started, No IA | Sunchase Power | tap 138kV 8102 El Campo - 8117 Ganado | Wharton | SOUTH | 2021-03-01 | SOL | PV | 150 |  | 2016-12-23 | 2017-02-14 | 2017-03-22 |  |  | No | Not Required | Not Required | Not Required
18INR0059 | East Raymond Wind | SS Completed, FIS Started, IA | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2020-09-15 | WIN | WT | 201.6 |  | 2017-01-27 | 2017-03-09 | 2017-02-10 |  | 2018-09-18 | Yes | Not Required | Not Required | Not Required | 2018-10-17
18INR0060 | Brightside Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 69kV 8198 Beeville - 8400 Three River | Bee | SOUTH | 2020-12-15 | SOL | PV | 50 |  | 2017-02-17 | 2017-03-20 | 2017-02-21 |  |  | No | Not Required | Not Required | Not Required
18INR0062 | Wagyu Solar | SS Completed, FIS Completed, No IA | Cypress Creek Renewables | tap 138kV 43380 West Columbia - 44010 WA Parish | Brazoria | COASTAL | 2020-06-01 | SOL | PV | 121.9 |  | 2017-02-22 | 2017-04-03 | 2017-02-22 | 2018-11-01 |  | No | Not Required | Not Required | Not Required
18INR0064 | Silver Star repower | SS Completed, FIS Completed, IA | Silver Star I Power Partners, LLC | 1642 Flat Creek 138kV | Eastland | NORTH | 2019-11-01 | WIN | WT | -7.2 |  | 2017-04-05 | 2017-05-08 | 2017-07-06 | 2018-04-26 | 2018-10-16 | No | Not Required | Not Required | Not Required
18INR0065 | Goodranch Solar | SS Completed, FIS Started, No IA | EDF Renewable Energy | 79600 Vealmoor 138kV OR 79640 Vealmoor 345kV | Borden | WEST | 2020-12-01 | SOL | PV | 200 |  | 2017-06-23 | 2017-08-04 | 2018-04-02 |  |  | No | Not Required | Not Required | Not Required
18INR0067 | Gopher Creek Wind | SS Completed, FIS Completed, IA | Terna Energy | 11306 Dermott 138kV | Borden | WEST | 2019-07-31 | WIN | WT | 158 |  | 2017-07-11 | 2017-08-28 | 2017-07-26 | 2018-01-26 | 2018-01-26 | Yes | Not Required | Not Required | Not Required | Date Not Available | 2018-09-06 | 2018-11-01
18INR0068 | Loraine Windpark Phase III | SS Completed, FIS Completed, IA | Third Planet Wind Power | 181153 Lonewolf 345kV | Mitchell | WEST | 2020-05-01 | WIN | WT | 100 |  | 2017-08-14 | 2017-10-05 | 2017-10-20 | 2018-04-11 | 2018-04-10 | Yes | Not Required | Not Required | Not Required | 2018-04-12 | 2018-09-12 | 2018-05-01
18INR0069 | Indian Mesa repower | SS Completed, FIS Completed, IA | Nextera | 76019 Indian NWP 138kV | Pecos | WEST | 2019-01-01 | WIN | WT | 0 |  | 2018-05-22 | Date Not Available | 2018-05-22 | 2018-10-03 | 2018-12-04 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2018-11-02
18INR0070 | Blue Summit II | SS Completed, FIS Completed, IA | Nextera | 61001 Jim Treece 345kV | Wilbarger | WEST | 2019-04-15 | WIN | WT | 102 |  | 2017-11-02 | 2017-12-21 | 2017-11-02 | 2018-05-24 | 2018-11-09 | Yes | Not Required | Not Required | Not Required | 2018-05-07 | 2018-09-12 | 2018-08-01 |  |  | 2018-12-18 | 2019-01-10
18INR0072 | Blue Summit repower | SS Completed, FIS Started, No IA | Nextera | 61001 Jim Treece 345kV | Wilbarger | WEST | 2019-06-03 | WIN | WT | 9.9 |  | 2018-01-04 | 2018-01-04 | 2018-01-04 |  |  | No | Not Required | Not Required | Not Required
18INR0073 | Sweetwater 1 repower | SS Completed, FIS Completed, No IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2019-03-01 | WIN | WT | 3 |  | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-12-27 |  | No | Not Required | Not Required | Not Required
18INR0075 | Gulf Wind 1 repower | SS Completed, FIS Started, No IA | Pattern Energy | 80071 Zorillo 345kV | Kenedy | COASTAL | 2020-06-01 | WIN | WT | 0 |  | 2018-03-05 | 2018-03-05 | 2018-03-05 |  |  | No | Not Required | Not Required | Not Required
18INR0076 | Wolf Hollow 2 repower | SS Completed, FIS Started, No IA | Exelon | 1877 Mitchell Bend 345kV | Hood | NORTH | 2019-05-15 | GAS | CC | 44 | COD | 2018-04-24 | 2018-04-24 | 2018-04-24 |  |  | No | Not Required | Not Required |  | 2018-10-31 | 2018-10-31 | 2018-10-31
18INR0077 | Colorado Bend 2 repower | SS Completed, FIS Started, No IA | Exelon | 44040 Bailey 345kV | Wharton | SOUTH | 2019-06-01 | GAS | CC | 45 | COD | 2018-04-24 | 2018-04-24 | 2018-04-24 |  |  | No | Not Required | Not Required |  | 2018-10-31 | 2018-10-31 12:40 | 2018-10-31
18INR0078 | Bobcat Bluff repower | SS Completed, FIS Completed, IA | EDF Renewable Energy | 1475 Windthorst 138kV | Archer | WEST | 2019-07-08 | WIN | WT | 12 |  | 2018-05-15 | 2018-07-19 | 2018-05-15 | 2018-10-24 | 2018-12-18 | No | Not Required | Not Required | Not Required | [6 empty] | 2018-12-20
18INR0079 | Woodward I repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2019-01-01 | WIN | WT | 0 |  | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2019-01-09 | 2018-12-12 | No | Not Required | Not Required | Not Required | [6 empty] | 2018-12-18
18INR0080 | Woodward 2 repower | SS Completed, FIS Completed, No IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2018-12-31 | WIN | WT | 0 |  | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-11-27 |  | No | Not Required | Not Required | Not Required | [6 empty] | 2018-12-19
19INR0001 | Texas Solar Nova | SS Completed, FIS Started, No IA | Clearway Energy | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2021-12-01 | SOL | PV | 252.2 | MW Size | 2015-11-17 | 2015-12-30 | 2016-07-06 |  |  | No | Not Required | Not Required | Not Required
19INR0002 | King Mountain Solar | SS Completed, FIS Started, No IA | Nextera | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | WEST | 2021-05-01 | SOL | PV | 350 |  | 2016-05-24 | 2016-06-06 | 2016-05-24 |  |  | No | Not Required | Not Required | Not Required
19INR0006 | Bluebonnet Solar | SS Completed, FIS Started, No IA | One Energy Renewables | tap 138kV 6680 Alamito - 60385 Solstice | Brewster | WEST | 2020-12-31 | SOL | PV | 60.7 |  | 2016-07-18 | 2016-10-07 | 2017-04-05 |  |  | No | Not Required | Not Required | Not Required
19INR0007 | Charbray Solar | SS Completed, FIS Started, No IA | 8minutenergy | 1032 Morgan Creek 138kV | Mitchell | WEST | 2020-10-01 | SOL | PV | 200 |  | 2016-07-26 | 2016-10-07 | 2017-04-07 |  |  | No | Not Required | Not Required | Not Required
19INR0009 | Holstein Solar | SS Completed, FIS Started, IA | 8minutenergy | 11406 Central Bluff 345kV | Nolan | WEST | 2020-04-01 | SOL | PV | 204 | SFS/NtP | 2016-07-26 | 2016-09-13 | 2017-01-31 |  | 2018-09-15 | Yes | Not Required | Not Required | Not Required
19INR0014 | Formosa Increase | SS Completed, FIS Completed, IA | Formosa Plastics |  | Calhoun | COASTAL | 2019-12-31 | GAS | CC | 240 | SFS/NtP | 2016-09-12 | 2016-11-14 | 2017-06-08 | 2019-02-20 | 2019-04-30 | Yes
19INR0017 | Tri-County Solar | SS Completed, FIS Started, No IA | First Solar | tap 138kV 1027 Odessa - 1107 Monahans2T | Crane | WEST | 2020-12-31 | SOL | PV | 177.75 |  | 2016-10-10 | 2016-11-29 | 2017-02-22 |  |  | No | Not Required | Not Required | Not Required
19INR0019 | Foard City Wind | SS Completed, FIS Completed, IA | Innergex | 60500 Edith Clarke 345kV | Foard | WEST | 2019-09-24 | WIN | WT | 350 |  | 2016-10-19 | 2016-11-28 | 2017-01-11 | 2018-08-01 | 2018-11-06 | Yes | Not Required | Not Required | Not Required | 2018-06-22 | 2018-11-05 | 2018-10-26
19INR0020 | SP-Pecos Bend Solar A | SS Completed, FIS Started, No IA | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | WEST | 2021-02-01 | SOL | PV | 200 | MW Size | 2016-10-26 | 2016-12-07 | 2016-10-31 |  |  | No | Not Required | Not Required | Not Required
19INR0020b | SP-Pecos Bend Solar B | SS Completed, FIS Started, No IA | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | WEST | 2021-02-01 | SOL | PV | 180 |  | 2016-10-26 | 2016-12-07 | 2016-10-31 |  |  | No | Not Required | Not Required | Not Required
19INR0022 | Monte Alto I | SS Completed, FIS Started, No IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2020-10-12 | WIN | WT | 223.8 |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  |  | No | Not Required | Not Required | Not Required
19INR0023 | Monte Alto 2 Wind | SS Completed, FIS Started, No IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2020-10-12 | WIN | WT | 236.9 |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  |  | No | Not Required | Not Required | Not Required
19INR0026 | Holstein 2 Solar | SS Completed, FIS Started, No IA | 8minutenergy | 11406 Central Bluff 345kV | Nolan | WEST | 2021-06-01 | SOL | PV | 100 | COD | 2016-12-21 | 2017-02-02 | 2017-02-13 |  |  | No | Not Required | Not Required | Not Required
19INR0028 | Normande Solar Farm | SS Completed, FIS Started, No IA | 8minutenergy | 59900 Long Draw 345kV | Borden | WEST | 2021-06-01 | SOL | PV | 360 |  | 2017-01-30 | 2017-02-22 | 2017-08-24 |  |  | No | Not Required | Not Required | Not Required
19INR0029 | Phoebe Solar | SS Completed, FIS Completed, IA | Longroad Energy | 11260 Dune Switch | Winkler | WEST | 2019-09-01 | SOL | PV | 250 |  | 2017-01-26 | 2017-02-15 | 2017-03-07 | 2018-10-23 | 2018-03-05 | Yes | Not Required | Not Required | Not Required | 2018-03-05 | 2018-09-14 | 2018-10-31 |  |  | 2019-04-12
19INR0030 | San Bernard Solar | SS Completed, FIS Started, No IA | Sunchase Power | 43012 NEWGLF60T3_8 to 43340 TXGLF__POI_8 60 138kV | Wharton | SOUTH | 2020-06-01 | SOL | PV | 100 |  | 2017-01-26 | 2017-04-12 | 2017-03-22 |  |  | No | Not Required | Not Required | Not Required
19INR0031 | Bestla Solar | SS Completed, FIS Started, No IA | Longroad Energy | tap 138kV 1147 Cheyenne - 131853 Notrees | Winkler | WEST | 2020-07-01 | SOL | PV | 180 |  | 2017-01-30 | 2017-03-06 | 2017-03-23 |  |  | No | Not Required | Not Required | Not Required
19INR0033 | Murphy Lake Solar | SS Completed, FIS Completed, No IA | S Power | 6904 CombinRC 138kV | Kaufman | NORTH | 2020-12-15 | SOL | PV | 120 |  | 2017-02-06 | 2017-03-03 | 2017-08-10 | 2019-03-28 |  | No | Not Required | Not Required | Not Required
19INR0034 | Greasewood Solar | SS Completed, FIS Started, IA | Concho Bluff, LLC | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Pecos | WEST | 2020-09-30 | SOL | PV | 200 |  | 2017-02-22 | 2017-04-17 | 2017-10-10 |  | 2019-01-25 | No | Not Required | Not Required | Not Required
19INR0035 | Norton Solar | SS Completed, FIS Started, No IA | 8minutenergy | tap 138kV 6325 Chad to 6340 Balg, 10mi from Chad | Runnels | WEST | 2021-06-01 | SOL | PV | 125 |  | 2017-03-06 | 2017-04-20 | 2017-11-08 |  |  | No | Not Required | Not Required | Not Required
19INR0036 | Oxbow Solar | SS Completed, FIS Started, No IA | ENGIE Long Draw Solar 2 LLC | 59905 Faraday 345kV | Borden | WEST | 2020-12-15 | SOL | PV | 225 |  | 2017-02-28 | 2017-04-13 | 2017-10-10 |  |  | No | Not Required | Not Required | Not Required
19INR0038 | High Lonesome W | SS Completed, FIS Completed, IA | Enel | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | WEST | 2019-12-31 | WIN | WT | 449.5 | COD | 2017-03-10 | 2017-04-17 | 2017-07-18 | 2019-01-21 | 2018-04-17 | Yes | Not Required | Not Required | Not Required | 2019-02-15 | 2019-02-15 | 2019-02-15
19INR0041 | Myrtle Solar | SS Completed, FIS Completed, No IA | Sunchase Power | 42110 Angleton 138kv or line tap to Rosharon 44600 | Brazoria | COASTAL | 2020-05-01 | SOL | PV | 240 |  | 2017-03-15 | 2017-04-28 | 2017-05-09 | 2019-03-12 |  | No | Not Required | Not Required | Not Required
19INR0042 | Long Point Solar | SS Completed, FIS Completed, No IA | SunChase Power | tap 138kV 44010 WAP - 42981 Nash98 | Brazoria | COASTAL | 2020-09-01 | SOL | PV | 100 |  | 2017-03-15 | 2017-04-20 | 2017-11-13 | 2019-03-12 |  | No | Not Required | Not Required | Not Required
19INR0044 | Lily Solar | SS Completed, FIS Completed, IA | SunChase Power | tap 138kV 6904 CombinRC - 6908 ScuryRC | Kaufman | NORTH | 2020-06-01 | SOL | PV | 150 |  | 2017-03-28 | 2017-04-28 | 2017-05-30 | 2018-09-26 | 2019-03-29 | No | Not Required | Not Required | Not Required
19INR0045 | Rayos Del Sol | SS Completed, FIS Completed, IA | Rayos Del Sol Solar Project,LLC | tap 138kV 8554 Mesquite - 80103 Rangerville | Cameron | COASTAL | 2020-12-31 | SOL | PV | 150 |  | 2017-03-28 | 2017-05-22 | 2017-03-28 | 2018-06-13 | 2018-11-06 | Yes | Not Required | Not Required | Not Required | 2019-01-23
19INR0048 | Buenos Aires 1 Wind | SS Completed, FIS Started, No IA | Terra-Gen | tap 345kV 8905 N Edinb - 8455 Lon Hill | Hidalgo | SOUTH | 2020-12-31 | WIN | WT | 222.5 | MW Size | 2017-03-30 | 2017-05-03 | 2017-08-28 |  |  | No | Not Required | Not Required | Not Required
19INR0049 | Buenos Aires 2 W | SS Completed, FIS Started, No IA | Terra-Gen | tap 345kV 8905 N Edinb - 8455 Lon Hill | Hidalgo | SOUTH | 2021-10-01 | WIN | WT | 236.9 | MW Size COD | 2017-03-30 | 2017-05-03 | 2017-08-28 |  |  | No | Not Required | Not Required | Not Required
19INR0051 | Vera Wind | SS Completed, FIS Completed, IA | Longroad Energy | tap 345kV 60500 EdithC - 60700 Gauss | Knox | WEST | 2020-06-01 | WIN | WT | 242.8 |  | 2017-04-04 | 2017-05-18 | 2017-06-13 | 2019-03-06 | 2018-07-10 | Yes | Not Required | Not Required | Not Required
19INR0052 | TG East Wind | SS Completed, FIS Completed, IA | Northrenew | new 345kV sub Coulomb in 60500 EdithC - 60700 Gauss line | Knox | WEST | 2020-10-01 | WIN | WT | 275.6 |  | 2017-04-04 | 2017-05-18 | 2017-06-13 | 2019-03-13 | 2018-10-22 | Yes | Not Required | Not Required | Not Required
19INR0053 | Hidalgo II Wind | SS Completed, FIS Completed, IA | EDP Renewables | 161705 Mirasole 345kV | Hidalgo | SOUTH | 2019-11-15 | WIN | WT | 51 | COD SFS/NtP | 2017-04-05 | 2017-05-19 | 2017-07-12 | 2019-04-30 | 2019-04-25 | Yes | Not Required | Not Required | Not Required | 2019-04-30 | 2019-04-30 | 2019-04-30
19INR0054 | Monte Cristo 1 W | SS Completed, FIS Started, No IA | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | SOUTH | 2020-12-31 | WIN | WT | 236.9 |  | 2017-04-11 | 2017-05-03 | 2017-07-28 |  |  | No | Not Required | Not Required | Not Required
19INR0055 | Monte Cristo 2 Wind | SS Completed, FIS Started, No IA | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | SOUTH | 2021-12-31 | WIN | WT | 236.9 |  | 2017-04-11 | 2017-05-03 | 2017-07-28 |  |  | No | Not Required | Not Required | Not Required
19INR0056 | Chamon 2 | SS Completed, FIS Completed, No IA | Castleman Power | 40260 Chamon 138kV | Harris | HOUSTON | 2020-05-01 | GAS | GT | 100 |  | 2017-04-24 | 2017-06-09 | 2017-07-06 | 2018-05-07 |  | No
19INR0057 | Old Bloomington Road | SS Completed, FIS Completed, No IA | Castleman Power | 8143 Dupont 138kV | Victoria | SOUTH | 2020-05-01 | GAS | GT | 100 |  | 2017-04-18 | 2017-05-22 | 2017-11-29 | 2019-03-06 |  | No
19INR0070 | Trevino Solar | SS Completed, FIS Started, No IA | S Power | 78015 Rosita 138kV | Maverick | SOUTH | 2021-12-15 | SOL | PV | 216 | COD | 2017-04-19 | 2017-06-02 | 2017-11-30 |  |  | No | Not Required | Not Required | Not Required
19INR0073 | Shakes Solar | SS Completed, FIS Started, IA | Cypress Creek Renewables | 8283 Asherton 138kV | Zavala | SOUTH | 2020-05-01 | SOL | PV | 206 |  | 2017-05-03 | 2017-06-15 | 2017-05-03 |  | 2018-10-26 | Yes | Not Required | Not Required | Not Required | 2019-03-04
19INR0074 | Karankawa 2 Wind | SS Completed, FIS Completed, IA | Avangrid | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | COASTAL | 2019-12-31 | WIN | WT | 101 |  | 2017-05-12 | 2017-06-23 | 2017-10-04 | 2019-01-16 | 2018-03-02 | Yes | Not Required | Not Required | Not Required | 2018-03-02 | 2019-01-18 | 2019-01-22
19INR0075 | Horseshoe Bend Solar | SS Completed, FIS Started, No IA | Clenera | 1444 Brown 345kV | Coleman | WEST | 2020-12-31 | SOL | PV | 300 |  | 2017-06-23 | 2017-08-07 | 2018-02-09 |  |  | No | Not Required | Not Required | Not Required
19INR0080 | Whitehorse Wind | SS Completed, FIS Completed, IA | Clearway Energy | 68001 Clayton 345kV | Fisher | WEST | 2019-12-15 | WIN | WT | 418.9 |  | 2017-06-23 | 2017-08-07 | 2018-02-16 | 2019-01-22 | 2018-12-05 | Yes | Not Required | Not Required | Not Required | 2019-03-12 | 2019-04-02
19INR0081 | Anson Solar | SS Completed, FIS Started, No IA | Coronal Energy | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2020-12-31 | SOL | PV | 200 |  | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  | No | Not Required | Not Required | Not Required
19INR0083 | Oberon Solar | SS Completed, FIS Completed, IA | 174 Power Global | tap 138kV 1292 Ectorharp - 1013 Wolf | Ector | WEST | 2019-12-15 | SOL | PV | 180 |  | 2017-05-31 | 2017-07-13 | 2017-05-31 | 2018-05-18 | 2018-10-11 | Yes | Not Required | Not Required | Not Required | 2018-11-28 | 2019-01-22 | 2019-01-22
19INR0085 | Blue Jay Solar | SS Completed, FIS Started, No IA | Open Road Renewables | 4 Iola 138kV | Grimes | NORTH | 2020-12-15 | SOL | PV | 210 |  | 2017-05-30 | 2017-08-11 | 2018-02-15 |  |  | No | Not Required | Not Required | Not Required
19INR0088 | Aragorn Solar | SS Completed, FIS Started, IA | Intersect Power | tap 138kV 71097 LCulberson - 7387 Kunitz | Culberson | WEST | 2021-06-30 | SOL | PV | 186.3 |  | 2017-05-30 | 2017-07-21 | 2017-08-08 |  | 2018-05-31 | No | Not Required | Not Required | Not Required
19INR0091 | Phoenix Solar | SS Completed, FIS Started, No IA | Pattern Energy | 1808 Bonham 138kV | Fannin | NORTH | 2020-06-26 | SOL | PV | 82.3 | COD | 2017-06-23 | 2017-08-23 | 2017-08-09 |  |  | No | Not Required | Not Required | Not Required
19INR0092 | Prospero Solar | SS Completed, FIS Started, IA | Longroad Energy | 79650 Clearfork 345kV + 10 mile gen-tie | Andrews | WEST | 2020-06-01 | SOL | PV | 300 |  | 2017-06-23 | 2017-08-07 | 2017-07-11 |  | 2018-04-20 | No | Not Required | Not Required | Not Required
19INR0093 | Solemio | SS Completed, FIS Completed, No IA | Pattern Energy | tap 138kV 1698 Sulphur Springs - 1814 Sulspg | Hopkins | NORTH | 2020-05-31 | SOL | PV | 79.8 |  | 2017-06-23 | 2017-08-23 | 2017-08-09 | 2019-03-14 |  | No | Not Required | Not Required | Not Required
19INR0096 | Shamrock Wind | SS Completed, FIS Started, No IA | Eon | 76005 Schneeman Draw 345kV | Crockett | WEST | 2020-12-31 | WIN | WT | 201.6 |  | 2017-07-28 | 2017-09-13 | 2017-10-04 |  |  | No | Not Required | Not Required | Not Required
19INR0097 | Shamrock Wind II | SS Completed, FIS Started, No IA | Eon | 76005 Schneeman Draw 345kV | Crockett | WEST | 2020-12-15 | WIN | WT | 201.6 |  | 2017-07-28 | 2017-09-13 | 2017-10-02 |  |  | No | Not Required | Not Required | Not Required
19INR0098 | Pease River Wind | SS Completed, FIS Started, No IA | Eon | 60500 Edith Clarke 345kV | Hardeman | WEST | 2021-12-30 | WIN | WT | 301.4 |  | 2017-07-11 | 2017-08-28 | 2017-07-14 |  |  | No | Not Required | Not Required | Not Required
19INR0099a | Kontiki 1 Wind (ERIK) | SS Completed, FIS Started, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2020-06-30 | WIN | WT | 255.3 |  | 2017-06-22 | 2017-08-04 | 2017-09-28 |  | 2018-05-07 | Yes | Not Required | Not Required | Not Required | 2018-05-07
19INR0099b | Kontiki 2 Wind (ERNEST) | SS Completed, FIS Started, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2021-06-30 | WIN | WT | 255.3 |  | 2017-06-22 | 2017-08-04 | 2017-09-28 |  | 2018-05-07 | Yes | Not Required | Not Required | Not Required | 2018-05-07
19INR0100 | Prairie Hill Wind | SS Completed, FIS Completed, IA | Prairie Hill LLC | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | McLennan | NORTH | 2020-06-01 | WIN | WT | 300 |  | 2017-06-19 | 2017-08-11 | 2017-06-19 | 2018-05-18 | 2018-09-17 | Yes | Not Required | Not Required | Not Required
19INR0101 | Tehuacana Wind | SS Completed, FIS Started, No IA | Infinity Renewables | 46020 Limestone 345kV + 34mi gentie | Limestone | NORTH | 2021-10-01 | WIN | WT | 600 | COD | 2017-06-19 | 2017-08-11 | 2017-06-19 |  |  | No | Not Required | Not Required | Not Required
19INR0102 | Queen Solar | SS Completed, FIS Started, IA | Roadrunner Solar Project, LLC | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | WEST | 2019-12-31 | SOL | PV | 400 | COD SFS/NtP | 2017-07-11 | 2017-08-28 | 2018-02-26 |  | 2018-09-26 | Yes | Not Required | Not Required | Not Required | 2019-04-01 | 2019-04-30
19INR0103 | Rodeo Solar | SS Completed, FIS Started, No IA | Core Solar | tap 138kV 1134 Littman - 1135 Gasland | Andrews | WEST | 2020-04-30 | SOL | PV | 205 |  | 2017-06-29 | 2017-08-04 | 2018-02-19 |  |  | No | Not Required | Not Required | Not Required
19INR0110 | Angelina Solar | SS Completed, FIS Started, No IA | EDP Renewables | 3349 TMPLinla 138kV | Angelina | NORTH | 2021-10-31 | SOL | PV | 150 |  | 2017-07-26 | 2017-09-15 | 2018-03-15 |  |  | No | Not Required | Not Required | Not Required
19INR0111 | Tom Green Solar | SS Completed, FIS Started, No IA | EDP Renewables | tap 138kV 6480 SAPS - 60423 Treadwell | Tom Green | WEST | 2021-10-31 | SOL | PV | 150 |  | 2017-07-26 | 2017-09-13 | 2018-03-15 |  |  | No | Not Required | Not Required | Not Required
19INR0112 | Cranel Wind | SS Completed, FIS Completed, IA | Eon | tap 345kV 8164 Coleto - 8455 Lon Hill | Refugio | COASTAL | 2019-12-31 | WIN | WT | 220 |  | 2017-09-12 | 2017-11-01 | 2017-11-30 | 2018-08-30 | 2018-10-12 | Yes | Not Required | Not Required | Not Required | 2018-10-12 | 2019-02-27 | 2019-03-26
19INR0113 | County Line Solar | SS Completed, FIS Started, No IA | S Power | 60385 Solstice 138kV | Pecos | WEST | 2021-12-15 | SOL | PV | 250 |  | 2017-08-15 | 2017-11-01 | 2017-08-15 |  |  | No | Not Required | Not Required | Not Required
19INR0114 | Rambler Solar | SS Completed, FIS Started, IA | Recurrent Energy | 76009 Twin Buttes 345kV | Tom Green | WEST | 2020-05-31 | SOL | PV | 150 | COD | 2017-08-09 | 2017-10-10 | 2018-01-05 |  | 2018-10-11 | No | Not Required | Not Required | Not Required
19INR0115 | Blackwater Draw Solar | SS Completed, FIS Started, No IA | Core Solar | tap 138kV 1170 Paul Davis tap - 18880 Jim Payne | Dawson | WEST | 2020-12-31 | SOL | PV | 151.9 |  | 2017-07-28 | 2017-10-09 | 2018-04-12 |  |  | No | Not Required | Not Required | Not Required
19INR0117 | Roadrunner Crossing Wind 1 | SS Completed, FIS Started, No IA | Eon | tap 345kV 68005 WShack - 68050 Romney | Eastland | NORTH | 2020-12-31 | WIN | WT | 200.2 |  | 2017-09-08 | 2017-11-07 | 2018-03-05 |  |  | No | Not Required | Not Required | Not Required
19INR0120 | Sherbino II Wind repower | SS Completed, FIS Completed, IA | Sherbino II Wind Farm LLC | 131454 Keo_3 138kV | Pecos | WEST | 2020-03-01 | WIN | WT | -13 |  | 2017-08-18 | 2017-09-28 | 2017-09-21 | 2018-12-04 | 2008-02-28 | No | Not Required | Not Required | Not Required
19INR0121 | Galloway Solar | SS Completed, FIS Started, IA | 8minutenergy | tap 345kV 6444 RedCr - 76006 Bow or tap 345kV 76009 Twin - 1444 Brown | Concho | WEST | 2020-12-01 | SOL | PV | 360 |  | 2017-08-25 | 2017-10-02 | 2017-08-25 |  | 2019-03-28 | No | Not Required | Not Required | Not Required
19INR0123 | GSE Eleven | SS Completed, FIS Completed, No IA | Pattern Energy | tap 138kV 3175 Canton - 3173 Expmtr | Van Zandt | NORTH | 2020-11-01 | SOL | PV | 135 |  | 2017-09-12 | 2017-11-13 | 2017-12-05 | 2019-04-18 |  | No | Not Required | Not Required | Not Required
19INR0128 | White Mesa Wind | SS Completed, FIS Completed, IA | Apex Clean | 76005 Schneeman Draw 345kV | Crockett | WEST | 2020-09-30 | WIN | WT | 500 |  | 2017-09-08 | 2017-11-20 | 2018-01-29 | 2019-04-24 | 2018-12-19 | No | Not Required | Not Required | Not Required
19INR0129 | Flatland Solar | SS Completed, FIS Started, No IA | Sunfinity Renewables | tap 138kV 1032 Morgan - 1064 Sun | Scurry | WEST | 2020-07-15 | SOL | PV | 147 |  | 2017-10-20 | 2017-12-13 | 2018-06-13 |  |  | No | Not Required | Not Required | Not Required
19INR0131 | Cutlass Solar | SS Completed, FIS Started, No IA | Lendlease Energy | tap 345kV 44000 WAP - 44200 Hillje, probably | Fort Bend | HOUSTON | 2020-06-01 | SOL | PV | 300 |  | 2017-09-21 | 2017-11-20 | 2018-05-15 |  |  | No | Not Required | Not Required | Not Required
19INR0132 | La Joya I Wind | SS Completed, FIS Started, No IA | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | SOUTH | 2021-10-01 | WIN | WT | 236.9 | Proj Name MW Size COD | 2017-09-22 | 2017-11-13 | 2017-09-22 |  |  | No | Not Required | Not Required | Not Required
19INR0133 | La Joya II Wind | SS Completed, FIS Started, No IA | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | SOUTH | 2021-12-31 | WIN | WT | 236.9 |  | 2017-09-22 | 2017-11-13 | 2017-09-22 |  |  | No | Not Required | Not Required | Not Required
19INR0134 | Cottonwood Bayou | SS Completed, FIS Completed, No IA | Sunchase Power | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2020-11-30 | SOL | PV | 150 |  | 2017-09-22 | 2017-11-17 | 2018-02-15 | 2019-03-25 |  | No | Not Required | Not Required | Not Required
19INR0135 | Hill Solar | SS Completed, FIS Started, No IA | Sunchase Power | tap 69kV 3523 Hillsboro - 3532 Itasco | Hill | NORTH | 2020-10-01 | SOL | PV | 80 |  | 2017-09-22 | 2017-11-17 | 2018-05-10 |  |  | No | Not Required | Not Required | Not Required
19INR0136 | Able Solar | SS Completed, FIS Started, No IA | Sunchase Power | 12469 Able Spring 138kV | Kaufman | NORTH | 2020-10-01 | SOL | PV | 50 |  | 2017-09-22 | 2017-11-17 | 2018-05-10 |  |  | No | Not Required | Not Required | Not Required
19INR0138 | Buffalo Gap 4 | SS Completed, FIS Started, No IA | AES | 66216 Bluff Creek 138kV | Nolan | WEST | 2020-09-01 | WIN | WT | 175 |  | 2017-10-06 | 2017-11-20 | 2017-10-06 |  |  | No | Not Required | Not Required | Not Required
19INR0142 | Bacon Switch Solar | SS Completed, FIS Started, No IA | SunChase Power | tap 345kV 6101 Riley - 1425 Fisher | Wichita | WEST | 2020-05-31 | SOL | PV | 180 |  | 2017-10-11 | 2017-11-08 | 2018-02-15 |  |  | No | Not Required | Not Required | Not Required
19INR0144 | Bird Dog Wind | SS Completed, FIS Started, No IA | Americlean | 1301 Willow Valley 138kV | Borden | WEST | 2019-10-01 | WIN | WT | 300 |  | 2017-10-20 | 2017-12-14 | 2018-07-05 |  |  | No | Not Required | Not Required | Not Required
19INR0145 | Aquilla Lake | SS Completed, FIS Started, No IA | Nextera | 68090 Sam Switch 345 kV | Hill | NORTH | 2020-08-30 | WIN | WT | 202 |  | 2018-07-18 | 2018-09-20 | 2018-07-18 |  |  | No | Not Required | Not Required | Not Required
19INR0147 | March Road Solar | SS Completed, FIS Started, No IA | Eon | tap 345kV 76009 TwinB - 6444 San Angelo Red Creek | Tom Green | WEST | 2020-12-30 | SOL | PV | 200 |  | 2017-11-13 | 2018-01-08 | 2017-12-01 |  |  | No | Not Required | Not Required | Not Required
19INR0150 | Millhouse Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 69kV 8500 Alice - 8889 Stadium | Jim Wells | SOUTH | 2020-12-31 | SOL | PV | 75 |  | 2017-11-13 | 2018-02-23 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
19INR0151 | Impact Solar | SS Completed, FIS Started, No IA | GSE Twelve LLC | tap 345kV 1695 Moses - 1692 Paris | Lamar | NORTH | 2020-11-01 | SOL | PV | 197 |  | 2017-12-18 | 2018-02-01 | 2018-05-04 |  |  | No | Not Required | Not Required | Not Required
19INR0155 | Morrow Lake Solar | SS Completed, FIS Started, No IA | Sunchase Power | loop into the Pearsall 5895 to MooreSwitch 5827 138-kV line | Frio | SOUTH | 2020-10-01 | SOL | PV | 150 |  | 2017-12-05 | 2018-01-15 | 2018-02-15 |  |  | No | Not Required | Not Required | Not Required
19INR0156 | Grape Creek Wind | SS Completed, FIS Started, IA | Apex Clean | 76090 Divide 345kV | Coke | WEST | 2020-10-01 | WIN | WT | 525 |  | 2017-12-06 | 2018-02-23 | 2018-01-25 |  | 2019-02-14 | No | Not Required | Not Required | Not Required
19INR0159 | Reiher Solar | SS Completed, FIS Started, No IA | Energie Kontor | 76597 Robb Sw 138kV | Upton | WEST | 2020-12-31 | SOL | PV | 101.6 |  | 2018-01-29 | 2018-03-27 | 2018-08-14 |  |  | No | Not Required | Not Required | Not Required
19INR0161 | Pierce Wind | SS Completed, FIS Started, No IA | Seventus | 345kV ROW between Hillje & WAP or 345kV Bailey to Hillje | Wharton | SOUTH | 2020-03-01 | WIN | WT | 300 |  | 2018-01-03 | 2018-02-16 | 2018-01-03 |  |  | No | Not Required | Not Required | Not Required
19INR0163 | Sage Draw Wind | SS Completed, FIS Completed, IA | Lincoln Clean | 79641 Farmland 345kV | Lynn | WEST | 2020-03-31 | WIN | WT | 338 |  | 2016-03-14 | 2016-03-23 | 2016-04-22 | 2019-04-17 | 2018-01-03 | Yes | Not Required | Not Required | Not Required | 2019-03-22 | 2019-04-30 | 2019-04-30
19INR0165 | Barranca Wind | SS Completed, FIS Started, No IA | Lincoln Clean Energy, LLC | tap 345kV 80307 Delsol - 80380 Cabezon | Zapata | SOUTH | 2020-04-30 | WIN | WT | 201.6 |  | 2018-05-09 | 2018-05-25 | 2018-02-28 |  |  | No | Not Required | Not Required | Not Required
19INR0166 | Loma Pinta II | SS Completed, FIS Started, No IA | Enerverse | 5705 Fowlerton 138kV | La Salle | SOUTH | 2019-12-31 | WIN | WT | 201.6 |  | 2018-02-28 | 2018-04-16 | 2018-02-28 |  |  | No | Not Required | Not Required | Not Required
19INR0167 | Gold Creek Solar | SS Completed, FIS Started, No IA | S Power | 1163 Lamesa 138kV | Dawson | WEST | 2021-12-15 | SOL | PV | 140 | COD | 2018-05-04 | 2018-06-28 | 2018-05-04 |  |  | No | Not Required | Not Required | Not Required
19INR0169 | Sun Valley | SS Completed, FIS Started, No IA | Alpin Sun | tap 345kV 68090 Sam Sw - 3405 or 13405 Tradinghouse | Hill | NORTH | 2020-12-01 | SOL | PV | 135 |  | 2018-03-02 | 2018-04-17 | 2018-07-19 |  |  | No | Not Required | Not Required | Not Required
19INR0171 | Concho Valley Solar | SS Completed, FIS Started, No IA | Merit SI | tap 138kV 6480 SAPOWER - 6490 Santiago | Tom Green | WEST | 2020-11-01 | SOL | PV | 150 |  | 2018-03-02 | 2018-04-13 | 2018-03-02 |  |  | No | Not Required | Not Required | Not Required
19INR0172 | Dillon Gulch | SS Completed, FIS Started, No IA | AES | tap 345kV 11420 Sweetwater East Switch - 11406 Central Bluff Switch | Nolan | WEST | 2020-12-15 | WIN | WT | 175 |  | 2018-04-12 | 2018-06-13 | 2018-04-12 |  |  | No | Not Required | Not Required | Not Required
19INR0173 | Magnet Wind | SS Completed, FIS Started, No IA | Seventus | 43190 South Lane City 138kV | Wharton | SOUTH | 2020-06-30 | WIN | WT | 125 |  | 2018-04-13 | 2018-06-12 | 2018-04-13 |  |  | No | Not Required | Not Required | Not Required
19INR0174 | Elbow Creek repower | SS Completed, FIS Completed, IA | NRG | 1058 Longshore 345kV | Howard | WEST | 2019-09-16 | WIN | WT | 0 |  | 2018-05-04 | 2018-05-18 | 2018-07-19 | 2018-09-17 | 2007-11-30 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31
19INR0175 | Changing Winds | SS Completed, FIS Started, No IA | Triglobal | 79501 Ogallala 345kV | Castro | PANHANDLE | 2020-10-30 | WIN | WT | 289 |  | 2018-04-26 | 2018-06-12 | 2018-12-06 |  |  | No | Not Required | Not Required | Not Required
19INR0176 | Roughneck Storage | SS Completed, FIS Started, No IA | Glidepath | 43380 W Columbia 138kV | Brazoria | COASTAL | 2021-07-01 | OTH | BA | 52.25 |  | 2018-05-09 | 2018-07-13 | 2018-11-07 |  |  | No | Not Required | Not Required | Not Required
19INR0177 | Shanghai Wind | SS Completed, FIS Started, No IA | Seventus | 8104 Lane City PM 138kV | Wharton | SOUTH | 2019-12-31 | WIN | WT | 153.3 |  | 2018-05-09 | 2018-06-21 | 2018-05-09 |  |  | No | Not Required | Not Required | Not Required
19INR0179 | Barranca Wind II | SS Completed, FIS Started, No IA | Lincoln Clean Energy, LLC | tap 345kV 80307 Delsol - 80380 Cabezon | Zapata | SOUTH | 2020-04-30 | WIN | WT | 201.6 |  | 2018-05-15 | 2018-06-01 | 2018-05-15 |  |  | No | Not Required | Not Required | Not Required
19INR0180 | Friendswood II | SS Completed, FIS Completed, No IA | Quantum | 47170 HOC 138kV | Brazoria | COASTAL | 2019-11-15 | GAS | GT | 117 |  | 2018-05-17 | 2018-07-11 | 2018-05-17 | 2019-03-29 |  | No
19INR0182 | Blue Summit Wind III | SS Completed, FIS Completed, IA | Nextera | 61001 Jim Treece 345kV | Wilbarger | WEST | 2019-11-01 | WIN | WT | 200 | SFS/NtP | 2018-06-06 | 2018-07-24 | 2018-06-06 | 2019-03-20 | 2019-04-09 | Yes | Not Required | Not Required | Not Required | 2019-04-09 | 2019-04-09 | 2019-04-09
19INR0184 | Oxy Solar | SS Completed, FIS Completed, IA | Oxy Renewable Energy | 11256 Goldsmith 138kV | Ector | WEST | 2019-07-15 | SOL | PV | 16.2 |  | 2018-07-18 | 2018-09-20 | 2018-08-07 | 2019-01-30 | 2019-01-30 | Yes | Not Required | Not Required | Not Required | 2019-01-30 | 2019-01-30 | 2019-01-31
19INR0185 | Lapetus Solar 2 | SS Completed, FIS Completed, IA | 7x Energy | tap 138kV 1284 Shafter Lake - 1272 Fullerton | Andrews | WEST | 2019-12-31 | SOL | PV | 100 |  | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2019-03-22 | 2018-12-21 | Yes | Not Required | Not Required | Not Required | 2019-02-27 | 2019-04-29 | 2019-04-29
19INR0186 | SP TX-12B Phase II | SS Completed, FIS Started, No IA | ConEd Development | 132943 SPTX12B 138kV | Upton | WEST | 2021-05-24 | SOL | PV | 25 | FIS Request | 2018-09-12 | 2018-09-18 |  |  |  | No | Not Required | Not Required | Not Required
19INR0187 | John Paul Jones | SS Completed, FIS Started, No IA | Dflex Power | 46510 Tomball 138kV | Harris | HOUSTON | 2020-05-31 | GAS | GT | 18.6 |  | 2018-08-02 | 2018-09-28 | 2018-08-02 |  |  | No
19INR0188 | Millhouse Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 69kV 8500 Alice - 8889 Stadium | Jim Wells | SOUTH | 2020-12-31 | OTH | BA | 38 |  | 2017-11-13 | 2018-02-23 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
19INR0189 | SP TX-12B Phase III | SS Completed, FIS Started, No IA | ConEd Development | 76040 Castillo 138kV | Upton | WEST | 2019-12-31 | SOL | PV | 40 |  | 2018-09-12 | 2018-10-03 |  |  |  | No | Not Required | Not Required | Not Required
19INR0203 | Angelo Solar | SS Completed, FIS Started, No IA | ANGELO SOLAR LLC | 76009 Twin Buttes 345kV | Tom Green | WEST | 2020-12-31 | SOL | PV | 195 |  | 2018-11-20 | 2019-02-05 | 2019-01-21 |  |  | No |  |  | Not Required
19INR0204 | Oak Grove Units 1 & 2 repower | SS Completed, FIS Started, No IA | OAK GROVE MANAGEMENT COMPANY LLC | 3400 Twin Oak 345kV | Robertson | NORTH | 2019-06-01 | COA | ST | 45 |  | 2019-01-28 | 2019-04-15 | 2019-01-25 |  |  | No
19INR0205 | RIO NOGALES AGP UPGRADE CT1 | SS Started, FIS Started, No IA | CPS Energy | Existing gen 170201 RIONOG_CT1 18kV | Guadalupe | SOUTH | 2019-05-31 | GAS | CC | 19 |  | 2019-02-28 |  | 2019-02-19 |  |  | No | Not Required | Not Required
20INR0005 | Shorthorn 2 Solar | SS Completed, FIS Started, No IA | 8minutenergy | 60501 Tesla 345kV | Childress | PANHANDLE | 2020-10-01 | SOL | PV | 200 |  | 2016-10-26 | 2016-11-14 | 2016-12-13 |  |  | No | Not Required | Not Required | Not Required
20INR0011 | Ranchero Wind | SS Completed, FIS Completed, IA | Scout Clean Energy | 7053 Noelke 345kV | Crockett | WEST | 2019-09-30 | WIN | WT | 300 |  | 2017-06-23 | 2017-08-07 | 2017-07-03 | 2018-11-01 | 2018-05-02 | Yes | Not Required | Not Required | Not Required | 2018-08-03 | 2018-10-31 | 2018-11-01
20INR0012 | Lueders Solar | SS Completed, FIS Started, No IA | Innovative Solar | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | WEST | 2020-08-01 | SOL | PV | 40 |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0013 | Basalt Solar | SS Completed, FIS Started, No IA | Innovative Solar | tap 138kV 8234 Uvalde - 8241 Razorback | Uvalde | SOUTH | 2020-08-01 | SOL | PV | 20 |  | 2017-07-11 | 2017-09-01 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0014 | Obsidian Solar | SS Completed, FIS Started, No IA | Innovative Solar | 6131 Padr 69kV | Cottle | WEST | 2020-08-01 | SOL | PV | 60 |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0015 | Citrine Solar | SS Completed, FIS Started, No IA | Innovative Solar | Tap 138kV 6135 Paducah Clare - 6117 E Munday | Cottle | WEST | 2020-08-01 | SOL | PV | 45 |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0016 | Opal Solar | SS Completed, FIS Started, No IA | Innovative Solar | tap 345kV 60501 Tesla - 60500 Edith Clark | Hardeman | WEST | 2020-08-01 | SOL | PV | 45 |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0019 | Trinity Hills Wind repower | SS Completed, FIS Completed, IA | Trinity Hills Wind Farm LLC | 150751 & 150752 Trinity Hills 34.5kV | Young | WEST | 2020-11-01 | WIN | WT | -27 |  | 2017-07-20 | 2017-09-08 | 2017-09-21 | 2018-08-02 | 2018-10-17 | No | Not Required | Not Required | Not Required
20INR0021 | Garnet Solar | SS Completed, FIS Completed, No IA | Innovative Solar | tap 69kV 3648 Granger - 3649 Taylor | Williamson | SOUTH | 2020-07-01 | SOL | PV | 20 |  | 2017-08-10 | 2017-10-10 | 2017-10-20 | 2018-09-28 |  | No | Not Required | Not Required | Not Required
20INR0022 | Sandine Solar | SS Completed, FIS Started, No IA | Innovative Solar | tap 138kV 6135 Paducah - 6320 Tardis | Cottle | WEST | 2020-08-01 | SOL | PV | 30 |  | 2017-08-10 | 2017-10-22 | 2017-10-24 |  |  | No | Not Required | Not Required | Not Required
20INR0023 | Agate Solar | SS Completed, FIS Completed, IA | Innovative Solar | new 345kV sub Forbes in 68090 Sam - 1906 Venus S | Ellis | NORTH | 2020-08-01 | SOL | PV | 60 |  | 2017-08-10 | 2017-10-18 | 2017-10-23 | 2018-10-26 | 2019-02-05 | No | Not Required | Not Required | Not Required
20INR0024 | Fluorite Solar | SS Completed, FIS Completed, No IA | Innovative Solar | 5817 FerrisSw 69kV | Uvalde | SOUTH | 2020-08-01 | SOL | PV | 25 |  | 2017-08-10 | 2017-10-22 | 2017-10-20 | 2018-11-02 |  | No | Not Required | Not Required | Not Required
20INR0025 | Spinel Solar | SS Completed, FIS Completed, IA | Innovative Solar | tap 138kV 5225 Hondo - 5813 Pearson | Medina | SOUTH | 2020-08-01 | SOL | PV | 30 |  | 2017-08-10 | 2017-10-09 | 2017-10-20 | 2018-07-26 | 2019-01-22 | No | Not Required | Not Required | Not Required
20INR0026 | Longbow Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 42870 Liverpool 138kV | Brazoria | COASTAL | 2020-03-01 | SOL | PV | 70 |  | 2017-08-16 | 2017-10-13 | 2017-08-16 |  |  | No | Not Required | Not Required | Not Required
20INR0029 | JA Ranch | SS Completed, FIS Started, No IA | EDF Renewable Energy | tap 345kV 6101 Riley - 1730 W Krum | Clay | WEST | 2021-10-01 | WIN | WT | 242 |  | 2017-09-12 | 2017-11-07 | 2018-05-08 |  |  | No | Not Required | Not Required | Not Required
20INR0031 | Rippey Solar | SS Completed, FIS Completed, No IA | Belltown Power | tap 138kV 1988 ValleyV - 1710 Gainvl | Cooke | NORTH | 2020-05-15 | SOL | PV | 60 |  | 2017-10-02 | 2017-11-13 | 2018-02-06 | 2019-03-20 |  | No | Not Required | Not Required | Not Required
20INR0032 | IP Titan | SS Completed, FIS Started, IA | Intersect Power | 71097 LCRA Culberson 138kV | Culberson | WEST | 2021-06-30 | SOL | PV | 272 |  | 2017-10-12 | 2017-12-08 | 2018-01-19 |  | 2019-02-04 | No | Not Required | Not Required | Not Required
20INR0033 | Cooke Wind II | SS Completed, FIS Started, No IA | Wildcat Creek | tap 345kV 1730 KrumW - 2373 Anna | Cooke | NORTH | 2020-10-31 | WIN | WT | 180 |  | 2017-10-18 | 2017-12-11 | 2018-06-14 |  |  | No | Not Required | Not Required | Not Required
20INR0035 | Angus Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 177 Bosque - 181 Cayote | Bosque | NORTH | 2020-08-31 | SOL | PV | 113 |  | 2017-11-13 | 2018-01-02 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
20INR0036 | Stillwater Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 345kV 8905 N Edinb - 8455 Lon Hill | Nueces | COASTAL | 2020-08-31 | SOL | PV | 144 |  | 2017-11-13 | 2018-01-15 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
20INR0037 | Coniglio Solar | SS Completed, FIS Started, No IA | Belltown Power | 1809 Boistret 138kV | Fannin | NORTH | 2020-08-01 | SOL | PV | 135 |  | 2017-11-28 | 2018-01-23 | 2018-05-25 |  |  | No | Not Required | Not Required | Not Required
20INR0038 | Red Mud Creek | SS Completed, FIS Started, No IA | Eon | tap 345kV 11318 Scurry - 59905 Faraday or 11318-59900 Long Draw | Borden | WEST | 2020-12-31 | WIN | WT | 201 |  | 2017-11-29 | 2018-02-05 | 2018-03-15 |  |  | No | Not Required | Not Required | Not Required
20INR0040 | Montgomery Ranch Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 60500 EdithC - 60700 Gauss | Foard | WEST | 2021-12-15 | WIN | WT | 200.2 |  | 2017-12-18 | 2018-02-06 | 2018-06-20 |  |  | No | Not Required | Not Required | Not Required
20INR0042 | Chalupa Wind | SS Completed, FIS Started, IA | Acciona | Kelvin Station | Cameron | COASTAL | 2020-12-21 | WIN | WT | 174 |  | 2017-12-22 | 2018-02-06 | 2018-01-24 |  | 2018-09-28 | Yes | Not Required | Not Required | Not Required | 2018-10-18 | 2018-12-18
20INR0043 | Gulf Wind 2 | SS Completed, FIS Started, No IA | Pattern Energy | 80071 Zorillo 345kV | Kenedy | COASTAL | 2020-06-01 | WIN | WT | 178.6 |  | 2018-01-04 | 2018-02-20 | 2018-02-14 |  |  | No | Not Required | Not Required | Not Required
20INR0044 | French Goldston Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 138kV 1431 Graham - 1477 Rice OR 1596 Graham 138kV | Young | WEST | 2021-02-01 | SOL | PV | 120 |  | 2018-01-03 | 2018-03-12 | 2018-09-19 |  |  | No | Not Required | Not Required | Not Required
20INR0045 | Maverick Creek I | SS Completed, FIS Completed, IA | RES Americas | tap 345kV 6444 RedCr - 76006 Bow or tap 345kV 76009 Twin - 1444 Brown | Concho | WEST | 2020-09-01 | WIN | WT | 268.5 |  | 2018-01-05 | 2018-02-20 | 2018-03-05 | 2019-04-03 | 2018-07-31 | No | Not Required | Not Required | Not Required
20INR0046 | Maverick Creek II | SS Completed, FIS Completed, IA | RES Americas | tap 345kV 6444 RedCr - 76006 Bow or tap 345kV 76009 Twin - 1444 Brown | Concho | WEST | 2020-09-01 | WIN | WT | 255.9 |  | 2018-01-05 | 2018-02-20 | 2018-03-05 | 2019-04-03 | 2018-07-31 | No | Not Required | Not Required | Not Required
20INR0048 | Century Oak Wind | SS Completed, FIS Started, No IA | Engie | tap 138kV 6670 Putnam - 6317 Cisco | Callahan | WEST | 2021-12-01 | WIN | WT | 126 |  | 2018-01-29 | 2018-02-28 | 2018-05-17 |  |  | No | Not Required | Not Required | Not Required
20INR0050 | Castro Solar | SS Completed, FIS Started, No IA | Oaktree Development | 79501 Ogallala 345kV | Castro | PANHANDLE | 2020-01-01 | SOL | PV | 212.95 |  | 2018-02-08 | 2018-04-09 | 2018-05-15 |  |  | No | Not Required | Not Required | Not Required
20INR0052 | Griffin Trail Wind | SS Completed, FIS Started, IA | Innergex | tap 345kV 60500 EdithC - 60702 Gauss | Knox | WEST | 2020-09-30 | WIN | WT | 201.6 |  | 2018-03-05 | 2018-05-04 | 2018-11-07 |  | 2019-03-04 | No | Not Required | Not Required | Not Required
20INR0053 | Bravepost Solar | SS Completed, FIS Started, No IA | Recurrent Energy | 6444 Red Creek 345kV | Tom Green | WEST | 2020-12-31 | SOL | PV | 200 |  | 2018-02-22 | 2018-04-13 | 2018-06-07 |  |  | No | Not Required | Not Required | Not Required
20INR0054 | Taygete Solar | SS Completed, FIS Started, IA | 7x Energy | 60393 Pig Creek 138kV | Pecos | WEST | 2020-12-01 | SOL | PV | 254.24 |  | 2018-02-26 | 2018-05-04 | 2018-02-26 |  | 2018-10-26 | Yes | Not Required | Not Required | Not Required | 2019-02-05
20INR0055 | Vaquero 2 Wind | SS Completed, FIS Started, No IA | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Zapata | SOUTH | 2020-12-31 | WIN | WT | 201.6 |  | 2018-03-15 | 2018-05-24 | 2018-03-15 |  |  | No | Not Required | Not Required | Not Required
20INR0056 | Point Mountain Solar | SS Completed, FIS Started, No IA | Hecate Energy | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | WEST | 2020-06-01 | SOL | PV | 514 |  | 2018-04-02 | 2018-05-17 | 2018-10-10 |  |  | No | Not Required | Not Required | Not Required
20INR0061 | Pflugerville 2 Solar | SS Completed, FIS Started, No IA | Core Solar | tap 138kV 7336 Gillie - 3650 Elgin | Travis | SOUTH | 2020-12-01 | SOL | PV | 120 |  | 2018-03-05 | 2018-04-19 | 2018-10-10 |  |  | No | Not Required | Not Required | Not Required
20INR0068 | Black Jack Creek Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 8164 Coleto - 8455 Lon Hill | Bee | SOUTH | 2020-12-31 | WIN | WT | 239.8 |  | 2018-04-02 | 2018-05-18 | 2018-11-07 |  |  | No | Not Required | Not Required | Not Required
20INR0069 | Danish Fields Solar | SS Completed, FIS Started, No IA | Sunchase Power | 44200 Hillje 345kV | Wharton | SOUTH | 2021-02-01 | SOL | PV | 200 |  | 2018-04-12 | 2018-06-05 | 2018-08-21 |  |  | No | Not Required | Not Required | Not Required
20INR0070 | Monte Bueno | SS Completed, FIS Started, No IA | Terra-Gen | tap 138kV 8392 Bates - 8394 Liston | Hidalgo | SOUTH | 2019-12-31 | WIN | WT | 201.1 |  | 2018-04-12 | 2018-05-30 | 2018-10-10 |  |  | No | Not Required | Not Required | Not Required
20INR0071 | Havana Wind | SS Completed, FIS Started, No IA | Terra-Gen | Goodwin (#8355) and La Grulla (#8798) buses | Hidalgo | SOUTH | 2019-12-31 | WIN | WT | 201.1 |  | 2018-04-12 | 2018-06-01 | 2018-10-10 |  |  | No | Not Required | Not Required | Not Required
20INR0074 | Pitts Dudik Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 138kV Hillsoboro 3522- Navarro 3478 183kV | Hill | NORTH | 2020-09-01 | SOL | PV | 90 |  | 2018-04-12 | 2018-05-18 | 2018-05-25 |  |  | No | Not Required | Not Required | Not Required
20INR0075 | Howle Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV 1906 Venus - 68090 Sam Sw | Ellis | NORTH | 2020-08-01 | SOL | PV | 75 |  | 2018-05-15 | 2018-07-02 | 2018-08-14 |  |  | No | Not Required | Not Required | Not Required
20INR0080 | Frye Solar | SS Completed, FIS Started, No IA | Hecate Energy | tap 345kV 79501 Ogallala - 79503 Tule Canyon | Swisher | PANHANDLE | 2021-06-01 | SOL | PV | 500 |  | 2018-05-17 | 2018-07-02 | 2018-11-20 |  |  | No | Not Required | Not Required | Not Required
20INR0081 | Strategic Energy | SS Completed, FIS Started, No IA | Alpin Sun | Tap 345kV 2435 Watermill - 68091 Navarro | Ellis | NORTH | 2020-11-01 | SOL | PV | 135 |  | 2018-04-26 | 2018-06-05 | 2018-07-18 |  |  | No | Not Required | Not Required | Not Required
20INR0082 | Vision Solar | SS Completed, FIS Started, No IA | Alpin Sun | tap 345kV 2428 Watermill - 68091 Navarro | Navarro | NORTH | 2020-11-01 | SOL | PV | 127.2 |  | 2018-04-26 | 2018-06-05 | 2018-05-17 |  |  | No | Not Required | Not Required | Not Required
20INR0083 | Baird North Wind | SS Completed, FIS Started, No IA | BMP Wind, LLC | tap 345kV 68005 WShack - 68050 Romney | Callahan | WEST | 2020-12-15 | WIN | WT | 293.55 |  | 2018-05-04 | 2018-06-12 | 2018-08-20 |  |  | No | Not Required | Not Required | Not Required
20INR0086 | Arroyo Solar | SS Completed, FIS Started, No IA | Belltown Power | tap Rio Hondo to La Palma 138-kV or 345-kV | Cameron | COASTAL | 2020-09-01 | SOL | PV | 180 |  | 2018-05-09 | 2018-07-09 | 2018-10-10 |  |  | No | Not Required | Not Required | Not Required
20INR0088 | West Raymond Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2020-09-15 | WIN | WT | 239.8 |  | 2018-05-14 | 2018-07-09 | 2018-07-06 |  |  | No | Not Required | Not Required | Not Required
20INR0089 | Chisholm Grid Battery Storage | SS Completed, FIS Started, No IA | Able Grid Energy | 2082 Hicks 138kV | Tarrant | NORTH | 2020-03-01 | OTH | BA | 200 |  | 2018-05-14 | 2018-06-19 | 2018-05-14 |  |  | No | Not Required | Not Required | Not Required
20INR0091 | Misae Solar II | SS Completed, FIS Completed, IA | Misae Solar Park II | 60501 Tesla 345kV | Childress | PANHANDLE | 2020-12-31 | SOL | PV | 517.35 |  | 2018-05-15 | 2018-07-06 | 2018-05-15 | 2019-03-29 | 2019-02-21 | Yes | Not Required | Not Required | Not Required
20INR0096 | Desert Rose | SS Completed, FIS Started, No IA | Apex Clean | 79650 Clearfork 345kV | Andrews | WEST | 2020-12-23 | SOL | PV | 200 |  | 2018-06-06 | 2018-07-30 | 2019-01-25 |  |  | No | Not Required | Not Required | Not Required
20INR0097 | El Suaz Ranch | SS Completed, FIS Started, No IA | El Sauz Ranch Wind, LLC | new Cebola station 345kV (near Rio Hondo) | Willacy | COASTAL | 2021-09-30 | WIN | WT | 301.74 |  | 2018-06-19 | 2018-08-22 | 2019-01-31 |  |  | No | Not Required | Not Required | Not Required
20INR0098 | Danciger Solar | SS Completed, FIS Started, No IA | Brazoria County Solar Project, LLC | tap 138kV 43120 Pledger - 43380 W Columbia | Brazoria | COASTAL | 2021-12-31 | SOL | PV | 200 |  | 2018-06-06 | 2018-08-01 | 2018-10-23 |  |  | No | Not Required | Not Required | Not Required
20INR0100 | Westoria Storage | SS Completed, FIS Started, No IA | Brazoria West Solar Project, LLC | tap 138kV 42980 Nash - 43380 W Columbia | Brazoria | COASTAL | 2021-12-31 | OTH | BA | 58 |  | 2018-06-07 | 2018-08-01 | 2018-11-20 |  |  | No |  |  | Not Required
20INR0101 | Westoria Solar | SS Completed, FIS Started, No IA | Brazoria West Solar Project,LLC | tap 138kV 42980 Nash - 43380 W Columbia | Brazoria | COASTAL | 2021-12-31 | SOL | PV | 200 |  | 2018-06-07 | 2018-07-30 | 2018-10-23 |  |  | No | Not Required | Not Required | Not Required
20INR0102 | Atascosa I Solar | SS Completed, FIS Started, No IA | Core Solar | tap 138kV 8221 Big Foot - 8203 Pleasant | Dawson | WEST | 2020-12-31 | SOL | PV | 126.6 |  | 2018-06-07 | 2018-08-24 | 2018-10-23 |  |  | No | Not Required | Not Required | Not Required
20INR0104 | GoodAlta | SS Completed, FIS Started, No IA | Alta Power | 3483 Goodloe 138kV | Navarro | NORTH | 2021-04-01 | GAS | GT | 150 |  | 2018-07-26 | 2018-09-18 | 2018-10-23 |  |  | No
20INR0106 | Wang Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2020-10-01 | SOL | PV | 120 |  | 2018-06-14 | 2018-08-13 | 2018-08-29 |  |  | No | Not Required | Not Required | Not Required
20INR0112 | Walstrom | SS Completed, FIS Started, No IA | Castleman Power | 46220 Peters 138kV | Austin | SOUTH | 2020-05-01 | GAS | GT | 200 |  | 2018-07-03 | 2018-09-18 | 2018-11-29 |  |  | No
20INR0116 | Gusty Hill Wind | SS Completed, FIS Started, No IA | Gusty Hill Wind Project, LLC | tap 7387 Kunitz 138 kV - 71097 Culberson 138kV | Culberson | WEST | 2021-12-31 | WIN | WT | 350 |  | 2018-06-29 | 2018-09-04 | 2019-02-26 |  |  | No | Not Required | Not Required | Not Required
20INR0118 | Merrifield Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 69kV 3523 Hillsboro - 3543 Mertens or tap 345kV 1906 Venus - 68090 Sam | Hill | NORTH | 2020-12-01 | SOL | PV | 80 |  | 2018-06-29 | 2018-09-18 | 2018-11-07 |  |  | No | Not Required | Not Required | Not Required
20INR0119 | Azure Sky Wind 1 | SS Completed, FIS Started, No IA | Tradewind Energy | 60515 Clear Crossing 345kV or tap 60515 - 1421 WillowCr | Throckmorton | WEST | 2020-09-30 | WIN | WT | 350 |  | 2018-06-29 | 2018-08-27 | 2018-11-30 |  |  | No | Not Required | Not Required | Not Required
20INR0120 | Azure Sky Wind 2 | SS Completed, FIS Started, No IA | Tradewind Energy | 60515 Clear Crossing 345kV or tap 60515 - 1421 WillowCr | Throckmorton | WEST | 2021-12-31 | WIN | WT | 350 |  | 2018-06-29 | 2018-08-27 | 2019-02-20 |  |  | No | Not Required | Not Required | Not Required
20INR0126 | Robles Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 8283 Asherton 138kV | Dimmit | SOUTH | 2020-12-31 | SOL | PV | 200 |  | 2018-07-18 | 2018-10-04 | 2018-07-18 |  |  | No | Not Required | Not Required | Not Required
20INR0128 | EK Tipton Solar | SS Completed, FIS Started, No IA | Energie Kontor | 6673 Musquiz 138kV | Reeves | WEST | 2020-12-31 | SOL | PV | 101.63 |  | 2018-09-27 | 2018-11-19 | 2018-09-27 |  |  | No | Not Required | Not Required | Not Required
20INR0129 | Foxtrot Wind | SS Completed, FIS Started, No IA | Lincoln Clean | Pawnee 345 kV bus 5725 | Karnes | SOUTH | 2020-12-01 | WIN | WT | 504 |  | 2018-07-26 | 2018-09-14 | 2018-07-26 |  |  | No | Not Required | Not Required | Not Required
20INR0130 | Ramsey Solar | SS Completed, FIS Started, No IA | Hecate Energy | 44200 Hillje 345kV | Wharton | SOUTH | 2020-06-01 | SOL | PV | 514 |  | 2018-10-10 | 2018-11-21 | 2018-10-10 |  |  | No | Not Required | Not Required | Not Required
20INR0132 | Altajac | SS Completed, FIS Started, No IA | Alta Power | 3253 Jaxvlsw 138kV | Cherokee | NORTH | 2021-04-01 | GAS | GT | 150 |  | 2018-07-18 | 2018-09-07 | 2018-10-23 |  |  | No
20INR0133 | Thickgrass Solar | SS Completed, FIS Started, No IA | Origis Energy | 8115 Wadsworth 138kV OR loop into STP - Jones Creek 345-kV line | Matagorda | COASTAL | 2020-06-30 | SOL | PV | 148.7 |  | 2018-07-18 | 2018-10-01 | 2019-03-13 |  |  | No | Not Required | Not Required | Not Required
20INR0134 | Half Moon Solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2020-12-31 | SOL | PV | 151.2 |  | 2018-09-13 | 2018-11-09 | 2018-11-06 |  |  | No | Not Required | Not Required | Not Required
20INR0135 | Half Moon Battery | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2020-12-31 | OTH | BA | 30.2 |  | 2018-09-13 | 2018-11-09 | 2018-11-06 |  |  | No | Not Required | Not Required | Not Required
20INR0142 | Ajax Wind | SS Completed, FIS Started, No IA | Lincoln Clean | 345kV line RILEY 6101 - Bowman 1422 | Wilbarger | WEST | 2021-12-01 | WIN | WT | 630 |  | 2018-08-14 | 2018-10-19 | 2018-08-14 |  |  | No | Not Required | Not Required | Not Required
20INR0143 | Soda Lake Solar 2 | SS Completed, FIS Started, IA | Arrington Solar | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | WEST | 2020-12-31 | SOL | PV | 200 |  |  | 2016-11-08 | 2017-02-10 |  | 2018-08-20 | No | Not Required | Not Required | Not Required
20INR0144 | Longbow Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 42870 Liverpool 138kV | Brazoria | COASTAL | 2020-03-01 | OTH | BA | 35 |  | 2017-08-16 | 2017-10-13 | 2017-08-16 |  |  | No | Not Required | Not Required | Not Required
20INR0146 | Angus Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 177 Bosque - 181 Cayote | Bosque | NORTH | 2020-08-31 | OTH | BA | 63 |  | 2017-11-13 | 2018-01-02 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
20INR0147 | Stillwater Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 345kV 8905 N Edinb - 8455 Lon Hill | Nueces | COASTAL | 2020-08-31 | OTH | BA | 72 |  | 2017-11-13 | 2018-01-15 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
20INR0150 | Robles Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 8283 Asherton 138kV | Dimmit | SOUTH | 2020-12-31 | OTH | BA | 100 |  | 2018-07-18 | 2018-10-04 | 2018-07-18 |  |  | No | Not Required | Not Required | Not Required
20INR0153 | Tiger Wind | SS Completed, FIS Started, No IA | Nextera | 68000 West Shackelford 345kV | Taylor | WEST | 2020-12-01 | WIN | WT | 300 |  | 2018-10-10 | 2018-11-16 | 2018-10-10 |  |  | No | Not Required | Not Required | Not Required
20INR0155 | Peyton Creek Wind II | SS Completed, FIS Started, No IA | Eon | 42400 Refuge 345kV | Matagorda | COASTAL | 2020-12-01 | WIN | WT | 242 |  | 2018-08-21 | 2018-11-02 | 2019-03-14 |  |  | No | Not Required | Not Required | Not Required
20INR0157 | Lacy Creek Wind Phase 1 | SS Completed, FIS Started, No IA | Seventus | 79565 Einstein 138kV | Glasscock | WEST | 2020-03-30 | WIN | WT | 200 |  | 2018-08-21 | 2018-11-07 |  |  |  | No | Not Required | Not Required | Not Required
20INR0162 | Diamondback Solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Starr | SOUTH | 2020-12-31 | SOL | PV | 201.6 |  | 2018-09-13 | 2018-12-06 | 2018-11-07 |  |  | No | Not Required | Not Required | Not Required
20INR0163 | Sand Bluff Repower | SS Completed, FIS Started, No IA | Eon | 1333 McDonald 138kV | Glasscock | WEST | 2020-06-30 | WIN | WT | 7.4 |  | 2018-08-28 | 2018-09-05 | 2018-08-28 |  |  | No | Not Required | Not Required | Not Required
20INR0164 | Neeley Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV 1907 Venus - 68090 Sam | Hill | NORTH | 2021-04-01 | SOL | PV | 175 |  | 2018-08-29 | 2018-11-08 | 2018-11-07 |  |  | No | Not Required | Not Required | Not Required
20INR0202 | Owens Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV Shackelford (#68000) to Navarro (#68091) | Bosque | NORTH | 2021-05-01 | SOL | PV | 200 | COD | 2018-09-19 | 2018-10-03 | 2018-10-10 |  |  | No |  |  | Not Required
20INR0203 | Pine Forest Solar | SS Completed, FIS Started, No IA | Telios Corporation | tap 345kV 1695 Moses - 1697 Sulsp | Hopkins | NORTH | 2020-12-31 | SOL | PV | 299.25 | FIS Request | 2018-10-04 | 2018-11-20 |  |  |  | No | Not Required | Not Required | Not Required
20INR0204 | Blue Bell Solar II | SS Completed, FIS Started, No IA | CAP RIDGE WIND IV LLC | 76090 Divide 345kV | Sterling | WEST | 2020-07-31 | SOL | PV | 101.25 |  | 2018-10-23 | 2018-12-13 | 2018-10-03 |  |  | No |  |  | Not Required
20INR0205 | Roseland | SS Completed, FIS Started, No IA | Hecate Energy LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2021-06-01 | SOL | PV | 500 |  | 2018-11-30 | 2019-02-04 | 2019-02-04 |  |  | No |  |  | Not Required
20INR0206 | PES1 | SS Completed, FIS Started, No IA | ProEnergy Services LLC | 47150 H O Clarke 138kV | Harris | HOUSTON | 2020-06-01 | GAS | GT | 484 |  | 2018-10-23 | 2018-11-16 | 2018-10-11 |  |  | No
20INR0208 | Signal Ranch | SS Completed, FIS Started, No IA | Belltown Power Texas, LLC | tap 138kV 6879 Weiland - 6883 Quinlan N | Hunt | NORTH | 2020-12-01 | SOL | PV | 70 | FIS Request | 2018-11-07 | 2018-12-20 |  |  |  | No |  |  | Not Required
20INR0210 | Hopkins | SS Completed, FIS Started, No IA | GSE Group LLC | tap 345kV 1685 Farmersvl - 1695 Moses | Hopkins | NORTH | 2021-06-30 | SOL | PV | 320 | COD | 2018-11-20 | 2019-02-06 | 2019-03-14 |  |  | No |  |  | Not Required
20INR0211 | Avocet | SS Completed, FIS Started, No IA | Alta Power Lufkin Acovet | tap 138kV 3324 Lufkin ET - 3335 Sheco | Angelina | NORTH | 2020-05-01 | GAS | GT | 150 |  | 2018-12-06 | 2019-01-11 | 2019-01-11 |  |  | No
20INR0213 | Brushy Creek Solar | SS Completed, FIS Started, No IA | San Angelo Solar 1 LLC | 6444 Red Creek 345kV | Tom Green | WEST | 2020-06-30 | SOL | PV | 125 |  | 2019-01-07 | 2019-03-26 | 2019-03-05 |  |  | No | Not Required | Not Required | Not Required
20INR0214 | Noble Solar | SS Completed, FIS Started, No IA | Belltown Power Texas, LLC | 1730 Krum 345kV | Denton | NORTH | 2020-12-01 | SOL | PV | 300 |  | 2018-11-06 | 2018-12-17 | 2018-11-06 |  |  | No |  |  | Not Required
20INR0216 | Starr Solar Ranch | SS Completed, FIS Started, No IA | Starr Solar Ranch LLC | 8795 Roma 138kV | Starr | SOUTH | 2020-10-01 | SOL | PV | 135.99 |  | 2018-11-07 | 2018-12-14 | 2018-11-07 |  |  | No | Not Required | Not Required | Not Required
20INR0218 | Morrow Lake Solar II | SS Completed, FIS Started, No IA | Morrow Lake Solar II, LLC | tap 138kV 5895 Pearsall - 5827 Mooresw | Frio | SOUTH | 2020-10-01 | SOL | PV | 50 | FIS Request | 2018-12-06 | 2019-01-17 |  |  |  | No |  |  | Not Required
20INR0219 | Eunice Solar | SS Completed, FIS Started, No IA | 2W Permian Solar LLC | tap 345kV 79650 Clearfork - 79630 Telephone Rd | Andrews | WEST | 2020-12-31 | SOL | PV | 403.8 |  | 2018-12-06 | 2019-01-30 | 2018-11-30 |  |  | No |  |  | Not Required
20INR0220 | Eunice Storage | SS Completed, FIS Started, No IA | 2W Permian Solar LLC | tap 345kV 79650 Clearfork - 79630 Telephone Rd | Andrews | WEST | 2020-12-31 | OTH | BA | 40.26 |  | 2018-12-06 | 2019-01-30 | 2018-11-30 |  |  | No | Not Required | Not Required | Not Required
20INR0221 | Braes Power Plant | SS Completed, FIS Started, No IA | ProEnergy Services LLC | 44650 Smithers 345kV | Fort Bend | HOUSTON | 2020-06-01 | GAS | GT | 484 |  | 2018-12-06 | 2019-01-30 | 2018-12-01 |  |  | No
20INR0222 | Tyson Nick Solar | SS Completed, FIS Started, No IA | Tyson Nick Solar Project, LLC | 1700 Toco 138kV | Lamar | NORTH | 2021-05-01 | SOL | PV | 90 |  | 2018-12-12 | 2019-02-15 | 2019-01-14 |  |  | No |  |  | Not Required
20INR0224 | Ponta Power Plant | SS Completed, FIS Started, No IA | Pro Energy Services LLC | 3109 Stryker Creek 345kV | Cherokee | NORTH | 2020-06-01 | GAS | GT | 484 |  | 2018-12-18 | 2019-03-07 | 2018-12-07 |  |  | No
20INR0226 | Timberwolf POI A | SS Completed, FIS Started, No IA | Solar Prime LLC | 76635 King Mt 138kV | Upton | WEST | 2021-05-01 | SOL | PV | 70 | COD | 2018-12-13 | 2019-01-17 | 2019-02-08 |  |  | No |  |  | Not Required
20INR0230 | Markum Solar | SS Completed, FIS Started, No IA | Glory Leasing | 177 Bosque 138kV | McLennan | NORTH | 2021-05-01 | SOL | PV | 134.89 |  | 2018-12-18 | 2019-01-03 | 2018-12-18 |  |  | No | Not Required | Not Required | Not Required
20INR0231 | Topaz Power Plant | SS Completed, FIS Started, No IA | ProEnergy Services LLC | 38500 GAF TNP 138kV | Galveston | HOUSTON | 2020-06-01 | GAS | GT | 605 |  | 2019-02-01 | 2019-04-26 | 2019-02-22 |  |  | No
20INR0233 | Impala Flats Wind | SS Completed, FIS Started, No IA | Antelope Flats Wind, LLC | 79641 Farmland 345kV | Lynn | WEST | 2020-11-01 | WIN | WT | 282 |  | 2019-01-11 | 2019-04-03 | 2018-12-21 |  |  | No |  |  | Not Required
20INR0235 | Knickerbocker Road Solar | SS Completed, FIS Started, No IA | San Angelo Solar 2 LLC (Knickerbocker Road Solar) | Tap 345kV 76003 Big Hill - 76009 Twin Buttes | Tom Green | WEST | 2020-11-30 | SOL | PV | 200 |  | 2019-01-07 | 2019-03-15 | 2019-03-04 13:38 |  |  | No | Not Required | Not Required | Not Required
20INR0238 | Space City Storage | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2021-12-01 | OTH | BA | 50 | FIS Request | 2019-01-14 | 2019-03-19 | 2019-04-26 13:12 |  |  | No | Not Required | Not Required | Not Required
20INR0242 | Anson Solar Center, Phase II | SS Completed, FIS Started, No IA | Anson Solar Center, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2020-12-31 | SOL | PV | 200 |  | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  | No | Not Required | Not Required | Not Required
20INR0244 | Montezuma Storage | SS Started, FIS Started, No IA | Montezuma Storage LLC | 7258 Glidden 138kV | Colorado | SOUTH | 2020-08-07 | OTH | BA | 47.12 |  | 2019-01-15 |  | 2019-03-15 |  |  | No | Not Required | Not Required | Not Required
20INR0245 | Volunteer Storage | SS Started, FIS Started, No IA | Blackjack Storage LLC | 7216 Lockhart 138kV | Caldwell | SOUTH | 2020-08-31 | OTH | BA | 47.12 |  | 2019-01-15 |  | 2019-03-15 |  |  | No | Not Required | Not Required | Not Required
20INR0246 | Ryan Energy Storage | SS Completed, FIS Started, No IA | Arrowhead Storage LLC | 37580 TNPancake 69kV | Coryell | NORTH | 2020-08-31 | OTH | BA | 47.12 |  | 2019-01-15 | 2019-04-05 | 2019-03-15 |  |  | No | Not Required | Not Required | Not Required
20INR0247 | Water Valley Wind Energy | SS Completed, FIS Started, No IA | Water Valley Wind Energy, LLC | 76011 Twin Buttes 138kV | Tom Green | WEST | 2021-10-31 | WIN | WT | 150 | COD | 2019-01-15 | 2019-03-29 | 2019-01-10 |  |  | No |  |  | Not Required
20INR0249 | Appaloosa Run Renewable Energy Project | SS Completed, FIS Started, No IA | Appaloosa Run, LLC | tap 138kV 60361 Santarita - 76032 NMcCamey | Upton | WEST | 2021-10-31 | WIN | WT | 175 | Proj Name COD | 2019-01-17 | 2019-04-02 | 2019-01-15 |  |  | No |  |  | Not Required
20INR0250 | Aguayo Wind | SS Started, FIS Started, No IA | Castle Gap Wind Power | tap 345kV 1444 Brown - 3422 Killeen | Mills | NORTH | 2020-11-15 | WIN | WT | 196 |  | 2019-02-05 |  | 2019-03-05 |  |  | No |  |  | Not Required
20INR0251 | Rockhound Solar | SS Started, FIS Started, No IA | Rockhound Solar 1, LLC | tap 138kV 1027 Odessa - 1107 Monahans | Ector | WEST | 2020-06-30 | SOL | PV | 250 |  | 2019-02-28 |  | 2019-01-30 |  |  | No |  |  | Not Required
20INR0252 | Toland Power Plant | SS Completed, FIS Started, No IA | ProEnergy Services LLC | 8961 Whitepoint 138kV | San Patricio | COASTAL | 2020-06-01 | GAS | GT | 363 |  | 2019-02-05 | 2019-04-26 | 2019-01-24 |  |  | No
20INR0254 | Greasewood II | SS Started, FIS Started, No IA | Concho Bluff, LLC | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Pecos | WEST | 2020-09-30 | SOL | PV | 55 |  | 2019-02-05 |  | 2019-02-01 |  |  | No |  |  | Not Required
20INR0255 | Dawn Solar | SS Started, FIS Started, No IA | Renegade Renewable LLC | Tap 345kV 79502 Windmill - 79504 AJ Swope | Deaf Smith | PANHANDLE | 2021-12-21 | SOL | PV | 514 |  | 2019-02-26 |  | 2019-02-07 |  |  | No |  |  | Not Required
20INR0260 | Gulf Wind 2 Expansion | SS Started, FIS Started, No IA | Texas GULF WIND 2 LLC | 80071 Zorillo 345kV | Kenedy | COASTAL | 2020-06-01 | WIN | WT | 47.9 | FIS Request | 2019-03-14 |  | 2019-03-26 15:39 |  |  | No |  |  | Not Required
20INR0261 | Kellam Solar | SS Started, FIS Started, No IA | BT Kellam Solar, LLC | Ben Wheeler | Van Zandt | NORTH | 2020-05-30 | SOL | PV | 100 |  | 2019-03-19 |  | 2019-03-13 |  |  | No |  |  | Not Required
20INR0262 | High Lonesome Wind Phase II | SS Started, FIS Started, No IA | HIGH LONESOME WIND POWER, LLC | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | WEST | 2020-01-30 | WIN | WT | 50.6 |  | 2019-03-25 |  | 2019-03-14 |  |  | No |  |  | Not Required
20INR0264 | Hale Wind 2 LLC | SS Started, FIS Started, No IA | NextEra Energy | 79506 Abernathy 345kV | Hale | PANHANDLE | 2020-12-01 | WIN | WT | 322 | FIS Request | 2019-04-03 |  | 2019-03-18 |  |  | No |  |  | Not Required
20INR0267 | Greens Bayou increase | SS Started, FIS Started, No IA | NRG Texas Power | 40715 Greens Bayou 138kV | Harris | HOUSTON | 2020-06-01 | GAS | GT | 140 | FIS Request | 2019-04-24 |  | 2019-04-23 |  |  | No
21INR0007 | Deepwater | SS Completed, FIS Started, No IA | AES | 40450 Deepwater 345kV | Harris | HOUSTON | 2021-04-30 | GAS | GT | 462.2 |  | 2017-12-05 | 2018-02-01 | 2017-12-05 |  |  | No
21INR0008 | Samson Solar | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2021-12-31 | SOL | PV | 200 |  | 2018-04-12 | 2018-06-12 | 2018-10-23 |  |  | No | Not Required | Not Required | Not Required
21INR0015 | Arroyo Del Bisonte Solar | SS Completed, FIS Started, No IA | Sunchase Power | tap 345kV 44005 WAP - 44040 Bailey or 44000 WAP - 44200 Hillje | Fort Bend | HOUSTON | 2021-04-01 | SOL | PV | 300 |  | 2018-05-09 | 2018-07-06 | 2018-08-21 |  |  | No | Not Required | Not Required | Not Required
21INR0016 | Danish Fields II | SS Completed, FIS Started, No IA | Sunchase Power | 44200 Hillje 345kV | Wharton | SOUTH | 2021-04-30 | SOL | PV | 200 |  | 2018-05-10 | 2018-07-11 | 2018-08-21 |  |  | No | Not Required | Not Required | Not Required
21INR0017 | Danish Fields III | SS Completed, FIS Started, No IA | Sunchase Power | 44200 Hillje 345kV | Wharton | SOUTH | 2021-06-30 | SOL | PV | 200 |  | 2018-05-10 | 2018-07-11 | 2018-08-27 |  |  | No | Not Required | Not Required | Not Required
21INR0019 | Zier Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 8252 Brackett - 78255 PintCr | Kinney | SOUTH | 2021-05-31 | SOL | PV | 120 |  | 2018-05-24 | 2018-07-20 | 2018-05-24 |  |  | No | Not Required | Not Required | Not Required
21INR0020 | El Zorro Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 80439 La Quinta - 8297 Bruni 138kV | Webb | SOUTH | 2021-02-01 | SOL | PV | 253.3 |  | 2018-06-29 | 2018-09-13 | 2018-06-29 |  |  | No | Not Required | Not Required | Not Required
21INR0021 | Green Holly Solar | SS Completed, FIS Started, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-08-01 | SOL | PV | 413.6 |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | No | Not Required | Not Required | Not Required
21INR0022 | Red Holly Solar | SS Completed, FIS Started, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-07-01 | SOL | PV | 260 |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | No | Not Required | Not Required | Not Required
21INR0024 | Samson Solar 2 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2021-12-31 | SOL | PV | 200 |  |  | 2018-06-12 | 2018-10-23 |  |  | No | Not Required | Not Required | Not Required
21INR0026 | Juno Solar | SS Completed, FIS Started, IA | Intersect Power | 59900 Long Draw 345kV | Borden | WEST | 2021-05-15 | SOL | PV | 495 |  | 2018-08-14 | 2018-10-25 | 2018-10-18 |  | 2018-12-28 | No | Not Required | Not Required | Not Required
21INR0027 | Zier Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 8252 Brackett - 78255 PintCr | Kinney | SOUTH | 2021-05-31 | OTH | BA | 60 |  | 2018-05-24 | 2018-07-20 | 2018-05-24 |  |  | No | Not Required | Not Required | Not Required
21INR0028 | El Zorro Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 80439 La Quinta - 8297 Bruni 138kV | Webb | SOUTH | 2021-02-01 | OTH | BA | 126.65 |  | 2018-06-29 | 2018-09-13 | 2018-06-29 |  |  | No | Not Required | Not Required | Not Required
21INR0029 | Green Holly Storage | SS Completed, FIS Started, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-08-01 | OTH | BA | 50 |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | No | Not Required | Not Required | Not Required
21INR0032 | Juno Storage | SS Completed, FIS Started, IA | Intersect Power | 59900 Long Draw 345kV | Borden | WEST | 2021-05-15 | OTH | BA | 495 |  | 2018-08-14 | 2018-10-25 | 2018-10-18 |  | 2018-12-28 | No | Not Required | Not Required | Not Required
21INR0033 | Red Holly Storage | SS Completed, FIS Started, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-07-01 | OTH | BA | 50 |  | 2018-09-27 | 2018-12-18 | 2018-12-11 |  |  | No | Not Required | Not Required | Not Required
21INR0201 | Brandon | SS Completed, FIS Started, No IA | Lubbock Power and Light | Brandon 69 kV | Lubbock | PANHANDLE | 2021-06-01 | GAS | GT | 21.5 |  | 2018-09-12 | 2018-09-12 | 2018-09-12 |  |  | No
21INR0202 | R Massengale | SS Completed, FIS Started, No IA | Lubbock Power and Light | MacKenzie 60 kV | Lubbock | PANHANDLE | 2021-06-01 | GAS | GT | 60 |  | 2018-09-12 | 2018-09-12 | 2018-09-12 |  |  | No
21INR0203 | Smithland Texas Solar | SS Completed, FIS Started, No IA | EDP RENEWABLES NORTH AMERICA LLC | tap 345kV 3687 Bell E - 39950 TNP One | Milam | SOUTH | 2021-12-31 | SOL | PV | 200.53 | FIS Request | 2018-10-10 | 2018-12-09 | 2019-04-23 13:28 |  |  | No |  |  | Not Required
21INR0204 | Lumina | SS Completed, FIS Started, No IA | IP Lumina, LLC | 11305 Dermott 345kV | Scurry | WEST | 2021-12-31 | SOL | PV | 313.2 |  | 2018-09-27 | 2018-11-08 | 2018-11-07 |  |  | No |  |  | Not Required
21INR0205 | Radian | SS Completed, FIS Started, No IA | IP Radian, LLC | 1444 Brown 345kV | Brown | NORTH | 2021-05-31 | SOL | PV | 313.2 | COD | 2018-09-27 | 2018-11-08 | 2018-11-07 |  |  | No | Not Required | Not Required | Not Required
21INR0206 | Elrond | SS Completed, FIS Started, No IA | IP Elrond, LLC | 6161 Paint Creek 138kV | Haskell | WEST | 2021-12-31 | SOL | PV | 313.2 |  | 2018-09-27 | 2018-11-14 | 2018-11-07 |  |  | No |  |  | Not Required
21INR0207 | Quantum | SS Completed, FIS Started, No IA | IP Quantum, LLC | 60515 Clear Crossing 345kV | Haskell | WEST | 2021-12-31 | SOL | PV | 313.2 |  | 2018-09-27 | 2018-11-14 | 2018-11-07 |  |  | No |  |  | Not Required
21INR0213 | Vancourt | SS Completed, FIS Started, No IA | Rayos Del Sol II Solar Project, LLC | tap 138kV 80103 Rangerville - 8554 Mesquite | Cameron | COASTAL | 2021-12-31 | SOL | PV | 50 |  | 2018-11-07 | 2018-12-12 | 2018-11-07 |  |  | No |  |  | Not Required
21INR0214 | Prickly Pear | SS Completed, FIS Started, No IA | EnergieKontor US TEXAS SP 13 LLC | 6500 Live Oak 138kV | Schleicher | WEST | 2021-12-31 | SOL | PV | 102.5 | FIS Request | 2018-11-07 | 2018-12-11 | 2019-04-25 11:44 |  |  | No |  |  | Not Required
21INR0217 | Spectrum | SS Completed, FIS Started, No IA | IP Spectrum, LLC | 1440 Comanche 345kV | Comanche | NORTH | 2022-05-31 | SOL | PV | 400 | COD | 2018-11-07 | 2018-12-20 | 2019-02-05 |  |  | No |  |  | Not Required
21INR0220 | Maleza Solar | SS Completed, FIS Started, No IA | Brush Solar LLC | tap 345kV 44200 Hillje - 44040 Bailey | Fort Bend | HOUSTON | 2021-06-01 | SOL | PV | 250 |  | 2018-12-06 | 2019-01-18 |  |  |  | No |  |  | Not Required
21INR0229 | Prospero Solar II | SS Completed, FIS Started, No IA | Sungold Renewables, LLC | 79650 Clearfork 345kV + 10 mile gen-tie | Andrews | WEST | 2021-07-01 | SOL | PV | 250 |  | 2018-11-29 | 2019-02-12 | 2018-12-10 |  |  | No |  |  | Not Required
21INR0232 | Cowboy Solar | SS Completed, FIS Started, No IA | AP Solar Holdings LLC | tap 138kV 5827 Moore - 5885 Downie | Frio | SOUTH | 2021-01-01 | SOL | PV | 152.49 |  | 2018-12-07 | 2019-01-11 | 2018-12-07 |  |  | No | Not Required | Not Required | Not Required
21INR0233 | Taygete II Solar | SS Completed, FIS Started, IA | TAYGETE ENERGY PROJECT LLC | 60393 Pig Creek 138kV | Pecos | WEST | 2021-02-01 | SOL | PV | 256.25 |  | 2018-12-17 | 2019-01-15 | 2018-12-13 |  | 2019-03-27 | No | Not Required | Not Required | Not Required
21INR0237 | Space City Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2021-12-01 | SOL | PV | 300 | FIS Request | 2019-01-04 | 2019-03-19 | 2019-04-26 |  |  | No | Not Required | Not Required | Not Required
21INR0236 | Osprey1 | SS Completed, FIS Started, No IA | Alta Power LLC | 8503 Alice 138kV | Jim Wells | SOUTH | 2021-04-01 | GAS | GT | 150 |  | 2018-12-17 | 2019-03-12 | 2018-12-13 |  |  | No
21INR0240 | La Casa Wind | SS Completed, FIS Started, No IA | EC&R development, LLC | tap 138kV 1618 Caddo - 1619 Colony Creek | Stephens | NORTH | 2021-12-15 | WIN | WT | 201 |  | 2018-12-28 | 2019-03-12 | 2018-12-29 |  |  | No |  |  | Not Required
21INR0244 | Madero Grid | SS Completed, FIS Started, No IA | Madero Grid | 8824 Railroad 138kV | Hidalgo | SOUTH | 2021-05-31 | OTH | BA | 201.96 |  | 2018-12-20 | 2019-03-12 | 2018-12-19 |  |  | No | Not Required | Not Required | Not Required
21INR0247 | Anson Solar Center, Phase III | SS Completed, FIS Started, No IA | Anson Solar Center, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2021-06-01 | SOL | PV | 200 |  | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  | No |  |  | Not Required
21INR0257 | Mercury Solar | SS Started, FIS Started, No IA | Mercury Solar, LLC | 68090 Sam Sw 345kV | Hill | NORTH | 2021-12-01 | SOL | PV | 201.6 |  | 2019-02-14 |  | 2019-02-07 |  |  | No | Not Required | Not Required | Not Required
21INR0258 | Mercury Storage | SS Started, FIS Started, No IA | Mercury Storage, LLC | 68090 Sam Sw 345kV | Hill | NORTH | 2021-12-01 | OTH | BA | 205.9 |  | 2019-02-14 |  | 2019-02-07 |  |  | No | Not Required | Not Required | Not Required
21INR0259 | Sunshine Solar | SS Completed, FIS Started, No IA | Sunshine Energy LLC | tap 138kV 8125 Lolita - 8172 Victoria | Victoria | SOUTH | 2021-03-31 | SOL | PV | 172.83 |  | 2019-02-14 | 2019-03-29 | 2019-02-08 |  |  | No |  |  | Not Required
21INR0260 | Chariot Storage | SS Started, FIS Started, No IA | Chariot Storage LLC | 99 Ben Hur 69kV | Limestone | NORTH | 2021-06-18 | OTH | BA | 47.12 |  | 2019-03-06 |  | 2019-02-11 |  |  | No | Not Required | Not Required | Not Required
21INR0261 | Horizon Solar | SS Started, FIS Started, No IA | First Solar Development, LLC | tap 138kV 5895 Pearsall - 5827 Moore | Frio | SOUTH | 2021-12-31 | SOL | PV | 204.09 |  | 2019-03-05 |  | 2019-03-01 |  |  | No |  |  | Not Required
21INR0262 | King Mountain Storage | SS Started, FIS Started, No IA | King Mountain Storage LLC | tap 345kV 11028 Odessa - 76000 North McCamey 345kV | Upton | WEST | 2021-12-01 | OTH | BA | 205.9 |  | 2019-03-25 |  | 2019-02-14 |  |  | No |  |  | Not Required
21INR0265 | Sisters Solar | SS Completed, FIS Started, No IA | Oberon Solar LLC | tap 345kV 1018 Moss - 11084 Riverton | Ector | WEST | 2021-06-01 | SOL | PV | 1219.23 |  | 2019-02-28 | 2019-03-29 | 2019-02-20 |  |  | No | Not Required | Not Required | Not Required
21INR0268 | Greyhound Solar | SS Started, FIS Started, No IA | Rockhound Solar 2, LLC dba "Greyhound Solar" | tap 345kV 11028 Odessa - 1018 Moss | Ector | WEST | 2021-06-30 | SOL | PV | 740 |  | 2019-03-28 |  | 2019-03-21 |  |  | No |  |  | Not Required
21INR0276 | Elara Solar | SS Started, FIS Started, No IA | Elara Energy Project, LLC | 5866 PaloduroSw 138kV | Frio | SOUTH | 2021-05-01 | SOL | PV | 205 |  | 2019-03-26 |  | 2019-03-15 |  |  | No | Not Required | Not Required | Not Required
21INR0278 | Fighting Jays Solar | SS Started, FIS Started, No IA | AP Solar Holdings, LLC | tap 345kV 44000 WA Parish - 44200 Hillje | Fort Bend | HOUSTON | 2021-05-01 | SOL | PV | 356.55 |  | 2019-03-26 |  | 2019-03-20 |  |  | No |  |  | Not Required
21INR0280 | Edgewater Storage | SS Started, FIS Started, No IA | Edgewater Battery Storage LLC | 210 Reagor Springs 69kV | Ellis | NORTH | 2021-06-28 | OTH | BA | 47.12 | FIS Request | 2019-04-08 |  | 2019-03-24 |  |  | No | Not Required | Not Required | Not Required
21INR0281 | Byrd Ranch Storage | SS Started, FIS Started, No IA | Byrd Ranch Storage LLC | 39700 TNSweeny 138kV | Brazoria | COASTAL | 2021-06-18 | OTH | BA | 47.12 | FIS Request | 2019-04-08 |  | 2019-03-24 |  |  | No | Not Required | Not Required | Not Required
21INR0283 | Sun Valley 2 | SS Started, FIS Started, No IA | Sun Valley Solar LLC | tap 345kV 68090 Sam Sw - 3405 or 13405 Tradinghouse | Hill | NORTH | 2021-12-01 | SOL | PV | 115 | FIS Request | 2019-03-29 |  | 2019-04-09 06:44 |  |  | No |  |  | Not Required
21INR0322 | Fronton Solar | SS Started, FIS Started, No IA | Thomason Construction LLC | 8795 Roma 138kV | Starr | SOUTH | 2021-01-31 | SOL | PV | 200 | FIS Request | 2019-04-25 |  | 2019-04-25 |  |  | No |  |  | Not Required
22INR0001 | Samson Solar 3 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2022-12-31 | SOL | PV | 200 |  |  | 2018-06-12 | 2018-10-23 |  |  | No | Not Required | Not Required | Not Required
22INR0201 | M-Bar Solar | SS Completed, FIS Started, No IA | M-Bar Solar Facility | 1141 Holt 138kV | Andrews | WEST | 2020-07-01 | SOL | PV | 200 |  | 2018-12-10 | 2019-01-15 | 2018-12-10 |  |  | No |  |  | Not Required
22INR0205 | Inverter Field Solar | SS Completed, FIS Started, No IA | CG Wharton County LLC | Tap 138kV 44190 East Bernard - 44130 Caney | Wharton | SOUTH | 2021-06-01 | SOL | PV | 175 | FIS Request | 2019-01-03 | 2019-03-13 | 2019-03-29 |  |  | No | Not Required | Not Required | Not Required
22INR0206 | Inverter Field Storage | SS Completed, FIS Started, No IA | CG WHARTON COUNTY LLC | Tap 138kV 44190 East Bernard - 44130 Caney | Wharton | SOUTH | 2021-06-01 | OTH | BA | 80 | FIS Request | 2019-01-03 | 2019-03-13 | 2019-04-30 13:25 |  |  | No | Not Required | Not Required | Not Required
22INR0213 | Dexter Solar | SS Started, FIS Started, No IA | 241BB 8me LLC | tap 345kV 60040 Bluff Creek - 6444 Red Creek | Runnels | WEST | 2022-06-01 | SOL | PV | 330.12 |  | 2019-03-05 |  | 2019-02-18 |  |  | No | Not Required | Not Required | Not Required

## GINR Trends
GINR Trends
Reflects all projects for which a Security Screening Study has been requested.
Nameplate capacity will change across time due to additional projects, cancelations, expirations, adjustments from study results, and projects being placed into service.
| Year | Month | Total Projects | Project Count | [5 empty] | Project Capacity (MW)
|  |  |  | GINR milestones | [5 empty] | Fuel Type
|  |  |  | Initial Screening Study | Screening Study Complete | In Full Study | Completed Full Study | Signed Interconnection Agreement | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Battery | Other
| 2016 | Apr | 241 | 8 | 12 | 111 | 11 | 99 | 5 | 24951 | 7762 | 22982 | 0 | 240 | 0 | 30 | 614
| 2016 | May | 236 | 4 | 16 | 108 | 8 | 100 | 9 | 25304 | 7414 | 23149 | 0 | 240 | 0 | 30 | 614
| 2016 | Jun | 232 | 12 | 14 | 104 | 8 | 94 | 8 | 25215 | 8321 | 22471 | 0 | 240 | 0 | 30 | 614
| 2016 | Jul | 231 | 13 | 16 | 98 | 7 | 96 | 7 | 25215 | 8321 | 22304 | 0 | 240 | 0 | 30 | 614
| 2016 | Aug | 235 | 17 | 24 | 88 | 6 | 100 | 5 | 25895 | 9538 | 21077 | 0 | 240 | 0 | 30 | 664
| 2016 | Sep | 226 | 10 | 22 | 90 | 6 | 98 | 7 | 25254 | 9391 | 19671 | 0 | 240 | 0 | 30 | 664
| 2016 | Oct | 250 | 16 | 27 | 93 | 6 | 99 | 2 | 26643 | 12439 | 19771 | 0 | 240 | 0 | 30 | 644
| 2016 | Nov | 247 | 18 | 31 | 98 | 3 | 98 | 3 | 26643 | 12439 | 19771 | 0 | 240 | 0 | 30 | 644
| 2016 | Dec | 254 | 23 | 33 | 103 | 2 | 96 | 4 | 26732 | 13724 | 18816 | 0 | 240 | 0 | 30 | 594
| 2017 | Jan | 257 | 16 | 36 | 105 | 4 | 96 | 2 | 26270 | 14498 | 18816 | 0 | 240 | 0 | 30 | 594
| 2017 | Feb | 263 | 8 | 33 | 127 | 2 | 93 | 5 | 26512 | 14958 | 19016 | 0 | 240 | 0 | 30 | 0
| 2017 | Mar | 264 | 11 | 27 | 131 | 3 | 92 | 3 | 26593 | 15338 | 16750 | 0 | 240 | 0 | 0 | 0
| 2017 | Apr | 284 | 28 | 28 | 136 | 3 | 89 | 5 | 28470 | 17054 | 19316 | 0 | 240 | 0 | 0 | 0
| 2017 | May | 287 | 23 | 35 | 139 | 3 | 87 | 4 | 28259 | 18012 | 17620 | 0 | 240 | 0 | 0 | 0
| 2017 | Jun | 320 | 33 | 45 | 154 | 3 | 85 | 4 | 31835 | 22275 | 15656 | 0 | 240 | 0 | 30 | 0
| 2017 | Jul | 323 | 38 | 44 | 155 | 3 | 83 | 7 | 30279 | 21974 | 15656 | 0 | 0 | 0 | 30 | 0
| 2017 | Aug | 333 | 32 | 61 | 155 | 5 | 80 | 11 | 30068 | 23814 | 14357 | 0 | 0 | 0 | 0 | 0
| 2017 | Sep | 336 | 35 | 60 | 157 | 5 | 79 | 18 | 29915 | 24089 | 12001 | 0 | 0 | 0 | 0 | 0
| 2017 | Oct | 339 | 25 | 66 | 163 | 9 | 76 | 6 | 30090 | 24729 | 14201 | 0 | 0 | 0 | 0 | 0
| 2017 | Nov | 340 | 14 | 64 | 172 | 15 | 75 | 17 | 29882 | 24893 | 13747 | 0 | 0 | 0 | 0 | 0
| 2017 | Dec | 337 | 7 | 57 | 166 | 19 | 73 | 8 | 30198 | 24123 | 13969 | 0 | 0 | 0 | 30 | 0
| 2018 | Jan | 335 | 15 | 56 | 169 | 21 | 74 | 17 | 31420 | 22739 | 12768 | 0 | 0 | 0 | 0 | 0
| 2018 | Feb | 334 | 11 | 46 | 177 | 27 | 73 | 9 | 32258 | 22413 | 12727 | 0 | 0 | 0 | 0 | 0
| 2018 | Mar | 340 | 14 | 41 | 179 | 27 | 79 | 8 | 32897 | 23515 | 12065 | 0 | 0 | 0 | 0 | 0
| 2018 | Apr | 349 | 18 | 48 | 172 | 30 | 81 | 4 | 33427 | 24709 | 13484 | 0 | 0 | 0 | 0 | 0
| 2018 | May | 369 | 33 | 36 | 180 | 34 | 86 | 13 | 33799 | 27766 | 13442 | 0 | 0 | 0 | 200 | 0
| 2018 | Jun | 379 | 32 | 42 | 190 | 27 | 88 | 6 | 34376 | 28448 | 13674 | 0 | 0 | 0 | 522 | 0
| 2018 | Jul | 404 | 34 | 60 | 197 | 25 | 88 | 6 | 37708 | 30518 | 11668 | 0 | 0 | 0 | 522 | 0
| 2018 | Aug | 417 | 26 | 57 | 220 | 26 | 88 | 11 | 40851 | 29649 | 10814 | 0 | 0 | 0 | 2177 | 0
| 2018 | Sep | 426 | 30 | 67 | 212 | 26 | 91 | 15 | 40327.45 | 31655.3 | 8589.6 | 0 | 0 | 0 | 1889 | 0
| 2018 | Oct | 429 | 26 | 60 | 221 | 24 | 98 | 4 | 40237.59 | 32248.91 | 9073.6 | 0 | 0 | 0 | 1889 | 0
| 2018 | Nov | 443 | 23 | 59 | 235 | 26 | 100 | 7 | 40283.09 | 36682.4 | 7503.4 | 0 | 0 | 0 | 2048.35 | 0
| 2018 | Dec | 465 | 31 | 67 | 237 | 27 | 103 | 9 | 39596.45 | 40732.49 | 9249.4 | 0 | 0 | 0 | 2342.82 | 0
| 2019 | Jan | 489 | 43 | 69 | 244 | 26 | 107 | 20 | 39222.25 | 43504.49 | 10824.6 | 0 | 45 | 0 | 3147.38 | 0
| 2019 | Feb | 493 | 38 | 70 | 246 | 24 | 115 | 12 | 37419.7 | 47140.55 | 10528.6 | 0 | 45 | 0 | 3011.92 | 300
| 2019 | Mar | 505 | 42 | 68 | 247 | 33 | 115 | 18 | 35555.28 | 50999.9 | 10536.6 | 0 | 45 | 0 | 3265.2 | 441.8
| 2019 | Apr | 527 | 38 | 79 | 260 | 30 | 120 | 9 | 35644.28 | 54655.45 | 10102.6 | 0 | 45 | 0 | 3501.24 | 300
Note: Other contains all Fuel and Technology Types not in the Solar, Wind, Gas or Battery categories.

## data_GINR Trends_1 (hidden)
| # Initial Screening study | # Screening Study Complete | # in Full Study | # Completed Full Study | # Signed Interconnect Agreement | MW Capacity
Apr-18 | 18 | 48 | 172 | 30 | 81 | 71620
May-18 | 33 | 36 | 180 | 34 | 86 | 75207
Jun-18 | 32 | 42 | 190 | 27 | 88 | 77020
Jul-18 | 34 | 60 | 197 | 25 | 88 | 80416
Aug-18 | 26 | 57 | 220 | 26 | 88 | 83491
Sep-18 | 30 | 67 | 212 | 26 | 91 | 82461.35
Oct-18 | 26 | 60 | 221 | 24 | 98 | 83449.1
Nov-18 | 23 | 59 | 235 | 26 | 100 | 86517.24
Dec-18 | 31 | 67 | 237 | 27 | 103 | 91921.16
Jan-19 | 43 | 69 | 244 | 26 | 107 | 96743.72
Feb-19 | 38 | 70 | 246 | 24 | 115 | 98104.77
Mar-19 | 42 | 68 | 247 | 33 | 115 | 100836.78
Apr-19 | 38 | 79 | 260 | 30 | 120 | 104248.57

## data_GINR Trends_2 (hidden)
| MW Natural Gas | Nuclear | Coal | Wind | Solar | Biomass | Battery | Other | Total Project Count | Cancelled Project Count
Apr-18 | 13484 | 0 | 0 | 33427 | 24709 | 0 | 0 | 0 | 349 | 4
May-18 | 13442 | 0 | 0 | 33799 | 27766 | 0 | 200 | 0 | 369 | 13
Jun-18 | 13674 | 0 | 0 | 34376 | 28448 | 0 | 522 | 0 | 379 | 6
Jul-18 | 11668 | 0 | 0 | 37708 | 30518 | 0 | 522 | 0 | 404 | 6
Aug-18 | 10814 | 0 | 0 | 40851 | 29649 | 0 | 2177 | 0 | 417 | 11
Sep-18 | 8589.6 | 0 | 0 | 40327.45 | 31655.3 | 0 | 1889 | 0 | 426 | 15
Oct-18 | 9073.6 | 0 | 0 | 40237.59 | 32248.91 | 0 | 1889 | 0 | 429 | 4
Nov-18 | 7503.4 | 0 | 0 | 40283.09 | 36682.4 | 0 | 2048.35 | 0 | 443 | 7
Dec-18 | 9249.4 | 0 | 0 | 39596.45 | 40732.49 | 0 | 2342.82 | 0 | 465 | 9
Jan-19 | 10824.6 | 0 | 45 | 39222.25 | 43504.49 | 0 | 3147.38 | 0 | 489 | 20
Feb-19 | 10528.6 | 0 | 45 | 37419.7 | 47140.55 | 0 | 3011.92 | 300 | 493 | 12
Mar-19 | 10536.6 | 0 | 45 | 35555.28 | 50999.9 | 0 | 3265.2 | 441.8 | 505 | 18
Apr-19 | 10102.6 | 0 | 45 | 35644.28 | 54655.45 | 0 | 3501.24 | 300 | 527 | 9

## data_GINR Trends_3 (hidden)
|  | Gas | Wind | Solar | Battery | Other
COASTAL | 2019 | 664 | 1067.74
| 2020 | 363 | 2662.3 | 1699.6 | 107
| 2021 |  | 301.74 | 2034 | 297.37
| 2022 |  |  | 400
| 2023 |  |  | 200
HOUSTON | 2018 | 12
| 2019 | 11
| 2020 | 1831.6 |  | 540
| 2021 | 462.2 |  | 1056.55
| 2025 |  |  |  |  | 100
WEST | 2018 |  | 129
| 2019 |  | 4109.34 | 1123.6
| 2020 |  | 7429.95 | 10057.63 | 198.06
| 2021 | 742.9 | 3889.9 | 13335.48 | 1142.5
| 2022 | 742.9 |  | 980.12 | 125
NORTH | 2019 | 44 | -7.2 |  |  | 45
| 2020 | 984 | 1378.2 | 3326.55 | 310.12
| 2021 | 2157.5 | 2179.2 | 6016.29 | 415.14
| 2022 | 328 |  | 1500
| 2025 |  |  |  |  | 200
PANHANDLE | 2019 |  | 210 | 240.8
| 2020 |  | 3506.8 | 930.3
| 2021 | 81.5 | 1302.6 | 1725
| 2022 | 280 |  | 650
SOUTH | 2019 | 64 | 1746.2 | 200
| 2020 | 300 | 3890.91 | 3181.79 | 387.44
| 2021 | 1034 | 1847.6 | 5307.74 | 518.61
| 2022 |  |  | 150