## Contents
GIM Activity: Dec 01, 2023 to Dec 31, 2023
Table of Contents
Disclaimer and References | Disclaimer on the use of this report, and references to associated ERCOT Binding Documents ***Please read***
Acronyms | A list of the various acronyms used throughout the report
Summary | Tables that provide project aggregate counts and megawatt capacities by GIM phase and fuel type
Project Details - Large Gen | A table that list project details for Large Generators as defined in ERCOT Planning Guide Section 5.2.1(3); only include projects for which a Full Interconnection Study has been requested
Project Details - Small Gen | A table that list project details for Small Generators as defined in ERCOT Planning Guide 5.2.1(3); only include projects for which the Resource Registration form has been approved by ERCOT
GIM Trends | Charts and tables that show historical and projected interconnection study trends
Commissioning Update | A table listing project commissioning approval milestones met for the month: energization, synchronization, and commercial operations approval
Inactive Projects | A table listing Inactive projects
Cancellation Update | A table listing the projects cancelled for the month
Time of Report Run: Jan 1, 2024 8:00:41 AM

## Disclaimer and References
Generator Interconnection Status Report - Disclaimer
FOR PLANNING PURPOSES ONLY
This ERCOT Working Paper has been prepared for specific ERCOT and Market Participant purposes, and has been
developed from data provided by Interconnecting Entities and Transmission Service Providers that has been entered into the online RIOO system.
The data may contain errors or be obsolete depending on when the data was entered. ERCOT MAKES NO WARRANTY, EXPRESS
OR IMPLIED,INCLUDING ANY WARRANTY OF MERCHANTABILITY OR FITNESS FOR ANY PARTICULAR PURPOSE,
AND DISCLAIMS ANY AND ALL LIABILITY WITH RESPECT TO THE ACCURACY OF SAME OR THE FITNESS OR
APPROPRIATENESS OF SAME FOR ANY PARTICULAR USE. THIS ERCOT WORKING PAPER IS SUPPLIED WITH ALL FAULTS.
References
The links below provide more information on the ERCOT interconnection process:
http://www.ercot.com/mktrules/guides/planning/current
See the Resource Interconnection Handbook, available on ERCOT’s Resource Integration webpage:
http://www.ercot.com/services/rq/integration

## Acronyms
Acronyms
GIM = Generator Interconnection or Modification request
GINR = Generation Interconnection or Change Request
COD = Commercial Operation Date
SS = Security Screening Study
FIS = Full Interconnection Study
IA = Interconnection Agreement; can be either of the following:
- Standard Generation Interconnection Agreement (SGIA)
- Public financially binding agreement
- An official letter from a Municipally Owned Utility or Electric Cooperative signifying developer intent to build and operate generation facilities and
interconnect with the MOU or EC
POI = Point of lnterconnection
INR = Interconnection Request Number
TSP = Transmission Service Provider
NtP = Notice-to-Proceed given to the TSP for interconnection construction
CDR = Capacity, Demand and Reserves Report
SFS = Sufficient Financial Security provided to the TSP for construction of the interconnection facilities
QSA = Quarterly Stability Assessment
INA = Inactive status
PLN = Planned status
Fuel Types | Technology Types
BIO = Biomass | BA = Battery Energy Storage
COA = Coal | CC = Combined-Cycle
GAS = Gas | CE = Compressed Air Energy Storage
GEO = Geothermal | CP = Concentrated Solar Power
HYD = Hydrogen | EN = Energy Storage
NUC = Nuclear | FC = Fuel Cell
OIL = Fuel Oil | GT = Combustion (gas) Turbine, but not part of a Combined-Cycle
OTH = Other | HY = Hydroelectric Turbine
PET = Petcoke | IC = Internal Combustion Engine, eg. Reciprocating
SOL = Solar | OT = Other
WAT = Water | PV = Photovoltaic Solar
WIN = Wind | ST = Steam Turbine other than Combined-Cycle
WT = Wind Turbine

## Summary
Summary |  |  | Major GIM Milestone Status by Fuel/Technology Type, MW
Currently tracking 1671 generation interconnection or change requests as of Dec 31, 2023 |  |  | Includes only those (1) Large Generator projects for which a Screening Study has been requested, (2) Small Generators for which an interconnection request has been made, and (3) projects that are not Inactive
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  |  | Fuel | Technology | SS Started | SS Started | SS Completed | SS Completed | SS Completed | SS Started | SS Started | SS Completed | SS Completed | SS Completed | Small Generator | Small Generator | TOTAL
Includes only those (1) Large Generator projects for which a Screening Study has been requested, |  |  | Type | Type | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | Not Model Ready | Model Ready
(2) Small Generators for which an interconnection request has been made and |  |  |  |  | No IA | No IA | No IA | No IA | No IA | IA | IA | IA | IA | IA
and (3) projects that are not Inactive
Status of SS, FIS and IA | Project Count | % of Total | Gas | Combined-Cycle | 44.3 |  | 33 | 1350 | 11.3 |  |  |  | 697 | 146 | 3.1 | 3.1 | 2287.8
LARGE GENERATORS |  |  | Gas | Combustion Turbine | 1645.5 | 1952.75 | 3299 | 3483.85 | 753.68 |  |  |  | 94 | 716 |  |  | 11944.78
SS Started, FIS Not Started, No IA | 39 | 2.334% | Gas | Internal Combustion Engine |  |  |  | 218.4 | [5 empty] | 337.8 |  |  | 556.2
SS Started, FIS Started, No IA | 96 | 5.745% | Gas | Compressed Air Energy Storage
SS Completed, FIS Not Started, No IA | 116 | 6.942% | Gas | Steam Turbine |  |  |  | 680 | [5 empty] | 14 |  |  | 694
SS Completed, FIS Started, No IA | 878 | 52.54% | Gas | Fuel Cell
SS Completed, FIS Completed, No IA | 92 | 5.506% | Gas | Total gas | 1689.8 | 1952.75 | 3332 | 5732.25 | 764.98 |  |  |  | 791 | 1213.8 | 3.1 | 3.1 | 15482.78
SS Started, FIS Not Started, IA | 0 | 0% | Coal
SS Started, FIS Started, IA | 0 | 0% | Wind |  | 1700 | 1820.38 | 7845 | 13033.72 | 42.32 |  |  |  | 2222.21 | 7927.32 |  |  | 34590.95
SS Completed, FIS Not Started, IA | 3 | 0.2394% | Solar |  | 2487.08 | 5329.59 | 10415.81 | 72100.98 | 10369.19 |  |  | 812.44 | 16354.23 | 27749.59 | 17.99 | 17.12 | 145654.02
SS Completed, FIS Started, IA | 122 | 7.301% | Biomass | [5 empty] | 53 | [7 empty] | 53
SS Completed, FIS Completed, IA | 254 | 15.26% | Other | Battery | 3545.7 | 11131.23 | 7444.93 | 78887.87 | 7887.18 |  |  |  | 8209.14 | 9351.85 | 366.93 | 242.9 | 127067.73
SMALL GENERATORS |  |  | Other* |  |  | 150 | 785 | 1432 | [8 empty] | 2367
Not Model Ready* | 41 | 2.454% | TOTAL |  | 9422.58 | 20383.95 | 29822.74 | 171186.82 | 19116.67 | 0 | 0 | 812.44 | 27576.58 | 46242.56 | 388.02 | 263.12 | 325215.48
Model Ready* | 28 | 1.676% | * Other includes petroleum coke (pet coke), hydroelectric, fuel oil, geothermal energy, other miscellaneous fuels reported by developers, and fuel cells that use fuels other than natural gas.
Total Interconnection Requests | 1671
Inactive (since last month) | 3
Cancelled (since last month) | 10
Capacity, MW
Total Capacity Under Study | 325215.48
Interconnection Agreements Executed | 75364.18
Inactive (since last month) | 260.99
Inactive changed to Planned (since last month) | 983.22
Inactive changed to Cancelled (since last month) | 0
Cancelled (since last month) | 1419.51
* "Not Model Ready" means that a Small Generator's data has not yet been loaded into the Network
Operations Model. "Model Ready" means that the data has been loaded into the NOM, and the Resource is
ready to begin the commissioning process.

## Project Details - Large Gen
GIM Project Details - Large Generators
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study has been requested are included.
Excludes projects that have a status of Inactive (status = INA).
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GIM system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not been obtained or reported to ERCOT yet.
A developer may split a project into two or more additional projects with different INR numbers during the interconnection request process. Due to current RIOO interface limitations,
the new projects do not inherit certain milestone dates entered for the original project. As a result, dates may be blank even though the milestones have been met.
A “1-1-1900” date is used to signify that an actual date for a project milestone is not available. This typically occurs for project data migrated from the legacy GINR database to the RIOO system.
Project Attributes | [10 empty] | Changes from Last Report | GIM Project Milestone Dates
INR | Project Name | GIM Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | Economic Study Required | IA Signed |  | Air Permit | GHG Permit | Water Availability | Meets Planning | Meets All Planning |  | Construction Start | Construction End | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Change indicators: Proj Name, MW | Approval Date for | [6 empty] | Financial Security |  |  |  | Guide Section 6.9(1) | Guide Section 6.9 | Meets Planning Guide
[11 empty] | Size, COD, SFS/NtP, FIS Request, | Submission of Proof of | [6 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[11 empty] | Status Change INA-to-PLN | Site Control | [6 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[23 empty] | Models | Models
14INR0033 | Goodnight Wind | SS Completed, FIS Completed, IA | FGE Goodnight I, LLC | tap 345kV 79500 Alibates - 79503 Tule Canyon CKT2 | Armstrong | PANHANDLE | 2024-02-14 | WIN | WT | 258.1 |  | 1899-12-31 | 2012-07-24 | 2012-09-19 | 2013-03-04 | 2023-02-06 | No | 2019-08-18 | Yes | Not Required | Not Required | Not Required | 2023-05-01 | 2023-05-01 | 2023-05-01 |  |  | 2023-11-15 | 2023-11-21
15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2024-01-31 | WIN | WT | 162.1 |  |  | 2013-11-27 | 2014-01-27 | 2014-04-15 | 2017-09-27 | No | 2018-05-30 | Yes | Not Required | Not Required | Not Required | 2018-05-30 | 2018-09-19 | 2019-01-22 |  |  | 2020-02-10 | 2020-05-12
16INR0049 | Nazareth Solar | SS Completed, FIS Completed, IA | TX Nazareth Solar, LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala C2 | Castro | PANHANDLE | 2025-03-24 | SOL | PV | 204 |  | 2014-07-07 | 2014-06-19 | 2014-07-25 | 2014-07-01 | 2023-04-17 | No | 2023-06-07 | Yes | Not Required | Not Required | Not Required
16INR0081 | Mesteno Wind | SS Completed, FIS Completed, IA | Mesteno Windpower, LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2024-03-31 | WIN | WT | 201.6 | COD | 1899-12-31 | 2014-12-30 | 2015-03-09 | 2014-12-30 | 2018-01-29 | No | 2018-04-25 | Yes | Not Required | Not Required | Not Required | 2018-04-25 | 2019-03-28 | 2019-04-01 |  |  | 2019-11-26 | 2019-12-12
16INR0085 | Priddy Wind | SS Completed, FIS Completed, IA | ENGIE North America | tap 345kV 1444 Brown – 3422 Killeen | Mills | NORTH | 2023-12-30 | WIN | WT | 302.4 |  | 2015-03-06 | 2015-01-14 | 2015-02-10 | 2015-03-06 | 2021-04-30 | No | 2020-08-13 | Yes | Not Required | Not Required | Not Required | 2021-03-29 | 2021-04-30 | 2021-04-30 |  |  | 2021-10-13 | 2021-11-19
16INR0104 | Big Sampson Wind | SS Completed, FIS Started, IA | Big Sampson Wind Project, LLC | tap 345kV 76015 Cedar Canyon - 7053 Noelke | Crockett | WEST | 2025-10-04 | WIN | WT | 400 |  |  | 2015-05-11 | 2015-06-17 | 2015-05-11 |  | No | 2019-11-08 | No | Not Required | Not Required | Not Required
16INR0112 | Loma Pinta Wind | SS Completed, FIS Started, IA | Enerverse | 5705 Fowlerton 138kV | La Salle | SOUTH | 2025-03-31 | WIN | WT | 197.01 |  |  | 2015-05-18 | 2015-07-02 | 2015-05-18 |  | No | 2017-12-13 | No | Not Required | Not Required | Not Required
17INR0027b | Coyote Wind | SS Completed, FIS Completed, IA | Coyote Wind | 11305 Dermott 345kV | Scurry | WEST | 2023-12-15 | WIN | WT | 242.6 |  |  | 2015-04-22 | 2015-05-22 | 2015-06-11 | 2020-01-31 | No | 2016-08-09 | Yes | Not Required | Not Required | Not Required | 2016-08-09 | 2020-01-28 | 2020-01-31 |  |  | 2020-08-24 | 2020-11-25
17INR0052 | Horse13 CallD repower | SS Completed, FIS Completed, IA | Nextera | 6216 Bluff Creek 138kV | Taylor | WEST | 2023-12-31 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2018-04-10 | No | 2019-05-22 | Yes | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13 |  |  |  | 2021-03-16
17INR0053 | HHGT repower Horse13+CallD | SS Completed, FIS Completed, IA | Nextera | 7046 Kendal 345kV | Taylor | WEST | 2023-12-31 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2017-07-06 | No | 2009-06-26 | No | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13 |  |  |  | 2021-09-10
17INR0054 | Capricorn I & III repower | SS Completed, FIS Completed, IA | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WEST | 2022-07-30 | WIN | WT | 32 |  | 2017-03-09 | 2017-03-09 | 2017-04-24 | 2017-03-09 | 2018-02-26 | No | 2006-11-14 | No | Not Required | Not Required | Not Required | 2021-02-28 | 2021-02-28 | 2021-02-28 |  |  |  | 2021-03-04
17INR0061 | Capricorn IV repower | SS Completed, FIS Completed, IA | Nextera | 76090 Divide 345kV | Sterling | WEST | 2022-05-31 | WIN | WT | 9 |  | 2017-08-23 | 2017-08-23 | 2017-09-15 | 2017-08-23 | 2018-02-06 | No | 2008-01-15 | No | Not Required | Not Required | Not Required | 2020-08-28 | 2020-08-28 | 2018-03-30 |  |  |  | 2020-08-19
17INR0068 | Sweetwater 2 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2024-01-31 | WIN | WT | 7.3 |  | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-11-10 | No | 2003-06-27 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2017-12-20
17INR0069 | Trent repower | SS Completed, FIS Completed, IA | TRENT WIND FARM LLC | 1338 Eskota 138kV | Nolan | WEST | 2024-12-31 | WIN | WT | 6.4 |  | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-03-01 | No | 2018-10-19 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-05-09
17INR0070 | Desert Sky repower | SS Completed, FIS Completed, IA | DESERT SKY WIND FARM LLC | two LCRA 138kV | Pecos | WEST | 2023-05-16 | WIN | WT | 7.2 |  | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-02-06 | No | 2018-10-18 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-09-06
18INR0030 | Canyon Wind | SS Completed, FIS Completed, IA | Canyon Wind Energy, LLC | 11319 SCOSW ScurryCounty 138kV | Scurry | WEST | 2024-05-03 | WIN | WT | 308.82 |  | 2017-03-02 | 2016-05-09 | 2016-07-22 | 2017-03-02 | 2023-03-27 | No | 2018-09-20 | Yes | Not Required | Not Required | Not Required | 2020-02-07 | 2023-04-28 | 2023-05-01 |  |  | 2023-11-15 | 2023-12-01
18INR0031 | Maryneal Wind | SS Completed, FIS Completed, IA | Maryneal Windpower, LLC | 71050 Bitter Creek 345kV | Nolan | WEST | 2024-03-31 | WIN | WT | 182.4 | COD | 2016-07-22 | 2016-05-26 | 2016-07-21 | 2016-07-22 | 2020-01-31 | No | 2020-01-31 | Yes | Not Required | Not Required | Not Required | 2020-01-31 | 2020-01-31 | 2020-01-31 |  |  | 2021-01-08 | 2021-04-23
18INR0043 | Lacy Creek wind | SS Completed, FIS Completed, IA | Lacy Creek Wind, LLC | 59907 Bernoulli 345kV | Glasscock | WEST | 2024-01-31 | WIN | WT | 301.3 |  | 2017-02-01 | 2016-10-26 | 2016-12-22 | 2017-02-01 | 2021-11-04 | Yes | 2017-09-28 | Yes | Not Required | Not Required | Not Required | 2022-04-21 | 2022-04-21 | 2022-04-21 |  |  | 2022-11-07 | 2022-12-01
18INR0058 | Texana Solar | SS Completed, FIS Completed, IA | Sunchase Power | 8675 TEXNAPOI4A 138kV | Wharton | SOUTH | 2024-11-27 | SOL | PV | 152.34 |  | 2017-03-22 | 2016-12-23 | 2017-02-14 | 2017-03-22 | 2020-12-01 | No | 2021-06-30 | Yes | Not Required | Not Required | Not Required | 2022-11-03
18INR0064 | Silver Star repower | SS Completed, FIS Completed, IA | Silver Star I Power Partners, LLC | 1642 Flat Creek 138kV | Eastland | NORTH | 2023-12-30 | WIN | WT | -7.2 | COD | 2017-07-06 | 2017-04-05 | 2017-05-08 | 2017-07-06 | 2018-04-26 | No | 2018-10-16 | Yes | Not Required | Not Required | Not Required | 2019-10-23 | 2019-10-23 | 2019-10-28 |  |  |  | 2020-07-28
18INR0069 | Indian Mesa repower | SS Completed, FIS Completed, IA | Nextera | 76019 Indian NWP 138kV | Pecos | WEST | 2023-12-31 | WIN | WT | 82.5 |  | 2018-05-22 | 2018-05-22 | 1899-12-31 | 2018-05-22 | 2018-10-03 | No | 2018-12-04 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2018-11-02
18INR0073 | Sweetwater 1 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2024-01-31 | WIN | WT | 3 |  | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-12-27 | No | 2002-10-23 | No | Not Required | Not Required | Not Required
18INR0079 | Woodward I repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2023-12-31 | WIN | WT | 0 |  | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2019-01-09 | No | 2018-12-12 | Yes | Not Required | Not Required | Not Required | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2019-11-07 | 2019-11-13
18INR0080 | Woodward 2 repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2023-12-31 | WIN | WT | 0 |  | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-11-27 | No | 2018-12-18 | Yes | Not Required | Not Required | Not Required | 2018-11-29 | 2018-11-29 | 2020-10-30 |  |  |  | 2018-12-19
19INR0001 | Texas Solar Nova | SS Completed, FIS Completed, IA | TEXAS SOLAR NOVA 1, LLC | 138kV 59909 WETT Nova Prime | Kent | WEST | 2024-02-13 | SOL | PV | 253.51 | COD | 2016-07-06 | 2015-11-17 | 2015-12-30 | 2016-07-06 | 2022-06-03 | No | 2019-06-28 | Yes | Not Required | Not Required | Not Required | 2019-11-08 | 2022-06-28 | 2022-08-03 |  |  | 2023-04-12 | 2023-05-09
19INR0002 | Grandfalls Solar | SS Completed, FIS Started, No IA | Nextera | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | WEST | 2027-07-01 | SOL | PV | 178 |  | 2016-05-24 | 2016-05-24 | 2016-06-06 | 2016-05-24 |  |  |  | No | Not Required | Not Required | Not Required
19INR0022 | Monte Alto I | SS Completed, FIS Started, IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2025-12-01 | WIN | WT | 189 |  |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  | No | 2020-02-13 | Yes | Not Required | Not Required | Not Required
19INR0023 | Monte Alto 2 Wind | SS Completed, FIS Started, IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2025-12-01 | WIN | WT | 272.76 |  |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  | No | 2022-03-22 | Yes | Not Required | Not Required | Not Required
19INR0026 | Holstein 2 Solar | SS Completed, FIS Started, No IA | 229HD 8me LLC | 11406 Central Bluff 345kV | Nolan | WEST | 2026-05-01 | SOL | PV | 101.7 |  | 2017-02-13 | 2016-12-21 | 2017-02-02 | 2017-02-13 |  |  |  | No | Not Required | Not Required | Not Required
19INR0035 | Norton Solar | SS Completed, FIS Completed, IA | TAI Norton Solar, LLC | 60451 Garnet 138kV | Runnels | WEST | 2025-10-01 | SOL | PV | 125 |  | 2017-11-08 | 2017-03-06 | 2017-04-20 | 2017-11-08 | 2023-05-04 | No | 2019-06-20 | Yes | Not Required | Not Required | Not Required | 2019-07-12 | 2023-05-30
19INR0041 | Myrtle Solar | SS Completed, FIS Completed, IA | Myrtle Solar, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2024-01-31 | SOL | PV | 321.2 | COD |  | 2017-03-15 | 2017-04-28 | 2017-05-09 | 2022-01-25 |  | 2019-11-13 | Yes | Not Required | Not Required | Not Required | 2019-11-30 | 2020-05-06 | 2022-02-01 |  |  | 2022-12-07 | 2022-12-20
19INR0042 | Long Point Solar | SS Completed, FIS Started, IA | Long Point Solar, LLC | 138 KV (CEHE Sub) Tap Burke (42410) - Eagle Nest (42430) ckt 02 | Brazoria | COASTAL | 2025-12-31 | SOL | PV | 101.25 |  | 2017-11-02 | 2017-03-15 | 2017-04-20 | 2017-11-13 |  |  | 2019-10-24 | No | Not Required | Not Required | Not Required |  |  |  | 2024-10-15 | 2025-10-30
19INR0054 | Monte Cristo 1 Wind | SS Completed, FIS Started, IA | Terra-Gen | tap 345kV #8574 Pomelo - #8383 North Edinburg ckt 2 | Hidalgo | SOUTH | 2025-09-30 | WIN | WT | 236.9 |  | 2017-07-28 | 2017-04-11 | 2017-05-03 | 2017-07-28 |  | No | 2023-05-09 | Yes | Not Required | Not Required | Not Required | 2023-08-18
19INR0055 | Monte Cristo 2 Wind | SS Completed, FIS Started, No IA | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | SOUTH | 2025-09-30 | WIN | WT | 236.9 | COD | 2017-07-28 | 2017-04-11 | 2017-05-03 | 2017-07-28 |  |  |  | No | Not Required | Not Required | Not Required
19INR0075 | Horseshoe Bend Solar | SS Completed, FIS Started, No IA | Clenera | 1444 Brown 345kV | Brown | NORTH | 2025-05-31 | SOL | PV | 301.1 |  | 2018-02-09 | 2017-06-23 | 2017-08-07 | 2018-02-09 |  | No |  | No | Not Required | Not Required | Not Required
19INR0080 | Whitehorse Wind | SS Completed, FIS Completed, IA | MESQUITE STAR SPECIAL LLC | 68001 Clayton 345kV | Fisher | WEST | 2024-03-31 | WIN | WT | 418.9 | COD |  | 2017-06-23 | 2017-08-07 | 2018-02-16 | 2019-01-22 | No | 2018-12-05 | Yes | Not Required | Not Required | Not Required | 2019-03-12 | 2019-04-02 | 2019-05-01 |  |  | 2019-12-12 | 2019-12-27
19INR0085 | Blue Jay Solar | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2023-12-31 | SOL | PV | 141.05 | COD | 2018-02-15 | 2017-05-30 | 2017-08-11 | 2018-02-15 | 2021-04-26 | No | 2020-10-26 | Yes | Not Required | Not Required | Not Required | 2020-12-02 | 2021-04-26 | 2021-04-29 |  |  | 2021-11-11 | 2022-06-28
19INR0100 | Prairie Hill Wind | SS Completed, FIS Completed, IA | Prairie Hill LLC | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | McLennan | NORTH | 2023-12-30 | WIN | WT | 300 |  | 2017-06-19 | 2017-06-19 | 2017-08-11 | 2017-06-19 | 2020-04-03 | No | 2018-09-17 | Yes | Not Required | Not Required | Not Required | 2018-11-27 | 2020-04-21 | 2020-04-21 |  |  | 2020-10-19 | 2020-11-12
19INR0103 | Rodeo Solar | SS Completed, FIS Started, IA | Core Solar SPV I, LLC | tap 138kV 1134 Littman - 1135 Gasland | Andrews | WEST | 2025-04-01 | SOL | PV | 200 |  | 2018-02-19 | 2017-06-29 | 2017-08-04 | 2018-02-19 |  |  | 2019-08-20 | Yes | Not Required | Not Required | Not Required | 2021-03-10 | 2022-11-01
19INR0110 | Azalea Springs Solar | SS Completed, FIS Completed, IA | EDP Renewables | tap 138kV Jim English – Lufkin Chipper Mill | Angelina | NORTH | 2025-05-31 | SOL | PV | 181 |  |  | 2017-07-26 | 2017-09-15 | 2018-03-15 | 2023-02-27 | No | 2023-09-14 | No | Not Required | Not Required | Not Required
19INR0117 | Roadrunner Crossing Wind SLF | SS Completed, FIS Completed, IA | Roadrunner Crossing Wind Farm, LLC | 68051 Reata 345kV | Eastland | NORTH | 2025-01-20 | WIN | WT | 128 | Proj Name | 2018-03-01 | 2017-09-08 | 2017-11-07 | 2018-03-05 | 2023-04-26 | No | 2021-04-17 | Yes | Not Required | Not Required | Not Required | 2020-09-17 | 2023-04-26 | 2023-05-01
19INR0120 | Sherbino II Wind repower | SS Completed, FIS Completed, IA | Sherbino II Wind Farm LLC | 38430 TN White Baker 138kV | Pecos | WEST | 2024-03-01 | WIN | WT | -18 | COD | 2017-09-21 | 2017-08-18 | 2017-09-28 | 2017-09-21 | 2018-12-04 | No | 2008-02-28 | Yes | Not Required | Not Required | Not Required | 2019-10-28 | 2019-10-28 | 2019-10-28 |  |  |  | 2020-06-09
19INR0134 | Cottonwood Bayou Solar | SS Completed, FIS Completed, IA | Cottonwood Bayou Solar, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2024-08-13 | SOL | PV | 351.4 |  |  | 2017-09-22 | 2017-11-17 | 2018-02-15 | 2023-04-27 | No | 2019-11-13 | Yes | Not Required | Not Required | Not Required | 2023-04-27 | 2023-04-27 | 2023-04-27
19INR0155 | Morrow Lake Solar | SS Completed, FIS Completed, IA | Morrow Lake Solar, LLC | 5895 Pearsall 138kV | Frio | SOUTH | 2024-08-01 | SOL | PV | 201.1 |  | 2018-02-15 | 2017-12-05 | 2018-01-15 | 2018-02-15 | 2023-11-01 | No | 2019-08-29 | Yes | Not Required | Not Required | Not Required | 2019-11-18 | 2023-11-01 | 2023-11-01
19INR0165 | Barranca Wind | SS Completed, FIS Started, No IA | Barranca Wind Energy LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2026-09-23 | WIN | WT | 201.6 |  |  | 2018-05-09 | 2018-05-25 | 2018-02-28 |  |  |  | No | Not Required | Not Required | Not Required
19INR0169 | Sun Valley Solar | SS Completed, FIS Completed, IA | Sun Valley Solar LLC | tap 345kV 68090 Sam Sw - 3405 Tradinghouse | Hill | NORTH | 2023-05-30 | SOL | PV | 252 |  | 2018-11-09 | 2018-03-02 | 2018-04-17 | 2018-07-19 | 2022-01-29 | No | 2020-03-15 | Yes | Not Required | Not Required | Not Required | 2021-08-13 | 2021-12-21 | 2022-02-01 |  |  | 2022-09-14 | 2022-11-01
19INR0174 | Elbow Creek repower | SS Completed, FIS Completed, IA | NRG | 1058 Longshore 345kV | Howard | WEST | 2024-05-31 | WIN | WT | 0 |  | 2018-07-19 | 2018-05-04 | 2018-05-18 | 2018-07-19 | 2018-09-17 | No | 2007-11-30 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-27
19INR0175 | Shifting Gale Wind | SS Completed, FIS Started, No IA | SEAWAY WIND ENERGY LLC | 23912 Ogallala 345kV | Castro | PANHANDLE | 2025-12-31 | WIN | WT | 289 |  | 2018-12-06 | 2018-04-26 | 2018-06-12 | 2018-12-06 |  | No |  | No | Not Required | Not Required | Not Required
19INR0177 | Crawfish | SS Completed, FIS Completed, IA | Prairie Switch Wind, LLC | 8679 Arroz4A 138kV | Wharton | SOUTH | 2024-03-01 | WIN | WT | 163.2 |  |  | 2018-05-09 | 2018-06-21 | 2018-05-09 | 2022-07-28 | No | 2021-07-06 | Yes | Not Required | Not Required | Not Required | 2022-05-13 | 2022-10-15 | 2022-10-31
19INR0179 | Barranca Wind II | SS Completed, FIS Started, No IA | Barranca Wind Energy LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2026-09-23 | WIN | WT | 201.6 |  |  | 2018-05-15 | 2018-06-01 | 2018-05-15 |  |  |  | No | Not Required | Not Required | Not Required
19INR0189 | SP TX-12B Phase III | SS Completed, FIS Started, No IA | ConEd Development | 76040 Castillo 138kV | Upton | WEST | 2025-12-02 | SOL | PV | 40 | COD | 2019-01-29 | 2018-09-12 | 2018-10-03 |  |  | No |  | No | Not Required | Not Required | Not Required
19INR0203 | Angelo Solar | SS Completed, FIS Completed, IA | ANGELO SOLAR LLC | 76009 Twin Buttes 345kV | Tom Green | WEST | 2024-08-12 | SOL | PV | 195.41 |  | 2019-01-17 | 2018-11-20 | 2019-02-05 | 2019-01-21 | 2023-05-01 | No | 2021-12-03 | Yes | Not Required | Not Required | Not Required | 2023-05-01 | 2023-05-01 | 2023-05-01
20INR0012 | Lueders Solar | SS Completed, FIS Started, No IA | Innovative Solar 75 | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | WEST | 2025-12-31 | SOL | PV | 40 | COD |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  | No |  | No | Not Required | Not Required | Not Required
20INR0019 | Trinity Hills Wind repower | SS Completed, FIS Completed, IA | Trinity Hills Wind Farm LLC | 17002 Garvey Rd 345kV | Young | WEST | 2024-05-01 | WIN | WT | -27 | COD | 2017-09-21 | 2017-07-20 | 2017-09-08 | 2017-09-21 | 2018-08-02 | No | 2018-10-17 | No | Not Required | Not Required | Not Required | 2019-10-29 | 2019-10-29 | 2019-10-29 |  |  |  | 2020-05-22
20INR0026 | Longbow Solar | SS Completed, FIS Completed, IA | Longbow Solar, LLC | 42110 Angelton - 42870 Liverpool 138kV | Brazoria | COASTAL | 2023-12-29 | SOL | PV | 78.15 |  |  | 2017-08-16 | 2017-10-13 | 2017-08-16 | 2021-10-15 | No | 2021-01-06 | Yes | Not Required | Not Required | Not Required | 2021-11-01 | 2021-11-01 | 2021-11-01 |  |  | 2022-07-20 | 2022-07-27
20INR0029 | Lutum Wind | SS Completed, FIS Started, No IA | RWE | tap 345kV 6101 Riley - 1730 W Krum | Clay | WEST | 2024-07-11 | WIN | WT | 241.5 | Status Change INA-to-PLN |  | 2017-09-12 | 2017-11-07 | 2018-05-08 |  | No |  | No | Not Required | Not Required | Not Required
20INR0033 | WILDWIND | SS Completed, FIS Completed, IA | Wildcat Creek | tap 345kV 1730 KrumW - 2373 Anna | Cooke | NORTH | 2024-02-29 | WIN | WT | 180.08 | COD | 2018-06-14 | 2017-10-18 | 2017-12-11 | 2018-06-14 | 2019-11-25 | No | 2020-02-21 | Yes | Not Required | Not Required | Not Required | 2020-03-23 | 2020-04-30 | 2020-04-30 |  |  | 2020-12-22 | 2021-02-10
20INR0035 | Angus Solar | SS Completed, FIS Completed, IA | Angus Solar, LLC | tap 138kV 177 Bosque - 181 Cayote | Bosque | NORTH | 2025-04-01 | SOL | PV | 112 |  | 2017-11-13 | 2017-11-13 | 2018-01-02 | 2017-11-13 | 2023-04-03 |  | 2021-12-06 | Yes | Not Required | Not Required | Not Required | 2022-08-24 | 2023-04-26
20INR0040 | Montgomery Ranch Wind | SS Completed, FIS Completed, IA | RWE Renewables Development, LLC | tap 345kV 60500 Edith Clark – 60506 Avogrado | Foard | WEST | 2024-09-01 | WIN | WT | 200.2 |  | 2018-06-20 | 2017-12-18 | 2018-02-06 | 2018-06-20 | 2023-07-31 | Yes | 2022-03-22 | Yes | Not Required | Not Required | Not Required | 2023-07-31 | 2023-07-31 | 2023-08-01
20INR0047 | Siete | SS Completed, FIS Started, IA | Apex Clean | 345kV 8718 Triada | Webb | SOUTH | 2026-10-31 | WIN | WT | 375.06 |  | 2019-06-13 | 2018-10-23 | 2018-12-11 | 2019-06-12 |  | No | 2022-06-30 | Yes | Not Required | Not Required | Not Required | 2022-07-19
20INR0050 | Castro Solar | SS Completed, FIS Started, IA | Castro Solar One, LLC | 23912 Ogallala 345kV | Castro | PANHANDLE | 2025-05-02 | SOL | PV | 222.95 |  | 2018-05-15 | 2018-02-08 | 2018-04-09 | 2018-05-15 |  | No | 2020-11-30 | No | Not Required | Not Required | Not Required
20INR0069 | Danish Fields Solar | SS Completed, FIS Completed, IA | Danish Fields Solar, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2024-02-15 | SOL | PV | 602.8 | COD | 2023-03-20 | 2018-04-12 | 2018-06-05 | 2018-08-21 | 2022-07-25 | No | 2020-02-24 | Yes | Not Required | Not Required | Not Required | 2022-07-28 | 2022-07-28 | 2022-07-28 |  |  | 2023-03-27 | 2023-05-04
20INR0080 | Frye Solar | SS Completed, FIS Completed, IA | Hecate Energy | Kress sub KRSSW 23913 345 kV | Swisher | PANHANDLE | 2024-04-08 | SOL | PV | 502 | COD | 2018-10-23 | 2018-05-17 | 2018-07-02 | 2018-11-20 | 2023-01-31 | No | 2021-02-06 | Yes | Not Required | Not Required | Not Required | 2023-01-31 | 2023-01-31 | 2023-01-31 |  |  | 2023-08-09 | 2023-08-28
20INR0083 | Baird North Wind | SS Completed, FIS Completed, IA | BMP Wind, LLC | 68008 Latimer 345kV | Callahan | WEST | 2025-12-31 | WIN | WT | 350 |  |  | 2018-05-04 | 2018-06-12 | 2018-08-20 | 2020-10-30 | No | 2019-05-31 | Yes | Not Required | Not Required | Not Required | 2019-07-19 | 2020-10-30 | 2020-11-01 |  |  | 2021-08-09 | 2021-08-20
20INR0086 | Arroyo Solar | SS Completed, FIS Started, IA | BT Cantwell Solar, LLC | 345 KV Tap #8318 Rio Hondo - #8317 La Palma | Cameron | COASTAL | 2024-11-30 | SOL | PV | 180 |  | 2018-10-10 | 2018-05-09 | 2018-07-09 | 2018-10-10 |  | No | 2021-09-28 | Yes | Not Required | Not Required | Not Required
20INR0091 | Fagus Solar Park SLF | SS Completed, FIS Started, IA | Excel Advantage Services, LLC dba Misae Solar Park II | 60501 Tesla 345kV | Childress | PANHANDLE | 2025-05-15 | SOL | PV | 519.46 |  | 2018-05-15 | 2018-05-15 | 2018-07-06 | 2018-05-15 |  | No | 2019-02-21 | Yes | Not Required | Not Required | Not Required | 2021-01-15
20INR0097 | El Sauz Ranch | SS Completed, FIS Completed, IA | El Sauz Ranch Wind, LLC | 8663 EL SAUZ POI 345kV | Willacy | COASTAL | 2024-01-26 | WIN | WT | 301.5 | COD | 2019-02-01 | 2018-06-19 | 2018-08-22 | 2019-01-31 | 2021-10-29 |  | 2021-01-27 | Yes | Not Required | Not Required | Not Required | 2021-10-14 | 2022-01-26 | 2022-01-26 |  |  | 2022-09-28 | 2023-02-28
20INR0106 | Wang Solar SLF | SS Completed, FIS Started, No IA | BT Yixin Solar, LLC | tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2026-03-31 | SOL | PV | 144.6 |  | 2018-08-29 | 2018-06-14 | 2018-08-13 | 2018-08-29 |  | No |  | No | Not Required | Not Required | Not Required
20INR0120 | Vortex Wind | SS Completed, FIS Completed, IA | AZURE SKY WIND PROJECT LLC | loop 345kV 60515 Clear Crossing - 1421 WillowCr 345kV | Throckmorton | WEST | 2023-12-31 | WIN | WT | 350 | COD | 2019-02-28 | 2018-06-29 | 2018-08-27 | 2019-02-20 | 2021-04-30 | No | 2020-12-01 | Yes | Not Required | Not Required | Not Required | 2021-03-25 | 2021-04-29 | 2021-04-30 |  |  | 2021-11-19 | 2022-02-23
20INR0127 | Milam Solar 1 | SS Completed, FIS Started, No IA | Sandow Lakes Ranch Solar I, LLC | tap one 345kV 7040 Austrop - 13429 Sandow line | Milam | SOUTH | 2026-12-01 | SOL | PV | 215.2 | MW Size | 2019-08-13 | 2018-07-03 | 2018-09-18 |  |  |  |  | No | Not Required | Not Required | Not Required
20INR0129 | Foxtrot Wind | SS Completed, FIS Completed, IA | Lincoln Clean | AEP 88689 Tango 345kV station | Bee | SOUTH | 2024-03-01 | WIN | WT | 268.2 |  |  | 2018-07-26 | 2018-09-14 | 2018-07-26 | 2021-07-30 | No | 2020-05-05 | Yes | Not Required | Not Required | Not Required | 2021-07-30 | 2021-07-30 | 2021-07-30 |  |  | 2022-02-23 | 2022-03-09
20INR0130 | Plainview Solar | SS Completed, FIS Completed, IA | Hecate Energy Ramsey LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2024-01-31 | SOL | PV | 514 | COD | 2018-07-18 | 2018-10-10 | 2018-11-21 | 2018-10-10 | 2020-10-26 | No | 2020-05-29 | Yes | Not Required | Not Required | Not Required | 2020-10-07 | 2020-10-26 | 2020-10-26 |  |  | 2021-07-17 | 2021-07-26
20INR0134 | Half Moon Solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2028-07-01 | SOL | PV | 151.2 |  |  | 2018-09-13 | 2018-11-09 | 2018-11-06 |  | No |  | No | Not Required | Not Required | Not Required
20INR0135 | Half Moon Battery | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2028-07-01 | OTH | BA | 30.2 |  |  | 2018-09-13 | 2018-11-09 | 2018-11-06 |  | No |  | No | Not Required | Not Required | Not Required
20INR0155 | Peyton Creek Wind II | SS Completed, FIS Started, No IA | RWE Renewables Development, LLC | 42400 Refuge 345kV | Matagorda | COASTAL | 2024-12-03 | WIN | WT | 241.2 |  | 2019-01-30 | 2018-08-21 | 2018-11-02 | 2019-03-14 |  | No |  | No | Not Required | Not Required | Not Required
20INR0162 | Diamondback solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Starr | SOUTH | 2025-07-31 | SOL | PV | 201.6 |  |  | 2018-09-13 | 2018-12-06 | 2018-11-07 |  | No |  | No | Not Required | Not Required | Not Required
20INR0203 | Pine Forest Solar | SS Completed, FIS Not Started, IA | Pine Forest Solar I, LLC | Monticello Switch – Allen Switch 345 kV Line | Hopkins | NORTH | 2025-06-29 | SOL | PV | 305 |  | 2019-03-26 | 2018-10-04 | 2018-11-20 |  |  | No | 2020-07-29 | No | Not Required | Not Required | Not Required
20INR0205 | Roseland Solar | SS Completed, FIS Completed, IA | Enel Green Power Roseland Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2024-01-31 | SOL | PV | 254 | COD | 2018-11-05 | 2018-11-30 | 2019-02-04 | 2019-02-04 | 2021-10-25 | No | 2020-12-10 | Yes | Not Required | Not Required | Not Required | 2021-08-18 | 2021-11-01 | 2021-10-25 |  |  | 2022-06-07 | 2022-09-26
20INR0208 | Signal Solar | SS Completed, FIS Completed, IA | Adapture Renewables, Inc | tap 138kV 6879 Wieland - 6883 Quinlan N | Hunt | NORTH | 2025-03-15 | SOL | PV | 51.79 |  | 2019-04-02 | 2018-11-07 | 2018-12-20 |  | 2023-09-01 | No | 2020-10-23 | Yes | Not Required | Not Required | Not Required | 2023-06-12
20INR0210 | Hopkins Solar | SS Completed, FIS Completed, IA | Hopkins Energy LLC | tap 345kV 11688 THORNTRE - 11689 CYCLONE | Hopkins | NORTH | 2023-12-30 | SOL | PV | 253.08 |  | 2019-03-15 | 2018-11-20 | 2019-02-06 | 2019-03-14 | 2023-04-26 | No | 2020-09-25 | Yes | Not Required | Not Required | Not Required | 2023-04-28 | 2023-04-28 | 2023-04-28 |  |  | 2023-09-12 | 2023-10-11
20INR0213 | Brushy Creek Solar SLF | SS Completed, FIS Started, No IA | Brushy Creek Solar LLC | 6444 Red Creek 345kV | Tom Green | WEST | 2025-09-20 | SOL | PV | 177.09 |  | 2019-03-26 | 2019-01-07 | 2019-03-26 | 2019-03-05 |  | No |  | No | Not Required | Not Required | Not Required
20INR0216 | Starr Solar Ranch | SS Completed, FIS Started, IA | Starr Solar Ranch LLC | 8795 Roma 138kV | Starr | SOUTH | 2024-12-01 | SOL | PV | 136.66 |  | 2018-11-07 | 2018-11-07 | 2018-12-14 | 2018-11-07 |  | No | 2020-10-01 | Yes | Not Required | Not Required | Not Required | 2020-11-19
20INR0217 | CAROL wind | SS Completed, FIS Completed, IA | NextERA Energy | 23906 AJ Swope 345kV | Potter | PANHANDLE | 2024-12-31 | WIN | WT | 165.42 | COD | 2019-06-10 | 2018-12-06 | 2019-01-18 | 2019-06-05 | 2023-10-30 | No | 2020-09-11 | Yes | Not Required | Not Required | Not Required
20INR0222 | Tyson Nick Solar | SS Completed, FIS Started, IA | Tyson Nick Solar Project, LLC | 1700 Toco 138kV | Lamar | NORTH | 2024-12-15 | SOL | PV | 90.5 | MW Size | 2019-02-25 | 2018-12-12 | 2019-02-15 | 2019-01-14 |  | No | 2020-08-28 | No | Not Required | Not Required | Not Required
20INR0230 | Markum Solar | SS Completed, FIS Completed, IA | Glory Leasing LLC | 177 Bosque 138kV | McLennan | NORTH | 2025-02-28 | SOL | PV | 161.54 |  | 2018-12-17 | 2018-12-18 | 2019-01-03 | 2018-12-18 | 2023-11-28 |  | 2021-06-28 | Yes | Not Required | Not Required | Not Required | 2021-10-04
20INR0233 | Impala Flats Wind | SS Completed, FIS Started, No IA | Antelope Flats Wind, LLC | 79641 Farmland 345kV | Lynn | WEST | 2025-06-03 | WIN | WT | 282 |  | 2019-01-15 | 2019-01-11 | 2019-04-03 | 2018-12-21 |  |  |  | No |  |  | Not Required
20INR0235 | Knickerbocker Solar SLF | SS Completed, FIS Started, No IA | Knickerbocker Solar LLC | Tap 345kV 76003 Big Hill - 76009 Twin Buttes | Tom Green | WEST | 2025-01-15 | SOL | PV | 241.26 |  | 2019-03-12 | 2019-01-07 | 2019-03-15 | 2019-03-04 |  |  |  | No | Not Required | Not Required | Not Required
20INR0236 | Old Hickory Solar | SS Completed, FIS Started, IA | Old Hickory Solar LLC | OLD_HCKRY_5 bus 5323 345 kV | Jackson | SOUTH | 2025-09-30 | SOL | PV | 225.7 | COD | 2019-08-27 | 2019-01-25 | 2019-04-19 | 2019-08-12 |  |  | 2020-06-30 | Yes | Not Required | Not Required | Not Required | 2021-04-12
20INR0238 | Voyager Storage | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2026-04-08 | OTH | BA | 50.14 |  | 2019-04-30 | 2019-01-14 | 2019-03-19 | 2019-04-26 |  |  |  | No | Not Required | Not Required | Not Required
20INR0241 | Crowded Star Solar | SS Completed, FIS Started, IA | Jones City Solar, LLC | tap 345kV 68001 Claytonville – 68004 Phantom Hill c2 | Jones | WEST | 2026-01-26 | SOL | PV | 218.34 |  | 2019-05-23 | 2019-01-21 | 2019-04-19 | 2019-05-22 |  | Yes | 2019-12-17 | Yes | Not Required | Not Required | Not Required | 2021-12-01
20INR0242 | Anson Solar Center, Phase II | SS Completed, FIS Started, No IA | Anson Solar Center 2, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2025-12-01 | SOL | PV | 200.9 |  | 2018-02-15 | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  |  | No | Not Required | Not Required | Not Required
20INR0244 | Montezuma Storage | SS Completed, FIS Completed, No IA | Montezuma Storage LLC | 7258 Glidden 138kV | Colorado | SOUTH | 2024-11-01 | OTH | BA | 50.6 |  | 2019-01-08 | 2019-01-15 | 2019-07-02 | 2019-03-15 | 2023-11-30 |  |  | No | Not Required | Not Required | Not Required
20INR0245 | Volunteer Storage | SS Completed, FIS Started, No IA | Blackjack Storage LLC | 7216 Lockhart 138kV | Caldwell | SOUTH | 2024-11-01 | OTH | BA | 50.6 |  | 2019-01-16 | 2019-01-15 | 2019-07-02 | 2019-03-15 |  |  |  | No | Not Required | Not Required | Not Required
20INR0246 | Ryan Energy Storage | SS Completed, FIS Completed, IA | Ryan Storage LLC | 37580 TNPancake 69kV | Coryell | NORTH | 2024-10-21 | OTH | BA | 50 |  | 2019-02-08 | 2019-01-15 | 2019-04-05 | 2019-03-15 | 2020-08-16 | No | 2021-02-18 | Yes | Not Required | Not Required | Not Required | 2022-08-03
20INR0247 | Water Valley Wind Energy | SS Completed, FIS Started, No IA | Water Valley Wind Energy, LLC | 345 kV 76009 Twin Buttes to 76090 Divide Double Circuit | Tom Green | WEST | 2026-12-31 | WIN | WT | 180 |  | 2019-01-10 | 2019-01-15 | 2019-03-29 | 2019-01-10 |  |  |  | No |  |  | Not Required
20INR0248 | Second Division Solar | SS Completed, FIS Completed, IA | TX Gulf Solar 1 LLC | Tap 138 kV SANBER_POI_8 (Bus# 43110) to WEST COLUMBIA (Bus# 43380) Ckt 60 Line | Brazoria | COASTAL | 2024-09-17 | SOL | PV | 100.3 |  | 2019-08-06 | 2019-03-28 | 2019-06-18 | 2019-07-29 | 2022-10-28 | No | 2020-10-14 | Yes | Not Required | Not Required | Not Required | 2023-10-31 | 2023-10-31 | 2023-10-31
20INR0249 | Appaloosa Run Wind | SS Completed, FIS Completed, IA | Appaloosa Run Wind, LLC | tap 138kV 60361 Santarita - 76032 NMcCamey | Upton | WEST | 2024-01-31 | WIN | WT | 175 |  | 2019-02-19 | 2019-01-17 | 2019-04-02 | 2019-01-15 | 2022-04-06 |  | 2021-04-12 | Yes | Not Required | Not Required | Not Required | 2022-04-21 | 2022-04-21 | 2022-04-25 |  |  | 2022-12-12 | 2022-12-19
20INR0255 | Renegade Project | SS Completed, FIS Started, IA | Renegade Renewable LLC | Tap 345kV 23910 Windmill - 23906 AJ Swope | Deaf Smith | PANHANDLE | 2025-07-31 | SOL | PV | 515.66 |  | 2019-04-01 | 2019-02-26 | 2019-05-17 | 2019-02-07 |  |  | 2021-01-04 | Yes | Not Required | Not Required | Not Required
20INR0266 | Tres Bahias Solar | SS Completed, FIS Completed, IA | Tres Bahias Solar Power LLC | 8140 Joslin 138kV | Calhoun | COASTAL | 2023-12-20 | SOL | PV | 195 | COD | 2019-06-03 | 2019-03-26 | 2019-06-11 | 2019-06-03 | 2022-01-21 |  | 2020-08-07 | Yes | Not Required | Not Required | Not Required | 2020-10-07 | 2022-12-20 | 2023-01-30 |  |  | 2023-06-26 | 2023-09-12
20INR0269 | Texas Solar Nova 2 | SS Completed, FIS Completed, IA | TEXAS SOLAR NOVA 2, LLC | 138kV 59909 WETT Nova Prime | Kent | WEST | 2024-02-26 | SOL | PV | 201.14 | COD | 2016-07-06 | 2019-06-24 | 2015-12-30 | 2019-06-19 | 2022-05-19 |  | 2021-07-16 | Yes |  |  | Not Required | 2022-07-29 | 2022-07-29 | 2022-08-03 |  |  | 2023-08-22 | 2023-11-13
20INR0271 | Blue Hills Wind | SS Completed, FIS Started, No IA | Greenalia Wind Power Blue Hills | Tap 138kV 8683 Comstock - 60389 Corral | Val Verde | WEST | 2026-06-15 | WIN | WT | 276 |  | 2019-12-03 | 2019-05-07 | 2019-07-26 | 2019-11-21 |  | No |  | No | Not Required | Not Required | Not Required
20INR0286 | Wise County Power Repower (CT1, CT2) | SS Completed, FIS Completed, IA | Wise County Power Company LLC | 1421 Willow Creek 345kV | Wise | NORTH | 2023-12-23 | GAS | CC | 21 |  | 2019-07-15 | 2019-07-25 | 2019-10-23 | 2019-07-16 | 2019-10-23 | No | 2001-03-19 | Yes | 2020-01-21 | Not Required | 2019-12-05 | 2020-01-22 | 2020-01-27 | 2020-01-27
20INR0296 | Sand Bluff Wind Repower | SS Completed, FIS Completed, IA | RWE Renewables Development, LLC | 1333 McDonald 138kV | Glasscock | WEST | 2024-02-01 | WIN | WT | 89.5 |  | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-19 | 2022-04-18 | No | 2006-11-11 | No | Not Required | Not Required | Not Required | 2022-05-02 | 2022-05-02 | 2022-05-02 |  |  |  | 2022-11-01
21INR0006 | Giddings Wind | SS Completed, FIS Started, No IA | Pioneer Natural Resources | 71212 Upton 138kV | Upton | WEST | 2026-06-30 | WIN | WT | 240 |  | 2019-04-02 | 2017-09-06 | 2019-08-19 | 2020-01-15 |  |  |  | No | Not Required | Not Required | Not Required
21INR0012 | Air Products GCA | SS Completed, FIS Completed, IA | Air Products | 39140 TNTxCityMain 69kV (Will be upgraded to 138kV) | Galveston | HOUSTON | 2024-01-12 | GAS | ST | 14 |  | 2019-03-26 | 2018-06-07 | 2018-08-01 |  | 2023-03-10 |  | 2020-08-07 | Yes | Not Required | Not Required | 2020-03-31 | 2023-03-13 | 2023-03-13 | 2023-03-13 |  |  | 2023-11-07
21INR0019 | Zier Solar | SS Completed, FIS Completed, IA | Zier Solar, LLC | 78255 Pinto Creek 138kV | Kinney | SOUTH | 2024-03-01 | SOL | PV | 162.99 |  |  | 2018-05-24 | 2018-07-20 | 2018-05-24 | 2023-01-24 | No | 2020-10-22 | Yes | Not Required | Not Required | Not Required | 2022-09-27 | 2023-01-31 | 2023-01-31 |  |  | 2023-11-08 | 2023-11-27
21INR0021 | Green Holly Solar | SS Completed, FIS Started, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2026-05-30 | SOL | PV | 413.6 |  |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | 2020-05-19 | No | Not Required | Not Required | Not Required
21INR0022 | Red Holly Solar | SS Completed, FIS Started, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2026-05-30 | SOL | PV | 260 |  |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  | No | 2020-10-19 | No | Not Required | Not Required | Not Required
21INR0027 | Zier Storage | SS Completed, FIS Completed, IA | Zier Solar, LLC | 78255 Pinto Creek 138kV | Kinney | SOUTH | 2024-02-09 | OTH | BA | 40.41 |  |  | 2018-05-24 | 2018-07-20 | 2018-05-24 | 2023-01-24 | No | 2020-10-22 | Yes | Not Required | Not Required | Not Required | 2022-09-27 | 2023-01-31 | 2023-01-31 |  |  | 2023-11-08 | 2023-12-21
21INR0029 | Green Holly Storage | SS Completed, FIS Started, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2026-05-30 | OTH | BA | 50 |  |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | 2020-10-19 | No | Not Required | Not Required | Not Required
21INR0031 | Indigo Solar | SS Completed, FIS Started, IA | Innovative Solar 245, LLC | tap 345kV 68001 Clayton 345kV - 68000 WShack | Fisher | WEST | 2024-12-16 | SOL | PV | 125 |  | 2019-05-16 | 2018-09-27 | 2018-11-20 | 2019-05-15 |  | No | 2022-09-15 | No | Not Required | Not Required | Not Required
21INR0033 | Red Holly Storage | SS Completed, FIS Started, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2026-05-30 | OTH | BA | 50 |  |  | 2018-09-27 | 2018-12-18 | 2018-12-11 |  | No | 2020-10-19 | No | Not Required | Not Required | Not Required
21INR0201 | Brandon | SS Completed, FIS Completed, IA | City of Lubbock, by and through Lubbock Power and Light (RE) | Brandon 12.47 kV | Lubbock | PANHANDLE | 2021-11-15 | GAS | GT | 21 |  | 2019-05-23 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2020-10-23 | No | 2020-10-30 | Yes | 2007-01-01 | Not Required | 2020-08-09 | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2021-07-02 | 2021-07-19
21INR0202 | R Massengale | SS Completed, FIS Completed, IA | City of Lubbock, by and through Lubbock Power and Light | Mackenzie 115 kV | Lubbock | PANHANDLE | 2021-11-15 | GAS | CC | 58 |  | 2020-08-10 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2020-10-23 | No | 2020-10-30 | Yes | 2000-01-03 | Not Required | 2020-08-09 | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2021-07-23 | 2021-07-26
21INR0203 | Eastbell Milam Solar | SS Completed, FIS Completed, IA | EDP RENEWABLES NORTH AMERICA LLC | 345 kV Bell County East Switch (bus# 3687) - TNP One (bus# 39950) circuit 2 | Milam | SOUTH | 2024-02-01 | SOL | PV | 244.86 | COD | 2019-04-23 | 2018-10-10 | 2018-12-09 | 2019-04-23 | 2022-10-28 | No | 2022-09-02 | Yes | Not Required | Not Required | Not Required | 2022-11-03 | 2022-11-03 | 2022-11-12 |  |  | 2023-10-13 | 2023-11-01
21INR0207 | Quantum Solar | SS Completed, FIS Started, IA | IP QUANTUM II, LLC | tap 345kV 60514 Clear Crossing - 60507 Pendulo | Haskell | WEST | 2026-03-31 | SOL | PV | 374.4 |  | 2018-11-07 | 2018-09-27 | 2018-11-14 | 2018-11-07 |  | No | 2023-10-26 | No |  |  | Not Required
21INR0210 | Adamstown Solar | SS Completed, FIS Completed, IA | Adams Creek Solar Project, LLC | tap 345kV 1730 West Krum - 6101 Riley | Wichita | WEST | 2026-09-30 | SOL | PV | 251.28 |  | 2019-05-22 | 2018-11-20 | 2019-02-04 | 2019-05-16 | 2022-01-11 | No | 2022-08-08 | No |  |  | Not Required
21INR0220 | Maleza Solar | SS Completed, FIS Not Started, IA | Brush Solar LLC | tap Blue – Hillje 345 kv Ckt.#27 | Wharton | SOUTH | 2024-12-01 | SOL | PV | 254.94 |  | 2019-03-07 | 2018-12-06 | 2019-01-18 |  |  | No | 2021-01-27 | Yes |  |  | Not Required | 2022-12-08
21INR0221 | Samson Solar 1 | SS Completed, FIS Completed, IA | Samson Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2024-02-15 | SOL | PV | 250 | COD | 2019-05-13 | 2018-11-20 | 2019-01-04 | 2019-05-03 | 2020-06-09 | No | 2020-08-26 | Yes | Not Required | Not Required | Not Required | 2020-08-26 | 2020-10-15 | 2020-10-26 |  |  | 2021-06-30 | 2021-08-31
21INR0223 | Tulsita Solar | SS Completed, FIS Completed, IA | Ray Ranch Solar LLC | Tap 138kV 8590 Tuleta - 8595 Euler | Goliad | SOUTH | 2024-12-31 | SOL | PV | 256.2 |  | 2019-05-20 | 2018-12-05 | 2019-02-21 | 2019-05-17 | 2023-03-15 | No | 2022-09-19 | Yes | Not Required | Not Required | Not Required | 2022-10-03
21INR0226 | Equinox Solar 1 | SS Completed, FIS Started, IA | Invenergy Solar Project Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2026-12-30 | SOL | PV | 200 |  | 2019-08-14 | 2018-12-11 | 2019-01-23 | 2019-07-30 |  | No | 2021-01-28 | No | Not Required | Not Required | Not Required
21INR0227 | Equinox Solar 2 | SS Completed, FIS Started, No IA | Invenergy Solar Project Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2026-12-30 | SOL | PV | 200 |  | 2019-08-05 | 2018-12-11 | 2019-01-31 | 2019-07-30 |  | No |  | No | Not Required | Not Required | Not Required
21INR0237 | Voyager Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2025-12-01 | SOL | PV | 303.9 |  | 2019-04-30 | 2019-01-04 | 2019-03-19 | 2019-04-26 |  |  |  | No | Not Required | Not Required | Not Required
21INR0240 | La Casa Wind | SS Completed, FIS Completed, IA | Nextera Energy Resources LLC | New switching station: 138kV Graham Plant Switch - Breckenridge - Leon Switch | Stephens | NORTH | 2025-06-10 | WIN | WT | 148.33 |  |  | 2018-12-28 | 2019-03-12 | 2018-12-29 | 2023-09-22 |  | 2023-09-07 | No | Not Required | Not Required | Not Required
21INR0247 | Anson Solar Center, Phase III | SS Completed, FIS Started, No IA | Anson Solar Center 3, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2024-06-03 | SOL | PV | 200 |  | 2018-02-15 | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  |  | No |  |  | Not Required
21INR0253 | Ulysses Solar | SS Completed, FIS Started, IA | BNB Tennyson Solar LLC | tap 345kV 6444 Red Creek - 60040 Bluff Creek | Coke | WEST | 2025-12-31 | SOL | PV | 150 |  | 2019-05-14 | 2019-01-25 | 2019-04-05 | 2019-05-10 |  |  | 2022-10-03 | Yes | Not Required | Not Required | Not Required | 2022-12-05
21INR0254 | Blue Cut Solar | SS Completed, FIS Started, No IA | Blue Cut Solar, LLC | tap 138kV 7064 Lampasas - 260 Kempner | Lampasas | NORTH | 2025-06-01 | SOL | PV | 150 |  | 2019-10-10 | 2019-01-30 | 2019-04-12 | 2019-10-08 |  |  |  | No | Not Required | Not Required | Not Required
21INR0256 | Amsterdam Solar | SS Completed, FIS Started, IA | Cottonwood Bayou Solar II, LLC | tap 345kV 43035 Oasis - 42500 Dow c27, c18 | Brazoria | COASTAL | 2025-03-01 | SOL | PV | 509.88 |  | 2019-10-18 | 2019-02-07 | 2019-04-29 | 2019-07-31 |  | No | 2022-02-17 | No | Not Required | Not Required | Not Required
21INR0257 | Mercury Solar | SS Completed, FIS Completed, IA | Mercury Solar, LLC | 68092 Liberty Station 345kV | Hill | NORTH | 2024-06-28 | SOL | PV | 206.11 |  | 2019-02-07 | 2019-02-14 | 2019-05-03 | 2019-02-07 | 2021-10-14 |  | 2021-10-18 | Yes | Not Required | Not Required | Not Required | 2022-03-21 | 2022-04-29 | 2022-04-29 |  |  | 2023-10-19 | 2023-10-31
21INR0258 | Mercury Storage | SS Completed, FIS Started, No IA | Mercury Storage, LLC | 68092 Liberty Station 345kV | Hill | NORTH | 2025-08-30 | OTH | BA | 205.9 |  | 2019-02-07 | 2019-02-14 | 2019-05-03 | 2019-02-07 |  |  |  | No | Not Required | Not Required | Not Required
21INR0260 | Chariot Storage | SS Completed, FIS Started, No IA | Chariot Storage LLC | tap 69kV 99 Ben Hur - 107 Prairie Hill | Limestone | NORTH | 2024-11-01 | OTH | BA | 50 |  | 2019-02-19 | 2019-03-06 | 2019-05-24 | 2019-02-11 |  | No |  | No | Not Required | Not Required | Not Required
21INR0261 | Horizon Solar | SS Completed, FIS Completed, IA | Horizon Solar, LLC | 5897 Horizon Switch 138kV | Frio | SOUTH | 2023-12-29 | SOL | PV | 203.5 | COD | 2019-03-05 | 2019-03-05 | 2019-05-20 | 2019-03-01 | 2022-08-22 | No | 2019-07-12 | Yes | Not Required | Not Required | Not Required | 2019-08-09 | 2019-12-09 | 2022-10-26 |  |  | 2023-08-11 | 2023-08-25
21INR0262 | Grandfalls Storage | SS Completed, FIS Started, No IA | King Mountain Storage LLC | tap 345kV 11028 Odessa - 76000 North McCamey | Upton | WEST | 2026-08-29 | OTH | BA | 205.9 |  | 2019-02-14 | 2019-03-25 | 2019-06-17 | 2019-02-14 |  |  |  | No |  |  | Not Required
21INR0263 | Monarch Creek Wind | SS Completed, FIS Started, IA | EDF Renewables Development, Inc. | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek Switch (North Circuit) | Throckmorton | WEST | 2025-12-31 | WIN | WT | 344.48 |  | 2019-10-28 | 2019-04-25 | 2019-07-19 | 2019-08-05 |  | No | 2020-08-24 | No | Not Required | Not Required | Not Required
21INR0265 | Sisters Solar | SS Completed, FIS Started, No IA | Oberon Solar LLC | tapping the 345 kV line connecting Moss Switch (Bus# 1018) to Wolf Switching Station (Bus# 11010) | Ector | WEST | 2025-09-15 | SOL | PV | 301.42 |  | 2019-02-28 | 2019-02-28 | 2019-03-29 | 2019-02-20 |  | Yes |  | No | Not Required | Not Required | Not Required
21INR0268 | Greyhound Solar | SS Completed, FIS Started, IA | Rockhound Solar 2, LLC dba "Greyhound Solar" | Tap 345kV 11010 Wolf - 1018 Moss | Ector | WEST | 2025-05-01 | SOL | PV | 608.7 |  | 2019-03-14 | 2019-03-28 | 2019-06-05 | 2019-03-21 |  | No | 2022-01-15 | No | Not Required | Not Required | Not Required
21INR0271 | TERRANOVA SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY&INFRASTRUCTURE LLC | 60506 Avogadro 345kV | Knox | WEST | 2024-03-01 | SOL | PV | 152.32 |  | 2019-12-05 | 2019-04-01 | 2019-06-10 | 2019-12-12 |  |  |  | No |  |  | Not Required
21INR0274 | Carol Solar | SS Completed, FIS Started, IA | Carol Solar LLC | 23906 AJ Swope 345kV | Potter | PANHANDLE | 2025-12-31 | SOL | PV | 223.2 |  | 2019-06-11 | 2019-03-26 | 2019-06-11 | 2019-06-07 |  | No | 2020-09-11 | No | Not Required | Not Required | Not Required
21INR0278 | Fighting Jays Solar | SS Completed, FIS Completed, IA | AP Solar Holdings, LLC | tap 345kV 44000 WA Parish - 44200 Hillje c64 | Fort Bend | HOUSTON | 2023-12-23 | SOL | PV | 351.29 |  | 2019-04-30 | 2019-03-26 | 2019-06-17 | 2019-03-20 | 2021-06-30 | No | 2020-06-22 | Yes | Not Required | Not Required | Not Required | 2021-07-29 | 2021-07-29 | 2021-07-29 |  |  | 2022-03-18 | 2022-03-31
21INR0280 | Edgewater Storage | SS Completed, FIS Started, No IA | Edgewater Battery Storage LLC | 210 Reagor Springs 69kV | Ellis | NORTH | 2024-11-01 | OTH | BA | 50 |  | 2019-04-02 | 2019-04-08 | 2019-07-04 | 2019-03-24 |  | No |  | No | Not Required | Not Required | Not Required
21INR0294 | Mountaineer Solar | SS Completed, FIS Started, No IA | Mustang Mountaineer Solar LLC | 1444 Brown 345 kV | Brown | NORTH | 2026-06-30 | SOL | PV | 332 |  | 2019-12-11 | 2019-04-16 | 2019-06-11 | 2019-12-08 |  | No |  | No | Not Required | Not Required | Not Required
21INR0295 | Sterling Prairie Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 8608 Pavlov A 138kV | Matagorda | COASTAL | 2025-12-15 | SOL | PV | 119.91 |  | 2020-01-22 | 2019-04-24 | 2019-07-23 | 2020-01-21 |  | No |  | No |  |  | Not Required
21INR0302 | Aureola Solar | SS Completed, FIS Completed, IA | Ben Milam Solar 1 | tap 345kV 3687 Bell E - 39950 TNTNP One, one-third from Bell | Milam | SOUTH | 2024-06-28 | SOL | PV | 203 |  | 2020-07-15 | 2019-12-19 | 2020-03-12 | 2020-07-06 | 2022-09-19 |  | 2022-09-19 | Yes | Not Required | Not Required | Not Required | 2023-08-01 | 2023-08-01 | 2023-08-01
21INR0303 | Mandorla Solar | SS Completed, FIS Completed, IA | Ben Milam Solar 2 | tap 345kV 3687 Bell E - 39950 TNTNP One, one-half from Bell | Milam | SOUTH | 2024-11-29 | SOL | PV | 254 |  | 2020-07-15 | 2020-01-22 | 2020-04-13 | 2020-07-06 | 2022-09-19 |  | 2022-09-19 | Yes | Not Required | Not Required | Not Required | 2023-08-24 | 2023-10-31 | 2023-10-31
21INR0304 | Halo Solar | SS Completed, FIS Completed, IA | Ben Milam Solar 3 | tap 345kV 3687 Bell E - 39950 TNTNP One, one-fourth from Bell | Bell | NORTH | 2024-06-20 | SOL | PV | 254 |  | 2020-08-10 | 2020-01-22 | 2020-04-13 | 2020-07-06 | 2022-09-19 |  | 2022-08-18 | Yes | Not Required | Not Required | Not Required | 2023-08-01 | 2023-08-01 | 2023-08-01
21INR0314 | AQUAMARINE SOLAR | SS Completed, FIS Started, No IA | BdPU Texas Solar Project II, LLC | tap 138kV 720 Salt Creek Reactor – 6150 Spur | Dickens | PANHANDLE | 2025-10-31 | SOL | PV | 151.69 |  | 2020-02-13 | 2019-05-10 | 2019-07-31 | 2020-01-27 |  |  |  | No | Not Required | Not Required | Not Required
21INR0320 | Ion Solar | SS Completed, FIS Started, No IA | GSE Group LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2026-05-29 | SOL | PV | 384 |  | 2020-02-03 | 2019-05-17 | 2019-08-01 | 2020-01-28 |  |  |  | No |  |  | Not Required
21INR0323 | Spanish Crown | SS Completed, FIS Completed, IA | BPL Crown Solar | Tap 138kV 3420 Temple Pecan Creek - 3410 Lake Creek (138 kV Cow Bayou Switch, a new switching station) | Falls | NORTH | 2023-12-28 | SOL | PV | 103.1 | COD | 2019-05-10 | 2019-05-13 | 2019-07-31 | 2019-05-10 | 2021-07-07 | No | 2021-01-13 | Yes | Not Required | Not Required | Not Required | 2021-01-28 | 2021-05-17 | 2022-04-29 |  |  | 2022-12-28 | 2023-02-09
21INR0324 | Board Creek Wind | SS Completed, FIS Completed, IA | Limestone Wind Project, LLC | 345kV 3386 Outlaw Switch | Navarro | NORTH | 2024-01-31 | WIN | WT | 299.2 | COD | 2019-11-08 | 2019-04-24 | 2019-07-22 | 2019-11-05 | 2022-04-26 | No | 2021-08-19 | Yes | Not Required | Not Required | Not Required | 2022-04-05 | 2022-04-21 | 2022-04-26 |  |  | 2022-09-19 | 2022-10-06
21INR0325 | Sheep Creek Wind | SS Completed, FIS Completed, IA | Century Oak Wind Project, LLC | 68051 Reata 345kV | Callahan | WEST | 2024-01-31 | WIN | WT | 153 |  | 2020-02-05 | 2019-05-30 | 2019-08-15 | 2020-01-29 | 2023-04-22 | No | 2021-10-01 | Yes | Not Required | Not Required | Not Required | 2023-05-01 | 2023-05-01 | 2023-05-01 |  |  | 2023-09-14 | 2023-11-17
21INR0326 | Dove Run Solar | SS Completed, FIS Started, IA | Dove Run Solar Project, LLC | tap 138kV 8510 Falfurrias - 8695 Crestonio | Duval | SOUTH | 2026-07-31 | SOL | PV | 120.59 |  | 2019-05-07 | 2019-05-07 | 2019-07-23 | 2019-05-02 |  |  | 2023-10-31 | Yes |  |  | Not Required
21INR0334 | NIGHTFALL SOLAR | SS Completed, FIS Started, IA | BDPU SOLAR NIGHTFALL, LLC | Tap 138kV 8241 Razorback - 8234 Uvalde | Uvalde | SOUTH | 2025-12-31 | SOL | PV | 152.1 |  | 2020-09-24 | 2019-05-10 | 2019-07-31 | 2020-01-24 |  |  | 2023-10-26 | Yes |  |  | Not Required
21INR0341 | Space City Solar | SS Completed, FIS Started, IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2025-07-01 | SOL | PV | 609.74 |  | 2019-10-28 | 2019-11-01 | 2020-03-06 | 2019-10-15 |  |  | 2021-01-06 | Yes | Not Required | Not Required | Not Required | 2021-01-11
21INR0343 | Flag City Solar | SS Completed, FIS Completed, No IA | Flag City Solar Project, LLC | tap 138kV 5588 Red Bluff - 5546 Danevang c1 | Jackson | SOUTH | 2025-07-01 | SOL | PV | 167.3 |  | 2019-05-07 | 2019-05-07 | 2019-07-29 | 2019-05-02 | 2023-01-25 | No |  | No | Not Required | Not Required | Not Required
21INR0344 | Lunis Creek Solar SLF | SS Completed, FIS Started, IA | Lunis Creek Solar Project, LLC | tap 345 kV Static (#8676) - South Texas Project (#5915) | Jackson | SOUTH | 2025-07-01 | SOL | PV | 617.12 |  | 2019-05-02 | 2019-05-02 | 2019-07-03 | 2019-05-02 |  |  | 2021-10-29 | Yes |  |  | Not Required | 2022-09-27
21INR0347 | Lunis Creek Storage SLF | SS Completed, FIS Started, No IA | Lunis Creek Solar Project, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2025-07-01 | OTH | BA | 0 |  | 2019-05-02 | 2019-05-02 | 2019-07-30 | 2019-05-02 |  |  |  | No |  |  | Not Required
21INR0349 | Pearl Crescent Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 7640 Rock Island 138kV | Colorado | SOUTH | 2025-12-08 | SOL | PV | 208.35 |  | 2019-06-04 | 2019-05-31 | 2019-08-26 | 2019-09-30 |  |  |  | No |  |  | Not Required
21INR0351 | 7V Solar | SS Completed, FIS Completed, IA | 7V Solar Ranch, LLC | tap 138kV 7248 Flatonia - 7274 Plum | Fayette | SOUTH | 2024-03-15 | SOL | PV | 240.63 |  | 2019-10-16 | 2019-04-16 | 2019-07-03 | 2019-08-16 | 2022-10-21 |  | 2020-09-01 | Yes | Not Required | Not Required | Not Required | 2022-10-07 | 2022-10-24 | 2022-10-28 |  |  | 2023-11-20 | 2023-12-13
21INR0353 | Big Elm Solar | SS Completed, FIS Completed, IA | Big Elm Solar, LLC | 345kV #3404 Belfalls Switch | Bell | NORTH | 2024-06-19 | SOL | PV | 200.29 | COD | 2020-03-25 | 2019-06-27 | 2019-09-23 | 2020-03-23 | 2023-07-25 | No | 2022-09-01 | Yes |  |  | Not Required | 2022-09-08 | 2023-07-31 | 2023-07-31
21INR0356 | Welder Solar | SS Completed, FIS Started, No IA | Welder Solar, LLC | tap 345kV 8624 Grissom - 8455 Lon Hill | Bee | SOUTH | 2024-10-31 | SOL | PV | 300 |  | 2020-07-08 | 2019-06-18 | 2019-09-13 | 2020-03-16 |  |  |  | No | Not Required | Not Required | Not Required
21INR0359 | Hickerson Solar | SS Completed, FIS Started, No IA | Hickerson Solar | tap 345kV 68091 Navarro - 68040 Kopperl | Bosque | NORTH | 2025-12-31 | SOL | PV | 316.3 |  | 2020-05-13 | 2019-05-29 | 2019-08-23 | 2020-02-19 |  | Yes |  | No |  |  | Not Required
21INR0362 | Oystercatcher Solar | SS Completed, FIS Started, IA | Oystercatcher Solar, LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2025-09-15 | SOL | PV | 220.33 |  | 2020-01-15 | 2019-05-30 | 2019-08-07 | 2019-12-20 |  | Yes | 2021-08-20 | No | Not Required | Not Required | Not Required
21INR0368 | Eliza Solar | SS Completed, FIS Completed, IA | Ables Springs Solar, LLC | tap 345kV 2478 Royse - 3103 Shamburger | Kaufman | NORTH | 2024-11-01 | SOL | PV | 151.6 |  | 2020-05-04 | 2019-06-21 | 2019-08-30 | 2020-02-24 | 2023-10-30 | No | 2022-08-04 | Yes | Not Required | Not Required | Not Required | 2023-02-17 | 2023-09-18 | 2023-10-30
21INR0371 | HIP Solar Project | SS Completed, FIS Started, No IA | ConnectGen Operating LLC | tap 345kV 967 Gibbons Creek - 46020 Limestone ckt 18 | Leon | NORTH | 2025-07-01 | SOL | PV | 137.6 |  | 2019-08-27 | 2019-08-16 | 2019-11-05 | 2019-08-22 |  |  |  | No |  |  | Not Required
21INR0376 | Barranca Wind III | SS Completed, FIS Started, No IA | Barranca Wind Energy, LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2026-09-23 | WIN | WT | 205 |  | 2019-07-12 | 2019-06-26 | 2019-09-23 | 2019-07-11 |  |  |  | No |  |  | Not Required
21INR0379 | Ash Creek Solar | SS Completed, FIS Completed, IA | Ash Creek Solar LLC | 68090 SAM SW 345kV | Hill | NORTH | 2025-01-31 | SOL | PV | 408.85 |  | 2020-10-27 | 2019-07-29 | 2019-10-25 | 2019-07-19 | 2022-07-25 | No | 2022-11-11 | Yes |  |  | Not Required
21INR0380 | Charolais Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 44000 W A Parish - 5915 STP | Matagorda | COASTAL | 2026-12-15 | SOL | PV | 261.63 |  | 2020-05-11 | 2019-08-05 | 2019-10-31 | 2020-04-27 |  | Yes |  | No |  |  | Not Required
21INR0387 | Anchor Wind | SS Completed, FIS Completed, IA | Ranchland Wind Project,LLC | 345 kV Aspire Station (68011) | Eastland | NORTH | 2023-10-30 | WIN | WT | 98.9 |  | 2019-06-26 | 2019-08-26 | 2019-11-12 | 2019-08-13 | 2021-04-30 | No | 2020-11-30 | Yes | Not Required | Not Required | Not Required | 2020-12-02 | 2021-04-30 | 2021-04-30 |  |  | 2021-11-29 | 2022-02-11
21INR0389 | Hollywood Solar | SS Completed, FIS Completed, IA | Red Tailed Hawk Solar LLC | tap 345kV 44200 Bailey-44040 Hillje ckt 72 | Wharton | SOUTH | 2024-06-30 | SOL | PV | 353.41 |  | 2019-07-01 | 2019-07-08 | 2019-10-02 | 2019-07-01 | 2022-08-31 | No | 2020-08-28 | Yes | Not Required | Not Required | Not Required | 2023-02-03 | 2023-02-03 | 2023-02-03 |  |  | 2023-10-26 | 2023-11-10
21INR0391 | Grandslam Solar | SS Completed, FIS Started, IA | Grandslam Solar | 5700 Miracle Lake 138kV | Atascosa | SOUTH | 2025-03-01 | SOL | PV | 121.89 |  | 2019-09-03 | 2019-07-29 | 2019-10-30 | 2019-07-26 |  |  | 2021-01-29 | No | Not Required | Not Required | Not Required
21INR0393 | Talitha Solar | SS Completed, FIS Completed, IA | Talitha Energy Project, LLC | 5660 Orange Grove 138kV | Jim Wells | SOUTH | 2024-06-30 | SOL | PV | 131.03 |  | 2019-07-12 | 2019-07-12 | 2019-09-09 | 2019-07-08 | 2021-12-07 | No | 2022-06-08 | Yes |  |  | Not Required
21INR0395 | SunRay | SS Completed, FIS Completed, IA | AP Sunray LLC | Dry Frio 138 kV station | Uvalde | SOUTH | 2024-05-23 | SOL | PV | 203.5 |  | 2019-09-13 | 2019-07-17 | 2019-10-14 | 2019-07-15 | 2023-10-20 | No | 2021-07-06 | Yes | Not Required | Not Required | Not Required | 2022-08-24 | 2023-08-24 | 2023-10-30
21INR0401 | Young Wind | SS Completed, FIS Completed, IA | Young Wind, LLC | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek | Young | WEST | 2024-01-31 | WIN | WT | 499.14 |  | 2020-04-13 | 2019-07-29 | 2019-10-25 | 2020-03-27 | 2021-05-28 | No | 2022-02-18 | Yes | Not Required | Not Required | Not Required | 2022-03-31 | 2022-04-22 | 2022-04-22 |  |  | 2022-12-01 | 2022-12-08
21INR0406 | Buffalo Creek | SS Completed, FIS Completed, IA | Lincoln Clean Energy Development | tap 345kV 44000 WA Parish – 44040 BAILEY | Fort Bend | HOUSTON | 2024-06-01 | SOL | PV | 438.75 |  | 2019-08-06 | 2019-08-01 | 2019-10-30 | 2019-07-31 | 2021-04-23 | No | 2020-04-16 | Yes | Not Required | Not Required | Not Required | 2020-05-06 | 2021-04-15 | 2021-04-23 |  |  | 2021-12-08 | 2022-01-06
21INR0413 | Big Star Solar | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | Tap 345kV 9074 Lytton - 9073 Holman | Bastrop | SOUTH | 2024-01-31 | SOL | PV | 203.1 |  | 2020-01-02 | 2019-08-27 | 2019-11-08 | 2019-12-20 | 2021-07-19 |  | 2020-10-02 | Yes |  |  | Not Required | 2020-12-04 | 2021-07-19 | 2021-07-30 |  |  | 2022-12-06 | 2022-12-19
21INR0414 | Jayhawk Solar | SS Completed, FIS Started, No IA | Renewable Energy Ventures, LLC | tap 345kV 1030 Morgan - 76030 Gasconades | Mitchell | WEST | 2025-10-30 | SOL | PV | 101.5 |  | 2020-06-22 | 2019-08-05 | 2019-10-31 | 2020-01-17 |  |  |  | No |  |  | Not Required
21INR0421 | Armadillo Solar | SS Completed, FIS Started, IA | Lincoln Clean Energy Development | 3478 Navarro 138kV | Navarro | NORTH | 2025-10-15 | SOL | PV | 204 |  | 2019-09-05 | 2019-08-28 | 2019-11-22 | 2019-08-28 |  | No | 2021-02-02 | Yes | Not Required | Not Required | Not Required
21INR0424 | Tierra Bonita Solar | SS Completed, FIS Completed, IA | Greasewood II LLC | 844 Nevilesw – 134905 Greaswod 345 kV | Pecos | WEST | 2024-10-29 | SOL | PV | 306.9 | MW Size | 2020-09-18 | 2019-10-15 | 2020-01-02 | 2020-06-26 | 2023-08-18 | No | 2022-09-08 | Yes | Not Required | Not Required | Not Required | 2023-07-24
21INR0428 | Nabatoto Solar North | SS Completed, FIS Completed, IA | CG Leon County II LLC | tap 345kV 967 Gibbons Creek - 46020 Limestone ckt 50 | Leon | NORTH | 2025-02-01 | SOL | PV | 365.7 |  | 2019-08-16 | 2019-09-23 | 2019-12-10 | 2019-09-11 | 2023-12-05 | Yes | 2021-02-26 | No |  |  | Not Required
21INR0430 | Holstein 2 Energy Storage | SS Completed, FIS Started, No IA | 229HD 8me LLC | 11406 Central Bluff 345kV | Nolan | WEST | 2026-05-01 | OTH | BA | 102.42 |  | 2019-09-16 | 2019-08-26 | 2019-11-12 | 2019-08-16 |  |  |  | No |  |  | Not Required
21INR0431 | Galloway 2 Solar | SS Completed, FIS Completed, IA | 224WB 8me LLC | 7077 Amos Cr 345kV | Concho | WEST | 2024-01-05 | SOL | PV | 113.88 | COD | 2019-08-28 | 2019-08-28 | 2017-10-02 | 2019-08-28 | 2022-08-23 |  | 2019-12-20 | Yes | Not Required | Not Required | Not Required | 2020-07-27 | 2021-03-23 | 2022-10-31 |  |  | 2023-04-03 | 2023-06-23
21INR0432 | Diversion Wind | SS Completed, FIS Started, No IA | Diversion Wind Development LLC | 6101 Riley 345kV | Baylor | WEST | 2024-12-30 | WIN | WT | 300 |  | 2020-07-15 | 2019-09-10 | 2019-12-04 | 2020-06-04 |  |  |  | No |  |  | Not Required
21INR0434 | Golinda Solar | SS Completed, FIS Completed, IA | BPL Sol Solar | Tap 138kV 3420 Temple Pecan Creek - 3410 Lake Creek | Falls | NORTH | 2023-12-29 | SOL | PV | 103.1 | COD | 2019-08-26 | 2019-09-23 | 2019-12-10 | 2019-09-03 | 2021-07-07 | No | 2021-03-21 | Yes | Not Required | Not Required | Not Required | 2021-01-28 | 2021-08-05 | 2022-04-29 |  |  | 2023-01-13 | 2023-02-03
21INR0440 | Wren Solar | SS Completed, FIS Started, No IA | Wren Solar, LLC | 8601 Cebolla 345kV | Willacy | COASTAL | 2024-10-31 | SOL | PV | 170 |  | 2020-10-27 | 2019-10-15 | 2020-01-02 | 2020-07-28 |  |  |  | No | Not Required | Not Required | Not Required
21INR0442 | Myrtle Storage | SS Completed, FIS Completed, IA | Myrtle Storage, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2024-01-19 | OTH | BA | 151.2 |  | 2020-08-03 | 2019-11-04 | 2020-02-07 | 2020-07-30 | 2023-01-31 |  | 2022-06-13 | Yes |  |  | Not Required | 2023-01-31 | 2023-01-31 | 2023-01-31 |  |  | 2023-10-19 | 2023-11-10
21INR0443 | Cottonwood Bayou Storage | SS Completed, FIS Started, IA | Cottonwood Bayou Storage, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2025-03-05 | OTH | BA | 150.83 | COD | 2020-07-20 | 2019-10-31 | 2020-01-23 | 2020-07-17 |  | No | 2022-03-18 | No |  |  | Not Required
21INR0444 | Long Point Storage | SS Completed, FIS Completed, IA | Long Point Storage, LLC | 138 KV (CEHE Sub) Tap Burke (42410) - Eagle Nest (42430) ckt 02 | Brazoria | COASTAL | 2025-12-01 | OTH | BA | 100.62 |  | 2020-09-17 | 2019-11-01 | 2020-02-05 | 2020-09-01 | 2023-01-05 | No | 2023-08-28 | No | Not Required | Not Required | Not Required
21INR0446 | Knickerbocker Storage SLF | SS Completed, FIS Started, No IA | Knickerbocker Solar LLC | Tap 345kV 76003 Big Hill - 76009 Twin Buttes | Tom Green | WEST | 2025-01-15 | OTH | BA | 0 |  | 2020-01-10 | 2019-12-19 | 2020-03-06 | 2019-12-05 |  |  |  | No |  |  | Not Required
21INR0450 | Danish Fields Storage | SS Completed, FIS Completed, IA | Danish Fields Storage, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2024-03-06 | OTH | BA | 152.43 | COD | 2020-07-20 | 2019-10-31 | 2020-01-24 | 2020-07-17 | 2023-07-24 | No | 2022-06-13 | Yes | Not Required | Not Required | Not Required | 2023-07-11 | 2023-07-24 | 2023-07-31 |  |  | 2023-12-18 | 2023-12-28
21INR0454 | Racetrack Solar | SS Completed, FIS Started, No IA | Innergex Renewables USA, LLC | tap 138kV 8234 Uvalde - 8236 West Batesville | Uvalde | SOUTH | 2026-12-01 | SOL | PV | 121 |  | 2020-09-08 | 2019-11-18 | 2020-01-28 | 2020-07-09 |  |  |  | No |  |  | Not Required
21INR0455 | Independence Trail Storage | SS Completed, FIS Started, No IA | KCE TX 16, LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2026-01-01 | OTH | BA | 100 |  | 2019-11-11 | 2019-12-03 | 2020-02-24 | 2019-10-22 |  |  |  | No | Not Required | Not Required | Not Required
21INR0456 | Maleza Storage | SS Completed, FIS Started, No IA | Brush Storage, LLC | tap Blue – Hillje 345 kv Ckt.#27 | Wharton | SOUTH | 2024-12-01 | OTH | BA | 150.83 |  | 2020-08-24 | 2019-10-31 | 2020-01-24 | 2020-08-18 |  |  |  | No |  |  | Not Required
21INR0458 | Porter Solar | SS Completed, FIS Completed, IA | Porter Solar, LLC | tap 345kv 1429 Jacksboro - 1730 Krum West | Denton | NORTH | 2024-04-30 | SOL | PV | 245.83 |  | 2020-08-24 | 2020-01-30 | 2020-04-17 | 2020-08-06 | 2023-04-28 | No | 2022-02-03 | Yes | Not Required | Not Required | Not Required | 2022-08-18 | 2023-04-28 | 2023-04-28 |  |  | 2023-11-20 | 2023-12-11
21INR0467 | Apogee Wind | SS Completed, FIS Completed, IA | EDF Renewables Development, Inc. | Tap 345kV 6235 Mulberry - 6076 Foxtail | Haskell | WEST | 2023-12-01 | WIN | WT | 393.24 |  | 2019-11-27 | 2019-12-03 | 2020-03-08 | 2019-11-18 | 2021-04-30 | No | 2022-05-13 | Yes | Not Required | Not Required | Not Required | 2020-03-27 | 2021-04-30 | 2021-04-30 |  |  | 2021-12-22 | 2022-01-11
21INR0469 | Big Star Storage | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | Tap 345kV 9074 Lytton - 9073 Holman | Bastrop | SOUTH | 2024-01-19 | OTH | BA | 80 |  | 2020-10-23 | 2020-01-02 | 2020-03-26 | 2020-08-28 | 2021-07-19 |  | 2020-10-02 | Yes |  |  | Not Required | 2021-08-18 | 2021-08-18 | 2021-07-30 |  |  | 2023-04-13 | 2023-11-06
21INR0470 | Pearl Crescent Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 7640 Rock Island 138kV | Colorado | SOUTH | 2025-12-08 | OTH | BA | 50.26 |  | 2020-09-18 | 2019-12-20 | 2020-03-12 | 2020-04-10 |  |  |  | No |  |  | Not Required
21INR0481 | Old Lunar Solar | SS Completed, FIS Completed, No IA | EDF Renewables Development, Inc. | tap 345kV 5133 Elm Creek - 5915 STP (CKT 1) | Wharton | SOUTH | 2024-12-01 | SOL | PV | 609.74 |  | 2020-03-30 | 2019-12-17 | 2020-03-11 | 2019-12-17 | 2021-12-22 | No |  | No | Not Required | Not Required | Not Required
21INR0482 | Sisters Storage | SS Completed, FIS Started, No IA | 174 Power Global Properties | tapping the 345 kV line connecting Moss Switch (Bus# 1018) to Wolf Switching Station (Bus# 11010) | Ector | WEST | 2026-03-15 | OTH | BA | 208.89 |  | 2020-03-30 | 2019-12-18 | 2020-03-11 | 2019-12-18 |  |  |  | No |  |  | Not Required
21INR0483 | Morrow Lake Storage | SS Completed, FIS Started, No IA | Morrow Lake Storage, LLC | 5895 Pearsall 138kV | Frio | SOUTH | 2024-02-08 | OTH | BA | 201.13 |  | 2020-11-10 | 2020-02-07 | 2020-04-30 | 2020-10-26 |  |  |  | No |  |  | Not Required
21INR0484 | Mustang Creek Storage | SS Completed, FIS Completed, IA | Ganado Solar, LLC | tap 138kV 5523 ETP - 78104 Ricebird new sub Galow | Jackson | SOUTH | 2024-01-12 | OTH | BA | 70.5 | COD | 2020-09-22 | 2020-01-02 | 2020-03-23 | 2020-09-11 | 2022-01-20 | No | 2019-01-04 | Yes |  |  | Not Required | 2022-02-21 | 2022-02-21 | 2022-04-06 |  |  | 2023-04-20 | 2023-07-12
21INR0490 | Samson Solar 2 | SS Completed, FIS Completed, IA | Samson Solar Energy II LLC | 345 kV TTRSW 11688 | Lamar | NORTH | 2024-12-15 | SOL | PV | 203 |  | 2020-01-14 | 2020-01-13 | 2019-01-04 | 2020-01-13 | 2020-06-09 |  | 2020-08-27 | Yes | Not Required | Not Required | Not Required | 2021-04-12 | 2022-08-12 | 2022-08-12
21INR0491 | Samson Solar 3 | SS Completed, FIS Completed, IA | Samson Solar Energy III LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2024-02-29 | SOL | PV | 250 | COD | 2020-01-14 | 2020-01-13 | 2019-01-04 | 2020-01-13 | 2020-06-09 |  | 2020-08-27 | Yes | Not Required | Not Required | Not Required | 2020-08-27 | 2020-10-15 | 2020-10-26 |  |  | 2021-06-30 | 2021-10-26
21INR0492 | Stockyard Grid Batt | SS Completed, FIS Completed, IA | Stockyard Grid, LLC | 2082 Hicks 138kV | Tarrant | NORTH | 2024-03-29 | OTH | BA | 150.6 |  | 2020-02-05 | 2020-01-13 | 2020-03-30 | 2020-01-13 | 2022-07-14 | No | 2022-10-26 | Yes | Not Required | Not Required | Not Required | 2022-10-26 | 2022-10-26 | 2022-10-26
21INR0499 | Neptune Solar | SS Completed, FIS Completed, IA | Matagorda Solar LLC | 110471 Formosa 138 kV | Jackson | SOUTH | 2025-12-22 | SOL | PV | 204.65 |  | 2020-04-16 | 2020-04-13 | 2020-07-07 | 2020-03-26 | 2021-07-27 | No | 2000-05-30 | Yes |  |  | Not Required | 2022-04-11 | 2022-04-11 | 2022-03-31
21INR0500 | SkySealy | SS Completed, FIS Completed, IA | Sky Global Power Two, LLC | tap 138kV 44700 Gebhardt - 44740 Wallis circuit 65 | Austin | SOUTH | 2025-06-01 | GAS | IC | 149.4 |  | 2020-06-19 | 2020-05-01 | 2020-07-15 | 2020-03-20 | 2022-10-21 | No | 2023-02-03 | No | 2020-04-15 | Not Required
21INR0505 | Ramsey Storage | SS Completed, FIS Started, IA | Hecate Energy Ramsey Storage LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2025-12-31 | OTH | BA | 510.4 |  | 2021-01-20 | 2020-05-20 | 2020-07-30 | 2020-12-23 |  | No | 2022-08-11 | Yes |  |  | Not Required | 2023-08-18
21INR0506 | Ty Cooke | SS Completed, FIS Completed, IA | City of Lubbock, by and through Lubbock Power and Light | 59166 LP Holly 69kV | Lubbock | PANHANDLE | 2021-11-15 | GAS | GT | 33 |  | 2020-10-23 | 2020-08-21 | 2020-08-22 | 2020-08-10 | 2020-10-23 |  | 2020-10-30 | Yes | 2004-02-27 | Not Required | 2020-10-05 | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2021-07-09 | 2021-07-14
21INR0507 | Arana Creek Batt | SS Completed, FIS Started, No IA | Arana Creek LLC | 5648 Loyola 138kV | Kleberg | COASTAL | 2025-05-31 | OTH | BA | 153.5 |  | 2020-10-12 | 2020-06-03 | 2020-08-10 | 2020-10-06 |  |  |  | No |  |  | Not Required
21INR0508 | Angels Creek | SS Completed, FIS Completed, No IA | Angels Creek LLC | 5888 Bruni 69kV | Webb | SOUTH | 2024-06-01 | OTH | BA | 31.68 |  | 2020-07-27 | 2020-06-03 | 2020-08-18 | 2020-07-23 | 2021-06-22 | No |  | No |  |  | Not Required
21INR0509 | McClure Solar | SS Completed, FIS Started, No IA | McClure Solar LLC | tap 69kV 785 Oran - 343 Morris Sheppard | Palo Pinto | NORTH | 2024-12-28 | SOL | PV | 105.73 |  | 2021-03-18 | 2020-06-03 | 2020-08-18 | 2021-02-24 |  | No |  | No |  |  | Not Required
21INR0511 | Wolf Ridge Repower | SS Completed, FIS Completed, IA | Wolf Ridge Wind Energy, LLC | 730 Wolf Ridge 138kV | Cooke | NORTH | 2024-04-02 | WIN | WT | 9 |  | 2020-10-09 | 2020-06-26 | 2020-09-14 | 2020-10-08 | 2023-05-01 | No | 2007-11-01 | Yes | Not Required | Not Required | Not Required | 2023-03-31 | 2023-03-31 | 2023-05-01 |  |  |  | 2023-10-10
21INR0515 | Roadrunner Crossing Wind II SLF | SS Completed, FIS Completed, IA | Roadrunner Crossing Wind Farm, LLC | tap 345kV 68005 WShack - 68050 Romney | Eastland | NORTH | 2025-01-20 | WIN | WT | 126.72 |  | 2020-10-27 | 2020-07-02 | 2020-09-14 | 2020-07-09 | 2023-05-01 |  | 2020-04-17 | Yes | Not Required | Not Required | Not Required | 2023-05-01 | 2023-05-01 | 2023-05-01
21INR0517 | Tidwell Prairie Storage 1 | SS Completed, FIS Started, IA | Tidwell Prairie LLC | 39950 TNP ONE PLANT 345kV - 3400 TWIN OAK | Robertson | NORTH | 2025-07-15 | OTH | BA | 200 | COD | 2020-07-23 | 2020-07-24 | 2020-10-20 | 2020-07-16 |  |  | 2022-11-03 | Yes |  |  | Not Required
21INR0520 | Viking Solar | SS Completed, FIS Started, No IA | Yellow Viking Development One, LLC | ap 345kV 1900 Comanche Peak - 11886 Timberview Switch | Hood | NORTH | 2026-11-07 | SOL | PV | 288.99 |  | 2020-10-09 | 2020-10-23 | 2021-01-12 | 2020-08-20 |  |  |  | No |  |  | Not Required
21INR0527 | Hays Energy Unit 3 Repower | SS Completed, FIS Started, No IA | HAYS ENERGY, LLC | 7043 Hays 345kV | Hays | SOUTH | 2024-08-30 | GAS | GT | 18 | COD | 2021-02-09 | 2020-10-07 | 2020-12-30 | 2021-02-05 |  |  |  | No | 2020-11-05
21INR0529 | Topaz Energy Storage | SS Completed, FIS Started, No IA | WattBridge Energy, LLC | 38745 TN Attwater 138kV | Galveston | HOUSTON | 2025-04-01 | OTH | BA | 202.32 |  | 2020-11-25 | 2020-12-03 | 2021-02-19 | 2020-11-25 |  |  |  | No |  |  | Not Required
21INR0532 | Brazos Wind Repower | SS Completed, FIS Completed, No IA | BRAZOS WIND VENTURES, LLC | 1064 Sun 138kV | Scurry | WEST | 2024-01-31 | WIN | WT | 22.4 | COD | 2020-12-18 | 2020-12-22 | 2021-03-10 | 2020-11-30 | 2022-04-01 |  |  | Yes | Not Required | Not Required | Not Required | 2022-08-03 | 2022-10-21 | 2023-02-03 |  |  | 2023-04-25 | 2023-07-01
21INR0534 | Midlothian Unit 2 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1939 Midlothian ELP 345kV | Ellis | NORTH | 2024-07-16 | GAS | GT | 18 |  | 2021-04-28 | 2021-01-25 | 2021-04-30 | 2021-02-08 |  |  |  | No
21INR0538 | Blue Jay Solar II | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2023-12-31 | SOL | PV | 68.95 | COD | 2018-02-15 | 2021-04-13 | 2021-04-14 |  | 2021-04-26 | No | 2020-10-26 | Yes |  |  | Not Required | 2020-12-02 | 2021-04-26 | 2021-04-29 |  |  | 2021-11-11 | 2021-11-19
21INR0539 | Anchor Wind II | SS Completed, FIS Completed, IA | Ranchland Wind Project II, LLC | tap 345kV 68008 LATIMER - 68010 ROMNEY | Eastland | NORTH | 2023-10-30 | WIN | WT | 128.7 |  | 2019-06-26 | 2021-04-13 | 2021-04-14 |  | 2021-04-30 | No | 2020-11-30 | Yes |  |  | Not Required | 2021-04-30 | 2021-04-30 | 2021-04-30 |  |  | 2021-11-29 | 2022-02-11
21INR0543 | Jefferson Enterprise Energy | SS Completed, FIS Completed, No IA | ONCOR | 3118 LUFKIN SWITCH 138kV | Angelina | NORTH | 2025-04-15 | BIO | ST | 53 |  | 2022-06-08 | 2021-09-24 | 2021-12-02 | 2022-05-26 | 2023-03-10 |  |  | No
21INR0546 | Anchor Wind III | SS Completed, FIS Completed, IA | RANCHLAND WIND PROJECT LLC | 345 kV Aspire Station (68011) | Eastland | NORTH | 2023-10-30 | WIN | WT | 16 |  | 2019-06-26 | 2021-12-03 | 2022-03-01 |  | 2021-04-30 | No | 2020-11-30 | Yes | Not Required | Not Required | Not Required | 2020-12-02 | 2021-04-30 | 2021-04-30 |  |  | 2021-11-29 | 2022-12-13
22INR0202 | Delilah Solar 1 | SS Completed, FIS Completed, IA | Delilah Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2024-06-30 | SOL | PV | 300 |  | 2019-05-13 | 2018-11-20 | 2019-01-03 | 2019-05-03 | 2020-06-09 | No | 2020-12-22 | Yes | Not Required | Not Required | Not Required | 2021-03-23 | 2021-03-23 | 2021-04-27 |  |  | 2023-07-11
22INR0203 | Delilah Solar 2 | SS Completed, FIS Completed, IA | Delilah Solar Energy II LLC | 345 kV TTRSW 11688 | Lamar | NORTH | 2025-04-15 | SOL | PV | 317.58 |  | 2019-05-13 | 2018-11-20 | 2019-01-03 | 2019-05-03 | 2020-06-09 | No | 2020-12-22 | Yes | Not Required | Not Required | Not Required | 2021-03-23 | 2022-08-12 | 2022-08-12
22INR0205 | Sbranch Solar | SS Completed, FIS Completed, IA | Bernard Creek Solar, LLC | Tap 138kV 44190 East Bernard - 44130 Caney | Wharton | SOUTH | 2023-12-31 | SOL | PV | 233.52 |  | 2019-04-01 | 2019-01-03 | 2019-03-13 | 2019-03-29 | 2021-07-29 | No | 2020-07-26 | Yes | Not Required | Not Required | Not Required | 2020-10-07 | 2021-07-06 | 2021-07-29 |  |  | 2022-09-12 | 2023-11-21
22INR0209 | Felix North Solar | SS Completed, FIS Started, No IA | Crescent Solar, LLC | 6101 Riley 345kV | Wilbarger | WEST | 2027-07-31 | SOL | PV | 100.54 |  | 2019-09-23 | 2019-01-17 | 2019-04-02 | 2019-09-20 |  |  |  | No | Not Required | Not Required | Not Required
22INR0211 | Schoolhouse Solar | SS Completed, FIS Started, IA | Schoolhouse Solar, LLC | tap 345kV 7040 Austrop - 13429 Sandow | Lee | SOUTH | 2025-09-22 | SOL | PV | 150.84 |  | 2019-10-08 | 2019-01-30 | 2019-04-09 | 2019-10-02 |  | No | 2021-07-11 | No | Not Required | Not Required | Not Required
22INR0215 | TEXAS SOLAR NOVA 3 | SS Completed, FIS Started, No IA | Texas Solar Nova 1, LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2026-01-31 | SOL | PV | 200.2 |  | 2019-05-28 | 2019-06-24 | 2015-12-30 | 2019-06-19 |  |  |  | No |  |  | Not Required
22INR0218 | Greyhound Solar 2 | SS Completed, FIS Started, No IA | Greyhound Solar 2 | tap 345kV dbl ckt 11010 Wolf - 1018 Moss and 11008 Wolf - 11028 Odessa | Ector | WEST | 2025-12-31 | SOL | PV | 500 |  | 2019-05-23 | 2019-05-14 | 2019-08-05 | 2019-05-10 |  |  |  | No | Not Required | Not Required | Not Required
22INR0220 | Lamkin Solar | SS Completed, FIS Completed, No IA | Commanche Solar, LLC | tap 69kV 258 Hamilton - 273 Gustine | Comanche | NORTH | 2025-12-31 | SOL | PV | 101.5 |  | 2020-05-11 | 2019-06-24 | 2019-09-18 | 2020-03-13 | 2022-07-11 |  |  | No |  |  | Not Required
22INR0237 | Dragan Solar | SS Completed, FIS Completed, No IA | Hecate Comanche Solar LLC | 1440 Comanche 345kV | Comanche | NORTH | 2025-06-01 | SOL | PV | 411 |  | 2019-11-11 | 2019-11-11 | 2020-02-17 | 2019-08-23 | 2022-04-25 | No |  | No |  |  | Not Required
22INR0238 | Rockefeller Solar SLF | SS Completed, FIS Started, No IA | Mittel Rockefeller Solar LLC | 76003 Big Hill 345kV | Schleicher | WEST | 2027-06-01 | SOL | PV | 207.48 | COD | 2020-08-20 | 2019-10-31 | 2020-01-24 | 2020-07-21 |  | No |  | No |  |  | Not Required
22INR0239 | Rockefeller Storage SLF | SS Completed, FIS Started, No IA | Mittel Rockefeller Solar LLC | 76003 Big Hill 345kV | Schleicher | WEST | 2027-06-01 | OTH | BA | 0 | COD | 2020-08-20 | 2019-10-31 | 2020-01-24 | 2020-07-21 |  | No |  | No | Not Required | Not Required | Not Required
22INR0242 | Bright Arrow Solar | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | 11689 CYCLONE 345 KV | Hopkins | NORTH | 2024-06-25 | SOL | PV | 305.07 |  | 2020-03-09 | 2020-02-12 | 2020-05-01 | 2020-03-04 | 2022-04-19 | No | 2021-02-18 | Yes |  |  | Not Required | 2021-03-01 | 2022-04-28 | 2022-04-28 |  |  | 2023-06-28 | 2023-11-27
22INR0243 | Painted Horse Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Wilson | SOUTH | 2025-12-15 | SOL | PV | 200.58 |  | 2021-01-13 | 2020-02-12 | 2020-05-06 | 2020-11-05 |  |  |  | No |  |  | Not Required
22INR0244 | Razorbill Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP to 44200 Hillje 345kV Ckt 64 | Matagorda | COASTAL | 2025-12-15 | SOL | PV | 240 |  | 2020-10-23 | 2020-01-02 | 2020-03-26 | 2020-09-16 |  |  |  | No | Not Required | Not Required | Not Required
22INR0251 | Shaula I Solar | SS Completed, FIS Started, IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | DeWitt | SOUTH | 2025-10-30 | SOL | PV | 205.2 |  | 2019-11-27 | 2019-12-03 | 2020-03-08 | 2019-11-20 |  | No | 2022-02-16 | Yes |  |  | Not Required | 2023-03-27
22INR0254 | Pisgah Ridge Solar | SS Completed, FIS Completed, IA | Pisgah Ridge Solar, LLC | tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2024-03-31 | SOL | PV | 253.85 | COD | 2019-11-01 | 2019-11-01 | 2020-02-07 | 2019-10-21 | 2022-04-29 | No | 2021-01-27 | Yes | Not Required | Not Required | Not Required | 2022-02-28 | 2022-02-28 | 2022-04-27 |  |  | 2022-06-27 | 2022-10-07
22INR0257 | Corazon Solar Phase II | SS Completed, FIS Started, IA | BAYWA R.E. SOLAR PROJECTS | 80219 Lobo 345kV | Webb | SOUTH | 2025-01-12 | SOL | PV | 203.9 |  | 2019-12-16 | 2019-12-19 | 2020-03-12 | 2019-12-04 |  | No | 2020-08-04 | No | Not Required | Not Required | Not Required
22INR0260 | Eliza Storage | SS Completed, FIS Completed, IA | Ables Springs Storage, LLC | tap 345kV 2478 Royse - 3103 Shamburger | Kaufman | NORTH | 2024-11-01 | OTH | BA | 100.2 |  | 2020-08-21 | 2019-12-03 | 2020-02-25 | 2020-08-19 | 2023-10-30 |  | 2022-08-04 | Yes | Not Required | Not Required | Not Required | 2023-02-17 | 2023-09-18 | 2023-10-30
22INR0261 | Dorado Solar | SS Completed, FIS Started, IA | Eldorado Solar Power LLC | 68051 Reata 345kV | Callahan | WEST | 2025-12-31 | SOL | PV | 406.25 |  | 2020-09-02 | 2020-01-09 | 2020-03-30 | 2020-08-27 |  | Yes | 2023-06-19 | Yes | Not Required | Not Required | Not Required | 2023-07-10
22INR0262 | Deville Solar | SS Completed, FIS Started, IA | Deville Solar LLC | 68051 Reata 345kV | Callahan | WEST | 2025-05-31 | SOL | PV | 425.02 |  | 2020-09-02 | 2020-01-22 | 2020-04-08 | 2020-08-27 |  |  | 2023-08-29 | No |  |  | Not Required
22INR0267 | Shaula II Solar | SS Completed, FIS Started, IA | Shaula Energy Project II, LLC | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | DeWitt | SOUTH | 2026-05-30 | SOL | PV | 205.2 |  | 2019-12-27 | 2019-12-18 | 2020-03-12 | 2019-12-18 |  | No | 2022-04-27 | Yes |  |  | Not Required | 2023-03-27
22INR0270 | Brass Fork Solar 1 | SS Completed, FIS Started, IA | Miller's Branch Solar, LLC | Tap 345kV 60703 Gauss - 60514 Clear Crossing (60712 QUASAR) | Haskell | WEST | 2025-12-01 | SOL | PV | 304.78 |  | 2020-08-27 | 2019-12-17 | 2020-03-06 | 2020-06-19 |  |  | 2021-06-14 | Yes |  |  | Not Required | 2021-06-25
22INR0274 | Crowded Star Solar II | SS Completed, FIS Started, IA | Jones City Solar II, LLC | tap 345kV 68001 Claytonville – 68004 Phantom Hill c2 | Jones | WEST | 2026-01-26 | SOL | PV | 189.37 |  | 2019-05-23 | 2020-03-26 | 2020-06-05 | 2021-03-24 |  | No | 2019-12-17 | No | Not Required | Not Required | Not Required
22INR0276 | Trinidad ESS Addition | SS Completed, FIS Completed, No IA | LUMINANT GENERATION COMPANY LLC | Tap 138kV 3127 Trinidad – 3466 Kerens | Henderson | NORTH | 2026-03-20 | OTH | BA | 110 |  | 2021-04-16 | 2019-12-11 | 2020-03-06 | 2020-09-17 | 2023-01-20 | No |  | No | Not Required | Not Required | Not Required
22INR0279 | Clutch City Solar Phase I SLF | SS Completed, FIS Started, IA | HZ Solar I, LLC | tap 138kV 42960 Mustang Bayou – 42100 Hudson CKT #04 | Brazoria | COASTAL | 2026-10-01 | SOL | PV | 200.75 |  | 2020-03-16 | 2020-01-22 | 2020-04-08 | 2020-02-11 |  | No | 2022-09-30 | No |  |  | Not Required
22INR0281 | Pink Solar | SS Completed, FIS Started, IA | General Solar, LLC | 971 Pruitt 138kV | Hunt | NORTH | 2025-10-01 | SOL | PV | 151 |  | 2020-10-21 | 2020-01-30 | 2020-04-20 | 2020-10-16 |  |  | 2022-08-30 | No | Not Required | Not Required | Not Required
22INR0283 | Peregrine Solar | SS Completed, FIS Completed, IA | SP-Peregrine Solar LLC | tap 345kV 8624 Grissom – 8164 Coleto Creek | Goliad | SOUTH | 2024-07-01 | SOL | PV | 301.3 |  | 2020-07-29 | 2020-01-07 | 2020-03-30 | 2020-05-27 | 2021-11-29 | No | 2021-06-19 | Yes |  |  | Not Required | 2021-07-02 | 2023-11-02 | 2023-11-02
22INR0295 | Coral Solar | SS Completed, FIS Completed, IA | Copperhead Solar, LLC | tap 138kV 3410 Lake Creek Switch - 3582 Falls County | Falls | NORTH | 2024-03-31 | SOL | PV | 151.6 |  | 2020-08-17 | 2020-06-03 | 2020-06-16 | 2020-07-30 | 2022-10-31 | No | 2021-12-29 | Yes | Not Required | Not Required | Not Required | 2022-08-05 | 2022-08-05 | 2022-11-07 |  |  | 2023-06-28 | 2023-11-27
22INR0301 | Fortuna Wind | SS Completed, FIS Started, No IA | RWE Renewables Development, LLC | Tap 345kV 1429 Jacksboro - 1730 WKrum | Jack | NORTH | 2026-07-01 | WIN | WT | 295.3 |  | 2021-01-18 | 2020-03-06 | 2020-05-27 | 2020-11-24 |  |  |  | No |  |  | Not Required
22INR0302 | Bright Arrow Storage | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | 11689 CYCLONE 345 KV | Hopkins | NORTH | 2024-02-01 | OTH | BA | 103.56 |  | 2021-01-11 | 2020-03-06 | 2020-05-05 | 2020-11-02 | 2022-08-01 |  | 2022-03-17 | Yes |  |  | Not Required | 2022-08-01 | 2022-08-01 | 2022-08-01 |  |  | 2023-08-14 | 2023-11-13
22INR0307 | Desert Vine Solar | SS Completed, FIS Started, IA | Desert Vine Solar LLC | Tap 138kV 8957 Lopeno - 8299 Zapata Will be TSP’s Snapdragon Station | Zapata | SOUTH | 2026-12-30 | SOL | PV | 121.29 | COD | 2021-10-06 | 2020-05-01 | 2020-07-13 | 2021-02-03 |  | No | 2022-12-16 | Yes |  |  | Not Required
22INR0314 | Lan Solar SLF | SS Completed, FIS Started, No IA | General Solar, LLC | Tap 345kV 1729 Valley South – 1692 Paris Switch | Lamar | NORTH | 2025-08-26 | SOL | PV | 182.2 |  | 2021-10-12 | 2020-05-01 | 2020-07-07 | 2021-01-04 |  | No |  | No | Not Required | Not Required | Not Required
22INR0322 | Paleo BESS | SS Completed, FIS Completed, IA | BRP Paleo BESS LLC | 23920 Blackwater Draw 345kV | Hale | PANHANDLE | 2024-05-19 | OTH | BA | 200.8 | COD | 2020-04-09 | 2020-04-13 | 2020-06-25 | 2020-03-25 | 2021-10-29 |  | 2021-02-05 | Yes | Not Required | Not Required | Not Required | 2021-02-05 | 2021-09-27 | 2021-10-29
22INR0325 | Dickens BESS | SS Completed, FIS Completed, IA | BRP INTERMEDIATECO I LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2024-04-11 | OTH | BA | 200.8 | COD | 2020-04-16 | 2020-04-22 | 2020-07-09 | 2020-04-06 | 2021-09-01 |  | 2020-11-02 | Yes | Not Required | Not Required | Not Required | 2021-01-14 | 2021-10-11 | 2021-10-29
22INR0327 | Hummingbird Storage | SS Completed, FIS Completed, IA | KCE TX 10, LLC | 1730 Krum 345kV | Denton | NORTH | 2024-03-29 | OTH | BA | 103.8 |  | 2020-05-29 | 2020-05-20 | 2020-07-30 | 2020-04-24 | 2022-10-27 | No | 2022-02-23 | Yes |  |  | Not Required | 2022-09-20 | 2022-10-31 | 2022-11-01
22INR0328 | Inertia BESS | SS Completed, FIS Completed, IA | Inertia Energy Storage, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2024-06-30 | OTH | BA | 13 |  | 2020-08-24 | 2020-06-03 | 2021-02-02 | 2020-05-27 | 2022-07-25 | No | 2021-05-04 | Yes | Not Required | Not Required | Not Required | 2021-10-08 | 2022-10-03 | 2022-10-31
22INR0330 | Old Aqueduct Batt | SS Completed, FIS Completed, No IA | Old Aqueduct LLC | 23920 Blackwater 345kV | Hale | PANHANDLE | 2024-03-01 | OTH | BA | 302.94 |  | 2020-07-24 | 2020-05-01 | 2020-07-13 | 2020-06-29 | 2021-10-06 |  |  | No |  |  | Not Required
22INR0332 | Brantley Branch Batt | SS Completed, FIS Started, No IA | Brantley Branch LLC | Mt. Enterprise (Bus # 3116) – Martin Lake 345kv Line (Bus # 3100 | Rusk | NORTH | 2026-09-14 | OTH | BA | 302.35 | MW Size COD | 2020-12-07 | 2020-05-01 | 2020-07-15 | 2020-11-24 |  | No |  | No |  |  | Not Required
22INR0335 | Estonian Solar | SS Completed, FIS Not Started, IA | Enel Green Power Estonian Solar Project, LLC | tap 138kV 17011 Enloe POI – 1816 Commerce Switch | Delta | NORTH | 2024-10-15 | SOL | PV | 202.5 |  | 2020-01-17 | 2020-04-22 | 2020-06-29 |  |  | No | 2021-08-12 | Yes | Not Required | Not Required | Not Required | 2022-04-21 | 2022-07-18 | 2022-07-28 |  |  | 2023-12-05
22INR0336 | Estonian Storage | SS Completed, FIS Completed, IA | Enel Green Power Estonian Solar Project, LLC | tap 138kV 17011 Enloe POI – 1816 Commerce Switch | Delta | NORTH | 2024-08-30 | OTH | BA | 101.6 |  | 2020-02-26 | 2020-04-22 | 2020-06-29 |  | 2022-06-13 | No | 2021-08-12 | Yes | Not Required | Not Required | Not Required | 2022-04-21 | 2022-07-18 | 2022-07-18 |  |  | 2023-12-05
22INR0337 | Skylab Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 5915 STP - 8249 Angstrom | Wharton | SOUTH | 2024-12-01 | SOL | PV | 609.74 |  | 2020-08-10 | 2020-06-03 | 2020-08-11 | 2020-05-27 |  | No |  | No |  |  | Not Required
22INR0338 | Limousin Oak Storage | SS Completed, FIS Completed, IA | KCE TX 15, LLC | 44645 Singleton 345kV | Grimes | NORTH | 2024-04-29 | OTH | BA | 104.62 |  | 2020-05-14 | 2020-05-20 | 2020-07-30 | 2020-04-24 | 2022-07-10 | No | 2022-04-01 | Yes | Not Required | Not Required | Not Required | 2022-07-29 | 2022-07-29 | 2022-07-29
22INR0342 | Matagorda Solar | SS Completed, FIS Completed, IA | Leeward Renewable Energy Development, LLC | 5555 Shropshire 69kV | Matagorda | COASTAL | 2025-12-27 | SOL | PV | 101 |  | 2020-12-08 | 2020-05-01 | 2020-07-15 | 2020-11-05 | 2021-09-14 |  | 2022-06-08 | No |  |  | Not Required
22INR0347 | BRP Crater BESS | SS Completed, FIS Started, No IA | BRP Crater BESS LLC | tap 345kV 1025 Falcon Seaboard - 1021 Midland East | Howard | WEST | 2025-12-01 | OTH | BA | 310.31 |  | 2020-05-18 | 2020-05-20 | 2020-07-30 | 2020-04-30 |  |  |  | No |  |  | Not Required
22INR0349 | BRP Antlia BESS | SS Completed, FIS Completed, IA | BRP Antlia BESS LLC | 88999 ANTLAPOI4A 138kV | Val Verde | WEST | 2024-12-01 | OTH | BA | 70.95 |  | 2020-06-18 | 2020-06-03 | 2020-08-11 | 2020-05-14 | 2021-05-21 | No | 2021-06-05 | Yes | Not Required | Not Required | Not Required | 2022-11-03
22INR0350 | Milam Solar 2 | SS Completed, FIS Started, No IA | Sandow Lakes Ranch Solar II, LLC | tap one 345kV 7040 Austrop - 13429 Sandow line | Milam | SOUTH | 2025-09-30 | SOL | PV | 287.18 | MW Size | 2020-08-24 | 2020-09-11 | 2021-02-08 | 2020-05-28 |  |  |  | No |  |  | Not Required
22INR0352 | Sparta Solar | SS Completed, FIS Completed, IA | Sparta Solar | AEP 8689 Tango 345kV station | Bee | SOUTH | 2024-02-15 | SOL | PV | 252.35 |  | 2020-06-25 | 2020-05-20 | 2020-07-30 | 2020-05-07 | 2021-07-29 | No | 2020-08-14 | Yes | Not Required | Not Required | Not Required | 2020-08-17 | 2021-08-02 | 2021-07-30 |  |  | 2023-03-24 | 2023-10-16
22INR0353 | BRP Carina BESS | SS Completed, FIS Completed, IA | BRP Carina BESS LLC | 88479 (138 kV CRINAPOI4A) | Nueces | COASTAL | 2024-12-31 | OTH | BA | 151.85 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 | 2020-06-22 | 2021-07-06 |  | 2021-08-03 | Yes | Not Required | Not Required | Not Required | 2023-07-18
22INR0354 | XE MURAT Solar | SS Completed, FIS Completed, IA | Liberty 1 Solar | tap 138kV 40391 Crosby C66 - 40130 Atascocita | Harris | HOUSTON | 2024-05-13 | SOL | PV | 60.36 |  | 2021-01-20 | 2020-08-04 | 2020-10-16 | 2021-01-05 | 2021-12-06 |  | 2022-03-04 | Yes | Not Required | Not Required | Not Required | 2023-08-03 | 2023-08-03 | 2023-08-03
22INR0356 | Jungmann Solar | SS Completed, FIS Completed, IA | BT Jungmann LLC | Tap 69kV 3643 Temp SS - 3689 Marak c1 | Milam | SOUTH | 2024-12-31 | SOL | PV | 40.21 |  | 2021-02-05 | 2020-06-03 | 2020-08-11 | 2021-02-05 | 2021-10-26 |  | 2022-02-15 | No |  |  | Not Required
22INR0357 | Loma Pinta Solar | SS Completed, FIS Started, No IA | Loma Pinta Wind Energy, LLC | 5705 Fowlerton 138kV | La Salle | SOUTH | 2024-12-16 | SOL | PV | 203.06 |  | 2020-09-08 | 2020-06-03 | 2020-08-18 | 2020-05-28 |  | No |  | No |  |  | Not Required
22INR0360 | Jade Solar | SS Completed, FIS Completed, IA | IP RENEWABLE ENERGY HOLDINGS LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Scurry | WEST | 2023-12-22 | SOL | PV | 326.6 | COD | 2020-07-15 | 2020-06-26 | 2020-09-14 | 2020-06-15 | 2021-11-16 | Yes | 2021-01-22 | Yes | Not Required | Not Required | Not Required | 2021-05-03 | 2022-07-05 | 2022-07-26 |  |  | 2023-02-27 | 2023-04-11
22INR0361 | Sibyl Power Station | SS Completed, FIS Completed, No IA | WattBridge Energy, LLC | Tap 138kV 43261 Southwyck - 44552 Telview | Fort Bend | HOUSTON | 2025-07-01 | GAS | GT | 298.68 |  | 2020-08-26 | 2020-09-02 | 2020-11-12 | 2020-08-18 | 2021-11-02 |  |  | No
22INR0362 | Pluto Solar | SS Completed, FIS Started, No IA | Pluto Solar, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2028-07-01 | SOL | PV | 228 |  | 2020-07-28 | 2020-06-26 | 2020-09-14 | 2020-06-23 |  |  |  | No |  |  | Not Required
22INR0363 | Hayhurst Texas Solar | SS Completed, FIS Completed, IA | Hayhurst Texas Solar, LLC | tap 138 kV Three Mile Draw Switch – Horseshoe Springs Switch Line | Culberson | WEST | 2024-04-09 | SOL | PV | 24.76 |  | 2020-10-23 | 2020-08-21 | 2020-11-04 | 2020-08-13 | 2023-04-26 |  | 2021-09-09 | Yes |  |  | Not Required | 2022-04-29 | 2022-04-29 | 2023-04-27 |  |  | 2023-11-10 | 2023-12-12
22INR0364 | Painted Horse Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Wilson | SOUTH | 2025-12-15 | OTH | BA | 53.22 |  | 2021-03-17 | 2020-07-02 | 2020-09-14 | 2021-03-07 |  |  |  | No |  |  | Not Required
22INR0365 | BRP Mensa BESS | SS Completed, FIS Started, No IA | BRP Mensa BESS LLC | 60718 Pecos Valley 138kV | Pecos | WEST | 2024-06-01 | OTH | BA | 404.99 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 | 2020-06-22 |  |  |  | No | Not Required | Not Required | Not Required
22INR0366 | LIBRA BESS | SS Completed, FIS Completed, IA | Libra Storage LLC | 5133 Elm Creek 345kV | Guadalupe | SOUTH | 2024-01-26 | OTH | BA | 206.21 | Proj Name | 2020-07-03 | 2020-06-26 | 2020-09-14 | 2020-06-22 | 2023-05-15 | No | 2022-02-16 | Yes | Not Required | Not Required | Not Required | 2023-02-10 | 2023-04-24 | 2023-05-15 |  |  | 2023-11-21 | 2023-12-05
22INR0368 | Padua Grid BESS | SS Completed, FIS Started, IA | Padua Grid, LLC | 5395 O.W Sommers 138kV | Bexar | SOUTH | 2024-12-01 | OTH | BA | 51.1 | MW Size | 2020-07-23 | 2020-07-10 | 2020-09-28 | 2020-06-29 |  | No | 2021-11-16 | Yes | Not Required | Not Required | Not Required | 2022-08-24
22INR0372 | Hydra BESS | SS Completed, FIS Completed, IA | BRP Hydra BESS LLC | 76002 Bakersfield 345kV | Pecos | WEST | 2024-04-04 | OTH | BA | 200.8 | COD | 2020-07-27 | 2020-07-24 | 2020-10-20 | 2020-07-06 | 2021-10-28 | No | 2021-05-08 | Yes | Not Required | Not Required | Not Required | 2021-09-21 | 2021-10-29 | 2021-10-29
22INR0374 | Inertia Solar | SS Completed, FIS Started, IA | Inertia Solar Project, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2026-07-01 | SOL | PV | 202.39 |  | 2020-10-26 |  | 2021-02-02 | 2020-10-13 |  |  | 2023-05-10 | Yes | Not Required | Not Required | Not Required | 2021-10-08
22INR0375 | Inertia BESS 2 | SS Completed, FIS Started, IA | Inertia Energy Storage, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2025-03-31 | OTH | BA | 100.77 |  | 2020-10-26 |  | 2021-02-02 | 2020-10-13 |  |  | 2023-05-10 | Yes | Not Required | Not Required | Not Required | 2021-10-08
22INR0382 | Razorbill Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP to 44200 Hillje 345kV Ckt 64 | Matagorda | COASTAL | 2025-12-15 | OTH | BA | 120 |  | 2021-06-25 | 2020-08-04 | 2020-10-28 | 2021-06-11 |  |  |  | No | Not Required | Not Required | Not Required
22INR0383 | BRP Musca BESS | SS Completed, FIS Started, No IA | BRP Musca BESS LLC | 60361 Santa Rita 138kV | Reagan | WEST | 2024-12-01 | OTH | BA | 100.51 |  | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  | No |  | No |  |  | Not Required
22INR0384 | Pavo BESS | SS Completed, FIS Completed, IA | BRP Pavo BESS LLC | 38430 TN White Baker 138kV | Pecos | WEST | 2024-06-04 | OTH | BA | 175.8 | COD | 2020-08-19 | 2020-07-24 | 2020-10-08 | 2020-08-17 | 2021-07-30 | No | 2021-07-15 | Yes | Not Required | Not Required | Not Required | 2021-07-29 | 2021-07-29 | 2021-07-30
22INR0385 | BRP Pictor BESS | SS Completed, FIS Started, No IA | BRP Pictor BESS LLC | 60400 Lynx 138kV | Crane | WEST | 2025-11-01 | OTH | BA | 201.07 |  | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  | No |  | No |  |  | Not Required
22INR0386 | BRP Octans BESS | SS Completed, FIS Started, No IA | BRP OCTANS BESS LLC | 6671 Tombstone 138kV | Pecos | WEST | 2026-06-01 | OTH | BA | 129.57 | COD | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  |  |  | No |  |  | Not Required
22INR0387 | Val Vista Grid BESS | SS Completed, FIS Started, No IA | Val Vista Grid, LLC | Tap 345kV 8383 North Edinburg - 80137 Stewart Road | Hidalgo | SOUTH | 2028-06-01 | OTH | BA | 209.32 | MW Size | 2020-08-04 | 2020-08-04 | 2020-10-16 | 2020-07-21 |  |  |  | No |  |  | Not Required
22INR0388 | BRP Cachi BESS | SS Completed, FIS Started, IA | BRP Cachi BESS LLC | 7680 Clear Springs 138kV | Guadalupe | SOUTH | 2024-12-31 | OTH | BA | 202.46 |  | 2020-10-14 | 2020-08-21 | 2020-11-10 | 2020-08-26 |  |  | 2021-06-11 | No | Not Required | Not Required | Not Required
22INR0390 | BRP Perseus BESS | SS Completed, FIS Started, No IA | BRP Perseus BESS LLC | tap 138 kV line from Lon Hill (#8452) to Bessel (#8060) | Nueces | COASTAL | 2024-12-01 | OTH | BA | 202.5 |  | 2020-08-19 | 2020-08-21 | 2020-11-10 | 2020-08-17 |  |  |  | No |  |  | Not Required
22INR0392 | Kalina Solar | SS Completed, FIS Started, No IA | Aurora Solar LLC | 8606 Goddard 345kV | San Patricio | COASTAL | 2026-07-01 | SOL | PV | 120 |  | 2021-03-31 | 2020-08-04 | 2020-10-28 | 2021-03-29 |  |  |  | No | Not Required | Not Required | Not Required
22INR0398 | Cameron Storage | SS Completed, FIS Completed, IA | Cameron Wind 1, LLC | 5761 Paredes 138kV | Cameron | COASTAL | 2023-12-15 | OTH | BA | 18 |  | 2021-06-22 | 2020-09-11 | 2020-11-30 | 2021-05-28 | 2022-05-02 | No | 2022-10-31 | Yes | Not Required | Not Required | Not Required | 2022-05-02 | 2022-05-02 | 2022-05-02 |  |  | 2023-08-24 | 2023-09-19
22INR0400 | Dragan Storage | SS Completed, FIS Started, No IA | Hecate Grid Dragan Storage LLC | 1440 Comanche 345kV | Comanche | NORTH | 2026-02-28 | OTH | BA | 408.3 |  | 2020-10-02 | 2020-08-21 | 2020-11-04 | 2020-08-13 |  |  |  | No |  |  | Not Required
22INR0401 | Eval Storage | SS Completed, FIS Started, IA | Hecate Grid East Valley Storage LLC | 80229 Cavazos 138kV | Cameron | COASTAL | 2025-12-31 | OTH | BA | 255 |  | 2020-12-29 | 2020-10-23 | 2021-01-12 | 2020-11-03 |  |  | 2022-02-03 | Yes | Not Required | Not Required | Not Required
22INR0402 | Frye Storage | SS Completed, FIS Completed, No IA | Hecate Energy Frye Storage LLC | new 345kV sub Kress connecting both 23912 Ogallala - 23914 Tule Canyon circuits | Swisher | PANHANDLE | 2025-03-15 | OTH | BA | 510 |  | 2020-08-26 | 2020-09-02 | 2020-11-19 | 2020-08-17 | 2023-09-18 | No |  | No |  |  | Not Required
22INR0404 | Fence Post Solar | SS Completed, FIS Completed, IA | Fence Post Solar Project, LLC | tap 138kV 3127 Trinidad – 3483 Goodloe | Navarro | NORTH | 2024-03-15 | SOL | PV | 237.31 |  | 2020-10-02 | 2020-11-05 | 2021-01-20 | 2020-10-21 | 2023-11-01 |  | 2021-08-12 | Yes | Not Required | Not Required | Not Required | 2022-04-28 | 2022-04-28 | 2023-11-01 |  |  | 2023-11-20 | 2023-12-05
22INR0405 | Fence Post BESS | SS Completed, FIS Completed, IA | Fence Post Solar Project, LLC | tap 138kV 3127 Trinidad – 3483 Goodloe | Navarro | NORTH | 2024-05-22 | OTH | BA | 72.23 |  | 2020-10-02 | 2020-11-05 | 2021-01-20 | 2020-10-13 | 2023-11-01 |  | 2021-08-12 | Yes | Not Required | Not Required | Not Required | 2022-04-27 | 2022-04-27 | 2023-11-01 |  |  | 2023-11-20 | 2023-12-05
22INR0408 | BRP Pular BESS | SS Completed, FIS Started, No IA | BRP Pular BESS LLC | 8963 Hidalgo Energy Center 138kV | Hidalgo | SOUTH | 2025-02-01 | OTH | BA | 233.1 |  | 2020-09-02 | 2020-09-11 | 2021-06-10 | 2020-08-25 |  |  |  | No |  |  | Not Required
22INR0409 | Stampede Solar | SS Completed, FIS Completed, IA | Stampede Solar Project, LLC | tap 345kV 1685 Farmersville - 11688 Thorn Tree ckt 1 | Hopkins | NORTH | 2024-08-19 | SOL | PV | 256.34 |  | 2020-10-16 | 2020-11-05 | 2021-01-20 | 2020-10-21 | 2023-11-01 |  | 2021-12-15 | Yes |  |  | Not Required | 2022-04-11 | 2022-04-27 | 2023-11-01 |  |  | 2023-11-28 | 2023-12-22
22INR0410 | Stampede BESS | SS Completed, FIS Completed, IA | Stampede Solar Project, LLC | tap 345kV 1685 Farmersville - 11688 Thorn Tree ckt 1 | Hopkins | NORTH | 2024-05-22 | OTH | BA | 72.38 |  | 2020-10-16 | 2020-11-05 | 2021-01-20 | 2020-10-21 | 2023-11-01 |  | 2021-12-15 | Yes | Not Required | Not Required | Not Required | 2022-04-11 | 2022-04-27 | 2023-11-01 |  |  | 2023-11-28 | 2023-12-22
22INR0412 | Andromeda Solar | SS Completed, FIS Completed, IA | IP Renewable Energy Holdings LLC | Tap 345kV 11305 Dermott - 60706 Kirchhoff C | Scurry | WEST | 2023-12-22 | SOL | PV | 326.6 | COD | 2020-09-22 | 2020-09-11 | 2020-11-30 | 2020-09-02 | 2021-08-30 | No | 2021-04-01 | Yes |  |  | Not Required | 2022-04-12 | 2022-07-08 | 2022-08-01 |  |  | 2023-04-27 | 2023-05-01
22INR0417 | Amsterdam Storage | SS Completed, FIS Started, IA | Cottonwood Bayou II Storage, LLC | tap 345kV 43035 Oasis - 42500 Dow c27 | Brazoria | COASTAL | 2025-03-01 | OTH | BA | 201.13 |  | 2020-09-30 | 2020-10-07 | 2020-12-30 | 2020-09-11 |  |  | 2022-04-14 | No |  |  | Not Required
22INR0422 | Ferdinand Grid BESS | SS Completed, FIS Started, IA | Ferdinand Grid, LLC | 5260 Leon Creek 138kV | Bexar | SOUTH | 2026-05-31 | OTH | BA | 202.65 |  | 2021-01-28 | 2021-03-01 | 2021-05-12 | 2021-01-28 |  | No | 2022-11-28 | Yes | Not Required | Not Required | Not Required | 2023-08-18
22INR0423 | BRP Quela BESS | SS Completed, FIS Started, No IA | BRP Quela BESS LLC | Tap 138kV 5110 J.T. Deely - 5294 Martinez | Bexar | SOUTH | 2025-12-01 | OTH | BA | 303.74 |  | 2020-09-25 | 2020-09-25 | 2020-12-16 | 2020-09-15 |  |  |  | No |  |  | Not Required
22INR0424 | BRP Denali BESS | SS Completed, FIS Started, No IA | BRP Denali BESS LLC | Tap 138kV 5395 Sommers - 5030 Braunig East | Bexar | SOUTH | 2025-06-01 | OTH | BA | 258.41 |  | 2020-09-25 | 2020-09-25 | 2020-12-16 | 2020-09-17 |  |  |  | No | Not Required | Not Required | Not Required
22INR0425 | MAKALU SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green X LLC | Tap 138kV 977 Pruitt - 971 Greenville | Hunt | NORTH | 2026-04-15 | SOL | PV | 50.16 |  | 2021-08-17 | 2021-01-21 | 2021-01-28 | 2021-08-10 |  |  |  | No |  |  | Not Required
22INR0426 | LUBIO SOLAR | SS Completed, FIS Completed, No IA | BDPU Solar Lubio LLC | tap 138kV 2727 Crandall - 2724 Kaufman Northwest | Kaufman | NORTH | 2025-10-07 | SOL | PV | 54.47 |  | 2021-07-01 | 2020-10-07 | 2020-12-28 | 2021-06-28 | 2023-10-30 |  |  | No |  |  | Not Required
22INR0427 | BRP Kabru BESS | SS Completed, FIS Started, No IA | BRP Kabru BESS LLC | 1159 Andrew North - 11284 Blackbird 138kV | Andrews | WEST | 2025-12-01 | OTH | BA | 202.45 |  | 2020-09-28 | 2020-10-07 | 2020-12-28 | 2020-09-22 |  | No |  | No |  |  | Not Required
22INR0437 | TORMES SOLAR | SS Completed, FIS Completed, No IA | BDPU Solar Tormes LLC | tap 345kV 1906 Venus - 68091 Navarro | Navarro | NORTH | 2025-09-04 | SOL | PV | 382.12 |  | 2021-07-26 | 2020-10-23 | 2021-01-12 | 2021-07-19 | 2023-10-19 |  |  | No |  |  | Not Required
22INR0443 | Bowstring BESS | SS Completed, FIS Completed, No IA | Longbow Energy Storage, LLC | 8961 White Point 138kV | San Patricio | COASTAL | 2025-12-31 | OTH | BA | 155 |  | 2021-04-01 | 2020-11-18 | 2021-02-09 | 2021-03-24 | 2023-05-30 |  |  | No |  |  | Not Required
22INR0444 | Liberty Senate Solar 1 | SS Completed, FIS Completed, No IA | Senate Solar LLC | 1445 Burwick 345kV | Jack | NORTH | 2025-10-27 | SOL | PV | 202 |  | 2021-09-16 | 2021-03-01 | 2021-05-13 | 2021-09-10 | 2023-03-31 |  |  | No | Not Required | Not Required | Not Required
22INR0445 | SPC Bloom BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 2, LLC | 8911 Black Bayou 138kV | Victoria | SOUTH | 2024-12-01 | OTH | BA | 100 |  | 2021-02-04 | 2020-12-03 | 2021-02-19 | 2020-11-13 |  |  |  | No |  |  | Not Required
22INR0449 | Sibyl Energy Storage | SS Completed, FIS Started, No IA | WattBridge Energy, LLC | Tap 138kV 43261 Southwyck - 44552 Telview | Fort Bend | HOUSTON | 2024-11-01 | OTH | BA | 202.32 |  | 2020-11-25 | 2020-12-03 | 2021-02-18 | 2020-11-25 |  |  |  | No | Not Required | Not Required | Not Required
22INR0454 | DR Solar | SS Completed, FIS Completed, IA | Delaware Ranch Solar, LLC | tap 138kV 11112 Chimney Well - 11271 Owl Hill | Culberson | WEST | 2025-04-11 | SOL | PV | 46.02 |  | 2020-11-04 | 2020-12-22 | 2021-03-10 | 2020-12-17 | 2022-10-17 |  | 2022-02-07 | Yes |  |  | Not Required | 2022-08-24
22INR0455 | Blue Sky Sol | SS Completed, FIS Completed, IA | Blue Sky Solar LLC | 6562 Friends Ranch 138kV | Crockett | WEST | 2025-02-15 | SOL | PV | 101.2 |  | 2020-12-09 | 2020-12-03 | 2021-02-16 | 2020-11-10 | 2023-07-05 | No | 2022-02-01 | Yes | Not Required | Not Required | Not Required | 2022-02-07 | 2023-07-31 | 2023-07-31
22INR0457 | Anson BAT | SS Completed, FIS Started, No IA | Anson Solar Center, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2024-12-28 | OTH | BA | 156.86 |  | 2022-03-03 | 2020-12-03 | 2021-02-19 | 2022-02-23 |  |  |  | No |  |  | Not Required
22INR0462 | Old Aqueduct Solar | SS Completed, FIS Started, No IA | Old Aqueduct Solar | 23920 Blackwater 345kV | Hale | PANHANDLE | 2024-03-01 | SOL | PV | 511.63 |  | 2021-07-09 | 2020-12-03 | 2021-02-19 | 2021-06-29 |  |  |  | No |  |  | Not Required
22INR0466 | Pajarita BESS | SS Completed, FIS Started, No IA | VESI 29 LLC | 8266 Marconi 138kV | Cameron | COASTAL | 2025-02-15 | OTH | BA | 205.5 | COD | 2021-12-15 | 2021-01-25 | 2021-04-12 | 2021-12-01 |  | No |  | No | Not Required | Not Required | Not Required
22INR0467 | Bird Dog BESS | SS Completed, FIS Started, No IA | VESI 37 LLC | 5668 Mathis 69kV | Live Oak | SOUTH | 2025-05-19 | OTH | BA | 60 |  | 2022-06-02 | 2021-02-04 | 2021-04-19 | 2022-05-19 |  |  |  | No | Not Required | Not Required | Not Required
22INR0468 | Lower Rio BESS | SS Completed, FIS Completed, IA | VESI 38 LLC | 5792 Sioux 138kV | Hidalgo | SOUTH | 2025-01-15 | OTH | BA | 60.45 |  | 2021-11-10 | 2021-02-09 | 2021-05-06 | 2021-11-08 | 2022-10-04 | No | 2023-07-10 | No | Not Required | Not Required | Not Required
22INR0469 | Harper Energy Storage | SS Completed, FIS Started, No IA | VESI 31 LLC | Tap 138kV 8314 La Palma - 80229 Villa Cavazos | Cameron | COASTAL | 2026-02-02 | OTH | BA | 82.42 |  | 2022-02-10 | 2021-12-03 | 2022-03-01 | 2022-01-27 |  |  |  | No |  |  | Not Required
22INR0471 | MARATUA SOLAR | SS Completed, FIS Started, No IA | Invenergy Solar Project Development LLC | tap 345kV 44645 Singleton - 3391 Jewett ckt 74 | Grimes | NORTH | 2026-12-30 | SOL | PV | 217.07 |  | 2021-08-19 | 2020-12-03 | 2021-02-19 | 2021-08-13 |  | Yes |  | No |  |  | Not Required
22INR0473 | TAIN SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green VII LLC | tap 138kV 7216 Lockhart - 7224 Luling City | Caldwell | SOUTH | 2025-03-11 | SOL | PV | 37.54 |  | 2021-11-02 | 2020-12-03 | 2021-02-17 | 2021-10-20 |  |  |  | No |  |  | Not Required
22INR0480 | Pachanga Wind | SS Completed, FIS Started, No IA | Pachanga Wind LLC | tap 345kV 5966 Palmito - 80137 Stewart Rd | Cameron | COASTAL | 2027-04-01 | WIN | WT | 300 |  | 2021-06-28 | 2021-02-09 | 2021-05-06 | 2021-04-05 |  |  |  | No |  |  | Not Required
22INR0482 | Rowland Solar II | SS Completed, FIS Completed, IA | Cutlass Solar II LLC | tap 345kV 44005 WAP - 44090 Cedar Creek | Fort Bend | HOUSTON | 2024-06-15 | SOL | PV | 202.81 |  | 2020-12-29 | 2020-12-23 | 2017-11-20 | 2020-12-28 | 2022-07-07 | No | 2020-09-23 | Yes | Not Required | Not Required | Not Required | 2021-10-27 | 2023-08-01 | 2023-08-01
22INR0488 | Venture Hill Storage | SS Completed, FIS Started, No IA | KCE TX 24, LLC | 7336 Gilleland Creek 138kV | Travis | SOUTH | 2026-12-01 | OTH | BA | 70.44 |  | 2021-01-08 | 2021-02-09 | 2021-05-06 | 2020-12-29 |  |  |  | No |  |  | Not Required
22INR0489 | Christoval Solar | SS Completed, FIS Started, No IA | Bridgelink Cave Springs LLC | 76003 Big Hills 345kV | Tom Green | WEST | 2024-06-30 | SOL | PV | 324 |  | 2021-05-07 | 2021-02-04 | 2021-04-19 | 2021-04-30 |  |  |  | No |  |  | Not Required
22INR0490 | Callisto I Energy Center | SS Completed, FIS Completed, IA | Callisto I energy center LLC | 47150 HO Clarke 138kV | Harris | HOUSTON | 2024-06-01 | OTH | BA | 206.4 |  | 2021-03-05 | 2021-03-16 | 2021-05-28 | 2021-03-05 | 2023-07-28 |  | 2022-04-07 | Yes | Not Required | Not Required | Not Required | 2022-09-20 | 2023-07-21 | 2023-08-01
22INR0493 | Oscar Storage Project | SS Completed, FIS Started, No IA | Woodlands Energy Renewables LLC | 3413 Knob Creek 345kV | Bell | NORTH | 2024-06-01 | OTH | BA | 50 |  | 2022-06-07 | 2021-03-01 | 2021-05-13 | 2022-05-18 |  |  |  | No |  |  | Not Required
22INR0494 | Quail Run Storage System | SS Completed, FIS Started, No IA | to be determined | 11016 Quail Run Switch 345kV | Ector | WEST | 2024-08-01 | OTH | BA | 50 |  | 2022-01-21 | 2021-02-09 | 2021-05-06 | 2021-12-28 |  |  |  | No | Not Required | Not Required | Not Required
22INR0497 | TEXPO | SS Completed, FIS Started, No IA | Oklaunion Power Station, LLC | 6100 Oklaunion 345kV | Wilbarger | WEST | 2024-10-31 | GAS | ST | 680 |  | 2021-11-30 | 2021-03-16 | 2021-05-28 | 2021-11-23 |  | No |  | No | Not Required | Not Required | 2022-05-02
22INR0499 | Aquilla Lake 3 Wind | SS Completed, FIS Started, No IA | Aquilla Lake 3 Wind | tap 345 kV 68040 Kopperl to 68091 Navarro | Hill | NORTH | 2026-10-31 | WIN | WT | 225 |  | 2021-03-05 | 2021-03-08 | 2021-05-28 | 2021-02-18 |  |  |  | No |  |  | Not Required
22INR0502 | Shamrock | SS Completed, FIS Completed, IA | Shamrock Interconnection LLC | Tap 345 kV 7053 Noelke - 76005 Schneeman | Crockett | WEST | 2024-04-19 | WIN | WT | 223.92 |  | 2021-02-23 | 2021-03-01 | 2021-05-13 | 2021-02-24 | 2023-04-27 | No | 2022-05-13 | Yes | Not Required | Not Required | Not Required | 2023-04-28 | 2023-04-28 | 2023-04-28 |  |  | 2023-12-07 | 2023-12-13
22INR0503 | Tidwell Prairie II Batt | SS Completed, FIS Started, No IA | TIDWELL PRAIRIE LLC | Tap 345kV 3400 Twin Oak - 39950 TNP One | Robertson | NORTH | 2026-03-24 | OTH | BA | 200 | COD | 2021-03-02 | 2021-03-16 | 2021-05-28 | 2021-02-17 |  |  |  | No |  |  | Not Required
22INR0504 | Tidwell Prairie III Batt | SS Completed, FIS Started, No IA | Tidwell Prairie LLC | Tap 345kV 3400 Twin Oak - 39950 TNP One | Robertson | NORTH | 2026-05-01 | OTH | BA | 200 | COD | 2021-03-02 | 2021-03-16 | 2021-05-28 | 2021-02-17 |  |  |  | No |  |  | Not Required
22INR0506 | Roseland Solar II | SS Completed, FIS Completed, IA | Enel Green Power Roseland Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2024-01-31 | SOL | PV | 254 | COD | 2018-11-05 | 2021-10-05 | 2019-02-04 |  | 2021-10-25 |  | 2020-12-10 | Yes | Not Required | Not Required | Not Required | 2021-10-26 | 2021-10-26 | 2021-10-26 |  |  | 2022-06-07 | 2022-09-26
22INR0511 | Gransolar Texas One | SS Completed, FIS Completed, IA | Gransolar Texas One, LLC | Tap 138kV 3659 Thorndale North - 116 Salty | Milam | SOUTH | 2024-12-31 | SOL | PV | 50 |  | 2021-03-10 | 2021-03-16 | 2021-06-11 | 2021-03-08 | 2022-01-24 |  | 2022-02-09 | No |  |  | Not Required
22INR0514 | Wang Storage SLF | SS Completed, FIS Started, No IA | BT Yixin Solar, LLC | tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2026-03-31 | OTH | BA | 0 |  | 2021-06-09 | 2022-11-07 | 2023-02-03 | 2022-09-23 |  |  |  | No |  |  | Not Required
22INR0515 | Flagtail BESS | SS Completed, FIS Started, No IA | Flagtail LLC | Tap 138kV 5 Sandy Switch - 7 Sandy | Grimes | NORTH | 2026-07-01 | OTH | BA | 203.8 |  | 2021-03-15 | 2021-04-05 | 2021-06-24 | 2021-03-15 |  | No |  | No |  |  | Not Required
22INR0516 | Amber Storage | SS Completed, FIS Completed, No IA | Belltown Power Texas | 730 Wolf Ridge 138kV | Cooke | NORTH | 2025-03-15 | OTH | BA | 50 |  | 2021-03-19 | 2021-03-19 | 2021-06-11 | 2021-03-19 | 2023-01-19 | No |  | No | Not Required | Not Required | Not Required
22INR0517 | Ray Gulf Wind | SS Completed, FIS Started, IA | Lane City Wind, LLC | 44040 Bailey 345kV | Wharton | SOUTH | 2025-06-30 | WIN | WT | 207 |  | 2021-05-05 | 2021-04-26 | 2021-07-28 | 2021-04-26 |  | No | 2022-05-13 | No | Not Required | Not Required | Not Required
22INR0523 | Midlothian 4 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1940 Midlothian ANP 345kV | Ellis | NORTH | 2024-07-16 | GAS | GT | 18 |  | 2021-04-28 | 2021-04-26 | 2021-07-28 | 2021-04-21 |  |  |  | No
22INR0524 | St. Gall I Energy Storage | SS Completed, FIS Completed, IA | St. Gall Energy Storage I LLC | 38355 TNLeon Creek 138kV | Pecos | WEST | 2024-03-15 | OTH | BA | 102.6 | COD | 2021-04-15 | 2021-04-13 | 2021-07-02 | 2021-04-08 | 2023-01-31 | No | 2023-01-10 | Yes | Not Required | Not Required | Not Required | 2023-01-19 | 2023-04-27 | 2023-04-27 |  |  | 2023-10-18
22INR0525 | St. Gall II Energy Storage | SS Completed, FIS Started, No IA | St. Gall Energy Storage LLC | 38355 TNLeon Creek 138kV | Pecos | WEST | 2026-06-01 | OTH | BA | 102.6 |  | 2021-04-15 | 2021-04-13 | 2021-07-02 | 2021-04-08 |  | No |  | Yes | Not Required | Not Required | Not Required
22INR0526 | Pine Forest BESS | SS Completed, FIS Completed, No IA | Pine Forest Hybrid I, LLC | tap 345kV 1696 Monticello SES - 2514 Allen Switch | Hopkins | NORTH | 2025-06-29 | OTH | BA | 421 |  | 2021-07-30 | 2021-05-04 | 2021-07-30 | 2021-07-19 | 2023-10-12 |  |  | No |  |  | Not Required
22INR0533 | Temple Generation I Repower | SS Completed, FIS Completed, IA | Panda Temple Power | 3413 Knob Creek 345kV | Bell | NORTH | 2022-06-09 | GAS | CC | 67 |  | 2021-04-26 | 2021-04-26 | 2021-05-13 | 2021-04-22 | 2021-09-30 |  | 2012-06-21 | Yes | Not Required | Not Required |  | 2021-10-26 | 2021-10-26 | 2021-10-26
22INR0540 | Walstrom BESS | SS Completed, FIS Started, IA | Sealy Power LLC | 46220 Peters 138kV | Austin | SOUTH | 2025-05-05 | OTH | BA | 200 |  | 2021-05-17 | 2021-07-08 | 2021-10-04 | 2021-06-03 |  |  | 2023-06-30 | Yes |  |  | Not Required
22INR0541 | ALWEST BESS | SS Completed, FIS Started, No IA | Castleman Power | 3114 Paltalco 138kV | Anderson | NORTH | 2025-08-05 | OTH | BA | 208.63 |  | 2021-05-17 | 2021-08-24 | 2021-11-15 | 2021-06-03 |  |  |  | No |  |  | Not Required
22INR0543 | Midlothian Unit 3 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1940 Midlothian ELP 345kV | Ellis | NORTH | 2024-07-16 | GAS | GT | 18 |  | 2021-05-21 | 2021-05-24 | 2021-08-06 | 2021-05-11 |  |  |  | No
22INR0546 | Enchanted Rock NEWPP | SS Completed, FIS Started, No IA | Enchanted Rock Electric, LLC | 40475 Deusen 138kV | Harris | HOUSTON | 2023-11-01 | GAS | IC | 30 |  | 2022-12-01 | 2021-11-10 | 2022-01-17 | 2022-07-13 |  |  |  | No
22INR0549 | Tanzanite Storage | SS Completed, FIS Completed, IA | Tanzanite Energy Storage LLC | 6867 NORTH ATHENS 138kV | Henderson | NORTH | 2025-03-01 | OTH | BA | 265.8 | COD | 2021-07-27 | 2021-09-01 | 2021-11-18 | 2021-08-16 | 2023-12-14 | No | 2022-07-15 | Yes | Not Required | Not Required | Not Required | 2022-11-04
22INR0550 | BLUE SUMMIT I REPOWER | SS Completed, FIS Completed, IA | Blue Summit Wind LLC | 61001 JIM TREECE 345kV | Wilbarger | WEST | 2023-12-31 | WIN | WT | 4.4 |  | 2021-08-27 | 2021-11-01 | 2022-01-28 | 2021-09-27 | 2022-04-29 |  | 2012-02-22 | No | Not Required | Not Required | Not Required | 2022-04-29 | 2022-04-29 | 2022-05-02 |  |  |  | 2022-11-04
22INR0552 | Sowers Storage | SS Completed, FIS Completed, IA | Sowers Energy Storage LLC | 6894 Rose Hill_RC Sub 138 kV | Kaufman | NORTH | 2025-12-01 | OTH | BA | 206.1 |  | 2021-08-17 | 2021-08-18 | 2021-11-05 | 2021-08-18 | 2021-12-17 | No | 2022-04-22 | Yes | Not Required | Not Required | Not Required | 2022-12-05
22INR0554 | Platinum Storage | SS Completed, FIS Started, IA | Platinum Energy Storage LLC | 1729 Valley South 345kV | Fannin | NORTH | 2025-04-15 | OTH | BA | 309.3 | COD | 2021-08-20 | 2021-09-02 | 2021-11-18 | 2021-08-31 |  | No | 2022-11-17 | No | Not Required | Not Required | Not Required
22INR0555 | Guevara Storage | SS Completed, FIS Started, IA | BT Smith Storage, LLC | 2483 Royse Switch 345kV | Rockwall | NORTH | 2025-07-15 | OTH | BA | 125.36 |  | 2021-08-24 | 2021-09-02 | 2021-11-18 | 2021-08-26 |  | No | 2023-11-08 | Yes | Not Required | Not Required | Not Required | 2023-11-13
22INR0558 | Callisto II Energy Center | SS Completed, FIS Started, IA | Callisto II Energy Center LLC | 47150 HO Clarke 138kV | Harris | HOUSTON | 2025-12-10 | OTH | BA | 406.06 |  | 2021-10-07 | 2021-10-07 | 2021-12-08 | 2021-09-29 |  |  | 2023-12-11 | No |  |  | Not Required
22INR0559 | Honeycomb Solar | SS Completed, FIS Started, IA | Honeycomb Solar, LLC | 69 kV Tynan Substation (#8107) | Bee | SOUTH | 2025-06-01 | SOL | PV | 61.1 |  | 2021-10-26 | 2021-11-16 | 2022-01-17 | 2021-11-02 |  | No | 2023-05-01 | Yes | Not Required | Not Required | Not Required
22INR0562 | Anchor Wind IV | SS Completed, FIS Completed, IA | Ranchland Wind Project,LLC | 345 kV Aspire Station (68011) | Eastland | NORTH | 2023-10-30 | WIN | WT | 19.32 |  | 2019-06-26 | 2021-12-03 | 2022-03-01 |  | 2021-04-30 |  | 2020-11-30 | Yes | Not Required | Not Required | Not Required | 2021-04-30 | 2021-04-30 | 2021-04-30 |  |  | 2021-11-29 | 2022-05-05
22INR0586 | Hays Energy Unit 2 Repower | SS Completed, FIS Started, No IA | HAYS ENERGY, LLC | 7043 Haysen 345kV | Hays | SOUTH | 2024-08-30 | GAS | GT | 18 | COD | 2022-12-01 | 2022-02-21 | 2022-05-21 | 2022-11-15 |  |  |  | No
22INR0605 | Camino Santiago Solar | SS Completed, FIS Started, No IA | Karol Solar I | Tap 345kV 3687 Bell County East Switch – 39950 TNP One Plant Ckt 2 (North Circuit). | Milam | SOUTH | 2026-04-19 | SOL | PV | 180.83 |  | 2023-02-08 | 2022-09-02 | 2022-11-30 |  |  |  |  | No |  |  | Not Required
23INR0006 | Sierra Madre Solar | SS Completed, FIS Started, No IA | Sierra Madre Solar LLC | tap 345kV 80307 Del Sol - 80225 Cenizo | Zapata | SOUTH | 2025-12-01 | SOL | PV | 255.15 |  | 2020-10-07 | 2020-01-22 | 2020-04-08 | 2020-10-05 |  |  |  | No |  |  | Not Required
23INR0007 | Outpost Solar | SS Completed, FIS Started, IA | Hecate Energy Outpost Solar LLC | Tap 345kV 80219 Lobo - 5709 Fowlerton | Webb | SOUTH | 2025-01-07 | SOL | PV | 513.7 |  | 2020-02-11 | 2019-12-06 | 2020-02-25 | 2019-12-02 |  |  | 2022-01-11 | Yes | Not Required | Not Required | Not Required | 2022-11-07
23INR0008 | Harley Hand Solar | SS Completed, FIS Started, No IA | HECTATE ENERGY HARLEY HAND SOLAR LLC | 11420 Sweetwater East 345kV | Nolan | WEST | 2025-08-01 | SOL | PV | 513.7 |  | 2019-12-12 | 2019-12-16 | 2020-03-11 | 2019-12-06 |  | No |  | No | Not Required | Not Required | Not Required
23INR0009 | Shaula III Solar | SS Completed, FIS Started, No IA | Shaula Energy Project III, LLC | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | DeWitt | SOUTH | 2025-12-24 | SOL | PV | 205.2 |  | 2020-01-13 | 2019-12-18 | 2020-03-11 | 2019-12-18 |  |  |  | No |  |  | Not Required
23INR0010 | Plateau Solar | SS Completed, FIS Completed, No IA | Innovative Solar 206, LLC | tap 345kV 68000 West Shackelford - 68001 Claytonville | Jones | WEST | 2025-05-31 | SOL | PV | 300 |  | 2020-09-04 | 2019-12-06 | 2020-02-25 | 2020-08-20 | 2022-03-22 | No |  | No | Not Required | Not Required | Not Required
23INR0014 | Hedgehog Solar | SS Completed, FIS Started, No IA | Innovative Solar 408, LLC | tap 138kV 8234 Uvalde - 8241 Razorback | Medina | SOUTH | 2025-07-08 | SOL | PV | 85 |  | 2020-09-16 | 2019-12-11 | 2020-03-06 | 2020-08-31 |  |  |  | No |  |  | Not Required
23INR0015 | Scarlet Solar | SS Completed, FIS Started, No IA | Innovative Solar 416, LLC | tap 345kV 23912 Ogallala - 23910 Windmill | Castro | PANHANDLE | 2025-08-26 | SOL | PV | 180 |  | 2020-09-16 | 2019-12-11 | 2020-03-06 | 2020-08-31 |  |  |  | No |  |  | Not Required
23INR0021 | Hornet Solar | SS Completed, FIS Completed, IA | Hornet Solar LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala | Swisher | PANHANDLE | 2024-12-31 | SOL | PV | 611 |  | 2020-05-15 | 2020-02-04 | 2020-04-29 | 2020-02-04 | 2021-10-06 | No | 2021-12-06 | Yes | Not Required | Not Required | Not Required | 2021-12-22 | 2023-09-28 | 2023-10-31
23INR0026 | Baker Branch Solar | SS Completed, FIS Completed, IA | Mockingbird Solar Center, LLC | tap 345kV 1692 Paris - 1690 Valley | Lamar | NORTH | 2024-08-01 | SOL | PV | 469.42 |  | 2020-04-09 | 2020-03-26 | 2020-06-04 | 2020-03-05 | 2023-10-30 |  | 2022-02-14 | Yes | Not Required | Not Required | Not Required | 2023-10-03 | 2023-10-30 | 2023-10-30
23INR0027 | Cachena Solar SLF | SS Completed, FIS Completed, IA | Clear Fork Creek Solar LLC | Tap 345KV 5133 Elm Creek - 5323 Old Hickory | Wilson | SOUTH | 2026-12-31 | SOL | PV | 600 |  | 2020-08-19 | 2020-05-01 | 2020-07-13 | 2020-08-17 | 2023-10-02 | No | 2021-11-23 | Yes | Not Required | Not Required | Not Required | 2021-11-29
23INR0029 | Cedar Bayou5 | SS Completed, FIS Started, IA | NRG Cedar Bayou 5 LLC | 40000 Cedar Bayou 345kV | Chambers | HOUSTON | 2027-02-02 | GAS | CC | 697 |  | 2020-03-31 | 2020-03-26 | 2020-06-04 | 2020-03-18 |  | No | 2022-01-10 | No | 1899-12-31 | 2021-03-17
23INR0030 | Langer Solar | SS Completed, FIS Started, IA | Langer Solar LLC | tap 345kV 68040 Kopperl - 68091 Navarro | Bosque | NORTH | 2025-09-24 | SOL | PV | 249.8 |  | 2020-11-06 | 2020-06-03 | 2020-08-18 | 2020-10-30 |  | Yes | 2023-08-31 | No |  |  | Not Required
23INR0031 | Solace Solar | SS Completed, FIS Completed, No IA | IP QUANTUM, LLC. | tap 345kV 1430 Graham - 1048 Tonkawas | Haskell | WEST | 2026-09-01 | SOL | PV | 374.4 |  | 2020-04-21 | 2020-04-22 | 2020-07-09 | 2020-04-03 | 2023-10-26 |  |  | No |  |  | Not Required
23INR0035 | Starling Solar | SS Completed, FIS Started, IA | Starling Solar, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2025-05-09 | SOL | PV | 123 |  | 2021-02-09 | 2020-06-26 | 2020-09-14 | 2021-01-22 |  |  | 2021-12-03 | No |  |  | Not Required
23INR0040 | Dori BQ Solar | SS Completed, FIS Completed, IA | Sunnyside Energy, LLC | tap 138kV 47210 Holmes – 42680 Garden Villas | Harris | HOUSTON | 2024-10-30 | SOL | PV | 50.42 |  | 2021-02-10 | 2020-06-09 | 2020-08-18 | 2021-01-29 | 2022-12-02 | No | 2022-12-01 | No | Not Required | Not Required | Not Required
23INR0044 | Parliament Solar | SS Completed, FIS Started, IA | Parliament Solar LLC | Tap 345kV 44900 Zenith - 967 Gibbons Creek ckt 18 | Waller | HOUSTON | 2024-12-31 | SOL | PV | 484.56 |  | 2020-08-03 | 2020-06-19 | 2020-09-08 | 2020-06-08 |  | No | 2022-05-26 | Yes | Not Required | Not Required | Not Required
23INR0045 | GP Solar | SS Completed, FIS Completed, IA | HEP Aquamarine Holdings LLC | Tap 138kV 6829 Glen Pine - 6833 Explorer | Van Zandt | NORTH | 2025-05-15 | SOL | PV | 121.97 |  | 2016-02-23 | 2020-09-25 | 2020-12-16 | 2021-02-22 | 2021-11-10 | No | 2021-12-29 | Yes | Not Required | Not Required | Not Required | 2021-12-13 | 2021-12-13 | 2022-08-01
23INR0047 | Charger Solar | SS Completed, FIS Completed, IA | AP Solar 4, LLC | tap 345kV 8249 Angstrom – 5915 STP | Refugio | COASTAL | 2025-05-31 | SOL | PV | 406.77 |  | 2020-07-29 | 2020-06-19 | 2020-09-08 | 2020-06-07 | 2022-04-04 | No | 2021-06-05 | Yes |  |  | Not Required | 2022-04-04
23INR0048 | Equinox Storage | SS Completed, FIS Started, No IA | Invenergy Storage Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2026-12-30 | OTH | BA | 101.2 |  | 2021-03-23 | 2020-06-26 | 2020-09-14 | 2021-03-12 |  |  |  | No |  |  | Not Required
23INR0054 | Tanglewood Solar | SS Completed, FIS Completed, IA | Brazoria Solar, LLC | Tap 345kV 42500 Dow - 43035 Oasis Ckt 18 | Brazoria | COASTAL | 2025-01-16 | SOL | PV | 257 |  | 2021-01-15 | 2020-07-10 | 2020-09-28 | 2020-11-24 | 2022-03-22 | Yes | 2022-11-01 | Yes |  |  | Not Required | 2023-02-10
23INR0055 | Tabor Solar | SS Completed, FIS Started, No IA | Quanah Solar LLC | Tap 345kV 60504 Tesla - 61001 Jim Treece | Hardeman | WEST | 2025-05-01 | SOL | PV | 506.4 |  | 2020-08-31 | 2020-09-02 | 2020-11-19 | 2020-07-07 |  | No |  | No |  |  | Not Required
23INR0056 | Caliche Mound Solar | SS Completed, FIS Completed, IA | Tierra Blanco Solar LLC | tap 345kV 23906 AJSwope - 23910 Windmill | Deaf Smith | PANHANDLE | 2025-08-28 | SOL | PV | 408.21 |  | 2020-08-27 | 2020-07-24 | 2020-09-08 | 2020-07-07 | 2023-08-22 |  | 2023-10-12 | Yes |  |  | Not Required
23INR0057 | Duffy Solar | SS Completed, FIS Started, IA | VDA Solar Texas 1 LLC | Tap 345kV 44200 Hilje and 5915 STP c64 | Matagorda | COASTAL | 2026-11-01 | SOL | PV | 545.21 |  | 2021-02-05 | 2020-09-11 | 2020-11-19 | 2021-02-04 |  | Yes | 2023-04-12 | Yes |  |  | Not Required
23INR0058 | Erin Solar | SS Completed, FIS Completed, IA | Erin Solar LLC | 44040 Bailey 345 kV | Wharton | SOUTH | 2025-05-31 | SOL | PV | 202.5 |  | 2021-02-15 | 2020-07-24 | 2020-10-08 | 2021-01-26 | 2022-05-24 | No | 2023-03-22 | No | Not Required | Not Required | Not Required
23INR0059 | Briggs Solar | SS Completed, FIS Started, No IA | Briggs Solar, LLC | tap 345kV 60515 Clear Crossing - 60507 Pendulo | Haskell | WEST | 2024-12-31 | SOL | PV | 309.6 |  | 2021-03-15 | 2020-08-04 | 2020-10-28 | 2021-03-04 |  |  |  | No |  |  | Not Required
23INR0061 | Noria Solar DCC | SS Completed, FIS Started, IA | Noria Hondo Solar, LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2025-09-01 | SOL | PV | 145 |  | 2021-03-15 | 2020-08-04 | 2020-10-28 | 2021-03-10 |  |  | 2022-10-12 | Yes |  |  | Not Required
23INR0062 | Noria Storage | SS Completed, FIS Started, IA | Noria Hondo Solar, LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2025-09-01 | OTH | BA | 75 |  | 2021-04-01 | 2020-08-04 | 2020-10-28 | 2021-03-30 |  |  | 2022-10-12 | Yes | Not Required | Not Required | Not Required | 2023-04-12
23INR0065 | Bonita Creek Solar | SS Completed, FIS Started, No IA | Invenergy Solar Development North America LLC | tap 345kV 5133 Elm Creek - 5901 San Miguel | Atascosa | SOUTH | 2026-12-31 | SOL | PV | 200 |  | 2021-07-16 | 2020-12-03 | 2021-03-10 | 2021-06-16 |  |  |  | No |  |  | Not Required
23INR0066 | Accalia Point Solar | SS Completed, FIS Started, No IA | Accalia Point Solar LLC | Tap 345kV 79500 Palmito - 80137 Stewart | Cameron | COASTAL | 2027-05-31 | SOL | PV | 190.5 | COD | 2021-02-10 | 2020-10-23 | 2021-01-12 | 2021-01-27 |  | No |  | No |  |  | Not Required
23INR0070 | Chillingham Solar | SS Completed, FIS Completed, IA | Chillingham Solar LLC | 3687 Bell County East 345kV | Bell | NORTH | 2024-12-15 | SOL | PV | 352.39 |  | 2020-09-02 | 2020-08-04 | 2020-10-28 | 2020-08-26 | 2021-07-22 |  | 2022-02-04 | No | Not Required | Not Required | Not Required
23INR0071 | BRP Volans BESS | SS Completed, FIS Completed, No IA | BRP Volans BESS LLC | 11189 Quarry Field SW - 1074 Wink 138kV | Winkler | WEST | 2024-12-01 | OTH | BA | 206.88 |  | 2020-08-26 | 2020-08-04 | 2020-10-28 | 2020-08-24 | 2021-10-11 | No |  | No |  |  | Not Required
23INR0072 | Tortolas BESS | SS Completed, FIS Completed, IA | BRP Tortolas BESS LLC | 39030 Alvin 138kV | Brazoria | COASTAL | 2023-12-31 | OTH | BA | 50.3 |  | 2020-08-27 | 2020-08-04 | 2020-10-28 | 2020-08-24 | 2021-07-30 |  | 2021-07-15 | Yes | Not Required | Not Required | Not Required | 2021-07-30 | 2021-07-30 | 2021-07-30
23INR0073 | BRP Galan BESS | SS Completed, FIS Started, No IA | BRP Galan BESS LLC | 5007 Alamo One 138kV | Bexar | SOUTH | 2024-12-01 | OTH | BA | 75.97 |  | 2020-08-20 | 2020-08-04 | 2020-10-28 | 2020-08-17 |  |  |  | No |  |  | Not Required
23INR0074 | BRP Ampato BESS | SS Completed, FIS Started, No IA | BRP Ampato BESS LLC | 10002 NS Crane Switch 138kV | Crane | WEST | 2024-12-01 | OTH | BA | 121.56 |  | 2020-08-26 | 2020-08-04 | 2020-10-28 | 2020-08-24 |  |  |  | No |  |  | Not Required
23INR0075 | BRP Rhine BESS | SS Completed, FIS Completed, No IA | BRP Rhine BESS LLC | Tap 345kV 11188 QUARRYFLD - 11010 WOLF | Ward | WEST | 2025-12-01 | OTH | BA | 206.89 |  | 2020-09-22 | 2020-08-04 | 2020-11-02 | 2020-09-17 | 2021-09-29 |  |  | No |  |  | Not Required
23INR0076 | Cannon Solar SLF | SS Completed, FIS Started, No IA | Cannon Solar, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2026-12-31 | SOL | PV | 152.5 |  | 2020-09-21 | 2020-09-11 | 2020-12-07 | 2020-09-11 |  |  |  | No | Not Required | Not Required | Not Required
23INR0077 | Cachena Storage SLF | SS Completed, FIS Started, No IA | Clear Fork Creek Solar LLC | Tap 345KV 5133 Elmcreek - 5323 Old Hickory | Wilson | SOUTH | 2026-12-31 | OTH | BA | 0 |  | 2020-08-21 | 2020-08-21 | 2020-10-16 | 2020-08-17 |  |  |  | No | Not Required | Not Required | Not Required
23INR0078 | Shaw Solar SLF | SS Completed, FIS Started, No IA | Rio Lago Solar, LLC | Tap 138kV 7146 Verde Creek - 7438 Bandera | Bandera | SOUTH | 2025-09-12 | SOL | PV | 123 | COD | 2021-05-21 | 2020-10-23 | 2021-01-12 | 2021-05-11 |  |  |  | No |  |  | Not Required
23INR0079 | Chillingham Storage | SS Completed, FIS Completed, IA | Chillingham Solar LLC | 3687 Bell County East 345kV | Bell | NORTH | 2024-12-31 | OTH | BA | 153.75 |  | 2020-09-04 | 2020-09-11 | 2020-11-30 | 2020-08-26 | 2021-07-22 |  | 2022-02-04 | No | Not Required | Not Required | Not Required
23INR0082 | Bottom Grass Solar | SS Completed, FIS Completed, IA | Bottom Grass Solar Project, LLC | tap 345 kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2026-04-01 | SOL | PV | 508.61 |  | 2020-10-19 | 2020-11-05 | 2021-02-02 | 2020-10-21 | 2022-12-13 |  | 2023-06-29 | No |  |  | Not Required
23INR0083 | Bottom Grass BESS | SS Completed, FIS Completed, IA | Bottom Grass Solar Project, LLC | tap 345 kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2026-04-01 | OTH | BA | 202.21 |  | 2020-10-19 | 2020-11-05 | 2021-02-02 | 2020-10-21 | 2022-12-13 |  | 2023-06-29 | No | Not Required | Not Required | Not Required
23INR0084 | Lavaca Bay Solar | SS Completed, FIS Completed, IA | TC Energy Solar LLC | tap 345 kV REFUGE 42400 - JONES CREEK 47532 ckt 27 | Matagorda | COASTAL | 2024-12-04 | SOL | PV | 243.46 |  | 2021-03-05 | 2020-09-11 | 2020-11-19 | 2021-03-05 | 2022-03-21 | Yes | 2022-06-15 | Yes |  |  | Not Required
23INR0086 | Hanson Solar | SS Completed, FIS Started, IA | Hanson Solar, LLC | tap 345kV 1444 Brown - 11406 Central Bluff | Coleman | WEST | 2025-10-21 | SOL | PV | 400.58 |  | 2021-03-30 | 2020-10-23 | 2021-02-02 | 2021-03-25 |  |  | 2023-09-20 | Yes |  |  | Not Required
23INR0087 | Kinenos Solar | SS Completed, FIS Started, No IA | Encino del Sol Energy, LLC | tap 345kV 8905 North Edinburg - 8455 Lon Hill | Brooks | SOUTH | 2024-12-31 | SOL | PV | 203.17 |  | 2020-08-28 | 2020-12-22 | 2021-03-10 | 2020-12-03 |  | No |  | No |  |  | Not Required
23INR0088 | Nockenut Springs Solar 1 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Guadalupe | SOUTH | 2025-02-28 | SOL | PV | 203.17 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No |  |  | Not Required
23INR0089 | Donegal Solar | SS Completed, FIS Started, IA | HE-Cottonwood Solar LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2024-11-30 | SOL | PV | 204.2 |  | 2020-10-08 | 2020-10-07 | 2020-12-28 | 2020-09-11 |  |  | 2022-07-25 | No |  |  | Not Required
23INR0090 | Iguala Solar | SS Completed, FIS Started, No IA | Iguala Solar LLC | tap 345kV 5915 STP - 8249 Angstrom | Victoria | SOUTH | 2025-12-31 | SOL | PV | 250 |  | 2021-06-11 | 2020-10-07 | 2020-12-28 | 2021-06-07 |  | Yes |  | No |  |  | Not Required
23INR0091 | Cascade Solar | SS Completed, FIS Completed, IA | Cascade Solar Energy, LLC | 345kV Oasis (43035) – Seabreeze (43020) circuit 27 | Brazoria | COASTAL | 2024-12-31 | SOL | PV | 254.2 |  | 2021-05-05 | 2021-02-09 | 2021-05-06 | 2021-04-28 | 2023-03-02 | No | 2023-04-17 | Yes | Not Required | Not Required | Not Required | 2023-12-07
23INR0093 | Alila Solar | SS Completed, FIS Completed, IA | Electra Energy Project, LLC | 8249 Angstrom 345kV | San Patricio | COASTAL | 2026-05-15 | SOL | PV | 256.5 |  | 2020-10-19 | 2020-10-07 | 2020-12-30 | 2020-09-11 | 2023-03-16 | No | 2023-01-03 | Yes |  |  | Not Required
23INR0094 | BRP Pyxis BESS | SS Completed, FIS Completed, No IA | BRP Pyxis BESS LLC | tap 138kV 1009 Yucca - 11197 Sand Tank Pod | Ward | WEST | 2025-12-01 | OTH | BA | 206.87 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 | 2021-09-23 |  |  | No |  |  | Not Required
23INR0100 | Evergreen Solar | SS Completed, FIS Completed, No IA | Bucks Bayou LLC | 8111 Magilla 138kV | Matagorda | COASTAL | 2025-12-31 | SOL | PV | 150 |  | 2021-07-02 | 2020-12-03 | 2021-02-18 | 2021-06-07 | 2023-08-18 |  |  | No |  |  | Not Required
23INR0101 | Atria Solar | SS Completed, FIS Completed, No IA | Atria Energy Project, LLC | 40770 Hacher 138kV | Chambers | HOUSTON | 2025-12-30 | SOL | PV | 112.4 |  | 2020-10-19 | 2020-10-23 | 2021-01-12 | 2020-09-28 | 2021-12-15 |  |  | No |  |  | Not Required
23INR0103 | Burksol BESS | SS Completed, FIS Started, IA | Donegal BESS | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2024-11-30 | OTH | BA | 103.27 |  | 2020-10-12 | 2020-10-23 | 2021-01-12 | 2020-09-28 |  |  | 2022-11-17 | No |  |  | Not Required
23INR0104 | BRP Kamet BESS | SS Completed, FIS Started, No IA | BRP Kamet BESS LLC | Andrews North – McKenzie Draw Switch 138 kV | Andrews | WEST | 2025-12-01 | OTH | BA | 202.46 |  | 2020-09-28 | 2020-10-07 | 2020-12-30 | 2020-09-23 |  | No |  | No |  |  | Not Required
23INR0111 | GULF STAR SOLAR | SS Completed, FIS Completed, IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2025-01-02 | SOL | PV | 300.5 |  | 2020-12-03 | 2020-10-23 | 2021-02-02 | 2020-11-24 | 2022-11-28 | No | 2021-10-01 | Yes | Not Required | Not Required | Not Required | 2021-11-05 | 2023-01-27 | 2023-01-27
23INR0113 | Cannon Storage SLF | SS Completed, FIS Started, No IA | Cannon Solar, LLC | Tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2026-12-31 | OTH | BA | 0 |  | 2020-10-19 | 2020-11-05 | 2020-12-07 | 2020-10-29 |  |  |  | No | Not Required | Not Required | Not Required
23INR0114 | True North Solar | SS Completed, FIS Completed, IA | True North Solar LLC | Tap 345 kV St. Johns Switch (3384) – Jewett Switch (3390) | Falls | NORTH | 2024-06-30 | SOL | PV | 238.26 |  | 2021-09-27 | 2021-01-25 | 2021-04-12 | 2021-09-21 | 2023-02-01 | No | 2023-04-20 | Yes | Not Required | Not Required | Not Required | 2023-06-06 | 2023-10-16 | 2023-10-30
23INR0115 | BRP Pobeda BESS | SS Completed, FIS Started, No IA | BRP Pobeda BESS LLC | 44645 Singleton 345kV | Grimes | NORTH | 2024-12-01 | OTH | BA | 301.41 |  | 2020-11-06 | 2020-11-18 | 2021-02-08 | 2020-10-27 |  |  |  | No |  |  | Not Required
23INR0118 | Blevins Solar | SS Completed, FIS Completed, IA | Blevins Solar, LLC | Tap Bellfalls Switch (3404) – Lake Creek Switch (3409) | Falls | NORTH | 2025-07-01 | SOL | PV | 275.6 |  | 2021-02-18 | 2021-02-04 | 2021-04-19 | 2021-02-12 | 2023-05-03 |  | 2023-06-17 | Yes |  |  | Not Required
23INR0119 | Blevins Storage | SS Completed, FIS Completed, IA | Blevins Solar, LLC | tap 345kV 3414 Temple Switch - 3409 Lake Creek | Falls | NORTH | 2025-07-01 | OTH | BA | 183.7 |  | 2021-02-19 | 2021-02-04 | 2021-04-19 | 2021-02-12 | 2023-05-03 |  | 2023-06-17 | Yes |  |  | Not Required
23INR0123 | Vaca Storage | SS Completed, FIS Started, No IA | Long Mount Storage, LLC | 138kV 8723 Cangrejo | Calhoun | COASTAL | 2025-06-01 | OTH | BA | 101 |  | 2022-06-01 | 2021-03-26 | 2021-06-14 | 2022-05-11 |  |  |  | No | Not Required | Not Required | Not Required
23INR0124 | Coral Storage | SS Completed, FIS Completed, IA | Copperhead Solar, LLC | tap 138kV 3410 Lake Creek Switch - 3582 Falls County | Falls | NORTH | 2024-03-31 | OTH | BA | 99 | COD | 2021-02-26 | 2021-03-01 | 2021-05-13 | 2021-02-01 | 2022-10-31 | No | 2022-10-28 | Yes | Not Required | Not Required | Not Required | 2022-11-07 | 2022-11-07 | 2022-11-07 |  |  | 2023-09-18 | 2023-12-11
23INR0126 | Sigma Storage | SS Completed, FIS Started, No IA | AES Distributed Energy, Inc | 40460 Deepwater 138kV | Harris | HOUSTON | 2024-12-31 | OTH | BA | 408.4 |  | 2022-02-17 | 2021-05-11 | 2021-07-30 | 2022-02-04 |  | No |  | No |  |  | Not Required
23INR0127 | Beacon Storage | SS Completed, FIS Started, No IA | AES Distributed Energy, Inc | 40450 Deepwater 345kV | Harris | HOUSTON | 2024-12-31 | OTH | BA | 408.7 |  | 2022-03-23 | 2021-05-05 | 2021-07-27 | 2022-02-28 |  | No |  | No |  |  | Not Required
23INR0130 | Ocee Creek Solar | SS Completed, FIS Started, No IA | OCI LoneSun LLC | 173 Crawford 138kV | McLennan | NORTH | 2025-07-01 | SOL | PV | 101.52 |  | 2021-01-25 | 2021-02-09 | 2021-05-06 | 2020-12-22 |  |  |  | No | Not Required | Not Required | Not Required
23INR0131 | BRP Batura BESS | SS Completed, FIS Started, No IA | BRP Batura BESS LLC | 5260 Leon Creek 138kV | Bexar | SOUTH | 2025-12-01 | OTH | BA | 251.65 |  | 2020-11-12 | 2020-12-03 | 2021-02-16 | 2020-11-12 |  |  |  | No |  |  | Not Required
23INR0132 | BRP Bonete BESS | SS Completed, FIS Started, No IA | BRP Bonete BESS LLC | 8951 Stewart Road 138kV | Hidalgo | SOUTH | 2024-06-01 | OTH | BA | 201.13 |  | 2020-11-17 | 2020-12-03 | 2021-02-16 | 2020-11-18 |  | No |  | No |  |  | Not Required
23INR0134 | BRP Kailas BESS | SS Completed, FIS Started, No IA | BRP Kailas BESS LLC | 6216 Bluff Creek 138kV | Taylor | WEST | 2024-12-01 | OTH | BA | 201.29 |  | 2020-11-20 | 2020-12-03 | 2021-02-16 | 2020-11-20 |  |  |  | No |  |  | Not Required
23INR0135 | BRP Elbus BESS | SS Completed, FIS Started, No IA | BRP Elbus BESS LLC | 9075 Lytton 138kV | Caldwell | SOUTH | 2024-12-01 | OTH | BA | 201.11 |  | 2020-11-30 | 2020-12-03 | 2021-02-18 | 2020-11-25 |  |  |  | No |  |  | Not Required
23INR0137 | BRP Diran BESS | SS Completed, FIS Completed, No IA | BRP Diran BESS LLC | 43190 South Lane City 138kV | Wharton | SOUTH | 2025-12-01 | OTH | BA | 100.63 |  | 2020-11-30 | 2020-12-03 | 2021-02-18 | 2020-11-25 | 2022-04-15 | No |  | No |  |  | Not Required
23INR0139 | BRP Passu BESS | SS Completed, FIS Started, No IA | BRP Passu BESS LLC | 6111 Riley 345kV | Wilbarger | WEST | 2024-12-01 | OTH | BA | 301.82 |  | 2020-11-30 | 2020-12-03 | 2021-02-19 | 2020-11-27 |  | No |  | No |  |  | Not Required
23INR0140 | BRP Seine BESS | SS Completed, FIS Started, No IA | BRP Seine BESS LLC | 60500 Edith Clarke 345kV | Foard | WEST | 2024-12-01 | OTH | BA | 301.69 |  | 2020-11-30 | 2020-12-03 | 2021-02-19 | 2020-11-27 |  | No |  | No |  |  | Not Required
23INR0143 | BRP Sepik BESS | SS Completed, FIS Started, No IA | BRP Sepik BESS LLC | tap 138kV 11342 Loraine South – 1032 Morgan Creek | Mitchell | WEST | 2024-12-01 | OTH | BA | 200.85 |  | 2020-12-08 | 2020-12-22 | 2021-03-15 | 2020-12-01 |  |  |  | No |  |  | Not Required
23INR0144 | Galactic Solar | SS Completed, FIS Completed, IA | UKA North America, LLC | Tap 138kV 1744 Gordonville - 11704 Sherman West | Grayson | NORTH | 2024-03-01 | SOL | PV | 205.2 |  | 2020-12-08 | 2020-12-22 | 2021-03-10 | 2020-12-01 | 2021-12-21 | No | 2022-08-12 | No |  |  | Not Required
23INR0150 | Cradle Solar | SS Completed, FIS Completed, IA | Cradle Solar LLC | tap 345kV 42500 Dow - 43035 Oasis ckt 18 | Brazoria | COASTAL | 2025-01-02 | SOL | PV | 225 |  | 2021-03-26 | 2021-02-04 | 2021-04-21 | 2021-03-15 | 2022-06-14 | No | 2023-03-15 | No |  |  | Not Required
23INR0153 | Mercury II Solar | SS Completed, FIS Completed, IA | Mercury II Solar, LLC | 68092 Liberty Station 345kV | Hill | NORTH | 2024-06-28 | SOL | PV | 206.11 |  | 2020-12-22 | 2021-01-26 | 2021-04-12 | 2020-12-11 | 2021-10-14 |  | 2021-10-18 | Yes | Not Required | Not Required | Not Required | 2022-03-21 | 2022-04-29 | 2022-04-29 |  |  | 2023-10-19 | 2023-10-31
23INR0154 | Ebony Energy Storage | SS Completed, FIS Completed, IA | Ebony Energy Storage, LLC | 5180 Green Mountain 138kV | Comal | SOUTH | 2024-05-06 | OTH | BA | 203.5 | COD | 2021-02-03 | 2021-02-04 | 2021-04-21 | 2021-01-20 | 2023-02-16 | No | 2022-05-31 | Yes | Not Required | Not Required | Not Required | 2023-02-10 | 2023-05-01 | 2023-05-01
23INR0155 | Umbra (Stockyard) Solar | SS Completed, FIS Completed, IA | Stockyard Solar Project, LLC | tap 345kV 1695 Monticello - 11699 Woodard | Franklin | NORTH | 2026-04-16 | SOL | PV | 207.84 | COD | 2021-05-20 | 2021-01-25 | 2021-04-12 | 2020-12-31 | 2022-06-16 | No | 2022-10-11 | No |  |  | Not Required
23INR0156 | Umbra (Stockyard) BESS | SS Completed, FIS Completed, IA | Stockyard Solar Project, LLC | tap 345kV 1695 Monticello - 11699 Woodard | Franklin | NORTH | 2026-04-16 | OTH | BA | 72.98 | COD | 2021-05-20 | 2021-01-25 | 2021-04-12 | 2020-12-31 | 2022-06-16 | No | 2022-10-11 | No | Not Required | Not Required | Not Required
23INR0159 | Five Wells Storage | SS Completed, FIS Completed, IA | Five Wells Solar Center LLC | 3687 Bell Country East 345kV | Bell | NORTH | 2023-12-30 | OTH | BA | 220.8 | COD | 2021-03-01 | 2021-02-04 | 2021-04-21 | 2021-01-22 | 2023-04-28 |  | 2023-02-27 | Yes | Not Required | Not Required | Not Required | 2023-02-27 | 2023-04-28 | 2023-04-28 |  |  | 2023-12-07
23INR0160 | Grimes County Solar | SS Completed, FIS Completed, IA | Grimes County Solar Project, LLC | 2 Keith Switch 138kV | Grimes | NORTH | 2025-03-15 | SOL | PV | 210 |  | 2020-12-16 | 2021-01-26 | 2021-04-12 | 2020-12-16 | 2022-08-01 |  | 2022-06-23 | Yes |  |  | Not Required | 2022-09-21
23INR0162 | Redonda Solar | SS Completed, FIS Started, IA | J&R Power DevCo, LLC | tap 345kV 80307 Del Sol - 80225 Cenizo | Zapata | SOUTH | 2026-12-30 | SOL | PV | 253.21 | COD | 2021-08-19 | 2021-01-25 | 2021-04-12 | 2021-08-11 |  |  | 2021-12-28 | Yes | Not Required | Not Required | Not Required | 2022-04-27
23INR0163 | Ringtail Ridge Storage | SS Completed, FIS Started, No IA | KCE TX 26, LLC | 7150 Kendall 138kV | Kendall | SOUTH | 2025-08-01 | OTH | BA | 100.57 |  | 2021-01-08 | 2021-01-25 | 2021-04-16 | 2020-12-29 |  |  |  | No |  |  | Not Required
23INR0164 | Steppe Reserve Storage | SS Completed, FIS Started, No IA | KCE TX 25, LLC | 8283 Asherton 138 kV | Dimmit | SOUTH | 2026-03-01 | OTH | BA | 51.9 |  | 2021-01-08 | 2021-01-25 | 2021-04-16 | 2020-12-29 |  |  |  | No |  |  | Not Required
23INR0166 | Great Kiskadee Storage | SS Completed, FIS Completed, IA | Great Kiskadee Storage, LLC | 8951 Stewart Rd 138kV | Hidalgo | SOUTH | 2024-09-06 | OTH | BA | 103.05 |  | 2021-10-08 | 2021-01-26 | 2021-04-12 | 2021-08-24 | 2023-10-24 |  | 2022-06-30 | Yes |  |  | Not Required | 2022-09-20 | 2023-10-25
23INR0168 | Charolais Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 44000 W A Parish - 5915 STP | Matagorda | COASTAL | 2026-12-15 | OTH | BA | 150 |  | 2021-06-25 | 2021-02-09 | 2021-05-06 | 2021-06-11 |  |  |  | No |  |  | Not Required
23INR0171 | Goodalta Solar | SS Completed, FIS Completed, No IA | GoodAlta Power Center LLC | tap 138kV 3127 Trinidad - 212 Winkler | Navarro | NORTH | 2025-08-26 | SOL | PV | 180 |  | 2021-08-03 | 2021-01-25 | 2021-04-12 | 2021-01-07 | 2023-05-26 | No |  | No |  |  | Not Required
23INR0174 | Lutum Wind Alt. POI 1 | SS Completed, FIS Started, No IA | RWE | tap 345kV 1458 Cobb - 1429 Jacksboro | Jack | NORTH | 2024-07-11 | WIN | WT | 241.5 | Status Change INA-to-PLN | 2021-09-28 | 2021-02-09 | 2021-05-06 | 2021-09-01 |  |  |  | No |  |  | Not Required
23INR0177 | Wren Storage | SS Completed, FIS Started, No IA | Wren Storage, LLC | 8601 Cebolla 345kV | Willacy | COASTAL | 2024-10-31 | OTH | BA | 170 |  | 2021-08-30 | 2021-01-25 | 2021-04-16 | 2021-08-26 |  | No |  | No | Not Required | Not Required | Not Required
23INR0180 | Jackalope Solar | SS Completed, FIS Completed, IA | Peacock Energy Project, LLC | 8173 Gibbs 138kV | San Patricio | COASTAL | 2024-10-31 | SOL | PV | 155.68 |  | 2021-01-29 | 2021-02-09 | 2021-05-06 | 2021-02-02 | 2021-11-18 |  | 2021-09-30 | Yes | Not Required | Not Required | Not Required | 2021-10-18 | 2022-10-24 | 2023-10-19
23INR0181 | Starling Storage | SS Completed, FIS Completed, No IA | Starling Storage, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2024-11-30 | OTH | BA | 63.6 |  | 2021-10-20 | 2021-01-25 | 2021-04-16 | 2021-10-07 | 2023-07-31 | No |  | No | Not Required | Not Required | Not Required
23INR0182 | Welder Storage | SS Completed, FIS Started, No IA | Welder Storage, LLC | tap 345kV 8624 Grissom - 8455 Lon Hill | San Patricio | COASTAL | 2024-10-31 | OTH | BA | 100 |  | 2021-10-18 | 2021-01-25 | 2021-04-16 | 2021-10-07 |  | Yes |  | No | Not Required | Not Required | Not Required
23INR0183 | Pradera Storage | SS Completed, FIS Started, No IA | Pradera Storage, LLC | tap 345 kV Lobo 80219 - Fowlerton 5709 ckt #2 | Webb | SOUTH | 2024-10-31 | OTH | BA | 153.11 |  | 2021-10-18 | 2021-01-25 | 2021-04-16 | 2021-10-13 |  |  |  | No |  |  | Not Required
23INR0187 | Leitrim 1 Solar | SS Completed, FIS Completed, No IA | Leitsol LLC | tap 138kV 3522 Hillsboro - 3546 Whitney | Hill | NORTH | 2026-10-01 | SOL | PV | 98.44 |  | 2021-03-23 | 2021-01-26 | 2021-04-12 | 2021-03-18 | 2022-02-01 | No |  | No |  |  | Not Required
23INR0189 | Bayside Solar | SS Completed, FIS Completed, No IA | Bayside Solar, LLC | tap between 345kV 5915 STP - 5133 Elm Creek ckt #1 and Cachena (#5068) and Old Hickory (#5323). | Victoria | SOUTH | 2026-08-31 | SOL | PV | 508.9 |  | 2021-01-25 | 2021-02-09 | 2021-05-06 | 2021-01-25 | 2023-12-06 | Yes |  | No | Not Required | Not Required | Not Required
23INR0190 | Cosmos Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 9073 Holman - 44200 Hillje | Wharton | SOUTH | 2024-12-01 | SOL | PV | 609.74 |  | 2021-02-10 | 2021-03-01 | 2021-05-13 | 2021-03-01 |  |  |  | No | Not Required | Not Required | Not Required
23INR0193 | Stockdale Solar | SS Completed, FIS Started, No IA | Stockdale Solar, LLC | tap 345kV 5133 Elm Creek - 5323 Old Hickory Ckt 2 | Wilson | SOUTH | 2025-12-31 | SOL | PV | 152.5 |  | 2021-01-15 | 2021-04-01 | 2021-07-02 | 2021-02-22 |  |  |  | No |  |  | Not Required
23INR0194 | Pequin Energy Storage | SS Completed, FIS Started, No IA | Pequin Energy Storage, LLC | 39500 TN West Columbia 138kV | Brazoria | COASTAL | 2025-06-14 | OTH | BA | 103.4 |  | 2021-06-29 | 2021-01-25 | 2021-04-16 | 2021-06-14 |  |  |  | No |  |  | Not Required
23INR0195 | Desert Willow BESS | SS Completed, FIS Completed, IA | Desert Willow Energy Storage, LLC | tap 345kV 1906 Venus_S5 - 1916 LiggettA1_5 | Ellis | NORTH | 2024-10-31 | OTH | BA | 154.4 |  | 2021-06-29 | 2021-02-04 | 2021-04-22 | 2021-06-14 | 2023-02-01 | No | 2023-05-15 | No |  |  | Not Required
23INR0200 | Paradiso BESS | SS Completed, FIS Started, No IA | VESI 13 | 8203 Pleasanton 138kV | Atascosa | SOUTH | 2024-05-30 | OTH | BA | 100.92 |  | 2021-09-03 | 2021-03-01 | 2021-05-13 | 2021-08-20 |  | No |  | No | Not Required | Not Required | Not Required
23INR0202 | Erath County Solar | SS Completed, FIS Started, IA | Erath County Solar, LLC | tap 345kV 68020 Romney1E - 68030 KopperlW | Erath | NORTH | 2026-08-27 | SOL | PV | 207.4 | COD | 2021-01-20 | 2021-03-08 | 2021-05-28 | 2021-03-06 |  | Yes | 2023-06-01 | Yes |  |  | Not Required
23INR0204 | GALVANIC BESS | SS Completed, FIS Started, No IA | CED Development Inc | 8252 Bracketville 138kV | Kinney | SOUTH | 2025-11-30 | OTH | BA | 100 |  | 2022-06-15 | 2021-02-09 | 2021-05-06 | 2022-05-13 |  |  |  | No |  |  | Not Required
23INR0205 | SUNSETTER BESS | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2025-11-30 | OTH | BA | 100 |  | 2022-05-27 | 2021-02-09 | 2021-05-06 | 2022-05-13 |  |  |  | No |  |  | Not Required
23INR0206 | PEREGRINE BESS | SS Completed, FIS Started, No IA | CED Development Inc. | tap 345kV 8624 Grissom - 8164 Coleto Creek | Goliad | SOUTH | 2025-05-01 | OTH | BA | 150 |  | 2022-06-15 | 2021-02-10 | 2021-05-06 | 2022-05-13 |  |  |  | No |  |  | Not Required
23INR0207 | El Patrimonio Solar | SS Completed, FIS Started, IA | Heritage Solar LLC | tap 138kV 5429 Trumbo - 5260 Leon Creek | Bexar | SOUTH | 2024-08-30 | SOL | PV | 146.85 |  | 2022-03-02 | 2021-03-16 | 2021-05-28 | 2021-11-23 |  |  | 2023-12-11 | No |  |  | Not Required
23INR0209 | Outpost Storage | SS Completed, FIS Started, No IA | Hecate Energy Outpost Storage LLC | Tap 345kV 80219 Lobo - 5709 Fowlerton | Webb | SOUTH | 2025-04-01 | OTH | BA | 508.1 |  | 2021-02-15 | 2021-03-01 | 2021-05-13 | 2021-02-15 |  |  |  | No |  |  | Not Required
23INR0211 | Rosscommon Solar | SS Completed, FIS Started, No IA | Roscsol, LLC | tap 138kV 1691 Valley Switch - 1776 Paris Switch | Lamar | NORTH | 2025-03-07 | SOL | PV | 91 |  | 2021-01-30 | 2021-03-01 | 2021-05-13 | 2021-02-01 |  |  |  | No |  |  | Not Required
23INR0214 | Harley Hand Storage | SS Completed, FIS Started, No IA | Hecate Energy Harley Hand Solar LLC | 11420 Sweetwater East 345kV | Nolan | WEST | 2025-08-01 | OTH | BA | 509 |  | 2022-04-04 | 2021-03-01 | 2021-05-13 | 2022-03-22 |  |  |  | No | Not Required | Not Required | Not Required
23INR0215 | Big River Solar | SS Completed, FIS Started, No IA | Rio Grande River Solar LLC | tap 138kV 8299 Zapata - 8957 Lopeno4A | Zapata | SOUTH | 2025-12-01 | SOL | PV | 104.35 |  | 2021-04-09 | 2021-05-04 | 2021-07-27 | 2021-04-15 |  |  |  | No |  |  | Not Required
23INR0216 | Venus Mill Storage | SS Completed, FIS Started, No IA | KCE TX 14, LLC | 138 kV Tap #442 Rail Port - #1905 Griffith | Ellis | NORTH | 2026-01-20 | OTH | BA | 100.61 |  | 2022-02-11 | 2022-03-14 | 2022-06-09 | 2022-03-04 |  |  |  | No | Not Required | Not Required | Not Required
23INR0217 | Snap Jaw BESS | SS Completed, FIS Started, No IA | Moccasin Pointe Grid, LLC | tap 138kV 40941 La Porte - 40200 Bimont (Air Liquide) | Harris | HOUSTON | 2026-06-01 | OTH | BA | 201.28 |  | 2021-04-02 | 2021-04-05 | 2021-07-02 | 2021-03-16 |  |  |  | No |  |  | Not Required
23INR0218 | Stump Tail BESS | SS Completed, FIS Completed, No IA | Moccasin Pointe Grid, LLC | Tap 345kV 42000 PH Robinson – 40240 Center | Harris | HOUSTON | 2026-06-01 | OTH | BA | 301.69 |  | 2021-04-02 | 2021-04-05 | 2021-07-02 | 2021-03-17 | 2021-11-09 | Yes |  | No | Not Required | Not Required | Not Required
23INR0219 | Dogfish BESS | SS Completed, FIS Completed, IA | Momentum Dogfish LLC | tap 138kV 38331 TN Alamo St – 38455 TN Holiday | Pecos | WEST | 2024-12-31 | OTH | BA | 75 |  | 2021-09-23 | 2021-03-16 | 2021-05-28 | 2021-09-14 | 2023-05-18 | No | 2023-06-01 | Yes | Not Required | Not Required | Not Required | 2023-08-01
23INR0220 | HOPSLAM BESS | SS Completed, FIS Started, No IA | Momentum LRC Holdco LLC | 38430 White Baker TNP 138kV | Pecos | WEST | 2025-09-20 | OTH | BA | 151.11 |  | 2021-11-15 | 2021-03-16 | 2021-05-28 | 2021-11-09 |  |  |  | No | Not Required | Not Required | Not Required
23INR0222 | Sunbelt Solar | SS Completed, FIS Started, No IA | Rose Hill Solar LLC | tap 138kV 6902 Talty - 6801 Patton | Kaufman | NORTH | 2024-12-24 | SOL | PV | 81.5 |  | 2021-10-05 | 2021-03-16 | 2021-05-28 | 2021-09-30 |  |  |  | No |  |  | Not Required
23INR0223 | Garcitas Creek Solar | SS Completed, FIS Started, IA | Garcitas Creek Solar LLC | Tap 345 kV 5915 South Texas Project – 8249 Angstrom | Jackson | SOUTH | 2025-03-31 | SOL | PV | 201.94 |  | 2021-10-18 | 2021-10-05 | 2021-12-08 | 2021-10-08 |  |  | 2022-06-30 | Yes | Not Required | Not Required | Not Required | 2022-08-24
23INR0224 | Morning Glory Solar | SS Completed, FIS Started, No IA | Armadillo Solar, LLC | tap 345kV 7077 Amos Creek - 76009 Twin Buttes | Tom Green | WEST | 2024-11-30 | SOL | PV | 122.4 | COD | 2022-05-31 | 2021-06-16 | 2021-09-07 | 2022-05-17 |  |  |  | No |  |  | Not Required
23INR0225 | MRG GOODY SOLAR | SS Completed, FIS Completed, IA | MRG GOODY SOLAR PROJECT, LLC | Tap 138 kV Toco Switch (#1700) – Paris Switch (#1693) | Lamar | NORTH | 2025-07-07 | SOL | PV | 171.72 |  | 2022-04-04 | 2021-03-16 | 2021-06-11 | 2022-03-22 | 2023-11-21 |  | 2023-11-07 | No |  |  | Not Required
23INR0227 | Maleza Solar II | SS Completed, FIS Started, No IA | Brush Solar, LLC | tap Blue – Hillje 345 kv Ckt.#27 | Wharton | SOUTH | 2024-12-01 | SOL | PV | 254.94 |  | 2021-05-24 | 2021-04-06 | 2021-06-24 | 2021-05-19 |  |  |  | No |  |  | Not Required
23INR0228 | Hiru Solar | SS Completed, FIS Completed, No IA | Hecate Energy Hazel LLC | Tap 345kV 6111 Riley - 1730 West Krum ckt 1 | Clay | WEST | 2025-12-31 | SOL | PV | 614.4 |  | 2021-09-08 | 2021-04-21 | 2021-07-14 | 2021-08-30 | 2023-05-18 | No |  | No | Not Required | Not Required | Not Required
23INR0229 | Solterra Solar | SS Completed, FIS Started, No IA | CH Solterra LLC | Tap 138kV 11796 White Oak POI - 11797 Brinker POI | Hopkins | NORTH | 2025-09-17 | SOL | PV | 143 |  | 2021-03-17 | 2021-03-19 | 2021-06-11 | 2021-03-18 |  | No |  | No | Not Required | Not Required | Not Required
23INR0231 | Rocinante Solar | SS Completed, FIS Started, IA | Brush Country Solar Project, LLC | tap 138kV 7595 Deer Creek - 7621 Nixon | Gonzales | SOUTH | 2024-12-14 | SOL | PV | 95 |  | 2021-04-28 | 2021-04-22 | 2021-07-14 | 2021-04-22 |  | No | 2022-04-25 | No |  |  | Not Required
23INR0232 | Rocinante BESS | SS Completed, FIS Started, IA | Brush Country Solar Project, LLC | tap 138kV 7595 Deer Creek - 7621 Nixon | Gonzales | SOUTH | 2024-12-14 | OTH | BA | 33 |  | 2021-04-28 | 2021-04-22 | 2021-07-14 | 2021-04-22 |  | No | 2022-04-25 | No |  |  | Not Required
23INR0233 | Earthwise Solar | SS Completed, FIS Started, No IA | Quanah Solar 2 | Tap 345kV 60504 Tesla - 61001 Jim Treece | Hardeman | WEST | 2024-12-29 | SOL | PV | 370.5 |  | 2022-02-23 | 2022-03-14 | 2022-06-09 | 2022-02-25 |  |  |  | No |  |  | Not Required
23INR0234 | Chiltepin Solar | SS Completed, FIS Started, No IA | Chiltepin Solar-Storage, LLC | 6673 Musquiz 138kV | Reeves | WEST | 2025-06-30 | SOL | PV | 200 |  | 2021-11-09 | 2021-04-22 | 2021-07-14 | 2021-10-31 |  |  |  | No |  |  | Not Required
23INR0235 | Hoyte Solar | SS Completed, FIS Completed, IA | Milano Solar, LLC | Tap 138kV 64 Milano - 32 Robertson | Milam | SOUTH | 2025-09-30 | SOL | PV | 203.97 | COD | 2021-04-02 | 2021-04-01 | 2021-07-02 | 2021-03-25 | 2022-06-07 | No | 2022-10-14 | Yes |  |  | Not Required
23INR0237 | Big River BESS | SS Completed, FIS Started, No IA | Rio Grande River Solar LLC | tap 138kV 8299 Zapata - 8957 Lopeno4A | Zapata | SOUTH | 2025-12-01 | OTH | BA | 51.26 |  | 2021-04-09 | 2021-05-04 | 2021-07-27 | 2021-04-15 |  |  |  | No |  |  | Not Required
23INR0239 | Giga Texas Energy Storage | SS Completed, FIS Completed, IA | Giga Texas Energy, LLC. | 7047 Hornsby 345kV | Travis | SOUTH | 2024-01-31 | OTH | BA | 131.05 |  | 2021-07-22 | 2021-04-20 | 2021-07-02 | 2021-07-22 | 2022-08-22 | No | 2021-12-03 | Yes | Not Required | Not Required | Not Required | 2023-02-01 | 2023-02-01 | 2023-02-02 |  |  | 2023-12-13
23INR0240 | Welder Solar II | SS Completed, FIS Started, No IA | Welder Solar, LLC | tap 345kV 8624 Grissom - 8249 Angstrom | San Patricio | COASTAL | 2024-04-29 | SOL | PV | 300 |  | 2022-01-03 | 2021-04-09 | 2021-06-30 | 2021-12-15 |  |  |  | No |  |  | Not Required
23INR0241 | Welder Storage II | SS Completed, FIS Started, No IA | Welder Storage, LLC | tap 345kV 8624 Grissom - 8249 Angstrom | San Patricio | COASTAL | 2024-04-29 | OTH | BA | 100 |  | 2022-01-17 | 2021-04-09 | 2021-06-30 | 2021-12-15 |  |  |  | No | Not Required | Not Required | Not Required
23INR0244 | Tiger Solar | SS Completed, FIS Started, No IA | Vaca Del Sol, LLC | 68004 PHANTOM HILL 345KV | Jones | WEST | 2026-10-15 | SOL | PV | 306.24 |  | 2021-04-21 | 2021-04-29 | 2021-07-22 | 2021-04-29 |  |  |  | No |  |  | Not Required
23INR0245 | Tiger Storage | SS Completed, FIS Started, No IA | Vaca Del Sol, LLC | 68004 PHANTOM HILL 345kV | Jones | WEST | 2026-10-15 | OTH | BA | 251.04 |  | 2021-04-21 | 2021-04-29 | 2021-07-22 | 2021-04-29 |  |  |  | No |  |  | Not Required
23INR0248 | Limewood Storage | SS Completed, FIS Started, No IA | Limewood Bell Renewables LLC | 3420 Temple Pecan Creek 138kV | Bell | NORTH | 2028-12-31 | OTH | BA | 50 | COD | 2021-11-03 | 2021-04-30 | 2021-07-22 | 2021-10-06 |  |  |  | No | Not Required | Not Required | Not Required
23INR0249 | Limewood Solar | SS Completed, FIS Completed, No IA | Limewood Bell Renewables LLC | 3420 Temple Pecan Creek 138kV | Bell | NORTH | 2025-12-31 | SOL | PV | 204 | COD | 2021-11-03 | 2021-04-30 | 2021-07-22 | 2021-10-06 | 2023-02-15 | No |  | No | Not Required | Not Required | Not Required
23INR0250 | Cody Solar | SS Completed, FIS Started, No IA | Woodlands Energy Renewables LLC | 3607 Temple 138kV | Bell | NORTH | 2025-05-01 | SOL | PV | 150 |  | 2022-02-03 | 2021-04-26 | 2021-07-20 | 2022-01-17 |  |  |  | No |  |  | Not Required
23INR0251 | Cody Storage | SS Completed, FIS Started, No IA | Woodlands Energy Renewables LLC | 3607 Temple 138kV | Bell | NORTH | 2025-05-01 | OTH | BA | 50 |  | 2022-02-08 | 2021-04-26 | 2021-07-20 | 2022-01-17 |  |  |  | No |  |  | Not Required
23INR0260 | Flatland Solar Project | SS Completed, FIS Started, No IA | Flatland Solar Project, LLC | 11319 Scurry County 138kV | Scurry | WEST | 2025-12-31 | SOL | PV | 182.2 |  | 2021-05-04 | 2021-05-10 | 2021-07-30 | 2021-04-28 |  | No |  | No | Not Required | Not Required | Not Required
23INR0261 | Dodd Solar I | SS Completed, FIS Started, No IA | Forest Grove Solar LLC | Tap 138kV 6951 Eustace Southeast Switch – 3131 Forest Grove Switch | Henderson | NORTH | 2026-03-01 | SOL | PV | 201.8 |  | 2022-04-12 | 2021-06-24 | 2021-09-20 | 2022-04-04 |  |  |  | No |  |  | Not Required
23INR0266 | Langer Storage | SS Completed, FIS Started, No IA | Langer Solar, LLC | tap 345kV 68040 Kopperl - 68091 Navarro | Bosque | NORTH | 2025-09-24 | OTH | BA | 61.92 |  | 2022-03-22 | 2021-05-10 | 2021-07-30 | 2022-02-25 |  |  |  | No |  |  | Not Required
23INR0272 | BRP Aras BESS | SS Completed, FIS Started, No IA | BRP Aras BESS LLC | 76595 North McCamey 138kV | Upton | WEST | 2025-12-01 | OTH | BA | 303.59 |  | 2021-05-27 | 2021-05-31 | 2021-08-19 | 2021-05-10 |  |  |  | No | Not Required | Not Required | Not Required
23INR0273 | Poco Trail Solar | SS Completed, FIS Started, No IA | Eastern Trail Solar Center, LLC | Tap 345kV 6101 Riley - 1422 Bowman | Wilbarger | WEST | 2026-03-15 | SOL | PV | 438.75 | COD | 2021-06-02 | 2021-09-14 | 2021-11-30 | 2021-07-12 |  |  |  | No | Not Required | Not Required | Not Required
23INR0274 | BRP Parana BESS | SS Completed, FIS Started, No IA | BRP Parana BESS | 7178 Marion 138kV | Guadalupe | SOUTH | 2025-12-01 | OTH | BA | 303.67 |  | 2021-06-01 | 2021-05-31 | 2021-08-19 | 2021-05-10 |  |  |  | No | Not Required | Not Required | Not Required
23INR0275 | BRP Nile BESS | SS Completed, FIS Started, No IA | BRP Nile BESS LLC | 80220 Cenizo 345kV | Webb | SOUTH | 2024-12-01 | OTH | BA | 202.34 |  | 2021-06-01 | 2021-05-31 | 2021-08-19 | 2021-05-10 |  |  |  | No |  |  | Not Required
23INR0278 | BRP Tucana BESS | SS Completed, FIS Started, No IA | BRP Tucana BESS LLC | 1157 Andrews County South 138kV | Andrews | WEST | 2026-01-31 | OTH | BA | 206.98 |  | 2021-06-01 | 2021-06-03 | 2021-08-19 | 2021-05-10 |  | No |  | No |  |  | Not Required
23INR0279 | BRP Trivor BESS | SS Completed, FIS Started, No IA | BRP Trivor BESS LLC | 1272 Fullerton 138kV | Andrews | WEST | 2024-12-01 | OTH | BA | 202.34 |  | 2021-06-01 | 2021-06-03 | 2022-03-15 | 2021-05-10 |  | No |  | No |  |  | Not Required
23INR0282 | BAYSIDE II SOLAR | SS Completed, FIS Started, No IA | Bayside II Solar, LLC | Tap between 345kV 5915 STP - 5133 Elm Creek ckt #1 and Cachena (#5068) and Old Hickory (#5323). | DeWitt | SOUTH | 2026-11-30 | SOL | PV | 252.8 |  | 2021-06-02 | 2021-07-28 | 2021-10-11 | 2021-06-09 |  |  |  | No | Not Required | Not Required | Not Required
23INR0283 | Kota Battery | SS Completed, FIS Started, No IA | Kota Storage, LLC | 23900 Alibates 345kV | Carson | PANHANDLE | 2026-07-01 | OTH | BA | 200.6 |  | 2021-06-02 | 2021-06-07 | 2021-08-27 | 2021-06-02 |  |  |  | No |  |  | Not Required
23INR0284 | Las Moras Battery | SS Completed, FIS Started, No IA | Las Moras Storage, LLC | 8252 Brackett 138kV | Kinney | SOUTH | 2025-06-01 | OTH | BA | 101 |  | 2021-06-01 | 2021-06-07 | 2021-08-27 | 2021-06-02 |  | No |  | No |  |  | Not Required
23INR0285 | BRP Chena BESS | SS Completed, FIS Started, No IA | BRP Chena BESS LLC | Tap 138 kV 1951 Handley SES – 2246 Lakewood | Tarrant | NORTH | 2025-06-01 | OTH | BA | 202.32 |  | 2021-06-02 | 2021-08-05 | 2021-10-18 | 2021-08-05 |  |  |  | No | Not Required | Not Required | Not Required
23INR0286 | Dry Creek Solar I | SS Completed, FIS Completed, IA | OAK HILL SOLAR LLC | tap 345kV 3100 Martin Lake - 3105 Elkton | Rusk | NORTH | 2025-09-01 | SOL | PV | 202.54 |  | 2022-04-04 | 2021-08-18 | 2021-11-05 | 2022-03-30 | 2023-09-27 | No | 2023-11-02 | Yes | Not Required | Not Required | Not Required
23INR0287 | BRP Avila BESS | SS Completed, FIS Started, IA | BRP Avila BESS LLC | 38340 TN Airport 138kV | Pecos | WEST | 2024-12-01 | OTH | BA | 164.95 |  | 2021-06-02 | 2021-05-31 | 2022-01-17 | 2021-05-20 |  | No | 2023-02-06 | Yes |  |  | Not Required
23INR0289 | Skull Creek Solar | SS Completed, FIS Completed, No IA | Skull Creek Solar, LLC | Tap 138kV 3281 Tennessee Colony - 3499 Blackfoot | Anderson | NORTH | 2025-09-16 | SOL | PV | 136.76 |  | 2022-01-10 | 2021-05-28 | 2021-08-19 | 2021-12-16 | 2023-11-22 | No |  | No | Not Required | Not Required | Not Required
23INR0290 | BRP Zeya BESS | SS Completed, FIS Started, IA | BRP Zeya BESS LLC | 38740 Heights 138kV | Galveston | HOUSTON | 2024-12-01 | OTH | BA | 256.83 |  | 2021-06-02 | 2021-05-31 | 2022-03-09 | 2021-05-20 |  | No | 2023-01-20 | Yes | Not Required | Not Required | Not Required
23INR0295 | Sultan Solar | SS Completed, FIS Started, No IA | Lake Whitney Solar, LLC | tap 345kV 68080 Sam Switch – 68090 Kopperl | Bosque | NORTH | 2026-12-31 | SOL | PV | 206.11 |  | 2021-06-03 | 2021-07-01 | 2021-09-27 | 2021-06-29 |  |  |  | No |  |  | Not Required
23INR0296 | Trojan Solar | SS Completed, FIS Completed, IA | NextEra Energy Resources Interconnection Holdings, LLC | 11735 Cedar Elm Switch 345kV | Cooke | NORTH | 2026-02-28 | SOL | PV | 151.25 |  | 2021-06-03 | 2021-07-01 | 2021-09-22 | 2021-06-30 | 2022-09-21 | No | 2022-10-10 | Yes | Not Required | Not Required | Not Required | 2023-07-28
23INR0299 | Anole BESS | SS Completed, FIS Started, IA | Anole Energy Storage, LLC | 2432 Tri-Corner 345kV | Dallas | NORTH | 2024-11-30 | OTH | BA | 247.3 |  | 2021-06-30 | 2021-07-01 | 2021-09-22 | 2021-06-14 |  | No | 2023-04-26 | No |  |  | Not Required
23INR0300 | Greater Bryant G Solar | SS Completed, FIS Completed, IA | Greater Bryant G Solar, LLC | Tap 138kV 1124 Midessa S – 1023 Midland E Circuit 1 | Midland | WEST | 2025-04-11 | SOL | PV | 41.6 |  | 2021-06-09 | 2021-06-17 | 2021-09-01 | 2021-06-16 | 2022-10-28 | No | 2022-07-18 | No |  |  | Not Required
23INR0308 | Fowler Ranch Storage | SS Completed, FIS Started, No IA | Crane BESS, LLC | 76025 Castle Mountain 138kV | Crane | WEST | 2025-01-02 | OTH | BA | 26.44 |  | 2022-06-03 | 2021-06-21 | 2021-09-07 | 2022-05-18 |  |  |  | No |  |  | Not Required
23INR0309 | Peeler Solar | SS Completed, FIS Started, No IA | Peeler Solar, LLC | 5704 San Miguel 138kV | Atascosa | SOUTH | 2024-10-31 | SOL | PV | 209.81 |  | 2021-11-17 | 2021-07-01 | 2021-09-22 | 2021-11-12 |  |  |  | No | Not Required | Not Required | Not Required
23INR0310 | Dunkel BESS | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners | 59156 Yellow House Canyon 115kV | Lubbock | PANHANDLE | 2026-04-03 | OTH | BA | 225 |  | 2022-06-10 | 2022-06-27 | 2022-09-22 | 2022-06-20 |  |  |  | No |  |  | Not Required
23INR0312 | Hofbrau BESS | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners, LLC | 6442 Redcreek 138kV | Tom Green | WEST | 2026-05-05 | OTH | BA | 180.72 |  | 2021-09-22 | 2021-09-22 | 2021-12-09 | 2021-09-22 |  | No |  | No |  |  | Not Required
23INR0317 | Kingfisher Energy Storage | SS Completed, FIS Started, No IA | Nopalosa Energy Storage, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2025-05-31 | OTH | BA | 204.97 |  | 2021-07-01 | 2021-07-08 | 2021-09-28 | 2021-07-02 |  |  |  | No |  |  | Not Required
23INR0318 | Marcelina Storage | SS Completed, FIS Started, No IA | Marcelina Solar, LLC | Tap 345 kV 5133 Elm Creek - 5901 San Miguel | Wilson | SOUTH | 2024-06-01 | OTH | BA | 203.21 |  | 2022-05-03 | 2021-08-09 | 2021-10-29 | 2022-04-22 |  |  |  | No |  |  | Not Required
23INR0322 | Columbus Storage | SS Completed, FIS Started, No IA | EDP Renewables North America LLC | 78103 Nada Substation 138kV | Colorado | SOUTH | 2025-03-15 | OTH | BA | 51.3 |  | 2022-04-20 | 2021-08-12 | 2021-10-29 | 2022-04-06 |  |  |  | No |  |  | Not Required
23INR0324 | Foxland Storage | SS Completed, FIS Completed, No IA | EDP Renewables North America LLC | 138 kV Tap 3110 Stryker Creek - 3147 Troup | Cherokee | NORTH | 2025-10-31 | OTH | BA | 51.3 |  | 2022-04-20 | 2021-08-12 | 2021-10-29 | 2022-04-06 | 2023-07-24 | No |  | No | Not Required | Not Required | Not Required
23INR0330 | BRP Snowdon BESS | SS Completed, FIS Started, No IA | BRP SNOWDON BESS LLC | 23914 Tule Canyon Substation 345kV | Briscoe | PANHANDLE | 2026-07-01 | OTH | BA | 410.94 | COD | 2021-09-15 | 2021-09-15 | 2021-11-29 | 2021-09-08 |  |  |  | No |  |  | Not Required
23INR0331 | Talitha BESS | SS Completed, FIS Completed, IA | Talitha Energy Project, LLC | 5660 Orange Grove Switching Station 138 kV | Jim Wells | SOUTH | 2024-06-30 | OTH | BA | 61.39 |  | 2021-07-20 | 2021-07-15 | 2021-09-28 | 2021-07-15 | 2022-05-03 | No | 2022-11-30 | Yes | Not Required | Not Required | Not Required | 2023-04-04
23INR0332 | Backwater Solar | SS Completed, FIS Completed, No IA | Backwater Solar LLC | Tap 138 kV line from Spring (#684) - Leo(#685) | Cooke | NORTH | 2024-12-31 | SOL | PV | 80 |  | 2021-09-17 | 2021-08-24 | 2021-11-15 | 2021-08-24 | 2023-04-24 |  |  | No |  |  | Not Required
23INR0334 | Liberty Senate Energy Storage 1 | SS Completed, FIS Completed, No IA | Senate Solar LLC | 1445 Burwick 345kV | Jack | NORTH | 2025-10-27 | OTH | BA | 207.4 |  | 2021-09-16 | 2021-10-05 | 2021-12-08 | 2021-10-03 | 2023-03-31 |  |  | No | Not Required | Not Required | Not Required
23INR0335 | BRP Bachman BESS | SS Completed, FIS Completed, No IA | BRP Bachman BESS LLC | 44040 BAILEY 345kV | Wharton | SOUTH | 2024-12-02 | OTH | BA | 411.04 |  | 2021-10-05 | 2021-10-05 | 2021-12-08 | 2021-09-14 | 2022-07-08 |  |  | No |  |  | Not Required
23INR0336 | Bypass Battery Storage | SS Completed, FIS Completed, No IA | Bypass BESS LLC | 44000 W_A_P__POI5A 345 kV | Fort Bend | HOUSTON | 2024-12-15 | OTH | BA | 206.9 |  | 2022-02-18 | 2021-08-18 | 2021-11-05 | 2022-02-03 | 2023-04-24 | No |  | No | Not Required | Not Required | Not Required
23INR0339 | Remy Jade Power Station | SS Completed, FIS Completed, IA | Remy Jade Generating, LLC | Tap 138 kV line from Crosby (#40390) to Highlands (#40811) | Harris | HOUSTON | 2024-05-15 | GAS | GT | 408 |  | 2021-08-24 | 2021-08-24 | 2021-11-15 | 2021-08-13 | 2022-02-23 |  | 2022-08-01 | Yes | 2021-11-22 | Not Required | 2022-07-26 | 2022-11-08 | 2023-02-07 | 2023-04-27
23INR0340 | Larkspur Energy Storage | SS Completed, FIS Started, IA | Larkspur Energy Storage LLC | 71213 Benedum 138kV | Upton | WEST | 2025-01-31 | OTH | BA | 307.46 |  | 2021-07-30 | 2021-08-02 | 2021-10-25 | 2021-07-27 |  |  | 2022-02-28 | No | Not Required | Not Required | Not Required
23INR0342 | BRP Brizo BESS | SS Completed, FIS Started, No IA | BRP Brizo BESS LLC | 138 kV Loop 463 Substation (#5680) | Victoria | SOUTH | 2024-12-01 | OTH | BA | 143.85 |  | 2021-10-05 | 2021-10-05 | 2021-12-22 | 2021-09-24 |  |  |  | No |  |  | Not Required
23INR0343 | Guajillo Energy Storage | SS Completed, FIS Completed, IA | Guajillo Energy Storage LLC | 80219 Lobo Substation 345kV | Webb | SOUTH | 2025-09-30 | OTH | BA | 201.09 |  | 2021-08-02 | 2021-08-09 | 2021-11-01 | 2021-07-27 | 2023-01-31 | No | 2021-12-21 | Yes | Not Required | Not Required | Not Required | 2022-06-27
23INR0344 | XE Hermes Solar | SS Completed, FIS Started, IA | Bell Solar 1 LLC | Tap 345kV 3687 Bell County East Switch - 39950 TNP One Plant Ckt 2 | Bell | NORTH | 2025-08-25 | SOL | PV | 100.36 |  | 2022-06-14 | 2021-09-21 | 2021-12-09 | 2022-06-01 |  |  | 2023-11-08 | Yes |  |  | Not Required
23INR0345 | Elmax Power Station | SS Completed, FIS Started, No IA | Elmax Generating, LLC | Tap 138 kV Lake Houston (#40820) - Atascocita (#40130) ckt 66 | Harris | HOUSTON | 2026-06-01 | GAS | GT | 518.83 |  | 2021-09-14 | 2021-09-14 | 2021-11-30 | 2021-09-14 |  | No |  | No | 2023-10-06 | Not Required | 2023-10-06
23INR0348 | Aggie Energy storage | SS Completed, FIS Completed, No IA | KINGFISHER ENERGY STORAGE LLC | TABOR RD (#32882) | Brazos | NORTH | 2026-06-15 | OTH | BA | 104.4 |  | 2021-08-13 | 2021-08-16 | 2021-11-05 | 2021-08-13 | 2023-07-12 |  |  | No |  |  | Not Required
23INR0349 | Tokio Solar | SS Completed, FIS Completed, IA | Gransolar Texas Eight, LLC | Tap 138kV 3592 Waco Atco - 170 Cotton Belt | McLennan | NORTH | 2025-08-25 | SOL | PV | 177.64 |  | 2022-05-04 | 2021-08-12 | 2021-11-01 | 2022-04-14 | 2023-04-11 |  | 2023-11-06 | Yes | Not Required | Not Required | Not Required | 2023-11-17
23INR0350 | Fort Duncan BESS | SS Completed, FIS Started, IA | Fort Duncan BESS LLC | 78015 Rosita Creek 138kV will be at the new LCRA TSC Sunglow Substation | Maverick | SOUTH | 2025-01-31 | OTH | BA | 106.15 |  | 2021-08-09 | 2021-08-17 | 2021-11-05 | 2021-08-16 |  |  | 2022-12-12 | Yes | Not Required | Not Required | Not Required
23INR0351 | Seven Flags BESS | SS Completed, FIS Started, IA | Seven Flags BESS LLC | 8295 Wormser Substation 138kV | Webb | SOUTH | 2025-09-30 | OTH | BA | 100.58 |  | 2021-09-01 | 2021-09-01 | 2021-11-22 | 2021-08-19 |  | No | 2023-05-19 | Yes | Not Required | Not Required | Not Required
23INR0352 | Blue Valley Solar | SS Completed, FIS Started, No IA | Blue Valley Solar, LLC | Tap on the 138 kV Comstock(#8683) - Corral Line(#60389) | Val Verde | WEST | 2025-12-27 | SOL | PV | 147.99 |  | 2021-11-12 | 2021-11-16 | 2022-01-17 | 2021-11-04 |  | No |  | No | Not Required | Not Required | Not Required
23INR0354 | Bordertown BESS | SS Completed, FIS Started, IA | Bordertown BESS LLC | 8796 Roma 138kV | Starr | SOUTH | 2025-01-31 | OTH | BA | 106.15 |  | 2021-08-17 | 2021-09-01 | 2021-11-22 | 2021-08-19 |  | No | 2022-10-12 | Yes | Not Required | Not Required | Not Required
23INR0357 | BRP Yarra BESS | SS Completed, FIS Started, No IA | BRP Yarra BESS LLC | 138 kV Lake Crest bus #(12492) | Dallas | NORTH | 2025-12-01 | OTH | BA | 205.36 |  | 2021-10-05 | 2021-10-05 | 2021-12-22 | 2021-09-24 |  |  |  | No |  |  | Not Required
23INR0358 | BRP Castor BESS | SS Completed, FIS Started, IA | BRP Castor BESS LLC | 138 kV West Columbia Local Substation (#39530) | Brazoria | COASTAL | 2024-12-01 | OTH | BA | 205.35 |  | 2021-10-01 | 2021-10-04 | 2021-12-22 | 2021-09-24 |  | No | 2023-09-15 | Yes | Not Required | Not Required | Not Required
23INR0359 | BRP Crios BESS | SS Completed, FIS Started, No IA | BRP Crios BESS LLC | Tap 138 kV 1649 HASSE_P8 - 1684 SABANA_8 | Comanche | NORTH | 2025-12-01 | OTH | BA | 87.37 |  | 2021-10-18 | 2021-10-18 | 2022-01-07 | 2021-09-30 |  |  |  | No |  |  | Not Required
23INR0360 | BRP Charon BESS | SS Completed, FIS Completed, No IA | BRP Charon BESS LLC | Tap Smithers (#44650) and Bellaire (#47000) 345kV | Fort Bend | HOUSTON | 2024-12-01 | OTH | BA | 410.81 |  | 2021-10-08 | 2021-10-08 | 2021-12-22 | 2021-09-24 | 2022-10-10 | No |  | No |  |  | Not Required
23INR0361 | Third Coast BESS | SS Completed, FIS Started, IA | Third Coast BESS LLC | 8125 Lolita substation 138kV | Jackson | SOUTH | 2025-09-30 | OTH | BA | 101.21 |  | 2021-09-16 | 2021-08-24 | 2021-11-16 | 2021-09-01 |  | No | 2023-05-17 | Yes | Not Required | Not Required | Not Required
23INR0363 | River Bend | SS Completed, FIS Completed, IA | Brazos Bend BESS LLC | 138 kV Fort Bend Switch (#44280) | Fort Bend | HOUSTON | 2024-05-31 | OTH | BA | 101.64 |  | 2021-09-17 | 2021-08-24 | 2021-11-16 | 2021-09-01 | 2022-06-23 |  | 2022-10-18 | Yes |  |  | Not Required | 2022-11-16 | 2023-07-03 | 2023-07-31
23INR0364 | Tierra Seca BESS | SS Completed, FIS Started, IA | Tierra Seca BESS LLC | 138kV 8255 HAMILTON4A (Hamilton Road Substation) | Val Verde | WEST | 2025-09-30 | OTH | BA | 101.21 |  | 2021-09-14 | 2021-08-24 | 2021-11-16 | 2021-09-01 |  | No | 2023-05-18 | No | Not Required | Not Required | Not Required
23INR0366 | Amsterdam Solar II | SS Completed, FIS Completed, No IA | Cottonwood Bayou Solar II, LLC | tap 345kV 43035 Oasis - 42500 Dow c27, c18 | Brazoria | COASTAL | 2025-03-01 | SOL | PV | 509.88 |  | 2021-12-02 | 2021-08-12 | 2021-10-29 | 2021-11-18 | 2023-07-31 |  |  | No | Not Required | Not Required | Not Required
23INR0367 | Fewell Solar | SS Completed, FIS Completed, IA | Fewell Solar LLC | Tap 138kV 3597 Groesbeck - 3634 Groesbeck Main | Limestone | NORTH | 2025-09-09 | SOL | PV | 203.5 |  | 2022-02-28 | 2021-08-19 | 2021-11-05 | 2022-02-17 | 2023-04-17 | No | 2023-08-18 | Yes | Not Required | Not Required | Not Required | 2023-08-28
23INR0368 | Rocking X Solar | SS Completed, FIS Started, No IA | 7100 Tin Top LLC | Tap the 345 kV Parker Switch (bus#1436) – Comanche Peak SES (bus#1900) Double-Circuit line, Circuit 1. | Parker | NORTH | 2027-04-02 | SOL | PV | 602.2 |  | 2023-09-25 | 2023-10-04 | 2023-12-19 | 2023-09-06 |  |  |  | No |  |  | Not Required
23INR0369 | Anemoi Energy Storage | SS Completed, FIS Completed, IA | Anemoi Energy Storage, LLC | 8574 POMELO 345kV | Hidalgo | SOUTH | 2024-05-06 | OTH | BA | 205 | COD | 2021-09-03 | 2021-09-03 | 2021-11-18 | 2021-08-24 | 2022-07-25 |  | 2022-01-05 | Yes | Not Required | Not Required | Not Required | 2022-07-28 | 2022-07-28 | 2022-07-28
23INR0373 | Fronton Solar 1 | SS Completed, FIS Completed, No IA | Meshek USA Inc. | 8796 Roma Substation 138kV | Starr | SOUTH | 2026-04-14 | SOL | PV | 132.7 |  | 2021-10-05 | 2021-10-05 | 2021-12-22 | 2021-09-17 | 2023-08-10 | No |  | No | Not Required | Not Required | Not Required
23INR0374 | Grand Acres | SS Completed, FIS Started, No IA | Meshek USA Inc. | 8359 South Santa Rosa 138 kV | Cameron | COASTAL | 2026-06-23 | SOL | PV | 153.03 |  | 2021-10-06 | 2021-10-07 | 2021-12-22 | 2021-10-06 |  | No |  | No | Not Required | Not Required | Not Required
23INR0375 | Backwater Storage | SS Completed, FIS Completed, No IA | Backwater Solar LLC | Tap 138 kV 684 Spring - 685 Leo | Cooke | NORTH | 2024-05-31 | OTH | BA | 100 |  | 2021-09-02 | 2021-09-17 | 2021-12-06 | 2021-09-17 | 2023-04-24 |  |  | No |  |  | Not Required
23INR0376 | Cascade Storage | SS Completed, FIS Started, No IA | Oyster Creek LLC | 345kV Oasis (43035) – Seabreeze circuit 27 | Brazoria | COASTAL | 2025-05-31 | OTH | BA | 250 |  | 2021-09-09 | 2021-09-09 | 2021-11-29 | 2021-09-09 |  |  |  | No |  |  | Not Required
23INR0381 | Soportar ESS | SS Completed, FIS Completed, IA | Bexar ESS LLC | 5007 Alamo One 138kV | Bexar | SOUTH | 2025-03-15 | OTH | BA | 102.11 |  | 2022-01-05 | 2021-09-21 | 2021-12-06 |  | 2023-07-28 |  | 2023-07-31 | Yes |  |  | Not Required | 2023-08-25
23INR0382 | Outer Loop BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II | 40700 Greens Bayou 345kV | Harris | HOUSTON | 2025-07-15 | OTH | BA | 201.2 |  | 2022-05-02 | 2021-09-29 | 2021-12-06 | 2022-04-19 |  | No |  | No |  |  | Not Required
23INR0385 | Camp Creek Solar SLF | SS Completed, FIS Completed, IA | White Rock Solar, LLC | TAP 345 KV 3400 TWIN OAK SWITCH - 46020 LIMESTONE PLANT CIRCUIT 1 | Robertson | NORTH | 2024-08-31 | SOL | PV | 165.6 |  | 2021-12-17 | 2021-12-24 | 2022-03-17 | 2021-12-09 | 2023-01-18 | Yes | 2023-07-15 | No |  |  | Not Required
23INR0387 | Pioneer DJ Wind | SS Completed, FIS Completed, IA | Pioneer Hutt Wind Energy LLC | 138 kV Driver station (Bus #: 23863) | Midland | WEST | 2024-05-03 | WIN | WT | 140.32 |  | 2021-10-11 | 2021-10-11 | 2021-12-22 | 2021-10-07 | 2023-03-28 | No | 2023-04-04 | Yes | Not Required | Not Required | Not Required | 2023-04-28 | 2023-04-28 | 2023-04-28 |  |  | 2023-12-19
23INR0388 | White Wing I Energy Storage | SS Completed, FIS Started, No IA | White Wing I Energy Storage LLC | 8418 Rincon Station 138 kV | San Patricio | COASTAL | 2025-12-01 | OTH | BA | 101.63 |  | 2021-10-05 | 2021-10-05 | 2021-12-10 | 2021-09-28 |  | No |  | No | Not Required | Not Required | Not Required
23INR0389 | White Wing II Energy Storage | SS Completed, FIS Started, No IA | White Wing II Energy Storage LLC | 8418 Rincon Station 138 kV | San Patricio | COASTAL | 2025-12-01 | OTH | BA | 101.63 |  | 2021-10-05 | 2021-10-05 | 2021-12-10 | 2021-09-28 |  |  |  | No | Not Required | Not Required | Not Required
23INR0390 | Markum Solar Storage SLF | SS Completed, FIS Started, No IA | Markum Solar Farm, LLC | 177 BOSQUE 138 KV SUBSTATION | McLennan | NORTH | 2024-10-31 | OTH | BA | 0 |  | 2022-09-08 | 2021-10-28 | 2022-02-08 | 2022-08-01 |  |  |  | No |  |  | Not Required
23INR0391 | THUNDER ROAD ENERGY STORAGE | SS Completed, FIS Started, No IA | Hecate Grid Thunder Road Storage LLC | 12491 FISH CREEK 138KV | Dallas | NORTH | 2027-05-31 | OTH | BA | 153.4 |  | 2021-12-29 | 2021-10-22 | 2022-01-17 | 2021-12-17 |  |  |  | No |  |  | Not Required
23INR0392 | Honeycomb Storage SLF | SS Completed, FIS Started, IA | Honeycomb Solar, LLC | 69 kV Tynan Substation (#8107) | Bee | SOUTH | 2025-06-01 | OTH | BA | 0 |  | 2021-10-26 | 2021-11-16 | 2022-01-17 | 2021-11-02 |  | No | 2023-05-01 | Yes | Not Required | Not Required | Not Required
23INR0401 | Headcamp | SS Completed, FIS Completed, No IA | Momentum Headcamp, LLC | tap 138kV 38331 TN Alamo St – 38455 TN Holiday | Pecos | WEST | 2024-12-31 | OTH | BA | 150 | COD | 2022-02-11 | 2021-12-03 | 2022-02-28 | 2022-01-21 | 2023-05-18 | No |  | No | Not Required | Not Required | Not Required
23INR0403 | Connolly Storage | SS Completed, FIS Completed, IA | BT Connolly Storage, LLC | Tap 138kV 1568 Allison – 11568 Flatwood | Wise | NORTH | 2024-08-15 | OTH | BA | 125.36 |  | 2021-10-27 | 2021-10-27 | 2021-12-29 | 2021-10-27 | 2023-11-07 | No | 2023-02-27 | Yes |  |  | Not Required
23INR0408 | TECO GTG2 | SS Completed, FIS Completed, IA | Thermal Energy Corp. | 47430 TECO 138 kV | Harris | HOUSTON | 2024-01-30 | GAS | GT | 50 |  | 2021-12-09 | 2021-11-04 | 2022-01-31 | 2021-12-01 | 2023-04-20 | No | 2022-10-05 | Yes | 2022-06-22 | Not Required | 2022-06-22 | 2023-04-20 | 2023-08-10 | 2023-08-10
23INR0409 | Sunbelt Storage | SS Completed, FIS Started, No IA | Rose Hill Solar LLC | Tap 138kV 6902 Talty - 6894 Rose Hill | Kaufman | NORTH | 2024-12-24 | OTH | BA | 52 |  | 2021-11-09 | 2021-11-12 | 2022-02-08 | 2021-11-09 |  |  |  | No |  |  | Not Required
23INR0411 | SkySealy2 | SS Completed, FIS Started, No IA | Sky Global Power 2, LLC | tap 138kV 44700 Gebhardt - 44740 Wallis circuit 65 | Austin | SOUTH | 2025-06-01 | GAS | GT | 150 |  | 2023-05-08 | 2023-05-15 | 2023-08-11 | 2023-05-08 |  |  |  | No
23INR0414 | Flag City Storage SLF | SS Completed, FIS Completed, No IA | Flag City Solar Project, LLC | tap 138kV 5588 Red Bluff - 5546 Danevang | Jackson | SOUTH | 2025-07-01 | OTH | BA | 0 |  | 2021-11-16 | 2021-11-18 | 2022-02-08 | 2021-11-18 | 2023-01-25 | No |  | No | Not Required | Not Required | Not Required
23INR0418 | Angelo Storage | SS Completed, FIS Completed, IA | Angelo Storage, LLC | 76009 Twin Buttes 345kV | Tom Green | WEST | 2024-05-03 | OTH | BA | 102.97 |  | 2021-11-15 | 2021-11-22 | 2022-02-15 | 2021-11-16 | 2023-05-01 |  | 2021-12-03 | Yes | Not Required | Not Required | Not Required | 2023-05-01 | 2023-05-01 | 2023-05-01
23INR0419 | SOHO BESS | SS Completed, FIS Completed, IA | Black Mountain Energy Storage II | 43035 Oasis 345kV | Brazoria | COASTAL | 2025-01-01 | OTH | BA | 206.32 |  | 2021-12-13 | 2021-12-03 | 2022-02-28 | 2021-12-03 | 2022-06-28 | No | 2022-12-01 | Yes | Not Required | Not Required | Not Required | 2023-01-19
23INR0421 | Tidwell Prairie IV Energy Storage | SS Completed, FIS Started, No IA | Tidwell Prairie LLC | Tap TNP ONE 39950 and Twin Oak 3400 | Robertson | NORTH | 2027-07-01 | OTH | BA | 200 |  | 2021-11-15 | 2021-11-15 | 2022-02-11 | 2021-11-09 |  |  |  | No |  |  | Not Required
23INR0422 | Masroor Storage | SS Completed, FIS Completed, No IA | Masroor Energy Storage LLC | Bus #1760 Bonham 138kV | Fannin | NORTH | 2025-06-26 | OTH | BA | 203 |  | 2021-11-16 | 2021-11-16 | 2022-02-12 | 2021-11-16 | 2023-05-26 |  |  | No |  |  | Not Required
23INR0423 | Camp Creek Storage SLF | SS Completed, FIS Completed, IA | White Rock Solar | TAP 345 KV 3400 TWIN OAK SWITCH - 46020 LIMESTONE PLANT CIRCUIT 1 | Robertson | NORTH | 2024-08-31 | OTH | BA | 0 |  | 2021-12-24 | 2021-12-24 | 2022-03-17 | 2021-12-21 | 2023-01-18 | Yes | 2023-07-15 | No |  |  | Not Required
23INR0425 | Coneflower Storage Project | SS Completed, FIS Completed, No IA | Coneflower Storage Project LLC | 40855 JORDON 138 kV | Chambers | HOUSTON | 2025-06-01 | OTH | BA | 170 |  | 2022-07-11 | 2021-12-20 | 2022-03-11 | 2022-07-06 | 2023-09-12 | No |  | No | Not Required | Not Required | Not Required
23INR0431 | BRP Pollux BESS | SS Completed, FIS Started, No IA | BRP Pollux BESS LLC | 138 kV Olsen Switching Station (#37460) | Bosque | NORTH | 2024-06-01 | OTH | BA | 163.42 |  | 2021-12-20 | 2022-01-06 | 2022-03-16 | 2022-01-04 |  |  |  | No | Not Required | Not Required | Not Required
23INR0439 | Smokey Willie Solar SLF | SS Completed, FIS Completed, No IA | Neches Solar, LLC | Tap 138kV 3325 Blackburn Switch – 3272 Palestine | Anderson | NORTH | 2026-03-13 | SOL | PV | 200.92 |  | 2021-12-29 | 2022-01-06 | 2022-03-31 | 2021-12-29 | 2023-09-22 | No |  | No |  |  | Not Required
23INR0441 | Bug Tussle Wind Project | SS Completed, FIS Started, No IA | Bug Tussle Wind, LLC | Tap 1729 Valley South and 1692 Paris | Lamar | NORTH | 2026-04-20 | WIN | WT | 396.8 |  | 2022-08-30 | 2022-01-13 | 2022-04-11 | 2022-08-16 |  |  |  | No |  |  | Not Required
23INR0455 | Bessie Storage | SS Completed, FIS Started, No IA | Duke Energy Renewables Storage, LLC | Charly Egner Substation Tap 345kV 80355 Del Sol - 80368 LV4 Bridge | Starr | SOUTH | 2025-06-30 | OTH | BA | 210.8 | COD | 2022-02-08 | 2022-02-21 | 2022-05-19 | 2022-02-07 |  |  |  | No | Not Required | Not Required | Not Required
23INR0456 | Bronze Quinta Storage | SS Completed, FIS Started, No IA | KCE TX 28, LLC | S_MCALLN 8371 (S. McAllen 138kV Substation) | Hidalgo | SOUTH | 2025-10-01 | OTH | BA | 103.51 |  | 2022-01-12 | 2022-01-13 | 2022-04-11 | 2022-01-11 |  |  |  | No | Not Required | Not Required | Not Required
23INR0457 | Hive Hollows Storage | SS Completed, FIS Started, No IA | KCE TX 27, LLC | 3415 TEMPLE SWITCH 138kV | Bell | NORTH | 2026-01-01 | OTH | BA | 103.51 |  | 2022-06-30 | 2022-01-28 | 2022-04-26 | 2022-01-18 |  |  |  | No |  |  | Not Required
23INR0460 | GULF STAR STORAGE | SS Completed, FIS Completed, IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2024-06-25 | OTH | BA | 301 |  | 2022-05-18 | 2022-06-02 | 2022-08-29 | 2022-05-11 | 2023-04-10 |  | 2023-03-23 | Yes | Not Required | Not Required | Not Required | 2023-04-28 | 2023-04-28 | 2023-04-28
23INR0462 | Palladium Storage | SS Completed, FIS Started, No IA | Palladium Energy Storage LLC | Tap 138 kV 8656 Luna - 8033 Pantera | Hidalgo | SOUTH | 2026-04-27 | OTH | BA | 152 |  |  | 2022-02-28 | 2022-05-27 | 2022-01-21 |  |  |  | No |  |  | Not Required
23INR0464 | Sloan Storage | SS Completed, FIS Started, No IA | Sloan Energy Storage LLC | 3179 Pauline 138kV | Henderson | NORTH | 2026-03-27 | OTH | BA | 200.9 |  | 2022-07-13 | 2022-02-21 | 2022-05-21 | 2022-06-29 |  |  |  | No | Not Required | Not Required | Not Required
23INR0466 | Shoshana Storage | SS Completed, FIS Started, No IA | Shoshana Storage Project LLC | Tap 345kV 5915 South Texas Project (SO_TEX_345A) - 47531 Jones Creek (JONCRK18LR) Ckt 18 | Matagorda | COASTAL | 2026-08-28 | OTH | BA | 220.15 |  | 2022-05-31 | 2022-03-30 | 2022-06-26 | 2022-05-16 |  |  |  | No |  |  | Not Required
23INR0467 | Lavender Storage Project | SS Completed, FIS Started, No IA | Lavender Storage Project LLC | Tap 138kV Deely (bus 5110) - Laredo (bus 5255) | Bexar | SOUTH | 2026-06-01 | OTH | BA | 231.9 |  | 2022-11-03 | 2022-02-28 | 2022-05-27 | 2022-10-21 |  |  |  | No |  |  | Not Required
23INR0468 | Petunia Storage Project | SS Completed, FIS Started, No IA | Petunia Storage Project LLC | 138kV Tap 3675 Rogers - 3485 Tin Roof Pod | Milam | SOUTH | 2025-06-30 | OTH | BA | 231.86 |  | 2022-04-14 | 2022-03-12 | 2022-06-02 | 2022-04-01 |  |  |  | No | Not Required | Not Required | Not Required
23INR0469 | Big Elm Storage | SS Completed, FIS Started, No IA | Big Elm Storage, LLC | Tap 345 kV 3414 Temple Switch - 3409 Lake Creek | Bell | NORTH | 2025-06-01 | OTH | BA | 102.8 |  | 2022-10-25 | 2022-04-18 | 2022-07-08 | 2022-10-11 |  |  |  | No |  |  | Not Required
23INR0470 | BoCo BESS | SS Completed, FIS Completed, IA | BoCo BESS | 59906 Long Draw 138kV | Borden | WEST | 2024-06-22 | OTH | BA | 155.48 |  | 2022-05-17 | 2022-05-10 | 2022-08-05 | 2022-05-03 | 2023-07-28 | No | 2022-12-09 | Yes | Not Required | Not Required | Not Required | 2023-03-09 | 2023-07-18 | 2023-07-28
23INR0471 | Ophelia Solar | SS Completed, FIS Started, No IA | Ophelia Solar | Tapping the 138 kV Line from Moss Switch (Bus# 1019) to Shin Oak POD (Bus# 11128). The project has a 110 MW PUN load at the high side of the MPT (refer to the substation SLD). | Ector | WEST | 2025-12-18 | SOL | PV | 110.5 |  | 2022-08-15 | 2022-09-02 | 2022-11-29 | 2022-08-01 |  |  |  | No |  |  | Not Required
23INR0473 | Sepanta Solar | SS Completed, FIS Started, No IA | BREG - Belgian Renewable Energy Group | 1339 ESKOTA_9 138kV (PSS/E BUS #1339, Station Name: ESKOTA_8, kV: 138 kV) Property is adjacent (West) to the Oncor Sweetwater Eskota Switch #1339. POI would simply be on the other side of the fence of the switch. | Nolan | WEST | 2026-04-20 | SOL | PV | 217.26 |  | 2022-11-17 | 2022-10-18 | 2023-01-13 | 2022-11-15 |  |  |  | No |  |  | Not Required
23INR0474 | AP Greenport | SS Completed, FIS Completed, No IA | AP Greenport | Austrop – Lost Pines 345 kV transmission line (Bus #7040 – 9041) | Travis | SOUTH | 2026-02-18 | OTH | BA | 100.45 |  | 2022-09-14 | 2022-06-10 | 2022-09-06 | 2022-06-24 | 2023-09-29 | No |  | No |  |  | Not Required
23INR0478 | XE Rhoda Storage | SS Completed, FIS Started, No IA | Milam 2 Solar LLC | Tap 138kV 32 Robertson - 64 Milano | Milam | SOUTH | 2025-02-24 | OTH | BA | 41.6 |  | 2022-03-31 | 2022-04-18 | 2022-07-15 | 2022-03-18 |  |  |  | No | Not Required | Not Required | Not Required
23INR0479 | Taormina Storage | SS Completed, FIS Started, No IA | Taormina Storage Project LLC | Tap 138kV VH Braunig (5025) to Valley Road 138kV (5465) | Bexar | SOUTH | 2026-06-01 | OTH | BA | 231.86 |  | 2022-11-08 | 2022-04-18 | 2022-07-15 | 2022-10-26 |  |  |  | No |  |  | Not Required
23INR0480 | Camellia Storage | SS Completed, FIS Started, No IA | Camellia Storage Project LLC | Tap 138 kV 8358 NORTH MERCEDES - 8327 HARLINGEN 138 kV | Hidalgo | SOUTH | 2025-06-01 | OTH | BA | 90.76 |  | 2022-07-12 | 2022-07-05 | 2022-10-01 | 2022-07-06 |  |  |  | No | Not Required | Not Required | Not Required
23INR0485 | Hacienda Storage | SS Completed, FIS Started, No IA | Galveston Energy Storage LLC | 38745 Attwater 138kV | Galveston | HOUSTON | 2026-06-09 | OTH | BA | 209.14 |  | 2022-04-20 | 2022-05-10 | 2022-08-06 | 2022-04-04 |  |  |  | No |  |  | Not Required
23INR0494 | Cartwheel BESS 1 | SS Completed, FIS Started, IA | RWE Renewables | Tap 345kV 1697 Sulphur Springs Switch – 2464 Cash Switch | Hopkins | NORTH | 2025-06-15 | OTH | BA | 156.91 |  | 2022-05-20 | 2022-06-02 | 2022-08-30 | 2022-05-10 |  |  | 2023-11-10 | Yes |  |  | Not Required
23INR0495 | Cartwheel BESS 2 | SS Completed, FIS Started, No IA | RWE Renewables | Tap 345kV 1697 Sulphur Springs Switch – 2464 Cash Switch | Hopkins | NORTH | 2025-06-15 | OTH | BA | 156.91 |  | 2022-05-20 | 2022-06-02 | 2022-08-30 | 2022-05-10 |  |  |  | No |  |  | Not Required
23INR0496 | San Perlita BESS 1 | SS Completed, FIS Started, No IA | RWE Renewables | 8601 Cebolla 345kV | Willacy | COASTAL | 2025-12-15 | OTH | BA | 150 |  | 2022-05-20 | 2022-06-02 | 2022-08-29 | 2022-05-10 |  |  |  | No |  |  | Not Required
23INR0497 | San Perlita BESS 2 | SS Completed, FIS Started, No IA | RWE Renewables | 8601 Cebolla 345kV | Willacy | COASTAL | 2025-12-15 | OTH | BA | 150 |  | 2022-05-20 | 2022-06-02 | 2022-08-29 | 2022-05-10 |  |  |  | No |  |  | Not Required
23INR0501 | Soda Lake BESS 1 | SS Completed, FIS Completed, No IA | Mendoza Trail BESS, LLC | 138kV Soda Lake Substation (#76026) | Crane | WEST | 2024-08-15 | OTH | BA | 200.78 |  | 2022-08-03 | 2022-09-02 | 2022-11-29 | 2022-08-09 | 2023-12-05 |  |  | No |  |  | Not Required
23INR0502 | Adelite Storage | SS Completed, FIS Started, No IA | Adelite Storage Project LLC | Tap 138kV Thorndale North (bus #3659) – Rookie Switch (bus #3701) | Milam | SOUTH | 2026-02-28 | OTH | BA | 231.88 |  | 2022-09-13 | 2022-06-27 | 2022-09-22 | 2022-09-09 |  |  |  | No |  |  | Not Required
23INR0503 | Ardesia Storage | SS Completed, FIS Started, No IA | Ardesia Storage Project LLC | Tap 138kV 7325 Mendoza - 7216 Lockhart | Caldwell | SOUTH | 2026-08-28 | OTH | BA | 100 |  | 2022-08-29 | 2022-06-10 | 2022-09-06 | 2022-07-22 |  |  |  | No |  |  | Not Required
23INR0506 | Beachwood II Power Station | SS Completed, FIS Completed, IA | Mark One II LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2024-08-01 | GAS | GT | 102 | COD | 2022-06-21 | 2020-12-03 | 2021-12-19 | 2022-06-20 | 2022-07-28 |  | 2022-08-01 | Yes | 2022-08-01 | Not Required | 2022-08-01 | 2022-08-24 | 2022-10-31 | 2022-10-31
23INR0524 | Temple II Repower | SS Completed, FIS Completed, IA | Panda Temple Power II | 3413 Knob Creek | Bell | NORTH | 2023-10-15 | GAS | CC | 0 |  | 2022-08-01 | 2022-08-05 | 2022-11-01 | 2022-07-22 | 2023-01-04 |  | 2012-06-21 | Yes | 2020-06-18 |  | 2023-01-26 | 2023-01-29 | 2023-01-29 | 2023-01-31
23INR0525 | Pyron Wind Repower | SS Completed, FIS Completed, No IA | RWE Renewables Development | Existing TKWSW Bus #1048 | Nolan | WEST | 2024-02-01 | WIN | WT | 19.92 |  | 2022-08-04 | 2022-08-16 | 2022-11-11 | 2022-08-04 | 2023-05-04 |  |  | Yes |  |  | Not Required | 2023-10-13 | 2023-10-13 | 2023-05-05 |  |  |  | 2023-10-12
23INR0538 | Roadrunner Crossing BESS SLF | SS Completed, FIS Started, No IA | Roadrunner Crossing BESS | 68051 Reata 354kV | Eastland | NORTH | 2025-02-28 | OTH | BA | 40 | Proj Name MW Size COD | 2022-10-23 | 2022-11-15 | 2023-02-10 | 2022-10-28 |  |  |  | No |  |  | Not Required
23INR0561 | Cascabel Wind 2 | SS Completed, FIS Started, No IA | Vaquero Wind Energy, LLC | 345 kV Rapido Substation (New ETT Substation) tapping the existing 345 kV Line from CENIZO7C (#80225) to DELSOL7C (#80307). | Zapata | SOUTH | 2025-02-28 | WIN | WT | 197.75 |  | 2023-03-08 | 2023-03-13 | 2023-06-09 | 2023-02-15 |  |  |  | No |  |  | Not Required
23INR0637 | Goodnight Wind II | SS Completed, FIS Completed, IA | FGE Goodnight I, LLC | tap 345kV 79500 Alibates - 79503 Tule Canyon CKT2 | Armstrong | PANHANDLE | 2024-12-30 | WIN | WT | 258.3 |  | 2023-04-28 | 2023-04-19 | 2023-04-19 |  | 2023-02-06 | No | 2019-08-18 | Yes | Not Required | Not Required | Not Required | 2023-05-01 | 2023-05-01 | 2023-05-01
24INR0003 | Stem Solar | SS Completed, FIS Started, No IA | Innovative Solar 134, LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala | Swisher | PANHANDLE | 2025-08-26 | SOL | PV | 200 |  | 2020-12-03 | 2020-02-04 | 2020-04-27 | 2020-10-22 |  |  |  | No |  |  | Not Required
24INR0004 | Ponil Solar | SS Completed, FIS Started, No IA | Innovative Solar 377, LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2025-07-08 | SOL | PV | 145 |  | 2020-12-03 | 2020-02-04 | 2020-04-29 | 2020-10-22 |  |  |  | No |  |  | Not Required
24INR0007 | Nockenut Springs Solar 2 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Guadalupe | SOUTH | 2025-02-28 | SOL | PV | 203.26 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No |  |  | Not Required
24INR0010 | Pinnington Solar | SS Completed, FIS Completed, IA | Hecate Energy Longhorn Solar LLC | tap both 345kV 1430 Graham - 1436 Parker 345kV lines | Jack | NORTH | 2025-10-15 | SOL | PV | 666.1 |  | 2020-11-03 | 2020-12-03 | 2021-02-17 | 2020-11-10 | 2023-10-18 |  | 2023-11-02 | Yes |  |  | Not Required | 2023-11-15
24INR0011 | Pinnington Storage | SS Completed, FIS Completed, No IA | Hecate Energy Longhorn Storage LLC | tap both 345kV 1430 Graham - 1436 Parker 345kV lines | Jack | NORTH | 2025-10-15 | OTH | BA | 508.7 |  | 2020-11-10 | 2020-12-03 | 2021-02-17 | 2020-11-10 | 2023-10-18 |  |  | No |  |  | Not Required
24INR0015 | Five Wells Solar | SS Completed, FIS Completed, IA | Five Wells Solar Center LLC | 3687 Bell Country East 345kV | Bell | NORTH | 2023-12-29 | SOL | PV | 322.82 |  | 2021-02-18 | 2021-02-04 | 2021-04-21 | 2021-01-22 | 2023-03-09 |  | 2022-09-01 | Yes | Not Required | Not Required | Not Required | 2023-03-22 | 2023-04-28 | 2023-04-28 |  |  | 2023-09-14 | 2023-10-11
24INR0020 | Percy Farm Solar | SS Completed, FIS Completed, No IA | Percy Farm Solar 1, LLC | Tap 345kV 8123 Blessing - 5915 STP | Matagorda | COASTAL | 2026-05-31 | SOL | PV | 198.63 |  | 2021-08-05 | 2021-03-16 | 2021-06-11 | 2021-07-21 | 2023-11-08 | No |  | No | Not Required | Not Required | Not Required
24INR0022 | Boxcar Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345kV 1907 Venus N - 68091 Navarro | Ellis | NORTH | 2027-04-01 | SOL | PV | 355.82 |  | 2021-03-25 | 2021-03-31 | 2021-06-17 | 2021-03-17 |  |  |  | No |  |  | Not Required
24INR0023 | Compadre Solar | SS Completed, FIS Started, IA | Hill Solar I, LLC | tap 345kV 68090 Sam Switch - 1907 Venus | Hill | NORTH | 2024-12-11 | SOL | PV | 406.14 |  | 2021-03-29 | 2021-03-16 | 2021-05-28 | 2021-03-08 |  |  | 2022-11-12 | No |  |  | Not Required
24INR0025 | Clarion Solar | SS Completed, FIS Started, No IA | IBV Energy Partners LLC | 5290 Lytle 138kV | Medina | SOUTH | 2024-08-01 | SOL | PV | 180 |  | 2021-11-15 | 2021-03-01 | 2021-05-13 | 2021-11-08 |  |  |  | No |  |  | Not Required
24INR0031 | Stoneridge Solar | SS Completed, FIS Completed, IA | Stoneridge Solar, LLC | Tap 345 kV 13429 SANDOW SWITCH - 7040 AUSTROP | Milam | SOUTH | 2024-12-15 | SOL | PV | 201.6 |  | 2022-02-14 | 2021-10-08 | 2022-01-03 | 2022-01-31 | 2023-05-18 | No | 2023-05-15 | Yes | Not Required | Not Required | Not Required
24INR0038 | SP Jaguar Solar | SS Completed, FIS Completed, IA | SP-Jaguar Solar LLC | Tap 345kV 13405 Tradinghouse SES - 68090 Sam Switch | McLennan | NORTH | 2025-06-30 | SOL | PV | 300 |  | 2021-07-23 | 2021-03-18 | 2021-06-11 | 2021-07-15 | 2022-08-30 |  | 2022-09-12 | Yes |  |  | Not Required | 2023-08-25
24INR0039 | SP Jaguar BESS | SS Completed, FIS Completed, IA | SP-Jaguar Solar LLC | Tap 345kV 13405 Tradinghouse SES - 68090 Sam Switch | McLennan | NORTH | 2025-06-30 | OTH | BA | 300 |  | 2021-08-13 | 2021-03-18 | 2021-06-11 | 2021-07-15 | 2022-08-30 |  | 2022-09-12 | Yes |  |  | Not Required | 2023-08-25
24INR0040 | Rosebud Solar | SS Completed, FIS Started, No IA | Rosebud Solar, LLC | tap 69kV 65 Silver City - 69 Barclay | Falls | NORTH | 2025-04-15 | SOL | PV | 133.76 |  | 2022-01-12 | 2021-04-13 | 2021-07-06 | 2022-01-10 |  |  |  | No |  |  | Not Required
24INR0041 | Rock N' Roll Solar SLF | SS Completed, FIS Started, No IA | Rock N Roll Solar | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2024-12-31 | SOL | PV | 151.97 |  | 2022-02-10 | 2021-05-10 | 2021-07-30 | 2022-01-20 |  | No |  | No | Not Required | Not Required | Not Required
24INR0042 | Yaupon Solar SLF | SS Completed, FIS Completed, IA | Yaupon Solar, LLC | Tap 345 kV Brangus Switch (#3705) – TNP One (#39950) | Milam | SOUTH | 2025-09-17 | SOL | PV | 204.08 | SFS/NtP | 2021-12-07 | 2021-03-30 | 2021-06-17 | 2021-11-23 | 2023-09-25 |  | 2023-09-28 | Yes |  |  | Not Required
24INR0056 | Pradera Solar | SS Completed, FIS Started, No IA | Pradera Solar, LLC | tap 345 kV Lobo (80219) - Fowlerton (5709) | Webb | SOUTH | 2024-10-31 | SOL | PV | 118 |  | 2021-06-02 | 2021-07-08 | 2021-09-28 | 2021-06-23 |  |  |  | No |  |  | Not Required
24INR0057 | Hanson Storage | SS Completed, FIS Started, IA | Hanson Solar, LLC | tap 345kV 1444 Brown - 11406 Central Bluff | Coleman | WEST | 2025-10-21 | OTH | BA | 101.39 |  | 2021-08-23 | 2021-06-21 | 2021-09-08 | 2021-08-19 |  |  | 2023-09-20 | No |  |  | Not Required
24INR0058 | Briggs Storage | SS Completed, FIS Started, No IA | Briggs Solar, LLC | tap 345kV 60515 Clear Crossing - 60507 Pendulo | Haskell | WEST | 2024-12-31 | OTH | BA | 70.39 |  | 2022-03-18 | 2021-05-31 | 2021-08-18 | 2022-03-04 |  |  |  | No |  |  | Not Required
24INR0059 | Cuchillas Solar | SS Completed, FIS Started, IA | Gransolar Texas Two, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2026-05-01 | SOL | PV | 305.6 |  | 2022-02-24 | 2021-06-02 | 2021-08-18 | 2022-02-11 |  | No | 2023-06-20 | Yes |  |  | Not Required
24INR0061 | Eighteenmile Solar SLF | SS Completed, FIS Started, No IA | Weser Solar, LLC | Tap 138kV 5730 Four Corners - 5728 Choate | Goliad | SOUTH | 2025-09-02 | SOL | PV | 153.06 |  | 2021-09-02 | 2021-08-18 | 2021-11-05 | 2021-08-24 |  |  |  | No |  |  | Not Required
24INR0062 | Eighteenmile Storage SLF | SS Completed, FIS Started, No IA | Weser Solar, LLC | Tap 5730 Four Corners to 5728 Choate 138 kV | Goliad | SOUTH | 2025-09-02 | OTH | BA | 0 |  | 2022-01-12 | 2021-12-29 | 2022-02-08 | 2022-01-07 |  |  |  | No |  |  | Not Required
24INR0065 | Keys Hollow Solar Phase II SLF | SS Completed, FIS Started, No IA | Keys Hollow Solar, LLC | 345kV Tap 8164 Coleto Creek - 8673 RAPTOR7A | Goliad | SOUTH | 2027-07-01 | SOL | PV | 204.08 |  | 2021-08-25 | 2021-06-17 | 2021-09-01 | 2021-07-29 |  | No |  | No | Not Required | Not Required | Not Required
24INR0066 | Keys Hollow Storage Phase II SLF | SS Completed, FIS Started, No IA | Keys Hollow Solar, LLC | 345kV Tap 8164 Coleto Creek - 8673 RAPTOR7A | Goliad | SOUTH | 2027-07-01 | OTH | BA | 0 |  | 2022-01-20 | 2021-06-17 | 2021-09-01 | 2022-01-10 |  | No |  | No | Not Required | Not Required | Not Required
24INR0067 | KEYS HOLLOW SOLAR SLF | SS Completed, FIS Started, No IA | Keys Hollow Solar, LLC | TAP 345 KV LINE FROM COLETO 8164 - RAPTOR7A 8673 | Goliad | SOUTH | 2027-07-01 | SOL | PV | 204.08 |  | 2022-03-10 | 2021-06-17 | 2021-09-01 | 2022-03-04 |  | No |  | No |  |  | Not Required
24INR0068 | KEYS HOLLOW STORAGE SLF | SS Completed, FIS Started, No IA | Keys Hollow Solar, LLC | TAP 345 KV LINE FROM COLETO 8164 - RAPTOR7A 8673 | Goliad | SOUTH | 2027-07-01 | OTH | BA | 0 |  | 2022-03-10 | 2021-06-17 | 2021-09-01 | 2022-03-04 |  | No |  | No |  |  | Not Required
24INR0069 | Triple B Solar Alt#2 | SS Completed, FIS Started, No IA | Triple B Solar LLC | Tap 138kV 7066 Adamsville - 7064 Lampasas | Lampasas | NORTH | 2024-09-01 | SOL | PV | 150 |  | 2021-12-15 | 2021-06-10 | 2021-09-01 | 2021-11-15 |  |  |  | No |  |  | Not Required
24INR0070 | Sypert Branch Solar Project | SS Completed, FIS Completed, IA | Sypert Branch Solar LLC | Tap 345kV 13429 Sandow Switch - 3687 Bell County East Switch Ckt 2 | Milam | SOUTH | 2025-06-01 | SOL | PV | 261.78 |  | 2022-05-10 | 2021-09-21 | 2021-12-06 | 2022-04-28 | 2023-10-09 | No | 2023-10-12 | Yes | Not Required | Not Required | Not Required | 2023-10-18
24INR0073 | Hyacinth Storage | SS Completed, FIS Started, No IA | Hyacinth Storage, LLC | 46500 Tomball 345 kV | Harris | HOUSTON | 2023-12-01 | OTH | BA | 103.05 |  | 2022-04-02 | 2021-07-02 | 2021-09-22 | 2022-03-21 |  |  |  | No |  |  | Not Required
24INR0074 | Cabeza de Vaca | SS Completed, FIS Started, No IA | PREMIER ENGINEERING USA CORP | 1788 Brookston 69kV | Lamar | NORTH | 2026-02-20 | SOL | PV | 37.8 | COD | 2022-11-02 | 2021-12-03 | 2022-02-28 | 2022-09-13 |  |  |  | No |  |  | Not Required
24INR0075 | Blue Bird Solar | SS Completed, FIS Completed, No IA | Gigawatt Solar LLC | tap 345kV 1880 Rocky Creek - 1898 Mitchell Bend Switch | Johnson | NORTH | 2025-06-01 | SOL | PV | 1004 |  | 2021-11-10 | 2021-11-10 | 2022-02-07 | 2021-07-30 | 2023-05-18 | No |  | No |  |  | Not Required
24INR0077 | Quarter Ranch Solar | SS Completed, FIS Started, No IA | Gransolar Texas Three LLC | 80223 Cenizo Substation 345kV | Zapata | SOUTH | 2026-09-30 | SOL | PV | 154.12 |  | 2022-03-28 | 2021-07-13 | 2021-09-28 | 2022-03-23 |  | No |  | No |  |  | Not Required
24INR0078 | Apogee Wind II | SS Completed, FIS Started, No IA | King Creek Wind Farm 3, LLC | 60791 Perigee Substation 345kV | Throckmorton | WEST | 2024-12-31 | WIN | WT | 47.25 | COD | 2021-12-29 | 2021-07-13 | 2021-09-20 | 2021-12-14 |  |  |  | No |  |  | Not Required
24INR0079 | Boxcar Solar 2 | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345 kV 1907 Venus N - 68091 Navarro | Ellis | NORTH | 2026-04-01 | SOL | PV | 251.3 |  | 2022-06-07 | 2021-07-13 | 2021-09-28 | 2022-05-23 |  |  |  | No |  |  | Not Required
24INR0081 | SANJAC BESS | SS Completed, FIS Started, No IA | Castleman Power | 40270 Riverside 138kV | Harris | HOUSTON | 2024-12-01 | OTH | BA | 202.37 |  | 2021-07-08 | 2021-07-08 | 2021-09-28 | 2021-07-08 |  |  |  | No |  |  | Not Required
24INR0086 | Pisgah Ridge Solar 2 | SS Completed, FIS Completed, No IA | Pisgah Ridge Solar 2, LLC | Tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2026-12-31 | SOL | PV | 101.89 |  | 2021-09-07 | 2021-07-14 | 2021-10-07 | 2021-08-25 | 2023-09-01 | No |  | No | Not Required | Not Required | Not Required
24INR0087 | Pisgah Ridge Storage 3 | SS Completed, FIS Completed, No IA | Pisgah Ridge 3, LLC | Tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2026-12-31 | OTH | BA | 101.36 |  | 2021-09-07 | 2021-07-14 | 2021-10-07 | 2021-08-25 | 2023-09-01 | No |  | No | Not Required | Not Required | Not Required
24INR0088 | Tres Margaritas Solar | SS Completed, FIS Started, No IA | Gransolar Texas Six, LLC | Tap 138kV 8613 Big Wells – 8212 Dilley Switching Station | Dimmit | SOUTH | 2025-03-03 | SOL | PV | 60.95 |  | 2022-03-08 | 2021-07-13 | 2021-10-08 | 2022-02-21 |  | No |  | No |  |  | Not Required
24INR0091 | BRP Springbok Solar | SS Completed, FIS Completed, No IA | Antelope Solar LLC | 23920 Blackwater Draw Switching Station 345kV | Hale | PANHANDLE | 2024-12-15 | SOL | PV | 202.39 |  | 2021-08-25 | 2021-08-25 | 2021-11-17 | 2021-08-02 | 2022-11-01 | No |  | No | Not Required | Not Required | Not Required
24INR0093 | Oriana Solar | SS Completed, FIS Started, IA | Oriana Solar LLC | Tap 138kV 5502 Rayburn - 5584 Vanderbilt | Victoria | SOUTH | 2025-04-06 | SOL | PV | 181 | MW Size COD | 2021-08-25 | 2021-08-25 | 2021-11-17 | 2021-08-13 |  |  | 2023-02-27 | No | Not Required | Not Required | Not Required
24INR0094 | Dovetail Solar 1 | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Solar Holdings LLC | Tap 345 KV 1421 Willow Creek - 60515 Clear Crossing Ckt 2 | Jack | NORTH | 2026-09-14 | SOL | PV | 666.1 |  | 2022-06-23 | 2021-09-21 | 2021-12-09 | 2022-06-06 |  |  |  | No | Not Required | Not Required | Not Required
24INR0095 | Dovetail Solar 2 | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Solar Holdings LLC | Tap 345 KV 1421 Willow Creek - 60515 Clear Crossing | Jack | NORTH | 2027-12-31 | SOL | PV | 666.1 |  | 2022-07-29 | 2021-10-26 | 2022-01-21 | 2022-07-15 |  |  |  | No |  |  | Not Required
24INR0096 | BRP Volga BESS | SS Completed, FIS Started, No IA | BRP Volga BESS LLC | 138 kV Seagoville Switch Substation (#2434; ONCOR) | Dallas | NORTH | 2024-12-01 | OTH | BA | 174.63 |  | 2021-12-13 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  | No |  | No | Not Required | Not Required | Not Required
24INR0097 | Dovetail Solar 3 | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Solar Holdings LLC | Tap 345kV 1421 Willow Creek – 11523 THOMPRIC | Jack | NORTH | 2028-12-29 | SOL | PV | 666.1 |  | 2022-08-29 | 2021-12-13 | 2022-02-08 | 2022-08-06 |  |  |  | No |  |  | Not Required
24INR0098 | Dovetail Storage | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Storage LLC | Tap 345 KV 1421 Willow Creek-60515 Clear Crossing CKT#2 | Jack | NORTH | 2026-09-14 | OTH | BA | 508.7 |  | 2022-06-20 | 2021-09-28 | 2021-12-03 | 2022-05-31 |  |  |  | No |  |  | Not Required
24INR0099 | Two Rivers Solar | SS Completed, FIS Started, No IA | Two Rivers Solar, LLC | Tap 138kV 64 Milano – 32 Robertson | Milam | SOUTH | 2025-03-14 | SOL | PV | 219.35 |  | 2021-07-27 | 2021-07-27 | 2021-10-21 | 2021-07-22 |  | No |  | No | Not Required | Not Required | Not Required
24INR0100 | Sheep Creek Storage | SS Completed, FIS Completed, IA | Longhorn Storage LLC | 68051 Reata 345kV | Callahan | WEST | 2024-07-01 | OTH | BA | 142.1 | MW Size | 2022-06-02 | 2021-07-26 | 2021-10-22 | 2022-05-16 | 2023-11-01 |  | 2023-12-21 | Yes | Not Required | Not Required | Not Required | 2023-11-01 | 2023-11-01 | 2023-11-01
24INR0101 | Lampe Solar | SS Completed, FIS Completed, No IA | Gransolar Texas Seven LLC | Tap 138 kV 7572 Gay Hill - 7573 Lyons | Washington | SOUTH | 2025-09-01 | SOL | PV | 60.24 |  | 2022-04-27 | 2021-08-03 | 2021-10-18 | 2022-04-14 | 2023-08-01 | No |  | No |  |  | Not Required
24INR0102 | Seguro Grid | SS Completed, FIS Started, No IA | Val Vista Grid, LLC | Tap 345kV 8383 North Edinburg - 80137 Stewart Road | Hidalgo | SOUTH | 2028-06-01 | OTH | BA | 201.33 |  | 2021-09-30 | 2021-10-01 | 2021-12-09 | 2021-10-01 |  |  |  | No | Not Required | Not Required | Not Required
24INR0103 | Opuntia Solar SLF | SS Completed, FIS Started, No IA | Opuntia Solar, LLC | tap 138kV 5607 Warburton - 8912 Medio Creek | Refugio | COASTAL | 2026-09-08 | SOL | PV | 102.04 |  | 2021-08-24 | 2021-08-24 | 2021-11-16 | 2021-08-09 |  |  |  | No | Not Required | Not Required | Not Required
24INR0104 | Braswell Solar | SS Completed, FIS Completed, No IA | Gransolar Texas Nine, LLC | Tap 69kV 147 Lorena - 3580 Eddy Substation (Will be converted to 138kV line before 3/14/25 per TSP) | McLennan | NORTH | 2025-09-16 | SOL | PV | 44.22 |  | 2022-04-20 | 2021-08-30 | 2021-11-18 | 2022-04-08 | 2023-10-16 | No |  | No | Not Required | Not Required | Not Required
24INR0106 | Payne Battlecreek | SS Completed, FIS Completed, No IA | Gransolar Texas Ten, LLC | tap 138kV 213 Haney - 3515 Hubbard | Hill | NORTH | 2026-05-15 | SOL | PV | 84.99 |  | 2022-03-23 | 2021-08-12 | 2021-10-29 | 2022-03-10 | 2023-04-17 | No |  | No | Not Required | Not Required | Not Required
24INR0108 | Louisa Energy Storage | SS Completed, FIS Completed, No IA | Viridity Energy Solutions Inc. | 138 kV Helotes (#5200) | Bexar | SOUTH | 2026-05-01 | OTH | BA | 102.77 | COD | 2021-11-16 | 2021-11-16 | 2022-01-17 | 2021-11-08 | 2023-07-10 | No |  | No | Not Required | Not Required | Not Required
24INR0109 | Oriana BESS | SS Completed, FIS Started, IA | Oriana Solar LLC | Tap 138kV 5502 Rayburn - 5584 Vanderbilt | Victoria | SOUTH | 2025-07-02 | OTH | BA | 60.3 |  | 2022-02-24 | 2021-08-25 | 2021-11-17 | 2022-02-14 |  |  | 2023-02-27 | Yes | Not Required | Not Required | Not Required | 2023-08-25
24INR0110 | Kildare | SS Completed, FIS Completed, No IA | Galsol, LLC | 5524 Cordele 69 Sub 69 kV | Jackson | SOUTH | 2025-09-30 | SOL | PV | 70 |  | 2022-01-19 | 2022-01-28 | 2022-04-26 | 2022-01-18 | 2023-12-06 |  |  | No |  |  | Not Required
24INR0111 | BRP Triton BESS | SS Completed, FIS Started, No IA | BRP Triton BESS LLC | 138 kV Comanche Switch Substation (#1441) | Comanche | NORTH | 2024-11-01 | OTH | BA | 205.36 |  | 2021-10-18 | 2021-10-18 | 2022-01-12 | 2021-10-08 |  |  |  | No | Not Required | Not Required | Not Required
24INR0115 | Aster Solar | SS Completed, FIS Started, No IA | Aster Solar | 7042 Zorn 345kV | Guadalupe | SOUTH | 2024-12-29 | SOL | PV | 203.52 |  | 2022-06-16 | 2021-09-21 | 2021-12-09 | 2022-05-24 |  |  |  | No |  |  | Not Required
24INR0116 | Hart Wind 2 | SS Completed, FIS Completed, IA | Hart Wind, LLC | Tap 345kV 23912 OGALLALA - 23920 BLACKWATER DRAW SWITCH | Castro | PANHANDLE | 2025-09-01 | WIN | WT | 166.38 |  | 2022-05-20 | 2021-10-21 | 2022-01-17 | 2022-05-06 | 2023-11-13 |  | 2023-10-06 | No |  |  | Not Required
24INR0117 | Utley Solar Project | SS Completed, FIS Started, No IA | Palmera Solar Development LLC | Tap 345kV 3381 Big Brown Switch - 3391 Jewett | Freestone | NORTH | 2025-04-15 | SOL | PV | 221.27 |  | 2022-03-23 | 2021-09-07 | 2021-11-29 | 2022-03-09 |  |  |  | No |  |  | Not Required
24INR0118 | Possum Kingdom Solar | SS Completed, FIS Started, No IA | Novis Renewables | Tap 345kV 1421 Willow Creek Switch – 11523 Thomas Price | Jack | NORTH | 2026-10-30 | SOL | PV | 261.36 |  | 2022-06-02 | 2021-09-13 | 2021-11-29 | 2022-05-23 |  |  |  | No | Not Required | Not Required | Not Required |  |  |  | 2025-05-01 | 2026-05-08
24INR0120 | Eytcheson Ranches Solar | SS Completed, FIS Started, No IA | Gransolar Texas Fourteen, LLC | Tap 69kV 186 Navarro Mills – 107 Prairie Hill | Navarro | NORTH | 2028-01-01 | SOL | PV | 76.42 |  | 2022-05-31 | 2021-09-14 | 2021-11-29 | 2022-05-26 |  |  |  | No |  |  | Not Required
24INR0121 | PHOTO BESS 1 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2024-12-31 | OTH | BA | 75 |  | 2022-05-31 | 2021-10-29 | 2021-12-08 | 2022-05-13 |  |  |  | No |  |  | Not Required
24INR0122 | PHOTO BESS 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2024-05-31 | OTH | BA | 150 |  | 2022-05-31 | 2021-10-29 | 2021-12-08 | 2022-05-13 |  |  |  | No |  |  | Not Required
24INR0124 | High Noon Solar | SS Completed, FIS Started, No IA | High Noon Solar Project, LLC | Tap 138kV 445 Yates - 444 Covington | Hill | NORTH | 2026-04-01 | SOL | PV | 182 |  | 2021-11-02 | 2021-11-03 | 2021-12-29 | 2021-11-02 |  |  |  | No |  |  | Not Required
24INR0125 | Grasshopper Solar | SS Completed, FIS Started, No IA | Grasshopper Solar LLC | Smoky Hill 345kV Sub (Bus #6104) Locational coordinates : 33.34414; 99.624637 | Haskell | WEST | 2025-03-15 | SOL | PV | 407.68 |  | 2021-09-28 | 2021-09-28 | 2021-12-09 | 2021-09-22 |  |  |  | No |  |  | Not Required
24INR0126 | High Noon Storage | SS Completed, FIS Started, No IA | High Noon Solar Project, LLC | Tap 138kV 445 Yates - 444 Covington | Hill | NORTH | 2026-04-01 | OTH | BA | 94 |  | 2021-11-02 | 2021-11-03 | 2021-12-29 | 2021-11-02 |  |  |  | No |  |  | Not Required
24INR0127 | Naduah Solar | SS Completed, FIS Completed, No IA | Gransolar Texas Fifteen, LLC | Tap 69kV Ben Hur (99) - Prairie Hill (107) | Limestone | NORTH | 2026-06-15 | SOL | PV | 103.35 |  | 2022-06-17 | 2021-09-27 | 2021-12-09 | 2022-06-06 | 2023-11-01 | No |  | No |  |  | Not Required
24INR0128 | BRP Desna BESS | SS Completed, FIS Completed, IA | BRP Desna BESS LLC | 39703 TNP FM524 138kV | Brazoria | COASTAL | 2024-12-01 | OTH | BA | 205.44 |  | 2021-12-05 | 2021-12-15 | 2022-03-11 | 2021-11-29 | 2023-06-11 |  | 2023-09-15 | Yes |  |  | Not Required
24INR0130 | BRP Artemis BESS | SS Completed, FIS Started, No IA | BRP Artemis BESS LLC | 40600 Roans Prairie Substation 345kV | Grimes | NORTH | 2025-06-01 | OTH | BA | 414.07 |  | 2021-12-15 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No |  |  | Not Required
24INR0131 | BRP Zelus BESS | SS Completed, FIS Started, No IA | BRP Zelus BESS LLC | the 138 kV Zapata Substation (#8299; AEP) | Zapata | SOUTH | 2024-12-01 | OTH | BA | 206.96 |  | 2021-12-15 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No |  |  | Not Required
24INR0132 | Bowhead Solar | SS Completed, FIS Started, No IA | Baffin Bay Solar, LLC | Tap 138kV 8519 Kleberg – 8518 Kingsville | Kleberg | COASTAL | 2026-01-15 | SOL | PV | 165 |  | 2022-08-30 | 2021-11-16 | 2022-02-12 | 2022-08-09 |  |  |  | No |  |  | Not Required
24INR0133 | BRP Hestia BESS | SS Completed, FIS Started, No IA | BRP Hestia BESS LLC | the 69 kV Rock Springs Substation (#78238, LCRA) | Edwards | SOUTH | 2025-06-01 | OTH | BA | 29.05 |  | 2021-12-28 | 2021-12-29 | 2022-03-25 | 2021-12-28 |  |  |  | No |  |  | Not Required
24INR0134 | BRP Hemera BESS | SS Completed, FIS Completed, No IA | BRP Hemera BESS LLC | 345 kV Deaf Smith Substation (#23908, Oncor) | Deaf Smith | PANHANDLE | 2025-12-01 | OTH | BA | 206.96 |  | 2021-12-20 | 2021-12-29 | 2022-03-25 | 2021-12-14 | 2023-04-06 |  |  | No |  |  | Not Required
24INR0135 | BRP Mekong BESS | SS Completed, FIS Started, No IA | BRP Mekong BESS LLC | Tap 345 kV line from Twin Oak Switch (#3400) to TPN One Plant Switchyard (#39950) | Robertson | NORTH | 2024-12-01 | OTH | BA | 413.74 |  | 2021-12-15 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No |  |  | Not Required
24INR0136 | Eagle Springs Storage | SS Completed, FIS Started, No IA | Eagle Springs Solar, LLC | Tap Lake Creek Substation (#6835) – Enloe Switching station (#6834) 138 kV Line | Delta | NORTH | 2024-12-31 | OTH | BA | 55.1 |  | 2022-06-20 | 2021-10-18 | 2022-01-12 | 2022-06-13 |  | No |  | No |  |  | Not Required
24INR0137 | Eagle Springs Solar | SS Completed, FIS Started, No IA | Eagle Springs Solar, LLC | Tap Lake Creek Substation (#6835) – Enloe Switching station (#6834) 138 kV Line | Delta | NORTH | 2024-12-31 | SOL | PV | 110.1 |  | 2022-06-20 | 2021-10-18 | 2022-01-12 | 2022-06-13 |  | No |  | No |  |  | Not Required
24INR0138 | Midpoint Storage | SS Completed, FIS Completed, IA | Midpoint Solar, LLC | 138 KV Tap #3518 BLUM to #237 Blanton | Hill | NORTH | 2025-08-30 | OTH | BA | 52.24 |  | 2022-05-24 | 2021-10-15 | 2022-01-04 | 2022-05-11 | 2023-05-10 | No | 2023-10-31 | Yes | Not Required | Not Required | Not Required | 2023-11-13
24INR0139 | Midpoint Solar | SS Completed, FIS Completed, IA | Midpoint Solar, LLC | 138 KV Tap #3518 BLUM to #237 Blanton | Hill | NORTH | 2025-08-30 | SOL | PV | 103.8 |  | 2022-05-18 | 2021-10-15 | 2022-01-04 | 2022-05-04 | 2023-05-10 | No | 2023-10-31 | Yes | Not Required | Not Required | Not Required | 2023-11-13
24INR0140 | Gaia Storage | SS Completed, FIS Started, IA | Gaia Solar, LLC | Tap 138kV 3127 Trinidad SES - 3454 Montfort Switch | Navarro | NORTH | 2025-07-31 | OTH | BA | 76.83 |  | 2022-05-23 | 2021-12-29 | 2022-03-23 | 2022-05-11 |  | No | 2023-11-08 | Yes | Not Required | Not Required | Not Required | 2023-11-15
24INR0141 | Gaia Solar | SS Completed, FIS Started, IA | Gaia Solar, LLC | Tap 138kV 3127 Trinidad SES - 3454 Montfort Switch | Navarro | NORTH | 2025-07-31 | SOL | PV | 152.65 |  | 2022-05-23 | 2021-12-29 | 2022-03-23 | 2022-05-11 |  | No | 2023-11-08 | Yes | Not Required | Not Required | Not Required | 2023-11-15
24INR0142 | BRP De Los Santos BESS | SS Completed, FIS Started, No IA | BRP De Los Santos BESS LLC | 78015 Rosita Creek Substation 138kV | Maverick | SOUTH | 2024-12-01 | OTH | BA | 206.87 |  | 2022-02-09 | 2022-05-10 | 2022-08-05 | 2022-04-18 |  |  |  | No | Not Required | Not Required | Not Required
24INR0145 | Calpine Guadalupe Peakers | SS Completed, FIS Started, No IA | Guadalupe Peaking Energy Center, LLC | 7044 Marion 345kV | Guadalupe | SOUTH | 2027-05-23 | GAS | GT | 450 |  | 2021-10-26 | 2021-11-15 | 2022-02-11 | 2021-10-18 |  |  |  | No
24INR0147 | Citadel BESS | SS Completed, FIS Completed, IA | Citadel BESS LLC | 40390 Crosby 138kV | Harris | HOUSTON | 2024-09-21 | OTH | BA | 209.32 | COD | 2021-11-15 | 2021-11-15 | 2022-02-11 | 2021-11-11 | 2023-10-24 | No | 2022-07-29 | Yes | Not Required | Not Required | Not Required | 2023-01-19 | 2023-10-24 | 2023-10-31
24INR0150 | Lupinus Solar 1 | SS Completed, FIS Started, No IA | Lupinus Solar, LLC | Tap 345 kV 11699 Woodard Switch - 1695 Monticello SES | Franklin | NORTH | 2026-09-21 | SOL | PV | 164.86 |  | 2022-05-23 | 2021-12-08 | 2022-03-04 | 2022-05-11 |  |  |  | No |  |  | Not Required
24INR0153 | Lupinus Storage 1 | SS Completed, FIS Started, No IA | Lupinus Solar, LLC | Tap 345 kV 11699 Woodard Switch - 1695 Monticello SES | Franklin | NORTH | 2026-09-21 | OTH | BA | 82.97 |  | 2022-05-23 | 2021-12-13 | 2022-03-10 | 2022-05-11 |  |  |  | No |  |  | Not Required
24INR0154 | Lupinus Solar 2 | SS Completed, FIS Started, No IA | Lupinus Solar 2, LLC | 1794 Monticello Tap Substation 138 kV | Franklin | NORTH | 2026-09-21 | SOL | PV | 244.24 |  | 2022-05-23 | 2021-12-13 | 2022-03-10 | 2022-05-11 |  |  |  | No | Not Required | Not Required | Not Required
24INR0155 | Lupinus Storage 2 | SS Completed, FIS Started, No IA | Lupinus Solar 2, LLC | 1794 Monticello Tap Substation 138 kV | Franklin | NORTH | 2026-09-21 | OTH | BA | 122.92 |  | 2022-06-03 | 2021-12-13 | 2022-03-10 | 2022-05-11 |  |  |  | No |  |  | Not Required
24INR0156 | Moonstone Solar Project | SS Completed, FIS Started, No IA | Ignis TX Solar One LLC | Tap 138kV Eagle Creek (5132) to Floresville (5155) | Wilson | SOUTH | 2026-03-31 | SOL | PV | 145.81 |  | 2022-06-20 | 2021-10-27 | 2022-01-24 | 2022-06-07 |  |  |  | No |  |  | Not Required
24INR0157 | BRP Merope BESS | SS Completed, FIS Started, No IA | BRP Merope BESS LLC | 345 kV Corn Trail Switch Substation (#11441) | Comanche | NORTH | 2025-12-31 | OTH | BA | 413.74 |  | 2021-12-13 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No |  |  | Not Required
24INR0160 | Huisache Solar | SS Completed, FIS Started, No IA | Novis Renewables | Tap 345kV 5133 Elm Creek - 5915 Southern Texas Project Ckt 1 | Wilson | SOUTH | 2026-02-15 | SOL | PV | 125.59 |  | 2022-07-11 | 2021-12-03 | 2022-03-01 | 2022-06-22 |  |  |  | No | Not Required | Not Required | Not Required
24INR0161 | Miranda Solar Project | SS Completed, FIS Started, No IA | Cactus Solar Development LLC | Tap 345kV 5709 Fowlerton - 5901 San Miguel Ckt 1 | McMullen | SOUTH | 2024-12-01 | SOL | PV | 261.42 |  | 2022-06-27 | 2021-11-03 | 2022-01-07 | 2022-06-22 |  |  |  | No |  |  | Not Required
24INR0162 | Chiltepin Storage | SS Completed, FIS Started, No IA | Chiltepin Solar-Storage, LLC | 6673 Musquiz 138kV | Reeves | WEST | 2024-12-01 | OTH | BA | 100 |  | 2021-11-09 | 2022-01-13 | 2022-04-11 | 2021-12-16 |  |  |  | No |  |  | Not Required
24INR0166 | Stillhouse Solar | SS Completed, FIS Started, IA | Stillhouse Solar LLC | tap 345kV Bell County East Switch (3687) – Hog Creek Switch (3704) | Bell | NORTH | 2025-06-01 | SOL | PV | 212.51 |  | 2021-11-17 | 2021-11-24 | 2022-02-19 | 2021-11-23 |  | No | 2023-06-07 | No | Not Required | Not Required | Not Required
24INR0167 | OCI SunRoper | SS Completed, FIS Started, No IA | OCI SunRoper LLC | tap138kV #43190 South Lane City to #42985 Dyann CKT#60 | Wharton | SOUTH | 2026-07-01 | SOL | PV | 265.1 |  | 2021-11-18 | 2021-11-24 | 2022-02-19 | 2021-11-23 |  |  |  | No |  |  | Not Required
24INR0168 | Tejano Storage | SS Completed, FIS Started, No IA | Tejano Storage, LLC | Tap 138kV 8125 Lolita - 8172 Victoria | Victoria | SOUTH | 2025-06-01 | OTH | BA | 152 |  | 2022-05-06 | 2022-03-30 | 2022-06-26 | 2022-04-18 |  | No |  | No |  |  | Not Required
24INR0169 | Yaupon Storage SLF | SS Completed, FIS Completed, IA | Yaupon Solar, LLC | Tap 345 kV Brangus Switch (#3705) – TNP One (#39950) | Milam | SOUTH | 2025-09-17 | OTH | BA | 0 |  | 2022-01-12 | 2021-11-10 | 2022-02-08 | 2022-01-10 | 2023-09-25 |  | 2023-09-28 | No |  |  | Not Required
24INR0171 | Hollow Branch Creek Solar SLF | SS Completed, FIS Completed, No IA | Hollow Branch Creek Solar LLC | Jewett – Singleton 345 kV [PTI Bus # 3390 – 44645] | Leon | NORTH | 2025-12-31 | SOL | PV | 712 |  | 2021-11-09 | 2021-12-13 | 2022-02-04 | 2021-12-07 | 2023-03-28 | Yes |  | No |  |  | Not Required
24INR0172 | Smith Lake Solar | SS Completed, FIS Started, No IA | Smith Lake Solar | TAP 345 KV 44645 SINGLETON - 44900 ZENITH Ckt #99 | Grimes | NORTH | 2026-11-30 | SOL | PV | 402 |  | 2022-11-30 | 2022-02-07 | 2022-05-06 | 2022-11-02 |  |  |  | No |  |  | Not Required
24INR0174 | Solar Star North Herty Storage | SS Completed, FIS Started, No IA | Solar Star North Herty Storage, LLC | 3319 Redland Switch 138 kV | Angelina | NORTH | 2026-04-20 | OTH | BA | 125.4 |  | 2022-09-09 | 2022-02-21 | 2022-05-21 | 2022-08-15 |  |  |  | No |  |  | Not Required
24INR0177 | Mitchell Plant Road Solar | SS Completed, FIS Started, No IA | DHI Power, LLC | 138 kV 38430 White Baker TNP | Pecos | WEST | 2025-07-01 | SOL | PV | 201.5 |  | 2022-01-31 | 2022-02-21 | 2022-05-21 | 2022-01-28 |  | No |  | No | Not Required | Not Required | Not Required
24INR0178 | Cumulus Grid BESS | SS Completed, FIS Started, No IA | Cumulus Grid, LLC | 1906 Venus Switch Substation 345kV | Ellis | NORTH | 2027-06-01 | OTH | BA | 210.74 |  | 2022-11-01 | 2022-03-14 | 2022-04-18 | 2022-10-18 |  |  |  | No |  |  | Not Required
24INR0179 | Bowhead Storage | SS Completed, FIS Started, No IA | Baffin Bay Solar, LLC | Tap 138kV 8519 Kleberg – 8518 Kingsville | Kleberg | COASTAL | 2026-01-15 | OTH | BA | 40 |  | 2022-09-13 | 2021-12-03 | 2022-02-28 | 2022-08-26 |  |  |  | No |  |  | Not Required
24INR0180 | Frio Farm | SS Completed, FIS Started, No IA | PREMIER ENGINEERING USA CORP. | 8221 BIG FOOT4A 138kV | Frio | SOUTH | 2026-06-25 | SOL | PV | 106.5 | COD | 2022-10-03 | 2021-12-20 | 2022-03-10 | 2022-09-13 |  |  |  | No |  |  | Not Required
24INR0181 | Bynum Solar Project | SS Completed, FIS Completed, No IA | Bynum Solar Project, LLC | Tap 69kV 37470 Olsen - 37520 Sycamore | Coryell | NORTH | 2025-12-15 | SOL | PV | 65.4 | Status Change INA-to-PLN | 2022-06-02 | 2021-12-18 | 2022-03-11 | 2022-05-23 | 2023-08-03 |  |  | No |  |  | Not Required
24INR0182 | DeSpain Solar Project | SS Completed, FIS Started, No IA | Gransolar Texas Thirteen LLC | 7425 Odlaw Switch 138kV | Kinney | SOUTH | 2026-07-01 | SOL | PV | 236.17 |  | 2022-06-22 | 2021-12-05 | 2022-03-02 | 2022-06-16 |  |  |  | No |  |  | Not Required
24INR0183 | Altamira Solar | SS Completed, FIS Started, No IA | J&R Power DevCo, LLC | 8985 San Ygnacio 138 kV Substation | Zapata | SOUTH | 2025-09-29 | SOL | PV | 150.66 |  | 2022-10-25 | 2022-01-20 | 2022-04-18 | 2022-10-07 |  |  |  | No |  |  | Not Required
24INR0184 | Slate Solar Project | SS Completed, FIS Started, No IA | Ignis TX Solar Three LLC | Tap 138kV 8646 Rio Bravo - 8985 San Ygancio | Zapata | SOUTH | 2025-09-30 | SOL | PV | 104.89 |  | 2022-08-03 | 2021-12-20 | 2022-03-10 | 2022-07-13 |  | No |  | No |  |  | Not Required
24INR0185 | BRP Kotys BESS | SS Completed, FIS Started, No IA | BRP Kotys BESS LLC | 138 kV Argyle Substation (#1984) | Denton | NORTH | 2024-11-01 | OTH | BA | 163.41 |  | 2022-02-11 | 2022-02-28 | 2022-05-27 | 2022-02-24 |  |  |  | No | Not Required | Not Required | Not Required
24INR0186 | Rowdy Creek Solar SLF | SS Completed, FIS Started, No IA | Rowdy Creek Solar LLC | Tap 345kV 1692 Paris Switch – 1690 Valley SES | Lamar | NORTH | 2026-03-10 | SOL | PV | 702.03 | COD | 2021-12-13 | 2022-01-28 | 2022-04-27 | 2022-01-25 |  |  |  | No |  |  | Not Required
24INR0187 | Rowdy Creek BESS SLF | SS Completed, FIS Started, No IA | Rowdy Creek Solar LLC | Tap 345kV 1692 Paris Switch – 1690 Valley SES | Lamar | NORTH | 2026-03-10 | OTH | BA | 0 | COD | 2021-12-13 | 2022-01-28 | 2022-04-27 | 2022-01-25 |  |  |  | No |  |  | Not Required
24INR0188 | Tehuacana Creek Solar SLF | SS Completed, FIS Started, No IA | Tehuacana Creek Solar LLC | Tap 345kV 3381 Big Brown – 68091 Navarro | Navarro | NORTH | 2026-03-10 | SOL | PV | 838.5 |  | 2021-12-15 | 2021-12-20 | 2022-03-10 | 2021-12-09 |  |  |  | No |  |  | Not Required
24INR0189 | Tehuacana Creek BESS SLF | SS Completed, FIS Started, No IA | Tehuacana Creek Solar LLC | Tap 345kV 3381 Big Brown – 68091 Navarro | Navarro | NORTH | 2026-03-10 | OTH | BA | 0 |  | 2021-12-15 | 2021-12-20 | 2022-03-10 | 2021-12-09 |  |  |  | No |  |  | Not Required
24INR0196 | Dori BQ BESS | SS Completed, FIS Completed, IA | Sunnyside Energy LLC | 138kV line Holmes (#47210) - Garden Villas (#42680); CNP | Harris | HOUSTON | 2024-10-30 | OTH | BA | 154 |  | 2022-01-05 | 2022-02-07 | 2022-05-06 | 2022-01-19 | 2022-12-02 | No | 2023-05-31 | No | Not Required | Not Required | Not Required
24INR0197 | Opuntia Storage SLF | SS Completed, FIS Started, No IA | Opuntia Solar, LLC | tap 138 kV 5607 Warburton - 8912 Medio Creek | Refugio | COASTAL | 2026-09-08 | OTH | BA | 0 |  | 2022-02-01 | 2022-02-07 | 2022-05-07 | 2022-01-20 |  |  |  | No | Not Required | Not Required | Not Required
24INR0198 | Two Forks BESS | SS Completed, FIS Started, No IA | Two Forks LLC | 684 SPRING 138kV | Cooke | NORTH | 2025-12-04 | OTH | BA | 309 |  | 2022-10-23 | 2022-01-28 | 2022-04-26 | 2022-10-13 |  |  |  | No |  |  | Not Required
24INR0200 | White Tail Solar | SS Completed, FIS Started, No IA | Mule Deer Solar LLC | Tap 345kV Windmill (23910) – AJ Swope (23906) | Deaf Smith | PANHANDLE | 2026-04-22 | SOL | PV | 228.5 |  | 2022-11-09 | 2022-02-07 | 2022-05-07 | 2022-10-21 |  |  |  | No |  |  | Not Required
24INR0201 | Short Creek Solar | SS Completed, FIS Started, No IA | Wichita Solar I, LLC | Tap 345kV 6101 Riley - 1425 Fisher Road Switch | Wichita | WEST | 2027-12-01 | SOL | PV | 625 |  | 2022-10-17 | 2022-01-20 | 2022-04-18 | 2022-10-12 |  |  |  | No |  |  | Not Required
24INR0204 | Trigo Solar Project | SS Completed, FIS Started, No IA | Ignis TX Solar Two LLC | 5705 Fowlerton 138kV | La Salle | SOUTH | 2025-12-15 | SOL | PV | 145.62 |  | 2022-08-15 | 2022-01-07 | 2022-04-01 | 2022-07-27 |  |  |  | No |  |  | Not Required
24INR0205 | Wensowitch Solar | SS Completed, FIS Completed, No IA | Greenalia Solar Power Wensowitch LLC | Tapping 138 kV line Telico (192) to Montfort Switch (3454) | Navarro | NORTH | 2025-10-15 | SOL | PV | 145.58 |  | 2022-08-15 | 2022-01-07 | 2022-04-01 | 2022-07-25 | 2023-12-13 |  |  | No |  |  | Not Required
24INR0206 | Glasgow Solar | SS Completed, FIS Started, IA | Glasgow Solar LLC | 345kV line between BUS #2466 Big Onion to #68091 Navarro circuit | Navarro | NORTH | 2025-11-10 | SOL | PV | 203.5 |  | 2022-02-03 | 2022-02-07 | 2022-05-07 | 2022-01-12 |  | No | 2023-11-08 | Yes | Not Required | Not Required | Not Required
24INR0207 | Glasgow Storage | SS Completed, FIS Started, IA | Glasgow Solar LLC | 345kV line between BUS #2466 Big Onion to #68091 Navarro circuit | Navarro | NORTH | 2025-11-10 | OTH | BA | 101 |  |  | 2022-02-21 | 2022-05-07 | 2022-02-02 |  |  | 2023-11-08 | Yes | Not Required | Not Required | Not Required
24INR0208 | Eastbell Milam Solar II | SS Completed, FIS Started, IA | Cattlemen Solar Park II LLC | 345 kV Bell County East Switch (bus# 3687) - TNP One (bus# 39950) circuit 2 | Milam | SOUTH | 2024-12-20 | SOL | PV | 152.52 |  | 2022-02-07 | 2022-03-07 | 2022-06-02 | 2022-02-03 |  |  | 2023-10-25 | Yes |  |  | Not Required
24INR0210 | Raven Storage | SS Completed, FIS Started, No IA | Raven Storage, LLC | Tap 138kV 44740 Wallis - 44190 East Bernard CKT#65 | Wharton | SOUTH | 2025-10-01 | OTH | BA | 101.83 |  | 2022-11-01 | 2022-01-28 | 2022-04-26 | 2022-10-18 |  | No |  | No |  |  | Not Required
24INR0213 | Owens Solar | SS Completed, FIS Started, No IA | Owens Solar LLC | Tap 138kV line between 177 BOSQUE and 181 Cayote | Bosque | NORTH | 2025-12-31 | SOL | PV | 203.5 |  | 2022-02-01 | 2022-02-07 | 2022-05-06 | 2022-01-12 |  |  |  | No |  |  | Not Required
24INR0233 | St. Gall Solar | SS Completed, FIS Started, No IA | St. Gall Solar LLC | 38355 Leon Creek 138kV | Pecos | WEST | 2025-06-01 | SOL | PV | 207 |  | 2022-02-07 | 2022-02-28 | 2022-05-27 | 2022-02-24 |  |  |  | No |  |  | Not Required
24INR0234 | Rock N' Roll Storage SLF | SS Completed, FIS Started, No IA | Rock N' Roll Solar, LLC | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2024-12-31 | OTH | BA | 0 |  | 2022-02-10 | 2022-02-28 | 2022-05-27 | 2022-02-11 |  | No |  | No | Not Required | Not Required | Not Required
24INR0235 | Rock N' Roll Storage Two | SS Completed, FIS Started, No IA | Rock N' Roll Solar, LLC | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2024-12-31 | OTH | BA | 206 |  | 2022-02-24 | 2022-02-28 | 2022-05-27 | 2022-02-11 |  | No |  | No | Not Required | Not Required | Not Required
24INR0236 | Bayside 2 BESS | SS Completed, FIS Started, No IA | Bayside 2 BESS | Tap between 345kV 5915 STP - 5133 Elm Creek ckt #1 and Cachena (#5068) and Old Hickory (#5323). | DeWitt | SOUTH | 2026-11-11 | OTH | BA | 252.3 |  | 2022-02-10 | 2022-03-07 | 2022-06-02 | 2022-03-01 |  |  |  | No | Not Required | Not Required | Not Required
24INR0237 | Bayside BESS | SS Completed, FIS Started, No IA | Bayside BESS | Tap between 345kV 5915 STP - 5133 Elm Creek ckt #1 and Cachena (#5068) and Old Hickory (#5323). | Victoria | SOUTH | 2025-09-04 | OTH | BA | 507.8 |  | 2022-02-11 | 2022-03-07 | 2022-06-02 | 2022-03-01 |  |  |  | No | Not Required | Not Required | Not Required
24INR0240 | Whitethorn Solar | SS Completed, FIS Started, No IA | Greasewood III LLC | Tap 345kV 76002 Bakerfield - 60404 Solstice CKT#1 | Pecos | WEST | 2025-07-18 | SOL | PV | 274.83 |  | 2022-10-07 | 2022-05-11 | 2022-06-29 | 2022-09-23 |  |  |  | No |  |  | Not Required
24INR0242 | Stockdale BESS | SS Completed, FIS Started, No IA | Stockdale BESS | Tap 345kV 5133 Elm Creek - 5068 Cachena Ckt 2 | Wilson | SOUTH | 2024-08-30 | OTH | BA | 203.9 |  | 2022-02-15 | 2022-03-14 | 2022-06-09 | 2022-03-01 |  |  |  | No |  |  | Not Required
24INR0243 | Solar Star Western Hills Storage | SS Completed, FIS Started, No IA | Solar Star Western Hills Storage, LLC | Tap 138kV 1955 CALMONT SWITCH – 2087 Western Hills | Tarrant | NORTH | 2025-09-30 | OTH | BA | 160 |  | 2022-12-14 | 2022-02-21 | 2022-05-21 | 2022-11-10 |  |  |  | No | Not Required | Not Required | Not Required
24INR0245 | Diamondback BESS | SS Completed, FIS Started, No IA | Diamondback BESS | 80355 Del Sol 345kV | Starr | SOUTH | 2025-08-30 | OTH | BA | 203.8 |  | 2022-02-16 | 2022-03-07 | 2022-06-02 | 2022-03-01 |  |  |  | No | Not Required | Not Required | Not Required
24INR0246 | Sultan BESS | SS Completed, FIS Started, No IA | Sultan BESS | tap 345kV 68080 Sam Switch – 68090 Kopperl | Bosque | NORTH | 2024-08-30 | OTH | BA | 203.8 |  | 2022-02-16 | 2022-03-07 | 2022-06-02 | 2022-03-01 |  |  |  | No |  |  | Not Required
24INR0249 | Hickerson BESS | SS Completed, FIS Started, No IA | Hickerson BESS | tap 345kV 68091 Navarro - 68040 Kopperl | Bosque | NORTH | 2024-08-30 | OTH | BA | 302.4 |  | 2022-02-24 | 2022-03-07 | 2022-06-02 | 2022-02-24 |  |  |  | No |  |  | Not Required
24INR0252 | Kruth Storage | SS Completed, FIS Started, No IA | Martinez Energy Storage LLC | 3319 Redland 138kV | Angelina | NORTH | 2026-03-31 | OTH | BA | 203 |  | 2022-08-05 | 2022-02-28 | 2022-05-27 | 2022-07-22 |  |  |  | No | Not Required | Not Required | Not Required
24INR0255 | Mitchell Plant Road Storage | SS Completed, FIS Started, No IA | DHI POWER, LLC | 138 kV 38430 White Baker TNP | Pecos | WEST | 2025-07-01 | OTH | BA | 201.6 |  | 2022-02-23 | 2022-02-28 | 2022-05-21 | 2022-02-25 |  | No |  | No | Not Required | Not Required | Not Required
24INR0256 | Kennedy Solar | SS Completed, FIS Started, No IA | Kennedy Bypass Solar LLC | Tap 345kV 68040 Kopprl Capacitor Yard - 68091 Navarro | Navarro | NORTH | 2025-11-10 | SOL | PV | 101.5 |  | 2022-07-11 | 2022-03-07 | 2022-06-02 | 2022-06-29 |  |  |  | No |  |  | Not Required
24INR0257 | Pruett Solar | SS Completed, FIS Started, No IA | Crandall Solar LLC | Tap 138kV 587 Greenwood - 685 Leo | Wise | NORTH | 2026-04-30 | SOL | PV | 150.54 |  | 2022-04-13 | 2022-02-28 | 2022-05-27 | 2022-04-05 |  |  |  | No |  |  | Not Required
24INR0258 | Zeissel Solar | SS Completed, FIS Started, No IA | ZSS Power Holdings, LLC | 60700 Gauss 345 KV | Knox | WEST | 2028-12-31 | SOL | PV | 691.44 |  | 2022-05-19 | 2022-02-28 | 2022-05-27 | 2022-04-25 |  |  |  | No | Not Required | Not Required | Not Required
24INR0259 | Zeissel Storage SLF | SS Completed, FIS Started, No IA | ZSS Power Holdings, LLC | 60700 Gauss 345 KV | Knox | WEST | 2028-12-31 | OTH | BA | 0 |  | 2022-05-10 | 2022-02-28 | 2022-05-27 | 2022-04-25 |  |  |  | No | Not Required | Not Required | Not Required
24INR0260 | Lager Storage | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners,LLC | 8031 Gillrina 69kV | Nueces | COASTAL | 2026-04-30 | OTH | BA | 30 |  | 2022-02-21 | 2022-02-28 | 2022-05-27 | 2022-02-23 |  | No |  | No |  |  | Not Required
24INR0262 | Lan Battery SLF | SS Completed, FIS Started, No IA | General Solar, LLC | Tap 345kV 1729 Valley South – 1692 Paris Switch | Lamar | NORTH | 2025-08-26 | OTH | BA | 0 |  | 2022-04-04 | 2022-06-10 | 2022-09-06 | 2022-04-27 |  | No |  | No |  |  | Not Required
24INR0263 | Cold Creek Solar | SS Completed, FIS Started, No IA | Cold Creek Solar LLC | 76003 Big Hill Substation 345kV | Schleicher | WEST | 2025-06-30 | SOL | PV | 455 | MW Size | 2022-03-30 | 2022-04-18 | 2022-07-08 | 2022-04-13 |  |  |  | No |  |  | Not Required
24INR0265 | Ironman BESS | SS Completed, FIS Completed, IA | SMT Ironman BESS LLC | 43035 Oasis Substation 345kV | Brazoria | COASTAL | 2024-11-01 | OTH | BA | 304.2 |  | 2022-02-28 | 2022-03-14 | 2022-04-18 | 2022-03-08 | 2022-12-08 |  | 2022-12-15 | Yes |  |  | Not Required | 2023-08-25
24INR0266 | Cold Creek Storage | SS Completed, FIS Started, No IA | Cold Creek Solar LLC | 76003 Big Hill Substation 345kV | Schleicher | WEST | 2025-06-30 | OTH | BA | 172.4 | MW Size | 2022-04-13 | 2022-04-18 | 2022-07-08 | 2022-04-13 |  |  |  | No |  |  | Not Required
24INR0269 | Bar Candela Solar SLF | SS Completed, FIS Started, No IA | Bar Candela Solar Project LLC | Long Lake Sub (Bus 3280) – Long Lake Tap Switch (Bus 3279) | Freestone | NORTH | 2026-06-30 | SOL | PV | 200.3 |  | 2022-12-16 | 2022-03-21 | 2022-06-13 | 2022-12-06 |  |  |  | No |  |  | Not Required
24INR0271 | Bar Candela Storage SLF | SS Completed, FIS Started, No IA | Bar Candela Storage Project LLC | Long Lake Sub (Bus 3280) – Long Lake Tap Switch (Bus 3279) | Freestone | NORTH | 2026-06-30 | OTH | BA | 0 |  | 2022-12-16 | 2022-03-21 | 2022-06-13 | 2022-12-05 |  |  |  | No | Not Required | Not Required | Not Required
24INR0272 | Brushy Creek Storage SLF | SS Completed, FIS Started, No IA | Brushy Creek Solar | the 345 kV San Angelo Red Creek Substation (#6444); AEP | Tom Green | WEST | 2025-09-20 | OTH | BA | 0 |  | 2022-03-03 | 2022-03-30 | 2022-06-26 | 2022-03-08 |  | No |  | No |  |  | Not Required
24INR0273 | Al Pastor BESS | SS Completed, FIS Completed, IA | Al Pastor BESS LLC | 1163 Lamesa Substation 138kV | Dawson | WEST | 2024-08-16 | OTH | BA | 103.1 | MW Size COD | 2022-03-02 | 2022-03-07 | 2022-06-02 | 2022-03-02 | 2022-11-02 | No | 2023-01-24 | Yes | Not Required | Not Required | Not Required | 2023-11-01 | 2023-11-01 | 2023-11-01
24INR0274 | Bufflehead BESS | SS Completed, FIS Completed, No IA | Black Mountain Energy Storage II | 2475 Lavon Switch 138kV | Collin | NORTH | 2026-02-15 | OTH | BA | 100.8 |  | 2022-02-25 | 2022-03-07 | 2022-06-02 | 2022-02-28 | 2023-05-04 |  |  | No | Not Required | Not Required | Not Required
24INR0275 | Picadillo BESS | SS Completed, FIS Completed, No IA | Black Mountain Energy Storage II | 23837 Buffalo 138kV | Martin | WEST | 2026-02-15 | OTH | BA | 100.83 |  | 2022-02-25 | 2022-03-07 | 2022-06-02 | 2022-02-28 | 2023-06-13 |  |  | No |  |  | Not Required
24INR0280 | Port Bay ESC | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | 8434 Rockport Substation (ROCKPORT4A) 138kV | Aransas | COASTAL | 2026-09-30 | OTH | BA | 200 | COD | 2022-03-18 | 2022-03-21 | 2022-06-16 | 2022-03-07 |  | No |  | No |  |  | Not Required
24INR0281 | Red Egret BESS | SS Completed, FIS Started, IA | Red Egret LLC | 38820 FREEWAY PARK 138KV | Galveston | HOUSTON | 2025-06-01 | OTH | BA | 310.58 |  | 2022-10-23 | 2022-03-14 | 2022-06-09 | 2022-10-13 |  | No | 2023-06-07 | Yes | Not Required | Not Required | Not Required | 2023-08-08
24INR0282 | Royal River BESS | SS Completed, FIS Started, No IA | Royal River LLC | Tap 138kV 42110 Angleton - 43381 West Columbia | Brazoria | COASTAL | 2025-11-28 | OTH | BA | 309 |  | 2023-02-08 | 2022-03-30 | 2022-06-27 |  |  | No |  | No |  |  | Not Required
24INR0283 | Sunshine Solar | SS Completed, FIS Started, No IA | Sunshine Energy LLC | Tap on the 138kV Lolita (#8125) - Victoria (#8172) Line | Victoria | SOUTH | 2026-12-01 | SOL | PV | 130.72 |  | 2022-08-29 | 2022-09-02 | 2022-11-29 | 2022-08-24 |  |  |  | No |  |  | Not Required
24INR0285 | APV Plumwood Storage | SS Completed, FIS Completed, No IA | APV Lonestar Energy LLC | Tap 138kV 40171 Baytown - 40015Cedar Bayou Plant | Chambers | HOUSTON | 2026-01-15 | OTH | BA | 200.82 |  | 2022-03-18 | 2022-03-30 | 2022-06-26 | 2022-03-22 | 2023-11-21 |  |  | No |  |  | Not Required
24INR0287 | Rockridge Solar Project | SS Completed, FIS Started, No IA | Magnolia Solar Development LLC | 7225 Hickory Forest 138kV | Guadalupe | SOUTH | 2024-11-15 | SOL | PV | 221.27 |  | 2022-08-10 | 2022-04-18 | 2022-07-12 | 2022-08-03 |  |  |  | No |  |  | Not Required
24INR0289 | Ratcliff Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Ratcliff | Tap 138kV 3279 Long Lake Tap Switch - 3280 Long Lake | Freestone | NORTH | 2025-10-15 | SOL | PV | 85.45 |  | 2022-08-22 | 2022-06-27 | 2022-09-23 | 2022-08-17 |  |  |  | No |  |  | Not Required
24INR0291 | Rubicon Alpha Wind | SS Completed, FIS Started, No IA | Rubicon Wind | Tap 345kV 60791 Perigee – 6235 Abilene Mulberry Creek | Haskell | WEST | 2027-07-01 | WIN | WT | 225.6 |  | 2022-03-28 | 2022-05-10 | 2022-08-06 | 2022-04-15 |  |  |  | No | Not Required | Not Required | Not Required
24INR0294 | Citrus Flatts BESS | SS Completed, FIS Started, IA | Citrus Flatts Energy Center, LLC | 80022 Oleander 138kV | Cameron | COASTAL | 2025-07-15 | OTH | BA | 100.8 |  | 2022-03-21 | 2022-03-30 | 2022-06-26 | 2022-03-24 |  | No | 2023-09-08 | Yes |  |  | Not Required
24INR0295 | Lucky Bluff BESS | SS Completed, FIS Completed, IA | Lucky Bluff BESS LLC | tap 138kV 1641 Stephenville - 1636 Dublin | Erath | NORTH | 2025-05-31 | OTH | BA | 100.8 |  | 2022-03-23 | 2022-03-30 | 2022-06-26 | 2022-03-24 | 2023-02-14 | No | 2023-11-08 | Yes | Not Required | Not Required | Not Required | 2023-11-20
24INR0298 | Leighton Solar SLF | SS Completed, FIS Started, No IA | Lavender Solar LLC | 99 BENHUR 69kV | Limestone | NORTH | 2024-11-04 | SOL | PV | 183 |  | 2022-04-27 | 2022-05-11 | 2022-08-05 | 2022-03-16 |  |  |  | No |  |  | Not Required
24INR0301 | Merchant BESS | SS Completed, FIS Started, No IA | Merchant BESS LLC | 46510 TOMBALL 138KV | Harris | HOUSTON | 2025-07-15 | OTH | BA | 201.2 |  | 2022-04-02 | 2022-04-18 | 2022-07-12 | 2022-04-04 |  | No |  | No | Not Required | Not Required | Not Required
24INR0302 | Pintail Pass BESS | SS Completed, FIS Started, IA | EEC Pintail | 8249 ANGSTROM 345KV | San Patricio | COASTAL | 2025-07-15 | OTH | BA | 201.2 |  | 2022-04-02 | 2022-04-18 | 2022-06-16 | 2022-04-07 |  | No | 2023-05-16 | No |  |  | Not Required
24INR0303 | Erika Solar | SS Completed, FIS Completed, IA | Erika Solar, LLC | Tap 345kV ELKTON 5 (#3105 ) to Tricrn1 5 (#2432) | Kaufman | NORTH | 2025-08-31 | SOL | PV | 203.5 |  | 2022-05-02 | 2022-07-25 | 2022-10-18 | 2022-07-06 | 2023-09-08 |  | 2023-10-12 | No |  |  | Not Required
24INR0304 | Barton Bishop BESS | SS Completed, FIS Completed, No IA | Jack Barton BESS LLC | 1599 Barton Chapel Wind Farm station 138kV | Jack | NORTH | 2025-08-27 | OTH | BA | 47.34 |  | 2022-04-04 | 2022-08-05 | 2022-11-01 | 2022-04-20 | 2023-09-11 |  |  | No |  |  | Not Required
24INR0305 | MRG Goody Storage | SS Completed, FIS Completed, No IA | MRG Goody Solar Project LLC | Tap 138 kV Toco Switch (#1700) – Paris Switch (#1693) | Lamar | NORTH | 2025-07-07 | OTH | BA | 50.4 |  | 2022-04-07 | 2022-05-10 | 2022-08-05 | 2022-04-11 | 2023-11-21 |  |  | No |  |  | Not Required
24INR0306 | Arroyo Storage | SS Completed, FIS Started, IA | BT Cantwell Solar, LLC | Tap 345kV 8318 Rio Hondo - 8317 La Palma (New Gulch Substation ) | Cameron | COASTAL | 2024-11-30 | OTH | BA | 148.51 | MW Size | 2022-05-03 | 2022-05-10 | 2022-08-05 | 2022-04-26 |  |  | 2022-08-10 | No |  |  | Not Required
24INR0308 | Forts Trail Solar | SS Completed, FIS Started, No IA | JC Central Bluff, LLC | 11406 Central Bluff Switch 345kV | Taylor | WEST | 2026-06-20 | SOL | PV | 200.93 |  | 2022-06-07 | 2022-06-02 | 2022-08-30 | 2022-06-03 |  |  |  | No |  |  | Not Required
24INR0310 | Webb County Renewables Solar | SS Completed, FIS Started, No IA | Webb County Renewables, LLC | 161105 Bordas 345kV | Webb | SOUTH | 2024-06-01 | SOL | PV | 203.4 |  | 2022-06-19 | 2022-07-25 | 2022-10-19 | 2022-06-20 |  |  |  | No |  |  | Not Required
24INR0311 | Webb County Renewables Storage | SS Completed, FIS Started, No IA | Webb County Renewables, LLC | 161105 Bordas 345kV | Webb | SOUTH | 2024-06-01 | OTH | BA | 203.4 |  | 2022-07-18 | 2022-07-25 | 2022-10-19 | 2022-07-06 |  |  |  | No |  |  | Not Required
24INR0312 | Wigeon Whistle BESS | SS Completed, FIS Completed, IA | Wigeon Whistle BESS | 811 NEVADA 138KV | Collin | NORTH | 2024-09-01 | OTH | BA | 122.9 | MW Size | 2022-04-27 | 2022-04-18 | 2022-07-11 | 2022-04-13 | 2023-10-23 | No | 2022-12-08 | Yes | Not Required | Not Required | Not Required | 2023-10-31 | 2023-10-31 | 2023-10-31
24INR0313 | Backbone Creek BESS | SS Completed, FIS Started, IA | Backbone Creek BESS LLC | 7351 STARCKE 138kV | Burnet | SOUTH | 2024-09-01 | OTH | BA | 120.69 |  | 2022-05-09 | 2022-04-18 | 2022-07-08 | 2022-04-27 |  |  | 2023-12-22 | No |  |  | Not Required
24INR0319 | Burro Loco Energy Storage | SS Completed, FIS Started, No IA | VESI | 8626 Resaca 69kV | Cameron | COASTAL | 2025-07-01 | OTH | BA | 25.14 |  | 2022-07-14 | 2022-07-18 | 2022-10-14 | 2022-07-08 |  |  |  | No |  |  | Not Required
24INR0323 | Coati Solar | SS Completed, FIS Completed, No IA | Coati Solar, LLC | Tapping the 138 kV line from Ridge (Bus# 37) to Robertson (Bus# 32) | Robertson | NORTH | 2024-12-31 | SOL | PV | 296.07 |  | 2022-05-10 | 2022-05-24 | 2022-08-19 | 2022-04-28 | 2023-10-24 | No |  | No |  |  | Not Required
24INR0325 | Coati Storage | SS Completed, FIS Completed, No IA | Coati Solar, LLC | Tapping the 138 kV line from Ridge (Bus# 37) to Robertson (Bus# 32) | Robertson | NORTH | 2024-12-31 | OTH | BA | 145.97 |  | 2022-05-10 | 2022-05-24 | 2022-08-19 | 2022-04-28 | 2023-10-24 | No |  | No |  |  | Not Required
24INR0326 | Blarney Solar | SS Completed, FIS Completed, No IA | Sligsol, LLC | tap 138kV 1815 Cumby Tap - 1819 Commerce South Sub | Hopkins | NORTH | 2025-10-11 | SOL | PV | 81 |  | 2022-04-20 | 2022-07-05 | 2022-10-01 | 2022-04-21 | 2023-10-18 |  |  | No |  |  | Not Required
24INR0329 | XE Murat Storage | SS Completed, FIS Completed, IA | Liberty 1 Solar LLC | tap the 138 kV CROSBY C66(#40391) -ATASCOCITA (#40130) Line; CNP | Harris | HOUSTON | 2024-12-14 | OTH | BA | 62.05 |  | 2022-05-16 | 2022-06-02 | 2022-08-30 | 2022-04-28 | 2023-05-02 | No | 2023-11-01 | No |  |  | Not Required
24INR0330 | TRAVIS KIMBRO BESS | SS Completed, FIS Started, No IA | Travis Kimbro BESS LLC | 7337 Kimbro 138kV | Travis | SOUTH | 2025-07-01 | OTH | BA | 36.84 |  | 2022-04-20 | 2022-09-02 | 2022-11-29 | 2022-04-25 |  |  |  | No |  |  | Not Required
24INR0331 | Chisme Storage | SS Completed, FIS Started, No IA | Blue Heron Solar, LLC | Tap 345 kV 1444 BROWN SWITCH - 3424 BUCKHORN SWITCH | Brown | NORTH | 2026-02-20 | OTH | BA | 146 |  | 2023-01-11 | 2023-01-17 | 2023-04-14 | 2023-01-11 |  |  |  | No |  |  | Not Required
24INR0333 | Chisme Solar | SS Completed, FIS Started, No IA | Blue Heron Solar, LLC | Tap 345 kV 1444 BROWN SWITCH - 3424 BUCKHORN SWITCH | Brown | NORTH | 2026-02-20 | SOL | PV | 147 |  | 2023-01-11 | 2023-01-17 | 2023-04-14 | 2023-01-11 |  |  |  | No |  |  | Not Required
24INR0335 | Evergreen Storage | SS Completed, FIS Started, No IA | Evergreen Energy LLC | 8111 Magilla 138kV | Matagorda | COASTAL | 2024-12-31 | OTH | BA | 100 |  | 2022-05-02 | 2022-06-02 | 2022-08-29 | 2022-05-04 |  |  |  | No |  |  | Not Required
24INR0337 | Eldora Solar | SS Completed, FIS Completed, IA | Eldora Energy LLC | Tap 345 kV 5915 South Texas Project – 44200 Hillje Ckt 1 | Matagorda | COASTAL | 2026-06-30 | SOL | PV | 200.94 |  | 2022-05-31 | 2022-06-10 | 2022-09-06 | 2022-06-01 | 2023-12-18 |  | 2023-11-15 | Yes | Not Required | Not Required | Not Required | 2023-12-18
24INR0338 | Eldora BESS | SS Completed, FIS Completed, IA | Eldora Energy LLC | 345 kV South Texas Project (Bus# 5915) – Hillje (Bus# 44200) Transmission Line Ckt 1 | Matagorda | COASTAL | 2026-06-30 | OTH | BA | 201.31 |  | 2022-06-03 | 2022-06-10 | 2022-09-06 | 2022-06-01 | 2023-12-18 |  | 2023-11-15 | Yes | Not Required | Not Required | Not Required | 2023-12-18
24INR0339 | Mystic Springs Renewable Energy Solar SLF | SS Completed, FIS Started, No IA | Tawakoni Park Solar LLC | Tap 345kV Royse Switch (2470) – Shamburger (3223) | Kaufman | NORTH | 2026-06-01 | SOL | PV | 258.83 |  | 2022-12-14 | 2022-05-10 | 2022-08-06 | 2022-11-28 |  |  |  | No |  |  | Not Required
24INR0340 | Mystic Springs Renewable Energy Storage SLF | SS Completed, FIS Started, No IA | Tawakoni Park Storage LLC | Tap 345kV Royse Switch (2470) – Shamburger (3223) | Kaufman | NORTH | 2026-06-01 | OTH | BA | 0 |  | 2022-12-14 | 2022-05-10 | 2022-08-06 | 2022-11-28 |  |  |  | No |  |  | Not Required
24INR0341 | Forts Trail BESS | SS Completed, FIS Started, No IA | JC Central Bluff, LLC | 11406 Central Bluff Switch 345kV | Taylor | WEST | 2026-06-20 | OTH | BA | 200.93 |  | 2022-06-06 | 2022-06-02 | 2022-08-30 | 2022-06-03 |  |  |  | No | Not Required | Not Required | Not Required
24INR0345 | Schoolhouse BESS | SS Completed, FIS Started, No IA | Schoolhouse Storage, LLC | tap 345kV 7040 Austrop - 13429 Sandow | Lee | SOUTH | 2025-09-22 | OTH | BA | 150.68 |  | 2022-06-09 | 2022-06-17 | 2022-09-14 | 2022-06-10 |  |  |  | No |  |  | Not Required
24INR0348 | Best Southwest BESS | SS Completed, FIS Started, No IA | North Texas Energy Storage LLC | 2431 DESOTO SW 345kV | Dallas | NORTH | 2025-05-31 | OTH | BA | 241.44 |  | 2022-05-09 | 2022-05-16 | 2022-08-05 | 2022-04-26 |  |  |  | No |  |  | Not Required
24INR0350 | Brushwood Energy Storage | SS Completed, FIS Completed, No IA | Flagtail LLC | Tap 345kV 44645 Singleton - 40600 Roans Prairie | Grimes | NORTH | 2026-12-31 | OTH | BA | 203.78 |  | 2022-06-06 | 2022-06-10 | 2022-09-06 | 2022-05-27 | 2023-07-06 | Yes |  | No |  |  | Not Required
24INR0352 | Guinness BESS | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners,LLC | Tap 138kV 7520 BERTRA - 7522 ANDICE | Williamson | SOUTH | 2026-04-30 | OTH | BA | 100.51 |  | 2022-11-02 | 2022-07-25 | 2022-10-20 | 2022-09-27 |  |  |  | No |  |  | Not Required
24INR0353 | Exodus | SS Completed, FIS Started, No IA | Exodus Solar LLC. | Tap 345kV 7040 Austrop – 7042 Zorn | Caldwell | SOUTH | 2025-08-20 | SOL | PV | 152.9 |  | 2022-05-16 | 2022-06-10 | 2022-09-06 | 2022-05-20 |  |  |  | No | Not Required | Not Required | Not Required
24INR0355 | Anatole Renewable Energy Storage | SS Completed, FIS Started, No IA | Eustace Storage LLC | (Bus# 6951) Eustace Southeast 138kV Substation (owned by Rayburn Electric Cooperative) | Henderson | NORTH | 2026-06-01 | OTH | BA | 207.82 |  | 2022-12-14 | 2022-06-02 | 2022-08-30 | 2022-12-02 |  |  |  | No |  |  | Not Required
24INR0356 | Cibeles Solar | SS Completed, FIS Started, No IA | Elawan Cibeles Solar, LLC | Tap 345kV 3388 Four Brothers Switch – 3405 Tradinghouse SES | McLennan | NORTH | 2026-08-01 | SOL | PV | 251 |  | 2023-01-31 | 2022-05-16 | 2022-08-13 |  |  |  |  | No |  |  | Not Required
24INR0358 | Blanket Ranch South Solar | SS Completed, FIS Started, No IA | Blanket Ranch South Solar, LLC | Tap 345kV 11441 CORN TRAIL SWITCH - 1444 BROWN SWITCH | Brown | NORTH | 2026-04-03 | SOL | PV | 133.4 |  | 2022-11-30 | 2022-06-10 | 2022-09-06 | 2022-11-17 |  |  |  | No |  |  | Not Required
24INR0360 | Blanket Ranch North Solar | SS Completed, FIS Started, No IA | Blanket Ranch North Solar, LLC | Tap 345kV 11441 CORN TRAIL SWITCH - 1444 BROWN SWITCH | Brown | NORTH | 2026-04-03 | SOL | PV | 234.6 |  | 2022-12-08 | 2022-06-10 | 2022-09-06 | 2022-11-29 |  |  |  | No |  |  | Not Required
24INR0361 | Blanket Ranch South Storage | SS Completed, FIS Started, No IA | Blanket Ranch South Solar, LLC | Tap 345kV 11441 CORN TRAIL SWITCH - 1444 BROWN SWITCH | Brown | NORTH | 2026-04-03 | OTH | BA | 33 |  | 2022-11-30 | 2022-06-10 | 2022-09-06 | 2022-11-17 |  |  |  | No |  |  | Not Required
24INR0362 | Blanket Ranch North Storage | SS Completed, FIS Started, No IA | Blanket Ranch North Solar, LLC | Tap 345kV 11441 CORN TRAIL SWITCH - 1444 BROWN SWITCH | Brown | NORTH | 2026-04-03 | OTH | BA | 50 |  | 2022-12-08 | 2022-06-10 | 2022-09-06 | 2022-11-29 |  |  |  | No |  |  | Not Required
24INR0364 | Pitts Dudik II | SS Completed, FIS Started, No IA | Pitts Dudik II | 138 kV Ash Creek Switch (#3473) | Hill | NORTH | 2025-07-01 | SOL | PV | 30.23 |  | 2022-08-28 | 2022-07-18 | 2022-10-14 | 2022-08-04 |  |  |  | No |  |  | Not Required
24INR0365 | XE Hermes Storage | SS Completed, FIS Started, IA | Bell Solar 1 LLC | Tap 345kV 3687 Bell County East Switch - 39950 TNP One Plant Ckt 2 | Bell | NORTH | 2025-08-25 | OTH | BA | 100.42 |  | 2022-07-14 | 2022-07-18 | 2022-10-12 | 2022-06-30 |  |  | 2023-11-08 | Yes |  |  | Not Required
24INR0368 | Glory Bee Solar | SS Completed, FIS Completed, No IA | Riley Solar LLC | Tap 345kV 1440 Comanche Switch - 1900 Comanche Peak | Erath | NORTH | 2025-04-11 | SOL | PV | 305 |  | 2022-06-06 | 2022-06-10 | 2022-09-06 | 2022-06-06 | 2023-04-18 |  |  | No |  |  | Not Required
24INR0369 | Glory Bee Storage | SS Completed, FIS Completed, No IA | Riley Solar LLC | Tap 345kV 1440 Comanche Switch - 1900 Comanche Peak | Erath | NORTH | 2025-04-11 | OTH | BA | 101 |  | 2022-06-06 | 2022-06-10 | 2022-09-06 | 2022-06-06 | 2023-04-18 |  |  | No | Not Required | Not Required | Not Required
24INR0370 | Dogwood Creek Solar | SS Completed, FIS Started, No IA | Dogwood Creek Solar LLC | tap 345kV 7040 Austrop - 9041 Lost Pines | Bastrop | SOUTH | 2025-05-31 | SOL | PV | 432.02 |  | 2022-06-20 | 2022-06-27 | 2022-09-22 | 2022-06-06 |  |  |  | No |  |  | Not Required
24INR0371 | Dogwood Creek Storage | SS Completed, FIS Started, No IA | Dogwood Creek Solar LLC | tap 345kV 7040 Austrop - 9041 Lost Pines | Bastrop | SOUTH | 2025-05-31 | OTH | BA | 431.3 |  | 2022-06-20 | 2022-07-05 | 2022-09-22 | 2022-06-06 |  |  |  | No | Not Required | Not Required | Not Required
24INR0372 | GIGA AUSTIN SOLAR | SS Completed, FIS Started, No IA | GIGA TEXAS ENERGY LLC | 7047 HORNSBY Substation 138kV | Travis | SOUTH | 2025-03-14 | SOL | PV | -53.3 |  | 2022-08-09 | 2022-07-18 | 2022-10-14 | 2022-07-26 |  |  |  | No |  |  | Not Required
24INR0374 | Farrier Station Energy Storage | SS Completed, FIS Started, No IA | Farrier Station Energy Storage Project, LLC | MONTICELLO SES (BUS# 1696) - ALLEN SWITCH (BUS# 2514) | Hopkins | NORTH | 2026-04-21 | OTH | BA | 409.9 |  | 2023-01-10 | 2023-01-17 | 2023-04-14 | 2023-01-10 |  |  |  | No |  |  | Not Required
24INR0375 | Possum Kingdom BESS | SS Completed, FIS Started, No IA | Novis Renewables, LLC | Tap 345kV 1421 Willow Creek – 11523 Thomas Price | Jack | NORTH | 2026-10-30 | OTH | BA | 201.33 |  | 2023-05-31 | 2022-09-02 | 2022-11-29 |  |  |  |  | No | Not Required | Not Required | Not Required |  |  |  | 2025-05-01 | 2026-05-08
24INR0376 | Huisache BESS | SS Completed, FIS Started, No IA | Novis Renewables, LLC | Tap 345kV 5133 Elm Creek - 5915 Southern Texas Project Ckt 1 | Wilson | SOUTH | 2026-02-15 | OTH | BA | 100.67 |  | 2023-01-11 | 2022-08-05 | 2022-11-01 | 2022-11-07 |  |  |  | No |  |  | Not Required
24INR0378 | Solara BESS 1 | SS Completed, FIS Started, No IA | CED Development Inc. | 60387 Hendrick 138kV | Jones | WEST | 2025-11-30 | OTH | BA | 150 |  | 2022-08-08 | 2022-07-05 | 2022-10-01 | 2022-07-26 |  |  |  | No |  |  | Not Required
24INR0379 | Solara BESS 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 60387 Hendrick 138kV | Jones | WEST | 2025-11-30 | OTH | BA | 150 |  | 2022-08-08 | 2022-07-05 | 2022-10-01 | 2022-07-26 |  |  |  | No |  |  | Not Required
24INR0380 | Photo BESS 3 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie Substation 138kV | Uvalde | SOUTH | 2024-05-31 | OTH | BA | 100 |  | 2022-07-28 | 2022-07-25 | 2022-10-21 | 2022-07-26 |  |  |  | No |  |  | Not Required
24INR0381 | Alexandrite Storage | SS Completed, FIS Started, No IA | Johnson Energy Storage, LLC | 8359 Santa Rosa (S_SNROSA4A) 138kV | Cameron | COASTAL | 2026-12-10 | OTH | BA | 203 |  | 2022-06-20 | 2022-06-27 | 2022-09-22 | 2022-06-15 |  |  |  | No |  |  | Not Required
24INR0382 | Remy Jade II Power Station | SS Completed, FIS Completed, IA | Remy Jade II Generating, LLC | Tap 138kV 40390 Crosby - 40811 Highlands | Harris | HOUSTON | 2024-11-30 | GAS | GT | 102 |  | 2022-07-14 | 2022-07-18 | 2022-10-12 | 2022-07-07 | 2023-03-14 |  | 2022-08-01 | No | 2022-03-16 |  | 2023-03-14
24INR0384 | Lucas Solar SLF | SS Completed, FIS Started, No IA | Clip Road Solar LLC | TAP 69 KV LINE FROM BERCLAIR 8586 - GOLIAD 8587 | Goliad | SOUTH | 2025-08-31 | SOL | PV | 204.08 |  | 2022-07-11 | 2022-07-25 | 2022-10-21 | 2022-07-19 |  |  |  | No | Not Required | Not Required | Not Required
24INR0386 | Black & Gold Energy Storage | SS Completed, FIS Started, No IA | RES America Developments Inc. | 6364 Yellow Jacket Sub 138kV | Menard | WEST | 2025-07-16 | OTH | BA | 254.58 |  | 2022-09-13 | 2022-07-18 | 2022-10-14 | 2022-08-30 |  | No |  | No |  |  | Not Required
24INR0387 | PaleAle BESS | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners,LLC | Tap 138 kV Bus 7506 L_CEDAVA8_1Y - Bus 7507 L_FRIEND8_1Y | Hays | SOUTH | 2026-04-30 | OTH | BA | 75.38 |  | 2022-12-13 | 2022-07-18 | 2022-10-14 | 2022-12-06 |  |  |  | No |  |  | Not Required
24INR0388 | Lucas Storage SLF | SS Completed, FIS Started, No IA | Clip Road Solar, LLC | TAP 69 KV LINE FROM BERCLAIR 8586 - GOLIAD 8587 | Goliad | SOUTH | 2025-08-31 | OTH | BA | 0 |  |  | 2022-07-25 | 2022-10-21 | 2022-07-19 |  |  |  | No | Not Required | Not Required | Not Required
24INR0390 | Long Point Solar II | SS Completed, FIS Started, No IA | Long Point Solar, LLC | 138 KV (CEHE Sub) Tap Burke (42410) - Eagle Nest (42430) ckt 02 | Brazoria | COASTAL | 2025-12-30 | SOL | PV | 100.9 | COD | 2023-01-05 | 2023-01-17 | 2023-04-14 | 2022-12-09 |  |  |  | No |  |  | Not Required
24INR0391 | Kennedy Storage | SS Completed, FIS Started, No IA | Kennedy Bypass Solar LLC | Tap 345kV 68040 Kopprl Capacitor Yard - 68091 Navarro | Navarro | NORTH | 2025-11-10 | OTH | BA | 25.3 |  | 2022-07-06 | 2022-07-18 | 2022-10-12 | 2022-07-06 |  |  |  | No |  |  | Not Required
24INR0392 | Riverwalk BESS | SS Completed, FIS Started, No IA | CED Development Inc. | 5294 Martinez Substation 138kV | Bexar | SOUTH | 2026-10-31 | OTH | BA | 120 |  | 2022-07-14 | 2022-07-18 | 2022-10-14 | 2022-07-11 |  |  |  | No | Not Required | Not Required | Not Required
24INR0393 | ELECTRODE BESS | SS Completed, FIS Started, No IA | CED Development Inc. | Castillo Substation, Bus number : 76040 | Upton | WEST | 2024-12-15 | OTH | BA | 150 |  | 2022-07-18 | 2022-07-25 | 2022-10-21 | 2022-07-12 |  |  |  | No | Not Required | Not Required | Not Required
24INR0394 | CATHODE BESS | SS Completed, FIS Started, No IA | CED Development Inc. | 76635 King Mountain 138kV | Upton | WEST | 2024-05-31 | OTH | BA | 150 |  | 2022-07-25 | 2022-08-05 | 2022-11-01 | 2022-07-12 |  |  |  | No |  |  | Not Required
24INR0395 | Berkman Storage | SS Completed, FIS Completed, No IA | Berkman Storage, LLC | 138 kV League City (Bus# 38920) | Galveston | HOUSTON | 2025-12-16 | OTH | BA | 150.86 |  | 2022-08-03 | 2022-08-05 | 2022-11-01 | 2022-07-21 | 2023-06-27 |  |  | No | Not Required | Not Required | Not Required
24INR0397 | Destiny Storage | SS Completed, FIS Started, IA | Destiny Storage, LLC | Tap 138kV 40390 Crosby - 40680 Placid Ckt 86 | Harris | HOUSTON | 2026-01-31 | OTH | BA | 201.11 |  | 2022-08-12 | 2022-08-16 | 2022-11-11 | 2022-07-28 |  | No | 2023-09-20 | Yes |  |  | Not Required
24INR0398 | Lake Henry Wind | SS Completed, FIS Started, No IA | Lake Henry Wind | Tap: 345kV #59911 Mhos - #59908 Nova Prime | Kent | WEST | 2027-07-01 | WIN | WT | 305 |  | 2022-08-03 | 2022-09-15 | 2022-12-13 | 2022-08-11 |  |  |  | No | Not Required | Not Required | Not Required
24INR0399 | Buzios Solar | SS Completed, FIS Completed, IA | Roaring Springs Solar, LLC | Tap between Cottonwood (#59904) and White River (#23922) | Motley | PANHANDLE | 2026-06-30 | SOL | PV | 253.46 |  | 2022-08-03 | 2022-09-15 | 2022-12-13 | 2022-08-04 | 2023-09-27 |  | 2023-11-06 | No | Not Required | Not Required | Not Required
24INR0401 | Portside Energy Center (Solar) SLF | SS Completed, FIS Started, No IA | Portside Energy Center, LLC | 80064 Chocolate Bayou 138kV | Victoria | SOUTH | 2026-06-15 | SOL | PV | 40.8 |  | 2022-10-07 | 2022-11-15 | 2023-02-10 | 2022-11-01 |  |  |  | No |  |  | Not Required
24INR0403 | Portside Energy Center (BESS) SLF | SS Completed, FIS Started, No IA | Portside Energy Center, LLC | 80064 Chocolate Bayou 138kV | Victoria | SOUTH | 2026-06-15 | OTH | BA | 0 |  | 2022-10-07 | 2022-11-15 | 2023-02-10 | 2022-11-01 |  |  |  | No |  |  | Not Required
24INR0404 | Tres Rios Ranch Solar | SS Completed, FIS Started, No IA | LectricWind LLC | 76015 L_CEDACA5_1Y 345kV | Upton | WEST | 2025-12-31 | SOL | PV | 423.87 |  | 2023-05-04 | 2022-08-05 | 2022-11-01 |  |  |  |  | No |  |  | Not Required
24INR0405 | Crowned Heron BESS | SS Completed, FIS Completed, No IA | RWE Renewables | WA Parish 345 kV Bus #44000 | Fort Bend | HOUSTON | 2024-12-15 | OTH | BA | 150 |  | 2022-07-14 | 2022-07-18 | 2022-10-14 | 2022-07-12 | 2023-05-17 |  |  | No |  |  | Not Required
24INR0407 | Mercury Solar III | SS Completed, FIS Started, No IA | Mercury Solar | 68092 Liberty Station 345kV | Hill | NORTH | 2025-12-31 | SOL | PV | 203.5 |  | 2022-08-02 | 2022-08-16 | 2022-11-11 | 2022-08-03 |  |  |  | No |  |  | Not Required
24INR0408 | Pruett Storage | SS Completed, FIS Started, No IA | Crandall Solar LLC | Tap 138kV 587 Greenwood - 685 Leo | Wise | NORTH | 2026-04-30 | OTH | BA | 50.48 |  | 2022-07-20 | 2022-07-25 | 2022-10-18 | 2022-07-15 |  |  |  | No |  |  | Not Required
24INR0410 | Greens Bayou 9 CT 138 | SS Completed, FIS Completed, No IA | NRG Texas Power | Position 1/0 PSSE 40710, Greens Bayou Substation, 138 kV | Harris | HOUSTON | 2026-06-02 | GAS | GT | 455 |  | 2022-07-21 | 2022-08-16 | 2022-11-11 | 2022-07-21 | 2023-11-27 |  |  | No
24INR0411 | Greens Bayou Unit 9 CT 345 | SS Completed, FIS Started, No IA | NRG Texas Power LLC | Position 1/0 PSSE 40700, Greens Bayou Substation | Harris | HOUSTON | 2026-06-02 | GAS | GT | 455 |  | 2022-09-07 | 2022-09-21 | 2022-12-19 | 2022-09-16 |  |  |  | No
24INR0412 | Camino Ranch Solar SLF | SS Completed, FIS Started, No IA | Camino Ranch Solar Project LLC | 3345 Flat Branch 138kV | Houston | NORTH | 2026-09-30 | SOL | PV | 300 |  | 2023-07-01 | 2022-10-06 | 2023-01-03 |  |  |  |  | No |  |  | Not Required
24INR0413 | Furay Battery Energy Storage System | SS Completed, FIS Completed, No IA | Blue Topaz 1, LLC | Tap 138kV 45660 Jonte substation – 46332 Scenic Woods Tapping both radial lines. | Harris | HOUSTON | 2024-12-01 | OTH | BA | 304 |  | 2022-08-31 | 2022-09-02 | 2022-11-29 | 2022-09-01 | 2023-09-21 | No |  | No | Not Required | Not Required | Not Required
24INR0416 | Trelas | SS Completed, FIS Started, No IA | Trelasol, LLC | 76006 Bow Wood 345kV Bus | McCulloch | SOUTH | 2025-09-01 | OTH | BA | 200.83 |  | 2022-08-15 | 2022-09-02 | 2022-11-29 | 2022-08-15 |  |  |  | No |  |  | Not Required
24INR0417 | Sierra Diablo Energy Storage | SS Completed, FIS Started, No IA | SIERRA DIABLO ENERGY STORAGE LLC | Tap 138kv Long Pasture POD (11132) – Screwbean Tap (1095) | Reeves | WEST | 2026-04-20 | OTH | BA | 203.81 |  | 2022-07-28 | 2022-08-05 | 2022-11-01 | 2022-07-26 |  |  |  | No |  |  | Not Required
24INR0418 | Middlebrook Solar | SS Completed, FIS Started, No IA | Middlebrook Solar LLC | Tap Stryker [3109] - Lufkin [3117] 345 kV line | Nacogdoches | NORTH | 2026-02-20 | SOL | PV | 609.1 |  | 2022-09-21 | 2022-10-18 | 2023-01-13 | 2022-10-06 |  |  |  | No | Not Required | Not Required | Not Required
24INR0419 | High Plains Storage | SS Completed, FIS Started, No IA | ROBP Holdings, LLC | 45880 Hockley 138kV | Harris | HOUSTON | 2025-10-30 | OTH | BA | 157.7 |  | 2022-08-18 | 2022-09-02 | 2022-11-29 | 2022-08-18 |  |  |  | No | Not Required | Not Required | Not Required
24INR0420 | Camino Ranch Storage SLF | SS Completed, FIS Started, No IA | Camino Solar Ranch, LLC | 3345 Flat Branch 138kV | Houston | NORTH | 2026-09-30 | OTH | BA | 0 |  | 2023-07-04 | 2022-10-18 | 2023-01-03 |  |  |  |  | No |  |  | Not Required
24INR0421 | Swift Air Solar | SS Completed, FIS Started, No IA | Swift Air Solar, LLC | Tap 138kV 1019 Moss Switch – 11128 Shin Oak POD | Ector | WEST | 2024-12-20 | SOL | PV | 148.84 |  | 2022-10-25 | 2022-11-07 | 2023-02-03 | 2022-09-01 |  |  |  | No | Not Required | Not Required | Not Required
24INR0422 | Hollow Branch Creek 2 Solar SLF | SS Completed, FIS Completed, No IA | Hollow Branch Creek Solar II LLC | Tap 345kV 3390 Jewett - 44645 Singleton | Leon | NORTH | 2025-12-31 | SOL | PV | 400 |  | 2022-09-06 | 2022-09-02 | 2022-11-29 | 2022-08-15 | 2023-03-28 | Yes |  | No |  |  | Not Required
24INR0423 | Hollow Branch Creek 2 Storage SLF | SS Completed, FIS Completed, No IA | Hollow Branch Creek Solar II LLC | Jewett – Singleton 345 kV [PTI Bus # 3390 – 44645] | Leon | NORTH | 2025-12-31 | OTH | BA | 0 |  | 2022-09-20 | 2022-09-02 | 2022-11-29 | 2022-09-16 | 2023-03-28 | Yes |  | No |  |  | Not Required
24INR0424 | Cascabel Wind 1 | SS Completed, FIS Started, No IA | Vaquero Wind Energy, LLC | 345 kV Rapido Substation (New ETT Substation) tapping the existing 345 kV Line from CENIZO7C (#80225) to DELSOL7C (#80307) | Zapata | SOUTH | 2025-02-28 | WIN | WT | 197.75 |  | 2023-03-08 | 2023-03-13 | 2023-06-09 | 2023-02-15 |  |  |  | No |  |  | Not Required
24INR0425 | Two Brothers Battery Energy Storage System | SS Completed, FIS Started, No IA | Blue Topaz 2, LLC | 8911 BLKBYU4A 138kV | Victoria | SOUTH | 2024-12-01 | OTH | BA | 152 |  | 2022-09-13 | 2022-09-15 | 2022-12-13 | 2022-09-14 |  | No |  | No | Not Required | Not Required | Not Required
24INR0426 | Leighton BESS SLF | SS Completed, FIS Started, No IA | Lavender Solar LLC | 99 BENHUR 69kV | Limestone | NORTH | 2024-11-04 | OTH | BA | 0 |  | 2022-09-13 | 2022-09-21 | 2022-12-19 | 2022-09-16 |  |  |  | No |  |  | Not Required
24INR0427 | CPS AvR CT1 Rotor Replacement | SS Completed, FIS Completed, No IA | CPS Energy | 5475 Braunig 345kV | Bexar | SOUTH | 2024-01-30 | GAS | CC | 11.3 |  | 2022-08-30 | 2022-10-24 | 2023-01-20 | 2022-09-20 | 2023-04-18 |  |  | No | 2018-06-01 |  | 2023-04-21 | 2023-04-18 | 2023-04-18 | 2023-05-01 |  |  |  | 2023-12-04
24INR0432 | HGP Pacesetter BESS | SS Completed, FIS Started, No IA | HGP Storage, LLC | 2431 DESSW1_5 345kV | Dallas | NORTH | 2026-04-01 | OTH | BA | 200.83 |  | 2023-03-08 | 2022-09-15 | 2022-12-13 |  |  |  |  | No |  |  | Not Required
24INR0436 | Carambola BESS | SS Completed, FIS Started, IA | SMT McAllen II LLC | North Mcallen 138 kV Substation (N_MCALLN, Bus#8368) | Hidalgo | SOUTH | 2026-05-31 | OTH | BA | 97.43 |  | 2022-10-04 | 2022-10-18 | 2023-01-13 | 2022-10-05 |  | No | 2023-07-31 | Yes | Not Required | Not Required | Not Required | 2023-08-08
24INR0437 | Umbra Solar II | SS Completed, FIS Started, No IA | Saddle House Solar Project, LLC | tap 345kV 1695 Monticello -11699 Woodard | Franklin | NORTH | 2026-04-16 | SOL | PV | 343.9 | COD | 2023-06-09 | 2023-06-28 | 2023-09-20 | 2023-05-23 |  |  |  | No |  |  | Not Required
24INR0438 | Umbra BESS II | SS Completed, FIS Started, No IA | Saddle House Solar Project, LLC | tap 345kV 1695 Monticello -11699 Woodard | Franklin | NORTH | 2026-09-07 | OTH | BA | 147.3 |  | 2023-06-09 | 2023-06-28 | 2023-09-20 | 2023-05-23 |  |  |  | No |  |  | Not Required
24INR0439 | Citrus Grove Energy Storage | SS Completed, FIS Started, No IA | SANTA ANA ENERGY STORAGE I LLC | 8354 Weslaco Switch 138kV | Hidalgo | SOUTH | 2026-01-01 | OTH | BA | 204.93 |  | 2022-10-03 | 2022-11-07 | 2023-02-04 | 2022-10-20 |  | No |  | No |  |  | Not Required
24INR0440 | Starling Solar Phase II | SS Completed, FIS Started, No IA | Starling Solar, LLC | tap 138kV 7224 Luling - 7245 Gonzales. Starling Solar Phase II is a an addition of 42.24MW to the 23INR0035 (solar) filed in 2020. 23INR0181 (storage) was filed in 2021. | Gonzales | SOUTH | 2025-05-09 | SOL | PV | 43.56 |  | 2023-06-21 | 2022-10-06 | 2022-12-28 |  |  |  |  | No |  |  | Not Required
24INR0442 | Midnight Sun Energy Storage | SS Completed, FIS Started, No IA | RES America Developments Inc. | 6601 Rio Pecos 138kV | Crockett | WEST | 2025-12-23 | OTH | BA | 510 |  | 2022-12-05 | 2022-12-07 | 2023-03-04 | 2022-11-18 |  | No |  | No |  |  | Not Required
24INR0443 | Hollow Branch Creek Storage SLF | SS Completed, FIS Completed, No IA | Hollow Branch Creek Solar LLC | Tap 345kV 3390 Jewett – 44645 Singleton | Madison | NORTH | 2025-12-31 | OTH | BA | 0 |  | 2022-10-07 | 2022-10-18 | 2023-01-15 | 2022-10-10 | 2023-03-28 | Yes |  | No |  |  | Not Required
24INR0444 | Hiru Storage | SS Completed, FIS Started, No IA | Hecate Energy Hazel LLC | Tap 345kV 6111 Riley - 1730 West Krum ckt 1 | Clay | WEST | 2026-08-01 | OTH | BA | 509 | FIS Request | 2023-12-22 | 2022-11-15 | 2023-02-10 |  |  |  |  | No |  |  | Not Required
24INR0445 | ASD Flores TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | TAP 138KV 8793 RIO GRANDE CITY - 8798 LAGRULLA | Starr | SOUTH | 2026-12-31 | OTH | BA | 200 | MW Size COD | 2023-10-01 | 2022-12-15 | 2023-03-13 |  |  |  |  | No | Not Required | Not Required | Not Required
24INR0446 | ASD Gongora Hill TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | Tap 138kV 8796 Roma – 7870 Escobares | Starr | SOUTH | 2026-12-31 | OTH | BA | 200 | MW Size COD | 2023-11-02 | 2023-02-27 | 2023-03-13 | 2022-11-22 |  |  |  | No | Not Required | Not Required | Not Required
24INR0447 | ASD Chihuahua TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | Tap 138kV 8392 Bates – 8394 Liston | Hidalgo | SOUTH | 2026-12-31 | OTH | BA | 200 | MW Size COD | 2023-09-25 | 2022-12-07 | 2023-03-06 |  |  |  |  | No | Not Required | Not Required | Not Required
24INR0448 | ASD Minnesota TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | Tap 138kV 8372 North Pharr – 8906 North Alamo | Hidalgo | SOUTH | 2026-12-31 | OTH | BA | 100 | FIS Request | 2023-08-21 | 2022-11-15 | 2023-02-09 |  |  |  |  | No | Not Required | Not Required | Not Required
24INR0449 | ASD Richardson TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc. | TAP 138KV 8374 SOUTH EAST EDINBURG - 8029 CLOSNER | Hidalgo | SOUTH | 2026-12-31 | OTH | BA | 100 | MW Size COD | 2023-09-28 | 2022-12-07 | 2023-03-06 |  |  |  |  | No | Not Required | Not Required | Not Required
24INR0450 | Smokey Willie BESS SLF | SS Completed, FIS Completed, No IA | Neches Solar, LLC | Tap 138kV 3325 Blackburn Switch – 3272 Palestine | Anderson | NORTH | 2026-03-13 | OTH | BA | 0 |  | 2022-11-11 | 2022-11-15 | 2023-02-09 | 2022-10-28 | 2023-09-22 | No |  | No |  |  | Not Required
24INR0452 | Longfellow Solar I | SS Completed, FIS Started, No IA | CENTURY GAS PROCESSING, LLC | 38431 TNCENTRY1_1 138 KV | Pecos | WEST | 2024-12-31 | SOL | PV | 178.2 |  | 2023-04-26 | 2022-11-07 | 2023-02-03 |  |  |  |  | No |  |  | Not Required
24INR0453 | Longfellow BESS I | SS Completed, FIS Started, No IA | CENTURY GAS PROCESSING, LLC | 38431 TNCENTRY1_1 138 KV | Pecos | WEST | 2024-12-31 | OTH | BA | 54.99 |  | 2023-04-25 | 2022-11-07 | 2023-02-03 |  |  |  |  | No |  |  | Not Required
24INR0454 | Longfellow Solar II | SS Completed, FIS Started, No IA | CENTURY GAS PROCESSING, LLC | 38432 TNCENTRY2_1 138 KV | Pecos | WEST | 2024-12-31 | SOL | PV | 207.36 |  | 2023-04-25 | 2022-11-07 | 2023-02-03 |  |  |  |  | No |  |  | Not Required
24INR0455 | Longfellow BESS II | SS Completed, FIS Started, No IA | CENTURY GAS PROCESSING, LLC | TNCENTRY2_1 (38432) 138 KV SUBSTATION | Pecos | WEST | 2024-12-31 | OTH | BA | 105.75 |  | 2023-04-26 | 2022-11-07 | 2023-02-03 |  |  |  |  | No |  |  | Not Required
24INR0456 | FRIENDSWOOD ENERGY GENCO | SS Completed, FIS Started, No IA | Tejas Power Generation LLC | 47170 H O CLARKE 138KV | Harris | HOUSTON | 2024-12-01 | GAS | GT | 143.7 |  | 2023-05-04 | 2022-12-07 | 2023-03-06 |  |  | No |  | No
24INR0458 | ORION BRANGUS STORAGE | SS Completed, FIS Started, No IA | ORION BESS | Tap 345kV 3687 BELL COUNTY EAST SWITCH - 39950 TNP ONE PLANT | Milam | SOUTH | 2024-08-30 | OTH | BA | 355.21 |  | 2022-11-04 | 2022-11-23 | 2023-02-17 | 2022-11-17 |  |  |  | No |  |  | Not Required
24INR0459 | Project Exodus (BESS) | SS Completed, FIS Started, No IA | Exodus Solar LLC | Tap 345kV 7040 Austrop – 7042 Zorn | Caldwell | SOUTH | 2025-12-12 | OTH | BA | 202.15 |  | 2023-06-30 | 2023-07-10 | 2023-10-05 | 2023-06-30 |  |  |  | No |  |  | Not Required
24INR0460 | Evelyn Battery Energy Storage System | SS Completed, FIS Started, IA | BRP Blue Topaz 4, LLC | Hidden Lakes 138kV (38900) | Galveston | HOUSTON | 2025-06-10 | OTH | BA | 451.98 |  | 2022-12-01 | 2023-01-03 | 2023-03-30 | 2022-12-08 |  |  | 2023-09-14 | No |  |  | Not Required
24INR0461 | Augie BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 5, LLC | 46560 Waller 138kV | Waller | HOUSTON | 2024-12-31 | OTH | BA | 200.81 |  | 2022-12-01 | 2023-01-23 | 2023-04-22 | 2023-01-18 |  | No |  | No |  |  | Not Required
24INR0462 | Ventana Ranch Solar | SS Completed, FIS Started, No IA | Monarch Energy Development LLC | Tap 345 kV Lone Hill (Bus# 8455) -- North Edinburg (Bus# 8905) | Jim Wells | SOUTH | 2024-12-01 | SOL | PV | 502.03 |  | 2022-11-10 | 2022-11-15 | 2023-02-10 | 2022-11-10 |  |  |  | No |  |  | Not Required
24INR0470 | McGee Solar | SS Completed, FIS Started, No IA | BT McGee Solar, LLC | Bus #6843 at Rayburn Barton Chapel Substation | Henderson | NORTH | 2024-12-31 | SOL | PV | 152.5 |  | 2022-11-09 | 2022-11-15 | 2023-02-09 | 2022-11-03 |  |  |  | No |  |  | Not Required
24INR0471 | McGee Storage | SS Completed, FIS Started, No IA | BT McGee Storage, LLC | Bus #6843 at Rayburn Barton Chapel Substation | Henderson | NORTH | 2026-05-29 | OTH | BA | 151.39 |  | 2022-11-10 | 2022-11-15 | 2023-02-09 | 2022-11-09 |  |  |  | No |  |  | Not Required
24INR0472 | Amador Storage | SS Completed, FIS Completed, IA | BT Amador Storage, LLC | 6833 Explorer Switching Station 138kV | Van Zandt | NORTH | 2024-12-31 | OTH | BA | 100.92 |  | 2022-11-15 | 2022-11-23 | 2023-02-17 | 2022-11-18 | 2023-10-23 | No | 2023-11-02 | No |  |  | Not Required
24INR0473 | Hooper Solar | SS Completed, FIS Started, No IA | BT Brown Solar, LLC | Tap 138kV line between Lexington (Bus #7571) and Lyle Wolz (Bus #7567) | Lee | SOUTH | 2025-05-15 | SOL | PV | 50.48 |  | 2022-12-01 | 2022-12-07 | 2023-03-06 | 2022-11-03 |  |  |  | No |  |  | Not Required
24INR0474 | Hooper Storage | SS Completed, FIS Started, No IA | BT Brown Solar, LLC | Tap 138kV line between Lexington (Bus #7571) and Lyle Wolz (Bus #7567) | Lee | SOUTH | 2025-05-15 | OTH | BA | 30.68 |  | 2022-11-23 | 2022-12-07 | 2023-03-06 | 2022-11-23 |  |  |  | No |  |  | Not Required
24INR0475 | DOS RIOS SOLAR SLF | SS Completed, FIS Started, No IA | DOS RIOS SOLAR, LLC | TAP 69 KV 61 BRANCHVILLE -- 65 SILVER CITY | Milam | SOUTH | 2025-10-22 | SOL | PV | 120.6 |  | 2023-03-29 | 2022-11-15 | 2023-02-11 |  |  |  |  | No |  |  | Not Required
24INR0476 | DOS RIOS ENERGY STORAGE SLF | SS Completed, FIS Started, No IA | DOS RIOS SOLAR, LLC | TAP 69 KV 61 BRANCHVILLE -- 65 SILVER CITY | Milam | SOUTH | 2025-10-22 | OTH | BA | 0 |  | 2023-03-29 | 2022-11-15 | 2023-02-11 |  |  |  |  | No |  |  | Not Required
24INR0477 | Barrett Solar | SS Completed, FIS Completed, IA | Barrett Solar Project, LLC | Tap 6869 SNYPT_RC - 6871 LNOK_RC 138kV line | Rains | NORTH | 2024-12-31 | SOL | PV | 127.5 | Status Change INA-to-PLN | 2022-11-30 | 2023-02-27 | 2023-05-26 | 2023-02-22 | 2023-10-02 | No | 2023-10-05 | No |  |  | Not Required
24INR0478 | Barrett Storage | SS Completed, FIS Started, No IA | BT Barrett Solar, LLC | Tap 138 kV 6869 SNYPT_RC - 6871 LNOK_RC Rayburn owned | Rains | NORTH | 2024-12-31 | OTH | BA | 76.5 |  | 2022-11-11 | 2022-12-07 | 2023-03-06 | 2022-12-05 |  |  |  | No |  |  | Not Required
24INR0479 | NRG THW GT 138 | SS Completed, FIS Started, No IA | NRG THW GT LLC | 138 kV Bus Number: 45515, Bus Name: T_H_W__POI_8 | Harris | HOUSTON | 2025-07-01 | GAS | GT | 458 |  | 2022-11-17 | 2022-11-22 | 2023-02-17 | 2022-11-17 |  |  |  | No | 2022-12-05
24INR0482 | NRG THW GT 345 | SS Completed, FIS Started, No IA | NRG THW GT LLC | 345 kV Bus Number: 45500, Bus Name: T_H_W__POI_5 | Harris | HOUSTON | 2025-07-01 | GAS | GT | 456 |  | 2022-11-16 | 2022-11-17 | 2023-02-09 | 2022-11-17 |  |  |  | No | 2022-12-05
24INR0484 | Lupinus Solar 3 | SS Completed, FIS Started, No IA | Lupinus Solar 2, LLC | 1794 Monticello Tap Substation 138 kV | Franklin | NORTH | 2026-09-21 | SOL | PV | 100.8 |  | 2023-09-13 | 2023-09-23 | 2023-12-20 | 2023-09-13 |  |  |  | No |  |  | Not Required
24INR0485 | Rutile BESS | SS Completed, FIS Started, No IA | Rutile BESS, LLC | Tap 138kV 6340 BALLINGER - 60399 WEISS | Runnels | WEST | 2025-12-31 | OTH | BA | 100.65 |  | 2023-05-10 | 2023-01-23 | 2023-04-22 |  |  | No |  | No |  |  | Not Required
24INR0488 | Forts Trail BESS 2 | SS Completed, FIS Started, No IA | JC Central Bluff, LLC | 11406 Central Bluff Switch 345 kV | Taylor | WEST | 2026-06-20 | OTH | BA | 201.2 |  | 2023-02-15 | 2023-02-20 | 2023-05-20 | 2023-02-01 |  |  |  | No |  |  | Not Required
24INR0490 | Lupinus Storage 3 | SS Completed, FIS Started, No IA | Lupinus Solar 2, LLC | 1794 Monticello Tap Substation 138 kV | Franklin | NORTH | 2026-09-21 | OTH | BA | 50.9 |  | 2023-01-23 | 2023-09-23 | 2023-12-20 | 2023-09-13 |  |  |  | No |  |  | Not Required
24INR0491 | Gunnar BESS | SS Completed, FIS Started, IA | BRP Blue Topaz 6, LLC | 8029 CLOSNER4A 138kV | Hidalgo | SOUTH | 2025-12-01 | OTH | BA | 203 |  | 2023-02-01 | 2023-02-09 | 2023-05-05 | 2023-01-30 |  |  | 2023-09-22 | Yes | Not Required | Not Required | Not Required
24INR0493 | Crowned Heron BESS 2 | SS Completed, FIS Started, No IA | RWE Renewables | WA Parish 345 kV Bus #44000 | Fort Bend | HOUSTON | 2024-12-15 | OTH | BA | 150 |  | 2022-11-22 | 2022-11-23 | 2023-02-17 | 2022-11-15 |  |  |  | No |  |  | Not Required
24INR0494 | Hana Springs BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II LLC | 7064 LAMPASAS 138KV | Lampasas | NORTH | 2025-05-31 | OTH | BA | 100.8 |  | 2022-11-22 | 2022-11-23 | 2023-02-17 | 2022-11-18 |  |  |  | No |  |  | Not Required
24INR0495 | Barbers Hill BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II | 40850 JORDAN 345kV | Chambers | HOUSTON | 2025-02-01 | OTH | BA | 307.72 |  | 2022-12-28 | 2023-01-17 | 2023-04-14 | 2022-12-27 |  | No |  | No |  |  | Not Required
24INR0496 | Indigo Storage | SS Completed, FIS Started, No IA | Indigo Storage | Tap 345kV 68001 Clayton 345kV - 68000 WShack Ckt 2 | Fisher | WEST | 2025-05-22 | OTH | BA | 50.08 |  | 2023-10-16 | 2022-12-15 | 2023-03-13 |  |  |  |  | No |  |  | Not Required
24INR0498 | Fort Watt Storage | SS Completed, FIS Started, No IA | Fort Watt Storage, LLC | Tap 138kV 1933 Kennedale - 2208 Mansfield | Tarrant | NORTH | 2026-03-01 | OTH | BA | 201.4 |  | 2022-12-30 | 2023-01-03 | 2023-03-30 | 2022-12-07 |  |  |  | No |  |  | Not Required
24INR0500 | Claire BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 3, LLC | 40011 Cedar Bayou 138kV | Harris | HOUSTON | 2024-12-31 | OTH | BA | 406.01 |  | 2023-01-30 | 2023-02-09 | 2023-05-08 | 2023-01-30 |  |  |  | No |  |  | Not Required
24INR0505 | Corralitos Wind 1 | SS Completed, FIS Started, No IA | Vaquero Wind Energy, LLC | Tap 345kV 80225 CENIZO7C - 80307 DELSOL7C (New ETT Tiempo Substation) | Zapata | SOUTH | 2025-03-31 | WIN | WT | 196.1 |  | 2023-01-24 | 2023-01-30 | 2023-04-28 | 2023-01-19 |  |  |  | No |  |  | Not Required
24INR0506 | Corralitos Wind 2 | SS Completed, FIS Started, No IA | Vaquero Wind Energy, LLC | Tap 345kV 80225 CENIZO7C - 80307 DELSOL7C (New ETT Tiempo Substation) | Zapata | SOUTH | 2024-12-31 | WIN | WT | 195.4 |  | 2023-01-24 | 2023-01-30 | 2023-04-28 | 2023-01-19 |  |  |  | No |  |  | Not Required
24INR0507 | Young Wind II SLF | SS Completed, FIS Started, No IA | Young Wind II, LLC | Oncor's Thomas Price Station (#11523) | Young | WEST | 2025-12-31 | WIN | WT | 152.28 |  | 2023-04-18 | 2023-05-03 | 2023-07-31 | 2023-04-26 |  |  |  | No |  |  | Not Required
24INR0508 | White Oak King Wind | SS Completed, FIS Started, No IA | White Oak Energy, LLC | To 345 kV Gauss ( Bus # 60701) | King | WEST | 2025-07-01 | WIN | WT | 606.5 |  | 2023-01-06 | 2023-03-09 | 2023-06-05 | 2023-02-07 |  | No |  | No |  |  | Not Required
24INR0514 | Rogers Draw BESS | SS Completed, FIS Started, No IA | Rocky Mountain Energy Development, LLC | 7751 Headwaters substation 138kV | Gillespie | SOUTH | 2025-12-31 | OTH | BA | 148.61 |  | 2023-01-10 | 2023-01-03 | 2023-03-30 |  |  |  |  | No |  |  | Not Required
24INR0516 | French Riviera Storage | SS Completed, FIS Started, No IA | Arana Creek Battery Storage LLC | 5646 Riviera Substation 69kV | Kleberg | COASTAL | 2024-12-01 | OTH | BA | 75 |  | 2023-01-24 | 2023-02-09 | 2023-05-05 | 2023-01-21 |  |  |  | No |  |  | Not Required
24INR0519 | Roost Energy Storage | SS Completed, FIS Started, No IA | Bluff Creek Energy Storage LLC | KNDRSACRC Bus #11130 to Knapp Substation Bus #1310 | Scurry | WEST | 2026-09-15 | OTH | BA | 102.36 |  | 2023-01-24 | 2023-01-30 | 2023-04-28 | 2023-01-21 |  |  |  | No |  |  | Not Required
24INR0528 | Blanquilla BESS | SS Completed, FIS Started, No IA | Blanquilla BESS LLC | Tap 138kV 8452 LON_HILL4A - 8441 NUECES_B4A Line is owned by LCRA TSC | Nueces | COASTAL | 2024-12-11 | OTH | BA | 200.78 |  | 2023-03-14 | 2023-02-09 | 2023-05-08 |  |  |  |  | No |  |  | Not Required
24INR0530 | Southside Energy | SS Completed, FIS Started, No IA | Southside Energy, LLC | Tap 138kV 42960 Mustang Bayou - 42652 Friendswood ckt 4 | Brazoria | COASTAL | 2026-06-15 | OTH | BA | 101.2 |  | 2023-11-01 | 2023-02-27 | 2023-05-26 |  |  |  |  | No |  |  | Not Required
24INR0531 | Battlefield Energy | SS Completed, FIS Started, No IA | Battlefield Energy, LLC | Tap 138kV Los Fresnos (8333) – Stillman (79601) | Cameron | COASTAL | 2025-09-15 | OTH | BA | 101.2 |  | 2023-11-16 | 2023-02-27 | 2023-05-26 |  |  |  |  | No |  |  | Not Required
24INR0532 | Timber Cove Solar | SS Completed, FIS Started, No IA | Freestone Solar, LLC | Tap 138 kV Winkler (Bus#212) to Pin Oak (Bus#3510) Transmission Line | Freestone | NORTH | 2026-09-24 | SOL | PV | 100.5 |  | 2023-05-02 | 2023-05-22 | 2023-08-17 | 2023-05-17 |  |  |  | No |  |  | Not Required
24INR0533 | Padua Grid BESS Unit 2 | SS Completed, FIS Started, No IA | Padua Grid, LLC | 5395 Sommers 138kV | Bexar | SOUTH | 2025-06-01 | OTH | BA | 154.63 | COD | 2023-05-30 | 2023-06-07 | 2023-09-01 | 2023-06-01 |  |  |  | No |  |  | Not Required
24INR0534 | Lyford Energy | SS Completed, FIS Started, No IA | Lyford Energy, LLC | 5745 E Raymondville 138kV | Willacy | COASTAL | 2025-09-15 | OTH | BA | 101.2 |  | 2023-11-07 | 2023-03-08 | 2023-06-05 |  |  |  |  | No |  |  | Not Required
24INR0538 | FLIFER Solar I | SS Completed, FIS Started, No IA | FLIFER LLC | 1091 WARDGULF_8 138kV | Ward | WEST | 2026-09-22 | SOL | PV | 79.2 |  | 2023-05-08 | 2023-03-08 | 2023-06-01 |  |  |  |  | No |  |  | Not Required
24INR0541 | Kinney County Energy | SS Completed, FIS Started, No IA | Kinney County Energy, LLC | Tap 138kV 8252 Brackett4A - 78255 L_PINTCR8_1Y | Kinney | SOUTH | 2025-09-15 | OTH | BA | 101.2 |  | 2023-11-10 | 2023-03-27 | 2023-06-19 |  |  |  |  | No |  |  | Not Required
24INR0543 | Thomas Cameron BESS | SS Completed, FIS Started, No IA | Thomas Cameron BESS | Tap 345kV 3424 BUCKHORN SWITCH - 3422 KILLEEN SWITCH | Lampasas | NORTH | 2026-07-01 | OTH | BA | 200.82 |  | 2023-06-01 | 2023-06-07 | 2023-09-01 | 2023-06-02 |  |  |  | No |  |  | Not Required
24INR0544 | Wetzel BESS | SS Completed, FIS Started, No IA | Brown ESS, LLC | Tap 138kV 1654 Zephyr – 1655 Brownwood Switch | Brown | NORTH | 2026-09-15 | OTH | BA | 185.57 |  | 2023-03-14 | 2023-03-27 | 2023-06-20 | 2023-03-15 |  |  |  | No |  |  | Not Required
24INR0550 | Mercedes II BESS | SS Completed, FIS Started, No IA | SMT Mercedes II, LLC | TAP NORTH MERCEDES (BUS #8358) and NORTH WESLACO (BUS# 8357) | Hidalgo | SOUTH | 2025-10-09 | OTH | BA | 227.87 |  | 2023-04-28 | 2023-05-15 | 2023-08-11 | 2023-05-08 |  |  |  | No |  |  | Not Required
24INR0555 | Shaula I BESS | SS Completed, FIS Started, No IA | Shaula Energy Project LLC | 5380 Shaula 345kV | DeWitt | SOUTH | 2025-12-31 | OTH | BA | 86.88 |  | 2023-05-19 | 2023-07-10 | 2023-10-05 | 2023-07-03 |  |  |  | No |  |  | Not Required
24INR0557 | Hovey Energy Storage | SS Completed, FIS Started, No IA | Barilla Solar, LLC | 60385 Solstice 138kV | Pecos | WEST | 2024-12-31 | OTH | BA | 23 |  | 2023-06-29 | 2023-07-10 | 2023-10-02 | 2023-06-15 |  |  |  | No |  |  | Not Required
24INR0558 | Parthenon Energy | SS Completed, FIS Started, No IA | Parthenon Energy, LLC | Tap 138kV 88380 RGTAP4A - 8896 RACHAL4A | Hidalgo | SOUTH | 2026-06-15 | OTH | BA | 101.2 | COD | 2023-10-31 | 2023-04-19 | 2023-07-14 |  |  |  |  | No | Not Required | Not Required | Not Required
24INR0559 | Nerva Energy Storage | SS Completed, FIS Started, No IA | Nerva Energy Storage, LLC | Tap 138kV 402410 BURKE_POI_8 - 42430 EGLNST_POI_8 CKT#02 | Brazoria | COASTAL | 2026-06-15 | OTH | BA | 101.2 |  | 2023-10-30 | 2023-04-19 | 2023-07-14 |  |  |  |  | No | Not Required | Not Required | Not Required
24INR0567 | Wolf Hollow III | SS Completed, FIS Started, No IA | Wolf Hollow II Power LLC | Mitchell Bend 345KV Bus #1877 | Hood | NORTH | 2024-11-29 | GAS | GT | 306.32 |  | 2023-05-18 | 2023-06-07 | 2023-09-01 | 2023-05-30 |  |  |  | No
24INR0568 | Shamrock Energy Storage (SLF) | SS Completed, FIS Started, No IA | Shamrock Interconnection LLC | 76004 Single Tree 345kV | Crockett | WEST | 2025-07-01 | OTH | BA | 0 |  | 2023-07-02 | 2023-07-18 | 2023-10-15 | 2023-07-11 |  |  |  | No |  |  | Not Required
24INR0569 | Hadrian Energy Storage | SS Completed, FIS Started, No IA | Hadrian Energy Storage, LLC | Line Tap 138kV #43012 NEWGLF60T3_8 - #43190 S_LANE_B138 | Wharton | SOUTH | 2026-06-15 | OTH | BA | 101.2 |  | 2023-11-07 | 2023-05-15 | 2023-08-11 |  |  |  |  | No |  |  | Not Required
24INR0570 | Marcus Energy Storage | SS Completed, FIS Started, No IA | Marcus Energy Storage, LLC | Tap 138kV 39500 West Columbia Main - 110505 Sweeny Co-Gen LP Ckt 1 | Brazoria | COASTAL | 2025-09-01 | OTH | BA | 201.04 |  | 2023-10-31 | 2023-06-07 | 2023-09-01 |  |  |  |  | No |  |  | Not Required
24INR0572 | Harlingen III BESS | SS Completed, FIS Started, No IA | SMT Harlingen III LLC | 8320 WEST HARLINGEN 69kV | Cameron | COASTAL | 2026-08-15 | OTH | BA | 110 |  | 2023-06-27 | 2023-06-28 | 2023-09-20 | 2023-06-26 |  |  |  | No |  |  | Not Required
24INR0576 | Boling Generation | SS Started, FIS Started, No IA | Boling Generation | 43340 Gulftie 138kV | Wharton | SOUTH | 2025-05-15 | GAS | GT | 380 |  | 2023-10-11 | 2023-12-04 |  | 2023-11-02 |  |  |  | No
24INR0578 | Panther Creek 1 Repower | SS Completed, FIS Started, No IA | Panther Creek Wind Farm I&II, LLC | 1058 Longshore 345kV | Glasscock | WEST | 2024-05-31 | WIN | WT | 11.4 |  | 2023-06-27 | 2023-06-28 | 2023-09-21 | 2023-06-21 |  |  |  | No |  |  | Not Required
24INR0582 | Panther Creek 2 Repower | SS Completed, FIS Started, No IA | Panther Creek Wind Farm I&II, LLC | Longshore 345kV [Bus# 1058] | Glasscock | WEST | 2024-05-04 | WIN | WT | 9.24 |  | 2023-06-27 | 2023-06-28 | 2023-09-21 | 2023-06-27 |  |  |  | No |  |  | Not Required
24INR0584 | Houston IV BESS | SS Completed, FIS Started, No IA | SMT Houston IV LLC | 44140 CLODINE 138kV | Harris | HOUSTON | 2027-07-01 | OTH | BA | 168.6 |  | 2023-06-30 | 2023-07-10 | 2023-10-05 | 2023-06-27 |  |  |  | No |  |  | Not Required
24INR0589 | Antoninus Energy Storage | SS Completed, FIS Started, No IA | Antoninus Energy Storage, LLC | Tap 138kV #43190 S_LANE_B138 - #42985 DYANN_POI_8 Transmission Line. | Wharton | SOUTH | 2026-06-15 | OTH | BA | 101.2 |  | 2023-11-02 | 2023-06-28 | 2023-09-24 |  |  |  |  | No | Not Required | Not Required | Not Required
24INR0605 | TEXAS GULF SULPHUR REPOWER | SS Completed, FIS Started, IA | Wharton County Generation, LLC | 43340 Gulftie 138 kV | Wharton | SOUTH | 2024-05-18 | GAS | GT | 94 |  | 2023-07-22 | 2023-07-31 | 2023-10-27 | 2023-07-27 |  |  | 2022-03-01 | No
24INR0609 | Rodeo Ranch Energy Storage II | SS Completed, FIS Completed, IA | Rodeo Ranch Energy Storage, LLC | 38021 WORSHAM 138kV | Reeves | WEST | 2024-04-16 | OTH | BA | 10 | COD | 2023-10-16 | 2023-08-22 | 2021-11-18 | 2023-10-12 | 2022-07-28 |  | 2022-02-01 | Yes | Not Required | Not Required | Not Required | 2022-07-28 | 2022-07-28 | 2022-07-28
24INR0616 | GridGuardian BESS | SS Completed, FIS Started, No IA | SMT Temple BESS LLC | 3412 TEMPLE PECAN CREEK 345kV | Bell | NORTH | 2027-04-19 | OTH | BA | 227.99 |  | 2023-09-08 | 2023-09-22 | 2023-12-14 | 2023-09-11 |  |  |  | No | Not Required | Not Required | Not Required
24INR0617 | Serrano Storage | SS Completed, FIS Started, No IA | Maverick ESS, LLC | 8267 GANSO Substation 138kV | Maverick | SOUTH | 2026-12-01 | OTH | BA | 185.59 | COD | 2023-09-11 | 2023-09-23 | 2023-12-20 | 2023-08-31 |  |  |  | No | Not Required | Not Required | Not Required
24INR0627 | Champion Wind Repower | SS Completed, FIS Started, No IA | Champion Wind Farm, LLC | Bus# 1048 - Tonkawa | Nolan | WEST | 2024-12-20 | WIN | WT | 0.31 |  | 2023-09-13 | 2023-09-25 | 2023-12-21 | 2023-09-13 |  |  |  | No | Not Required | Not Required | Not Required
24INR0629 | Jade Storage SLF | SS Started, FIS Started, No IA | IP Renewable Energy Holdings LLC | 345 kV MHOS (Bus# 59911) | Scurry | WEST | 2024-09-30 | OTH | BA | 0 |  | 2023-10-31 | 2023-11-14 |  | 2023-11-01 |  |  |  | No |  |  | Not Required
24INR0630 | Andromeda Storage SLF | SS Started, FIS Started, No IA | IP Renewable Energy Holdings LLC | 60011 Nebulast 345kV | Scurry | WEST | 2024-09-30 | OTH | BA | 0 |  | 2023-10-22 | 2023-10-25 |  | 2023-10-17 |  |  |  | No |  |  | Not Required
24INR0631 | Radian Storage SLF | SS Started, FIS Started, No IA | IP Radian BESS, LLC. | 345 kV Brown Switch (Bus# 1444) | Brown | NORTH | 2026-02-01 | OTH | BA | 0 | COD | 2023-10-23 | 2023-10-25 |  | 2023-10-17 |  |  |  | No | Not Required | Not Required | Not Required
24INR0632 | Cedro Hill Wind Repower | SS Completed, FIS Completed, IA | CEDRO HILL WIND LLC | 80439 LA QUINTA 138kV | Webb | SOUTH | 2024-12-28 | WIN | WT | 9.93 |  | 2023-09-29 | 2023-09-28 | 2023-12-20 | 2023-09-28 | 2023-11-22 |  | 2009-09-09 | Yes |  |  | Not Required
24INR0635 | Ebony Energy Storage II | SS Completed, FIS Started, No IA | Ebony Energy Storage, LLC | 5180 Green Mountain 138kV | Comal | SOUTH | 2024-04-29 | OTH | BA | 5 |  | 2023-10-26 | 2021-02-04 | 2021-04-21 | 2023-10-26 |  |  |  | No |  |  | Not Required
24INR0636 | Anemoi Energy Storage II | SS Started, FIS Started, No IA | Anemoi Energy Storage, LLC | 8574 POMELO 345kV | Hidalgo | SOUTH | 2024-05-14 | OTH | BA | 5 |  | 2023-10-23 | 2023-10-30 |  | 2023-10-23 |  |  |  | No |  |  | Not Required
24INR0643 | Arroyo Storage (Placeholder) | SS Started, FIS Started, No IA | BT Cantwell Solar, LLC | 8704 Gulch 345kV | Cameron | COASTAL | 2024-11-30 | OTH | BA | 35.25 | FIS Request | 2023-12-13 |  |  | 2023-12-18 |  |  |  | No |  |  | Not Required
25INR0002 | Barcelona TxHSR TPSS HN-4 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 45885 HocklyC - 46220 Peters | Harris | HOUSTON | 2028-07-15 | OTH | OT | 50 |  | 2019-10-11 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  | No |  | No | Not Required | Not Required
25INR0005 | Tokyo TxHSR TPSS EW-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2241 Ennis W - 2321 Waxahachie | Ellis | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-09-13 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  |  |  | No | Not Required | Not Required
25INR0006 | Atlanta TxHSR TPSS DS-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2429 Watermill E - 3083 Wilmer | Dallas | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-10-11 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  |  |  | No | Not Required | Not Required
25INR0008 | BasRanch | SS Completed, FIS Started, No IA | CPV Basin Ranch, LLC | tap 345kV Riverton Switch - Sand Lake Switch, CKT02 | Reeves | WEST | 2028-03-01 | GAS | CC | 1350 |  | 2021-11-24 | 2020-08-04 | 2020-11-02 | 2021-10-28 |  |  |  | No
25INR0010 | Nockenut Springs Solar 3 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Gonzales | SOUTH | 2025-12-31 | SOL | PV | 203.39 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No |  |  | Not Required
25INR0012 | Alamosa Solar | SS Completed, FIS Started, No IA | Alamosa Solar LLC | 6100 Oklaunion 345kV | Wilbarger | WEST | 2025-01-01 | SOL | PV | 209.48 |  | 2021-08-19 | 2020-12-03 | 2021-02-17 | 2021-08-13 |  | No |  | No |  |  | Not Required
25INR0018 | Yellow Cat Wind | SS Completed, FIS Started, No IA | STEELHEAD WIND 2 LLC | Tap 345kV 1906 Venus - 68091 Navarro | Navarro | NORTH | 2026-03-31 | WIN | WT | 300 |  | 2022-03-18 | 2021-08-17 | 2021-11-05 | 2022-03-07 |  | No |  | No | Not Required | Not Required | Not Required
25INR0021 | Findley Solar | SS Completed, FIS Started, No IA | Gransolar Texas Sixteen, LLC | 107 Prairie Hill 69 kV | Limestone | NORTH | 2028-01-01 | SOL | PV | 50.34 |  | 2022-07-05 | 2021-10-05 | 2021-12-10 | 2022-05-24 |  |  |  | No |  |  | Not Required
25INR0022 | Alamosa Storage | SS Completed, FIS Started, No IA | Alamosa BESS West, LLC | 6100 Oklaunion 345kV | Wilbarger | WEST | 2025-01-01 | OTH | BA | 207.21 |  | 2021-10-06 | 2021-10-06 | 2021-12-13 | 2021-10-05 |  | No |  | No |  |  | Not Required
25INR0024 | Itsee Solar | SS Completed, FIS Started, No IA | Gransolar Texas Seventeen, LLC | Tap 138kV Trinidad Ses (Bus number 3127) to Goodloe Switch (Bus number 3483) | Navarro | NORTH | 2025-08-27 | SOL | PV | 53.31 |  | 2022-07-05 | 2021-10-12 | 2022-01-03 | 2022-05-24 |  |  |  | No |  |  | Not Required
25INR0029 | Whistle Solar | SS Completed, FIS Started, No IA | Gransolar Texas Nineteen, LLC | Tap 138kV 213 Haney – 3478 Navarro | Navarro | NORTH | 2026-05-30 | SOL | PV | 56.3 |  | 2022-08-10 | 2021-11-23 | 2022-02-18 | 2022-08-05 |  |  |  | No |  |  | Not Required
25INR0039 | Borderland ESC | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | 8368 McAllen 138kV (N_MCALLN4A) | Hidalgo | SOUTH | 2026-06-30 | OTH | BA | 200 | COD | 2022-02-08 | 2022-02-21 | 2022-05-22 | 2022-02-08 |  |  |  | No |  |  | Not Required
25INR0040 | McMEXICO STORAGE | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | 8644 Trade Zone 138kV | Hidalgo | SOUTH | 2026-06-30 | OTH | BA | 201.9 | COD | 2022-01-28 | 2022-02-28 | 2022-05-27 | 2022-02-15 |  | No |  | No | Not Required | Not Required | Not Required
25INR0045 | Smith Lake Storage | SS Completed, FIS Started, No IA | Smith Lake Solar | Tap 345kV 44645 Singleton - 44900 Zenith Ckt #99 | Grimes | NORTH | 2026-11-30 | OTH | BA | 65 |  | 2022-11-30 | 2022-03-07 | 2022-05-06 | 2022-11-02 |  |  |  | No |  |  | Not Required
25INR0046 | Ash Creek BESS | SS Completed, FIS Started, No IA | ACTX BESS Project LLC | 68090 SAM SW 345kV | Hill | NORTH | 2025-03-15 | OTH | BA | 309 |  | 2022-04-02 | 2022-05-10 | 2022-08-06 | 2022-04-15 |  |  |  | No |  |  | Not Required
25INR0049 | Point Mountain Solar | SS Completed, FIS Started, No IA | Hecate Energy Point Mountain Solar Facility LLC | Tap 345kV 11028 Odessa Ehv Switch - 842 King Mountain Switch | Upton | WEST | 2026-12-15 | SOL | PV | 514 |  | 2022-02-15 | 2022-07-18 | 2022-10-14 | 2022-02-24 |  |  |  | No |  |  | Not Required
25INR0052 | SanPat Solar | SS Completed, FIS Started, IA | Padre Solar LLC | Tap 345kV 8249 Angstrom – 8659 Naismith | San Patricio | COASTAL | 2025-07-01 | SOL | PV | 256.23 |  | 2022-07-29 | 2022-02-28 | 2022-05-27 | 2022-07-15 |  | Yes | 2023-10-18 | Yes |  |  | Not Required
25INR0054 | Sandman Power Storage | SS Completed, FIS Started, No IA | ALPIN HOLDING LLC | 1685 Farmersville Switch 345kV | Collin | NORTH | 2026-03-01 | OTH | BA | 100 | COD | 2022-03-14 | 2022-03-21 | 2022-06-16 | 2022-03-14 |  |  |  | No |  |  | Not Required
25INR0055 | Three W Solar | SS Completed, FIS Completed, IA | Three W Solar Project LLC | tap 138kV 3522 Hillboro1_8 - 237 Blanton CKT 1 | Hill | NORTH | 2025-06-01 | SOL | PV | 111.6 |  | 2022-02-25 | 2022-03-07 | 2022-06-02 | 2022-02-28 | 2023-01-04 |  | 2023-03-28 | Yes |  |  | Not Required
25INR0057 | Sombrero Solar | SS Completed, FIS Started, No IA | Aurora Solar LLC | Tap 345kV 76003 Big Hill - 60708 Orsted | Schleicher | WEST | 2026-05-31 | SOL | PV | 351.85 |  | 2023-01-23 | 2022-03-30 | 2022-06-26 | 2023-01-03 |  |  |  | No | Not Required | Not Required | Not Required
25INR0060 | Argenta Solar | SS Completed, FIS Started, No IA | National Grid Renewables Projects, LLC | Tap 345kV 8689 Tango - 8606 Goddard | Bee | SOUTH | 2026-07-01 | SOL | PV | 325 |  | 2022-07-27 | 2022-06-27 | 2022-09-21 | 2022-07-14 |  |  |  | No |  |  | Not Required
25INR0061 | Argenta Storage | SS Completed, FIS Started, No IA | National Grid Renewables Projects, LLC | Tap 345kV 8689 Tango - 8606 Goddard | Bee | SOUTH | 2026-07-01 | OTH | BA | 162 |  | 2022-07-21 | 2022-06-27 | 2022-09-21 | 2022-07-13 |  |  |  | No |  |  | Not Required
25INR0068 | High Chap Solar | SS Completed, FIS Started, No IA | HIGH CHAPARRAL SOLAR PROJECT LLC | 43035 Oasis 345kV - 42500 Dow Chemical 345 kV Ckt 18 | Brazoria | COASTAL | 2027-08-04 | SOL | PV | 152.25 |  | 2022-07-05 | 2022-07-05 | 2022-10-01 | 2022-06-17 |  | Yes |  | No |  |  | Not Required
25INR0070 | Albatross Solar | SS Completed, FIS Started, No IA | Albatross Solar, LLC | Tap 138kV 165 Windsor Switch - 161 McGregor | McLennan | NORTH | 2025-06-01 | SOL | PV | 101 |  | 2022-12-08 | 2022-05-16 | 2022-08-13 | 2022-10-25 |  |  |  | No |  |  | Not Required
25INR0071 | Albatross BESS | SS Completed, FIS Started, No IA | Albatross Solar, LLC | From Bus #165 Windsor Switch To Bus #161 McGregor | McLennan | NORTH | 2025-06-01 | OTH | BA | 50.4 |  | 2023-01-27 | 2022-05-16 | 2022-08-13 | 2022-10-25 |  |  |  | No |  |  | Not Required
25INR0072 | High Chap Storage | SS Completed, FIS Started, No IA | HIGH CHAPARRAL SOLAR PROJECT LLC | 43035 Oasis 345kV - 42500 Dow Chemical 345 kV Ckt 18 | Brazoria | COASTAL | 2027-08-04 | OTH | BA | 71.78 |  | 2022-07-21 | 2022-07-25 | 2022-10-21 | 2022-07-07 |  | Yes |  | No |  |  | Not Required
25INR0073 | Saltillo Storage | SS Completed, FIS Started, No IA | SALTILLO STORAGE | 7331 Cedarhill Substation 138kV | Bastrop | SOUTH | 2025-06-01 | OTH | BA | 101 |  | 2022-05-10 | 2022-05-10 | 2022-08-05 | 2022-04-25 |  |  |  | No |  |  | Not Required
25INR0076 | Violet Storage | SS Completed, FIS Started, No IA | VIOLET STORAGE | McKenzie Road (8858) 138 kV Substation | Nueces | COASTAL | 2026-07-01 | OTH | BA | 151 |  | 2022-04-13 | 2022-05-10 | 2022-08-06 | 2022-04-14 |  | No |  | No |  |  | Not Required
25INR0078 | Peregrine BESS 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 8673 RAPTOR7A 345kV | Goliad | SOUTH | 2025-05-01 | OTH | BA | 150 |  | 2022-08-15 | 2022-08-05 | 2022-11-01 | 2022-08-02 |  |  |  | No |  |  | Not Required
25INR0079 | Sunlight Solar | SS Completed, FIS Started, No IA | DG Penwell North | Tap 138kV 11293 Red Lakes Switch – 1292 Moss Switch | Ector | WEST | 2027-03-31 | SOL | PV | 203 |  | 2022-06-02 | 2022-06-10 | 2022-09-06 | 2022-06-01 |  |  |  | No | Not Required | Not Required | Not Required
25INR0080 | Meitner Solar | SS Completed, FIS Started, No IA | IP Meitner, LLC | 345 kV Gray (Bus# 79000) | Gray | PANHANDLE | 2026-09-30 | SOL | PV | 702.64 |  | 2022-07-26 | 2022-08-05 | 2022-11-01 | 2022-07-27 |  | Yes |  | No |  |  | Not Required
25INR0081 | SanPat Solar II | SS Completed, FIS Started, IA | CGRP 04, LLC | Tap 345kV 8249 Angstrom – 8659 Naismith | San Patricio | COASTAL | 2025-07-01 | SOL | PV | 308.88 |  | 2022-07-29 | 2022-07-18 | 2022-10-12 | 2022-07-15 |  | Yes | 2023-10-18 | Yes |  |  | Not Required
25INR0082 | Reis Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Reis LLC | Tapping into 138 kV line (5689) Choke Canyon AEP to (5902) San Miguel Gen | Atascosa | SOUTH | 2025-10-15 | SOL | PV | 105.48 |  | 2022-09-19 | 2022-06-02 | 2022-08-29 | 2022-09-09 |  |  |  | No |  |  | Not Required
25INR0087 | Capoterra | SS Completed, FIS Started, No IA | 206OF 8me LLC | Tap 345kV 39950 TNP One – 3687 East Bell County Ckt 1 | Milam | SOUTH | 2026-05-19 | SOL | PV | 598 |  | 2023-04-12 | 2022-06-17 | 2022-09-12 |  |  |  |  | No |  |  | Not Required
25INR0088 | Capoterra BESS | SS Completed, FIS Started, No IA | 206OF 8me LLC | Tap 345kV 39950 TNP One – 3687 East Bell County Ckt 1 | Milam | SOUTH | 2026-05-19 | OTH | BA | 600 |  | 2023-04-12 | 2022-06-17 | 2022-09-12 |  |  |  |  | No |  |  | Not Required
25INR0097 | Soleil Solar | SS Completed, FIS Started, No IA | Soleil Solar, LLC | Tap 345 kV 1730 Krum West Switch - 6111 Riley ckt 2 | Clay | WEST | 2026-03-30 | SOL | PV | 728.72 |  | 2022-08-31 | 2022-09-02 | 2022-11-29 | 2022-08-26 |  |  |  | No |  |  | Not Required
25INR0098 | Soleil Storage | SS Completed, FIS Started, No IA | Soleil Solar, LLC | Tap 345 kV 1730 Krum West Switch - 6111 Riley ckt 2 | Clay | WEST | 2026-03-30 | OTH | BA | 301.64 |  | 2022-08-31 | 2022-09-02 | 2022-11-29 | 2022-08-30 |  |  |  | No |  |  | Not Required
25INR0100 | Goldeneye BESS | SS Completed, FIS Completed, No IA | Black Mountain Energy Storage II | 3423 KILLEEN Switch 138 KV | Bell | NORTH | 2026-02-01 | OTH | BA | 201.6 |  | 2022-08-03 | 2022-06-10 | 2022-09-06 | 2022-07-13 | 2023-08-18 | No |  | No | Not Required | Not Required | Not Required
25INR0101 | Mallard BESS | SS Completed, FIS Started, No IA | North Texas Energy Storage LLC | 818 Olinger 138kV | Collin | NORTH | 2025-02-17 | OTH | BA | 154.42 |  | 2022-06-22 | 2022-06-02 | 2022-08-29 | 2022-06-17 |  |  |  | No | Not Required | Not Required | Not Required
25INR0102 | Austin Bayou Solar | SS Completed, FIS Completed, No IA | Austin Bayou Solar, LLC | Tap 345kV 42500 DOW CHEMICAL - 43035 OASIS CKT#27 | Brazoria | COASTAL | 2025-02-04 | SOL | PV | 753.4 |  | 2022-08-15 | 2022-06-27 | 2022-09-21 | 2022-07-26 | 2023-03-29 | No |  | No |  |  | Not Required
25INR0103 | Elio BESS | SS Completed, FIS Started, No IA | Elio Energy LLC | Tap 138kV 42980 Nash - 44010 Wa Parish circuit 02 | Brazoria | COASTAL | 2026-12-02 | OTH | BA | 317.2 |  | 2023-05-19 | 2022-07-05 | 2022-10-01 |  |  |  |  | No |  |  | Not Required
25INR0104 | Elio Solar | SS Completed, FIS Started, No IA | Elio Energy LLC | Tap 138kV 42980 Nash - 44010 Wa Parish CKt 02 | Brazoria | COASTAL | 2025-07-02 | SOL | PV | 160.64 |  | 2022-07-27 | 2022-08-05 | 2022-11-01 | 2022-07-13 |  |  |  | No |  |  | Not Required
25INR0105 | Diver Solar | SS Completed, FIS Completed, IA | Diver Solar | Tap 345kV 3384 St Johns - 3390 Jewett | Limestone | NORTH | 2026-06-30 | SOL | PV | 228.16 |  | 2022-06-23 | 2022-09-02 | 2022-11-29 | 2022-06-28 | 2023-07-26 | No | 2023-10-27 | Yes | Not Required | Not Required | Not Required | 2023-11-13
25INR0106 | Luthor Solar | SS Completed, FIS Started, No IA | TREX US Luthor LLC | Tap 138kV 23831 Luther Station – 10032 Little Luther | Howard | WEST | 2026-09-05 | SOL | PV | 101 |  | 2023-05-10 | 2022-06-27 | 2022-09-21 |  |  |  |  | No |  |  | Not Required
25INR0109 | Sun Cactus Solar | SS Completed, FIS Started, IA | Sun Cactus Solar Project, LLC | tap 138kV 8510 Falfurrias - 8695 Crestonio | Duval | SOUTH | 2026-08-31 | SOL | PV | 120.63 |  | 2022-06-17 | 2022-07-05 | 2022-10-01 | 2022-06-20 |  |  | 2023-11-06 | Yes |  |  | Not Required
25INR0112 | August Draw Energy | SS Completed, FIS Started, No IA | DBR Solar, LLC | Tap 138kV 60207 Verhalen – 60808 Hoefs Road | Reeves | WEST | 2026-02-01 | SOL | PV | 250 |  | 2023-06-22 | 2022-09-15 | 2022-12-13 |  |  |  |  | No |  |  | Not Required
25INR0122 | Vial BESS | SS Completed, FIS Started, No IA | Gransolar Texas Eleven LLC | Chatt(234) - Pecan Street (3352) 138kV | Hill | NORTH | 2026-07-15 | OTH | BA | 141.39 |  | 2023-04-03 | 2022-07-05 | 2022-10-01 |  |  |  |  | No |  |  | Not Required
25INR0129 | Demeter Solar | SS Completed, FIS Started, No IA | Demeter Solar, LLC | Transmission Line (From Bus #7224 LULING- To Bus #7216 LOCKHART) | Caldwell | SOUTH | 2026-03-28 | SOL | PV | 88 |  | 2023-03-17 | 2022-08-05 | 2022-11-01 |  |  |  |  | No |  |  | Not Required
25INR0130 | Demeter Storage | SS Completed, FIS Started, No IA | Demeter Solar, LLC | Tapping the Transmission Line (From Bus #7224 LULING - Bus #7216 LOCKHART) | Caldwell | SOUTH | 2026-03-28 | OTH | BA | 65 |  | 2023-03-17 | 2022-08-05 | 2022-11-01 |  |  |  |  | No |  |  | Not Required
25INR0131 | SOSA Storage | SS Completed, FIS Completed, IA | SOSA Energy Center LLC | Tap 138kV 25 North Zulch - 47 Hilltop Lakes | Madison | NORTH | 2026-03-31 | OTH | BA | 150.54 | SFS/NtP | 2022-07-21 | 2022-07-25 | 2022-10-20 | 2022-07-21 | 2023-09-21 | No | 2023-12-05 | Yes |  |  | Not Required
25INR0133 | Rose Quartz BESS | SS Completed, FIS Started, No IA | Rose Quartz BESS, LLC | Tap 138kV 8283 Asherton - 8613 Bigwells | Dimmit | SOUTH | 2025-11-01 | OTH | BA | 101.41 |  | 2022-10-27 | 2022-09-02 | 2022-11-30 | 2022-10-14 |  |  |  | No | Not Required | Not Required | Not Required
25INR0134 | Hoskins Solar | SS Completed, FIS Started, No IA | SGT HOSKINS SOLAR PROJECT, LLC | TAP 138 kV 1687 BLOSSOM_T8 - 1771 LAMARBM1_8 | Lamar | NORTH | 2026-08-31 | SOL | PV | 204.12 |  | 2023-08-10 | 2022-10-24 | 2023-01-20 |  |  |  |  | No |  |  | Not Required
25INR0135 | Hayrick BESS | SS Completed, FIS Started, No IA | Gransolar Texas Five LLC | 6351 Nicole 138kV | Coke | WEST | 2027-02-15 | OTH | BA | 113.9 |  | 2023-05-31 | 2022-08-16 | 2022-11-11 |  |  |  |  | No |  |  | Not Required
25INR0138 | Champaign BESS | SS Completed, FIS Started, No IA | Champaign BESS, LLC | Tap 138kV Shaw POD (18664) – Desert Wind Sub (11222) | Glasscock | WEST | 2026-09-14 | OTH | BA | 201.13 |  | 2022-12-30 | 2022-09-21 | 2022-12-19 |  |  |  |  | No |  |  | Not Required
25INR0139 | Dolce BESS | SS Completed, FIS Started, No IA | Dolce BESS, LLC | Tap 138kV 1189 BARBER_LK1_8 - 19520 CHINAGRVX2_8 | Mitchell | WEST | 2026-04-21 | OTH | BA | 100.65 |  | 2023-03-30 | 2022-09-27 | 2022-12-21 |  |  |  |  | No |  |  | Not Required
25INR0140 | Seragio BESS | SS Completed, FIS Started, No IA | Seragio BESS, LLC | 11140 ECTRCNTYN_8 138kV | Ector | WEST | 2026-04-21 | OTH | BA | 201.13 |  | 2022-12-27 | 2022-09-15 | 2022-12-13 |  |  |  |  | No |  |  | Not Required
25INR0141 | Fairgreen BESS | SS Completed, FIS Started, No IA | Fairgreen BESS, LLC | Tap 138kV 1322 BIGSPRIG_8 - 11351 HILLCREST_8 | Howard | WEST | 2026-09-14 | OTH | BA | 201.13 |  | 2023-02-01 | 2022-09-15 | 2022-12-13 |  |  |  |  | No |  |  | Not Required
25INR0142 | Sagewood BESS | SS Completed, FIS Started, No IA | Sagewood BESS, LLC | Tap 138kV McDonald Road Switch (bus #1333) – Desert Wind Sub (bus #11282) | Glasscock | WEST | 2026-09-14 | OTH | BA | 100.57 |  | 2022-12-30 | 2022-09-21 | 2022-12-19 |  |  |  |  | No |  |  | Not Required
25INR0143 | Ariji BESS | SS Completed, FIS Started, No IA | Ariji BESS, LLC | Tap 138kV 1394 GTTYVTAP_8 - 1322 BIGSPRIG_8 | Howard | WEST | 2026-09-14 | OTH | BA | 100.32 |  | 2023-06-19 | 2022-09-15 | 2022-12-13 |  |  |  |  | No |  |  | Not Required
25INR0144 | Jasper BESS | SS Completed, FIS Started, No IA | Jasper BESS, LLC | Tap 138kV 71230 Pleasant Farms - 1236 Pegasus South | Midland | WEST | 2026-09-14 | OTH | BA | 201.13 |  | 2023-04-03 | 2022-09-21 | 2022-12-19 |  |  |  |  | No |  |  | Not Required
25INR0146 | Blue Heron BESS | SS Completed, FIS Started, No IA | Blue Heron BESS, LLC | Tap 138kV MANSON (1094) - Riverton (11083) | Reeves | WEST | 2026-04-21 | OTH | BA | 201.08 |  | 2023-04-26 | 2022-10-24 | 2023-01-20 |  |  |  |  | No |  |  | Not Required
25INR0147 | Holly Branch Solar | SS Completed, FIS Started, No IA | Holly Branch Solar, LLC | Tap 345kV 967 Gibbons Creek - 3400 Twin Oak | Robertson | NORTH | 2027-06-01 | SOL | PV | 231.12 |  | 2023-05-30 | 2023-06-07 | 2023-09-01 | 2023-05-22 |  |  |  | No |  |  | Not Required
25INR0148 | Holly Branch Storage | SS Completed, FIS Started, No IA | Holly Branch Solar, LLC | Tap 345kV 967 Gibbons Creek - 3400 Twin Oak | Robertson | NORTH | 2027-06-01 | OTH | BA | 115.32 |  | 2023-05-30 | 2023-06-07 | 2023-09-01 | 2023-05-30 |  |  |  | No |  |  | Not Required
25INR0151 | Academy Wind | SS Completed, FIS Started, No IA | Alma Wind | Tap 345kV 59904 Cottonwood - 60500 Edith Clarke Ckt #1 | Dickens | PANHANDLE | 2028-12-31 | WIN | WT | 304.56 |  | 2022-08-15 | 2022-09-15 | 2022-12-12 | 2022-09-06 |  |  |  | No |  |  | Not Required
25INR0152 | Bottom Grass Solar II | SS Completed, FIS Started, No IA | Flint Rock Solar Project, LLC | Tap 345kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2026-04-01 | SOL | PV | 401.6 |  | 2022-11-01 | 2022-11-07 | 2023-02-04 | 2022-11-02 |  |  |  | No |  |  | Not Required
25INR0153 | Bottom Grass BESS II | SS Completed, FIS Started, No IA | Flint Rock Solar Project, LLC | Tap 345kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2026-04-01 | OTH | BA | 150.6 |  | 2022-11-01 | 2022-11-07 | 2023-02-03 | 2022-11-02 |  |  |  | No |  |  | Not Required
25INR0154 | Nymphaea Solar | SS Completed, FIS Started, No IA | Nymphaea Solar, LLC | Tap 345kV 1730 Krum West Swtich - 6111 Riley7B | Wichita | WEST | 2025-12-21 | SOL | PV | 120.9 |  | 2023-01-06 | 2022-09-21 | 2022-12-19 |  |  |  |  | No |  |  | Not Required
25INR0155 | Nymphaea Storage | SS Completed, FIS Started, No IA | Nymphaea Solar, LLC | Tap 345kV 1730 Krum West Swtich - 6111 Riley7B | Wichita | WEST | 2025-12-21 | OTH | BA | 61 |  | 2023-01-13 | 2022-09-21 | 2022-12-19 |  |  |  |  | No |  |  | Not Required
25INR0156 | Bay Prairie Solar | SS Completed, FIS Started, No IA | San Bernard Solar II, LLC | CenterPoint South Lane City 43190 138kV | Wharton | SOUTH | 2025-02-04 | SOL | PV | 200.9 |  | 2022-10-03 | 2022-10-06 | 2022-12-28 | 2022-09-28 |  |  |  | No |  |  | Not Required
25INR0157 | Bay Prairie Storage | SS Completed, FIS Started, No IA | San Bernard Storage, LLC | CenterPoint South Lane City 43190 138kV | Wharton | SOUTH | 2025-02-04 | OTH | BA | 201.02 |  | 2022-10-03 | 2022-10-06 | 2022-12-28 | 2022-09-28 |  |  |  | No | Not Required | Not Required | Not Required
25INR0159 | Mallard II BESS | SS Completed, FIS Started, No IA | North Texas Energy Storage LLC | 818 Olinger 138kV | Collin | NORTH | 2026-12-01 | OTH | BA | 101.76 |  | 2023-02-27 | 2022-09-15 | 2022-12-14 |  |  |  |  | No |  |  | Not Required
25INR0160 | Canvasback BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II | 8155 SANDCRAB4A | Calhoun | COASTAL | 2025-12-08 | OTH | BA | 150.5 |  | 2022-08-10 | 2022-08-16 | 2022-11-11 | 2022-08-09 |  |  |  | No |  |  | Not Required
25INR0162 | SOHO II BESS | SS Completed, FIS Completed, IA | Black Mountain Energy Storage II | 43035 Oasis 345kV | Brazoria | COASTAL | 2025-01-01 | OTH | BA | 206.32 |  | 2022-08-10 | 2022-08-16 | 2022-11-11 | 2022-08-10 | 2023-08-24 | No | 2023-04-15 | Yes | Not Required | Not Required | Not Required | 2023-08-24
25INR0164 | Star Dairy Solar | SS Completed, FIS Started, No IA | Star Dairy Solar LLC | Tap 345kV 1692 PARIS_SW1_5 -- 11699 WOODARD_5 | Lamar | NORTH | 2026-09-14 | SOL | PV | 125.61 |  | 2022-11-18 | 2022-11-23 | 2023-02-17 | 2022-11-09 |  |  |  | No | Not Required | Not Required | Not Required
25INR0165 | Timberlakes Solar | SS Completed, FIS Started, No IA | Donegalsol | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2026-10-31 | SOL | PV | 203.5 |  | 2022-08-26 | 2022-11-07 | 2023-02-03 | 2022-09-02 |  |  |  | No |  |  | Not Required
25INR0166 | Padrino Solar | SS Completed, FIS Started, No IA | Hill Solar II, LLC | Tap 345kV 68090 Sam Switch - 1907 Venus Switch | Hill | NORTH | 2026-03-23 | SOL | PV | 201.11 |  | 2023-03-17 | 2022-09-15 | 2022-12-13 |  |  |  |  | No |  |  | Not Required
25INR0167 | Padrino BESS | SS Completed, FIS Started, No IA | Hill Solar II, LLC | tap 345kV 68090 Sam Switch - 1907 Venus | Hill | NORTH | 2026-03-23 | OTH | BA | 100.77 |  | 2023-03-17 | 2022-09-15 | 2022-12-13 |  |  |  |  | No |  |  | Not Required
25INR0168 | Piedra Solar | SS Completed, FIS Started, No IA | Piedra Solar, LLC | Tap 345-kV line Navarro (68091) – Limestone (46020)) | Freestone | NORTH | 2026-04-20 | SOL | PV | 300.93 |  | 2023-03-09 | 2022-09-02 | 2022-11-30 |  |  |  |  | No |  |  | Not Required
25INR0169 | Piedra BESS | SS Completed, FIS Started, No IA | Piedra Solar, LLC | Tap 345-kV line Navarro (68091) – Limestone (46020) | Freestone | NORTH | 2026-04-20 | OTH | BA | 100.4 |  | 2023-03-08 | 2022-09-02 | 2022-11-30 |  |  |  |  | No |  |  | Not Required
25INR0170 | Pinewood Solar | SS Completed, FIS Started, No IA | Brazoria Solar II, LLC | Tap 345kV 42500 Dow - 43035 Oasis Ckt 18 | Brazoria | COASTAL | 2025-06-01 | SOL | PV | 150.68 | MW Size | 2023-07-03 | 2022-09-02 | 2022-11-30 |  |  |  |  | No |  |  | Not Required
25INR0171 | Pinewood BESS | SS Completed, FIS Started, No IA | Brazoria Solar II, LLC | Tap 345kV 42500 Dow - 43035 Oasis Ckt 18 | Brazoria | COASTAL | 2025-06-01 | OTH | BA | 100.9 | MW Size | 2023-07-10 | 2022-09-02 | 2022-11-30 |  |  |  |  | No |  |  | Not Required
25INR0172 | Wolf Spring Solar | SS Completed, FIS Started, No IA | Wolf Spring Solar, LLC | Tap 345kV 59904 Cotton Wood - 23922 White River Ckt 2 | Dickens | PANHANDLE | 2026-03-11 | SOL | PV | 195.7 |  | 2022-12-05 | 2022-12-07 | 2023-03-06 | 2022-11-30 |  |  |  | No |  |  | Not Required
25INR0173 | Wolf Spring Storage | SS Completed, FIS Started, No IA | Wolf Spring Solar, LLC | Tap 345kV 59904 Cotton Wood - 23922 White River Ckt 2 | Dickens | PANHANDLE | 2026-03-11 | OTH | BA | 202.7 |  | 2022-12-05 | 2022-12-15 | 2023-03-13 | 2022-12-07 |  |  |  | No |  |  | Not Required
25INR0174 | Concho Pearl Solar | SS Completed, FIS Started, No IA | Concho Pearl Solar, LLC | Tap 345kV 76009 Twin Buttes - 7077 Amos Creek | Concho | WEST | 2026-07-01 | SOL | PV | 171.9 |  | 2022-12-05 | 2022-12-07 | 2023-03-06 | 2022-11-30 |  |  |  | No |  |  | Not Required
25INR0175 | Concho Pearl Storage | SS Completed, FIS Started, No IA | Concho Pearl Solar, LLC | Tap 345kV 76009 Twin Buttes - 7077 Amos Creek | Concho | WEST | 2026-07-01 | OTH | BA | 162.4 |  | 2022-12-08 | 2022-12-15 | 2023-03-13 | 2022-12-07 |  |  |  | No |  |  | Not Required
25INR0176 | Masa Storage | SS Completed, FIS Started, No IA | Savannah Oaks Solar Project, LLC | tap 345 kV 46020 Limestone Plant - 967 Gibbons Creek ckt 18 | Madison | NORTH | 2025-09-01 | OTH | BA | 251.14 |  | 2022-08-23 | 2022-09-02 | 2022-11-30 | 2022-08-17 |  |  |  | No |  |  | Not Required
25INR0177 | Triangle Ranch Alpha | SS Completed, FIS Started, No IA | Triangle Ranch Wind | Edith Clark 345 kV (#60500) | Cottle | WEST | 2027-12-31 | WIN | WT | 301.74 |  | 2022-10-04 | 2022-10-06 | 2022-12-29 | 2022-09-15 |  |  |  | No |  |  | Not Required
25INR0178 | Triangle Ranch Bravo | SS Completed, FIS Started, No IA | Triangle Ranch Wind | Edith Clark 345 kV (#60500) | Cottle | WEST | 2027-12-31 | WIN | WT | 200.22 |  | 2022-10-04 | 2022-10-06 | 2022-12-29 | 2022-09-15 |  |  |  | No |  |  | Not Required
25INR0179 | Triangle Ranch Charlie | SS Completed, FIS Started, No IA | Triangle Ranch Wind | Edith Clark 345 kV (#60500) | Cottle | WEST | 2025-08-30 | WIN | WT | 200.22 |  | 2022-09-09 | 2022-09-15 | 2022-12-12 | 2022-09-09 |  |  |  | No |  |  | Not Required
25INR0180 | Triangle Ranch Delta | SS Completed, FIS Started, No IA | Triangle Ranch Wind | Edith Clark 345 kV (#60500) | Cottle | WEST | 2025-08-30 | WIN | WT | 101.52 |  | 2022-09-09 | 2022-09-15 | 2022-12-12 | 2022-09-09 |  |  |  | No |  |  | Not Required
25INR0181 | Triangle Ranch Echo | SS Completed, FIS Started, No IA | Triangle Ranch Wind | Edith Clark 345 kV (#60500) | Cottle | WEST | 2025-08-30 | WIN | WT | 100.52 |  | 2022-09-09 | 2022-09-15 | 2022-12-12 | 2022-09-09 |  |  |  | No |  |  | Not Required
25INR0182 | Triangle Ranch Fox | SS Completed, FIS Started, No IA | Triangle Ranch Wind | Edith Clark 345 kV (#60500) | Cottle | WEST | 2025-08-30 | WIN | WT | 100.52 |  | 2022-09-09 | 2022-09-15 | 2022-12-12 | 2022-09-09 |  |  |  | No |  |  | Not Required
25INR0184 | Legato BESS | SS Completed, FIS Started, No IA | Legato Storage, LLC | 608 Crafton Substation 138kV | Wise | NORTH | 2025-07-01 | OTH | BA | 202.65 |  | 2023-01-20 | 2022-09-27 | 2022-12-21 |  |  |  |  | No |  |  | Not Required
25INR0185 | Sonata BESS | SS Completed, FIS Started, No IA | Sonata Storage, LLC | LCRA Altair Substation (BUS#78106) | Colorado | SOUTH | 2025-07-01 | OTH | BA | 83.86 |  | 2023-02-10 | 2022-09-27 | 2022-12-22 |  |  |  |  | No |  |  | Not Required
25INR0186 | Moonlight Sonata BESS | SS Completed, FIS Started, No IA | Samsung Solar Energy 2, LLC | 78118 LCRA Altair 138kV | Colorado | SOUTH | 2026-03-16 | OTH | BA | 201.08 |  | 2023-07-01 | 2022-09-27 | 2022-12-22 |  |  |  |  | No |  |  | Not Required
25INR0189 | Staccato BESS | SS Completed, FIS Started, No IA | Staccato Storage, LLC | 138kV WARDA #7312. | Fayette | SOUTH | 2025-12-31 | OTH | BA | 202.65 |  | 2023-01-05 | 2022-11-07 | 2023-02-03 |  |  |  |  | No |  |  | Not Required
25INR0190 | Fortissimo BESS | SS Completed, FIS Started, No IA | Fortissimo BESS, LCC | 741 Dyemound 138kV | Montague | NORTH | 2025-07-01 | OTH | BA | 202.65 |  | 2023-02-28 | 2022-10-18 | 2023-01-13 |  |  |  |  | No |  |  | Not Required
25INR0192 | Palmvalley Storage | SS Completed, FIS Started, No IA | Palmvalley Energy Storage LLC | Frontera (#8980) | Hidalgo | SOUTH | 2025-07-01 | OTH | BA | 100 |  | 2022-08-26 | 2022-09-27 | 2022-12-21 | 2022-09-16 |  |  |  | No |  |  | Not Required
25INR0193 | Nockenut Springs Solar 4 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | The 345 kV Elm Creek - South Texas Project Line (Bus #5133 - #5915) | Gonzales | SOUTH | 2025-12-31 | SOL | PV | 201.15 |  | 2022-09-13 | 2022-09-15 | 2022-12-13 | 2022-08-31 |  |  |  | No |  |  | Not Required
25INR0194 | Photo Solar 1 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2026-05-31 | SOL | PV | 150 |  | 2022-10-04 | 2022-09-15 | 2022-12-13 | 2022-09-15 |  |  |  | No |  |  | Not Required
25INR0195 | Photo Solar 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2027-05-31 | SOL | PV | 300 |  | 2022-10-04 | 2022-09-15 | 2022-12-13 | 2022-09-15 |  |  |  | No |  |  | Not Required
25INR0196 | Inadale Solar | SS Completed, FIS Started, No IA | Inadale Solar, LLC | Tap 345 kV TONKAWAW_5 (11048) – SCURCNTYS_5 (11318) Circuit #2 | Scurry | WEST | 2025-12-30 | SOL | PV | 281.03 |  | 2023-02-17 | 2023-02-20 | 2023-05-19 | 2023-02-08 |  |  |  | No |  |  | Not Required
25INR0197 | Inadale BESS | SS Completed, FIS Started, No IA | Inadale BESS, LLC | Tap 345 kV TONKAWAW_5 (11048) – SCURCNTYS_5 (11318) Circuit #2 | Scurry | WEST | 2025-12-30 | OTH | BA | 281.06 |  | 2023-02-17 | 2023-02-20 | 2023-05-19 | 2023-02-16 |  |  |  | No |  |  | Not Required
25INR0199 | XE Bonham Solar 1 | SS Completed, FIS Started, No IA | J&J Solar Ranch LLC | TAP 138 kV MEXIA_2_1_8 3632 - GROES_SE1_8 3634 | Limestone | NORTH | 2026-04-27 | SOL | PV | 138.4 |  | 2022-11-09 | 2022-11-15 | 2023-02-09 | 2022-10-31 |  |  |  | No | Not Required | Not Required | Not Required
25INR0201 | Veer Energy | SS Completed, FIS Started, No IA | DBR Solar, LLC | TAP 69kV 38040 IH20 - 38090 Pecos | Reeves | WEST | 2025-05-31 | SOL | PV | 90.72 |  | 2023-10-06 | 2022-12-07 | 2023-03-04 |  |  |  |  | No | Not Required | Not Required | Not Required
25INR0202 | East West BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II, LLC | 7750 LCRA MOUNTAIN HOME SUB | Kerr | SOUTH | 2025-02-01 | OTH | BA | 100.8 |  | 2022-09-28 | 2022-10-06 | 2022-12-29 | 2022-09-27 |  |  |  | No |  |  | Not Required
25INR0204 | Claxton Solar | SS Completed, FIS Started, No IA | BT Claxton Solar, LLC | Tap 345kV line between Allen Switch (#2514) and Monticello (#1696) | Hopkins | NORTH | 2026-09-07 | SOL | PV | 150.64 |  | 2023-03-06 | 2022-09-21 | 2022-12-19 | 2022-11-03 |  |  |  | No |  |  | Not Required
25INR0205 | Claxton Storage | SS Completed, FIS Started, No IA | BT Claxton Solar, LLC | Tap 345kV line between Allen Switch (#2514) and Monticello (#1696) | Hopkins | NORTH | 2026-09-07 | OTH | BA | 75.7 |  | 2022-11-18 | 2022-09-21 | 2022-12-19 | 2022-11-03 |  |  |  | No |  |  | Not Required
25INR0207 | Shadow Ranch Solar | SS Completed, FIS Started, No IA | LectricWind LLC | 76000 North McCamey 345kV | Upton | WEST | 2026-06-01 | SOL | PV | 807.61 |  | 2023-07-24 | 2022-09-27 | 2023-01-12 |  |  |  |  | No |  |  | Not Required
25INR0208 | Iron Belt Energy Storage | SS Completed, FIS Started, IA | Iron Belt Energy Storage Project, LLC | Long Draw (# 59900) - Volta (#59910) 345kV | Borden | WEST | 2025-09-01 | OTH | BA | 401.9 |  | 2022-12-27 | 2023-01-03 | 2023-03-30 | 2022-12-19 |  |  | 2023-01-16 | No |  |  | Not Required
25INR0209 | Box Canyon Energy Storage | SS Started, FIS Started, No IA | Box Canyon Energy Storage Project, LLC | 68011 Aspire Substation 345 kV | Callahan | WEST | 2025-12-01 | OTH | BA | 306.34 | FIS Request | 2023-11-12 |  |  | 2023-11-30 |  |  |  | No |  |  | Not Required
25INR0210 | Fox Run Energy Storage | SS Completed, FIS Started, No IA | Fox Run Energy Project, LLC | Kirchhoff Substation (PTI#60704) | Jones | WEST | 2026-07-01 | OTH | BA | 301.36 |  | 2023-02-15 | 2023-02-20 | 2023-05-18 | 2023-02-14 |  | No |  | No |  |  | Not Required
25INR0214 | Burgos Solar | SS Completed, FIS Started, No IA | Karol Solar II | Tap 138kV 3659 THORNDALE NORTH - 116 SALTY | Milam | SOUTH | 2026-09-11 | SOL | PV | 105.52 |  | 2023-03-17 | 2022-10-18 | 2023-01-13 |  |  |  |  | No |  |  | Not Required
25INR0215 | Middlebrook BESS | SS Completed, FIS Started, No IA | Middlebrook Solar LLC | Tap Stryker [3109] - Lufkin [3117] 345 kV line | Nacogdoches | NORTH | 2026-02-20 | OTH | BA | 302.94 |  | 2022-09-21 | 2022-10-24 | 2023-01-20 | 2022-10-11 |  |  |  | No | Not Required | Not Required | Not Required
25INR0216 | Blue Sky Storage SLF | SS Completed, FIS Started, No IA | UKA North America, LLC | 138 kV Friend Ranch (Bus# 6562) | Crockett | WEST | 2025-11-15 | OTH | BA | 0 |  | 2022-10-17 | 2022-10-24 | 2023-01-22 | 2022-10-14 |  |  |  | No |  |  | Not Required
25INR0220 | Hector Solar | SS Completed, FIS Started, No IA | Hector Solar, LLC | Haney (213) - Hubbard_8 (3515) 138kV Line | Navarro | NORTH | 2025-12-31 | SOL | PV | 81.59 |  | 2023-01-06 | 2022-10-24 | 2023-01-20 |  |  |  |  | No |  |  | Not Required
25INR0221 | Hector Storage | SS Completed, FIS Started, No IA | Hector Solar, LLC | Haney (213) - Hubbard_8 (3515) 138kV Line | Navarro | NORTH | 2025-12-31 | OTH | BA | 42.69 |  | 2023-01-06 | 2022-10-24 | 2023-01-20 |  |  |  |  | No |  |  | Not Required
25INR0222 | Olympic BESS | SS Completed, FIS Started, No IA | SMT Olympic BESS LLC | AIRLINE 138 kV Substation (Bus# 8490) | Nueces | COASTAL | 2025-04-01 | OTH | BA | 222.81 |  | 2022-09-27 | 2022-10-18 | 2023-01-13 | 2022-09-29 |  |  |  | No |  |  | Not Required
25INR0223 | Uhland Maxwell | SS Completed, FIS Completed, IA | Lower Colorado River Authority | Clear Springs (#7050) and L_Hornsb8_1Y (#7047) | Caldwell | SOUTH | 2025-04-15 | GAS | IC | 188.4 |  | 2022-11-08 | 2022-09-27 | 2022-12-22 | 2022-10-26 | 2023-12-04 | Yes | 2023-03-03 | Yes | 2023-09-01 | Not Required |  | 2023-09-05
25INR0225 | Lucy Solar | SS Completed, FIS Started, No IA | Concho County Solar 1 LLC | Tap 345kV 7077 Amos Creek - 6444 San Angelo Red Creek and 7077 Amos Creek - 76009 Twin Buttes | Concho | WEST | 2026-04-14 | SOL | PV | 351.3 |  | 2023-06-15 | 2023-06-28 | 2023-09-20 | 2023-06-08 |  |  |  | No |  |  | Not Required
25INR0227 | SERENGETI SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green XIV LLC | Tap 138kV Enloe Tap (bus# 11806) – Delta sub (bus# 1802) | Delta | NORTH | 2026-09-14 | SOL | PV | 76.18 | MW Size | 2022-11-08 | 2022-12-07 | 2023-03-06 | 2022-11-18 |  |  |  | No |  |  | Not Required
25INR0229 | OCI Cobb Creek Solar | SS Completed, FIS Started, No IA | OCI Hillsboro Solar LLC | tap 345kV 1907 Venus - 68090 Sam Sw | Hill | NORTH | 2026-07-01 | SOL | PV | 202.2 |  | 2022-11-11 | 2022-11-15 | 2023-02-09 | 2022-11-09 |  |  |  | No | Not Required | Not Required | Not Required
25INR0230 | Great Rock BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II | Tap 345kV 46020 Limestone - 967 Gibbon Creek Ckt 18 | Leon | NORTH | 2026-04-15 | OTH | BA | 300.9 |  | 2022-10-19 | 2022-11-07 | 2023-02-04 | 2022-10-19 |  | No |  | No |  |  | Not Required
25INR0231 | Apache Hill BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II | 363 Hood 138kV | Hood | NORTH | 2025-05-15 | OTH | BA | 201.2 |  | 2022-10-25 | 2022-11-07 | 2023-02-03 | 2022-10-25 |  |  |  | No | Not Required | Not Required | Not Required
25INR0232 | Isaac Solar | SS Completed, FIS Started, IA | Industrial Bravo Project LLC | 8114 Conoco 138kV | Matagorda | COASTAL | 2026-03-31 | SOL | PV | 51.6 |  | 2022-10-24 | 2022-11-07 | 2023-02-03 | 2022-10-27 |  | No | 2023-10-18 | Yes | Not Required | Not Required | Not Required | 2023-10-31
25INR0233 | OCI Cobb Creek ESS | SS Completed, FIS Started, No IA | OCI Hillsboro Solar LLC | tap 345kV 1907 Venus - 68090 Sam Sw | Hill | NORTH | 2026-07-01 | OTH | BA | 201.3 |  | 2022-11-17 | 2022-12-07 | 2023-03-04 | 2022-11-23 |  |  |  | No |  |  | Not Required
25INR0234 | Maldives Solar | SS Completed, FIS Started, No IA | Maldives Solar | Tap 138kV Morgan Creek (1032) to Sun (1064) | Scurry | WEST | 2026-07-01 | SOL | PV | 184 |  | 2022-11-29 | 2022-12-07 | 2023-03-04 | 2022-11-29 |  |  |  | No | Not Required | Not Required | Not Required
25INR0235 | Austin Bayou Storage I | SS Completed, FIS Started, No IA | Austin Bayou Solar, LLC | Tap 345kV 43180 Savanna - 43020 Seabreeze Ckt 27 AND 43035 Oasis - 43060 Speedway Ckt 18 | Brazoria | COASTAL | 2025-07-01 | OTH | BA | 150.68 |  | 2023-03-02 | 2023-03-08 | 2023-06-05 | 2023-02-23 |  |  |  | No |  |  | Not Required
25INR0236 | Austin Bayou Storage II | SS Completed, FIS Started, No IA | Austin Bayou Solar, LLC | Tap 345kV 43180 Savanna - 43020 Seabreeze Ckt 27 AND 43035 Oasis - 43060 Speedway Ckt 18 | Brazoria | COASTAL | 2025-07-01 | OTH | BA | 150.68 |  | 2023-03-02 | 2023-03-08 | 2023-06-05 | 2023-02-23 |  |  |  | No |  |  | Not Required
25INR0237 | Austin Bayou Storage III | SS Completed, FIS Started, No IA | Austin Bayou Solar, LLC | Tap 345kV 43180 Savanna - 43020 Seabreeze Ckt 27 AND 43035 Oasis - 43060 Speedway Ckt 18 | Brazoria | COASTAL | 2025-07-01 | OTH | BA | 150.68 |  | 2023-03-02 | 2023-03-08 | 2023-06-05 | 2023-02-23 |  |  |  | No |  |  | Not Required
25INR0238 | Little Ridge Storage | SS Completed, FIS Started, No IA | TX BESS B LLC | Tap 138kV Swindell (812) - Olinger (818) | Collin | NORTH | 2025-12-11 | OTH | BA | 250 | COD | 2023-05-04 | 2023-05-15 | 2023-08-11 | 2023-04-25 |  |  |  | No |  |  | Not Required
25INR0239 | Big Five Storage | SS Completed, FIS Started, No IA | TX BESS 3 LLC | Tap 138kV (5784) Redgtss - (8380) Nedina | Hidalgo | SOUTH | 2025-06-01 | OTH | BA | 102.18 |  | 2023-05-24 | 2023-05-26 | 2023-08-17 | 2023-05-22 |  |  |  | No |  |  | Not Required
25INR0240 | Rosie Solar | SS Completed, FIS Started, No IA | Industrial Delta Project LLC | TNAAPIPLNC1 (38137) | Winkler | WEST | 2026-05-31 | SOL | PV | 61 |  | 2022-10-27 | 2022-11-07 | 2023-02-03 | 2022-11-02 |  |  |  | No |  |  | Not Required
25INR0241 | Halcon Storage | SS Completed, FIS Started, No IA | TX BESS A LLC | Tap 138kV 8957 Central Lopeno - 80106 Falcon Dam | Starr | SOUTH | 2025-06-01 | OTH | BA | 132.65 |  | 2023-05-15 | 2023-05-22 | 2023-08-17 | 2023-04-24 |  |  |  | No |  |  | Not Required
25INR0242 | Pato Blanco Storage | SS Completed, FIS Started, No IA | TX BESS 4, LLC | Tap 138 kV 44010 W A Parish - 42980 NASH___S02_8 | Fort Bend | HOUSTON | 2025-12-11 | OTH | BA | 71.78 | COD | 2023-04-25 | 2023-05-15 | 2023-08-11 | 2023-04-24 |  |  |  | No |  |  | Not Required
25INR0246 | VALDIVIAN SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green III LLC | 138kV 1816 Commerce Switch - 1809 Wolf City | Hunt | NORTH | 2026-09-26 | SOL | PV | 74.77 |  | 2022-11-17 | 2023-02-27 | 2023-05-26 | 2023-02-22 |  |  |  | No |  |  | Not Required
25INR0247 | Bluebonnet Prairie Wind | SS Completed, FIS Started, No IA | Leeward Renewable Energy Development, LLC | Tap 138kV 200 CHATFIELD - 3454 MONTFTSS__8 | Navarro | NORTH | 2025-12-31 | WIN | WT | 173 |  | 2022-12-06 | 2022-12-07 | 2023-03-06 | 2022-11-23 |  |  |  | No |  |  | Not Required
25INR0248 | Strawberry Acres Storage | SS Completed, FIS Started, No IA | Strawberry Acres Energy Center, LLC | 5132 Eagle Creek Substation 138kV | Wilson | SOUTH | 2026-09-30 | OTH | BA | 156.59 |  | 2022-11-11 | 2022-11-23 | 2023-02-17 | 2022-11-15 |  |  |  | No |  |  | Not Required
25INR0250 | Oorja Storage | SS Completed, FIS Started, No IA | Oorja Storage, LLC | 138 kV 8914 Coffee Port | Cameron | COASTAL | 2027-02-27 | OTH | BA | 201.1 |  | 2022-11-17 | 2022-11-23 | 2023-02-17 | 2022-11-10 |  | No |  | No | Not Required | Not Required | Not Required
25INR0252 | Papley Storage | SS Completed, FIS Started, No IA | Papley Storage, LLC | Tapping the 138kV line connecting Ganso (Bus# 8267) to Maverick (Bus# 8692) | Maverick | SOUTH | 2024-12-01 | OTH | BA | 201.07 |  | 2022-12-02 | 2022-12-07 | 2023-03-06 | 2022-11-18 |  |  |  | No |  |  | Not Required
25INR0253 | Whiskey BESS | SS Completed, FIS Started, No IA | UR-Silo DevCo LLC | 6828 Canton Tap 138 kV | Van Zandt | NORTH | 2025-07-02 | OTH | BA | 153.72 |  | 2023-05-04 | 2022-12-07 | 2023-03-06 |  |  |  |  | No |  |  | Not Required
25INR0257 | OCI SunRoper ESS | SS Completed, FIS Started, No IA | OCI SunRoper LLC | tap138kV #43190 South Lane City to #42985 Dyann Ckt 60 | Wharton | SOUTH | 2026-07-01 | OTH | BA | 265.6 |  | 2022-12-27 | 2023-01-30 | 2023-04-28 | 2023-01-09 |  |  |  | No |  |  | Not Required
25INR0262 | Shepard Energy Storage | SS Completed, FIS Started, No IA | Shepard Energy Storage LLC | Hidden Lakes 138kV substation (Bus# 38900) | Galveston | HOUSTON | 2025-07-09 | OTH | BA | 263.2 |  | 2022-12-02 | 2022-12-15 | 2023-03-11 | 2022-12-09 |  | No |  | No |  |  | Not Required
25INR0266 | East Blackland Battery Storage SLF | SS Completed, FIS Started, No IA | Duke Energy Renewables Storage, LLC | 7337 Kimbro 138kV | Travis | SOUTH | 2025-06-01 | OTH | BA | 75 |  | 2022-11-17 | 2022-11-23 | 2023-02-17 | 2022-11-22 |  |  |  | No |  |  | Not Required
25INR0270 | Harryoung Solar | SS Completed, FIS Started, No IA | Gransolar Texas Four LLC | 8319 Rio Hondo Sub 138kV | Cameron | COASTAL | 2027-05-15 | SOL | PV | 190.01 |  | 2023-11-02 | 2022-11-23 | 2023-02-17 |  |  |  |  | No | Not Required | Not Required | Not Required
25INR0271 | City Breeze BESS | SS Completed, FIS Started, No IA | Zenobe City Breeze BESS | 8111 MAGILL4A 138KV | Matagorda | COASTAL | 2025-12-15 | OTH | BA | 141.2 |  | 2022-12-14 | 2022-12-15 | 2023-03-11 | 2022-12-06 |  |  |  | No |  |  | Not Required
25INR0273 | Horse Wrangler Solar | SS Started, FIS Started, No IA | Horse Wrangler Solar Project, LLC | Tap 138kV 8153 Rosata Tap (Bus# ) - 8186 Kenedy Switch | Karnes | SOUTH | 2027-12-01 | SOL | PV | 251.33 | COD | 2023-11-15 | 2023-12-04 |  | 2023-11-14 |  |  |  | No | Not Required | Not Required | Not Required
25INR0274 | Horse Wrangler Storage | SS Started, FIS Started, No IA | Horse Wrangler Solar Project, LLC | Tap 138kV 8153 Rosata Tap - 8186 Kenedy Switch Ckt 1 | Karnes | SOUTH | 2027-12-01 | OTH | BA | 102.07 | COD | 2023-11-29 | 2023-11-30 |  | 2023-11-14 |  |  |  | No |  |  | Not Required
25INR0280 | Nockenut Springs Solar 5 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | Tap 345 kV 5133 Elm Creek - 5915 South Texas Project | Gonzales | SOUTH | 2025-12-31 | SOL | PV | 201.15 |  | 2023-01-24 | 2023-02-09 | 2023-05-08 | 2023-01-27 |  |  |  | No |  |  | Not Required
25INR0281 | Cosper Solar | SS Completed, FIS Started, No IA | Gransolar Texas Twenty LLC | Tap 138kV 115 Ding Dong - 3630 Copperas Cove Tu | Bell | NORTH | 2026-09-15 | SOL | PV | 148.16 |  | 2023-06-13 | 2023-01-03 | 2023-03-30 |  |  |  |  | No |  |  | Not Required
25INR0282 | Hornet Solar II SLF | SS Completed, FIS Started, No IA | Hornet Solar II LLC | Ozark Trail Switch 345kV substation (Bus #23901) | Castro | PANHANDLE | 2026-06-01 | SOL | PV | 208.95 |  | 2022-12-20 | 2023-01-03 | 2023-03-29 | 2022-12-20 |  |  |  | No |  |  | Not Required
25INR0283 | Hornet Storage II SLF | SS Completed, FIS Started, No IA | Hornet Storage II LLC | Ozark Trail Switch 345kV substation (Bus # 23901) | Castro | PANHANDLE | 2026-06-01 | OTH | BA | 0 |  | 2022-12-28 | 2023-01-03 | 2023-03-29 | 2022-12-20 |  |  |  | No |  |  | Not Required
25INR0284 | Railway BESS | SS Completed, FIS Started, No IA | Grand Reserve Energy, LLC | Martin Lake Switch (3100) – Elkton (3105) 345 kV Line | Rusk | NORTH | 2026-05-01 | OTH | BA | 254.8 |  | 2023-01-27 | 2023-01-30 | 2023-04-28 | 2023-01-23 |  |  |  | No |  |  | Not Required
25INR0286 | Savannah Oaks Solar | SS Completed, FIS Started, No IA | Savannah Oaks Solar Project LLC | Tap 345kV 46020 Limestone Plant - 967 Gibbons Creek | Madison | NORTH | 2027-09-30 | SOL | PV | 200.97 | MW Size COD | 2022-12-19 | 2023-01-03 | 2023-03-30 | 2022-12-02 |  |  |  | No |  |  | Not Required
25INR0288 | Buffalo Prairie Storage | SS Completed, FIS Started, No IA | Buffalo Meadow Energy Center, LLC | Tap 345kV 975 Jack Creek - 3400 Twin Oak | Robertson | NORTH | 2026-07-31 | OTH | BA | 150.56 |  | 2022-12-30 | 2023-01-03 | 2023-03-29 | 2022-12-02 |  |  |  | No |  |  | Not Required
25INR0290 | OCI SunShiner Solar | SS Completed, FIS Started, No IA | OCI SunShiner LLC | 8672 LaPryor2A 138 kV | Zavala | SOUTH | 2026-07-01 | SOL | PV | 130 |  | 2023-02-15 | 2023-02-20 | 2023-05-18 | 2023-01-30 |  |  |  | No |  |  | Not Required
25INR0293 | TOCE BESS 1 | SS Started, FIS Started, No IA | TOCE BESS 1, LLC | 138 kV Danevang Switching Station (Bus# 5546) | Wharton | SOUTH | 2026-05-01 | OTH | BA | 205.2 |  | 2023-10-02 | 2023-10-13 |  | 2023-09-22 |  |  |  | No |  |  | Not Required
25INR0297 | RIVERBEND SOLAR SLF | SS Completed, FIS Started, No IA | Riverbend Renewables, LLC | TAP 345 KV LINE FROM TRADINGHOUSE (#3405) TO TEMPLE PECAN CREEK (#3412) SUBSTATIONS | Falls | NORTH | 2026-01-20 | SOL | PV | 301 |  | 2023-02-13 | 2023-03-08 | 2023-06-05 | 2023-03-03 |  |  |  | No |  |  | Not Required
25INR0300 | Wizard BESS | SS Completed, FIS Started, IA | Rocky Mountain Energy Holdings, LLC | To the 138 kV League City Substation (#38920) | Galveston | HOUSTON | 2025-04-29 | OTH | BA | 150.65 |  | 2023-03-14 | 2023-03-27 | 2023-06-19 | 2023-03-15 |  |  | 2023-08-21 | No |  |  | Not Required
25INR0301 | Van Zandt Energy Storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Holdings, LLC | 1027 Odessa EHV Switch 138 kV | Ector | WEST | 2027-04-13 | OTH | BA | 256.58 | COD | 2023-03-21 | 2023-06-07 | 2023-09-01 | 2023-04-05 |  |  |  | No |  |  | Not Required
25INR0304 | XE Flying Kite Solar | SS Completed, FIS Started, No IA | FLYING KITE SOLAR LLC | Tap the 69kV La Pryor (#8672) - Uvalde (#8231) Line; AEP | Zavala | SOUTH | 2027-05-21 | SOL | PV | 80.38 |  | 2023-03-31 | 2023-04-07 | 2023-07-05 | 2023-03-17 |  |  |  | No |  |  | Not Required
25INR0306 | Red Top Solar I | SS Completed, FIS Started, No IA | Cat Red Top Solar, LLC | Tap 138kV 1431 Graham SES - 1477 Rice Switch | Young | WEST | 2026-06-30 | SOL | PV | 200.42 |  | 2023-10-24 | 2023-01-17 | 2023-04-14 |  |  |  |  | No | Not Required | Not Required | Not Required
25INR0307 | Red Top Solar II | SS Completed, FIS Started, No IA | Cat Red Top Solar, LLC | Tap 345kV 1430 Graham SES - 17002 Garvey Road Switch | Young | WEST | 2026-06-30 | SOL | PV | 173.67 |  | 2023-10-24 | 2023-01-17 | 2023-04-14 |  |  |  |  | No |  |  | Not Required
25INR0310 | IEP Blackhawk | SS Completed, FIS Started, No IA | IEP Texas Verde II, llc | 38740 Heights Substation 138kV | Galveston | HOUSTON | 2025-01-01 | OTH | BA | 100 |  | 2023-04-04 | 2023-04-07 | 2023-07-05 | 2023-03-08 |  |  |  | No |  |  | Not Required
25INR0311 | RIVERBEND STORAGE SLF | SS Completed, FIS Started, No IA | Riverbend Renewables, LLC | TAP 345 KV LINE FROM TRADINGHOUSE (#3405) TO TEMPLE PECAN CREEK (#3412) SUBSTATIONS | Falls | NORTH | 2026-01-20 | OTH | BA | 0 |  | 2023-02-13 | 2023-03-08 | 2023-06-05 | 2023-03-03 |  |  |  | No |  |  | Not Required
25INR0313 | Staked Plains BESS | SS Completed, FIS Started, No IA | Grand Reserve Energy, LLC | 345kV Dunbar Double Mountain Switch (Bus# 23928) | Lubbock | PANHANDLE | 2026-08-01 | OTH | BA | 254.8 |  | 2023-02-17 | 2023-03-13 | 2023-06-09 | 2023-03-02 |  |  |  | No |  |  | Not Required
25INR0318 | Silver Fox Solar | SS Completed, FIS Started, No IA | Industrial Lima Project LLC | 12677 Haggerty Switch 138kV | Grayson | NORTH | 2026-05-31 | SOL | PV | 101.2 |  | 2023-07-29 | 2023-07-31 | 2023-10-27 | 2023-07-24 |  |  |  | No |  |  | Not Required
25INR0319 | Northington Solar | SS Completed, FIS Started, No IA | Northington Solar, LLC | The 138 kV El Campo (#8102) - Pulsar (#8192) Line; AEP. | Wharton | SOUTH | 2025-12-31 | SOL | PV | 129.81 |  | 2023-02-17 | 2023-02-20 | 2023-05-19 | 2023-02-02 |  |  |  | No |  |  | Not Required
25INR0320 | Normangee Solar | SS Completed, FIS Started, No IA | Normangee Solar LLC | Tap 345kV 3391Jewett - 44645 Singleton | Leon | NORTH | 2026-02-15 | SOL | PV | 120.68 |  | 2023-03-08 | 2023-03-13 | 2023-06-09 | 2023-02-13 |  |  |  | No | Not Required | Not Required | Not Required
25INR0321 | El Molino Solar SLF | SS Completed, FIS Started, No IA | El Molino Solar, LLC | 138kV Bruni 8297 | Webb | SOUTH | 2025-07-01 | SOL | PV | 201.32 |  | 2023-01-16 | 2023-01-17 | 2023-04-14 | 2023-03-31 |  |  |  | No |  |  | Not Required
25INR0322 | El Molino Storage SLF | SS Completed, FIS Started, No IA | El Molino Solar, LLC | 138kV Bruni 8297 | Webb | SOUTH | 2025-07-01 | OTH | BA | 0 |  | 2023-01-16 | 2023-01-17 | 2023-04-14 | 2023-01-13 |  |  |  | No |  |  | Not Required
25INR0328 | Longbow BESS | SS Completed, FIS Completed, IA | Longbow BESS, LLC | 42875 Danbury 138kV | Brazoria | COASTAL | 2024-11-13 | OTH | BA | 180.8 | MW Size SFS/NtP | 2023-01-20 | 2023-01-23 | 2023-04-22 | 2023-01-16 | 2023-09-06 | No | 2023-07-18 | Yes | Not Required | Not Required | Not Required | 2023-12-12
25INR0329 | Project Lynx BESS | SS Completed, FIS Started, No IA | GIGA TEXAS ENERGY LLC | 138KV Tap 8921 Terra Verde - 8518 Kingsville | Nueces | COASTAL | 2025-06-28 | OTH | BA | 250.72 |  | 2023-03-02 | 2023-03-08 | 2023-06-01 | 2023-03-01 |  |  |  | No |  |  | Not Required
25INR0330 | Clutch City Solar Phase II SLF | SS Completed, FIS Started, No IA | HZ SOLAR I, LLC | tap 138kV 42960 Mustang Bayou – 42100 Hudson CKT#04 | Galveston | HOUSTON | 2026-10-01 | SOL | PV | 251.27 |  | 2023-02-17 | 2023-02-20 | 2023-05-20 | 2023-02-10 |  |  |  | No |  |  | Not Required
25INR0331 | Buffalo Meadow Solar | SS Completed, FIS Started, No IA | Buffalo Meadow Energy Center, LLC | Tap Jack Creek (975) - Twin Oak (3400) 345kV line | Robertson | NORTH | 2027-09-30 | SOL | PV | 251.26 | MW Size COD | 2023-02-15 | 2023-02-27 | 2023-05-26 | 2023-01-27 |  |  |  | No |  |  | Not Required
25INR0334 | Star Dairy Storage | SS Completed, FIS Started, No IA | Star Dairy Storage | Tap 345kV 1692 PARIS_SW1_5 -- 11699 WOODARD_5 | Lamar | NORTH | 2026-09-14 | OTH | BA | 204.93 |  | 2023-04-17 | 2023-04-19 | 2023-07-14 | 2023-04-11 |  |  |  | No |  |  | Not Required
25INR0335 | Jaguarundi Solar | SS Completed, FIS Started, No IA | Jaguarundi Solar, LLC | NAVY KICKAPOO SWITCH (NAVYKSS1_8 #1472) | Archer | WEST | 2025-07-01 | SOL | PV | 90.29 |  | 2023-03-21 | 2023-03-27 | 2023-06-19 | 2023-03-16 |  |  |  | No |  |  | Not Required
25INR0336 | Jaguarundi Storage | SS Completed, FIS Started, No IA | Jaguarundi Solar, LLC | NAVY KICKAPOO SWITCH (NAVYKSS1_8 #1472) | Archer | WEST | 2025-07-01 | OTH | BA | 91.09 |  | 2023-03-21 | 2023-03-27 | 2023-06-19 | 2023-03-16 |  |  |  | No |  |  | Not Required
25INR0337 | Butcherbird Solar | SS Started, FIS Started, No IA | Butcherbird Solar, LLC | Tap 138 kV - Bell County #133 to Bartlett Switch #114 | Bell | NORTH | 2027-02-01 | SOL | PV | 116 | FIS Request | 2023-11-28 | 2023-12-18 |  | 2023-12-06 |  |  |  | No |  |  | Not Required
25INR0338 | Les Energy Storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Development, LLC | Tap 138kV 23836 Natural Dam - 1326 Stanton East | Martin | WEST | 2026-09-21 | OTH | BA | 205.1 |  | 2023-02-23 | 2023-02-09 | 2023-05-05 |  |  |  |  | No |  |  | Not Required
25INR0339 | Fort Concho Energy storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Development, LLC | Tap 138 kV #76320 Schkade - #76011 Twin Buttes Line; LCRA | Tom Green | WEST | 2026-02-16 | OTH | BA | 251.15 |  | 2023-02-23 | 2023-01-30 | 2023-04-28 |  |  |  |  | No |  |  | Not Required
25INR0346 | Cado Storage | SS Completed, FIS Started, No IA | Cado Storage, LLC | 5417 STREICH RD 138 kV | Bexar | SOUTH | 2025-10-28 | OTH | BA | 205.2 |  | 2023-03-10 | 2023-03-13 | 2023-06-09 | 2023-03-07 |  |  |  | No |  |  | Not Required
25INR0347 | Cadet Storage | SS Completed, FIS Started, No IA | TX BESS 5, LLC | Tap 69kV 32864 BRYN_ATK69 to 32873 BRYN SHADY | Brazos | NORTH | 2026-04-01 | OTH | BA | 104.42 | COD |  | 2023-05-22 | 2023-08-18 | 2023-04-24 |  |  |  | No |  |  | Not Required
25INR0353 | Marshall Spring Solar | SS Completed, FIS Started, No IA | Ampyr Energy USA, LLC | New POI station between 7132 L_GILLES8_1Y - 7126 L_FERGUS8_1Y 138kV line and 7132 L_GILLES8_1Y - 7128 L_HORSBA8_1Y 138kV line, then loop in both lines into the new POI station. | Gillespie | SOUTH | 2026-06-30 | SOL | PV | 150 |  | 2023-10-04 | 2023-02-20 | 2023-05-18 |  |  |  |  | No |  |  | Not Required
25INR0354 | Marshall Spring Storage | SS Completed, FIS Started, No IA | Ampyr Energy USA, LLC | New POI station between 7132 L_GILLES8_1Y - 7126 L_FERGUS8_1Y 138kV line and 7132 L_GILLES8_1Y - 7128 L_HORSBA8_1Y 138kV line, then loop in both lines into the new POI station. | Gillespie | SOUTH | 2026-06-30 | OTH | BA | 150 |  | 2023-10-04 | 2023-02-20 | 2023-05-18 |  |  |  |  | No |  |  | Not Required
25INR0361 | Wallie Storage | SS Completed, FIS Started, No IA | Wallie Storage, LLC | Tap 138kV 11324 Leatherwood POD - 1326 Stanton East Switch | Howard | WEST | 2026-08-07 | OTH | BA | 205.4 |  | 2023-03-16 | 2023-03-27 | 2023-06-19 | 2023-03-02 |  |  |  | No |  |  | Not Required
25INR0363 | Emerald Hill Energy Storage | SS Completed, FIS Started, No IA | Emerald Hill Energy Storage LLC | Desoto Switch (2431) - Cedar Hill Switch (2420) 345kV Line | Dallas | NORTH | 2026-04-01 | OTH | BA | 261.02 |  | 2023-02-23 | 2023-02-27 | 2023-05-26 | 2023-02-23 |  |  |  | No |  |  | Not Required
25INR0368 | Echols Creek Solar | SS Completed, FIS Started, No IA | BT Ferguson Solar, LLC | Tap 138kV Reno T8 Bus# 1786 – Paris East Bus 1773 | Lamar | NORTH | 2026-04-15 | SOL | PV | 201.15 |  | 2023-03-17 | 2023-04-07 | 2023-07-05 | 2023-03-22 |  |  |  | No |  |  | Not Required
25INR0369 | Echols Creek Storage | SS Completed, FIS Started, No IA | BT Ferguson Solar, LLC | Tap 138kV Reno T8 Bus# 1786 – Paris East Bus 1773 | Lamar | NORTH | 2026-04-15 | OTH | BA | 100.57 |  | 2023-03-17 | 2023-04-07 | 2023-07-05 | 2023-03-22 |  |  |  | No |  |  | Not Required
25INR0370 | Willis Storage | SS Completed, FIS Started, No IA | BT Willis Storage, LLC | tap 138kV Emory North 3171 to Liberty POD 1723 | Rains | NORTH | 2026-09-07 | OTH | BA | 176.13 |  | 2023-03-03 | 2023-03-27 | 2023-06-24 | 2023-03-13 |  |  |  | No |  |  | Not Required
25INR0371 | McMurtre Storage | SS Completed, FIS Started, No IA | BT McMurtre Storage, LLC | tap 138kV 1819 Commerce South - 1815 Cumby Tap | Hunt | NORTH | 2026-09-07 | OTH | BA | 176.13 | MW Size | 2023-03-10 | 2023-03-13 | 2023-06-09 | 2023-03-06 |  |  |  | No |  |  | Not Required
25INR0372 | Elan BESS | SS Completed, FIS Started, No IA | Elan BESS, LLC | 42380 Needville 138kV | Fort Bend | HOUSTON | 2025-12-31 | OTH | BA | 202.65 |  | 2023-03-01 | 2023-03-08 | 2023-06-05 | 2023-02-15 |  |  |  | No |  |  | Not Required
25INR0373 | LARISA BESS | SS Completed, FIS Started, No IA | ME USA PROJECT II LLC | Tap 345kV 6235 Mulberry Creek – 60791 Perigee | Jones | WEST | 2025-09-10 | OTH | BA | 418.49 | FIS Request | 2023-12-13 | 2023-03-13 | 2023-06-09 |  |  |  |  | No |  |  | Not Required
25INR0374 | Meridian BESS | SS Completed, FIS Started, No IA | Navitas Energy- Meredian BESS | 319 Meridian 69 KV | Bosque | NORTH | 2025-05-01 | OTH | BA | 31.23 |  | 2023-03-10 | 2023-03-13 | 2023-06-09 | 2023-03-10 |  |  |  | No |  |  | Not Required
25INR0375 | NavBoot BESS | SS Completed, FIS Started, No IA | 1242 Mckinzie Owner | 8858 MCKENZIE4A 138kV | Nueces | COASTAL | 2025-06-01 | OTH | BA | 303.7 |  | 2023-03-10 | 2023-03-13 | 2023-06-09 | 2023-03-10 |  |  |  | No |  |  | Not Required
25INR0376 | Hawkins BESS | SS Completed, FIS Started, No IA | BRP BLUE TOPAZ 7, LLC | 85005 ELGATO4A 138 kV | Hidalgo | SOUTH | 2025-09-08 | OTH | BA | 150.45 |  | 2023-04-19 | 2023-05-03 | 2023-07-28 | 2023-04-19 |  |  |  | No |  |  | Not Required
25INR0377 | Proteus Vernon Solar SLF | SS Completed, FIS Started, No IA | Vernon Solar and Storage LLC (a Delaware LLC) | 6060 Vernon 138kV | Wilbarger | WEST | 2026-12-31 | SOL | PV | 75 |  | 2023-07-17 | 2023-03-27 | 2023-06-19 |  |  |  |  | No |  |  | Not Required
25INR0378 | Second Division Storage | SS Completed, FIS Started, No IA | Mound Creek Storage, LLC | Tap 138 kV SANBER_POI_8 (Bus# 43110) to WEST COLUMBIA (Bus# 43380) Ckt 60 Line | Brazoria | COASTAL | 2025-12-31 | OTH | BA | 0 |  | 2023-04-03 | 2023-04-19 | 2023-07-13 | 2023-03-15 |  |  |  | No |  |  | Not Required
25INR0379 | Starr Storage | SS Completed, FIS Started, No IA | Falcon Lake Storage, LLC | 8795 Roma 138kV | Starr | SOUTH | 2025-12-30 | OTH | BA | 0 | COD | 2023-04-03 | 2023-06-28 | 2023-09-22 | 2023-03-08 |  |  |  | No |  |  | Not Required
25INR0380 | Fike BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 9, LLC | 5754 Aderhold 138kV | Hidalgo | SOUTH | 2025-09-01 | OTH | BA | 200.83 |  | 2023-04-17 | 2023-05-15 | 2023-08-11 | 2023-04-19 |  |  |  | No |  |  | Not Required
25INR0382 | HappyDogSolar | SS Completed, FIS Started, No IA | Rosula Solar LLC | Tap 345kV 3704 Hog Creek Switch – 3687 Bell County East Switch | Milam | SOUTH | 2026-09-14 | SOL | PV | 85.54 |  | 2023-05-30 | 2023-06-07 | 2023-09-01 | 2023-05-25 |  |  |  | No |  |  | Not Required
25INR0384 | Zorro BESS | SS Completed, FIS Started, No IA | UR-Silo DevCo LLC | 138 kV Ben Wheeler (Bus# 6852) | Van Zandt | NORTH | 2025-07-02 | OTH | BA | 153.69 |  | 2023-06-13 | 2023-03-27 | 2023-06-19 |  |  |  |  | No |  |  | Not Required
25INR0385 | Bobcat Cameron BESS | SS Completed, FIS Started, No IA | Bobcat BESS, LLC | 5764 East Rio Hondo Substation 138kV | Cameron | COASTAL | 2025-12-01 | OTH | BA | 200.78 |  | 2023-04-06 | 2023-04-19 | 2023-07-14 | 2023-04-11 |  |  |  | No |  |  | Not Required
25INR0386 | Diaz BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 10, LLC | 8950 Olmito 138kV | Cameron | COASTAL | 2025-09-01 | OTH | BA | 244 |  | 2023-05-19 | 2023-05-22 | 2023-08-17 | 2023-05-17 |  | No |  | No |  |  | Not Required
25INR0389 | Stoneridge BESS | SS Completed, FIS Started, No IA | Stoneridge Solar, LLC | Tap 345 kV 13429 SANDOW SWITCH - 7040 AUSTROP CKT 1 | Milam | SOUTH | 2025-09-01 | OTH | BA | 101.9 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-03-09 |  |  |  | No |  |  | Not Required
25INR0390 | Macho Creek BESS | SS Completed, FIS Started, No IA | Macho Creek BESS, LLC | 8793 Rio Grande City 138kV | Starr | SOUTH | 2026-05-31 | OTH | BA | 150.56 |  | 2023-06-19 | 2023-06-28 | 2023-09-22 | 2023-06-06 |  |  |  | No |  |  | Not Required
25INR0391 | Purple Sage BESS 1 | SS Completed, FIS Started, No IA | Purple Sage, LLC | Anna 345 kV Bus# 2373. | Collin | NORTH | 2026-02-11 | OTH | BA | 156 |  | 2023-03-07 | 2023-03-08 | 2023-06-05 | 2023-03-07 |  |  |  | No |  |  | Not Required
25INR0392 | Purple Sage BESS 2 | SS Completed, FIS Started, No IA | Purple Sage, LLC | Anna 345 kV Bus# 2373 | Collin | NORTH | 2026-02-11 | OTH | BA | 156 |  | 2023-03-07 | 2023-03-08 | 2023-06-05 | 2023-03-07 |  |  |  | No |  |  | Not Required
25INR0393 | MICOT BESS | SS Completed, FIS Started, No IA | UR-Silo DevCo LLC | Tap 345kV 44645 Singleton - 46500 Tomball Ckt 74 | Montgomery | HOUSTON | 2025-05-30 | OTH | BA | 150 |  | 2023-05-25 | 2023-03-27 | 2023-06-23 |  |  |  |  | No |  |  | Not Required
25INR0394 | Orchard Ray BESS | SS Completed, FIS Started, No IA | Pettus BESS | 8593 PETTUS2A 69kV | Bee | SOUTH | 2025-05-01 | OTH | BA | 51.85 |  | 2023-05-22 | 2023-06-07 | 2023-09-01 | 2023-05-31 |  |  |  | No |  |  | Not Required
25INR0395 | Hinkell BESS | SS Completed, FIS Started, No IA | Reveille BESS | 8612 Reveille 138kV | La Salle | SOUTH | 2025-05-01 | OTH | BA | 78.05 |  | 2023-08-15 | 2023-08-21 | 2023-11-17 | 2023-08-14 |  |  |  | No |  |  | Not Required
25INR0396 | Stewart Grady BESS | SS Completed, FIS Started, No IA | Grady BESS | Tap 138kV 10031 LilGrady – 11368 Expanse Switch | Martin | WEST | 2026-09-15 | OTH | BA | 150.5 |  | 2023-05-22 | 2023-05-26 | 2023-08-22 | 2023-05-01 |  |  |  | No |  |  | Not Required
25INR0397 | Beeman BESS | SS Completed, FIS Started, No IA | Waelder BESS | 69kV Waelder Substation (7232) | Gonzales | SOUTH | 2025-05-01 | OTH | BA | 50.18 |  | 2023-04-07 | 2023-04-19 | 2023-07-13 | 2023-03-22 |  |  |  | No |  |  | Not Required
25INR0399 | Blossomheath BESS | SS Completed, FIS Started, No IA | Taurbeng LLC | tap VENUS SWITCH (#1907) – SAM SWITCH (#68090) 345 kV line | Ellis | NORTH | 2026-11-28 | OTH | BA | 300.78 |  | 2023-05-02 | 2023-05-26 | 2023-08-17 | 2023-05-23 |  |  |  | No |  |  | Not Required
25INR0400 | Maldives Solar (Alternate POI) | SS Completed, FIS Started, IA | Maldives Solar LLC | Tap 345kV 59900 Long Draw - 11318 Scurry County South | Scurry | WEST | 2027-07-01 | SOL | PV | 184 |  | 2023-07-08 | 2023-07-18 | 2023-10-15 | 2023-07-05 |  |  | 2023-12-01 | No |  |  | Not Required
25INR0401 | WOE Gyp King Wind | SS Completed, FIS Started, No IA | White Oak Energy, LLC | 33798 GYP8 138kV | King | WEST | 2025-07-01 | WIN | WT | 315 |  | 2023-04-18 | 2023-04-19 | 2023-07-12 | 2023-04-17 |  |  |  | No |  |  | Not Required
25INR0402 | Driet BESS | SS Completed, FIS Started, No IA | Weimar BESS | 7254 WEIMAR8 138kV | Colorado | SOUTH | 2025-06-01 | OTH | BA | 150.52 |  | 2023-05-22 | 2023-06-07 | 2023-09-01 | 2023-05-31 |  |  |  | No |  |  | Not Required
25INR0405 | Pledgor BESS | SS Completed, FIS Started, No IA | Pledgor BESS | 43120- Centerpoint Pledger Substation | Matagorda | COASTAL | 2025-06-01 | OTH | BA | 100.33 |  | 2023-04-26 | 2023-05-03 | 2023-07-31 | 2023-04-25 |  |  |  | No |  |  | Not Required
25INR0414 | Rogers Creek BESS | SS Completed, FIS Started, No IA | Dialville BESS | Tap 138 KV DailVille (3160) - Neches Pump (3296) | Cherokee | NORTH | 2026-09-15 | OTH | BA | 100.33 |  | 2023-05-03 | 2023-05-15 | 2023-08-11 | 2023-05-03 |  |  |  | No |  |  | Not Required
25INR0416 | Proteus Vernon Storage SLF | SS Completed, FIS Started, No IA | Vernon Solar and Storage LLC (a Delaware LLC) | 6060 Vernon 138kV | Wilbarger | WEST | 2026-12-31 | OTH | BA | 0 |  | 2023-07-13 | 2023-03-27 | 2023-06-19 |  |  |  |  | No |  |  | Not Required
25INR0417 | Mesa View Storage | SS Completed, FIS Started, No IA | Mesa View Storage, LLC | Tap 345 kV KINGMTSW (#842) to NORTMC (#76000) | Upton | WEST | 2025-05-31 | OTH | BA | 501.9 |  | 2023-04-11 | 2023-04-19 | 2023-07-12 | 2023-04-12 |  |  |  | No |  |  | Not Required
25INR0418 | Palacios BESS | SS Completed, FIS Started, No IA | BRP BLUE TOPAZ 11, LLC | 5767 HIWAY511SUB8 138kV | Cameron | COASTAL | 2025-09-08 | OTH | BA | 125.69 |  | 2023-04-25 | 2023-05-15 | 2023-08-11 | 2023-05-08 |  |  |  | No |  |  | Not Required
25INR0419 | Marengo BESS | SS Completed, FIS Started, No IA | BRP BLUE TOPAZ 8, LLC | 8640 Kelvin Station 138kV (AEP) | Cameron | COASTAL | 2025-09-08 | OTH | BA | 120.72 |  | 2023-04-25 | 2023-05-15 | 2023-08-11 | 2023-05-08 |  | No |  | No |  |  | Not Required
25INR0420 | Houston BESS | SS Completed, FIS Started, No IA | SMT Houston | Tap 138 kV LAUDER (#46002) - RITTENHOUSE (#46282) ckt 95 | Harris | HOUSTON | 2025-09-29 | OTH | BA | 227.9 |  | 2023-03-31 | 2023-04-07 | 2023-07-03 | 2023-03-28 |  |  |  | No |  |  | Not Required
25INR0421 | Aldrin 138 BESS | SS Completed, FIS Started, No IA | Aldrin Energy Storage LLC | (Bus: 39015) North Alvin TNMP 138kV | Brazoria | COASTAL | 2025-07-15 | OTH | BA | 207 |  | 2023-05-02 | 2023-05-15 | 2023-08-11 | 2023-05-04 |  |  |  | No |  |  | Not Required
25INR0422 | Waterloo Solar 1 | SS Completed, FIS Started, No IA | Waterloo Solar, LLC | AUSTROP TO GARFIELD 345kV LINE [Bus # 7040 - 7048] | Bastrop | SOUTH | 2025-06-01 | SOL | PV | 200.64 |  | 2023-04-18 | 2023-04-19 | 2023-07-12 | 2023-03-30 |  |  |  | No |  |  | Not Required
25INR0423 | Brackens Solar | SS Completed, FIS Started, No IA | Brackens Solar | 3558 Ranchland 138 kV | Freestone | NORTH | 2026-08-07 | SOL | PV | 179.57 | COD | 2023-05-04 | 2023-05-15 | 2023-08-11 | 2023-05-01 |  |  |  | No |  |  | Not Required
25INR0424 | Brackens BESS | SS Completed, FIS Started, No IA | Brackens BESS | 3558 Ranchland 138 kV | Freestone | NORTH | 2026-08-07 | OTH | BA | 104.31 | COD | 2023-04-19 | 2023-05-03 | 2023-07-28 | 2023-04-19 |  |  |  | No |  |  | Not Required
25INR0425 | Aldrin 345 BESS | SS Completed, FIS Started, No IA | Aldrin Energy Storage LLC | (Bus: 43030) Meadow 345kV substation | Brazoria | COASTAL | 2025-07-15 | OTH | BA | 362 |  | 2023-05-10 | 2023-05-15 | 2023-08-11 | 2023-05-05 |  |  |  | No |  |  | Not Required
25INR0430 | Hackberry Creek Solar | SS Completed, FIS Started, No IA | Hackberry Creek Solar LLC | Tap 345kV 1058 Longshore - 1030 Morgan Creek | Mitchell | WEST | 2027-06-01 | SOL | PV | 250 | COD | 2023-07-19 | 2023-07-31 | 2023-10-27 | 2023-07-19 |  |  |  | No |  |  | Not Required
25INR0431 | Millennium Energy Storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Development, LLC | Tap 138kV 23837 Buffalo - 23839 Triangle | Martin | WEST | 2026-09-21 | OTH | BA | 102.58 |  | 2023-07-13 | 2023-05-03 | 2023-07-31 |  |  |  |  | No |  |  | Not Required
25INR0432 | Brotherton Storage | SS Completed, FIS Completed, No IA | Belltown Power Texas 2 | 6937 Tucker Sub 138kV | Anderson | NORTH | 2025-05-31 | OTH | BA | 176.13 |  | 2023-04-12 | 2023-04-19 | 2023-07-13 | 2023-04-12 | 2023-12-08 | No |  | No |  |  | Not Required
25INR0434 | Bluegill BESS | SS Completed, FIS Started, No IA | Bluegill BESS | Tap 138 kV 40130 Atascocita - 40690 East Gate | Harris | HOUSTON | 2026-10-01 | OTH | BA | 501.9 |  | 2023-06-07 | 2023-06-28 | 2023-09-21 | 2023-05-18 |  |  |  | No |  |  | Not Required
25INR0436 | Hess King Solar Farm | SS Completed, FIS Started, No IA | Facility Innovations Group | 8212 DILLEYSW4A 138kV | Frio | SOUTH | 2025-12-31 | SOL | PV | 130 |  | 2023-08-25 | 2023-04-19 | 2023-07-13 |  |  |  |  | No |  |  | Not Required |  |  |  | 2023-09-01 | 2025-09-01
25INR0439 | Stephens Ranch Wind Repower | SS Completed, FIS Started, No IA | Stephens Ranch Wind Energy, LLC | 345 kV Long Draw (Bus# 59900) | Borden | WEST | 2025-09-15 | WIN | WT | 392.37 |  | 2023-06-07 | 2023-06-28 | 2023-09-20 | 2023-05-15 |  |  |  | No |  |  | Not Required
25INR0440 | Bronc Rodeo Solar Project | SS Completed, FIS Started, No IA | Energiekontor US Texas SP 16 LLC | Tap 345kV 3405 Tradinghouse SES - 3412 Temple Pecan | Falls | NORTH | 2027-04-12 | SOL | PV | 121.6 | COD | 2023-09-19 | 2023-05-03 | 2023-07-28 |  |  |  |  | No | Not Required | Not Required | Not Required
25INR0441 | Dios BESS | SS Completed, FIS Started, No IA | Dios BESS, LLC | 8117 GANADO138kV | Jackson | SOUTH | 2025-12-31 | OTH | BA | 201.08 |  | 2023-04-26 | 2023-05-15 | 2023-08-11 | 2023-05-08 |  |  |  | No |  |  | Not Required
25INR0442 | Happy Dog Storage | SS Completed, FIS Started, No IA | Rosula Solar LLC | Tap 345kV 3704 Hog Creek Switch – 3687 Bell County East Switch | Milam | SOUTH | 2026-09-14 | OTH | BA | 60.16 |  | 2023-05-23 | 2023-06-07 | 2023-09-01 | 2023-06-02 |  |  |  | No |  |  | Not Required
25INR0444 | Peridot Storage | SS Completed, FIS Started, No IA | BT Castro Storage, LLC | 5836 North Batesville 69kV | Zavala | SOUTH | 2025-12-31 | OTH | BA | 50.48 |  | 2023-05-05 | 2023-05-26 | 2023-08-22 | 2023-05-22 |  |  |  | No |  |  | Not Required
25INR0447 | Waterloo BESS 1 | SS Completed, FIS Started, No IA | Waterloo Solar, LLC | AUSTROP TO GARFIELD 345kV LINE [Bus # 7040 - 7048] | Bastrop | SOUTH | 2025-06-01 | OTH | BA | 105.64 |  | 2023-05-03 | 2023-05-15 | 2023-08-11 | 2023-05-03 |  |  |  | No |  |  | Not Required
25INR0451 | Tres Rios Ranch BESS | SS Completed, FIS Started, No IA | LectricWind LLC | 76015 L_CEDACA5_1Y 345kV | Upton | WEST | 2025-12-31 | OTH | BA | 0 |  | 2023-05-22 | 2023-05-26 | 2023-08-22 | 2023-05-23 |  |  |  | No |  |  | Not Required
25INR0452 | Spaniel Farm Solar Project | SS Completed, FIS Started, No IA | Energiekontor US Texas SP 18 LLC | Tap 138 kV 2241 Ennis West Switch - 12320 Templeton | Ellis | NORTH | 2027-04-12 | SOL | PV | 100.52 | COD | 2023-09-26 | 2023-05-03 | 2023-07-28 |  |  |  |  | No |  |  | Not Required
25INR0455 | John Bull BESS | SS Completed, FIS Started, No IA | BRP BLUE TOPAZ 13, LLC | 8482 WEIL TRC4A 138kV | Nueces | COASTAL | 2025-09-01 | OTH | BA | 147.42 |  | 2023-07-17 | 2023-07-31 | 2023-10-27 | 2023-07-27 |  |  |  | No |  |  | Not Required
25INR0456 | Harden BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 14, LLC | 7671 Macedonia 138kV | Waller | HOUSTON | 2025-09-01 | OTH | BA | 301.29 |  | 2023-07-17 | 2023-07-31 | 2023-10-27 | 2023-07-27 |  |  |  | No |  |  | Not Required
25INR0460 | Acker BESS | SS Completed, FIS Started, No IA | Ogallala BESS LLC | 23912 Ogallala 345 kV | Castro | PANHANDLE | 2026-09-15 | OTH | BA | 301.04 |  | 2023-05-26 | 2023-06-07 | 2023-09-01 | 2023-05-09 |  |  |  | No |  |  | Not Required
25INR0461 | Proteus Oak Forest Solar | SS Completed, FIS Started, No IA | Oak Forest Solar and Storage, LLC (a Delaware LLC) | 6053 KIRKLAND2A 69Kv | Childress | PANHANDLE | 2025-12-31 | SOL | PV | 100 |  | 2023-07-25 | 2023-07-31 | 2023-10-27 | 2023-07-25 |  |  |  | No |  |  | Not Required
25INR0462 | Proteus Oak Forest Storage SLF | SS Completed, FIS Started, No IA | Oak Forest Solar and Storage, LLC (a Delaware LLC) | 6053 Kirkland Substation 69kV POIB is located approximately 3 miles from "Oak Forest Solar and Storage" substation. | Childress | PANHANDLE | 2025-12-31 | OTH | BA | 0 |  | 2023-07-28 | 2023-07-31 | 2023-10-27 | 2023-07-17 |  |  |  | No |  |  | Not Required
25INR0464 | Unruh Solar | SS Completed, FIS Started, No IA | BT Unruh Solar, LLC | Tap 69kV 1785 BAGWELL1_9 – 1772 LAMARBM1_9 | Red River | NORTH | 2025-12-31 | SOL | PV | 150.74 |  | 2023-07-11 | 2023-07-18 | 2023-10-10 | 2023-07-11 |  |  |  | No |  |  | Not Required
25INR0465 | Unruh Storage | SS Completed, FIS Started, No IA | BT Unruh Solar, LLC | Tap 69kV 1785 BAGWELL1_9 – 1772 LAMARBM1_9 69kV line | Red River | NORTH | 2025-12-31 | OTH | BA | 50.47 |  | 2023-07-04 | 2023-07-10 | 2023-10-03 | 2023-06-29 |  |  |  | No |  |  | Not Required
25INR0466 | Yooperlite Storage | SS Completed, FIS Started, No IA | BT Yooperlite Storage, LLC | Tap 138 kV 580 Westbrook Switch - 588 Willow | Wise | NORTH | 2026-05-29 | OTH | BA | 175.65 |  | 2023-06-13 | 2023-06-28 | 2023-09-20 | 2023-06-06 |  |  |  | No |  |  | Not Required
25INR0467 | Bocanova BESS | SS Completed, FIS Started, IA | Bocanova Power LLC | 39030 TNALVIN 138kV | Brazoria | COASTAL | 2025-06-01 | OTH | BA | 300.92 |  | 2023-06-06 | 2023-06-07 | 2023-09-01 | 2023-05-26 |  | No | 2023-11-14 | Yes |  |  | Not Required
25INR0471 | Tyler BESS | SS Completed, FIS Started, No IA | SMT Tyler LLC | 3104 Shamburger Switch 138kV | Smith | NORTH | 2026-09-21 | OTH | BA | 305.3 |  | 2023-07-02 | 2023-07-10 | 2023-10-03 | 2023-07-03 |  |  |  | No |  |  | Not Required
25INR0472 | Crowded Star I BESS | SS Completed, FIS Started, No IA | Jones City Solar, LLC | 68014 Open Sky 345kV | Jones | WEST | 2025-12-31 | OTH | BA | 101.37 |  | 2023-07-22 | 2023-08-21 | 2023-11-02 | 2023-08-16 |  |  |  | No |  |  | Not Required
25INR0473 | Crowded Star II BESS | SS Completed, FIS Started, No IA | Jones City Solar II, LLC | 68014 Open Sky | Jones | WEST | 2025-12-31 | OTH | BA | 101.37 |  | 2023-07-25 | 2023-08-21 | 2023-11-02 | 2023-08-09 |  |  |  | No |  |  | Not Required
25INR0475 | Castle Corral BESS | SS Completed, FIS Started, No IA | Castle Corral BESS, LLC | 345 kV Russell Gap Switching Station Bus #3348 | Mills | NORTH | 2026-09-14 | OTH | BA | 206.4 |  | 2023-07-26 | 2023-07-31 | 2023-10-27 | 2023-07-26 |  |  |  | No |  |  | Not Required
25INR0480 | Bell Creek BESS | SS Completed, FIS Started, No IA | West Columbia BESS1 LLC | Tap 138kV 39500 West Colombia - 39703 FM524 | Brazoria | COASTAL | 2025-12-31 | OTH | BA | 200.9 | FIS Request | 2023-11-29 | 2023-06-28 | 2023-09-21 |  |  |  |  | No |  |  | Not Required
25INR0482 | Vault Solar | SS Completed, FIS Started, No IA | PPM THR Solar | Tap #331 Rwmiller - #320 Jaybird 138kV | Palo Pinto | NORTH | 2026-12-31 | SOL | PV | 108.5 |  | 2023-06-20 | 2023-06-28 | 2023-09-20 | 2023-06-16 |  |  |  | No |  |  | Not Required
25INR0485 | Diver Energy Storage | SS Started, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap #3390 Jewett to #3399 Rattle Snake Rd 345kV | Limestone | NORTH | 2025-12-31 | OTH | BA | 100 |  | 2023-09-13 |  |  | 2023-09-01 |  |  |  | No |  |  | Not Required
25INR0487 | Marick Rose BESS | SS Completed, FIS Started, No IA | Marick BESS | Tap 138kV 44521 Marick - 44615 Rosenberg Ckt 60 | Fort Bend | HOUSTON | 2026-05-01 | OTH | BA | 50.18 |  | 2023-07-01 | 2023-07-10 | 2023-10-05 | 2023-06-23 |  |  |  | No |  |  | Not Required
25INR0492 | Blue Summit Energy Storage | SS Started, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | 61001 JIM TREECE 345kV | Wilbarger | WEST | 2026-07-01 | OTH | BA | 75 |  | 2023-08-28 | 2023-10-20 |  | 2023-10-18 |  |  |  | No |  |  | Not Required
25INR0494 | Willow Beach Wind | SS Started, FIS Started, No IA | ACE DevCo NC LLC | Tap 138 kV Bus# 42100 HUD_8 – Bus# 42960 MUSTNG_S04_8 138kV CKT# 4 | Brazoria | COASTAL | 2027-10-01 | WIN | WT | 204 |  | 2023-08-28 | 2023-10-13 |  | 2023-09-20 |  |  |  | No |  |  | Not Required
25INR0495 | Dolomite Storage | SS Completed, FIS Started, No IA | BT Wilson Storage, LLC | 218 Rockett 69kV | Ellis | NORTH | 2026-12-01 | OTH | BA | 125.7 |  | 2023-08-15 | 2023-09-08 | 2023-12-04 | 2023-08-22 |  |  |  | No |  |  | Not Required
25INR0497 | Stegall Solar | SS Completed, FIS Started, No IA | BT Martin Solar, LLC | Elliott (Bus #53) to Franklin (Bus #57) 69kV Transmission Line | Robertson | NORTH | 2026-12-31 | SOL | PV | 81.57 |  | 2023-08-15 | 2023-08-21 | 2023-11-06 | 2023-08-02 |  |  |  | No |  |  | Not Required
25INR0498 | Stegall Storage | SS Completed, FIS Started, No IA | BT Martin Solar, LLC | Tap connection to a new switching station on the Elliott (Bus #53) - Franklin (Bus #57) 69 kV Transmission Line | Robertson | NORTH | 2026-12-31 | OTH | BA | 50.47 |  | 2023-08-07 | 2023-08-21 | 2023-11-06 | 2023-08-15 |  |  |  | No |  |  | Not Required
25INR0501 | Longday Solar SLF | SS Completed, FIS Started, No IA | Longday Solar | Tap138 kV 8252 Brackettville - 8260 Escondido | Kinney | SOUTH | 2027-07-15 | SOL | PV | 200.8 |  | 2023-07-22 | 2023-07-31 | 2023-10-27 | 2023-07-20 |  |  |  | No | Not Required | Not Required | Not Required
25INR0502 | Longday BESS SLF | SS Completed, FIS Started, No IA | Longday Solar | Tap 138 kV 8252 Brackettville - 8260 Escondido | Kinney | SOUTH | 2027-07-15 | OTH | BA | 0 |  | 2023-07-22 | 2023-07-31 | 2023-10-27 | 2023-07-20 |  |  |  | No |  |  | Not Required
25INR0503 | Uhland Maxwell Expansion | SS Completed, FIS Started, No IA | Lower Colorado River Authority | 7041 John Dumas 345kV | Caldwell | SOUTH | 2026-04-07 | GAS | IC | 188.4 |  | 2023-10-04 | 2023-09-22 | 2023-12-14 |  |  |  |  | No |  | Not Required
25INR0510 | Deer BESS | SS Completed, FIS Started, No IA | GRS BESS Texas Two | 1687 BLOOSOM_T8 138kV | Lamar | NORTH | 2025-10-31 | OTH | BA | 102.31 |  | 2023-07-29 | 2023-09-08 | 2023-12-01 | 2023-08-21 |  |  |  | No |  |  | Not Required
25INR0511 | Pearl Moon | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | Tap 345kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2028-03-31 | SOL | PV | 208 | COD | 2023-07-31 | 2023-09-07 | 2023-12-06 | 2023-08-23 |  |  |  | No | Not Required | Not Required | Not Required
25INR0512 | Monument Hill Solar | SS Started, FIS Started, No IA | RWE Solar Development, LLC | Tap 345kV 7055 Fayette - 9074 Lytton Springs | Fayette | SOUTH | 2027-06-01 | SOL | PV | 200 |  | 2023-07-31 | 2023-10-13 |  | 2023-08-23 |  |  |  | No |  |  | Not Required
25INR0513 | Kahla Storage | SS Completed, FIS Started, No IA | BT Kahla Storage, LLC | Tap 345kV 46020 Limestone 967 Gibbons Creek Ckt 18 | Leon | NORTH | 2026-04-30 | OTH | BA | 200.9 |  | 2023-08-16 | 2023-08-21 | 2023-11-17 | 2023-08-15 |  |  |  | No |  |  | Not Required
25INR0515 | Fagus Storage SLF | SS Started, FIS Started, No IA | Greenalia Energy Storage MISAE II LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2025-05-15 | OTH | BA | 0 |  | 2023-10-19 | 2023-10-25 |  | 2023-09-22 |  |  |  | No |  |  | Not Required
25INR0540 | Palm Bluff Energy Storage | SS Started, FIS Started, No IA | Palm Bluff Energy Storage, LLC | 138kV tap on Dublin1_8 #1636 to Stphnvil_8 #1641 transmission line. | Erath | NORTH | 2027-04-15 | OTH | BA | 101.2 |  | 2023-10-11 | 2023-10-13 |  | 2023-10-11 |  |  |  | No | Not Required | Not Required | Not Required
25INR0541 | Port City Energy Storage | SS Started, FIS Started, No IA | Port City Energy Storage, LLC | Tap 138kV 80258 Mayo4A - 80260 Gila4A | San Patricio | COASTAL | 2026-06-15 | OTH | BA | 101.2 | COD | 2023-10-17 | 2023-10-25 |  | 2023-10-17 |  |  |  | No | Not Required | Not Required | Not Required
25INR0542 | Hynes Bay Energy Storage | SS Started, FIS Started, No IA | Hynes Bay Energy Storage, LLC | Tap 138kV 5546 DANEVANG SW - 8121 BLESSING | Wharton | SOUTH | 2026-04-15 | OTH | BA | 101.2 | COD | 2023-10-16 | 2023-10-25 |  | 2023-10-16 |  |  |  | No | Not Required | Not Required | Not Required
25INR0543 | Pelton Lake Energy Storage | SS Started, FIS Started, No IA | Pelton Lake Energy Storage, LLC | Line tap to W_A_P_POI8A #44010-NASH_S02_8 #42980 CKT #2 transmission line. | Brazoria | COASTAL | 2026-06-15 | OTH | BA | 101.2 |  | 2023-11-01 | 2023-11-14 |  | 2023-10-10 |  |  |  | No |  |  | Not Required
25INR0544 | Palacios Bay Energy Storage | SS Started, FIS Started, No IA | Palacios Bay Energy Storage, LLC | Tap 138kV #8115 WADSWORT4A - #8139 CELNEBC4B | Matagorda | COASTAL | 2026-06-15 | OTH | BA | 101.2 | COD | 2023-10-10 | 2023-10-19 |  | 2023-10-10 |  |  |  | No | Not Required | Not Required | Not Required
25INR0545 | Blue Creek Energy Storage | SS Started, FIS Started, No IA | Blue Creek Energy Storage, LLC | Tap 138kV 42985 DYANN_POI8 - 43190 S_LANE_B138 Ckt 60 | Wharton | SOUTH | 2026-06-15 | OTH | BA | 101.2 |  | 2023-10-11 | 2023-10-13 |  | 2023-10-11 |  |  |  | No |  |  | Not Required
25INR0552 | HarryoungBESS | SS Completed, FIS Started, No IA | Gransolar Texas Four LLC | 8319 Rio Hondo sub 138kV | Cameron | COASTAL | 2027-05-15 | OTH | BA | 190.01 |  | 2023-09-26 | 2023-10-04 | 2023-12-19 | 2023-09-19 |  |  |  | No | Not Required | Not Required | Not Required
25INR0555 | Stargazer Solar | SS Started, FIS Started, No IA | Stargazer Solar LLC | 44010 WA Parish - 42980 Nash 138 kV Ckt 02 | Brazoria | COASTAL | 2025-12-01 | SOL | PV | 157.7 |  | 2023-10-11 | 2023-10-30 |  | 2023-10-23 |  |  |  | No | Not Required | Not Required | Not Required
25INR0556 | Stargazer BESS | SS Started, FIS Started, No IA | Stargazer Solar LLC | 44010 WA Parish - 42980 Nash 138 kV | Brazoria | COASTAL | 2025-12-01 | OTH | BA | 104.5 |  | 2023-10-20 | 2023-10-30 |  | 2023-10-23 |  |  |  | No |  |  | Not Required
25INR0557 | McCamey's Castle Battery | SS Started, FIS Started, No IA | Castle Storage, LLC | 76597 Robbins Switch 138 kV | Upton | WEST | 2025-12-15 | OTH | BA | 409.6 |  | 2023-09-29 | 2023-10-13 |  | 2023-10-09 |  |  |  | No |  |  | Not Required
25INR0558 | Ayass BESS | SS Started, FIS Started, No IA | Harvick BESS, LLC | 6206 Bush Knob 69kV | Throckmorton | WEST | 2027-07-01 | OTH | BA | 51.28 | COD | 2023-11-27 | 2023-12-04 |  | 2023-11-15 |  |  |  | No |  |  | Not Required
25INR0562 | Canyonland Energy Storage | SS Started, FIS Started, No IA | Canyonland Energy Storage, LLC | 1649 HASSE_P8 138kV | Comanche | NORTH | 2025-09-15 | OTH | BA | 101.2 |  | 2023-11-14 | 2023-11-30 |  | 2023-10-23 |  |  |  | No |  |  | Not Required
25INR0566 | Copano Bay Energy Storage | SS Started, FIS Started, No IA | Copano Bay Energy Storage, LLC | Tap 138kV 42980 Nash - 44010 WA Parish Ckt 2 | Brazoria | COASTAL | 2026-06-15 | OTH | BA | 101.2 |  | 2023-10-22 | 2023-10-25 |  | 2023-10-17 |  |  |  | No | Not Required | Not Required | Not Required
26INR0001 | Turin TxHSR TPSS HN-6 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | 8 Crutchfield 138kV | Grimes | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-10-22 | 2019-09-27 | 2021-04-28 | 2019-09-27 |  |  |  | No
26INR0004 | GRIMES SOLAR | SS Completed, FIS Started, No IA | CG Grimes County LLC | 40600 Roans Prairie 345kV | Grimes | NORTH | 2026-02-15 | SOL | PV | 153.45 |  | 2022-03-09 | 2022-03-14 | 2022-06-03 | 2022-03-07 |  |  |  | No |  |  | Not Required
26INR0008 | Puerto Del Sol 1 | SS Completed, FIS Started, No IA | PUERTO DEL SOL, LLC | Tap 345kV 79500 Palmito - 79501 King Fisher Ckt 1 | Cameron | COASTAL | 2026-12-31 | SOL | PV | 214.62 |  | 2023-01-20 | 2022-05-16 | 2022-08-13 |  |  |  |  | No | Not Required | Not Required | Not Required
26INR0014 | Greenwolfe Solar Alt POI | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345 kV line from Farmersville Switch (#1685) to Cyclone Switch (#11689) | Hunt | NORTH | 2026-09-24 | SOL | PV | 274.14 |  | 2022-10-24 | 2022-11-15 | 2023-02-10 | 2022-11-07 |  |  |  | No |  |  | Not Required
26INR0018 | Galactic Storage SLF | SS Completed, FIS Started, No IA | UKA North America, LLC | Tap 138kV 1744 Gordonville - 11704 Sherman West | Grayson | NORTH | 2026-11-15 | OTH | BA | 0 |  | 2022-08-24 | 2022-09-02 | 2022-11-30 | 2022-08-10 |  |  |  | No |  |  | Not Required
26INR0019 | HyFuels Green Lake Solar | SS Completed, FIS Started, No IA | HyFuels Green Lake Solar LLC | Tap 8154 INEOS/Green Lake (VISTRON4B) - 8152 North Carbide (NCARBIDE4A) 138kV | Victoria | SOUTH | 2026-10-01 | SOL | PV | 144.56 |  | 2023-06-09 | 2022-09-27 | 2022-12-22 |  |  |  |  | No |  |  | Not Required
26INR0021 | HyFuels Western Farmland Wind | SS Completed, FIS Started, No IA | HyFuels Green Lake Wind LLC | Tap 345kV 8715 RADIANT7A - 8728 Cobra | Victoria | SOUTH | 2026-04-02 | WIN | WT | 255.8 |  | 2023-07-01 | 2022-09-27 | 2022-12-22 |  |  |  |  | No |  |  | Not Required
26INR0022 | Bowhead Storage 2 | SS Completed, FIS Started, No IA | Baffin Bay Solar, LLC | Tap 138kV 8519 Kleberg-8518 Kingsville | Kleberg | COASTAL | 2026-01-15 | OTH | BA | 0 |  | 2022-08-30 | 2022-09-21 | 2022-12-16 | 2022-09-19 |  |  |  | No |  |  | Not Required
26INR0023 | Leon Solar Park | SS Completed, FIS Completed, No IA | MISAE SOLAR IV | Tap 138kV Grapeland Magnolia Tap (bus #3355) to Pleasant Springs POI (bus# 3357) section of the Jewett -Crockett 138kV Line | Leon | NORTH | 2026-07-01 | SOL | PV | 210.1 |  | 2022-08-11 | 2022-09-15 | 2022-12-13 | 2022-08-27 | 2023-09-22 | Yes |  | No |  |  | Not Required
26INR0024 | Becerra Creek Storage 1 | SS Completed, FIS Started, No IA | Bordas Renewable Energy, LLC | 345 kV Cenizo Substation (#80220) | Webb | SOUTH | 2026-12-01 | OTH | BA | 125.62 |  | 2022-09-19 | 2022-09-21 | 2022-12-19 | 2022-09-07 |  |  |  | No |  |  | Not Required
26INR0028 | HyFuels Calhoun Solar | SS Completed, FIS Started, No IA | HyFuels Green Lake Solar LLC | Tap 345kV 8715 RADIANT7A - 8728 COBRA7A | Victoria | SOUTH | 2026-10-01 | SOL | PV | 301.82 |  | 2023-07-17 | 2022-10-18 | 2023-01-15 |  |  |  |  | No |  |  | Not Required
26INR0030 | Perry Creek Solar SLF | SS Completed, FIS Started, No IA | Perry Creek Solar, LLC | 345kV Navarro (#68091) to Limestone (# 46020) | Freestone | NORTH | 2027-03-24 | SOL | PV | 102.04 |  | 2022-11-08 | 2022-12-07 | 2023-03-04 | 2022-11-08 |  |  |  | No | Not Required | Not Required | Not Required
26INR0031 | Perry Creek Storage SLF | SS Completed, FIS Started, No IA | Perry Creek Solar, LLC | 345kV Navarro (#68091) to Limestone (# 46020) | Freestone | NORTH | 2027-03-24 | OTH | BA | 0 |  | 2022-11-08 | 2022-12-07 | 2023-03-04 | 2022-11-08 |  |  |  | No |  |  | Not Required
26INR0033 | Fairway Storage | SS Completed, FIS Started, No IA | Fairway Storage LLC | Tap 138kV 3503 FAIRWPOD_8 - 196 FAIRFIELD | Freestone | NORTH | 2026-05-31 | OTH | BA | 121.03 |  | 2023-02-17 | 2022-11-07 | 2023-02-04 |  |  |  |  | No |  |  | Not Required
26INR0034 | Bracero Pecan Storage | SS Completed, FIS Started, No IA | Bracero Pecan Storage LLC | 60716 SARAGOSA 138kV | Reeves | WEST | 2026-06-01 | OTH | BA | 232 |  | 2023-07-13 | 2022-11-07 | 2023-02-04 |  |  |  |  | No |  |  | Not Required
26INR0035 | Country Haven Energy Storage | SS Completed, FIS Started, No IA | 174 Power Global Properties, LLC | 138 kV Lone Oak substation (Bus #6871) | Rains | NORTH | 2026-06-15 | OTH | BA | 72.05 |  | 2023-03-08 | 2023-03-13 | 2023-06-09 | 2023-02-16 |  |  |  | No |  |  | Not Required
26INR0042 | Valhalla Solar | SS Completed, FIS Started, No IA | Industrial Papa Project LLC | Tap 138 kV 42215 Copper to 42195 Booster | Brazoria | COASTAL | 2026-05-31 | SOL | PV | 306.8 |  | 2023-03-08 | 2023-03-09 | 2023-06-05 | 2023-03-08 |  | No |  | No |  |  | Not Required
26INR0045 | LUND STORAGE CENTER 1 | SS Completed, FIS Started, No IA | Lund Storage Center 1, LLC | TAP 138 KV LINE AND CREATE NEW BUS BETWEEN KIMBRO (7337) AND ELGIN SWITCH (3650) | Bastrop | SOUTH | 2026-12-31 | OTH | BA | 407.55 |  | 2023-05-26 | 2023-01-17 | 2023-04-14 |  |  |  |  | No |  |  | Not Required
26INR0046 | Paluxy Solar | SS Completed, FIS Started, No IA | S&S Renewables LLC | Double tapping: 345kV 5915 STP - 5133 Elm Creek ckt#1 and 345kV 5068 Cachena – 5323 Old Hickory ckt#2 | Victoria | SOUTH | 2026-03-31 | SOL | PV | 1029.06 |  | 2022-12-13 | 2023-01-03 | 2023-03-30 | 2022-12-27 |  |  |  | No |  |  | Not Required
26INR0047 | Paluxy Storage | SS Completed, FIS Started, No IA | S&S Renewables LLC | Double tapping: 345kV 5915 STP - 5133 Elm Creek ckt#1 and 345kV 5068 Cachena – 5323 Old Hickory ckt#2 | Victoria | SOUTH | 2026-03-31 | OTH | BA | 511.68 |  | 2022-12-14 | 2023-01-03 | 2023-03-30 | 2022-12-12 |  |  |  | No |  |  | Not Required
26INR0049 | Calpine Freestone Peaker 1 | SS Completed, FIS Started, No IA | Freestone Power Generation, LLC | 3134 RICHLAND CHAMBERS 345kV (PSS/E Bus Name: RICHLND1_5) | Freestone | NORTH | 2026-05-23 | GAS | GT | 228 |  | 2023-04-12 | 2023-04-19 | 2023-07-13 | 2023-04-11 |  |  |  | No
26INR0068 | Charro Creek Solar 1 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-05-31 | SOL | PV | 203 |  | 2023-01-23 | 2023-01-30 | 2023-04-28 | 2023-02-10 |  |  |  | No |  |  | Not Required
26INR0069 | Charro Creek Storage 1 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-05-31 | OTH | BA | 0 |  | 2023-02-27 | 2023-03-08 | 2023-04-28 | 2023-02-15 |  |  |  | No |  |  | Not Required
26INR0070 | Charro Creek Solar 2 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-05-31 | SOL | PV | 203 |  | 2023-02-27 | 2023-03-08 | 2023-06-01 | 2023-02-15 |  |  |  | No |  |  | Not Required
26INR0071 | Charro Creek Storage 2 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-05-31 | OTH | BA | 0 |  | 2023-02-27 | 2023-03-08 | 2023-06-01 | 2023-02-15 |  |  |  | No |  |  | Not Required
26INR0072 | Charro Creek Solar 3 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap on PAWNEESW5 (#5725) - COLETO7A (#8164) Line | Karnes | SOUTH | 2026-05-31 | SOL | PV | 203 |  | 2023-02-27 | 2023-03-08 | 2023-06-01 | 2023-02-15 |  |  |  | No |  |  | Not Required
26INR0073 | Charro Creek Storage 3 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-05-31 | OTH | BA | 0 |  | 2023-01-23 | 2023-01-30 | 2023-04-28 | 2023-02-10 |  |  |  | No |  |  | Not Required
26INR0074 | Anila Solar | SS Completed, FIS Started, No IA | Alina Energy LLC | Tap 345kV 5133 Elm Creek - 5901 San Miguel Gen Ckt 1 | Wilson | SOUTH | 2026-07-02 | SOL | PV | 200.8 |  | 2023-01-23 | 2023-01-30 | 2023-04-28 | 2023-01-20 |  |  |  | No |  |  | Not Required
26INR0076 | Matias Solar | SS Completed, FIS Started, No IA | Industrial Bravo Project II LLC | 8114 Conoco 138kV | Matagorda | COASTAL | 2026-01-30 | SOL | PV | 152.3 |  | 2023-03-07 | 2023-03-13 | 2023-06-09 | 2023-03-08 |  | No |  | No |  |  | Not Required
26INR0077 | Anila BESS | SS Completed, FIS Started, No IA | Alina Energy LLC | Tap of 345 kV Elm Creek (Bus# 5133) - San Miguel Gen (Bus# 5901) Transmission Line Ckt 1 | Wilson | SOUTH | 2026-07-02 | OTH | BA | 209 |  | 2023-06-01 | 2023-02-20 | 2023-05-20 |  |  |  |  | No |  |  | Not Required
26INR0082 | Amerada Solar | SS Completed, FIS Started, No IA | Amerada Solar, LLC | Tap 345kV 3133 RICHLND2_5 - 3381 BIGBRNW_5 | Freestone | NORTH | 2026-10-22 | SOL | PV | 301.57 |  | 2023-05-12 | 2023-05-15 | 2023-08-11 | 2023-04-28 |  |  |  | No |  |  | Not Required
26INR0083 | Zeppelin Energy Storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Development, LLC | 6464 San Angelo North | Tom Green | WEST | 2026-02-16 | OTH | BA | 163.93 |  | 2023-03-08 | 2023-01-30 | 2023-04-28 |  |  |  |  | No |  |  | Not Required
26INR0084 | Amerada Storage | SS Completed, FIS Started, No IA | Amerada Solar, LLC | Tap 345kV 3133 RICHLND2_5 - 3381 BIGBRNW_5 | Freestone | NORTH | 2026-10-22 | OTH | BA | 150.78 |  | 2023-05-10 | 2023-05-15 | 2023-08-11 | 2023-04-28 |  |  |  | No |  |  | Not Required
26INR0088 | La Salle Solar | SS Completed, FIS Started, No IA | OCI La Salle Solar LLC | Tap 345kV LOBO7A (#80219) - FOWLERTONSW5 (#5709) | La Salle | SOUTH | 2026-07-01 | SOL | PV | 500 | Proj Name | 2023-03-31 | 2023-04-19 | 2023-07-14 | 2023-04-03 |  | Yes |  | No |  |  | Not Required
26INR0089 | La Salle ESS | SS Completed, FIS Started, No IA | OCI La Salle ESS LLC | Tap 345kV LOBO7A (#80219) - FOWLERTONSW5 (#5709) CKT#2 | La Salle | SOUTH | 2026-07-01 | OTH | BA | 500 | Proj Name | 2023-03-15 | 2023-04-07 | 2023-07-03 | 2023-03-15 |  | Yes |  | No |  |  | Not Required
26INR0098 | Douie Solar | SS Completed, FIS Started, No IA | Buffalo Spring Solar LLC | Tap 138 kV 3501 Sea way Teague - 3394 Jewett | Leon | NORTH | 2027-04-14 | SOL | PV | 221.03 | COD | 2023-05-09 | 2023-05-15 | 2023-08-11 | 2023-05-12 |  |  |  | No |  |  | Not Required
26INR0106 | Upstream BESS | SS Completed, FIS Started, No IA | Upstream Storage LLC | 1902 Johnson Switch | Johnson | NORTH | 2026-05-29 | OTH | BA | 461.6 |  | 2023-03-20 | 2023-03-27 | 2023-06-24 | 2023-03-14 |  |  |  | No |  |  | Not Required
26INR0107 | Freedom Falcon BESS | SS Completed, FIS Started, No IA | Falcon BESS, LLC | Tap 345kV 80307 Delsol - 80225 Cenizo CKT#2 | Zapata | SOUTH | 2026-05-31 | OTH | BA | 501.9 |  | 2023-04-26 | 2023-06-28 | 2023-09-22 | 2023-06-14 |  |  |  | No |  |  | Not Required
26INR0109 | Calpine Freestone Peaker 2 | SS Completed, FIS Started, No IA | Freestone Power Generation, LLC | 3134 RICHLAND CHAMBERS (PSS/E Bus Name: RICHLND1_5) | Freestone | NORTH | 2026-05-23 | GAS | GT | 228 |  | 2023-04-12 | 2023-04-19 | 2023-07-13 | 2023-04-11 |  |  |  | No
26INR0110 | Western Flats Solar | SS Completed, FIS Started, No IA | Hecate Energy Point Mountain Solar Facility 1 LLC | Tap 138 kV 76615 Crane -76635 King Mountain; POI is 7.85 miles from Crane. | Crane | WEST | 2026-12-31 | SOL | PV | 410.2 |  | 2023-11-17 | 2023-04-07 | 2023-07-05 |  |  |  |  | No |  |  | Not Required
26INR0112 | Lemma Solar | SS Completed, FIS Started, No IA | Greening USA Corp. | 6088 Benjamin AEP 138kV | Knox | WEST | 2026-03-01 | SOL | PV | 100.61 |  | 2023-05-23 | 2023-04-07 | 2023-07-05 |  |  |  |  | No |  |  | Not Required
26INR0113 | Meitner Wind | SS Completed, FIS Started, No IA | IP Meitner, LLC | 79000 Gray Substation 345kV | Gray | PANHANDLE | 2026-09-17 | WIN | WT | 836.5 |  | 2023-07-13 | 2023-07-18 | 2023-10-15 | 2023-06-29 |  |  |  | No |  |  | Not Required
26INR0114 | Ochoa Energy Storage | SS Completed, FIS Started, No IA | Ochoa Energy Storage LLC | 44420 Katy 138kV | Waller | HOUSTON | 2025-07-01 | OTH | BA | 260.8 |  | 2023-04-18 | 2023-04-19 | 2023-07-14 | 2023-04-11 |  |  |  | No |  |  | Not Required
26INR0116 | Falcon Zapata Storage 138 | SS Completed, FIS Started, No IA | Falcon BESS, LLC | Tap 138kV 8299 Zapata - 8957 Lopeno | Zapata | SOUTH | 2026-05-31 | OTH | BA | 200.79 |  | 2023-04-28 | 2023-05-15 | 2023-08-11 | 2023-05-08 |  | No |  | No |  |  | Not Required
26INR0117 | Oyster Creek Solar I SLF | SS Completed, FIS Started, No IA | Oyster Creek Solar 1, LLC | Tap 138kV 42110 Angleton - 42050 Clute | Brazoria | COASTAL | 2026-06-23 | SOL | PV | 163.35 |  | 2023-05-15 | 2023-06-28 | 2023-09-22 | 2023-06-15 |  |  |  | No |  |  | Not Required
26INR0118 | Oyster Creek Storage I SLF | SS Completed, FIS Started, No IA | Oyster Creek Solar 1, LLC | Tap 138kV 42110 Angleton - 42050 Clute | Brazoria | COASTAL | 2026-06-23 | OTH | BA | 0 |  | 2023-06-02 | 2023-06-28 | 2023-09-22 | 2023-06-20 |  |  |  | No |  |  | Not Required
26INR0120 | Bramble Energy Center | SS Completed, FIS Started, No IA | Mission Clean Energy LLC | 8236 Batesville 138kV | Zavala | SOUTH | 2026-10-03 | OTH | BA | 225.1 |  | 2023-08-23 | 2023-09-08 | 2023-12-04 | 2023-08-15 |  |  |  | No |  |  | Not Required
26INR0130 | Elm Flats Solar SLF | SS Completed, FIS Started, No IA | Elm Flats Solar, LLC | Tap 138kV 3472 BRIAR_CRK_8 – 3467 POWELL1_8 | Navarro | NORTH | 2026-07-01 | SOL | PV | 125.58 |  | 2023-05-12 |  | 2023-09-01 | 2023-06-13 |  |  |  | No |  |  | Not Required
26INR0131 | Elm Flats Storage SLF | SS Completed, FIS Started, No IA | Elm Flats Solar, LLC | Tap 138kV 3472 BRIAR_CRK_8 – 3467 POWELL1_8 | Navarro | NORTH | 2026-07-01 | OTH | BA | 0 |  | 2023-05-17 | 2023-06-07 | 2023-09-01 | 2023-05-22 |  |  |  | No |  |  | Not Required
26INR0134 | Myers Solar | SS Completed, FIS Started, No IA | BT Myers Solar, LLC | 8629 Baez 69 kV | Bee | SOUTH | 2026-09-01 | SOL | PV | 100.94 |  | 2023-06-13 | 2023-06-28 | 2023-09-20 | 2023-06-01 |  |  |  | No |  |  | Not Required
26INR0135 | Myers Storage | SS Completed, FIS Started, No IA | BT Myers Solar, LLC | 8197 POESTA2A Substation 69kV | Bee | SOUTH | 2026-09-01 | OTH | BA | 75.7 |  | 2023-06-07 | 2023-06-28 | 2023-09-20 | 2023-06-01 |  |  |  | No |  |  | Not Required
26INR0138 | Weathervane Solar SLF | SS Completed, FIS Started, No IA | Mallard Place LLC | Tap 138 kV 620 Bowie - 741 Dye Mound | Montague | NORTH | 2026-12-31 | SOL | PV | 160.49 |  | 2023-08-02 | 2023-08-14 | 2023-11-02 | 2023-07-20 |  |  |  | No |  |  | Not Required
26INR0139 | Weathervane Storage SLF | SS Completed, FIS Started, No IA | Mallard Place LLC | Tap 138 kV 620 Bowie - 741 Dye Mound | Montague | NORTH | 2026-12-31 | OTH | BA | 32.47 |  | 2023-08-02 | 2023-08-14 | 2023-11-02 | 2023-07-20 |  |  |  | No |  |  | Not Required
26INR0143 | Santa Garcias Solar | SS Completed, FIS Started, No IA | Oxy Renewable Energy LLC | Tap 138kV 8515 Alazan - 8458 Barney Davis | Kleberg | COASTAL | 2026-05-31 | SOL | PV | 265 |  | 2023-06-06 | 2023-06-28 | 2023-09-22 | 2023-06-07 |  | No |  | No |  |  | Not Required
26INR0146 | DMF Sagerton Solar SLF | SS Completed, FIS Started, No IA | Double Mountain Fork LLC | Tap 138kV 6158 Aspermont – 6161 Paint Creek | Haskell | WEST | 2026-12-31 | SOL | PV | 125.5 |  | 2023-07-23 | 2023-07-31 | 2023-10-27 | 2023-07-24 |  |  |  | No |  |  | Not Required
26INR0147 | Seven Springs Solar | SS Completed, FIS Started, No IA | Hancock Springs, LLC | 7061 COPPERAS COVE 138kV | Coryell | NORTH | 2026-05-15 | SOL | PV | 145.57 |  | 2023-08-18 | 2023-09-22 | 2023-12-14 | 2023-09-05 |  |  |  | No |  |  | Not Required
26INR0148 | DMF Sagerton Storage SLF | SS Completed, FIS Started, No IA | Double Mountain Fork LLC | Tap 138kV 6158 Aspermont – 6161 Paint Creek | Haskell | WEST | 2026-12-31 | OTH | BA | 0 |  | 2023-07-23 | 2023-07-31 | 2023-10-27 | 2023-07-20 |  |  |  | No |  |  | Not Required
26INR0149 | Blue Bird BESS | SS Completed, FIS Started, No IA | Gigawatt Solar LLC | Tap 345kV 1880 Rocky Creek - 1898 Mitchel Bend | Hood | NORTH | 2026-11-30 | OTH | BA | 200.7 |  | 2023-06-04 | 2023-06-28 | 2023-09-21 | 2023-06-13 |  |  |  | No |  |  | Not Required
26INR0153 | Apis Solar | SS Completed, FIS Started, No IA | S&S Renewables LLC | Tap 345kV 8606 Goddard – 8689 Tango | Bee | SOUTH | 2026-09-30 | SOL | PV | 533.72 |  | 2023-07-12 | 2023-07-18 | 2023-09-22 | 2023-06-29 |  | Yes |  | No |  |  | Not Required
26INR0154 | Apis Storage | SS Completed, FIS Started, No IA | S&S Renewables LLC | to the 345kV Goddard (#8606) – Tango (#8689) line; AEP | Bee | SOUTH | 2026-09-30 | OTH | BA | 268.43 |  | 2023-06-13 | 2023-06-13 | 2023-09-22 | 2023-05-25 |  | Yes |  | No |  |  | Not Required
26INR0155 | Ross Solar | SS Completed, FIS Started, No IA | S&S Renewables, LLC | tap 345kV 8249 Angstrom – 8676 Static | Refugio | COASTAL | 2027-07-31 | SOL | PV | 1025.57 |  | 2023-07-17 | 2023-07-31 | 2023-10-27 | 2023-07-18 |  |  |  | No |  |  | Not Required
26INR0156 | Ross Storage | SS Completed, FIS Started, No IA | S&S Renewables, LLC | tap the 345 kV Angstrom (#8249) – Static (#8676) line; AEP | Refugio | COASTAL | 2027-07-31 | OTH | BA | 510.99 |  | 2023-07-21 | 2023-08-14 | 2023-11-03 | 2023-07-27 |  |  |  | No |  |  | Not Required
26INR0161 | Timberline Solar | SS Completed, FIS Started, No IA | Timberline Renewables, LLC | Tap 345 kV 3119 Nacogdoches SE - 3116 Mt Enterprise | Nacogdoches | NORTH | 2026-09-22 | SOL | PV | 200.78 | MW Size COD | 2023-07-24 | 2023-08-14 | 2023-11-10 | 2023-08-02 |  |  |  | No | Not Required | Not Required | Not Required
26INR0162 | Timberline Storage | SS Completed, FIS Started, No IA | Timberline Renewables, LLC | Tap 345 kV 3119 Nacogdoches SE - 3116 Mt Enterprise | Nacogdoches | NORTH | 2026-09-22 | OTH | BA | 100.3 | MW Size COD | 2023-08-15 | 2023-08-14 | 2023-11-10 | 2023-08-04 |  |  |  | No |  |  | Not Required
26INR0169 | AQUAMARINE BESS | SS Completed, FIS Started, No IA | ME USA Project I LLC | tap 138kV 720 Salt Creek Reactor – 6150 Spur | Dickens | PANHANDLE | 2026-05-23 | OTH | BA | 213.81 | FIS Request | 2023-12-22 | 2023-06-28 | 2023-09-20 |  |  |  |  | No |  |  | Not Required
26INR0171 | Lazy U Solar 1 | SS Completed, FIS Started, No IA | Lazy U Solar 1 | Tap 345kV 60505 EDITHCLA7B - 60501 TESLA7A ckt1 | Hardeman | WEST | 2026-07-01 | SOL | PV | 252 |  | 2023-08-07 | 2023-08-21 | 2023-11-02 | 2023-08-09 |  |  |  | No |  |  | Not Required
26INR0172 | Lazy U Solar 2 | SS Completed, FIS Started, No IA | Lazy U Solar 2 | Tap 345kV 60505 EDITHCLA7B - 60501 TESLA7A CKT2 | Hardeman | WEST | 2026-07-01 | SOL | PV | 252 |  | 2023-08-14 | 2023-08-21 | 2023-11-02 | 2023-08-15 |  |  |  | No |  |  | Not Required
26INR0173 | Lazy U ESS 1 | SS Completed, FIS Started, No IA | Lazy U ESS 1 | Tap EDITHCLA7B [60505] -- TESLA7A [60501] 345kV ckt1 | Hardeman | WEST | 2026-07-01 | OTH | BA | 251.5 |  | 2023-08-03 | 2023-09-08 | 2023-12-04 | 2023-08-16 |  |  |  | No |  |  | Not Required
26INR0174 | Lazy U ESS 2 | SS Completed, FIS Started, No IA | Lazy U ESS 2 | Tap EDITHCLA7B [60505] -- TESLA7A [60501] ckt2 | Hardeman | WEST | 2026-07-01 | OTH | BA | 251.5 |  | 2023-08-16 | 2023-08-21 | 2023-11-02 | 2023-08-16 |  |  |  | No |  |  | Not Required
26INR0176 | Dionysus Solar | SS Completed, FIS Started, No IA | Dionysus Solar, LLC | Tap 138kV 6733 Mustang Prairie - 6732 Latexo | Houston | NORTH | 2026-04-21 | SOL | PV | 153.26 |  | 2023-06-14 | 2023-06-28 | 2023-09-22 | 2023-06-05 |  |  |  | No |  |  | Not Required
26INR0177 | Dionysus Storage | SS Completed, FIS Started, No IA | Dionysus Solar, LLC | Tap 138kV 6733 Mustang Prairie - 6732 Latexo | Houston | NORTH | 2026-04-21 | OTH | BA | 77.28 |  | 2023-06-14 | 2023-06-28 | 2023-09-22 | 2023-06-05 |  |  |  | No |  |  | Not Required
26INR0178 | Alliance Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap 345kV 68091 Navarro - 1907 Venus Switch | Navarro | NORTH | 2028-07-01 | SOL | PV | 175 |  | 2023-06-27 | 2023-07-10 | 2023-10-05 | 2023-06-29 |  |  |  | No |  |  | Not Required
26INR0179 | SunShiner ESS | SS Completed, FIS Started, No IA | SunShiner ESS LLC | 8672 LaPryor2A 138 kV | Zavala | SOUTH | 2026-07-01 | OTH | BA | 131.8 |  | 2023-09-20 | 2023-09-25 | 2023-12-21 | 2023-09-20 |  |  |  | No |  |  | Not Required
26INR0180 | Cape Rich BESS | SS Completed, FIS Started, No IA | Cape Rich BESS | 3478 Navarro 138kV | Navarro | NORTH | 2026-09-27 | OTH | BA | 150.52 |  | 2023-07-03 | 2023-07-10 | 2023-10-06 | 2023-07-03 |  |  |  | No |  |  | Not Required
26INR0181 | Rayos del Sol BESS | SS Completed, FIS Started, No IA | Rayos Del Sol Solar Project | 163023 NEBULA 138kV | Cameron | COASTAL | 2025-12-31 | OTH | BA | 100.26 | FIS Request | 2023-12-23 | 2023-06-28 | 2023-09-22 |  |  |  |  | No |  |  | Not Required
26INR0184 | Arc Energy Storage | SS Completed, FIS Started, No IA | Paris Energy Storage, LLC | Line Tap 138kV 1693 Paris Switch - 11806 ENLOE T8 138kv | Lamar | NORTH | 2026-12-31 | OTH | BA | 200.6 |  | 2023-06-19 | 2023-07-31 | 2023-10-27 | 2023-07-25 |  |  |  | No |  |  | Not Required
26INR0185 | Beitel Energy Storage | SS Completed, FIS Started, No IA | Brazos Energy Storage, LLC | 579 Jack County 138kV | Jack | NORTH | 2026-12-31 | OTH | BA | 200.6 |  | 2023-06-26 | 2023-08-14 | 2023-11-10 | 2023-08-02 |  |  |  | No |  |  | Not Required
26INR0189 | Skipjack Energy Storage | SS Completed, FIS Started, No IA | Skipper Energy Storage LLC | Tap 138 42980 Nash - 44010 W A Parish ckt #2 | Brazoria | COASTAL | 2027-04-05 | OTH | BA | 150.6 |  | 2023-07-17 | 2023-07-31 | 2023-10-27 | 2023-07-29 |  |  |  | No |  |  | Not Required
26INR0195 | Realitos Storage SLF | SS Completed, FIS Started, No IA | Mesquite Creek LLC | Bruni (#8297) – Crestonio (#8695) 138 kV line; AEP | Duval | SOUTH | 2026-12-31 | OTH | BA | 0 |  | 2023-07-31 | 2023-09-07 | 2023-12-05 | 2023-08-02 |  |  |  | No | Not Required | Not Required | Not Required
26INR0196 | Realitos Solar SLF | SS Completed, FIS Started, No IA | Mesquite Creek LLC | Bruni (#8297) – Crestonio (#8695) 138 kV line; AEP | Duval | SOUTH | 2026-12-31 | SOL | PV | 150.49 |  | 2023-08-22 | 2023-09-07 | 2023-12-05 | 2023-07-20 |  |  |  | No | Not Required | Not Required | Not Required
26INR0200 | Vaughn Energy Storage | SS Completed, FIS Started, No IA | Vaughn Battery Storage, LLC | 13 Keith 138kV | Grimes | NORTH | 2026-12-31 | OTH | BA | 200.6 |  | 2023-08-21 | 2023-08-21 | 2023-11-17 | 2023-08-20 |  |  |  | No |  |  | Not Required
26INR0201 | Rock Rose Energy BESS | SS Completed, FIS Started, No IA | Rock Rose Energy LLC | 44070 Whaley 345 kV | Fort Bend | HOUSTON | 2026-07-02 | OTH | BA | 211.5 |  | 2023-03-21 | 2023-09-22 | 2023-12-14 | 2023-09-08 |  |  |  | No |  |  | Not Required
26INR0211 | Titus Low Carbon Ventures Solar 1 | SS Started, FIS Started, No IA | Vaquero Solar, LLC | Tap 345kV 8249 Angstrom - 8624 Grissom | San Patricio | COASTAL | 2026-12-31 | SOL | PV | 286.84 |  | 2023-08-21 | 2023-10-13 |  | 2023-09-21 |  |  |  | No |  |  | Not Required
26INR0215 | JackGard BESS | SS Completed, FIS Started, No IA | Jackgard BESS | 1429 Jacksboro 345kV | Jack | NORTH | 2026-09-14 | OTH | BA | 200.59 |  | 2023-08-12 | 2023-08-14 | 2023-11-02 | 2023-07-31 |  |  |  | No |  |  | Not Required
26INR0218 | Fort Chadbourne Cattle BESS | SS Completed, FIS Started, No IA | Fort Chadbourne BESS | AEP Fort Chadbourne 138 kv substation (#6324) | Coke | WEST | 2026-04-01 | OTH | BA | 50.23 |  | 2023-08-14 | 2023-08-21 | 2023-11-06 | 2023-07-31 |  |  |  | No |  |  | Not Required
26INR0219 | Mountain Springs BESS | SS Completed, FIS Started, No IA | Mountain Springs BESS | 704 Mountain Springs 138 kV | Cooke | NORTH | 2026-04-01 | OTH | BA | 150.52 |  | 2023-09-25 | 2023-10-04 | 2023-12-30 | 2023-09-21 |  |  |  | No |  |  | Not Required
26INR0226 | First Capitol BESS | SS Completed, FIS Started, No IA | First Capitol BESS, LLC | TNWCOLMAIN1 (BUS#39500) to TNPALMETT 1 (BUS#39510) | Brazoria | COASTAL | 2026-04-15 | OTH | BA | 256.2 |  | 2023-09-25 | 2023-10-04 | 2023-12-14 | 2023-09-22 |  |  |  | No |  |  | Not Required
26INR0230 | Titus Sienta Solar | SS Started, FIS Started, No IA | Sol Sienta Solar, LLC | Tap 138kV 1239 Coyanosa - 11238 Blair Lake Sub | Pecos | WEST | 2027-04-30 | SOL | PV | 406.8 | MW Size COD | 2023-08-21 | 2023-10-13 |  | 2023-10-09 |  |  |  | No |  |  | Not Required |  |  |  | 2025-10-01 | 2026-04-01
26INR0231 | Energy City BESS | SS Completed, FIS Started, No IA | Energy City BESS LLC | Tap 138kV 1179 Texaco Tap - 1200 Mariensfield | Midland | WEST | 2027-03-15 | OTH | BA | 204.9 |  | 2023-09-13 | 2023-10-04 | 2023-12-30 | 2023-09-25 |  |  |  | No |  |  | Not Required
26INR0235 | Noor Solar | SS Started, FIS Started, No IA | Industrial Kilo Project LLC | Tap 138kV 40390 Crosby - 40680 Placid Ckt 86 | Harris | HOUSTON | 2027-05-31 | SOL | PV | 188.2 |  | 2023-10-04 | 2023-10-13 |  | 2023-10-04 |  |  |  | No |  |  | Not Required
26INR0241 | Sol Marina Energy Center | SS Started, FIS Started, No IA | Adapture Solar Development, LLC | Tap 345kV 2427 Watermill - 2466 Big Onion | Ellis | NORTH | 2027-04-17 | SOL | PV | 175.3 | MW Size COD | 2023-10-17 | 2023-10-25 |  | 2023-09-07 |  |  |  | No | Not Required | Not Required | Not Required
26INR0242 | Sol Marina Energy Center BESS | SS Started, FIS Started, No IA | Adapture Solar Development, LLC | Tap 345kV 2427 Watermill - 2466 Big Onion | Ellis | NORTH | 2027-04-17 | OTH | BA | 57.6 | COD | 2023-10-17 | 2023-10-25 |  | 2023-09-07 |  |  |  | No | Not Required | Not Required | Not Required
26INR0245 | Cairos Storage | SS Completed, FIS Started, No IA | Cairos Solar, LLC | 7425 ODLAW SWITCH 138kV | Kinney | SOUTH | 2026-03-15 | OTH | BA | 77.28 |  | 2023-10-03 | 2023-10-25 | 2023-12-30 | 2023-10-03 |  |  |  | No |  |  | Not Required
26INR0246 | Cairos Solar | SS Completed, FIS Started, No IA | Cairos Solar, LLC | ODLAW SWITCH (#7425) | Kinney | SOUTH | 2026-03-15 | SOL | PV | 153.26 |  | 2023-09-26 | 2023-10-04 | 2023-12-30 | 2023-09-22 |  |  |  | No |  |  | Not Required
26INR0247 | Jane Storage Energy Center | SS Completed, FIS Started, No IA | NMRE Holdings, LLC | 59901 Grelton 345 kV | Martin | WEST | 2026-06-01 | OTH | BA | 240.96 |  | 2023-08-13 | 2023-09-08 | 2023-12-01 | 2023-08-28 |  |  |  | No | Not Required | Not Required | Not Required
26INR0248 | Sengun BESS | SS Started, FIS Started, No IA | BRP Blue Topaz 12, LLC | WEST_OSO4A (8484) 138 KV | Nueces | COASTAL | 2026-01-06 | OTH | BA | 200.89 | FIS Request | 2023-12-20 |  |  | 2023-12-18 |  |  |  | No |  |  | Not Required
26INR0250 | Duffy BESS | SS Completed, FIS Started, No IA | Duffy Energy Storage LLC | Tap 345kV 44200 Hilje and 5915 STP c64 | Matagorda | COASTAL | 2026-03-31 | OTH | BA | 235.7 |  | 2023-08-14 | 2023-08-21 | 2023-11-17 | 2023-08-08 |  |  |  | No |  |  | Not Required
26INR0252 | Neutron Storage | SS Completed, FIS Started, No IA | Neutron Storage | Tap 345kV 13405 Trading House - 68090 Sam Switch | McLennan | NORTH | 2026-10-07 | OTH | BA | 104.36 |  | 2023-08-21 | 2023-09-08 | 2023-12-01 | 2023-08-21 |  |  |  | No | Not Required | Not Required | Not Required
26INR0253 | Sodalite Solar | SS Completed, FIS Started, No IA | BT DJ4M Solar, LLC | Tap Connection Bus 2470 Royse to Bus 3223 Shamburger | Van Zandt | NORTH | 2027-04-02 | SOL | PV | 150.54 |  | 2023-09-15 | 2023-09-22 | 2023-12-14 | 2023-09-15 |  |  |  | No | Not Required | Not Required | Not Required
26INR0254 | Sodalite Storage | SS Completed, FIS Started, No IA | BT DJ4M Solar, LLC | Tap 345kV Royse to Shamburger | Van Zandt | NORTH | 2027-04-02 | OTH | BA | 100.44 |  | 2023-09-26 | 2023-10-04 | 2023-12-14 | 2023-09-20 |  |  |  | No | Not Required | Not Required | Not Required
26INR0255 | Operation Sunshine | SS Started, FIS Started, No IA | Duck Creek Solar, LLC | Amos Creek Substation (AMOSCR #7077) 345 kV | Concho | WEST | 2026-07-01 | SOL | PV | 602.1 |  | 2023-09-29 | 2023-11-14 |  | 2023-09-27 |  |  |  | No |  |  | Not Required
26INR0258 | Running Iron Solar | SS Started, FIS Started, No IA | Running Iron Solar, LLC | Conoco 138 kV Switching Station (bus no 8114) | Matagorda | COASTAL | 2025-12-30 | SOL | PV | 204.74 |  | 2023-10-04 | 2023-10-25 |  | 2023-10-19 |  |  |  | No |  |  | Not Required
26INR0259 | Cottontail Energy Center | SS Started, FIS Started, No IA | Mission Clean Energy LLC | 7258 Glidden Substation 138kV | Colorado | SOUTH | 2027-10-19 | OTH | BA | 200.85 |  | 2023-10-05 | 2023-10-25 |  | 2023-10-17 |  |  |  | No |  |  | Not Required
26INR0260 | Evans Creek Energy Storage | SS Started, FIS Started, No IA | Evans Creek Energy Storage LLC | Comstock 138kV Substation (PSSE Bus #8683) | Val Verde | WEST | 2026-06-30 | OTH | BA | 102.96 |  | 2023-09-13 | 2023-10-25 |  | 2023-10-19 |  |  |  | No |  |  | Not Required
26INR0269 | Moccasin Solar | SS Completed, FIS Started, No IA | Swenson Solar LLC | Tapping the 345 kV Line from Kirchhoff (Bus# 60707) to Clear Crossing (Bus# 60515) | Stonewall | WEST | 2027-07-06 | SOL | PV | 809.6 |  | 2023-08-30 | 2023-09-07 | 2023-12-06 | 2023-09-01 |  |  |  | No | Not Required | Not Required | Not Required
26INR0274 | Malala Storage | SS Started, FIS Started, No IA | Malala Storage, LLC | 2434 Seagoville SW 138kV | Dallas | NORTH | 2027-04-03 | OTH | BA | 205.5 | COD | 2023-10-16 | 2023-10-25 |  | 2023-10-09 |  |  |  | No |  |  | Not Required
26INR0277 | Salt-Lick Solar | SS Started, FIS Started, No IA | Salt-Lick Solar, LLC | Elcor_8 bus # 11198 | Culberson | WEST | 2027-04-30 | SOL | PV | 510 | COD | 2023-10-04 | 2023-10-13 |  | 2023-10-02 |  |  |  | No |  |  | Not Required |  |  |  | 2025-10-01 | 2027-04-01
26INR0279 | Firebird Solar | SS Started, FIS Started, No IA | TX Firebird SB 6, LLC | 138 kV ODESSA EHV (1027) - YARBROUGH (11111) LINE TAP | Ector | WEST | 2026-12-31 | SOL | PV | 100.42 | MW Size | 2023-10-31 | 2023-11-14 |  | 2023-10-31 |  |  |  | No |  |  | Not Required
26INR0280 | Pethrus BESS | SS Completed, FIS Started, No IA | Pethrus BESS, LLC | Tap Wichita Falls Switch (#1464) – North Star (#1467) 138 kV Line | Wichita | WEST | 2027-04-03 | OTH | BA | 174.08 | MW Size | 2023-09-15 | 2023-09-23 | 2023-12-20 | 2023-08-30 |  |  |  | No | Not Required | Not Required | Not Required
26INR0282 | Haute Stockage | SS Completed, FIS Started, No IA | Haute Stockage, LLC | 345 kV Cook Field Road Switch (Bus# 1442) | Shackelford | WEST | 2027-04-03 | OTH | BA | 307.32 | Status Change INA-to-PLN | 2023-09-29 | 2023-10-04 | 2023-12-30 | 2023-09-29 |  |  |  | No | Not Required | Not Required | Not Required
26INR0283 | Bonaparte BESS | SS Started, FIS Started, No IA | Bonaparte BESS, LLC | LCRA Lincoln Substation 138 kV (#7568) | Lee | SOUTH | 2026-08-01 | OTH | BA | 153.67 |  | 2023-11-07 | 2023-11-14 |  | 2023-09-06 |  |  |  | No |  |  | Not Required
26INR0284 | Burgundy BESS | SS Started, FIS Started, No IA | Burgundy BESS, LLC | 69 kV Prairie Hill (Bus# 107) | Limestone | NORTH | 2027-07-01 | OTH | BA | 102.48 |  | 2023-09-28 | 2023-10-04 |  | 2023-09-17 |  |  |  | No | Not Required | Not Required | Not Required
26INR0285 | Hill Valley BESS | SS Started, FIS Started, No IA | Hill Valley BESS, LLC | 345 kV Singleton (#44645) | Grimes | NORTH | 2026-12-01 | OTH | BA | 204.8 | COD | 2023-11-09 | 2023-12-04 |  | 2023-11-10 |  |  |  | No |  |  | Not Required
26INR0286 | Beaujolais BESS | SS Started, FIS Started, No IA | Beaujolais BESS, LLC | 345 kV Paris Switch (#1692) | Lamar | NORTH | 2026-01-15 | OTH | BA | 307.2 |  | 2023-11-30 | 2023-12-04 |  | 2023-11-17 |  |  |  | No |  |  | Not Required
26INR0287 | Firebird BESS | SS Started, FIS Started, No IA | TX BESS 6, LLC | 138 kV REITER (18545) - YARBROUGH (11111) LINE TAP | Ector | WEST | 2026-12-31 | OTH | BA | 100.42 | MW Size | 2023-10-31 | 2023-11-14 |  | 2023-10-31 |  |  |  | No | Not Required | Not Required | Not Required
26INR0289 | Wadsworth Storage Energy Center | SS Started, FIS Started, No IA | Nova Clean Energy Real Estate, LLC | 8115 Wadsworth Substation 138 kV | Matagorda | COASTAL | 2026-06-01 | OTH | BA | 200.8 |  | 2023-10-09 | 2023-10-25 |  | 2023-10-10 |  |  |  | No | Not Required | Not Required | Not Required
26INR0290 | Cold Creek Solar 2 | SS Started, FIS Started, No IA | Cold Creek Solar LLC | Tap 345kV line Big Hill (#76003) - Twin Buttes (#76009) | Schleicher | WEST | 2026-12-31 | SOL | PV | 445.41 | FIS Request | 2023-11-07 | 2023-12-18 |  | 2023-11-07 |  |  |  | No |  |  | Not Required
26INR0291 | Cold Creek Storage 2 | SS Started, FIS Started, No IA | Cold Creek Solar LLC | Tap 345kV line Big Hill (#76003) - Twin Buttes (#76009) | Schleicher | WEST | 2026-12-31 | OTH | BA | 174.24 |  | 2023-11-02 | 2023-12-04 |  | 2023-11-02 |  |  |  | No |  |  | Not Required
26INR0294 | Longleaf Power Station | SS Started, FIS Started, No IA | WattBridge Texas Holding, LLC | Redland Substation (# 3321) | Angelina | NORTH | 2026-06-01 | GAS | GT | 612 |  | 2023-10-04 | 2023-10-13 |  | 2023-10-04 |  |  |  | No | Not Required | Not Required
26INR0295 | Trinity Hills BESS SLF | SS Started, FIS Started, No IA | Phoenix Battery Storage, LLC | To the 345 kV Garvey Road Switch (#17002) | Archer | WEST | 2025-03-28 | OTH | BA | 27 |  | 2023-11-13 | 2023-11-30 |  | 2023-11-03 |  |  |  | No |  |  | Not Required
26INR0296 | Sherbino II BESS SLF | SS Started, FIS Started, No IA | Phoenix Battery Storage, LLC | 38430 TNMP White baker Switching Station 138kV | Pecos | WEST | 2025-03-28 | OTH | BA | 18 |  | 2023-11-19 | 2023-11-30 |  | 2023-11-16 |  |  |  | No |  |  | Not Required
26INR0297 | Buzzi Maryneal Wind Project | SS Started, FIS Started, No IA | Buzzi Unicem USA | 1413 SWEETCRK-9 | Nolan | WEST | 2026-01-02 | WIN | WT | 18 |  | 2023-10-02 | 2023-10-25 |  | 2023-10-16 |  |  |  | No | Not Required | Not Required | Not Required
26INR0300 | Whitewright Solar 2 | SS Started, FIS Started, No IA | SunWR, LLC | Tap 345kV 1729 Valley South – Farmersville 1685 | Grayson | NORTH | 2026-10-15 | SOL | PV | 300 | FIS Request | 2023-11-07 | 2023-12-18 |  | 2023-11-07 |  |  |  | No |  |  | Not Required
26INR0301 | Bhalu Storage | SS Started, FIS Started, No IA | Bhalu Storage, LLC | 138 kV Bulldog_SU Station (Bus# 23833) | Howard | WEST | 2027-03-03 | OTH | BA | 205.5 | COD | 2023-10-23 | 2023-10-30 |  | 2023-10-23 |  |  |  | No | Not Required | Not Required | Not Required
26INR0306 | Nautilus Heavy Storage | SS Started, FIS Started, No IA | Nautilus Heavy Storage, LLC | 8422 Dupont 138kV | San Patricio | COASTAL | 2026-05-30 | OTH | BA | 511.9 | FIS Request | 2023-12-11 | 2023-12-20 |  | 2023-12-01 |  |  |  | No |  |  | Not Required
26INR0312 | Senator Aggreko Storage | SS Started, FIS Started, No IA | Senator Aggreko Storage LLC | Escondido Substation (ESCONDID4A #8260) 138 kV | Maverick | SOUTH | 2026-10-31 | OTH | BA | 153.4 |  | 2023-11-09 | 2023-11-14 |  | 2023-10-25 |  |  |  | No |  |  | Not Required
26INR0313 | Edens Solar | SS Started, FIS Started, No IA | Hill PV, LLC | Tap 69kV 3532 Itasca - 3523 Hillsboro | Hill | NORTH | 2027-04-12 | SOL | PV | 70.37 | COD | 2023-10-18 | 2023-10-25 |  | 2023-10-20 |  |  |  | No |  |  | Not Required
26INR0316 | Lonesome Dove BESS | SS Started, FIS Started, No IA | Hawks BESS, LLC | To Tap 345 kV Tecumseh Creek Switch (Bus# 11418) to Willow Creek Switch (Bus# 1421) Line | Throckmorton | WEST | 2026-05-15 | OTH | BA | 256.1 |  | 2023-11-29 | 2023-11-30 |  | 2023-11-15 |  |  |  | No |  |  | Not Required
26INR0317 | Pinnacle Point Energy Storage | SS Started, FIS Started, No IA | GCI Pinnacle Point, LLC | Highlands 138kV (Bus 40812) | Harris | HOUSTON | 2026-06-01 | OTH | BA | 101.3 |  | 2023-11-07 | 2023-11-14 |  | 2023-11-08 |  |  |  | No |  |  | Not Required
26INR0318 | Sandford Solar | SS Started, FIS Started, No IA | BT Sandford Solar, LLC | Tap 345kV 1730 West Krum - 6111 Riley Ckt #1 | Wise | NORTH | 2026-05-29 | SOL | PV | 126.18 | FIS Request | 2023-12-20 |  |  | 2023-12-12 |  |  |  | No |  |  | Not Required
26INR0319 | Sandford Storage | SS Started, FIS Started, No IA | BT Sandford Solar, LLC | Tap 345kV 1730 West Krum - 6111 Riley Ckt #1 | Wise | NORTH | 2026-05-29 | OTH | BA | 100.93 | FIS Request | 2023-12-18 |  |  | 2023-12-12 |  |  |  | No |  |  | Not Required
26INR0321 | Windmill Ridge Storage | SS Started, FIS Started, No IA | BT WMR Storage, LLC | Angleton (Bus #42110) - West Columbia Local (Bus #43381) 138 kV Substation | Brazoria | COASTAL | 2026-12-31 | OTH | BA | 151.4 | COD | 2023-11-07 | 2023-11-14 |  | 2023-11-03 |  |  |  | No |  |  | Not Required
26INR0324 | Misty Hollow BESS | SS Started, FIS Started, No IA | Clear Fork BESS, LLC | 345 kV Singleton (#44645) | Grimes | NORTH | 2026-12-01 | OTH | BA | 204.8 | FIS Request | 2023-12-06 | 2023-12-20 |  | 2023-12-06 |  |  |  | No |  |  | Not Required
26INR0325 | Reynolds Park BESS | SS Started, FIS Started, No IA | Iowa Park BESS, LLC | Oncor Byrd Road Substation---345kV Bus #1466 | Wichita | WEST | 2027-02-01 | OTH | BA | 204.8 | FIS Request | 2023-12-06 | 2023-12-18 |  | 2023-11-28 |  |  |  | No |  |  | Not Required
26INR0326 | Nouveau BESS | SS Started, FIS Started, No IA | RamZ BESS, LLC | To Tap 345 kV Thomas Price Switch (Bus# 11523) to Clear Crossing (Bus# 60515) Line | Throckmorton | WEST | 2026-12-08 | OTH | BA | 256.1 | COD | 2023-11-20 | 2023-11-30 |  | 2023-11-15 |  |  |  | No | Not Required | Not Required | Not Required
26INR0327 | Sleepy Hollow BESS | SS Started, FIS Started, No IA | Sleepy Hollow BESS, LLC | Tap 138 kV 792 Murray - 6169 Paint Creek | Throckmorton | WEST | 2026-12-08 | OTH | BA | 123.1 | COD | 2023-11-30 | 2023-11-30 |  | 2023-11-15 |  |  |  | No | Not Required | Not Required | Not Required
26INR0328 | Yorktown BESS | SS Started, FIS Started, No IA | Navitas Energy LLC | (#78575) LCRA Yorktown 138 kV | DeWitt | SOUTH | 2026-12-16 | OTH | BA | 150.49 |  | 2023-10-18 | 2023-10-25 |  | 2023-10-10 |  |  |  | No |  |  | Not Required
26INR0333 | VERTUS ENERGY STORAGE | SS Started, FIS Started, No IA | VERTUS ENERGY STORAGE LLC | Bus Name: TnMainland1, Bus Number: 38830, | Galveston | HOUSTON | 2026-02-01 | OTH | BA | 412.02 |  | 2023-10-10 | 2023-10-13 |  | 2023-10-10 |  |  |  | No |  |  | Not Required
26INR0338 | Yellow Rose BESS | SS Started, FIS Started, No IA | Black Mountain Energy Storage II | TAP PAYNE SUB(1758) - PINKHIL (1763) | Grayson | NORTH | 2027-02-15 | OTH | BA | 201.2 |  | 2023-10-11 | 2023-10-13 |  | 2023-10-09 |  |  |  | No | Not Required | Not Required | Not Required
26INR0340 | SOUTHERN SELECT ENERGY STORAGE | SS Started, FIS Started, No IA | SOUTHERN SELECT ENERGY STORAGE LLC | Bus Name: TNHEIGHTS_1 Bus Number: 38740 | Galveston | HOUSTON | 2026-02-01 | OTH | BA | 404.3 |  | 2023-10-16 | 2023-10-25 |  | 2023-10-12 |  |  |  | No |  |  | Not Required
26INR0343 | Stinger Energy Storage | SS Started, FIS Started, No IA | Stinger Energy Storage LLC | Substation Tap at Atascocita 138kV Substation (Bus # 40130) | Harris | HOUSTON | 2026-01-31 | OTH | BA | 200.8 |  | 2023-11-02 | 2023-11-14 |  | 2023-11-02 |  |  |  | No |  |  | Not Required
26INR0347 | Midfield Energy Project | SS Started, FIS Started, No IA | HQC Solar Holdings 1, LLC | Tap 138kV 8121 Blessing - 8125 Lolita | Matagorda | COASTAL | 2026-12-01 | OTH | PV | 150 |  | 2023-11-13 | 2023-12-04 |  | 2023-11-28 |  |  |  | No
26INR0349 | ARTIO ENERGY STORAGE | SS Started, FIS Started, No IA | Artio Energy Storage LLC | Farmersville 345kV Substation (PSSE BUS # 1685) | Collin | NORTH | 2028-10-01 | OTH | BA | 205.94 | MW Size | 2023-10-30 | 2023-11-14 |  | 2023-10-30 |  |  |  | No | Not Required | Not Required | Not Required
26INR0350 | Jack County III – 138 kV | SS Started, FIS Started, No IA | Jack County Power Development, LLC | 579 JACK COUNTY 138kV | Jack | NORTH | 2026-05-01 | GAS | GT | 660 | FIS Request | 2023-12-23 | 2023-11-14 | [5 empty] | No
26INR0354 | Butterfield Energy Storage | SS Started, FIS Started, No IA | Butterfield Energy Storage LLC | 575 Jack Electric 345kV | Jack | NORTH | 2026-11-01 | OTH | BA | 207.6 |  | 2023-11-10 | 2023-11-14 |  | 2023-10-31 |  |  |  | No |  |  | Not Required
26INR0360 | Gail Mountain Solar | SS Started, FIS Started, No IA | Gail Mountain Solar, LLC | Tap 138 kV line #131955 Bull Creek Wind - #1301 Willow Valley | Borden | WEST | 2026-07-01 | SOL | PV | 152 | FIS Request | 2023-12-06 |  |  | 2023-12-08 |  |  |  | No |  |  | Not Required
26INR0372 | Centennial Solar | SS Started, FIS Started, No IA | Centennial AD 8 LLC | Tap 138kV 6364 YELLOW JACKET - 76390 FORT MASON | Menard | WEST | 2026-08-31 | SOL | PV | 61.36 | FIS Request | 2023-12-09 |  |  | 2023-12-22 |  |  |  | No |  |  | Not Required
26INR0375 | Avalon BESS | SS Started, FIS Started, No IA | Greenbelt ERCOT BESS Holdings, LLC | Tapping the 345 kV Line from WA Parish (Bus# 44005) to Bellaire (Bus# 47000) | Fort Bend | HOUSTON | 2026-12-01 | OTH | BA | 522.12 | FIS Request | 2023-12-06 | 2023-12-20 |  | 2023-11-30 |  |  |  | No |  |  | Not Required
27INR0002 | Puerto Del Sol 2 | SS Completed, FIS Started, No IA | PUERTO DEL SOL, LLC | Tap 345kV 79500 Palmito - 79501 King Fisher Ckt 1 | Cameron | COASTAL | 2027-12-31 | SOL | PV | 214.62 |  | 2023-03-28 | 2022-05-16 | 2022-08-13 |  |  |  |  | No |  |  | Not Required
27INR0003 | Becerra Creek Storage 2 | SS Completed, FIS Started, No IA | Bordas Renewable Energy, LLC | 345 kV Cenizo Substation (#80220) | Webb | SOUTH | 2027-12-01 | OTH | BA | 125.62 |  | 2022-09-19 | 2022-09-21 | 2022-12-19 | 2022-09-07 |  |  |  | No |  |  | Not Required
27INR0004 | Dundee North Wind | SS Completed, FIS Started, No IA | Felix 2, LLC | 345 kV Riley Substation (#6101); AEP | Wilbarger | WEST | 2027-07-31 | WIN | WT | 307.72 |  | 2022-12-28 | 2023-01-03 | 2023-03-30 | 2022-12-28 |  | No |  | No |  |  | Not Required
27INR0005 | Dundee South A Wind | SS Completed, FIS Started, No IA | Felix 2, LLC | 345 kV Riley Substation (#6101); AEP | Baylor | WEST | 2027-07-31 | WIN | WT | 307.23 |  | 2022-12-28 | 2023-01-03 | 2023-03-30 | 2022-12-22 |  | No |  | No |  |  | Not Required
27INR0007 | Felix East Solar | SS Completed, FIS Started, No IA | Felix 1, LLC | The 345 kV Riley Substation (#6101); AEP | Wilbarger | WEST | 2027-07-31 | SOL | PV | 301.44 |  | 2022-12-28 | 2023-01-03 | 2023-03-30 | 2022-12-22 |  | No |  | No |  |  | Not Required
27INR0009 | Felix Storage | SS Completed, FIS Started, No IA | Felix 1, LLC | The 345 kV Riley Substation (#6101); AEP | Wilbarger | WEST | 2027-07-31 | OTH | BA | 100.54 |  | 2022-12-28 | 2023-01-03 | 2023-03-30 | 2022-12-22 |  | No |  | No |  |  | Not Required
27INR0011 | Dundee South B Wind | SS Completed, FIS Started, No IA | Felix 2, LLC | 345 kV Riley Substation (#6101); AEP | Baylor | WEST | 2027-07-31 | WIN | WT | 300.27 |  | 2023-01-06 | 2023-01-17 | 2023-04-14 | 2023-01-03 |  | No |  | No |  |  | Not Required
27INR0012 | Felix West Solar | SS Completed, FIS Started, No IA | Felix 1, LLC | 6101 Riley 345 kV | Wilbarger | WEST | 2027-07-31 | SOL | PV | 200.95 |  | 2023-01-06 | 2023-01-17 | 2023-04-14 | 2023-01-03 |  | No |  | No |  |  | Not Required
27INR0014 | Kit Fox Storage | SS Completed, FIS Started, No IA | Kit Fox Storage, LLC | 6842 WALTON 138KV | Henderson | NORTH | 2027-07-01 | OTH | BA | 153.6 |  | 2023-03-08 | 2023-03-13 | 2023-06-09 | 2023-03-10 |  |  |  | No |  |  | Not Required
27INR0015 | Cumbia Energy Center | SS Completed, FIS Started, No IA | Mission Clean Energy LLC | Westside Bulk 138kV substation, owned by AEP Texas Central Co., bus number #8485 | Nueces | COASTAL | 2026-12-31 | OTH | BA | 200 |  | 2023-03-20 | 2023-03-27 | 2023-06-19 | 2023-03-21 |  |  |  | No |  |  | Not Required
27INR0020 | SCOTT CROSSING PV1 | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | Tap 345kV 60514 Clear Crossing - 60507 | Haskell | WEST | 2027-09-01 | SOL | PV | 364.14 |  | 2023-03-14 | 2023-03-27 | 2023-06-19 | 2023-03-13 |  |  |  | No |  |  | Not Required
27INR0021 | Live Oak Bayou Solar SLF | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | Tap 345kV 42530 Jones Creek – 42400 Refuge POI ckt 27 | Matagorda | COASTAL | 2027-09-01 | SOL | PV | 156.06 |  | 2023-05-09 | 2023-05-15 | 2023-08-11 | 2023-05-09 |  |  |  | No |  |  | Not Required
27INR0022 | Panhandle Flagship Solar 1 | SS Completed, FIS Started, No IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005) | Carson | PANHANDLE | 2027-12-01 | SOL | PV | 439.4 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-02-23 |  |  |  | No |  |  | Not Required
27INR0023 | Panhandle Flagship Solar 2 | SS Completed, FIS Started, No IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005). Station 2 (27INR0023) connects to Station 1 (27INR0022 & 27INR0025) via a 4.9 mile internal tie line. Station 1 (27INR0022 & 27INR0025) connects to POIB via 22.5 mile tie-line | Hutchinson | PANHANDLE | 2027-12-01 | SOL | PV | 304.4 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-02-23 |  |  |  | No |  |  | Not Required
27INR0024 | Panhandle Flagship Solar 3 | SS Completed, FIS Started, No IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005).Station 3 (27INR0024) connects to Station 2 (27INR0023) via a 4.4 mile internal tie line. Station 2 connects to Station 1 (27INR0022 & 27INR0025) via a 4.9 mile internal tie line. Station 1 connects to POI | Hutchinson | PANHANDLE | 2027-12-01 | SOL | PV | 260.3 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-02-23 |  |  |  | No |  |  | Not Required
27INR0025 | Panhandle Flagship Storage | SS Completed, FIS Started, No IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005) | Carson | PANHANDLE | 2027-12-01 | OTH | BA | 371.7 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-02-23 |  |  |  | No |  |  | Not Required
27INR0029 | Short Creek BESS | SS Completed, FIS Started, No IA | Wichita Solar I, LLC | Tap 345kV 6101 Riley - 1425 Fisher Road Switch | Wichita | WEST | 2027-12-01 | OTH | BA | 150.51 |  | 2023-04-12 | 2023-04-19 | 2023-07-14 | 2023-04-12 |  |  |  | No |  |  | Not Required
27INR0038 | SCOTT CROSSING STORAGE SLF | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | Tap 345kV 60514 Clear Crossing - 60507 Pendulo | Haskell | WEST | 2027-09-01 | OTH | BA | 0 |  | 2023-04-06 | 2023-04-19 | 2023-07-13 | 2023-04-07 |  |  |  | No |  |  | Not Required
27INR0039 | Live Oak Bayou Storage SLF | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | Tap 345kV 42530 Jones Creek – 42400 Refuge POI ckt 27 | Matagorda | COASTAL | 2027-09-01 | OTH | BA | 0 |  | 2023-04-06 | 2023-05-03 | 2023-07-28 | 2023-04-20 |  |  |  | No |  |  | Not Required
27INR0040 | Solar Star Rhome Storage | SS Completed, FIS Started, No IA | Solar Star Rhome Storage | 576 RHOME 138kV | Wise | NORTH | 2027-03-31 | OTH | BA | 220.7 |  | 2023-08-17 | 2023-04-19 | 2023-07-12 |  |  |  |  | No |  |  | Not Required
27INR0047 | Sunscape Renewable Energy Solar SLF | SS Completed, FIS Started, No IA | Sunscape Renewable Energy LLC | Bus# 8455 Lon C Hill to Bus# 80078 Reforzar 345 kV Line | Nueces | COASTAL | 2027-07-15 | SOL | PV | 522.75 |  | 2023-06-14 | 2023-06-28 | 2023-09-20 | 2023-05-30 |  |  |  | No |  |  | Not Required
27INR0048 | Sunscape Renewable Energy Storage SLF | SS Completed, FIS Started, No IA | Sunscape Renewable Energy LLC | Tap 345kV 8455 Lon C Hill -- 80078 Reforzar | Nueces | COASTAL | 2027-07-15 | OTH | BA | 0 |  | 2023-06-06 | 2023-06-28 | 2023-09-20 | 2023-06-06 |  |  |  | No |  |  | Not Required
27INR0049 | Darkwood Solar | SS Completed, FIS Started, No IA | Mustang Creek Solar, LLC | Tap 345KV 1900 Comanche Peak to 1440 Comanche SS | Comanche | NORTH | 2027-01-30 | SOL | PV | 150 |  | 2023-11-09 | 2023-06-28 | 2023-09-01 | 2023-11-09 |  |  |  | No |  |  | Not Required
27INR0052 | Aquilla Lake 3 Wind (Alternative POI Oncor 138KV) | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap 138kV 234 Chatt - 3352 Pecanst_8 | Hill | NORTH | 2026-12-31 | WIN | WT | 225.62 |  | 2023-08-10 | 2023-08-14 | 2023-11-02 | 2023-08-10 |  |  |  | No |  |  | Not Required
27INR0053 | Aquilla Lake 3 Wind ( Alternative POI Oncor 345kV) | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap #68090 Sam Switch to #1907 Venus 345kV | Hill | NORTH | 2026-12-31 | WIN | WT | 225.62 |  | 2023-08-24 | 2023-09-07 | 2023-12-04 | 2023-08-23 |  |  |  | No |  |  | Not Required
27INR0056 | Laurel Wind Energy Center | SS Completed, FIS Started, No IA | Laurel Energy Center, LLC | Solstice to Bakersfield (Bus# 60404 -76002) 345kV Ckt 2 line tap | Pecos | WEST | 2027-01-31 | WIN | WT | 501.83 |  | 2023-06-15 | 2023-06-28 | 2023-09-22 | 2023-06-08 |  |  |  | No |  |  | Not Required
27INR0063 | Supra Wind | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap #6101 Riley 7A to #60505 Edithcla 7B 345kV | Hardeman | WEST | 2027-12-23 | WIN | WT | 205.86 |  | 2023-07-05 | 2023-07-10 | 2023-10-05 | 2023-06-29 |  |  |  | No |  |  | Not Required
27INR0065 | Funston Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tapping #60791 Perigee7A to #6235 Abilene Mulberry Creek 345kV Line | Jones | WEST | 2028-07-01 | SOL | PV | 355.22 |  | 2023-08-23 | 2023-09-22 | 2023-12-20 | 2023-08-12 |  |  |  | No |  |  | Not Required
27INR0068 | Jerboa BESS | SS Completed, FIS Started, No IA | Jerboa Storage, LLC | Tap 138kV 8906 North Alamo - 8354 Weslaco Switching Station | Hidalgo | SOUTH | 2027-02-28 | OTH | BA | 201.08 |  | 2023-07-31 | 2023-08-14 | 2023-11-02 | 2023-07-18 |  |  |  | No |  |  | Not Required
27INR0077 | Cuchillas BESS | SS Completed, FIS Started, No IA | Gransolar Texas Two | 80219 Lobo 345kV | Webb | SOUTH | 2026-12-27 | OTH | BA | 306.94 |  | 2023-08-17 | 2023-09-26 | 2023-12-20 | 2023-08-17 |  |  |  | No |  |  | Not Required
27INR0080 | Laurel Storage Energy Center | SS Completed, FIS Started, No IA | Laurel Energy Center, LLC | Tap 345kV 60404 Solstice - 76002 Bakersfield Ckt 2 | Pecos | WEST | 2027-01-31 | OTH | BA | 200.8 |  | 2023-08-18 | 2023-09-07 | 2023-12-01 | 2023-08-21 |  |  |  | No |  |  | Not Required
27INR0082 | Orbit Energy Storage | SS Started, FIS Started, No IA | GCI Orbit Energy Storage, LLC | Tap 345 kV Calaveras Power Station (BUS #5400) to HOWARD_5 (BUS #5231). | Bexar | SOUTH | 2027-06-01 | OTH | BA | 501.94 |  | 2023-11-28 | 2023-11-30 |  | 2023-09-27 |  |  |  | No |  |  | Not Required
27INR0083 | Spinner Energy Storage | SS Started, FIS Started, No IA | GCI Wolf Energy Storage, LLC | 8196 Poesta Substation 138kV | Bee | SOUTH | 2027-06-01 | OTH | BA | 125.63 |  | 2023-10-05 | 2023-10-13 |  | 2023-09-27 |  |  |  | No |  |  | Not Required
27INR0085 | Eagle Claw Energy Center | SS Started, FIS Started, No IA | Cypress Energy Center, LLC | 30.615932, -95.962023 - Singleton (Bus #44645) - Zenith (Bus #44900) Circuit #98 345 kV Line | Grimes | NORTH | 2027-03-15 | OTH | BA | 200.84 |  | 2023-09-28 | 2023-10-13 |  | 2023-10-06 |  |  |  | No | Not Required | Not Required | Not Required
27INR0091 | Oak Tree Energy Storage | SS Started, FIS Started, No IA | Live Oak Energy Storage, LLC | Tap Shaula (#5380) – South Texas (#5915) | Lavaca | SOUTH | 2027-11-04 | OTH | BA | 310.2 |  | 2023-11-14 | 2023-12-04 |  | 2023-11-21 |  |  |  | No |  |  | Not Required
27INR0092 | Pecan BESS | SS Started, FIS Started, No IA | Gransolar Texas Three LLC | (PSSE BUS# 47) HILTOPLKS8 138kV | Leon | NORTH | 2027-07-15 | OTH | BA | 157.12 |  | 2023-10-11 | 2023-10-25 |  | 2023-10-12 |  |  |  | No |  |  | Not Required
27INR0095 | Bulldog Power | SS Started, FIS Started, No IA | Bulldog Power LLC | 39703 TNMP FM524 Substation 138kV | Brazoria | COASTAL | 2027-07-24 | GAS | GT | 300.75 |  | 2023-11-13 | 2023-11-14 |  | 2023-11-08 |  |  |  | No
27INR0096 | Rubicon Power BESS | SS Started, FIS Started, No IA | Rubicon Power LLC | TNMP FM524 Substation (#39703) | Brazoria | COASTAL | 2027-07-24 | OTH | BA | 301.38 |  | 2023-11-13 | 2023-11-14 |  | 2023-11-08 |  |  |  | No |  |  | Not Required
27INR0099 | Silver Spur Energy Center | SS Started, FIS Started, No IA | Silver Spur Energy Center, LLC | A DIRECT CONNECTION TO A NEW SWITCHING STATION ON THE BRYN_WBRN (BUS #32895) - MILL_SW138 (BUS #32856) 138 KV LINE | Brazos | NORTH | 2027-02-01 | OTH | BA | 200.83 | FIS Request | 2023-12-04 | 2023-12-04 |  | 2023-10-16 |  |  |  | No |  |  | Not Required
27INR0102 | Cottonseed Energy Storage | SS Started, FIS Started, No IA | Cottonseed Energy Storage LLC | South Lane City and PSEE # is 43190 | Wharton | SOUTH | 2027-04-20 | OTH | BA | 207.6 |  | 2023-11-01 | 2023-11-14 |  | 2023-11-02 |  |  |  | No |  |  | Not Required
27INR0124 | RedSun Solar | SS Started, FIS Started, No IA | Gransolar Texas Twenty Two | Tap 138kV 7100 Burnet - 7529 Bertram | Burnet | SOUTH | 2027-06-15 | SOL | PV | 84.04 |  | 2023-11-28 | 2023-12-04 |  | 2023-11-28 |  |  |  | No |  |  | Not Required
27INR0125 | RedSun BESS | SS Started, FIS Started, No IA | Gransolar Texas Twenty Two | Existing Line from Substation Name: Burnet (PSSE#7100) to Substation Name: Bertram (PSSE#7520) | Burnet | SOUTH | 2027-06-15 | OTH | BA | 84.04 | FIS Request | 2023-11-27 | 2023-12-04 |  | 2023-11-21 |  |  |  | No |  |  | Not Required
28INR0005 | Tetris Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings LLC | TAP 345kV 80307 Del Sol 7C - 80225 Cenizo 7C | Zapata | SOUTH | 2028-07-01 | SOL | PV | 350 |  | 2023-06-15 | 2023-07-28 | 2023-10-23 | 2023-07-21 |  |  |  | No |  |  | Not Required
28INR0007 | Tetris Solar (Alternative POI) | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings LLC | TAP 138kV 8985 San Ygnacio - 8299 Zapata | Zapata | SOUTH | 2028-07-01 | SOL | PV | 350 |  | 2023-06-30 | 2023-07-10 | 2023-10-03 | 2023-06-30 |  |  |  | No |  |  | Not Required
28INR0008 | Oriole Solar | SS Completed, FIS Started, No IA | Rolling Plain Solar | Tap 345kV 6076 Foxtail - 60791 Perigee | Knox | WEST | 2028-12-29 | SOL | PV | 504.18 |  | 2023-05-03 | 2023-05-15 | 2023-08-11 | 2023-05-09 |  |  |  | No |  |  | Not Required
28INR0009 | Oriole BES | SS Completed, FIS Started, No IA | Rolling Plains Solar | Tap 345kV 6076 Foxtail - 60791 Perigee | Knox | WEST | 2028-12-29 | OTH | BA | 150.24 |  | 2023-04-28 | 2023-05-15 | 2023-08-11 | 2023-05-09 |  |  |  | No |  |  | Not Required
28INR0012 | Shamrock II Wind | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | #76004 Single Tree Substation 345kV | Crockett | WEST | 2028-07-01 | WIN | WT | 256.62 |  | 2023-06-26 | 2023-07-10 | 2023-10-02 | 2023-06-28 |  |  |  | No |  |  | Not Required
28INR0013 | Varadero Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | #68092 Liberty Station 345kV | Limestone | NORTH | 2028-04-11 | SOL | PV | 304.74 |  | 2023-06-26 | 2023-07-10 | 2023-10-03 | 2023-07-05 |  |  |  | No |  |  | Not Required
28INR0018 | Channing Wind | SS Started, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | 23906 AJ Swope Station 345kV | Oldham | PANHANDLE | 2028-12-31 | WIN | WT | 352.38 | FIS Request | 2023-09-15 | 2023-12-20 |  | 2023-11-29 |  |  |  | No |  |  | Not Required
29INR0003 | Aurelius Solar | SS Completed, FIS Started, No IA | S&S Renewables, LLC | 23908 Deaf Smith station 345 kV | Deaf Smith | PANHANDLE | 2028-03-31 | SOL | PV | 1124.24 |  | 2023-07-13 | 2023-07-18 | 2023-10-15 | 2023-07-13 |  |  |  | No |  |  | Not Required
29INR0004 | Aurelius Wind | SS Completed, FIS Started, No IA | S&S Renewables, LLC | 23908 Deaf Smith station 345 kV | Deaf Smith | PANHANDLE | 2028-03-31 | WIN | WT | 623 |  | 2023-07-13 | 2023-08-14 | 2023-11-06 | 2023-08-07 |  |  |  | No |  |  | Not Required
29INR0009 | Aurelius 2 Solar | SS Started, FIS Started, No IA | IP Roman II, LLC | 23908 Deaf Smith station 345 kV. This INR has a 600 MW PUN load at the medium voltage side of the MPTs for a total of 1800 MW PUN load (refer to the substation SLD). | Deaf Smith | PANHANDLE | 2028-09-30 | SOL | PV | 445.4 | FIS Request | 2023-11-28 | 2023-12-04 |  | 2023-11-30 |  |  |  | No |  |  | Not Required
29INR0010 | Aurelius 2 Wind | SS Started, FIS Started, No IA | IP Roman II, LLC | 23908 Deaf Smith station 345kV | Deaf Smith | PANHANDLE | 2028-09-30 | WIN | WT | 623 | FIS Request | 2023-11-28 | 2023-12-04 |  | 2023-11-30 |  |  |  | No |  |  | Not Required
29INR0011 | Aurelius 3 Solar | SS Started, FIS Started, No IA | IP Roman III, LLC | 23908 Deaf Smith station 345 kV. This INR has a 600 MW PUN load at the medium voltage side of the MPTs for a total of 1800 MW PUN load (refer to the substation SLD). | Deaf Smith | PANHANDLE | 2029-03-31 | SOL | PV | 445.4 | FIS Request | 2023-11-20 | 2023-12-04 |  | 2023-11-30 |  |  |  | No |  |  | Not Required
29INR0012 | Aurelius 3 Wind | SS Started, FIS Started, No IA | IP Roman III, LLC | 23908 Deaf Smith station 345kV | Deaf Smith | PANHANDLE | 2029-03-31 | WIN | WT | 623 | FIS Request | 2023-11-28 | 2023-12-04 |  | 2023-11-30 |  |  |  | No |  |  | Not Required
30INR0002 | Southeast Oklahoma Pumped Storage | SS Completed, FIS Started, No IA | Apex Energy Solutions, LLC | 1692 Paris Switch 345kV | Lamar | NORTH | 2030-01-01 | OTH | EN | 1232 |  | 2023-03-28 | 2022-08-05 | 2022-11-01 |  |  |  |  | No
30INR0005 | Woodland Energy Storage | SS Started, FIS Started, No IA | Woodland Energy Storage, LLC | 68040 Kopperl Substation 345kV | Bosque | NORTH | 2030-10-01 | OTH | BA | 207.6 | FIS Request | 2023-10-28 | 2023-12-18 |  | 2023-10-23 |  |  |  | No |  |  | Not Required

## Project Details - Small Gen
GIM Project Details - Small Generators
NOTES:
Due to Protocol confidentiality provisions, only those Small Generator projects are included for which ERCOT has (1) received written Notice from Interconnecting Entities (IE) that authorize the project
information to be made public, or (2) approved the IE's completed Resource Registration form as indicated by assignment of a “Model Ready Date".
Excludes projects that have a status of Inactive (status = INA).
INR | Project Name | Model Ready Date | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) | Change indicators: Proj Name, MW | IA Signed | Financial Security | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Size, COD, SFS. |  | Required to fund
[11 empty] | Status Change INA-to-PLN |  | Dist. Upgrades
12INR0059b | HOVEY (Barilla Solar 1B) | 2015-09-02 | First Solar | 60385 Solstice 138kV | Pecos | WEST | 2024-01-31 | SOL | PV | 7.4 |  | 2013-12-26 | Yes | 2015-09-02 | 2015-09-14
22INR0596 | Grizzly Ridge BESS | 2022-09-01 | Grizzly Ridge Solar LLC | Pottsville Switching Substation (Bus# 178) | Hamilton | NORTH | 2023-05-31 | OTH | BA | 9.95 |  | 2021-10-18 | Yes | 2023-02-10
22INR0602 | Regis Palacios BESS | 2024-03-01 | Regis Palacios, LLC | Station Name (TSP STATION CODE): Palacios Load Name or Load Transformer name: 69_12_2 Bus# PTI Bus number: 8131 Voltage Transmission level kV: 69kV | Matagorda | COASTAL | 2024-05-24 | OTH | BA | 9.8 |  | 2022-10-07 | Yes
23INR0483 | Rio Nogales CT1 Rotor Replacement | 2023-04-12 | CPS Energy | Rio Nogales Substation 5362 RIONOG 345kV | Guadalupe | SOUTH | 2023-06-08 | GAS | CC | 3.1 |  | 2023-01-20 | Yes |  | 2023-04-27
23INR0498 | Moore Field BESS 2 | 2024-03-01 | Regis Monte Cristo LLC | Connected to AEP 12.47kV Substation Station Name (TSP Station Code): Moore Field (MOORE_FL) Load/Load Transformer Name: LD2 PTI Bus Number: #80117 Voltage in kV (Transmission Level): 138 kV Transformers: 3x 4000kVA 800VAC Δ - 12.47kVA Υ | Hidalgo | SOUTH | 2024-05-24 | OTH | BA | 9.8 |  | 2022-10-07 | Yes
23INR0522 | Diboll Bess | 2023-02-01 | HEN Infrastructure, LLC 1 | Station Name (TDSP Station Code): DIBOL Load/Load Transformer Name: LDLXFMR1 PTI BUS number: 3155 Voltage in kV: 138kV | Angelina | NORTH | 2024-01-20 | OTH | BA | 9.95 | COD | 2022-08-22 | Yes | 2023-12-08
23INR0523 | Damon_Storage | 2023-12-01 | Baccharis Storage LLC | Station Name: DA Load/Load Transformer Name: TR1 PTI BUS number: 42370 Voltage in kV (Transmission Level): 138 kV | Brazoria | COASTAL | 2024-06-04 | OTH | BA | 5 | COD | 2022-10-18 | Yes
23INR0539 | Gregory BESS | 2024-03-01 | Regis Gregory, LLC | Station Name: Gregory TSP Station Code: GREGORY Load Transformer name: LOAD2 Bus#: 8421 Voltage in kV (Transmission Level): 69kV | San Patricio | COASTAL | 2024-05-24 | OTH | BA | 9.8 |  | 2022-10-07 | Yes
23INR0541 | Telview BESS | 2023-12-01 | Goddess Storage LLC | Station Name: TV (Telview) Load/Load Transformer Name: TR1 PTI BUS number: 44691 Voltage in kV: 138 kV | Fort Bend | HOUSTON | 2024-06-11 | OTH | BA | 9.96 | COD | 2023-07-10 | Yes
23INR0543 | Continental BESS | 2023-10-04 | Regis Continental, LLC | Station Name (TDSP Station Code): CONTINEN Load/Load Transformer Name: 69_12 PTI BUS number: #8799 Voltage in kV (Transmission Level): 69 kV | Starr | SOUTH | 2024-03-29 | OTH | BA | 9.8 | COD | 2023-06-05 | Yes
23INR0553 | Val Verde BESS | 2023-03-01 | HEN Infrastructure, LLC 1 | Station Name (TDSP Station Code): MV_VALV4 Load/Load Transformer Name: 1 PTI BUS number: 5769 Voltage in kV (Transmission Level): 138 | Hidalgo | SOUTH | 2024-03-07 | OTH | BA | 9.95 |  |  | Yes | 2023-10-24 | 2023-12-06
23INR0554 | Hamilton BESS | 2023-05-03 | HEN Infrastructure, LLC 1 | Station Name (TDSP Station Code): HAMILTON Load/Load Transformer Name: 1_138_12 PTI BUS number: 8255 Voltage in kV (Transmission Level): 138 | Val Verde | WEST | 2024-01-20 | OTH | BA | 9.95 | COD | 2022-08-05 | Yes | 2023-12-08 | 2023-12-15
23INR0555 | Farmersville West BESS 1 | 2023-10-04 | HEN Infrastructure, LLC 1 | Station Name (TDSP Station Code) = FRMRSVLW Load/Load Transformer Name = FRMVW_1 PTI BUS number = 37291 Voltage in kV = 138kV | Collin | NORTH | 2024-02-27 | OTH | BA | 9.9 | COD | 2023-05-12 | Yes
23INR0556 | IEP Orchard BESS | 2024-01-04 | IEP Tejas Verde LLC | Station Name (TDSP Station Code): OR Load/Load Transformer Name :TR1 PTI BUS number: 44541 Voltage in kV (Transmission Level): 138 kV Project Size: 9.99 MW battery energy storage (BESS) system; 50 MWh connecting on CNP 34.5kV Distribution System. | Fort Bend | HOUSTON | 2024-08-06 | OTH | BA | 9.99 | COD | 2023-08-09 | Yes
23INR0565 | Garden City East BESS | 2023-06-01 | HEN Infrastructure, LLC 2 | GARDCITYE_9/LDLXFMR1/GRDNE_LD3 | Glasscock | WEST | 2024-02-07 | OTH | BA | 9.95 | COD | 2022-10-11 | Yes | 2023-12-22
23INR0569 | Weil Tract BESS | 2023-06-01 | HEN Infrastructure, LLC 2 | WEIL_TRC/8482/138_12/WEIL_TRC_LD1 | Nueces | COASTAL | 2024-05-28 | OTH | BA | 9.9 |  | 2022-12-21 | Yes
23INR0570 | Mineral Wells East BESS | 2023-06-01 | HEN Infrastructure, LLC 2 | MINWLLSE1_8/1584/LDLXFMR1 | Palo Pinto | NORTH | 2024-02-07 | OTH | BA | 9.95 | COD | 2022-10-11 | Yes | 2023-12-22
23INR0620 | Falfurrias BESS | 2023-10-04 | HEN INFRASTRUCTURE LLC 1 | FALFUR/2_138_12/8510 | Brooks | SOUTH | 2024-06-14 | OTH | BA | 9.9 |  | 2023-04-10 | Yes
23INR0688 | Midway1 BESS | 2023-11-01 | Midway BESS Station LLC | Station Code: MIDWY Station name: Midway Load/Load Transformer Name: LDXFMR1 PTI Bus number: 1253 Transmission level kV: 138kV | Ector | WEST | 2024-01-30 | OTH | BA | 9.95 | Proj Name | 2022-06-13 | Yes | 2023-12-01
24INR0580 | Texas Bluebonnet Solar | 2023-04-03 | Texas Bluebonnet Solar Partners, LLC | 3370 McGuffey POD 138 kV | McLennan | NORTH | 2024-06-17 | SOL | PV | 9.72 |  | 2023-08-28 | Yes
24INR0585 | Pauline BESS | 2023-11-01 | HEN INFRASTRUCTURE LLC 1 | LDLXFMR2/3179/PAULN | Henderson | NORTH | 2024-02-07 | OTH | BA | 9.95 | COD | 2022-11-15 | Yes | 2023-12-22
24INR0586 | Judkins BESS | 2023-11-01 | HEN INFRASTRUCTURE LLC 1 | LDLXFMR1/1102/JDKNS | Ector | WEST | 2024-01-20 | OTH | BA | 9.95 | COD | 2022-11-08 | Yes | 2023-12-08
24INR0587 | Lufkin South BESS | 2023-11-01 | HEN INFRASTRUCTURE LLC 1 | LDLXFMR1/3328/LFSTH | Angelina | NORTH | 2024-05-17 | OTH | BA | 9.95 |  | 2023-02-26 | Yes
24INR0588 | Cisco BESS | 2023-11-01 | HEN INFRASTRUCTURE LLC 1 | LD02/6317/CISC | Eastland | NORTH | 2024-06-14 | OTH | BA | 9.9 |  | 2023-07-19 | No
24INR0610 | Century BESS | 2024-04-03 | ESTX-PLD-GRANDPRAIRIE1, LLC | Site Address: 3601 Allen Ave Arlington TX 76014 and this project will be connected to Station Name: CENTURY TSP Station Code: CNTRY Load Name or Load Transformer name: LD6188 Bus#: 1930 Voltage: 345 kV | Tarrant | NORTH | 2024-05-31 | OTH | BA | 9.95 |  | 2023-04-14 | Yes
24INR0614 | Russek Street BESS | 2024-01-04 | HEN INFRASTRUCTURE LLC 1 | Substation (RUSSEKST) ERCOT LOAD NAME (LOAD2) ERCOT BUS 6517 DAC RUSSEKST_LD1 | Reagan | WEST | 2024-05-24 | OTH | BA | 9.9 |  | 2023-08-03 | Yes
24INR0615 | Pavlov BESS | 2024-01-04 | HEN INFRASTRUCTURE LLC 1 | Substation (PAVLOV) ERCOT LOAD NAME (138_13_2) ERCOT BUS 8614 DAC PAVLOV_LD1 | Matagorda | COASTAL | 2024-05-24 | OTH | BA | 9.9 |  | 2023-08-21 | No
24INR0624 | Mainland BESS | 2024-01-04 | HEN INFRASTRUCTURE LLC 1 | Substation/BUS#/ERCOTBUS/ERCOTLOAD/DAC MAINLAND/38830/TNMAINLAND1/MAINLD_2/MAINLAND_DL1 | Galveston | HOUSTON | 2024-05-24 | OTH | BA | 9.9 |  | 2023-08-22 | Yes

## GIM Trends
GIM Trends
Reflects all Large Generator projects for which a Security Screening Study has been requested. The third table reflects all Small Generator projects whose GIM applications have been approved.
Excludes projects that have a status of Inactive (status = INA).
Nameplate capacity will change across time due to additional projects, cancelations, expirations, adjustments from study results, and projects being placed into service.
| Year | Month | Total Projects |  |  | Project Count | [5 empty] | Project Capacity (MW)
[6 empty] | GIM milestones | [5 empty] | Fuel Type
|  |  |  | Small Generator Not Model Ready | Small Generator Model Ready | Initial Screening Study | Screening Study Complete | In Full Study | Completed Full Study | Signed Interconnection Agreement | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Battery | Other
| 2020 | Dec | 708 | 0 | 0 | 40 | 86 | 352 | 28 | 202 | 10 | 23619.61 | 88031.55 | 7178.58 | 13 | 0 | 0 | 23550.04 | 350
| 2021 | Jan | 738 | 0 | 0 | 57 | 84 | 354 | 27 | 216 | 9 | 23334.25 | 89895.91 | 7224.34 | 13 | 0 | 0 | 26107.2 | 350
| 2021 | Feb | 769 | 0 | 0 | 54 | 95 | 374 | 20 | 226 | 4 | 24552.13 | 92012.3 | 7236.54 | 13 | 0 | 0 | 28352.55 | 400
| 2021 | Mar | 778 | 0 | 0 | 73 | 66 | 392 | 17 | 230 | 33 | 23859.29 | 88856.46 | 7897.04 | 13 | 0 | 0 | 30300.62 | 400
| 2021 | Apr | 804 | 0 | 0 | 63 | 92 | 399 | 19 | 231 | 12 | 23640.17 | 91546.69 | 7894.04 | 0 | 0 | 0 | 32002.39 | 500
| 2021 | May | 807 | 0 | 0 | 37 | 120 | 395 | 27 | 228 | 11 | 23764.26 | 91769.36 | 7606.04 | 0 | 0 | 0 | 33671.49 | 350
| 2021 | Jun | 818 | 0 | 0 | 43 | 114 | 409 | 26 | 226 | 16 | 22518.72 | 92814.52 | 8341.04 | 0 | 0 | 0 | 36206.58 | 350
| 2021 | Jul | 832 | 0 | 0 | 40 | 125 | 395 | 36 | 236 | 4 | 21933.87 | 94468.15 | 10399.04 | 0 | 0 | 0 | 36953.54 | 350
| 2021 | Aug | 861 | 0 | 0 | 59 | 122 | 412 | 34 | 234 | 5 | 22625.84 | 94745.6 | 12907.04 | 0 | 0 | 0 | 39488 | 984.67
| 2021 | Sep | 890 | 0 | 0 | 52 | 133 | 428 | 40 | 237 | 10 | 22536.64 | 100293.12 | 13547.04 | 0 | 0 | 50 | 42465 | 1493.24
| 2021 | Oct | 902 | 0 | 0 | 42 | 143 | 441 | 48 | 228 | 6 | 21705.98 | 99988.53 | 17560.24 | 0 | 0 | 50 | 45029.43 | 985
| 2021 | Nov | 928 | 0 | 0 | 43 | 147 | 458 | 51 | 229 | 8 | 22091.28 | 100783.54 | 18449.74 | 0 | 0 | 50 | 46945.94 | 985
| 2021 | Dec | 964 | 0 | 0 | 49 | 156 | 467 | 62 | 230 | 5 | 21939 | 103923.04 | 18449.74 | 0 | 0 | 50 | 51416 | 985
| 2022 | Jan | 983 | 0 | 0 | 44 | 168 | 470 | 53 | 238 | 8 | 21370.17 | 105880.2 | 18399.52 | 0 | 0 | 50 | 52346.02 | 985
| 2022 | Feb | 1018 | 8 | 4 | 67 | 152 | 488 | 48 | 251 | 28 | 21261.67 | 110323.3 | 17763.62 | 0 | 0 | 50 | 55336.83 | 1216.9
| 2022 | Mar | 1024 | 1 | 10 | 64 | 141 | 505 | 52 | 251 | 23 | 20364.41 | 107046.12 | 17763.62 | 0 | 0 | 50 | 57741.69 | 1902.58
| 2022 | Apr | 1047 | 2 | 10 | 59 | 138 | 518 | 55 | 265 | 8 | 21566.29 | 108666.99 | 18287.62 | 0 | 0 | 50 | 59873.93 | 1670.72
| 2022 | May | 1017 | 4 | 9 | 37 | 89 | 552 | 58 | 268 | 55 | 19543.69 | 106920.38 | 12887.62 | 0 | 0 | 50 | 58248.93 | 1468.8
| 2022 | Jun | 1068 | 4 | 7 | 63 | 87 | 565 | 64 | 275 | 7 | 22243.19 | 111730.5 | 12744.32 | 0 | 0 | 53 | 65365.67 | 1476.78
| 2022 | Jul | 1105 | 4 | 6 | 67 | 87 | 590 | 70 | 281 | 7 | 22503.61 | 113903.73 | 11316.9 | 0 | 0 | 53 | 69043.91 | 1003.03
| 2022 | Aug | 1138 | 19 | 4 | 34 | 98 | 629 | 64 | 290 | 9 | 22118.23 | 115798.99 | 11255.04 | 0 | 0 | 53 | 71580.11 | 2235.03
| 2022 | Sep | 1192 | 21 | 4 | 56 | 107 | 649 | 58 | 297 | 10 | 22920.32 | 120296.29 | 11551.44 | 0 | 0 | 53 | 74877.41 | 2486.27
| 2022 | Oct | 1205 | 22 | 6 | 60 | 100 | 667 | 49 | 301 | 10 | 23024.78 | 122584.5 | 11513.34 | 0 | 0 | 53 | 75629.54 | 2486.27
| 2022 | Nov | 1214 | 22 | 8 | 56 | 90 | 682 | 52 | 304 | 18 | 23198.34 | 122704.82 | 12277.1 | 0 | 0 | 53 | 78746.39 | 2486.27
| 2022 | Dec | 1254 | 21 | 8 | 40 | 102 | 722 | 53 | 308 | 10 | 23875.87 | 123340.4 | 12935.1 | 0 | 0 | 53 | 82844.41 | 2486.27
| 2023 | Jan | 1298 | 23 | 5 | 51 | 105 | 736 | 63 | 315 | 1 | 24350.74 | 125568.83 | 12542.1 | 0 | 0 | 53 | 88430.16 | 2486.27
| 2023 | Feb | 1334 | 18 | 13 | 48 | 109 | 761 | 68 | 317 | 1 | 24702.44 | 127309.1 | 12542.1 | 0 | 0 | 53 | 91492.71 | 2486.27
| 2023 | Mar | 1373 | 14 | 17 | 39 | 100 | 810 | 73 | 320 | 22 | 25741.94 | 127764.63 | 12544.1 | 0 | 0 | 53 | 96356.26 | 2235.03
| 2023 | Apr | 1385 | 15 | 18 | 33 | 89 | 825 | 80 | 325 | 20 | 23702.82 | 129236.52 | 12984.8 | 0 | 0 | 53 | 96078.43 | 2235.03
| 2023 | May | 1424 | 18 | 20 | 36 | 86 | 843 | 86 | 335 | 19 | 22472.25 | 129506.95 | 13026 | 0 | 0 | 53 | 102825.36 | 2235.03
| 2023 | Jun | 1479 | 28 | 22 | 51 | 83 | 872 | 82 | 341 | 16 | 27151.55 | 130857.4 | 12476.33 | 0 | 0 | 53 | 109379.63 | 2235.03
| 2023 | Jul | 1500 | 25 | 28 | 50 | 76 | 903 | 83 | 335 | 16 | 28615.02 | 133978.64 | 12368.43 | 0 | 0 | 53 | 110408 | 2385.63
| 2023 | Aug | 1537 | 31 | 30 | 45 | 82 | 927 | 85 | 337 | 7 | 32034.48 | 136165.24 | 11841.53 | 0 | 0 | 53 | 111579.02 | 2235.03
| 2023 | Sep | 1580 | 40 | 32 | 43 | 102 | 924 | 93 | 346 | 15 | 31639.72 | 141315.27 | 11383.73 | 0 | 0 | 53 | 114563.15 | 2235.03
| 2023 | Oct | 1628 | 41 | 32 | 49 | 102 | 952 | 99 | 353 | 16 | 31915.72 | 143221.48 | 13637.63 | 0 | 0 | 53 | 120534.12 | 2235.03
| 2023 | Nov | 1656 | 44 | 30 | 55 | 99 | 961 | 92 | 375 | 10 | 32509.57 | 142605.97 | 15457.28 | 0 | 0 | 53 | 124941.16 | 2385.03
| 2023 | Dec | 1671 | 41 | 28 | 39 | 116 | 974 | 92 | 381 | 12 | 34590.95 | 145654.02 | 15482.78 | 0 | 0 | 53 | 127067.73 | 2367
Note: Other contains all Fuel and Technology Types not in the Solar, Wind, Gas or Battery categories.

## data_GIM Trends_1 (hidden)
| # Signed Interconnect Agreement | # Completed Full Study | # in Full Study | # Screening Study Complete | # Initial Screening study | GW Capacity
Dec-22 | 308 | 53 | 722 | 102 | 40 | 245.2649
Jan-23 | 315 | 63 | 736 | 105 | 51 | 253.1709
Feb-23 | 317 | 68 | 761 | 109 | 48 | 258.0432
Mar-23 | 320 | 73 | 810 | 100 | 39 | 264.4049
Apr-23 | 325 | 80 | 825 | 89 | 33 | 263.9807
May-23 | 335 | 86 | 843 | 86 | 36 | 269.7591
Jun-23 | 341 | 82 | 872 | 83 | 51 | 281.5763
Jul-23 | 335 | 83 | 903 | 76 | 50 | 287.3072
Aug-23 | 337 | 85 | 927 | 82 | 45 | 293.3349
Sep-23 | 346 | 93 | 924 | 102 | 43 | 300.5072
Oct-23 | 353 | 99 | 952 | 102 | 49 | 310.9044
Nov-23 | 375 | 92 | 961 | 99 | 55 | 317.2507
Dec-23 | 381 | 92 | 974 | 116 | 39 | 324.6657

## data_GIM Trends_2 (hidden)
| Natural Gas | Nuclear | Coal | Wind | Solar | Biomass | Battery | Other | Total Project Count | Cancelled Project Count
Dec-22 | 12.9351 | 0 | 0 | 23.8759 | 123.3404 | 0.053 | 82.8444 | 2.4863 | 1254 | 10
Jan-23 | 12.5421 | 0 | 0 | 24.3507 | 125.5688 | 0.053 | 88.4302 | 2.4863 | 1298 | 1
Feb-23 | 12.5421 | 0 | 0 | 24.7024 | 127.3091 | 0.053 | 91.4927 | 2.4863 | 1334 | 1
Mar-23 | 12.5441 | 0 | 0 | 25.7419 | 127.7646 | 0.053 | 96.3563 | 2.235 | 1373 | 22
Apr-23 | 12.9848 | 0 | 0 | 23.7028 | 129.2365 | 0.053 | 96.0784 | 2.235 | 1385 | 20
May-23 | 13.026 | 0 | 0 | 22.4722 | 129.5069 | 0.053 | 102.8254 | 2.235 | 1424 | 19
Jun-23 | 12.4763 | 0 | 0 | 27.1516 | 130.8574 | 0.053 | 109.3796 | 2.235 | 1479 | 16
Jul-23 | 12.3684 | 0 | 0 | 28.615 | 133.9786 | 0.053 | 110.408 | 2.3856 | 1500 | 16
Aug-23 | 11.8415 | 0 | 0 | 32.0345 | 136.1652 | 0.053 | 111.579 | 2.235 | 1537 | 7
Sep-23 | 11.3837 | 0 | 0 | 31.6397 | 141.3153 | 0.053 | 114.5631 | 2.235 | 1580 | 15
Oct-23 | 13.6376 | 0 | 0 | 31.9157 | 143.2215 | 0.053 | 120.5341 | 2.235 | 1628 | 16
Nov-23 | 15.4573 | 0 | 0 | 32.5096 | 142.606 | 0.053 | 124.9412 | 2.385 | 1656 | 10
Dec-23 | 15.4828 | 0 | 0 | 34.5909 | 145.654 | 0.053 | 127.0677 | 2.367 | 1670 | 12

## data_GIM Trends_3 (hidden)
| # Not Model Ready | # Model Ready | MW Capacity
Dec-22 | 21 | 8 | 270.13
Jan-23 | 23 | 5 | 260.23
Feb-23 | 18 | 13 | 290.03
Mar-23 | 14 | 17 | 290.03
Apr-23 | 15 | 18 | 309.92
May-23 | 18 | 20 | 359.49
Jun-23 | 28 | 22 | 478.65
Jul-23 | 25 | 28 | 501.55
Aug-23 | 31 | 30 | 573.37
Sep-23 | 40 | 32 | 682.72
Oct-23 | 41 | 32 | 692.56
Nov-23 | 44 | 30 | 701.31
Dec-23 | 41 | 28 | 651.14

## data_GIM Trends_4 (hidden)
|  | Gas | Wind | Solar | Battery | Other
COASTAL | 2023 |  |  | 0.27315 | 0.0683
| 2024 | 0.102 | 0.5677 | 2.2282 | 2.6409
| 2025 |  | 0.46176 | 4.8589 | 7.9584
| 2026 |  | 0.5 | 4.1443 | 4.8404 | 0.15
| 2027 | 0.30075 | 0.504 | 2.4518 | 1.7291
| 2030 |  | 2.5
HOUSTON | 2023 | 0.03 |  | 0.35129 | 0.10305
| 2024 | 0.7177 |  | 1.2369 | 4.1301
| 2025 | 1.2127 |  | 0.1124 | 4.2879 | 0.05
| 2026 | 1.4543 |  | 0.35327 | 3.7242
| 2027 | 0.697 |  | 0.1882 | 0.43106
| 2028 |  |  |  |  | 0.05
| 2030 |  | 1
WEST | 2022 |  | 0.041
| 2023 | 2.106 | 1.1679 | 0.6532
| 2024 | 0.68 | 3.4783 | 3.2512 | 4.6201
| 2025 |  | 3.3454 | 10.9868 | 7.9437
| 2026 | 0.45 | 2.214 | 13.8579 | 10.1683
| 2027 |  | 2.9055 | 5.7589 | 2.4702
| 2028 | 1.35 | 3.2066 | 3.2518 | 0.15024
NORTH | 2022 | 0.067
| 2023 | 0.054 | 0.85812 | 1.2441 | 0.24074
| 2024 | 0.37832 | 0.72978 | 7.4077 | 4.4598
| 2025 | 0.758 | 0.78605 | 14.3632 | 10.2498 | 0.153
| 2026 | 2.388 | 1.8783 | 15.7297 | 16.1456
| 2027 |  |  | 3.9689 | 3.2196
| 2028 |  |  | 1.2726 | 0.25594 | 0.15
| 2030 |  |  |  | 0.2076 | 1.232
PANHANDLE | 2021 | 0.112
| 2024 |  | 0.68182 | 2.0701 | 0.80781
| 2025 |  | 0.45538 | 2.8702 | 0.71696
| 2026 |  | 0.8365 | 2.0078 | 1.9089
| 2027 |  |  | 1.0041 | 0.3717
| 2028 |  | 1.9029 | 1.971
| 2029 |  | 0.623 | 0.4454
SOUTH | 2023 | 0.0031 |  | 0.49252
| 2024 | 0.1444 | 0.83833 | 10.0442 | 6.3849
| 2025 | 1.1141 | 1.8694 | 11.5791 | 11.3874
| 2026 | 0.1884 | 1.2391 | 11.5962 | 12.4695 | 0.635
| 2027 | 1.175 |  | 2.3417 | 2.5347
| 2028 |  |  | 1.2872 | 0.44085

## Commissioning Update
Commissioning Approvals during December 2023
Commissioning Category | INR | Size Category | Project Name | Fuel | County | Approval Date * | MW **
Commercial Operation Approved by ERCOT* | 22INR0485 | Large | House Mountain | Other | Brewster | 2023-12-21 | 63
Commercial Operation Approved by ERCOT* | 23INR0511 | Small | Mayberry BESS | Other | Cameron | 2023-12-20 | 9.99
Commercial Operation Approved by ERCOT* | 23INR0371 | Large | Rodeo Ranch Energy Storage | Other | Reeves | 2023-12-27 | 300.64
Commercial Operation Approved by ERCOT* | 23INR0515 | Small | Santa Rosa BESS | Other | Cameron | 2023-12-14 | 9.99
Commercial Operation Approved by ERCOT* | 22INR0429 | Large | Sun Valley BESS | Other | Hill | 2023-12-28 | 101.4
Commercial Operation Approved by ERCOT* | 22INR0495 | Large | TIMBERWOLF BESS 2 | Other | Crane | 2023-12-21 | 150
Commercial Operation Approved by ERCOT* | 23INR0513 | Small | Elsa BESS | Other | Hidalgo | 2023-12-14 | 9.99
Commercial Operation Approved by ERCOT* | 23INR0512 | Small | West Harlingen BESS | Other | Cameron | 2023-12-14 | 9.99
Commercial Operation Approved by ERCOT* | 23INR0514 | Small | North Mercedes BESS | Other | Hidalgo | 2023-12-14 | 9.99
Synchronization Approved by ERCOT | 21INR0027 | Large | Zier Storage | Other | Kinney | 2023-12-21 | 40.41
Synchronization Approved by ERCOT | 21INR0351 | Large | 7V Solar | Solar | Fayette | 2023-12-13 | 240.63
Synchronization Approved by ERCOT | 24INR0427 | Large | CPS AvR CT1 Rotor Replacement | Gas | Bexar | 2023-12-04 | 11.3
Synchronization Approved by ERCOT | 23INR0124 | Large | Coral Storage | Other | Falls | 2023-12-11 | 99
Synchronization Approved by ERCOT | 21INR0458 | Large | Porter Solar | Solar | Denton | 2023-12-11 | 245.83
Synchronization Approved by ERCOT | 22INR0363 | Large | Hayhurst Texas Solar | Solar | Culberson | 2023-12-12 | 24.76
Synchronization Approved by ERCOT | 18INR0030 | Large | Canyon Wind | Wind | Scurry | 2023-12-01 | 308.82
Synchronization Approved by ERCOT | 22INR0409 | Large | Stampede Solar | Solar | Hopkins | 2023-12-22 | 256.34
Synchronization Approved by ERCOT | 22INR0405 | Large | Fence Post BESS | Other | Navarro | 2023-12-05 | 72.23
Synchronization Approved by ERCOT | 22INR0366 | Large | LIBRA BESS | Other | Guadalupe | 2023-12-05 | 206.21
Synchronization Approved by ERCOT | 22INR0410 | Large | Stampede BESS | Other | Hopkins | 2023-12-22 | 72.38
Synchronization Approved by ERCOT | 21INR0450 | Large | Danish Fields Storage | Other | Wharton | 2023-12-28 | 152.43
Synchronization Approved by ERCOT | 23INR0554 | Small | Hamilton BESS | Other | Val Verde | 2023-12-15 | 9.95
Synchronization Approved by ERCOT | 22INR0502 | Large | Shamrock | Wind | Crockett | 2023-12-13 | 223.92
Synchronization Approved by ERCOT | 23INR0553 | Small | Val Verde BESS | Other | Hidalgo | 2023-12-06 | 9.95
Synchronization Approved by ERCOT | 22INR0404 | Large | Fence Post Solar | Solar | Navarro | 2023-12-05 | 237.31
Energization Approved by ERCOT | 24INR0586 | Small | Judkins BESS | Other | Ector | 2023-12-08 | 9.95
Energization Approved by ERCOT | 23INR0387 | Large | Pioneer DJ Wind | Wind | Midland | 2023-12-19 | 140.32
Energization Approved by ERCOT | 23INR0159 | Large | Five Wells Storage | Other | Bell | 2023-12-07 | 220.8
Energization Approved by ERCOT | 22INR0336 | Large | Estonian Storage | Other | Delta | 2023-12-05 | 101.6
Energization Approved by ERCOT | 24INR0585 | Small | Pauline BESS | Other | Henderson | 2023-12-22 | 9.95
Energization Approved by ERCOT | 22INR0502 | Large | Shamrock | Wind | Crockett | 2023-12-07 | 223.92
Energization Approved by ERCOT | 23INR0570 | Small | Mineral Wells East BESS | Other | Palo Pinto | 2023-12-22 | 9.95
Energization Approved by ERCOT | 23INR0239 | Large | Giga Texas Energy Storage | Other | Travis | 2023-12-13 | 131.05
Energization Approved by ERCOT | 23INR0522 | Small | Diboll Bess | Other | Angelina | 2023-12-08 | 9.95
Energization Approved by ERCOT | 21INR0450 | Large | Danish Fields Storage | Other | Wharton | 2023-12-18 | 152.43
Energization Approved by ERCOT | 23INR0565 | Small | Garden City East BESS | Other | Glasscock | 2023-12-22 | 9.95
Energization Approved by ERCOT | 23INR0688 | Small | Midway1 BESS | Other | Ector | 2023-12-01 | 9.95
Energization Approved by ERCOT | 22INR0335 | Large | Estonian Solar | Solar | Delta | 2023-12-05 | 202.5
Energization Approved by ERCOT | 23INR0554 | Small | Hamilton BESS | Other | Val Verde | 2023-12-08 | 9.95
* For projects approved for commercial operations, the approval date is the Resource Commissioning Date defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a
Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative
values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.

## Inactive Projects
Inactive Projects as of end of December 2023*
INR | Size Category | Project Name | Fuel | County | Inactive Date | MW **
16INR0044 | Large | Halyard Wharton | Gas | Wharton | 2019-08-30 13:26 | 484
13INR0025 | Large | Northdraw Wind | Wind | Randall | 2019-08-30 13:38 | 150
17INR0010 | Large | FGE Texas 2 Gas | Gas | Mitchell | 2019-08-30 13:41 | 742.9
16INR0099 | Large | Hecate Solar | Solar | Brewster | 2019-08-30 14:57 | 33
16INR0101 | Large | Chatee Solar | Solar | Pecos | 2019-08-30 14:59 | 57
16INR0102 | Large | Owego Solar | Solar | Pecos | 2019-08-30 15:01 | 74
13INR0010a | Large | Mariah Del Este Wind | Wind | Parmer | 2019-09-09 10:19 | 152.5
20INR0025 | Large | Spinel Solar | Solar | Medina | 2019-09-10 14:02 | 30
20INR0024 | Large | Fluorite Solar | Solar | Uvalde | 2019-09-11 13:32 | 25
17INR0036 | Large | Grandview 4 Phase A Wind | Wind | Carson | 2019-10-31 10:59 | 200.5
20INR0096 | Large | Desert Rose Solar | Solar | Andrews | 2019-11-12 13:44 | 200
18INR0009 | Large | Eagle Pines Gas | Gas | Cherokee | 2019-11-19 10:20 | 1173.5
19INR0031 | Large | Bestla Solar | Solar | Winkler | 2020-03-04 16:50 | 180
20INR0146 | Large | Angus Storage | Other | Bosque | 2020-05-04 11:36 | 63
22INR0329 | Large | Girasol | Solar | Zavala | 2020-05-22 08:29 | 200
20INR0023 | Large | Agate Solar | Solar | Ellis | 2020-05-22 15:12 | 60
19INR0101 | Large | Tehuacana Wind | Wind | Limestone | 2020-05-28 10:23 | 600
21INR0503 | Large | Celeste Energy Storage | Other | Pecos | 2020-06-03 10:35 | 60.89
19INR0030 | Large | San Bernard Solar | Solar | Wharton | 2020-06-18 11:51 | 100
17INR0043 | Large | Vaquero 1 Wind | Wind | Zapata | 2020-07-01 18:45 | 400
21INR0015 | Large | Arroyo Del Bisonte Solar | Solar | Wharton | 2020-07-06 16:03 | 300
20INR0299 | Large | Sparkl BESS | Other | Guadalupe | 2020-09-16 12:30 | 20
19INR0161 | Large | Pierce Wind | Wind | Wharton | 2021-03-16 10:13 | 300
20INR0043 | Large | Gulf Wind 2 | Wind | Kenedy | 2021-04-02 08:54 | 226.5
21INR0485 | Large | Texana Storage | Other | Wharton | 2021-04-05 22:27 | 150.94
20INR0267 | Large | Greens Bayou Expansion | Gas | Harris | 2021-04-17 01:08 | 140
18INR0072 | Large | Blue Summit repower | Wind | Wilbarger | 2021-04-28 15:42 | 9.9
21INR0465 | Large | San Bernard Storage | Other | Wharton | 2021-06-14 17:46 | 100.62
20INR0013 | Large | Basalt Solar | Solar | Uvalde | 2021-08-16 09:22 | 20
23INR0152 | Large | Madrone Energy Storage | Other | Comal | 2021-08-20 09:03 | 102.49
20INR0232 | Large | Mars Solar | Solar | Childress | 2021-11-17 09:06 | 52.75
22INR0548 | Large | Fighting Jays Battery | Other | Fort Bend | 2022-02-25 17:43 | 53.2
19INR0099b | Large | Kontiki 2 Wind (ERNEST) | Wind | Glasscock | 2022-03-10 15:42 | 250.1
19INR0099a | Large | Kontiki 1 Wind (ERIK) | Wind | Glasscock | 2022-03-10 15:46 | 250.1
20INR0259 | Large | San Bernard Solar II | Solar | Wharton | 2022-03-11 11:26 | 102
22INR0266 | Large | Creekfield Solar | Solar | Fort Bend | 2022-03-23 11:25 | 161.34
22INR0379 | Large | Creekfield Storage | Other | Fort Bend | 2022-03-25 16:59 | 69
23INR0067 | Large | Wekiva Grid | Other | Titus | 2022-05-09 21:05 | 202.61
23INR0158 | Large | High Chaparral BESS 138kV | Other | Brazoria | 2022-06-15 15:23 | 51.74
23INR0378 | Large | Heartfield Storage | Other | Hidalgo | 2022-07-15 16:29 | 152
23INR0526 | Large | Canyon Wind Alternative | Wind | Scurry | 2022-09-02 16:11 | 311.6
19INR0017 | Large | Tri-County Solar | Solar | Crane | 2022-09-21 15:00 | 177.75
16INR0033 | Large | Hart Wind | Wind | Castro | 2022-10-13 14:42 | 165
20INR0202 | Large | Rueter Solar | Solar | Bosque | 2022-11-01 16:15 | 200
21INR0363 | Large | Carol Battery | Other | Potter | 2022-11-07 14:57 | 168
21INR0486 | Large | Pandora Solar | Solar | Wilson | 2022-11-14 14:50 | 252
25INR0128 | Large | Fiji Solar | Solar | Limestone | 2023-01-03 14:04 | 202.7
23INR0210 | Large | Cornwall Solar | Solar | Williamson | 2023-01-19 21:20 | 204.5
24INR0244 | Large | Cornwall BESS | Other | Williamson | 2023-01-19 21:20 | 203.8
24INR0239 | Large | Trojan BESS | Other | Cooke | 2023-01-25 12:41 | 201.9
22INR0269 | Large | Shinnery Hill Solar | Solar | Wichita | 2023-02-17 10:50 | 502.54
21INR0285 | Large | LARISA SOLAR | Solar | Jones | 2023-03-14 08:07 | 408.34
24INR0290 | Large | Rubicon Echo Wind | Wind | Haskell | 2023-04-13 11:18 | 228.4
23INR0192 | Large | Utica Solar | Solar | Guadalupe | 2023-04-25 09:22 | 204.5
24INR0241 | Large | Utica BESS | Other | Guadalupe | 2023-04-25 09:23 | 203.9
25INR0454 | Large | Canvasback II BESS | Other | Calhoun | 2023-05-02 12:15 | 50.4
23INR0157 | Large | High Chaparral Solar 138kV | Solar | Brazoria | 2023-05-09 15:54 | 147.63
23INR0616 | Large | JUNO SOLAR 3 | Solar | Borden | 2023-05-15 14:33 | 9.99
17INR0022 | Large | MIRAGE | Gas | Harris | 2023-05-31 11:28 | 11
24INR0400 | Large | Bora Bora Solar | Solar | Wichita | 2023-06-05 16:38 | 233.35
25INR0243 | Large | CLUTCH CITY STORAGE I SLF | Other | Galveston | 2023-06-28 17:51 | 16.63
25INR0332 | Large | Clutch City Storage II SLF | Other | Brazoria | 2023-06-28 17:51 | 11.3
25INR0095 | Large | Brittlebush BESS | Other | Henderson | 2023-07-05 22:58 | 597.08
25INR0094 | Large | Brittlebush Solar | Solar | Henderson | 2023-07-05 22:58 | 594.01
20INR0143 | Large | Soda Lake Solar 1 SLF | Solar | Crane | 2023-07-11 08:47 | 202.99
23INR0080 | Large | Soda Lake Solar 2 SLF | Solar | Crane | 2023-07-11 08:48 | 202.59
24INR0383 | Large | Soda Lake BESS 2 SLF | Other | Crane | 2023-07-11 08:48 | 0
24INR0238 | Large | Appaloosa Run BESS | Other | Upton | 2023-07-31 08:50 | 200.5
25INR0089 | Large | Tempesta | Solar | Kaufman | 2023-08-11 14:22 | 443
25INR0090 | Large | Tempesta BESS | Other | Kaufman | 2023-08-11 14:23 | 600
24INR0402 | Large | Inertia BESS 3 | Other | Jones | 2023-08-21 15:56 | 108.44
24INR0248 | Large | Half Moon 2 BESS | Other | Hidalgo | 2023-08-21 16:00 | 102
22INR0275 | Large | Coleto Creek ESS Addition | Other | Goliad | 2023-09-18 12:23 | 100.1
26INR0121 | Large | Pioneer Hutt Solar (Alternative POI) | Solar | Midland | 2023-09-22 10:09 | 116
24INR0044 | Large | Brass Fork Solar 2 | Solar | Haskell | 2023-10-02 15:31 | 208.41
24INR0428 | Large | Pioneer Hutt Solar | Solar | Midland | 2023-10-05 23:23 | 116
24INR0315 | Large | Black Springs BESS | Other | Palo Pinto | 2023-11-13 10:31 | 120.96
23INR0116 | Large | Cantaloupe Solar | Solar | Reeves | 2023-11-15 09:24 | 303.13
23INR0117 | Large | Cantaloupe Storage | Other | Reeves | 2023-11-15 09:25 | 251.05
21INR0354 | Large | Kochab Solar | Solar | Uvalde | 2023-11-22 18:08 | 204
24INR0292 | Large | Urca Solar | Solar | Live Oak | 2023-12-10 02:38 | 204.1
23INR0372 | Large | Cross Trails Storage | Other | Scurry | 2023-12-22 09:38 | 38.86
22INR0592 | Large | Cross Trails Gravitational Storage | Other | Scurry | 2023-12-22 09:39 | 18.03
* Includes only those projects designated as Inactive by ERCOT or the project developer after the developer makes a Full Interconnection Study (FIS) request, or
in the case of Small Generators, after their Resource Registrations have been approved.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.

## Cancellation Update
Projects Cancelled by the Developer during December 2023*
INR | Size Category | Project Name | Fuel | County | Cancel Date | MW **
22INR0272 | Large | Brinton Fork Solar | Solar | Haskell | 2023-12-04 | 513.5
25INR0149 | Large | Enbridge Ingleside Solar SLF | Solar | San Patricio | 2023-12-04 18:37 | 61.9
25INR0150 | Large | Enbridge Ingleside Storage SLF | Other | San Patricio | 2023-12-04 18:37 | 0
25INR0563 | Large | Ambrose Energy Storage | Other | Erath | 2023-12-05 15:03 | 101.2
25INR0564 | Large | McCook Energy Storage | Other | Hidalgo | 2023-12-05 15:04 | 101.2
21INR0495 | Large | Belding 2 Batt | Other | Pecos | 2023-12-07 09:05 | 51.48
22INR0447 | Large | Beachwood Energy Storage (Mark One BESS) | Other | Brazoria | 2023-12-08 09:37 | 100.53
24INR0158 | Large | Comet Solar | Solar | Cottle | 2023-12-11 | 151.76
26INR0199 | Large | Gold Rush Energy Storage | Other | Mills | 2023-12-14 13:24 | 200.6
26INR0224 | Large | GIRALDA SOLAR | Solar | Van Zandt | 2023-12-19 08:32 | 137.34
* Includes only those projects cancelled by the developer after it makes a Full Interconnection Study (FIS) request, or in the case of Small Generators, after the Resource Registrations have been approved.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.