## Contents
GINR Activity: Feb 01, 2020 to Feb 29, 2020
Table of Contents
Disclaimer and References | Disclaimer on the use of this report, and references to associated ERCOT Binding Documents ***Please read***
Acronyms | A list of the various acronyms used throughout the report
Summary | Tables that provide project aggregate counts and megawatt capacities by GINR phase and fuel type
Project Details | A table that lists project details; only includes projects for which a Full Interconnection Study has been requested
GINR Trends | Charts and tables that show historical and projected interconnection study trends
Commissioning Update | A table listing project commissioning approval milestones met for the month: energization, synchronization, and commercial operations approval
Inactive Projects | A table listing Inactive projects
Cancellation Update | A table listing the projects cancelled for the month
Time of Report Run: Mar 1, 2020 8:00:22 AM

## Disclaimer and References
Generator Interconnection Status Report - Disclaimer
FOR PLANNING PURPOSES ONLY
This ERCOT Working Paper has been prepared for specific ERCOT and Market Participant purposes, and has been
developed from data provided by Interconnecting Entities and Transmission Service Providers that has been entered into the online GINR system.
The data may contain errors or be obsolete depending on when the data was entered. ERCOT MAKES NO WARRANTY, EXPRESS
OR IMPLIED,INCLUDING ANY WARRANTY OF MERCHANTABILITY OR FITNESS FOR ANY PARTICULAR PURPOSE,
AND DISCLAIMS ANY AND ALL LIABILITY WITH RESPECT TO THE ACCURACY OF SAME OR THE FITNESS OR
APPROPRIATENESS OF SAME FOR ANY PARTICULAR USE. THIS ERCOT WORKING PAPER IS SUPPLIED WITH ALL FAULTS.
References
The links below provide more information on the ERCOT interconnection process:
http://www.ercot.com/mktrules/guides/planning/current
http://www.ercot.com/services/rq/re/reg/Resource%20Interconnection%20Handbook.pdf

## Acronyms
Acronyms
GINR = Generation Interconnection or Change Request
COD = Commercial Operation Date
SS = Security Screening Study
FIS = Full Interconnection Study
IA = Interconnection Agreement; can be either of the following:
- Standard Generation Interconnection Agreement (SGIA)
- Public financially binding agreement
- An official letter from a Municipally Owned Utility or Electric Cooperative signifying developer intent to build and operate generation facilities and
interconnect with the MOU or EC
POI = Point of lnterconnection
INR = Interconnection Request Number
TSP = Transmission Service Provider
NtP = Notice-to-Proceed given to the TSP for interconnection construction
CDR = Capacity, Demand and Reserves Report
SFS = Sufficient Financial Security provided to the TSP for construction of the interconnection facilities
QSA = Quarterly Stability Assessment
INA = Inactive status
PLN = Planned status
Fuel Types | Technology Types
BIO = Biomass | BA = Battery Energy Storage
COA = Coal | CC = Combined-Cycle
GAS = Gas | CE = Compressed Air Energy Storage
GEO = Geothermal | CP = Concentrated Solar Power
HYD = Hydrogen | EN = Energy Storage
NUC = Nuclear | FC = Fuel Cell
OIL = Fuel Oil | GT = Combustion (gas) Turbine, but not part of a Combined-Cycle
OTH = Other | HY = Hydroelectric Turbine
PET = Petcoke | IC = Internal Combustion Engine, eg. Reciprocating
SOL = Solar | OT = Other
WAT = Water | PV = Photovoltaic Solar
WIN = Wind | ST = Steam Turbine other than Combined-Cycle
WT = Wind Turbine

## Summary
Summary |  |  | Major GINR Milestone Status by Fuel/Technology Type, MW
Currently tracking 633 generation interconnection or change requests as of Feb 29, 2020 |  |  | Includes only those projects for which a Screening Study (SS) has been requested and are not Inactive.
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  |  | Fuel | Technology | SS Started | SS Started | SS Completed | SS Completed | SS Completed | SS Completed | SS Completed | TOTAL
Includes only those projects for which a Screening Study (SS) has been requested |  |  | Type | Type | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | FIS Started | FIS Completed
and are not Inactive |  |  |  |  | No IA | No IA | No IA | No IA | No IA | IA | IA
Status of SS, FIS, and IA | Project Count | % of Total | Gas | Combined-Cycle |  |  |  | 103.3 | 83 | 45 | 292 | 523.3
SS Started, FIS Not Started, No IA | 48 | 7.583% | Gas | Combustion Turbine |  |  |  | 2598.7 | 1052.6 | 140 | 808 | 4599.3
SS Started, FIS Started, No IA | 28 | 4.423% | Gas | Internal Combustion Engine
SS Completed, FIS Not Started, No IA | 87 | 13.74% | Gas | Compressed Air Energy Storage |  |  | 324.4 |  |  |  |  | 324.4
SS Completed, FIS Started, No IA | 306 | 48.34% | Gas | Steam Turbine |  |  |  | 60 |  |  |  | 60
SS Completed, FIS Completed, No IA | 27 | 4.265% | Gas | Fuel Cell
SS Completed, FIS Started, IA | 43 | 6.793% | Gas | Total gas |  |  | 324.4 | 2762 | 1135.6 | 185 | 1100 | 5507
SS Completed, FIS Completed, IA | 94 | 14.85% | Coal
Total Interconnection Requests | 633 |  | Wind |  | 664 | 451.5 | 2185.2 | 13933.71 | 640.2 | 3779.72 | 8860.39 | 30514.72
Inactive (since last month) | 3 |  | Solar |  | 9615.28 | 4023.8 | 11314.71 | 39272.7 | 2524 | 5200.47 | 5748.16 | 77699.12
Cancelled (since last month) | 1 |  | Biomass
| Capacity, MW |  | Other | Battery | 1373.4 | 1721.4 | 2587 | 3804.56 | 50 | 242.22 | 200 | 9978.58
Total Capacity Under Study | 124062.42 |  | Other* |  |  | 50 | 150 | 150 | 13 |  |  | 363
Interconnection Agreements Executed | 25315.96 |  | TOTAL |  | 11652.68 | 6246.7 | 16561.31 | 59922.97 | 4362.8 | 9407.41 | 15908.55 | 124062.42
Inactive (since last month) | 430.2
Cancelled (since last month) | 201.6
* Other includes petroleum coke (pet coke), hydroelectric, fuel oil, geothermal energy, other miscellaneous fuels reported by developers, and fuel cells that use fuels other than natural gas.

## Project Details
GINR Project Details
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study has been requested are included.
Excludes projects that have a status of Inactive (status = INA).
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GINR system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not been obtained or reported to ERCOT yet.
Project Attributes | [10 empty] | Changes from Last Report | GINR Project Milestone Dates
INR | Project Name | GINR Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | IA Signed |  | Air Permit | GHG Permit | Water Availability | Meets Planning | Meets All Planning |  | Construction Start | Construction End | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Change indicators: Proj Name, MW | [5 empty] | Financial Security |  |  |  | Guide Section 6.9(1) | Guide Section 6.9 | Meets Planning Guide
[11 empty] | Size , COD, SFS/NtP, FIS Request | [5 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[11 empty] | Status Change SUS-to-PLN | [5 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[21 empty] | Models | Models
08INR0019b | Grandview 5 W | SS Completed, FIS Started, No IA | Eon | 79005 Railhead 345kV | Gray | PANHANDLE | 2020-12-15 | WIN | WT | 249 |  | 2006-07-21 | 2006-10-02 | 2006-07-21 |  |  | No | Not Required | Not Required | Not Required
11INR0062 | Shaffer | SS Completed, FIS Completed, IA | Clearway Energy | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2020-01-31 | WIN | WT | 226 |  | 2009-04-23 | 2009-06-16 | 2009-07-21 | 2018-06-13 | 2013-07-02 | Yes | Not Required | Not Required | Not Required | 2018-04-18 | 2018-09-28 | 2018-07-31 |  |  | 2019-03-27 | 2019-04-05
12INR0060 | Wilson Ranch | SS Completed, FIS Completed, IA | ENGIE | 76003 Big Hill 345kV | Schleicher | WEST | 2020-02-28 | WIN | WT | 199.5 | COD | 2010-12-03 | 2014-03-21 | 2011-06-06 | 2018-05-31 | 2018-05-21 | Yes | Not Required | Not Required | Not Required | 2018-05-21 | 2018-09-28 | 2018-04-30 |  |  | 2018-10-11 | 2018-11-29
14INR0009 | WKN Amadeus Wind | SS Completed, FIS Completed, IA | WKN | tap 345kV 11305 Dermott - 60706 Kirchhoff | Fisher | WEST | 2020-10-30 | WIN | WT | 250.12 | COD | 2011-01-24 | 2011-03-18 | 2011-09-12 | 2019-11-01 | 2018-03-15 | Yes | Not Required | Not Required | Not Required | 2019-03-07 | 2019-10-28 | 2019-11-01
14INR0033 | Goodnight Wind | SS Completed, FIS Started, IA | FGE Power | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | PANHANDLE | 2020-12-12 | WIN | WT | 504.4 |  | 2012-07-24 | 2012-09-19 | 2013-03-04 |  | 2018-03-07 | No | Not Required | Not Required | Not Required
15INR0044 | Corazon Solar | SS Completed, FIS Started, IA | Corazon Energy, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2021-05-31 | SOL | PV | 200 | Status Change INA-to-PLN | 2013-09-06 | 2013-09-16 | 2013-08-20 |  | 2020-01-09 | No | Not Required | Not Required | Not Required
15INR0059 | Emerald Grove Solar | SS Completed, FIS Started, IA | Emerald Grove Solar, LLC | 76602 Horse Crossing 138kV | Pecos | WEST | 2021-04-10 | SOL | PV | 108 |  | 2013-11-13 | 2013-12-23 | 2013-11-12 |  | 2018-06-27 | Yes | Not Required | Not Required | Not Required | Date Not Available | 2019-04-17
15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2020-04-16 | WIN | WT | 162.1 |  | 2013-11-27 | 2014-01-27 | 2014-04-15 | 2017-09-27 | 2018-05-30 | Yes | Not Required | Not Required | Not Required | 2018-05-30 | 2018-09-19 | 2019-01-22 |  |  | 2020-02-10
15INR0090 | Pflugerville Solar | SS Completed, FIS Completed, IA | RRE Solar | tap 138kV 7336 Gillie - 3650 Elgin | Travis | SOUTH | 2020-12-31 | SOL | PV | 144 |  | 2015-04-28 | 2015-07-01 | 2015-09-30 | 2020-01-31 | 2017-06-13 | Yes | Not Required | Not Required | Not Required
16INR0012 | Stella 2 Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 80076 Ajo - 80071 Zorillo | Kenedy | COASTAL | 2020-12-30 | WIN | WT | 201 |  | 2013-06-13 | 2013-03-15 | 2013-09-10 |  |  | No | Not Required | Not Required | Not Required
16INR0033 | Hart Wind | SS Completed, FIS Started, IA | Orion | 79501 Ogallala 345kV | Castro | PANHANDLE | 2021-12-31 | WIN | WT | 150 |  | 2014-02-10 | 2014-03-20 | 2014-10-27 |  | 2018-08-06 | No | Not Required | Not Required | Not Required
16INR0037c | Pumpkin Farm Wind | SS Completed, FIS Completed, IA | Apex Clean | 79505 White River 345kV | Floyd | PANHANDLE | 2020-12-01 | WIN | WT | 280.9 |  | 2014-02-24 | 2014-04-08 | 2014-02-18 | 2018-01-12 | 2017-03-24 | Yes | Not Required | Not Required | Not Required | 2017-03-24 | 2018-09-19
16INR0049 | Nazareth Solar | SS Completed, FIS Started, IA | Lendlease Energy | 79501 Ogallala 345kV | Castro | PANHANDLE | 2022-05-31 | SOL | PV | 201 |  | 2014-06-19 | 2014-07-25 | 2014-07-01 |  | 2018-05-10 | Yes | Not Required | Not Required | Not Required | 2019-06-06
16INR0054 | NA | SS Completed, FIS Completed, IA | NASA | 42970 Nasa 138kV | Harris | HOUSTON | 2018-09-01 | GAS | CC | 12 |  | 2015-03-10 | 2015-04-01 | 2015-03-10 | 2016-01-26 | 2016-10-27 | Yes | Not Required | Not Required |  | 2016-11-10 | 2018-09-28 |  |  |  |  | 2017-11-27
16INR0074 | Chocolate Bayou W | SS Completed, FIS Completed, IA | Engie | tap 138kV 42109 Hudson - 42960 Mustang | Brazoria | COASTAL | 2021-05-01 | WIN | WT | 149.5 |  | 2014-12-08 | 2015-03-02 | 2014-12-04 | 2019-02-26 | 2019-09-26 | No | Not Required | Not Required | Not Required
16INR0076 | Hudson (Ineos/Brazoria) | SS Completed, FIS Completed, IA | Ineos | 42100 Hudson 138kV | Brazoria | COASTAL | 2020-03-31 | GAS | GT | 96 | COD | 2015-01-12 | 2015-03-19 | 2015-06-24 | 2017-08-24 | 2017-12-05 | Yes | 2017-02-10 | 2017-02-10 | 2018-01-10 | 2018-10-09 | 2019-02-12 | 2018-08-01 |  |  | 2019-02-12 | 2019-08-16
16INR0081 | Mesteno Windpower | SS Completed, FIS Completed, IA | Mesteno Windpower, LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2020-04-01 | WIN | WT | 201.6 | COD | 2014-12-30 | 2015-03-09 | 2014-12-30 | 2018-01-29 | 2018-04-25 | Yes | Not Required | Not Required | Not Required | 2018-04-25 | 2019-03-28 | 2019-04-01 |  |  | 2019-11-26 | 2019-12-12
16INR0085 | Priddy Wind | SS Completed, FIS Started, No IA | ENGIE North America | tap 345kV 1444 Brown – 3422 Killeen | Mills | NORTH | 2021-09-01 | WIN | WT | 300 |  | 2015-01-14 | 2015-02-10 | 2015-03-06 |  |  | No | Not Required | Not Required | Not Required
16INR0086 | Cactus Flats Wind | SS Completed, FIS Completed, IA | Southern Power Company | tap 138kV 6480 SAPS - 6365 Yellow Jacket | Concho | WEST | 2020-06-30 | WIN | WT | 148.4 | COD | 2015-02-02 | 2015-03-27 | 2015-02-02 | 2017-10-20 | 2017-03-15 | Yes | Not Required | Not Required | Not Required | Date Not Available | 2018-09-05 | 2017-11-01 |  |  | 2018-05-24 | 2018-06-11
16INR0104 | Big Sampson Wind | SS Completed, FIS Completed, IA | Infinity Renewables | 76005 Schneeman Draw 345kV | Crockett | WEST | 2021-09-01 | WIN | WT | 400 |  | 2015-05-11 | 2015-06-17 | 2015-05-11 | 2018-12-11 | 2019-11-08 | No | Not Required | Not Required | Not Required
16INR0111 | Las Lomas Wind | SS Completed, FIS Started, IA | Las Lomas Wind Energy, LLC | 8957 Lopeno 138kV | Starr | SOUTH | 2020-12-01 | WIN | WT | 200 |  | 2015-05-18 | 2015-06-25 | 2015-05-18 |  | 2018-12-22 | Yes | Not Required | Not Required | Not Required | 2019-01-29
16INR0114 | Upton Solar | SS Completed, FIS Started, IA | Clearway Energy | 76020 SONNE 138-kV | Upton | WEST | 2020-09-01 | SOL | PV | 104.56 |  | 2015-05-27 | 2015-07-02 | 2015-06-08 |  | 2015-12-04 | Yes | Not Required | Not Required | Not Required | 2018-12-14
16INR0117 | Tecovas 1 W | SS Completed, FIS Started, No IA | Engie | 79503 Tule Canyon 345kV | Briscoe | PANHANDLE | 2020-06-01 | WIN | WT | 200 |  | 2015-06-23 | 2015-07-06 | 2015-10-19 |  |  | No | Not Required | Not Required | Not Required
17INR0020a | RE Maplewood 2a Solar | SS Completed, FIS Started, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2021-04-01 | SOL | PV | 222 |  | 2014-10-17 | 2014-12-01 | 2014-10-22 |  | 2019-05-06 | Yes | Not Required | Not Required | Not Required | 2018-03-19
17INR0020b | RE Maplewood 2b Solar | SS Completed, FIS Started, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2020-12-31 | SOL | PV | 28 |  | 2014-10-17 | 2014-12-01 | 2014-10-22 |  | 2019-05-06 | Yes | Not Required | Not Required | Not Required | 2018-03-19
17INR0020c | RE Maplewood 2c Solar | SS Completed, FIS Started, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2021-06-30 | SOL | PV | 250 |  | 2014-10-17 | 2014-12-01 | 2014-10-22 |  | 2019-05-06 | Yes | Not Required | Not Required | Not Required | 2018-03-19
17INR0022 | MIRAGE | SS Completed, FIS Completed, IA | Net Power | 111161 Mirage 13.8kV | Harris | HOUSTON | 2020-05-04 | GAS | GT | 11 | COD | 2015-02-17 | 2015-05-01 | 2015-05-20 | 2016-09-13 | 2016-08-31 | Yes | 2015-05-08 | Not Required | 2017-10-12 | 2016-10-11 | 2018-09-28 |  |  |  | 2017-02-06
17INR0025 | Reloj Del Sol Wind | SS Completed, FIS Started, IA | EDP Renewables | 80220 Cenizo 345kV | Zapata | SOUTH | 2020-10-31 | WIN | WT | 202 |  | 2015-03-24 | 2015-05-05 | 2015-09-14 |  | 2018-12-21 | Yes | Not Required | Not Required | Not Required | 2019-03-04
17INR0027b | Coyote Wind | SS Completed, FIS Completed, IA | Coyote Wind | 11305 Dermott 345kV | Scurry | WEST | 2020-10-29 | WIN | WT | 242.6 |  | 2015-04-22 | 2015-05-22 | 2015-06-11 | 2020-01-31 | 2016-08-09 | Yes | Not Required | Not Required | Not Required | 2016-08-09 | 2020-01-28 | 2020-01-31
17INR0031 | Espiritu Wind | SS Completed, FIS Completed, IA | Acciona | 8640 Kelvin 138kV | Cameron | COASTAL | 2020-12-21 | WIN | WT | 25.2 |  | 2015-05-19 | 2015-06-22 | 2015-10-26 | 2020-01-21 | 2020-01-29 | Yes | Not Required | Not Required | Not Required | 2020-01-29 | 2020-01-29 | 2020-01-29
17INR0033 | Tecovas 2 W | SS Completed, FIS Started, No IA | Engie | 79503 Tule Canyon 345kV | Briscoe | PANHANDLE | 2020-06-01 | WIN | WT | 200 |  | 2015-06-23 | 2015-07-06 | 2015-10-19 |  |  | No | Not Required | Not Required | Not Required
17INR0035 | Las Majadas Wind | SS Completed, FIS Completed, IA | EDF Renewable Energy | 8318 Rio Hondo 345kV plus 12.5mi gentie | Willacy | COASTAL | 2020-10-29 | WIN | WT | 272.6 |  | 2015-10-30 | 2015-12-14 | 2015-12-09 | 2020-01-30 | 2018-04-13 | Yes | Not Required | Not Required | Not Required | 2019-07-22 | 2020-01-30 | 2020-01-30
17INR0037 | Palmas Altas Wind | SS Completed, FIS Completed, IA | Acciona | 5760 PALMAS 138 kV | Cameron | COASTAL | 2020-03-16 | WIN | WT | 144.9 | COD | 2016-03-24 | 2016-05-06 | 2016-07-20 | 2018-08-07 | 2017-11-30 | Yes | Not Required | Not Required | Not Required | 2018-10-04 | 2018-10-04 | 2018-10-04 |  |  | 2019-12-03 | 2019-12-10
17INR0052 | Horse13 CallD repower | SS Completed, FIS Completed, IA | Nextera | 6216 Bluff Creek 138kV | Taylor | WEST | 2020-02-28 | WIN | WT | 44 | COD | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2018-04-10 | 2019-05-22 | Yes | Not Required | Not Required | Not Required
17INR0054 | Capricorn I & III repower | SS Completed, FIS Completed, IA | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WEST | 2020-07-05 | WIN | WT | 32 | COD | 2017-03-09 | 2017-04-24 | 2017-03-09 | 2018-02-26 | 2006-11-14 | No | Not Required | Not Required | Not Required
17INR0061 | Capricorn IV repower | SS Completed, FIS Completed, IA | Nextera |  | Sterling | WEST | 2020-06-30 | WIN | WT | 9 |  | 2017-08-23 | 2017-09-15 | 2017-08-23 | 2018-02-06 | 2008-01-15 | No | Not Required | Not Required | Not Required
17INR0068 | Sweetwater 2 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2020-04-30 | WIN | WT | 7.3 |  | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-11-10 | 2017-11-17 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2017-12-20
17INR0069 | Trent repower | SS Completed, FIS Completed, IA | Invenergy | 1338 Eskota 138kV | Nolan | WEST | 2020-03-31 | WIN | WT | 6.4 | COD | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-03-01 | 2018-10-19 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-05-09
17INR0070 | Desert Sky repower | SS Completed, FIS Completed, IA | Invenergy | two LCRA 138kV | Pecos | WEST | 2020-03-31 | WIN | WT | 7.2 | COD | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-02-06 | 2018-10-18 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-09-06
18INR0016 | RTS 2 Wind | SS Completed, FIS Completed, IA | Heart of Texas Wind, LLC | 76006 Bow Wood 345kV | McCulloch | SOUTH | 2020-08-06 | WIN | WT | 179.91 |  | 2015-11-02 | 2015-12-07 | 2015-12-31 | 2019-01-16 | 2017-11-21 | Yes | Not Required | Not Required | Not Required | 2019-07-11 | 2019-07-11 | 2019-07-11
18INR0018 | Peyton Creek Wind | SS Completed, FIS Completed, IA | Eon | 42400 Refuge 345kV | Matagorda | COASTAL | 2020-04-01 | WIN | WT | 151.2 |  | 2015-11-25 | 2015-12-22 | 2016-06-22 | 2017-07-24 | 2018-03-19 | Yes | Not Required | Not Required | Not Required | 2018-03-19 | 2018-09-19 | 2019-04-24 |  |  | 2019-10-28 | 2019-11-14
18INR0027 | Ponwar Solar Farm | SS Completed, FIS Started, No IA | 8minutenergy | tap 138kV 76032 N McCamey - 60361 Santa Rita | Upton | WEST | 2021-06-01 | SOL | PV | 180 |  | 2016-04-06 | 2016-05-27 | 2016-10-27 |  |  | No | Not Required | Not Required | Not Required
18INR0030 | Canyon Wind | SS Completed, FIS Started, IA | TriGlobal | 11319 ScurryCounty 138kV | Scurry | WEST | 2021-03-31 | WIN | WT | 360 | SFS/NtP | 2016-05-09 | 2016-07-22 | 2017-03-02 |  | 2018-09-20 | Yes | Not Required | Not Required | Not Required | 2020-02-07
18INR0031 | Maryneal Windpower | SS Completed, FIS Completed, IA | Maryneal Windpower, LLC | 71050 Bitter Creek 345kV | Nolan | WEST | 2021-02-15 | WIN | WT | 182.4 |  | 2016-05-26 | 2016-07-21 | 2016-07-22 | 2020-01-31 | 2020-01-31 | Yes | Not Required | Not Required | Not Required | 2020-01-31 | 2020-01-31 | 2020-01-31
18INR0033 | Oveja Wind | SS Completed, FIS Completed, IA | Invenergy | 76005 Schneeman Draw 345kV | Irion | WEST | 2020-02-28 | WIN | WT | 300 |  | 2016-07-12 | 2016-09-07 | 2016-10-21 | 2018-07-11 | 2018-07-24 | Yes | Not Required | Not Required | Not Required | 2018-07-30 | 2018-09-28 | 2018-07-30 |  |  | 2019-03-28 | 2019-04-05
18INR0038 | Barrow Ranch | SS Completed, FIS Completed, IA | Engie | 1134 Littman 138kV | Andrews | WEST | 2020-04-15 | WIN | WT | 160 | COD | 2016-10-02 | 2016-12-12 | 2017-06-19 | 2019-07-30 | 2018-06-26 | Yes | Not Required | Not Required | Not Required | 2018-09-04 | 2019-05-01 | 2019-08-01 |  |  | 2020-02-06 | 2020-02-26
18INR0039 | Fowler Ranch | SS Completed, FIS Completed, IA | CED Crane Solar, LLC | tap 138kV 60014 Spudder - 76615 Crane | Crane | WEST | 2020-06-03 | SOL | PV | 152.5 |  | 2016-10-07 | 2016-11-08 | 2016-12-23 | 2019-10-22 | 2018-10-23 | Yes | Not Required | Not Required | Not Required | 2019-03-28 | 2019-10-28 | 2019-10-28
18INR0040 | Soda Lake Solar 1 | SS Completed, FIS Started, IA | Arrington Solar | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | WEST | 2021-05-31 | SOL | PV | 202.59 |  | 2016-10-07 | 2016-11-08 | 2017-02-10 |  | 2018-08-20 | No | Not Required | Not Required | Not Required
18INR0042 | Kaiser Creek Wind | SS Completed, FIS Started, IA | Calpine | Tap 138kV 6275 Abilene East – 6670 Putnam | Callahan | WEST | 2020-12-01 | WIN | WT | 101.52 |  | 2016-10-12 | 2016-12-01 | 2016-10-07 |  | 2019-07-11 | No | Not Required | Not Required | Not Required
18INR0043 | Edmondson Ranch Wind | SS Completed, FIS Completed, IA | Wind Tex | 59903 Bearkat 345kV | Glasscock | WEST | 2021-12-01 | WIN | WT | 293.28 | MW Size COD | 2016-10-26 | 2016-12-22 | 2017-02-01 | 2018-01-30 | 2017-10-04 | Yes | Not Required | Not Required | Not Required | Date Not Available | 2018-09-05 | 2019-09-17
18INR0045 | Misae Solar | SS Completed, FIS Completed, IA | CIP | 60501 Tesla 345kV | Childress | PANHANDLE | 2020-03-13 | SOL | PV | 240.8 | COD | 2016-10-20 | 2017-01-06 | 2016-10-20 | 2019-01-28 | 2018-07-18 | Yes | Not Required | Not Required | Not Required | 2019-01-28 | 2019-01-30 | 2019-01-31 |  |  | 2019-08-21 | 2020-01-16
18INR0050 | Mustang Creek Solar | SS Completed, FIS Completed, IA | Sunchase Power | tap 138kV 5523 ETP - 78104 Ricebird new sub Galow | Jackson | SOUTH | 2021-05-01 | SOL | PV | 150 |  | 2016-11-16 | 2016-12-20 | 2017-03-22 | 2018-10-03 | 2019-01-04 | Yes | Not Required | Not Required | Not Required | 2019-10-04
18INR0053 | Fort Bend Solar | SS Completed, FIS Started, IA | Fort Bend Solar LLC | tap 138kV 44541 Orchard - 44190 E Bernard | Fort Bend | HOUSTON | 2021-05-31 | SOL | PV | 240 |  | 2016-12-19 | 2017-02-15 | 2017-09-08 |  | 2019-06-30 | No | Not Required | Not Required | Not Required
18INR0055 | Long Draw Solar | SS Completed, FIS Completed, IA | ENGIE | 59906 Long Draw 138kV | Borden | WEST | 2020-07-31 | SOL | PV | 226.73 |  | 2016-12-15 | 2017-02-02 | 2017-02-28 | 2019-12-19 | 2018-08-16 | Yes | Not Required | Not Required | Not Required | 2019-02-28 | 2019-12-31 | 2020-01-31
18INR0056 | Hallmark Solar | SS Completed, FIS Started, No IA | Hallmark Solar, LLC | tap 69kV 1824 Neyland - 1826 Cadmil | Hunt | NORTH | 2023-12-01 | SOL | PV | 43 |  | 2016-12-15 | 2017-02-16 | 2017-02-21 |  |  | No | Not Required | Not Required | Not Required
18INR0058 | Texana Solar | SS Completed, FIS Started, No IA | Sunchase Power | tap 138kV 8102 El Campo - 8117 Ganado | Wharton | SOUTH | 2021-03-01 | SOL | PV | 150 |  | 2016-12-23 | 2017-02-14 | 2017-03-22 |  |  | No | Not Required | Not Required | Not Required
18INR0059 | East Raymond Wind | SS Completed, FIS Completed, IA | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2020-06-30 | WIN | WT | 201.6 |  | 2017-01-27 | 2017-03-09 | 2017-02-10 | 2019-11-01 | 2018-09-18 | Yes | Not Required | Not Required | Not Required | 2018-10-17 | 2019-07-16 | 2019-11-01
18INR0060 | Brightside Solar | SS Completed, FIS Started, No IA | Brightside Solar, LLC | tap 69kV 8198 Beeville - 8400 Three River | Bee | SOUTH | 2020-12-15 | SOL | PV | 50 |  | 2017-02-17 | 2017-03-20 | 2017-02-21 |  |  | No | Not Required | Not Required | Not Required
18INR0062 | Wagyu Solar | SS Completed, FIS Completed, IA | Cypress Creek Renewables | tap 138kV 43380 West Columbia - 44010 WA Parish | Brazoria | COASTAL | 2020-06-01 | SOL | PV | 120 |  | 2017-02-22 | 2017-04-03 | 2017-02-22 | 2018-11-01 | 2019-06-03 | Yes | Not Required | Not Required | Not Required | 2019-10-23 | 2019-10-31 | 2019-10-31
18INR0064 | Silver Star repower | SS Completed, FIS Completed, IA | Silver Star I Power Partners, LLC | 1642 Flat Creek 138kV | Eastland | NORTH | 2020-08-10 | WIN | WT | -7.2 |  | 2017-04-05 | 2017-05-08 | 2017-07-06 | 2018-04-26 | 2018-10-16 | Yes | Not Required | Not Required | Not Required | 2019-10-23 | 2019-10-23 | 2019-10-28
18INR0065 | Goodranch Solar | SS Completed, FIS Started, No IA | EDF Renewable Energy | 79600 Vealmoor 138kV OR 79640 Vealmoor 345kV | Borden | WEST | 2021-09-30 | SOL | PV | 200 |  | 2017-06-23 | 2017-08-04 | 2018-04-02 |  |  | No | Not Required | Not Required | Not Required
18INR0067 | Gopher Creek Wind | SS Completed, FIS Completed, IA | Terna Energy | 11306 Dermott 138kV | Borden | WEST | 2020-01-31 | WIN | WT | 158 |  | 2017-07-11 | 2017-08-28 | 2017-07-26 | 2018-01-26 | 2018-01-26 | Yes | Not Required | Not Required | Not Required | Date Not Available | 2018-09-06 | 2018-11-01 |  |  | 2019-05-17 | 2019-05-30
18INR0068 | Loraine Windpark Phase III | SS Completed, FIS Completed, IA | Third Planet Wind Power | 181153 Lonewolf 345kV | Mitchell | WEST | 2021-05-01 | WIN | WT | 100 |  | 2017-08-14 | 2017-10-05 | 2017-10-20 | 2018-04-11 | 2018-04-10 | Yes | Not Required | Not Required | Not Required | 2018-04-12 | 2018-09-12 | 2018-05-01
18INR0069 | Indian Mesa repower | SS Completed, FIS Completed, IA | Nextera | 76019 Indian NWP 138kV | Pecos | WEST | 2020-06-30 | WIN | WT | 0 |  | 2018-05-22 | Date Not Available | 2018-05-22 | 2018-10-03 | 2018-12-04 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2018-11-02
18INR0070 | Blue Summit II | SS Completed, FIS Completed, IA | Nextera | 61001 Jim Treece 345kV | Wilbarger | WEST | 2020-06-30 | WIN | WT | 102 |  | 2017-11-02 | 2017-12-21 | 2017-11-02 | 2018-05-24 | 2018-11-09 | Yes | Not Required | Not Required | Not Required | 2018-05-07 | 2018-09-12 | 2018-08-01 |  |  | 2018-12-18 | 2019-01-10
18INR0072 | Blue Summit repower | SS Completed, FIS Started, No IA | Nextera | 61001 Jim Treece 345kV | Wilbarger | WEST | 2020-09-30 | WIN | WT | 9.9 |  | 2018-01-04 | 2018-01-04 | 2018-01-04 |  |  | No | Not Required | Not Required | Not Required
18INR0073 | Sweetwater 1 repower | SS Completed, FIS Completed, No IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2020-04-30 | WIN | WT | 3 |  | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-12-27 |  | No | Not Required | Not Required | Not Required
18INR0075 | Gulf Wind 1 repower | SS Completed, FIS Completed, IA | Pattern Gulf Wind LLC | 80071 Zorillo 345kV | Kenedy | COASTAL | 2020-06-01 | WIN | WT | 0 |  | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2019-05-29 | 2007-08-28 | No | Not Required | Not Required | Not Required | 2019-07-19 | 2019-07-19 | 2019-07-31
18INR0076 | Wolf Hollow 2 repower | SS Completed, FIS Started, No IA | Exelon | 1877 Mitchell Bend 345kV | Hood | NORTH | 2020-06-01 | GAS | CC | 44 |  | 2018-04-24 | 2018-04-24 | 2018-04-24 |  |  | No | Not Required | Not Required |  | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-19
18INR0077 | Colorado Bend 2 repower | SS Completed, FIS Started, IA | Exelon | 44040 Bailey 345kV | Wharton | SOUTH | 2020-07-01 | GAS | CC | 45 |  | 2018-04-24 | 2018-04-24 | 2018-04-24 |  | 2015-12-17 | No | Not Required | Not Required |  | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-19
18INR0078 | Bobcat Bluff repower | SS Completed, FIS Completed, IA | EDF Renewable Energy | 1475 Windthorst 138kV | Archer | WEST | 2020-02-24 | WIN | WT | 12 | COD | 2018-05-15 | 2018-07-19 | 2018-05-15 | 2018-10-24 | 2018-12-18 | No | Not Required | Not Required | Not Required | 2018-12-18 | 2019-08-16 | Date Not Available |  |  |  | 2018-12-20
18INR0079 | Woodward I repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2020-06-30 | WIN | WT | 0 |  | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2019-01-09 | 2018-12-12 | No | Not Required | Not Required | Not Required | [5 empty] | 2019-11-07 | 2019-11-13
18INR0080 | Woodward 2 repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2020-06-30 | WIN | WT | 0 |  | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-11-27 | 2018-12-18 | No | Not Required | Not Required | Not Required | [6 empty] | 2018-12-19
19INR0001 | Texas Solar Nova | SS Completed, FIS Started, IA | Clearway Energy | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2022-01-31 | SOL | PV | 252.2 |  | 2015-11-17 | 2015-12-30 | 2016-07-06 |  | 2019-07-01 | Yes | Not Required | Not Required | Not Required | 2019-11-08
19INR0002 | Grandfalls Solar | SS Completed, FIS Started, No IA | Nextera | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | WEST | 2021-12-01 | SOL | PV | 350 |  | 2016-05-24 | 2016-06-06 | 2016-05-24 |  |  | No | Not Required | Not Required | Not Required
19INR0006 | Bluebonnet Solar | SS Completed, FIS Started, No IA | One Energy Renewables | tap 138kV 6680 Alamito - 60444 Hayter | Brewster | WEST | 2020-12-31 | SOL | PV | 60.7 |  | 2016-07-18 | 2016-10-07 | 2017-04-05 |  |  | No | Not Required | Not Required | Not Required
19INR0007 | Charbray Solar | SS Completed, FIS Started, No IA | 8minutenergy | 1032 Morgan Creek 138kV | Mitchell | WEST | 2020-10-01 | SOL | PV | 200 |  | 2016-07-26 | 2016-10-07 | 2017-04-07 |  |  | No | Not Required | Not Required | Not Required
19INR0009 | Holstein Solar | SS Completed, FIS Completed, IA | Holstein Solar | 11406 Central Bluff 345kV | Nolan | WEST | 2020-06-01 | SOL | PV | 204.47 |  | 2016-07-26 | 2016-09-13 | 2017-01-31 | 2019-07-16 | 2018-09-15 | Yes | Not Required | Not Required | Not Required | 2019-04-26 | 2019-07-12 | 2019-07-29 |  |  | 2019-12-19 | 2020-01-16
19INR0014 | Formosa Increase | SS Completed, FIS Completed, IA | Formosa Plastics | 8126 Formosa 138kV | Calhoun | COASTAL | 2020-07-01 | GAS | CC | 240 | COD | 2016-09-12 | 2016-11-14 | 2017-06-08 | 2019-02-20 | 2019-04-30 | Yes | 2017-04-17 | 2017-07-12 | 2019-02-22 | 2019-04-30 | 2019-04-30 | 2019-04-30 |  |  | 2020-02-10
19INR0017 | Tri-County Solar | SS Completed, FIS Started, No IA | First Solar | tap 138kV 1027 Odessa - 1107 Monahans2T | Crane | WEST | 2020-12-31 | SOL | PV | 177.75 |  | 2016-10-10 | 2016-11-29 | 2017-02-22 |  |  | No | Not Required | Not Required | Not Required
19INR0020 | SP-Pecos Bend Solar A | SS Completed, FIS Completed, No IA | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | WEST | 2021-02-01 | SOL | PV | 200 |  | 2016-10-26 | 2016-12-07 | 2016-10-31 | 2019-08-15 |  | No | Not Required | Not Required | Not Required
19INR0020b | SP-Pecos Bend Solar B | SS Completed, FIS Completed, No IA | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | WEST | 2021-02-01 | SOL | PV | 180 |  | 2016-10-26 | 2016-12-07 | 2016-10-31 | 2019-08-15 |  | No | Not Required | Not Required | Not Required
19INR0022 | Monte Alto I | SS Completed, FIS Started, IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2021-12-31 | WIN | WT | 223.8 |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  | 2020-02-05 | No | Not Required | Not Required | Not Required
19INR0023 | Monte Alto 2 Wind | SS Completed, FIS Started, No IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2021-12-31 | WIN | WT | 236.9 |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  |  | No | Not Required | Not Required | Not Required
19INR0026 | Holstein 2 Solar | SS Completed, FIS Started, No IA | 8minutenergy | 11406 Central Bluff 345kV | Nolan | WEST | 2021-06-01 | SOL | PV | 100 |  | 2016-12-21 | 2017-02-02 | 2017-02-13 |  |  | No | Not Required | Not Required | Not Required
19INR0028 | Normande Solar Farm | SS Completed, FIS Started, No IA | 8minutenergy | 59900 Long Draw 345kV | Borden | WEST | 2021-06-01 | SOL | PV | 360 |  | 2017-01-30 | 2017-02-22 | 2017-08-24 |  |  | No | Not Required | Not Required | Not Required
19INR0030 | San Bernard Solar | SS Completed, FIS Started, No IA | Sunchase Power | 43012 NEWGLF60T3_8 to 43340 TXGLF__POI_8 60 138kV | Wharton | SOUTH | 2021-06-01 | SOL | PV | 100 |  | 2017-01-26 | 2017-04-12 | 2017-03-22 |  |  | No | Not Required | Not Required | Not Required
19INR0031 | Bestla Solar | SS Completed, FIS Completed, No IA | Longroad Energy | tap 138kV 1147 Cheyenne - 131853 Notrees | Winkler | WEST | 2021-03-19 | SOL | PV | 180 |  | 2017-01-30 | 2017-03-06 | 2017-03-23 | 2019-08-29 |  | No | Not Required | Not Required | Not Required
19INR0033 | Murphy Lake Solar | SS Completed, FIS Completed, IA | S Power | 6904 CombinRC 138kV | Kaufman | NORTH | 2021-03-15 | SOL | PV | 120 |  | 2017-02-06 | 2017-03-03 | 2017-08-10 | 2019-03-28 | 2019-12-27 | No | Not Required | Not Required | Not Required
19INR0034 | Greasewood Solar | SS Completed, FIS Completed, IA | Concho Bluff, LLC | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Pecos | WEST | 2020-11-30 | SOL | PV | 255 |  | 2017-02-22 | 2017-04-17 | 2017-10-10 | 2020-01-31 | 2019-01-25 | Yes | Not Required | Not Required | Not Required | 2020-01-29 | 2020-01-29 | 2020-01-31
19INR0035 | Norton Solar | SS Completed, FIS Started, IA | 8minutenergy | tap 138kV 6325 Chad to 6340 Balg, 10mi from Chad | Runnels | WEST | 2021-06-01 | SOL | PV | 125 |  | 2017-03-06 | 2017-04-20 | 2017-11-08 |  | 2019-06-20 | Yes | Not Required | Not Required | Not Required | 2019-07-12
19INR0036 | Oxbow Solar | SS Completed, FIS Started, No IA | ENGIE Long Draw Solar 2 LLC | 59905 Faraday 345kV | Borden | WEST | 2022-06-30 | SOL | PV | 225 |  | 2017-02-28 | 2017-04-13 | 2017-10-10 |  |  | No | Not Required | Not Required | Not Required
19INR0038 | High Lonesome W | SS Completed, FIS Completed, IA | Enel | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | WEST | 2020-03-20 | WIN | WT | 449.5 | COD | 2017-03-10 | 2017-04-17 | 2017-07-18 | 2019-01-21 | 2018-04-17 | Yes | Not Required | Not Required | Not Required | 2019-02-15 | 2019-02-15 | 2019-02-15 |  |  | 2019-11-12 | 2019-11-26
19INR0041 | Myrtle Solar | SS Completed, FIS Completed, IA | Sunchase Power | 42110 Angleton 138kV | Brazoria | COASTAL | 2021-06-01 | SOL | PV | 240 |  | 2017-03-15 | 2017-04-28 | 2017-05-09 | 2019-03-12 | 2019-11-13 | Yes | Not Required | Not Required | Not Required | 2019-11-30
19INR0042 | Long Point Solar | SS Completed, FIS Completed, IA | SunChase Power | tap 138kV 44010 WAP - 42981 Nash98 | Brazoria | COASTAL | 2021-12-01 | SOL | PV | 100 |  | 2017-03-15 | 2017-04-20 | 2017-11-13 | 2019-03-12 | 2019-10-24 | No | Not Required | Not Required | Not Required
19INR0044 | Lily Solar | SS Completed, FIS Completed, IA | Lily Solar, LLC | tap 138kV 6904 CombinRC - 6908 ScuryRC | Kaufman | NORTH | 2021-06-01 | SOL | PV | 148.05 |  | 2017-03-28 | 2017-04-28 | 2017-05-30 | 2018-09-26 | 2019-03-29 | No | Not Required | Not Required | Not Required
19INR0045 | Rayos Del Sol | SS Completed, FIS Started, IA | Rayos Del Sol Solar Project,LLC | tap 138kV 8554 Mesquite - 80103 Rangerville | Cameron | COASTAL | 2020-10-22 | SOL | PV | 150 |  | 2017-03-28 | 2017-05-22 | 2017-03-28 |  | 2018-11-06 | Yes | Not Required | Not Required | Not Required | 2019-01-23
19INR0048 | Buenos Aires 1 Wind | SS Completed, FIS Started, No IA | Terra-Gen | tap 345kV 8905 N Edinb - 8455 Lon Hill | Hidalgo | SOUTH | 2021-12-31 | WIN | WT | 222.5 |  | 2017-03-30 | 2017-05-03 | 2017-08-28 |  |  | No | Not Required | Not Required | Not Required
19INR0049 | Buenos Aires 2 W | SS Completed, FIS Started, No IA | Terra-Gen | tap 345kV 8905 N Edinb - 8455 Lon Hill | Hidalgo | SOUTH | 2021-12-31 | WIN | WT | 236.9 |  | 2017-03-30 | 2017-05-03 | 2017-08-28 |  |  | No | Not Required | Not Required | Not Required
19INR0051 | Vera Wind | SS Completed, FIS Completed, IA | Longroad Energy | tap 345kV 60500 EdithC - 60700 Gauss | Knox | WEST | 2020-07-01 | WIN | WT | 242.8 |  | 2017-04-04 | 2017-05-18 | 2017-06-13 | 2019-03-06 | 2018-07-10 | Yes | Not Required | Not Required | Not Required | 2019-08-02 | 2019-08-02 | 2019-08-02
19INR0052 | TG East Wind | SS Completed, FIS Started, IA | Northrenew | 60722 Coulomb 345kV | Knox | WEST | 2021-12-15 | WIN | WT | 336 |  | 2017-04-04 | 2017-05-18 | 2017-06-13 |  | 2018-10-22 | Yes | Not Required | Not Required | Not Required
19INR0053 | Hidalgo II Wind | SS Completed, FIS Completed, IA | EDP Renewables | 161705 Mirasole 345kV | Hidalgo | SOUTH | 2020-02-25 | WIN | WT | 51 | COD | 2017-04-05 | 2017-05-19 | 2017-07-12 | 2019-04-30 | 2019-04-25 | Yes | Not Required | Not Required | Not Required | 2019-04-30 | 2019-04-30 | 2019-04-30 |  |  | 2019-11-27 | 2019-12-10
19INR0054 | Monte Cristo 1 W | SS Completed, FIS Started, No IA | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | SOUTH | 2021-12-31 | WIN | WT | 236.9 | Status Change INA-to-PLN | 2017-04-11 | 2017-05-03 | 2017-07-28 |  |  | No | Not Required | Not Required | Not Required
19INR0056 | Chamon 2 | SS Completed, FIS Completed, IA | Castleman Power | 40260 Chamon 138kV | Harris | HOUSTON | 2021-05-01 | GAS | GT | 100 |  | 2017-04-24 | 2017-06-09 | 2017-07-06 | 2019-08-02 | 2019-09-20 | No | 2019-03-18 | Not Required
19INR0057 | Old Bloomington Road | SS Completed, FIS Completed, No IA | Castleman Power | 8143 Dupont 138kV | Victoria | SOUTH | 2021-05-01 | GAS | GT | 100 |  | 2017-04-18 | 2017-05-22 | 2017-11-29 | 2019-03-06 |  | No
19INR0070 | Trevino Solar | SS Completed, FIS Started, No IA | S Power | 78015 Rosita 138kV | Maverick | SOUTH | 2021-12-15 | SOL | PV | 216 |  | 2017-04-19 | 2017-06-02 | 2017-11-30 |  |  | No | Not Required | Not Required | Not Required
19INR0073 | Shakes Solar | SS Completed, FIS Completed, IA | Cypress Creek Renewables | 8283 Asherton 138kV | Zavala | SOUTH | 2021-02-12 | SOL | PV | 206 |  | 2017-05-03 | 2017-06-15 | 2017-05-03 | 2019-09-19 | 2018-10-26 | Yes | Not Required | Not Required | Not Required | 2019-03-04
19INR0075 | Horseshoe Bend Solar | SS Completed, FIS Started, No IA | Clenera | 1444 Brown 345kV | Coleman | WEST | 2020-12-31 | SOL | PV | 300 |  | 2017-06-23 | 2017-08-07 | 2018-02-09 |  |  | No | Not Required | Not Required | Not Required
19INR0080 | Whitehorse Wind | SS Completed, FIS Completed, IA | Clearway Energy | 68001 Clayton 345kV | Fisher | WEST | 2020-03-09 | WIN | WT | 418.9 |  | 2017-06-23 | 2017-08-07 | 2018-02-16 | 2019-01-22 | 2018-12-05 | Yes | Not Required | Not Required | Not Required | 2019-03-12 | 2019-04-02 | 2019-05-01 |  |  | 2019-12-12 | 2019-12-27
19INR0081 | Anson Solar | SS Completed, FIS Started, IA | Anson Solar Center, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2020-12-31 | SOL | PV | 201.53 |  | 2017-06-23 | 2017-08-07 | 2018-02-15 |  | 2019-06-05 | Yes | Not Required | Not Required | Not Required | 2019-11-18
19INR0083 | Oberon Solar | SS Completed, FIS Completed, IA | OBERON SOLAR IA LLC | tap 138kV 1292 Ectorharp - 1013 Wolf | Ector | WEST | 2020-04-29 | SOL | PV | 180 |  | 2017-05-31 | 2017-07-13 | 2017-05-31 | 2018-05-18 | 2018-10-11 | Yes | Not Required | Not Required | Not Required | 2018-11-28 | 2019-01-22 | 2019-01-22
19INR0085 | Blue Jay Solar | SS Completed, FIS Started, No IA | Open Road Renewables | 4 Iola 138kV | Grimes | NORTH | 2020-12-15 | SOL | PV | 210 |  | 2017-05-30 | 2017-08-11 | 2018-02-15 |  |  | No | Not Required | Not Required | Not Required
19INR0088 | Aragorn Solar | SS Completed, FIS Completed, IA | Intersect Power | tap 138kV 71097 LCulberson - 7387 Kunitz (71097 LCRA Culberson 138kV) | Culberson | WEST | 2021-06-30 | SOL | PV | 187.2 |  | 2017-05-30 | 2017-07-21 | 2017-08-08 | 2019-12-13 | 2018-05-31 | No | Not Required | Not Required | Not Required
19INR0091 | Phoenix Solar | SS Completed, FIS Completed, IA | G.S.E. ONE LLC | 1808 Bonham 138kV | Fannin | NORTH | 2021-04-23 | SOL | PV | 82.3 |  | 2017-06-23 | 2017-08-23 | 2017-08-09 | 2019-10-07 | 2019-10-22 | Yes | Not Required | Not Required | Not Required
19INR0092 | Prospero Solar | SS Completed, FIS Completed, IA | Longroad Energy | 79650 Clearfork 345kV + 10 mile gen-tie | Andrews | WEST | 2020-06-30 | SOL | PV | 300 |  | 2017-06-23 | 2017-08-07 | 2017-07-11 | 2019-07-31 | 2018-04-20 | Yes | Not Required | Not Required | Not Required | 2019-07-31 | 2019-07-31 | 2019-07-31
19INR0093 | Solemio | SS Completed, FIS Started, No IA | SOLEMIO LLC | tap 138kV 1698 Sulphur Springs - 1814 Sulspg | Hopkins | NORTH | 2021-04-27 | SOL | PV | 81.4 |  | 2017-06-23 | 2017-08-23 | 2017-08-09 |  |  | No | Not Required | Not Required | Not Required
19INR0096 | Shamrock Wind | SS Completed, FIS Started, No IA | Eon | 76005 Schneeman Draw 345kV | Crockett | WEST | 2021-12-15 | WIN | WT | 201.6 |  | 2017-07-28 | 2017-09-13 | 2017-10-04 |  |  | No | Not Required | Not Required | Not Required
19INR0097 | Shamrock Wind II | SS Completed, FIS Started, No IA | Eon | 76005 Schneeman Draw 345kV | Crockett | WEST | 2021-12-15 | WIN | WT | 201.6 |  | 2017-07-28 | 2017-09-13 | 2017-10-02 |  |  | No | Not Required | Not Required | Not Required
19INR0098 | Pease River Wind | SS Completed, FIS Started, No IA | Eon | 60500 Edith Clarke 345kV | Hardeman | WEST | 2021-12-30 | WIN | WT | 301.4 |  | 2017-07-11 | 2017-08-28 | 2017-07-14 |  |  | No | Not Required | Not Required | Not Required
19INR0099a | Kontiki 1 Wind (ERIK) | SS Completed, FIS Started, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2021-06-30 | WIN | WT | 255.3 |  | 2017-06-22 | 2017-08-04 | 2017-09-28 |  | 2018-05-07 | Yes | Not Required | Not Required | Not Required | 2018-05-07
19INR0099b | Kontiki 2 Wind (ERNEST) | SS Completed, FIS Started, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2022-06-30 | WIN | WT | 255.3 |  | 2017-06-22 | 2017-08-04 | 2017-09-28 |  | 2018-05-07 | Yes | Not Required | Not Required | Not Required | 2018-05-07
19INR0100 | Prairie Hill Wind | SS Completed, FIS Started, IA | Prairie Hill LLC | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | McLennan | NORTH | 2020-09-01 | WIN | WT | 300 |  | 2017-06-19 | 2017-08-11 | 2017-06-19 |  | 2018-09-17 | Yes | Not Required | Not Required | Not Required | 2018-11-27
19INR0101 | Tehuacana Wind | SS Completed, FIS Started, No IA | Infinity Renewables | 46020 Limestone 345kV + 34mi gentie | Limestone | NORTH | 2021-12-01 | WIN | WT | 600 |  | 2017-06-19 | 2017-08-11 | 2017-06-19 |  |  | No | Not Required | Not Required | Not Required
19INR0102 | Queen Solar Phase I | SS Completed, FIS Completed, IA | Roadrunner Solar Project, LLC | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | WEST | 2020-03-06 | SOL | PV | 200 | COD | 2017-07-11 | 2017-08-28 | 2018-02-26 | 2019-05-10 | 2018-09-26 | Yes | Not Required | Not Required | Not Required | 2019-04-01 | 2019-04-30 |  |  |  | 2019-12-05 | 2019-12-12
19INR0103 | Rodeo Solar | SS Completed, FIS Started, IA | Core Solar SPV I, LLC | tap 138kV 1134 Littman - 1135 Gasland | Andrews | WEST | 2021-05-15 | SOL | PV | 205 |  | 2017-06-29 | 2017-08-04 | 2018-02-19 |  | 2019-08-20 | No | Not Required | Not Required | Not Required
19INR0110 | Angelina Solar | SS Completed, FIS Started, No IA | EDP Renewables | 3349 TMPLinla 138kV | Angelina | NORTH | 2021-10-31 | SOL | PV | 178.89 |  | 2017-07-26 | 2017-09-15 | 2018-03-15 |  |  | No | Not Required | Not Required | Not Required
19INR0111 | Tom Green Solar | SS Completed, FIS Started, No IA | EDP Renewables | tap 138kV 6480 SAPS - 60423 Treadwell | Tom Green | WEST | 2021-10-31 | SOL | PV | 150 |  | 2017-07-26 | 2017-09-13 | 2018-03-15 |  |  | No | Not Required | Not Required | Not Required
19INR0112 | Cranel Wind | SS Completed, FIS Completed, IA | Eon | tap 345kV 8164 Coleto - 8455 Lon Hill | Refugio | COASTAL | 2020-05-15 | WIN | WT | 220 |  | 2017-09-12 | 2017-11-01 | 2017-11-30 | 2018-08-30 | 2018-10-12 | Yes | Not Required | Not Required | Not Required | 2018-10-12 | 2019-02-27 | 2019-03-26
19INR0113 | County Line Solar | SS Completed, FIS Started, No IA | S Power | 60385 Solstice 138kV | Pecos | WEST | 2021-12-15 | SOL | PV | 250 |  | 2017-08-15 | 2017-11-01 | 2017-08-15 |  |  | No | Not Required | Not Required | Not Required
19INR0114 | Rambler Solar | SS Completed, FIS Completed, IA | Rambler Solar | 76009 Twin Buttes 345kV | Tom Green | WEST | 2020-05-31 | SOL | PV | 200 |  | 2017-08-09 | 2017-10-10 | 2018-01-05 | 2019-08-02 | 2018-10-11 | Yes | Not Required | Not Required | Not Required | 2019-05-07 | 2019-07-25 | 2019-07-31 |  |  | 2020-01-31
19INR0115 | Blackwater Draw Solar | SS Completed, FIS Started, No IA | Core Solar | tap 138kV 1170 Paul Davis tap - 18880 Jim Payne | Dawson | WEST | 2021-12-31 | SOL | PV | 151.9 |  | 2017-07-28 | 2017-10-09 | 2018-04-12 |  |  | No | Not Required | Not Required | Not Required
19INR0117 | Roadrunner Crossing Wind 1 | SS Completed, FIS Started, No IA | Eon | tap 345kV 68005 WShack - 68050 Romney | Eastland | NORTH | 2021-06-30 | WIN | WT | 200.2 |  | 2017-09-08 | 2017-11-07 | 2018-03-05 |  |  | No | Not Required | Not Required | Not Required
19INR0120 | Sherbino II Wind repower | SS Completed, FIS Completed, IA | Sherbino II Wind Farm LLC | 131454 Keo_3 138kV | Pecos | WEST | 2020-08-10 | WIN | WT | -18 |  | 2017-08-18 | 2017-09-28 | 2017-09-21 | 2018-12-04 | 2008-02-28 | Yes | Not Required | Not Required | Not Required | 2019-10-28 | 2019-10-28 | 2019-10-28
19INR0121 | Galloway Solar | SS Completed, FIS Started, IA | 8minutenergy | tap 345kV 76009 Twin Buttes - 1444 Brown | Concho | WEST | 2021-06-01 | SOL | PV | 250 |  | 2017-08-25 | 2017-10-02 | 2017-08-25 |  | 2019-12-20 | No | Not Required | Not Required | Not Required
19INR0123 | OLD JACKSON SOLAR | SS Completed, FIS Started, No IA | OLD JACKSON SOLAR LLC | tap 138kV 3175 Canton - 3173 Expmtr | Van Zandt | NORTH | 2021-04-23 | SOL | PV | 129.3 |  | 2017-09-12 | 2017-11-13 | 2017-12-05 |  |  | No | Not Required | Not Required | Not Required
19INR0128 | White Mesa Wind | SS Completed, FIS Completed, IA | Apex Clean | 76005 Schneeman Draw 345kV | Crockett | WEST | 2020-12-31 | WIN | WT | 500 |  | 2017-09-08 | 2017-11-20 | 2018-01-29 | 2019-04-24 | 2018-12-19 | Yes | Not Required | Not Required | Not Required | 2019-06-03
19INR0129 | Flatland Solar | SS Completed, FIS Started, No IA | Sunfinity Renewables | tap 138kV 1032 Morgan - 1064 Sun | Scurry | WEST | 2020-07-15 | SOL | PV | 147 |  | 2017-10-20 | 2017-12-13 | 2018-06-13 |  |  | No | Not Required | Not Required | Not Required
19INR0131 | Cutlass Solar | SS Completed, FIS Started, No IA | Cutlass Solar LLC | tap 345kV 44000 WAP - 44200 Hillje, probably | Fort Bend | HOUSTON | 2021-05-31 | SOL | PV | 300 |  | 2017-09-21 | 2017-11-20 | 2018-05-15 |  |  | No | Not Required | Not Required | Not Required
19INR0132 | La Joya I Wind | SS Completed, FIS Completed, No IA | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | SOUTH | 2021-12-31 | WIN | WT | 236.9 |  | 2017-09-22 | 2017-11-13 | 2017-09-22 | 2019-10-24 |  | No | Not Required | Not Required | Not Required
19INR0134 | Cottonwood Bayou | SS Completed, FIS Completed, IA | Sunchase Power | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2021-06-01 | SOL | PV | 150 |  | 2017-09-22 | 2017-11-17 | 2018-02-15 | 2019-03-25 | 2019-11-13 | No | Not Required | Not Required | Not Required
19INR0135 | Hill Solar | SS Completed, FIS Started, No IA | Sunchase Power | tap 69kV 3523 Hillsboro - 3532 Itasca | Hill | NORTH | 2021-05-01 | SOL | PV | 80 |  | 2017-09-22 | 2017-11-17 | 2018-05-10 |  |  | No | Not Required | Not Required | Not Required
19INR0138 | Buffalo Gap 4 | SS Completed, FIS Started, No IA | AES | 66216 Bluff Creek 138kV | Nolan | WEST | 2020-09-01 | WIN | WT | 175 |  | 2017-10-06 | 2017-11-20 | 2017-10-06 |  |  | No | Not Required | Not Required | Not Required
19INR0142 | Bacon Switch Solar | SS Completed, FIS Started, No IA | SunChase Power | tap 345kV 6101 Riley - 1425 Fisher | Wichita | WEST | 2021-06-01 | SOL | PV | 180 |  | 2017-10-11 | 2017-11-08 | 2018-02-15 |  |  | No | Not Required | Not Required | Not Required
19INR0145 | Aquilla Lake Wind | SS Completed, FIS Completed, No IA | Nextera | 68090 Sam Switch 345 kV | Hill | NORTH | 2021-09-30 | WIN | WT | 202 | Proj Name | 2018-07-18 | 2018-09-20 | 2018-07-18 | 2020-01-17 |  | No | Not Required | Not Required | Not Required
19INR0147 | March Road Solar | SS Completed, FIS Started, No IA | Eon | tap 345kV 76009 TwinB - 6444 Red Creek | Tom Green | WEST | 2021-12-15 | SOL | PV | 200 |  | 2017-11-13 | 2018-01-08 | 2017-12-01 |  |  | No | Not Required | Not Required | Not Required
19INR0150 | Millhouse Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 69kV 8500 Alice - 8889 Stadium | Jim Wells | SOUTH | 2020-12-31 | SOL | PV | 75 |  | 2017-11-13 | 2018-02-23 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
19INR0151 | Impact Solar | SS Completed, FIS Completed, IA | IMPACT SOLAR 1 LLC | tap 345kV 1695 Moses - 1692 Paris | Lamar | NORTH | 2020-12-15 | SOL | PV | 198.55 |  | 2017-12-18 | 2018-02-01 | 2018-05-04 | 2019-09-19 | 2019-07-02 | Yes | Not Required | Not Required | Not Required | 2019-09-12 | 2019-10-28 | 2019-10-28
19INR0155 | Morrow Lake Solar | SS Completed, FIS Started, IA | Sunchase Power | Pearsall 138kV (5895) Substation | Frio | SOUTH | 2021-04-01 | SOL | PV | 204 | MW Size | 2017-12-05 | 2018-01-15 | 2018-02-15 |  | 2019-08-29 | Yes | Not Required | Not Required | Not Required | 2019-11-18
19INR0156 | Aviator Wind | SS Completed, FIS Completed, IA | Apex Clean | 76090 Divide 345kV | Coke | WEST | 2020-10-01 | WIN | WT | 525 |  | 2017-12-06 | 2018-02-23 | 2018-01-25 | 2019-11-01 | 2019-02-14 | Yes | Not Required | Not Required | Not Required | 2019-10-15 | 2019-10-24 | 2019-11-01
19INR0159 | Reiher Solar | SS Completed, FIS Started, No IA | EnergieKontor US Texas SP 7 LLC | 76597 Robb Sw 138kV | Upton | WEST | 2021-05-31 | SOL | PV | 120 |  | 2018-01-29 | 2018-03-27 | 2018-08-14 |  |  | No | Not Required | Not Required | Not Required
19INR0161 | Pierce Wind | SS Completed, FIS Started, No IA | Seventus | 345kV ROW between Hillje & WAP or 345kV Bailey to Hillje | Wharton | SOUTH | 2021-12-31 | WIN | WT | 300 |  | 2018-01-03 | 2018-02-16 | 2018-01-03 |  |  | No | Not Required | Not Required | Not Required
19INR0163 | Sage Draw Wind | SS Completed, FIS Completed, IA | Lincoln Clean | 79641 Farmland 345kV | Lynn | WEST | 2020-03-31 | WIN | WT | 338 |  | 2016-03-14 | 2016-03-23 | 2016-04-22 | 2019-04-17 | 2018-01-03 | Yes | Not Required | Not Required | Not Required | 2019-03-22 | 2019-04-30 | 2019-04-30 |  |  | 2019-12-03 | 2019-12-12
19INR0165 | Barranca Wind | SS Completed, FIS Started, No IA | Lincoln Clean Energy, LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2022-01-30 | WIN | WT | 201.6 |  | 2018-05-09 | 2018-05-25 | 2018-02-28 |  |  | No | Not Required | Not Required | Not Required
19INR0166 | Loma Pinta II | SS Completed, FIS Started, No IA | Enerverse | 5705 Fowlerton 138kV | La Salle | SOUTH | 2020-05-31 | WIN | WT | 201.6 |  | 2018-02-28 | 2018-04-16 | 2018-02-28 |  |  | No | Not Required | Not Required | Not Required
19INR0167 | Gold Creek Solar | SS Completed, FIS Started, No IA | S Power | 1163 Lamesa 138kV | Dawson | WEST | 2021-12-15 | SOL | PV | 140 |  | 2018-05-04 | 2018-06-28 | 2018-05-04 |  |  | No | Not Required | Not Required | Not Required
19INR0169 | Sun Valley | SS Completed, FIS Completed, No IA | Alpin Sun | tap 345kV 68090 Sam Sw - 3405 Tradinghouse | Hill | NORTH | 2021-12-01 | SOL | PV | 250 |  | 2018-03-02 | 2018-04-17 | 2018-07-19 | 2019-12-12 |  | No | Not Required | Not Required | Not Required
19INR0171 | Concho Valley Solar | SS Completed, FIS Started, No IA | Merit SI | tap 138kV 6480 SAPOWER - 6490 Santiago | Tom Green | WEST | 2021-11-01 | SOL | PV | 150 |  | 2018-03-02 | 2018-04-13 | 2018-03-02 |  |  | No | Not Required | Not Required | Not Required
19INR0172 | Dillon Gulch Wind | SS Completed, FIS Started, No IA | AES | tap 345kV 11420 Sweetwater East - 11406 Central Bluff | Nolan | WEST | 2020-12-15 | WIN | WT | 175 | Proj Name | 2018-04-12 | 2018-06-13 | 2018-04-12 |  |  | No | Not Required | Not Required | Not Required
19INR0173 | Magnet Wind | SS Completed, FIS Started, No IA | Seventus | 43190 South Lane City 138kV | Wharton | SOUTH | 2021-12-31 | WIN | WT | 125 |  | 2018-04-13 | 2018-06-12 | 2018-04-13 |  |  | No | Not Required | Not Required | Not Required
19INR0174 | Elbow Creek repower | SS Completed, FIS Completed, IA | NRG | 1058 Longshore 345kV | Howard | WEST | 2019-10-15 | WIN | WT | 0 |  | 2018-05-04 | 2018-05-18 | 2018-07-19 | 2018-09-17 | 2007-11-30 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-27
19INR0175 | Shifting Gale | SS Completed, FIS Started, No IA | SEAWAY WIND ENERGY LLC | 79501 Ogallala 345kV | Castro | PANHANDLE | 2021-10-31 | WIN | WT | 289 |  | 2018-04-26 | 2018-06-12 | 2018-12-06 |  |  | No | Not Required | Not Required | Not Required
19INR0176 | Roughneck Storage | SS Completed, FIS Completed, No IA | Glidepath | 43380 W Columbia 138kV | Brazoria | COASTAL | 2021-07-01 | OTH | BA | 50 |  | 2018-05-09 | 2018-07-13 | 2018-11-07 | 2019-11-04 |  | No | Not Required | Not Required | Not Required
19INR0177 | Shanghai Wind | SS Completed, FIS Started, No IA | Seventus | 8104 Lane City PM 138kV | Wharton | SOUTH | 2021-12-31 | WIN | WT | 153.3 |  | 2018-05-09 | 2018-06-21 | 2018-05-09 |  |  | No | Not Required | Not Required | Not Required
19INR0179 | Barranca Wind II | SS Completed, FIS Started, No IA | Lincoln Clean Energy, LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2021-12-31 | WIN | WT | 201.6 |  | 2018-05-15 | 2018-06-01 | 2018-05-15 |  |  | No | Not Required | Not Required | Not Required
19INR0180 | Friendswood II | SS Completed, FIS Completed, IA | Quantum | 47170 HOC 138kV | Brazoria | COASTAL | 2021-02-21 | GAS | GT | 117 |  | 2018-05-17 | 2018-07-11 | 2018-05-17 | 2019-03-29 | 2019-09-09 | No | 2018-08-10 | Not Required | 2019-05-21
19INR0182 | Blue Summit Wind III | SS Completed, FIS Completed, IA | Nextera | 61001 Jim Treece 345kV | Wilbarger | WEST | 2020-06-30 | WIN | WT | 200 |  | 2018-06-06 | 2018-07-24 | 2018-06-06 | 2019-03-20 | 2019-04-09 | Yes | Not Required | Not Required | Not Required | 2019-04-09 | 2019-04-09 | 2019-04-09 |  |  | 2019-11-14 | 2019-12-11
19INR0184 | Oxy Solar | SS Completed, FIS Completed, IA | Oxy Renewable Energy | 11256 Goldsmith 138kV | Ector | WEST | 2020-05-15 | SOL | PV | 16.2 |  | 2018-07-18 | 2018-09-20 | 2018-08-07 | 2019-01-30 | 2019-01-30 | Yes | Not Required | Not Required | Not Required | 2019-01-30 | 2019-01-30 | 2019-01-31 |  |  | 2019-07-31 | 2019-07-31
19INR0185 | Lapetus Solar | SS Completed, FIS Completed, IA | Lapetus Energy Project, LLC | tap 138kV 1284 Shafter Lake - 1272 Fullerton | Andrews | WEST | 2020-03-01 | SOL | PV | 100 | COD | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2019-03-22 | 2018-12-21 | Yes | Not Required | Not Required | Not Required | 2019-02-27 | 2019-04-29 | 2019-04-29 |  |  | 2019-11-19 | 2019-12-06
19INR0187 | John Paul Jones | SS Completed, FIS Completed, No IA | Dflex Power | 46510 Tomball 138kV | Harris | HOUSTON | 2020-12-31 | GAS | GT | 18.6 |  | 2018-08-02 | 2018-09-28 | 2018-08-02 | 2019-10-03 |  | No | 2019-02-14
19INR0188 | Millhouse Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 69kV 8500 Alice - 8889 Stadium | Jim Wells | SOUTH | 2020-12-31 | OTH | BA | 38 |  | 2017-11-13 | 2018-02-23 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
19INR0189 | SP TX-12B Phase III | SS Completed, FIS Started, No IA | ConEd Development | 76040 Castillo 138kV | Upton | WEST | 2021-05-24 | SOL | PV | 40 |  | 2018-09-12 | 2018-10-03 |  |  |  | No | Not Required | Not Required | Not Required
19INR0203 | Angelo Solar | SS Completed, FIS Started, No IA | ANGELO SOLAR LLC | 76009 Twin Buttes 345kV | Tom Green | WEST | 2021-03-15 | SOL | PV | 195 |  | 2018-11-20 | 2019-02-05 | 2019-01-21 |  |  | No |  |  | Not Required
20INR0011 | Ranchero Wind | SS Completed, FIS Completed, IA | Scout Clean Energy | 7053 Noelke 345kV | Crockett | WEST | 2020-03-31 | WIN | WT | 300 | COD | 2017-06-23 | 2017-08-07 | 2017-07-03 | 2018-11-01 | 2018-05-02 | Yes | Not Required | Not Required | Not Required | 2018-08-03 | 2018-10-31 | 2018-11-01 |  |  | 2019-07-31 | 2019-09-04
20INR0012 | Lueders Solar | SS Completed, FIS Started, No IA | Innovative Solar | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | WEST | 2022-05-15 | SOL | PV | 40 |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0013 | Basalt Solar | SS Completed, FIS Started, No IA | Innovative Solar | tap 138kV 8234 Uvalde - 8241 Razorback | Uvalde | SOUTH | 2022-05-15 | SOL | PV | 20 |  | 2017-07-11 | 2017-09-01 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0014 | Obsidian Solar | SS Completed, FIS Started, No IA | Innovative Solar | 6131 Padr 69kV | Cottle | WEST | 2022-05-15 | SOL | PV | 60 |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0015 | Citrine Solar | SS Completed, FIS Started, No IA | Innovative Solar | Tap 138kV 6135 Paducah Clare - 6117 E Munday | Cottle | WEST | 2022-05-15 | SOL | PV | 45 |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0016 | Opal Solar | SS Completed, FIS Started, No IA | Innovative Solar | tap 345kV 60501 Tesla - 60500 Edith Clark | Hardeman | WEST | 2022-05-15 | SOL | PV | 45 |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0019 | Trinity Hills Wind repower | SS Completed, FIS Completed, IA | Trinity Hills Wind Farm LLC | 150751 & 150752 Trinity Hills 34.5kV | Young | WEST | 2020-08-10 | WIN | WT | -27 |  | 2017-07-20 | 2017-09-08 | 2017-09-21 | 2018-08-02 | 2018-10-17 | No | Not Required | Not Required | Not Required | 2019-10-29 | 2019-10-29 | 2019-10-29
20INR0022 | Sandine Solar | SS Completed, FIS Started, No IA | Innovative Solar | tap 138kV 6135 Paducah - 6320 Tardis | Cottle | WEST | 2022-05-15 | SOL | PV | 30 |  | 2017-08-10 | 2017-10-22 | 2017-10-24 |  |  | No | Not Required | Not Required | Not Required
20INR0026 | Longbow Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 42870 Liverpool 138kV | Brazoria | COASTAL | 2021-06-11 | SOL | PV | 70 |  | 2017-08-16 | 2017-10-13 | 2017-08-16 |  |  | No | Not Required | Not Required | Not Required
20INR0029 | Lutum | SS Completed, FIS Started, No IA | EDF Renewable Energy | tap 345kV 6101 Riley - 1730 W Krum | Clay | WEST | 2021-10-01 | WIN | WT | 242 |  | 2017-09-12 | 2017-11-07 | 2018-05-08 |  |  | No | Not Required | Not Required | Not Required
20INR0032 | IP Titan | SS Completed, FIS Completed, IA | Intersect Power | 71097 LCRA Culberson 138kV | Culberson | WEST | 2021-06-30 | SOL | PV | 270 |  | 2017-10-12 | 2017-12-08 | 2018-01-19 | 2019-12-13 | 2019-02-04 | No | Not Required | Not Required | Not Required
20INR0033 | WILDWIND | SS Completed, FIS Completed, IA | Wildcat Creek | tap 345kV 1730 KrumW - 2373 Anna | Cooke | NORTH | 2020-12-15 | WIN | WT | 180.08 | Proj Name | 2017-10-18 | 2017-12-11 | 2018-06-14 | 2019-11-25 | 2020-02-21 | No | Not Required | Not Required | Not Required
20INR0035 | Angus Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 177 Bosque - 181 Cayote | Bosque | NORTH | 2020-08-31 | SOL | PV | 113 |  | 2017-11-13 | 2018-01-02 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
20INR0037 | Coniglio Solar | SS Completed, FIS Completed, No IA | Belltown Power | 1809 Boistret 138kV | Fannin | NORTH | 2020-12-11 | SOL | PV | 135 |  | 2017-11-28 | 2018-01-23 | 2018-05-25 | 2019-05-15 |  | Yes | Not Required | Not Required | Not Required
20INR0038 | Red Mud Creek | SS Completed, FIS Started, No IA | Eon | tap 345kV 11318 Scurry - 59905 Faraday or 11318-59900 Long Draw | Borden | WEST | 2022-12-15 | WIN | WT | 201 |  | 2017-11-29 | 2018-02-05 | 2018-03-15 |  |  | No | Not Required | Not Required | Not Required
20INR0040 | Montgomery Ranch Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 60500 EdithC - 60700 Gauss | Foard | WEST | 2022-12-15 | WIN | WT | 200.2 | COD | 2017-12-18 | 2018-02-06 | 2018-06-20 |  |  | No | Not Required | Not Required | Not Required
20INR0042 | Chalupa Wind | SS Completed, FIS Completed, IA | Acciona | 8640 Kelvin 138kV | Cameron | COASTAL | 2020-12-21 | WIN | WT | 174 |  | 2017-12-22 | 2018-02-06 | 2018-01-24 | 2019-08-01 | 2018-09-28 | Yes | Not Required | Not Required | Not Required | 2018-10-18 | 2018-12-18 | 2019-10-30
20INR0043 | Gulf Wind 2 | SS Completed, FIS Started, No IA | TEXAS GULF WIND 2 LLC | 80071 Zorillo 345kV | Kenedy | COASTAL | 2020-06-01 | WIN | WT | 226.5 |  | 2018-01-04 | 2018-02-20 | 2018-02-14 |  |  | No | Not Required | Not Required | Not Required
20INR0044 | French Goldston Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV 1430 Graham - 1445 Burwick Switch | Young | WEST | 2022-02-01 | SOL | PV | 144 | COD | 2018-01-03 | 2018-03-12 | 2018-09-19 |  |  | No | Not Required | Not Required | Not Required
20INR0045 | Maverick Creek I W | SS Completed, FIS Completed, IA | Maverick Creek Wind, LLC | 7077 Amos Cr 345kV | Concho | WEST | 2020-09-01 | WIN | WT | 373.2 | Proj Name | 2018-01-05 | 2018-02-20 | 2018-03-05 | 2019-04-03 | 2018-07-30 | Yes | Not Required | Not Required | Not Required | 2019-10-31 | 2019-10-31 | 2019-10-31
20INR0046 | Maverick Creek II W | SS Completed, FIS Started, IA | Maverick Creek Wind, LLC | 7077 Amos Cr 345kV | Concho | WEST | 2020-11-11 | WIN | WT | 118.8 | Proj Name | 2018-01-05 | 2018-02-20 | 2018-03-05 |  | 2018-07-30 | Yes | Not Required | Not Required | Not Required
20INR0047 | Siete | SS Completed, FIS Started, No IA | Apex Clean | 80219 Lobo 345kV | Webb | SOUTH | 2021-07-31 | WIN | WT | 375.06 |  | 2018-10-23 | 2018-12-11 | 2019-06-12 |  |  | No | Not Required | Not Required | Not Required
20INR0048 | Century Oak Wind | SS Completed, FIS Started, No IA | Engie | tap 138kV 6670 Putnam - 6317 Cisco | Callahan | WEST | 2021-12-01 | WIN | WT | 126 |  | 2018-01-29 | 2018-02-28 | 2018-05-17 |  |  | No | Not Required | Not Required | Not Required
20INR0050 | Castro Solar | SS Completed, FIS Started, No IA | Oaktree Development | 23912 Ogallala 345kV | Castro | PANHANDLE | 2021-12-15 | SOL | PV | 222.95 |  | 2018-02-08 | 2018-04-09 | 2018-05-15 |  |  | No | Not Required | Not Required | Not Required
20INR0052 | Griffin Trail Wind | SS Completed, FIS Started, IA | Innergex | tap 345kV 60500 EdithC - 60702 Gauss | Knox | WEST | 2020-09-30 | WIN | WT | 201.6 |  | 2018-03-05 | 2018-05-04 | 2018-11-07 |  | 2019-03-04 | No | Not Required | Not Required | Not Required
20INR0053 | Bravepost Solar | SS Completed, FIS Started, IA | Recurrent Energy | 6444 Red Creek 345kV | Tom Green | WEST | 2021-06-01 | SOL | PV | 200 |  | 2018-02-22 | 2018-04-13 | 2018-06-07 |  | 2019-10-30 | Yes | Not Required | Not Required | Not Required | 2019-11-18
20INR0054 | Taygete Solar | SS Completed, FIS Completed, IA | 7x Energy | 60393 Pig Creek 138kV | Pecos | WEST | 2020-12-01 | SOL | PV | 255.07 |  | 2018-02-26 | 2018-05-04 | 2018-02-26 | 2019-10-29 | 2018-10-26 | Yes | Not Required | Not Required | Not Required | 2019-02-05 | 2019-10-29 | 2019-10-29
20INR0061 | Pflugerville 2 Solar | SS Completed, FIS Started, No IA | RRE Power LLC 1 | tap 138kV 7336 Gillie - 3650 Elgin | Travis | SOUTH | 2021-12-16 | SOL | PV | 120 |  | 2018-03-05 | 2018-04-19 | 2018-10-10 |  |  | No | Not Required | Not Required | Not Required
20INR0068 | Blackjack Creek Wind | SS Completed, FIS Started, IA | Eon | tap 345kV 8164 Coleto - 8455 Lon Hill | Bee | SOUTH | 2021-12-15 | WIN | WT | 239.8 |  | 2018-04-02 | 2018-05-18 | 2018-11-07 |  | 2019-10-24 | Yes | Not Required | Not Required | Not Required | 2019-11-24
20INR0069 | Danish Fields Solar | SS Completed, FIS Completed, IA | Sunchase Power | 44200 Hillje 345kV | Wharton | SOUTH | 2021-06-01 | SOL | PV | 200 |  | 2018-04-12 | 2018-06-05 | 2018-08-21 | 2020-01-21 | 2020-02-24 | No | Not Required | Not Required | Not Required
20INR0070 | Monte Bueno | SS Completed, FIS Started, No IA | Terra-Gen | tap 138kV 8392 Bates - 8394 Liston | Hidalgo | SOUTH | 2022-12-31 | WIN | WT | 129.2 |  | 2018-04-12 | 2018-05-30 | 2018-10-10 |  |  | No | Not Required | Not Required | Not Required
20INR0071 | Havana Wind | SS Completed, FIS Started, No IA | Terra-Gen | tap 138kV 8355 Goodwin - 8798 La Grulla | Hidalgo | SOUTH | 2022-12-31 | WIN | WT | 129.2 |  | 2018-04-12 | 2018-06-01 | 2018-10-10 |  |  | No | Not Required | Not Required | Not Required
20INR0074 | Pitts Dudik Solar | SS Completed, FIS Completed, No IA | Belltown Power | tap 138kV Hillsoboro 3522- Navarro 3478 | Hill | NORTH | 2020-09-01 | SOL | PV | 50 |  | 2018-04-12 | 2018-05-18 | 2018-05-25 | 2020-02-25 |  | No | Not Required | Not Required | Not Required
20INR0075 | Howle Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV 1906 Venus - 68090 Sam Sw | Ellis | NORTH | 2022-03-01 | SOL | PV | 75 | COD | 2018-05-15 | 2018-07-02 | 2018-08-14 |  |  | No | Not Required | Not Required | Not Required
20INR0080 | Frye Solar | SS Completed, FIS Started, No IA | Hecate Energy | tap 345kV 79501 Ogallala - 79503 Tule Canyon | Swisher | PANHANDLE | 2021-12-31 | SOL | PV | 500 | COD | 2018-05-17 | 2018-07-02 | 2018-11-20 |  |  | No | Not Required | Not Required | Not Required
20INR0083 | Baird North Wind | SS Completed, FIS Started, IA | BMP Wind, LLC | tap 345kV 68005 WShack - 68050 Romney | Callahan | WEST | 2021-06-15 | WIN | WT | 331.2 |  | 2018-05-04 | 2018-06-12 | 2018-08-20 |  | 2019-05-31 | Yes | Not Required | Not Required | Not Required | 2019-07-19
20INR0086 | Arroyo Solar | SS Completed, FIS Started, No IA | Belltown Power | 8318 Rio Hondo 345kV | Cameron | COASTAL | 2021-10-01 | SOL | PV | 180 | COD | 2018-05-09 | 2018-07-09 | 2018-10-10 |  |  | No | Not Required | Not Required | Not Required
20INR0088 | West Raymond (El Trueno) Wind | SS Completed, FIS Completed, IA | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2020-12-15 | WIN | WT | 239.8 |  | 2018-05-14 | 2018-07-09 | 2018-07-06 | 2020-01-31 | 2019-05-20 | Yes | Not Required | Not Required | Not Required | 2019-06-06 | 2019-07-30 | 2020-01-31
20INR0089 | Chisholm Grid | SS Completed, FIS Completed, IA | Able Grid Energy | 2082 Hicks 138kV | Tarrant | NORTH | 2020-11-20 | OTH | BA | 200 |  | 2018-05-14 | 2018-06-19 | 2018-05-14 | 2019-06-26 | 2019-08-16 | Yes | Not Required | Not Required | Not Required | 2019-11-04
20INR0091 | Misae Solar II | SS Completed, FIS Started, IA | Misae Solar Park II | 60501 Tesla 345kV | Childress | PANHANDLE | 2021-06-21 | SOL | PV | 517.35 |  | 2018-05-15 | 2018-07-06 | 2018-05-15 |  | 2019-02-21 | Yes | Not Required | Not Required | Not Required
20INR0097 | El Suaz Ranch | SS Completed, FIS Started, No IA | El Sauz Ranch Wind, LLC | 8601 Cebolla 345kV | Willacy | COASTAL | 2021-09-30 | WIN | WT | 301.74 |  | 2018-06-19 | 2018-08-22 | 2019-01-31 |  |  | No | Not Required | Not Required | Not Required
20INR0098 | Danciger Solar | SS Completed, FIS Completed, No IA | Brazoria County Solar Project, LLC | tap 138kV 43120 Pledger - 43380 W Columbia | Brazoria | COASTAL | 2021-12-31 | SOL | PV | 200 |  | 2018-06-06 | 2018-08-01 | 2018-10-23 | 2019-09-26 |  | No | Not Required | Not Required | Not Required
20INR0101 | Westoria Solar | SS Completed, FIS Started, No IA | Brazoria West Solar Project,LLC | tap 138kV 42980 Nash - 43380 W Columbia | Brazoria | COASTAL | 2021-12-31 | SOL | PV | 200 |  | 2018-06-07 | 2018-07-30 | 2018-10-23 |  |  | No | Not Required | Not Required | Not Required
20INR0102 | Atascosa I Solar | SS Completed, FIS Started, No IA | Core Solar | tap 138kV 8221 Big Foot - 8203 Pleasant | Dawson | WEST | 2020-12-31 | SOL | PV | 126.6 |  | 2018-06-07 | 2018-08-24 | 2018-10-23 |  |  | No | Not Required | Not Required | Not Required
20INR0104 | GoodAlta | SS Completed, FIS Completed, No IA | Alta Power | tap 138kV 3483 Goodloe - 3127 Trinidad SES | Navarro | NORTH | 2021-04-01 | GAS | GT | 150 |  | 2018-07-26 | 2018-09-18 | 2018-10-23 | 2019-08-29 |  | No | 2019-06-13 | Not Required
20INR0106 | Wang Solar | SS Completed, FIS Started, No IA | Fresh Air Energy II, LLC | tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2020-10-01 | SOL | PV | 120 |  | 2018-06-14 | 2018-08-13 | 2018-08-29 |  |  | No | Not Required | Not Required | Not Required
20INR0112 | Walstrom | SS Completed, FIS Started, No IA | Castleman Power | 46220 Peters 138kV | Austin | SOUTH | 2021-05-01 | GAS | GT | 200 |  | 2018-07-03 | 2018-09-18 | 2018-11-29 |  |  | No | 2019-03-17 | Not Required
20INR0120 | Vortex Wind | SS Completed, FIS Started, No IA | Tradewind Energy | loop 345kV 60515 Clear Crossing - 1421 WillowCr 345kV | Throckmorton | WEST | 2021-12-31 | WIN | WT | 350 |  | 2018-06-29 | 2018-08-27 | 2019-02-20 |  |  | No | Not Required | Not Required | Not Required
20INR0125 | Alwest | SS Completed, FIS Started, No IA | Castleman Power | 3114 Paltalco 138kV | Anderson | NORTH | 2021-05-15 | GAS | GT | 200 |  | 2018-07-18 | 2018-10-02 |  |  |  | No | 2019-03-13 | Not Required
20INR0126 | Robles Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 8283 Asherton 138kV | Dimmit | SOUTH | 2020-12-31 | SOL | PV | 200 |  | 2018-07-18 | 2018-10-04 | 2018-07-18 |  |  | No | Not Required | Not Required | Not Required
20INR0127 | Milam Solar 1 | SS Completed, FIS Started, No IA | Solar Gen Resources | 13429 Sandow 345kV | Milam | SOUTH | 2021-09-30 | SOL | PV | 214 |  | 2018-07-03 | 2018-09-18 |  |  |  | No | Not Required | Not Required | Not Required
20INR0128 | EK Tipton Solar | SS Completed, FIS Started, No IA | EnergieKontor US Texas SP 1 LLC | 6673 Musquiz 138kV | Reeves | WEST | 2021-12-31 | SOL | PV | 120 |  | 2018-09-27 | 2018-11-19 | 2018-09-27 |  |  | No | Not Required | Not Required | Not Required
20INR0129 | Foxtrot Wind | SS Completed, FIS Started, No IA | Lincoln Clean | 5725 Pawnee 345kV | Karnes | SOUTH | 2022-02-01 | WIN | WT | 504 |  | 2018-07-26 | 2018-09-14 | 2018-07-26 |  |  | No | Not Required | Not Required | Not Required
20INR0130 | Ramsey Solar | SS Completed, FIS Completed, No IA | Hecate Energy | 44200 Hillje 345kV | Wharton | SOUTH | 2021-05-01 | SOL | PV | 514 |  | 2018-10-10 | 2018-11-21 | 2018-10-10 | 2020-01-07 |  | No | Not Required | Not Required | Not Required
20INR0132 | Altajac | SS Completed, FIS Completed, No IA | Alta Power | tap 3253 Jaxvlsw to 13253 Bullard 138kV | Cherokee | NORTH | 2021-04-01 | GAS | GT | 150 |  | 2018-07-18 | 2018-09-07 | 2018-10-23 | 2019-10-02 |  | No | 2019-05-21 | Not Required
20INR0133 | Thickgrass Solar | SS Completed, FIS Started, No IA | Origis Energy | 8115 Wadsworth 138kV OR loop into STP - Jones Creek 345-kV line | Matagorda | COASTAL | 2021-12-15 | SOL | PV | 148.7 |  | 2018-07-18 | 2018-10-01 | 2019-03-13 |  |  | No | Not Required | Not Required | Not Required
20INR0134 | Half Moon Solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2020-12-31 | SOL | PV | 151.2 |  | 2018-09-13 | 2018-11-09 | 2018-11-06 |  |  | No | Not Required | Not Required | Not Required
20INR0135 | Half Moon Battery | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2020-12-31 | OTH | BA | 30.2 |  | 2018-09-13 | 2018-11-09 | 2018-11-06 |  |  | No | Not Required | Not Required | Not Required
20INR0142 | Ajax Wind | SS Completed, FIS Started, No IA | Lincoln Clean | 345kV line RILEY 6101 - Bowman 1422 | Wilbarger | WEST | 2021-12-01 | WIN | WT | 630 |  | 2018-08-14 | 2018-10-19 | 2018-08-14 |  |  | No | Not Required | Not Required | Not Required
20INR0143 | Soda Lake Solar 2 | SS Completed, FIS Started, IA | Arrington Solar | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | WEST | 2021-05-31 | SOL | PV | 202.99 |  |  | 2016-11-08 | 2017-02-10 |  | 2018-08-20 | No | Not Required | Not Required | Not Required
20INR0146 | Angus Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 177 Bosque - 181 Cayote | Bosque | NORTH | 2020-08-31 | OTH | BA | 63 |  | 2017-11-13 | 2018-01-02 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
20INR0150 | Robles Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 8283 Asherton 138kV | Dimmit | SOUTH | 2020-12-31 | OTH | BA | 100 |  | 2018-07-18 | 2018-10-04 | 2018-07-18 |  |  | No | Not Required | Not Required | Not Required
20INR0153 | Tiger Wind | SS Completed, FIS Started, No IA | Nextera | 68000 West Shackelford 345kV | Taylor | WEST | 2020-12-01 | WIN | WT | 300 |  | 2018-10-10 | 2018-11-16 | 2018-10-10 |  |  | No | Not Required | Not Required | Not Required
20INR0155 | Peyton Creek Wind II | SS Completed, FIS Started, No IA | Eon | 42400 Refuge 345kV | Matagorda | COASTAL | 2021-12-15 | WIN | WT | 242 |  | 2018-08-21 | 2018-11-02 | 2019-03-14 |  |  | No | Not Required | Not Required | Not Required
20INR0162 | Diamondback Solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Starr | SOUTH | 2020-12-31 | SOL | PV | 201.6 |  | 2018-09-13 | 2018-12-06 | 2018-11-07 |  |  | No | Not Required | Not Required | Not Required
20INR0164 | Neeley Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV 1907 Venus - 68090 Sam | Hill | NORTH | 2021-04-01 | SOL | PV | 175 |  | 2018-08-29 | 2018-11-08 | 2018-11-07 |  |  | No | Not Required | Not Required | Not Required
20INR0202 | Owens Solar | SS Completed, FIS Completed, No IA | Belltown Power | tap 345kV 68091 Navarro - 68040 Kopperl | Bosque | NORTH | 2021-05-01 | SOL | PV | 200 |  | 2018-09-19 | 2018-10-03 | 2018-10-10 | 2020-02-24 |  | No |  |  | Not Required
20INR0203 | Pine Forest Solar | SS Completed, FIS Started, No IA | Telios Corporation | Monticello Switch – Allen Switch 345 kV Line | Hopkins | NORTH | 2021-06-01 | SOL | PV | 284.29 |  | 2018-10-04 | 2018-11-20 |  |  |  | No | Not Required | Not Required | Not Required
20INR0204 | BlueBell Solar II | SS Completed, FIS Completed, No IA | Bluebell Solar | 76090 Divide 345kV | Sterling | WEST | 2020-12-31 | SOL | PV | 115 |  | 2018-10-23 | 2018-12-13 | 2018-10-03 | 2020-02-06 |  | Yes |  |  | Not Required
20INR0205 | Roseland Solar | SS Completed, FIS Started, No IA | Hecate Energy LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2021-06-01 | SOL | PV | 500 |  | 2018-11-30 | 2019-02-04 | 2019-02-04 |  |  | No |  |  | Not Required
20INR0206 | PES1 | SS Completed, FIS Completed, IA | ProEnergy Services LLC | 47150 H O Clarke 138kV | Harris | HOUSTON | 2020-12-01 | GAS | GT | 484 | SFS/NtP | 2018-10-23 | 2018-11-16 | 2018-10-11 | 2019-12-02 | 2019-12-20 | Yes | 2019-04-10 | Not Required | 2019-12-06
20INR0208 | Signal Ranch | SS Completed, FIS Started, No IA | Belltown Power Texas, LLC | tap 138kV 6879 Weiland - 6883 Quinlan N | Hunt | NORTH | 2021-11-01 | SOL | PV | 70 | COD | 2018-11-07 | 2018-12-20 |  |  |  | No |  |  | Not Required
20INR0210 | Hopkins | SS Completed, FIS Started, No IA | GSE Group LLC | tap 345kV 1685 Farmersvl - 1695 Moses (Circuit #2) | Hopkins | NORTH | 2021-07-31 | SOL | PV | 320 |  | 2018-11-20 | 2019-02-06 | 2019-03-14 |  |  | No |  |  | Not Required
20INR0211 | Avocet | SS Completed, FIS Completed, No IA | Alta Power Lufkin Acovet | tap 138kV 3340 Lufkin - 3346 Champion Paper Mill Tap | Angelina | NORTH | 2021-03-01 | GAS | GT | 150 |  | 2018-12-06 | 2019-01-11 | 2019-01-11 | 2019-09-27 |  | No | 2019-07-30 | Not Required
20INR0213 | Brushy Creek Solar | SS Completed, FIS Started, No IA | Brushy Creek Solar LLC | 6444 Red Creek 345kV | Tom Green | WEST | 2021-12-15 | SOL | PV | 177.09 |  | 2019-01-07 | 2019-03-26 | 2019-03-05 |  |  | No | Not Required | Not Required | Not Required
20INR0214 | Noble Solar | SS Completed, FIS Started, No IA | Belltown Power Texas, LLC | 1730 Krum 345kV | Denton | NORTH | 2021-12-01 | SOL | PV | 300 | COD | 2018-11-06 | 2018-12-17 | 2018-11-06 |  |  | No |  |  | Not Required
20INR0215 | Double R Solar | SS Completed, FIS Started, No IA | Double R Solar Farm | 2433 Seagoville 345kV | Kaufman | NORTH | 2021-07-01 | SOL | PV | 280 |  | 2018-11-07 | 2018-12-11 | 2019-05-17 |  |  | No | Not Required | Not Required | Not Required
20INR0216 | Starr Solar Ranch | SS Completed, FIS Started, No IA | Starr Solar Ranch LLC | 8795 Roma 138kV | Starr | SOUTH | 2021-10-01 | SOL | PV | 135.99 | COD | 2018-11-07 | 2018-12-14 | 2018-11-07 |  |  | No | Not Required | Not Required | Not Required
20INR0217 | CAROL wind | SS Completed, FIS Started, No IA | Goat Mountain Renewables, LLC | 79504 AJ Swope 345kV | Potter | PANHANDLE | 2021-05-31 | WIN | WT | 169.2 |  | 2018-12-06 | 2019-01-18 | 2019-06-05 |  |  | No |  |  | Not Required
20INR0219 | Eunice Solar | SS Completed, FIS Started, IA | 2W Permian Solar LLC | tap 345kV 79650 Clearfork - 79630 Telephone Rd | Andrews | WEST | 2020-12-31 | SOL | PV | 420 | SFS/NtP | 2018-12-06 | 2019-01-30 | 2018-11-30 |  | 2019-12-11 | Yes |  |  | Not Required | 2020-02-06
20INR0220 | Eunice Storage | SS Completed, FIS Started, IA | 2W Permian Solar LLC | tap 345kV 79650 Clearfork - 79630 Telephone Rd | Andrews | WEST | 2020-12-31 | OTH | BA | 40.26 | SFS/NtP | 2018-12-06 | 2019-01-30 | 2018-11-30 |  | 2019-12-11 | Yes | Not Required | Not Required | Not Required | 2020-02-06
20INR0221 | Braes Power Plant | SS Completed, FIS Completed, No IA | ProEnergy Services LLC | 44650 Smithers 345kV | Fort Bend | HOUSTON | 2022-06-01 | GAS | GT | 484 | COD | 2018-12-06 | 2019-01-30 | 2018-12-01 | 2019-05-16 |  | No | 2018-12-04 | Not Required
20INR0222 | Tyson Nick Solar | SS Completed, FIS Started, No IA | Tyson Nick Solar Project, LLC | 1700 Toco 138kV | Lamar | NORTH | 2021-07-01 | SOL | PV | 90 | COD | 2018-12-12 | 2019-02-15 | 2019-01-14 |  |  | No |  |  | Not Required
20INR0226 | Timberwolf POI A | SS Completed, FIS Started, IA | CED Crane Solar 2, LLC | 76635 King Mt 138kV | Upton | WEST | 2021-05-01 | SOL | PV | 150 | Status Change INA-to-PLN | 2018-12-13 | 2019-01-17 | 2019-02-08 |  | 2019-12-11 | No |  |  | Not Required
20INR0230 | Markum Solar | SS Completed, FIS Started, No IA | Glory Leasing | 177 Bosque 138kV | McLennan | NORTH | 2021-05-01 | SOL | PV | 161 |  | 2018-12-18 | 2019-01-03 | 2018-12-18 |  |  | No | Not Required | Not Required | Not Required
20INR0231 | Topaz Power Plant | SS Completed, FIS Started, No IA | ProEnergy Services LLC | 38500 GAF TNP 138kV | Galveston | HOUSTON | 2021-06-01 | GAS | GT | 605 |  | 2019-02-01 | 2019-04-26 | 2019-02-22 |  |  | No | 2019-03-11 | Not Required
20INR0232 | Mars Solar | SS Completed, FIS Started, No IA | ABEI ENERGY&INFRASTRUCTURE LLC | 6030 Childress 138kV | Childress | PANHANDLE | 2022-01-10 | SOL | PV | 52.75 |  | 2019-02-06 | 2019-04-29 |  |  |  | No | Not Required | Not Required | Not Required
20INR0233 | Impala Flats Wind | SS Completed, FIS Started, No IA | Antelope Flats Wind, LLC | 79641 Farmland 345kV | Lynn | WEST | 2022-11-01 | WIN | WT | 282 |  | 2019-01-11 | 2019-04-03 | 2018-12-21 |  |  | No |  |  | Not Required
20INR0235 | Knickerbocker Solar | SS Completed, FIS Started, No IA | Knickerbocker Solar LLC | Tap 345kV 76003 Big Hill - 76009 Twin Buttes | Tom Green | WEST | 2022-11-01 | SOL | PV | 202.87 |  | 2019-01-07 | 2019-03-15 | 2019-03-04 |  |  | No | Not Required | Not Required | Not Required
20INR0236 | Old Hickory Solar | SS Completed, FIS Started, No IA | Old Hickory Solar LLC | tap 345kV 5133 Elmcreek - 5915 STP c2 | Jackson | SOUTH | 2021-05-21 | SOL | PV | 250 |  | 2019-01-25 | 2019-04-19 | 2019-08-12 |  |  | No | Not Required | Not Required | Not Required
20INR0238 | Voyager Storage | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2022-06-01 | OTH | BA | 50 |  | 2019-01-14 | 2019-03-19 | 2019-04-26 |  |  | No | Not Required | Not Required | Not Required
20INR0241 | Crowded Star Solar | SS Completed, FIS Started, IA | Jones City Solar, LLC | tap 345kV 68000 West Shack - 68001 Clayton c2 | Jones | WEST | 2021-07-02 | SOL | PV | 400 |  | 2019-01-21 | 2019-04-19 | 2019-05-22 |  | 2019-12-17 | No | Not Required | Not Required | Not Required
20INR0242 | Anson Solar Center, Phase II | SS Completed, FIS Started, No IA | Anson Solar Center, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2020-12-31 | SOL | PV | 200 |  | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  | No | Not Required | Not Required | Not Required
20INR0244 | Montezuma Storage | SS Completed, FIS Started, No IA | Montezuma Storage LLC | 7258 Glidden 138kV | Colorado | SOUTH | 2021-04-01 | OTH | BA | 47.12 |  | 2019-01-15 | 2019-07-02 | 2019-03-15 |  |  | No | Not Required | Not Required | Not Required
20INR0245 | Volunteer Storage | SS Completed, FIS Started, No IA | Blackjack Storage LLC | 7216 Lockhart 138kV | Caldwell | SOUTH | 2021-05-01 | OTH | BA | 47.12 |  | 2019-01-15 | 2019-07-02 | 2019-03-15 |  |  | No | Not Required | Not Required | Not Required
20INR0246 | Ryan Energy Storage | SS Completed, FIS Started, No IA | Arrowhead Storage LLC | 37580 TNPancake 69kV | Coryell | NORTH | 2020-08-31 | OTH | BA | 47.12 |  | 2019-01-15 | 2019-04-05 | 2019-03-15 |  |  | No | Not Required | Not Required | Not Required
20INR0247 | Water Valley Wind Energy | SS Completed, FIS Started, No IA | Water Valley Wind Energy, LLC | 76011 Twin Buttes 138kV | Tom Green | WEST | 2021-12-31 | WIN | WT | 150 |  | 2019-01-15 | 2019-03-29 | 2019-01-10 |  |  | No |  |  | Not Required
20INR0248 | Second Division Solar | SS Completed, FIS Completed, No IA | TX Gulf Solar 1 LLC | tap 138kV 43120 Pledger - 43380 W Columbia c4 | Brazoria | COASTAL | 2021-12-31 | SOL | PV | 100 |  | 2019-03-28 | 2019-06-18 | 2019-07-29 | 2020-02-06 |  | No | Not Required | Not Required | Not Required
20INR0249 | Appaloosa Run Renewable Energy Project | SS Completed, FIS Started, No IA | Appaloosa Run, LLC | tap 138kV 60361 Santarita - 76032 NMcCamey | Upton | WEST | 2021-12-31 | WIN | WT | 175 |  | 2019-01-17 | 2019-04-02 | 2019-01-15 |  |  | No |  |  | Not Required
20INR0250 | Aguayo Wind | SS Completed, FIS Started, No IA | Castle Gap Wind Power | tap 345kV 1444 Brown - 3422 Killeen | Mills | NORTH | 2021-03-31 | WIN | WT | 196 | COD | 2019-02-05 | 2019-05-03 | 2019-03-05 |  |  | No |  |  | Not Required
20INR0255 | Dawn Solar | SS Completed, FIS Started, No IA | Renegade Renewable LLC | Tap 345kV 23910 Windmill - 23906 AJ Swope | Deaf Smith | PANHANDLE | 2021-12-21 | SOL | PV | 515.66 |  | 2019-02-26 | 2019-05-17 | 2019-02-07 |  |  | No |  |  | Not Required
20INR0256 | Aquilla Lake 2 Wind | SS Completed, FIS Completed, No IA | NextEra Energy | 68090 Sam Switch 345 kV | Hill | NORTH | 2021-09-30 | WIN | WT | 100 |  | 2019-05-23 | 2019-08-13 | 2019-02-28 | 2020-01-17 |  | No | Not Required | Not Required | Not Required
20INR0257 | Snyder Wind Repower | SS Completed, FIS Started, No IA | Snyder Wind Farm, LLC | 6658 Plainview 69kV | Scurry | WEST | 2020-11-30 | WIN | WT | -15 |  | 2019-03-28 | 2019-06-20 | 2019-12-05 |  |  | No |  |  | Not Required
20INR0258 | Snyder BESS | SS Completed, FIS Started, No IA | Snyder Wind Farm, LLC | 6658 Plainview 69kV | Scurry | WEST | 2021-02-15 | OTH | BA | 17.58 | COD | 2019-03-28 | 2019-06-20 | 2019-12-05 |  |  | No | Not Required | Not Required | Not Required
20INR0259 | San Bernard Solar II | SS Completed, FIS Started, No IA | San Bernard Solar II, LLC | 43012 NEWGLF60T3_8 to 43340 TXGLF__POI_8 60 138kV | Wharton | SOUTH | 2021-06-01 | SOL | PV | 100 |  | 2019-03-25 | 2019-06-12 | 2019-06-10 |  |  | No |  |  | Not Required
20INR0262 | High Lonesome Wind Phase II | SS Completed, FIS Completed, IA | HIGH LONESOME WIND POWER, LLC | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | WEST | 2020-01-30 | WIN | WT | 50.6 |  | 2019-03-25 | 2019-06-20 | 2019-03-14 | 2019-07-31 | 2019-07-22 | Yes | Not Required | Not Required | Not Required | 2019-08-02 | 2019-08-02 | 2019-08-02 |  |  | 2020-02-18 | 2020-02-28
20INR0263 | Myrtle Solar II | SS Completed, FIS Started, No IA | Myrtle Solar II, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2021-06-01 | SOL | PV | 100 |  | 2019-03-25 | 2019-06-03 | 2019-06-10 |  |  | No |  |  | Not Required
20INR0264 | Hale 1 | SS Completed, FIS Started, No IA | NextEra Energy | 79506 Abernathy 345kV | Hale | PANHANDLE | 2020-12-01 | WIN | WT | 322 |  | 2019-04-03 | 2019-05-30 | 2019-03-18 |  |  | No |  |  | Not Required
20INR0265 | Karankawa 2 Expansion | SS Completed, FIS Completed, No IA | Karankawa Wind, LLC | tap 345kV 8455 Lon Hill - 5725 Pawnee, new sub Goddard | San Patricio | COASTAL | 2021-12-31 | WIN | WT | 98.3 |  | 2019-05-13 | 2017-06-23 | 2019-03-18 | 2019-01-16 |  | No |  |  | Not Required
20INR0266 | Tres Bahias Solar | SS Completed, FIS Started, No IA | Tres Bahias Solar Power LLC | 8140 Joslin 138kV | Calhoun | COASTAL | 2021-02-25 | SOL | PV | 195 | COD | 2019-03-26 | 2019-06-11 | 2019-06-03 |  |  | No |  |  | Not Required
20INR0267 | Greens Bayou Expansion | SS Completed, FIS Started, IA | NRG Texas Power | 40715 Greens Bayou 138kV | Harris | HOUSTON | 2021-06-01 | GAS | GT | 140 |  | 2019-04-24 | 2019-07-19 | 2019-04-23 |  | 2019-10-31 | No | Not Required | Not Required | 2019-10-28 |  |  | 2019-10-31
20INR0268 | Big Hat | SS Completed, FIS Started, No IA | Pyron Wind Farm, LLC | 1048 Tonkawas 345kV | Nolan | WEST | 2020-12-01 | OTH | BA | 30 |  | 2019-06-03 | 2019-08-30 | 2019-08-19 |  |  | No |  |  | Not Required
20INR0269 | Texas Solar Nova 2 | SS Completed, FIS Started, No IA | Texas Solar Nova 1, LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2022-09-30 | SOL | PV | 200.2 |  | 2019-06-24 | 2015-12-30 | 2019-06-19 |  |  | No |  |  | Not Required
20INR0271 | Blue Hills Wind | SS Completed, FIS Started, No IA | GH America Energy LLC | Tap 138kV 8683 Comstock - 60389 Corral | Val Verde | WEST | 2021-10-01 | WIN | WT | 253.8 |  | 2019-05-07 | 2019-07-26 | 2019-11-21 |  |  | No |  |  | Not Required
20INR0272 | RIO NOGALES AGP UPGRADE CT3 | SS Completed, FIS Completed, IA | CPS Energy | Existing gen 345kV Rio Nogales Power Project (# 5362) | Guadalupe | SOUTH | 2020-04-20 | GAS | CC | 19 |  | 2019-05-10 | 2019-08-02 | 2019-05-10 | 2019-07-30 | 2000-04-21 | Yes | 2019-06-21 | Not Required | 2019-06-21 | 2019-07-21 | 2019-07-21 | 2019-07-30
20INR0274 | SIXTY SIX Solar | SS Completed, FIS Started, No IA | MERIT SI DEVELOPMENT, LLC | 38212 TNMONMNTDC0 | Winkler | WEST | 2021-04-01 | SOL | PV | 3.75 |  | 2019-06-20 | 2019-09-17 | 2019-06-17 |  |  | No |  |  | Not Required
20INR0276 | North Fork | SS Completed, FIS Started, No IA | Energy Storage Resources, LLC | 7522 Andice 138kV | Williamson | SOUTH | 2021-05-15 | OTH | BA | 100 | COD | 2019-05-17 | 2019-08-13 | 2019-05-14 |  |  | No |  |  | Not Required
20INR0279 | SHIELD Solar | SS Completed, FIS Started, No IA | MERIT SI DEVELOPMENT, LLC | 60441 OLLIN4A | Crane | WEST | 2021-04-01 | SOL | PV | 1.88 |  | 2019-06-17 | 2019-09-05 | 2019-06-13 |  |  | No |  |  | Not Required
20INR0280 | High Lonesome BESS | SS Completed, FIS Started, No IA | HIGH LONESOME WIND POWER, LLC | tap 345kV 76002 Bakersfield - 7053 Noelke | Crockett | WEST | 2021-06-01 | OTH | BA | 50 |  | 2019-06-11 | 2019-08-30 | 2019-06-07 |  |  | No | Not Required | Not Required | Not Required
20INR0281 | Queen BESS | SS Completed, FIS Started, No IA | Roadrunner Solar Project, LLC | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | WEST | 2021-06-01 | OTH | BA | 50 |  | 2019-06-11 | 2019-10-23 | 2019-06-07 |  |  | No |  |  | Not Required
20INR0282 | Odessa-Ector Unit 2 (Block 2) Uprate Repower | SS Completed, FIS Completed, No IA | LA FRONTERA HOLDINGS LLC | 1026 Odessa 345kV | Ector | WEST | 2020-06-15 | GAS | CC | 83 | SFS/NtP | 2019-06-18 | 2019-10-23 | 2019-06-14 | 2019-11-01 |  | Yes | 2019-09-30 |  | 2019-10-01 | 2019-11-01 | 2019-11-01 | 2019-11-01
20INR0283 | CITY WEST Solar | SS Completed, FIS Started, No IA | MERIT SI DEVELOPMENT, LLC | 8507 Schottky 69kV | Live Oak | SOUTH | 2021-04-01 | SOL | PV | 4.13 |  | 2019-07-15 | 2019-10-07 | 2019-07-12 |  |  | No |  |  | Not Required
20INR0286 | Wise County Power Repower (CT1, CT2) | SS Completed, FIS Completed, IA | Wise County Power Company LLC | 1421 Willow Creek 345kV | Wise | NORTH | 2020-12-01 | GAS | CC | 21 |  | 2019-07-25 | 2019-10-23 | 2019-07-16 | 2019-10-23 | 2001-03-19 | Yes | 2020-01-21 |  | 2019-12-05 | 2020-01-22 | 2020-01-27 | 2020-01-27
20INR0287 | STP Unit 1 repower | SS Completed, FIS Completed, No IA | South Texas Electric Generating Station Unit 1 | 5915 STP 345kV | Matagorda | COASTAL | 2020-04-30 | NUC | ST | 13 |  | 2019-07-25 | 2019-10-22 | 2019-09-17 | 2019-10-28 |  | Yes | Not Required | Not Required |  | 2019-10-28 | 2019-10-28 | 2019-10-28
20INR0288 | Brazos BESS 2 | SS Completed, FIS Started, No IA | Brazos Wind Ventures, LLC | 1064 Sun 138kV | Borden | WEST | 2020-12-31 | OTH | BA | 50 |  | 2019-08-05 | 2019-10-31 | 2019-08-16 |  |  | No |  |  | Not Required
20INR0290 | River Valley Storage 1 | SS Completed, FIS Started, No IA | KCE TX 19, LLC | 3650 Elgin SS 138kV | Williamson | SOUTH | 2021-12-31 | OTH | BA | 50 |  | 2019-10-15 | 2020-01-07 | 2019-10-21 |  |  | No |  |  | Not Required
20INR0291 | Silicon Hill Storage | SS Completed, FIS Started, No IA | KCE TX 12, LLC | 7336 L_GILLCR8_1Y 138kV | Travis | SOUTH | 2021-06-01 | OTH | BA | 100 |  | 2019-10-15 | 2020-01-07 | 2019-10-22 |  |  | No |  |  | Not Required
20INR0293 | River Valley Storage 2 | SS Completed, FIS Started, No IA | KCE TX 21, LLC | 3650 Elgin SS 138kV | Williamson | SOUTH | 2021-12-31 | OTH | BA | 50 |  | 2019-10-15 | 2020-01-07 | 2019-10-21 |  |  | No |  |  | Not Required
20INR0294 | Lily Storage | SS Completed, FIS Started, No IA | Lily Solar, LLC | tap 138kV 6904 CombinRC - 6908 ScuryRC | Kaufman | NORTH | 2021-06-01 | OTH | BA | 53.6 |  | 2019-09-23 | 2019-12-11 | 2020-01-10 |  |  | No |  |  | Not Required
20INR0295 | McAdoo repower | SS Completed, FIS Started, No IA | McAdoo Wind Energy LLC | 6150 Spur 138kV | Dickens | PANHANDLE | 2020-10-30 | WIN | WT | 14.72 |  | 2019-10-24 | 2019-12-16 | 2019-10-09 |  |  | No |  |  | Not Required
20INR0296 | Sand Bluff Wind Repower | SS Completed, FIS Started, No IA | RWE Renewables Development, LLC | 1333 McDonald 138kV | Glasscock | WEST | 2020-12-15 | WIN | WT | 8 |  | 2019-11-27 | 2019-11-27 | 2019-11-19 |  |  | No |  |  | Not Required
20INR0298 | Queen Solar Phase II | SS Completed, FIS Completed, IA | Roadrunner Solar Project, LLC | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | WEST | 2020-04-30 | SOL | PV | 200 | FIS Request | 2019-12-05 | 2017-08-28 |  | 2019-05-10 | 2020-01-09 | Yes | Not Required | Not Required | Not Required | 2019-04-01 | 2019-04-30
20INR0299 | Sparkl BESS | SS Completed, FIS Started, No IA | Guadalupe Valley Electric Cooperative, Inc | 7606 McQueeney 138kV | Guadalupe | SOUTH | 2020-08-01 | OTH | BA | 20 |  | 2019-12-03 | 2020-02-24 | 2019-11-13 |  |  | No |  |  | Not Required
20INR0301 | Colorado Bend Power I LLC (Repower) | SS Started, FIS Started, No IA | Colorado Bend Power I, LLC | Dyann Substation (3821 S SH 60 Hwy, City of Wharton, Wharton County, TX 77488 | Wharton | SOUTH | 2020-07-07 | GAS | CC | 0 | FIS Request |  |  | 2020-02-28 16:32 |  |  | No
21INR0005 | Hutt Wind | SS Completed, FIS Started, No IA | Pioneer Natural Resources | tap 345kV 11028 Odessa - 59901 Grelton | Midland | WEST | 2021-10-06 | WIN | WT | 336 |  | 2017-09-06 | 2019-08-19 | 2020-01-15 |  |  | No | Not Required | Not Required | Not Required
21INR0006 | Giddings Wind | SS Completed, FIS Started, No IA | Pioneer Natural Resources | 71212 Upton 138kV | Upton | WEST | 2021-10-06 | WIN | WT | 240 |  | 2017-09-06 | 2019-08-19 | 2020-01-15 |  |  | No | Not Required | Not Required | Not Required
21INR0007 | Deepwater | SS Completed, FIS Started, No IA | AES | 40450 Deepwater 345kV | Harris | HOUSTON | 2021-04-30 | GAS | GT | 462.2 |  | 2017-12-05 | 2018-02-01 | 2017-12-05 |  |  | No
21INR0008 | Samson Solar | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2021-12-31 | SOL | PV | 200 |  | 2018-04-12 | 2018-06-12 | 2018-10-23 |  |  | No | Not Required | Not Required | Not Required
21INR0012 | Air Products | SS Completed, FIS Started, No IA | Air Products | 39140 TNTxCityMain 69kV | Galveston | HOUSTON | 2021-05-15 | GAS | ST | 0 |  | 2018-06-07 | 2018-08-01 |  |  |  | No
21INR0015 | Arroyo Del Bisonte Solar | SS Completed, FIS Started, No IA | Sunchase Power | tap 345kV 44005 WAP - 44040 Bailey | Wharton | SOUTH | 2021-04-01 | SOL | PV | 300 |  | 2018-05-09 | 2018-07-06 | 2018-08-21 |  |  | No | Not Required | Not Required | Not Required
21INR0016 | Danish Fields II | SS Completed, FIS Completed, No IA | Sunchase Power | 44200 Hillje 345kV | Wharton | SOUTH | 2021-06-01 | SOL | PV | 200 |  | 2018-05-10 | 2018-07-11 | 2018-08-21 | 2020-01-21 |  | No | Not Required | Not Required | Not Required
21INR0017 | Danish Fields III | SS Completed, FIS Completed, No IA | Sunchase Power | 44200 Hillje 345kV | Wharton | SOUTH | 2021-06-01 | SOL | PV | 200 |  | 2018-05-10 | 2018-07-11 | 2018-08-27 | 2020-01-21 |  | No | Not Required | Not Required | Not Required
21INR0019 | Zier Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 8252 Brackett - 78255 PintCr | Kinney | SOUTH | 2022-05-25 | SOL | PV | 160 |  | 2018-05-24 | 2018-07-20 | 2018-05-24 |  |  | No | Not Required | Not Required | Not Required
21INR0020 | El Zorro Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 80439 La Quinta - 8297 Bruni | Webb | SOUTH | 2021-02-01 | SOL | PV | 253.3 |  | 2018-06-29 | 2018-09-13 | 2018-06-29 |  |  | No | Not Required | Not Required | Not Required
21INR0021 | Green Holly Solar | SS Completed, FIS Started, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-08-01 | SOL | PV | 413.6 |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | No | Not Required | Not Required | Not Required
21INR0022 | Red Holly Solar | SS Completed, FIS Started, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-07-01 | SOL | PV | 260 |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | No | Not Required | Not Required | Not Required
21INR0024 | Samson Solar 2 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2021-12-31 | SOL | PV | 200 |  |  | 2018-06-12 | 2018-10-23 |  |  | No | Not Required | Not Required | Not Required
21INR0026 | Juno Solar | SS Completed, FIS Completed, IA | Intersect Power | 59906 Long Draw 138 kV | Borden | WEST | 2021-05-15 | SOL | PV | 313.2 |  | 2018-08-14 | 2018-10-25 | 2018-10-18 | 2019-12-12 | 2018-12-28 | No | Not Required | Not Required | Not Required
21INR0027 | Zier Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 8252 Brackett - 78255 PintCr | Kinney | SOUTH | 2022-05-25 | OTH | BA | 20 | COD | 2018-05-24 | 2018-07-20 | 2018-05-24 |  |  | No | Not Required | Not Required | Not Required
21INR0028 | El Zorro Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 80439 La Quinta - 8297 Bruni | Webb | SOUTH | 2021-02-01 | OTH | BA | 126.65 |  | 2018-06-29 | 2018-09-13 | 2018-06-29 |  |  | No | Not Required | Not Required | Not Required
21INR0029 | Green Holly Storage | SS Completed, FIS Started, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-08-01 | OTH | BA | 50 |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | No | Not Required | Not Required | Not Required
21INR0031 | Indigo Solar | SS Completed, FIS Started, No IA | Innovative Solar, LLC | tap 345kV 68001 Clayton 345kV - 68000 WShack | Fisher | WEST | 2021-12-15 | SOL | PV | 125 |  | 2018-09-27 | 2018-11-20 | 2019-05-15 |  |  | No | Not Required | Not Required | Not Required
21INR0033 | Red Holly Storage | SS Completed, FIS Started, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-07-01 | OTH | BA | 50 |  | 2018-09-27 | 2018-12-18 | 2018-12-11 |  |  | No | Not Required | Not Required | Not Required
21INR0035 | Elmer | SS Completed, FIS Started, No IA | Energy Storage Resources, LLC | 2208 Mansfield 138kV | Tarrant | NORTH | 2021-01-31 | OTH | BA | 100 |  | 2019-05-17 | 2019-07-29 | 2019-05-10 |  |  | No |  |  | Not Required
21INR0201 | Brandon | SS Completed, FIS Started, No IA | Lubbock Power and Light | Brandon 69 kV | Lubbock | PANHANDLE | 2021-06-03 | GAS | GT | 21.5 |  | 2018-09-12 | 2018-09-12 | 2018-09-12 |  |  | No
21INR0202 | R Massengale | SS Completed, FIS Started, No IA | Lubbock Power and Light | MacKenzie 60 kV | Lubbock | PANHANDLE | 2021-06-03 | GAS | GT | 60 |  | 2018-09-12 | 2018-09-12 | 2018-09-12 |  |  | No
21INR0203 | Smithland Texas Solar | SS Completed, FIS Started, No IA | EDP RENEWABLES NORTH AMERICA LLC | tap 345kV 3687 Bell E - 39950 TNP One | Milam | SOUTH | 2021-10-31 | SOL | PV | 238.89 |  | 2018-10-10 | 2018-12-09 | 2019-04-23 |  |  | No |  |  | Not Required
21INR0204 | Lumina | SS Completed, FIS Started, No IA | IP Lumina, LLC | 11305 Dermott 345kV | Scurry | WEST | 2022-05-31 | SOL | PV | 313.2 |  | 2018-09-27 | 2018-11-08 | 2018-11-07 |  |  | No |  |  | Not Required
21INR0205 | Radian | SS Completed, FIS Started, No IA | IP Radian, LLC | 1444 Brown 345kV | Brown | NORTH | 2022-05-31 | SOL | PV | 374.4 |  | 2018-09-27 | 2018-11-08 | 2018-11-07 |  |  | No | Not Required | Not Required | Not Required
21INR0207 | Quantum | SS Completed, FIS Started, No IA | IP Quantum, LLC | 60515 Clear Crossing 345kV | Haskell | WEST | 2021-12-31 | SOL | PV | 374.4 |  | 2018-09-27 | 2018-11-14 | 2018-11-07 |  |  | No |  |  | Not Required
21INR0209 | Adamstown Storage | SS Completed, FIS Started, No IA | Adams Creek Solar Project, LLC | tap 345kV 1730 West Krum - 6101 Riley | Wichita | WEST | 2022-12-31 | OTH | BA | 116 |  | 2018-11-20 | 2019-02-04 | 2019-05-16 |  |  | No |  |  | Not Required
21INR0210 | Adamstown Solar | SS Completed, FIS Started, No IA | Adams Creek Solar Project, LLC | tap 345kV 1730 West Krum - 6101 Riley | Wichita | WEST | 2022-12-31 | SOL | PV | 250 |  | 2018-11-20 | 2019-02-04 | 2019-05-16 |  |  | No |  |  | Not Required
21INR0213 | Vancourt | SS Completed, FIS Started, No IA | Rayos Del Sol II Solar Project, LLC | tap 138kV 80103 Rangerville - 8554 Mesquite | Cameron | COASTAL | 2021-12-31 | SOL | PV | 50 |  | 2018-11-07 | 2018-12-12 | 2018-11-07 |  |  | No |  |  | Not Required
21INR0217 | Spectrum Solar | SS Completed, FIS Started, No IA | IP Spectrum, LLC | 1440 Comanche 345kV | Comanche | NORTH | 2022-05-31 | SOL | PV | 400 | Proj Name | 2018-11-07 | 2018-12-20 | 2019-02-05 |  |  | No |  |  | Not Required
21INR0220 | Maleza Solar | SS Completed, FIS Started, No IA | Brush Solar LLC | tap 345kV 44200 Hillje - 44040 Bailey | Fort Bend | HOUSTON | 2021-06-01 | SOL | PV | 250 |  | 2018-12-06 | 2019-01-18 |  |  |  | No |  |  | Not Required
21INR0221 | Delilah Solar 1 | SS Completed, FIS Started, No IA | Samson Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2021-12-31 | SOL | PV | 250 |  | 2018-11-20 | 2019-01-04 | 2019-05-03 |  |  | No |  |  | Not Required
21INR0223 | Tulsita Solar | SS Completed, FIS Started, No IA | Tulsita Solar LLC | 8590 Tuleta 138kV | Goliad | SOUTH | 2021-05-28 | SOL | PV | 258.35 |  | 2018-12-05 | 2019-02-21 | 2019-05-17 |  |  | No | Not Required | Not Required | Not Required
21INR0226 | Equinox Solar 1 | SS Completed, FIS Started, No IA | Invenergy Solar Project Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2021-06-30 | SOL | PV | 200 |  | 2018-12-11 | 2019-01-23 | 2019-07-30 17:08 |  |  | No | Not Required | Not Required | Not Required
21INR0227 | Equinox Solar 2 | SS Completed, FIS Started, No IA | Invenergy Solar Project Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2021-12-31 | SOL | PV | 200 |  | 2018-12-11 | 2019-01-31 | 2019-07-30 |  |  | No | Not Required | Not Required | Not Required
21INR0228 | Cottonwood Bayou Solar II | SS Completed, FIS Started, No IA | Cottonwood Bayou Solar II, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2021-06-01 | SOL | PV | 200 |  | 2018-12-06 | 2019-02-07 | 2019-06-14 12:04 |  |  | No | Not Required | Not Required | Not Required
21INR0229 | Prospero Solar II | SS Completed, FIS Completed, IA | Sungold Renewables, LLC | 79650 Clearfork 345kV + 10 mile gen-tie | Andrews | WEST | 2021-07-01 | SOL | PV | 250 |  | 2018-11-29 | 2019-02-12 | 2018-12-10 | 2020-01-15 | 2020-01-17 | No |  |  | Not Required
21INR0233 | Taygete II Solar | SS Completed, FIS Started, IA | Taygete Energy Project II, LLC | 60393 Pig Creek 138kV | Pecos | WEST | 2021-06-01 | SOL | PV | 256.25 |  | 2018-12-17 | 2019-01-15 | 2018-12-13 |  | 2019-03-27 | Yes | Not Required | Not Required | Not Required | 2019-05-06
21INR0237 | Voyager Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2021-12-01 | SOL | PV | 300 |  | 2019-01-04 | 2019-03-19 | 2019-04-26 |  |  | No | Not Required | Not Required | Not Required
21INR0240 | La Casa Wind | SS Completed, FIS Started, No IA | EC&R development, LLC | tap 138kV 1618 Caddo - 1619 Colony Creek | Stephens | NORTH | 2021-12-15 | WIN | WT | 201 |  | 2018-12-28 | 2019-03-12 | 2018-12-29 |  |  | No |  |  | Not Required
21INR0244 | Madero Grid | SS Completed, FIS Started, IA | Madero Grid, LLC | 8824 Railroad 138kV | Hidalgo | SOUTH | 2021-05-31 | OTH | BA | 201.96 |  | 2018-12-20 | 2019-03-12 | 2018-12-19 |  | 2019-12-06 | Yes | Not Required | Not Required | Not Required | 2020-01-13
21INR0245 | TOUCAN SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY&INFRASTRUCTURE LLC | 38120 TNReeves 138kV | Reeves | WEST | 2022-01-15 | SOL | PV | 152.03 |  | 2019-01-29 | 2019-04-19 | 2019-10-16 |  |  | No | Not Required | Not Required | Not Required
21INR0247 | Anson Solar Center, Phase III | SS Completed, FIS Started, No IA | Anson Solar Center, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2021-06-01 | SOL | PV | 200 |  | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  | No |  |  | Not Required
21INR0252 | Monaville Solar | SS Completed, FIS Started, No IA | Monaville Solar LLC | 7664 Sunnyside 69kV | Waller | HOUSTON | 2021-12-31 | SOL | PV | 100 | MW Size | 2019-02-07 | 2019-04-29 | 2019-11-27 |  |  | No | Not Required | Not Required | Not Required
21INR0253 | Ulysses Solar | SS Completed, FIS Started, No IA | Ulysses Solar LLC | tap 345kV 6444 Red Creek - 60040 Bluff Creek | Coke | WEST | 2021-11-01 | SOL | PV | 150 |  | 2019-01-25 | 2019-04-05 | 2019-05-10 |  |  | No | Not Required | Not Required | Not Required
21INR0254 | Blue Cut Solar | SS Completed, FIS Started, No IA | Blue Cut Solar, LLC | tap 138kV 7064 Lampasas - 260 Kempner | Lampasas | NORTH | 2022-06-01 | SOL | PV | 150 |  | 2019-01-30 | 2019-04-12 | 2019-10-08 |  |  | No | Not Required | Not Required | Not Required
21INR0256 | Amsterdam Solar | SS Completed, FIS Started, No IA | Cottonwood Bayou Solar II, LLC | tap 345kV 43035 Oasis - 42500 Dow c27 | Brazoria | COASTAL | 2021-11-30 | SOL | PV | 500 |  | 2019-02-07 | 2019-04-29 | 2019-07-31 |  |  | No | Not Required | Not Required | Not Required
21INR0257 | Mercury Solar | SS Completed, FIS Started, No IA | Mercury Solar, LLC | 68090 Sam Sw 345kV | Hill | NORTH | 2021-12-01 | SOL | PV | 201.6 |  | 2019-02-14 | 2019-05-03 | 2019-02-07 |  |  | No | Not Required | Not Required | Not Required
21INR0258 | Mercury Storage | SS Completed, FIS Started, No IA | Mercury Storage, LLC | 68090 Sam Sw 345kV | Hill | NORTH | 2021-12-01 | OTH | BA | 205.9 |  | 2019-02-14 | 2019-05-03 | 2019-02-07 |  |  | No | Not Required | Not Required | Not Required
21INR0259 | Sunshine Solar | SS Completed, FIS Started, No IA | Sunshine Energy LLC | tap 138kV 8125 Lolita - 8172 Victoria | Victoria | SOUTH | 2021-03-31 | SOL | PV | 172.83 |  | 2019-02-14 | 2019-03-29 | 2019-02-08 |  |  | No |  |  | Not Required
21INR0260 | Chariot Storage | SS Completed, FIS Started, No IA | Chariot Storage LLC | 99 Ben Hur 69kV | Limestone | NORTH | 2021-06-18 | OTH | BA | 47.12 |  | 2019-03-06 | 2019-05-24 | 2019-02-11 |  |  | No | Not Required | Not Required | Not Required
21INR0261 | Horizon Solar | SS Completed, FIS Completed, IA | First Solar Development, LLC | tap 138kV 5895 Pearsall - 5827 Moore | Frio | SOUTH | 2021-12-31 | SOL | PV | 204.09 |  | 2019-03-05 | 2019-05-20 | 2019-03-01 | 2019-12-20 | 2019-07-12 | Yes | Not Required | Not Required | Not Required | 2019-08-09 | 2019-12-09
21INR0262 | Grandfalls Storage | SS Completed, FIS Started, No IA | King Mountain Storage LLC | tap 345kV 11028 Odessa - 76000 North McCamey | Upton | WEST | 2021-12-01 | OTH | BA | 205.9 |  | 2019-03-25 | 2019-06-17 | 2019-02-14 |  |  | No |  |  | Not Required
21INR0263 | Monarch Creek Wind | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 60515 Clear Crossing - 17013 Rocky Mound | Throckmorton | WEST | 2021-12-31 | WIN | WT | 349.13 |  | 2019-04-25 | 2019-07-19 | 2019-08-05 |  |  | No |  |  | Not Required
21INR0264 | Monarch Creek Wind (B) | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 60515 Clear Crossing - 17013 Rocky Mound | Haskell | WEST | 2021-12-31 | WIN | WT | 451.5 |  | 2019-04-25 | 2019-07-19 | 2019-11-15 |  |  | No |  |  | Not Required
21INR0265 | Sisters Solar | SS Completed, FIS Started, No IA | Oberon Solar LLC | loop station on double circuit 345kV line 1018 Moss Sw/1029 Odessa Ehv Sw - 11010 Wolf Sw | Ector | WEST | 2021-06-01 | SOL | PV | 1219.23 |  | 2019-02-28 | 2019-03-29 | 2019-02-20 |  |  | No | Not Required | Not Required | Not Required
21INR0266 | BLACKBIRD SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY&INFRASTRUCTURE LLC | 1318 China Grove 138kV | Mitchell | WEST | 2022-02-11 | SOL | PV | 151.55 |  | 2019-03-12 | 2019-05-24 | 2019-11-08 |  |  | No |  |  | Not Required
21INR0268 | Greyhound Solar | SS Completed, FIS Started, No IA | Rockhound Solar 2, LLC dba "Greyhound Solar" | tap 345kV dbl ckt 11010 Wolf - 1018 Moss and 11008 Wolf - 11028 Odessa | Ector | WEST | 2021-06-30 | SOL | PV | 650 | MW Size | 2019-03-28 | 2019-06-05 | 2019-03-21 |  |  | No |  |  | Not Required
21INR0270 | NIGHTINGALE SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY | 1189 Barber 138kV | Mitchell | WEST | 2022-03-04 | SOL | PV | 151.64 |  | 2019-03-26 | 2019-06-10 | 2019-12-02 |  |  | No |  |  | Not Required
21INR0271 | TERRANOVA SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY&INFRASTRUCTURE LLC | 6110 East Munday 138kV | Knox | WEST | 2022-03-04 | SOL | PV | 152.32 |  | 2019-04-01 | 2019-06-10 | 2019-12-12 |  |  | No |  |  | Not Required
21INR0272 | FLAMINGO SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY&INFRASTRUCTURE LLC | tap 138kV 60399 Weiss - 6340 Ballinger | Tom Green | WEST | 2022-03-04 | SOL | PV | 123 |  | 2019-03-26 | 2019-06-10 | 2019-12-05 |  |  | No |  |  | Not Required
21INR0273 | OLIVE SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY&INFRASTRUCTURE LLC | Tap 69kV 6422 Edith - 6423 Cedar Hill | Coke | WEST | 2022-03-01 | SOL | PV | 39.63 |  | 2019-04-16 | 2019-06-07 | 2019-12-11 |  |  | No |  |  | Not Required
21INR0274 | Carol Solar | SS Completed, FIS Started, No IA | Goat Mountain Renewables, LLC | 23906 AJ Swope 345kV | Potter | PANHANDLE | 2021-06-30 | SOL | PV | 223.2 | MW Size | 2019-03-26 | 2019-06-11 | 2019-06-07 |  |  | No |  |  | Not Required
21INR0276 | Elara Solar | SS Completed, FIS Completed, IA | Elara Energy Project, LLC | 5866 PaloduroSw 138kV | Frio | SOUTH | 2021-04-01 | SOL | PV | 134 | MW Size | 2019-03-26 | 2019-06-19 | 2019-03-15 | 2019-11-18 | 2019-07-12 | Yes | Not Required | Not Required | Not Required | 2019-09-27
21INR0278 | Fighting Jays Solar | SS Completed, FIS Started, No IA | AP Solar Holdings, LLC | tap 345kV 44000 WA Parish - 44200 Hillje c64 | Fort Bend | HOUSTON | 2021-05-01 | SOL | PV | 356.55 |  | 2019-03-26 | 2019-06-17 | 2019-03-20 |  |  | No |  |  | Not Required
21INR0280 | Edgewater Storage | SS Completed, FIS Started, No IA | Edgewater Battery Storage LLC | 210 Reagor Springs 69kV | Ellis | NORTH | 2021-06-28 | OTH | BA | 47.12 |  | 2019-04-08 | 2019-07-04 | 2019-03-24 |  |  | No | Not Required | Not Required | Not Required
21INR0281 | Byrd Ranch Storage | SS Completed, FIS Started, No IA | Byrd Ranch Storage LLC | 39700 TNSweeny 138kV | Brazoria | COASTAL | 2021-06-18 | OTH | BA | 47.12 |  | 2019-04-08 | 2019-07-04 | 2019-03-24 |  |  | No | Not Required | Not Required | Not Required
21INR0282 | Corner Solar | SS Completed, FIS Started, No IA | Shannon Solar LLC | 76005 Schneeman Draw 345kV | Crockett | WEST | 2021-06-01 | SOL | PV | 1221.64 |  | 2019-06-03 | 2019-08-28 | 2019-03-25 |  |  | No |  |  | Not Required
21INR0285 | LARISA SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY & INFRASTRUCTURE LLC | Tap 345kV 6235 Mulberry - 6076 Foxtail | Jones | WEST | 2022-03-25 | SOL | PV | 405.09 |  | 2019-04-24 | 2019-07-01 | 2019-12-23 |  |  | No |  |  | Not Required
21INR0289 | Saturn 1 | SS Completed, FIS Started, No IA | Saturn 1 wind | 80220 Cenizo 345kV | Zapata | SOUTH | 2021-08-31 | WIN | WT | 300 |  | 2019-07-19 | 2019-10-10 | 2019-07-17 |  |  | No |  |  | Not Required
21INR0291 | Saturn 2 | SS Completed, FIS Started, No IA | Saturn 2 | 80220 Cenizo 345kV | Zapata | SOUTH | 2021-08-31 | WIN | WT | 150 |  | 2019-07-19 | 2019-10-10 | 2019-07-10 |  |  | No |  |  | Not Required
21INR0292 | Slama Solar | SS Completed, FIS Started, No IA | Burkburnett Solar, LLC | Tap 345kV 6101 Riley - 1730 W Krum c1 | Wichita | WEST | 2022-06-01 | SOL | PV | 251.65 | MW Size | 2019-04-18 | 2019-07-03 | 2019-12-27 |  |  | No | Not Required | Not Required | Not Required
21INR0293 | Hat Creek Solar | SS Completed, FIS Started, No IA | Hat Creek Solar, LLC | 1464 South Wichita Falls 138kV | Archer | WEST | 2022-06-01 | SOL | PV | 251.67 |  | 2019-04-18 | 2019-06-24 | 2019-12-20 |  |  | No | Not Required | Not Required | Not Required
21INR0294 | Brooke Smith Solar | SS Completed, FIS Started, No IA | BN Wind Project LLC | 1444 Brown 345 kV | Brown | NORTH | 2022-05-15 | SOL | PV | 346.89 | COD | 2019-04-16 | 2019-06-11 | 2019-12-08 |  |  | No |  |  | Not Required
21INR0295 | Sterling Prairie Solar | SS Completed, FIS Started, No IA | EC&R Solar Development, LLC | tap 138kV 8127 Lane City 4A - 8121 Blessings c1 | Matagorda | COASTAL | 2021-12-20 | SOL | PV | 119.91 | MW Size COD | 2019-04-24 | 2019-07-23 | 2020-01-21 |  |  | No |  |  | Not Required
21INR0311 | MEISSA SOLAR | SS Completed, FIS Started, No IA | BLUE STONE RENEWABLE VIII LLC | 60417 Tennyson 138kV | Coke | WEST | 2022-03-25 | SOL | PV | 136.37 |  | 2019-04-24 | 2019-07-01 | 2019-12-23 |  |  | No |  |  | Not Required
21INR0312 | Nereida Solar | SS Completed, FIS Started, No IA | ABEI & INFRASTRUCTURE S.L. | Tap 138kV 1398 Radium - 6161 Paint Creek | Jones | WEST | 2022-04-25 | SOL | PV | 77.62 |  | 2019-05-10 | 2019-07-31 | 2020-01-28 |  |  | No |  |  | Not Required
21INR0314 | AQUAMARINE SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY & INFRASTRUCTURE LLC | 6150 Spur 138kV | Dickens | PANHANDLE | 2022-04-25 | SOL | PV | 151.69 | MW Size | 2019-05-10 | 2019-07-31 | 2020-01-27 |  |  | No |  |  | Not Required
21INR0320 | Ion Solar | SS Completed, FIS Started, No IA | GSE Group LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2021-12-01 | SOL | PV | 320 |  | 2019-05-17 | 2019-08-01 | 2020-01-28 |  |  | No |  |  | Not Required
21INR0323 | Spanish Crown | SS Completed, FIS Started, No IA | OCI Alamo 9 LLC | Tap 138kV 3420 Temple Pecan Creek - 3410 Lake Creek | Falls | NORTH | 2021-06-15 | SOL | PV | 100 |  | 2019-05-13 | 2019-07-31 | 2019-05-10 |  |  | No |  |  | Not Required
21INR0324 | Board Creek WP | SS Completed, FIS Started, No IA | Limestone Wind I, LLC | tap 345kV 68091 Navarro - 46020 Limestone c2 | Navarro | NORTH | 2021-10-15 | WIN | WT | 301 |  | 2019-04-24 | 2019-07-22 | 2019-11-05 |  |  | No |  |  | Not Required
21INR0325 | Sheep Creek Wind | SS Completed, FIS Started, No IA | Century Oak Wind Project, LLC | tap 345kV 68005 WShack - 68050 Romney | Callahan | WEST | 2022-11-15 | WIN | WT | 151.5 | MW Size | 2019-05-30 | 2019-08-15 | 2020-01-29 |  |  | No |  |  | Not Required
21INR0326 | Dove Run Solar | SS Completed, FIS Started, No IA | Dove Run Solar Project, LLC | tap 138kV 8510 Falfurrias - 8695 Crestonio | Duval | SOUTH | 2022-12-31 | SOL | PV | 101.25 | Proj Name | 2019-05-07 | 2019-07-23 | 2019-05-02 |  |  | No |  |  | Not Required
21INR0328 | RIO NOGALES AGP UPGRADE CT2 | SS Completed, FIS Started, No IA | CPS Energy | Existing gen 345kV Rio Nogales Power Project (# 5362) | Guadalupe | SOUTH | 2021-01-14 | GAS | CC | 19 |  | 2019-05-10 | 2019-08-02 | 2019-05-10 |  |  | No
21INR0334 | NIGHTFALL SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY & INFRASTRUCTURE LLC | Tap 138kV 8241 Razorback - 8234 Uvalde | Uvalde | SOUTH | 2022-04-25 | SOL | PV | 151.7 |  | 2019-05-10 | 2019-07-31 | 2020-01-24 |  |  | No |  |  | Not Required
21INR0340 | Estonian Solar | SS Completed, FIS Started, No IA | 249RD 8ME | 6834 Enloe Sw 138kV | Delta | NORTH | 2022-12-13 | SOL | PV | 102.38 |  | 2019-05-07 | 2019-07-19 | 2019-12-31 |  |  | No |  |  | Not Required
21INR0341 | Space City Solar | SS Started, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2021-12-01 | SOL | PV | 610.64 |  | 2019-11-01 |  | 2019-10-15 |  |  | No |  |  | Not Required
21INR0343 | Flag City | SS Completed, FIS Started, No IA | Flag City Solar Project, LLC | tap 138kV 5588 Red Bluff - 5546 Danevang c1 | Jackson | SOUTH | 2021-12-31 | SOL | PV | 150 |  | 2019-05-07 | 2019-07-29 | 2019-05-02 |  |  | No |  |  | Not Required
21INR0344 | Lunis Creek Solar 1 | SS Completed, FIS Started, No IA | Lunis Creek Solar Project, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2021-12-31 | SOL | PV | 202.5 |  | 2019-05-02 | 2019-07-03 | 2019-05-02 |  |  | No |  |  | Not Required
21INR0345 | Lunis Creek Storage 1 | SS Completed, FIS Started, No IA | Lunis Creek Solar Project, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2021-12-31 | OTH | BA | 81.2 |  | 2019-05-02 | 2019-07-03 | 2019-05-07 |  |  | No |  |  | Not Required
21INR0346 | Lunis Creek Solar 2 | SS Completed, FIS Started, No IA | Lunis Creek Solar Project II, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2021-12-31 | SOL | PV | 202.5 |  | 2019-05-02 | 2019-07-30 | 2019-05-02 |  |  | No |  |  | Not Required
21INR0347 | Lunis Creek Storage 2 | SS Completed, FIS Started, No IA | Lunis Creek Solar Project II, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2021-12-31 | OTH | BA | 81.2 |  | 2019-05-02 | 2019-07-30 | 2019-05-02 |  |  | No |  |  | Not Required
21INR0349 | Pearl Crescent Solar | SS Completed, FIS Started, No IA | EC&R Solar Development | 7640 Rock Island 138kV | Colorado | SOUTH | 2021-06-30 | SOL | PV | 208.35 |  | 2019-05-31 | 2019-08-26 | 2019-09-30 |  |  | No |  |  | Not Required
21INR0351 | 7V Solar | SS Completed, FIS Started, No IA | 7V Solar Ranch, LLC | tap 138kV 7248 Flatonia - 7274 Plum | Fayette | SOUTH | 2021-12-31 | SOL | PV | 240 |  | 2019-04-16 | 2019-07-03 | 2019-08-16 |  |  | No |  |  | Not Required
21INR0352 | YELLOW LIGHT SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY & INFRASTRUCTURE LLC | 6500 Live Oak 138kV | Schleicher | WEST | 2022-05-07 | SOL | PV | 150 | FIS Request | 2019-05-21 | 2019-08-13 | 2020-02-07 07:04 |  |  | No |  |  | Not Required
21INR0354 | Kochab Solar | SS Completed, FIS Started, No IA | Kochab Energy Project, LLC | 8241 Razorback 138kV | Uvalde | SOUTH | 2021-06-01 | SOL | PV | 204 |  | 2019-05-14 | 2019-08-10 | 2019-05-13 |  |  | No |  |  | Not Required
21INR0355 | Wilmeth Solar | SS Completed, FIS Started, No IA | Wilmeth Solar, LLC | tap 138kV 8212 Dilley - 8613 Big Well | Frio | SOUTH | 2022-10-31 | SOL | PV | 160 | FIS Request | 2019-06-17 | 2019-08-08 | 2020-02-05 |  |  | No |  |  | Not Required
21INR0357 | SP TX-12B Phase IV | SS Completed, FIS Started, No IA | CED Upton County Solar, LLC | 132943 SPTX12B 138kV | Upton | WEST | 2020-10-31 | OTH | BA | 25 |  | 2019-06-17 | 2019-09-09 | 2019-06-12 |  |  | No |  |  | Not Required
21INR0359 | Hickerson Solar | SS Completed, FIS Started, No IA | Belltown Power Texas | tap 345kV 68091 Navarro - 68040 Kopperl | Bosque | NORTH | 2021-11-01 | SOL | PV | 300 | FIS Request | 2019-05-29 | 2019-08-23 | 2020-02-19 |  |  | No |  |  | Not Required
21INR0362 | Oystercatcher Solar | SS Completed, FIS Started, No IA | Oysercatcher Solar LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2022-08-15 | SOL | PV | 244.55 | MW Size COD | 2019-05-30 | 2019-08-07 | 2019-12-20 |  |  | No |  |  | Not Required
21INR0364 | Gambit | SS Completed, FIS Started, No IA | Energy Storage Resources, LLC | 39560 TNAngleton 138kV | Brazoria | COASTAL | 2021-03-31 | OTH | BA | 100 |  | 2019-06-03 | 2019-08-28 | 2019-05-30 |  |  | No |  |  | Not Required
21INR0365 | Bat Cave | SS Completed, FIS Started, No IA | Energy Storage Resources, LLC | 76390 Fort Mason 138kV | Mason | SOUTH | 2021-03-31 | OTH | BA | 100 |  | 2019-05-31 | 2019-08-15 | 2019-05-30 |  |  | No |  |  | Not Required
21INR0366 | Brahman Solar | SS Completed, FIS Started, No IA | EC&R Development | tap 345kV 68040 Kopperl - 68091 Navarro | Navarro | NORTH | 2022-06-30 | SOL | PV | 144.01 | COD | 2019-07-08 | 2019-10-01 | 2019-11-04 |  |  | No |  |  | Not Required
21INR0368 | Eliza Solar | SS Completed, FIS Started, No IA | Ables Springs Solar, LLC | 12469 Ables Spring 138kV | Kaufman | NORTH | 2022-06-01 | SOL | PV | 150 | FIS Request | 2019-06-21 | 2019-08-30 | 2020-02-24 17:16 |  |  | No |  |  | Not Required
21INR0371 | Nabatoto Solar 1 | SS Completed, FIS Started, No IA | ConnectGen Operating LLC | tap 345kV 967 Gibbons Creek - 46020 Limestone. | Leon | NORTH | 2021-07-01 | SOL | PV | 300 |  | 2019-08-16 | 2019-11-05 | 2019-08-22 |  |  | No |  |  | Not Required
21INR0375 | Grizzly Ridge Solar | SS Completed, FIS Started, No IA | Diode Ventures | tap 69kV 273 Gustine - 258 Hamilton | Hamilton | NORTH | 2021-11-01 | SOL | PV | 100 |  | 2019-07-08 | 2019-10-01 | 2019-07-08 |  |  | No |  |  | Not Required
21INR0376 | Barranca Wind III | SS Completed, FIS Started, No IA | Barranca Wind Energy, LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2021-12-31 | WIN | WT | 205 |  | 2019-06-26 | 2019-09-23 | 2019-07-11 |  |  | No |  |  | Not Required
21INR0377 | Wagon Wheel Solar | SS Completed, FIS Started, No IA | Orion Power Generation, LLC | tap 138kV 60399 WEISS – 6340 Ballinger | Runnels | WEST | 2021-12-31 | SOL | PV | 120.63 |  | 2019-07-17 | 2019-10-08 | 2019-07-16 |  |  | No |  |  | Not Required
21INR0378 | Twin Mountain Solar | SS Completed, FIS Started, No IA | Orion Renewable Resources LLC | tap 138kV 1649 Hasse - 290 Shilo | Comanche | NORTH | 2021-12-31 | SOL | PV | 88.75 |  | 2019-07-29 | 2019-10-25 | 2019-07-19 |  |  | No |  |  | Not Required
21INR0379 | Ash Creek Solar | SS Completed, FIS Started, No IA | Orion Power Generation, LLC | 68090 SAM SW 345kV | Hill | NORTH | 2021-12-31 | SOL | PV | 433 |  | 2019-07-29 | 2019-10-25 | 2019-07-19 |  |  | No |  |  | Not Required
21INR0383 | Icarus Solar | SS Completed, FIS Started, No IA | AP Solar 5, LLC | Tap 138kV 1102 Judkins - 1103 Sandhills Tap | Ector | WEST | 2021-03-31 | SOL | PV | 152.64 |  | 2019-06-24 | 2019-09-06 | 2019-07-09 |  |  | No |  |  | Not Required
21INR0384 | Concho Valley Solar (Alternate POI) | SS Completed, FIS Started, No IA | MERIT SI, LLC | tap 69kV 6450 San Angelo Concho - 6527 San Angelo Lake Nasworthy | Tom Green | WEST | 2021-11-01 | SOL | PV | 150 |  | 2019-07-08 | 2019-12-18 | 2019-06-27 |  |  | No |  |  | Not Required
21INR0387 | Anchor Wind | SS Completed, FIS Started, No IA | Ranchland Wind Project,LLC | Tap 345kV 68005 Sam Switch Reactor - 68050 Romney | Eastland | NORTH | 2021-12-01 | WIN | WT | 300 |  | 2019-08-26 | 2019-11-12 | 2019-08-13 |  |  | No |  |  | Not Required
21INR0389 | Red-tailed Hawk Solar | SS Completed, FIS Started, No IA | AP Solar 6, LLC | tap 345kV 44200 Hillje - 44000 WA Parish | Wharton | SOUTH | 2021-12-31 | SOL | PV | 355.27 |  | 2019-07-08 | 2019-10-02 | 2019-07-01 |  |  | No |  |  | Not Required
21INR0391 | Grandslam Solar | SS Completed, FIS Started, No IA | Grandslam Solar | 5700 Miracle Lake 138kV | Atascosa | SOUTH | 2021-12-31 | SOL | PV | 228.23 |  | 2019-07-29 | 2019-10-30 | 2019-07-26 |  |  | No |  |  | Not Required
21INR0393 | Talitha Solar | SS Completed, FIS Started, No IA | Talitha Energy Project, LLC | 5660 Orange Grove 138kV | Jim Wells | SOUTH | 2021-06-01 | SOL | PV | 204 |  | 2019-07-12 | 2019-09-09 | 2019-07-08 |  |  | No |  |  | Not Required
21INR0394 | HERON1 | SS Completed, FIS Started, No IA | Alta Power LLC | tap 138kV 3340 Lufkin - 3346 Champion Tap, same as 20INR0211 | Angelina | NORTH | 2021-05-01 | GAS | GT | 150 |  | 2019-08-05 | 2019-10-31 | 2019-07-24 |  |  | No
21INR0395 | SunRay | SS Completed, FIS Started, No IA | OCI SunRay LLC | tap 138kV 8234 Uvalde - 8241 Razorback | Uvalde | SOUTH | 2021-06-15 | SOL | PV | 200 |  | 2019-07-17 | 2019-10-14 | 2019-07-15 |  |  | No |  |  | Not Required
21INR0397 | AltaRanch | SS Completed, FIS Started, No IA | Alta Power LLC | tap 138kV 42680 Garden Villa - 42762 Hall | Harris | HOUSTON | 2021-11-30 | GAS | GT | 300 |  | 2019-08-13 | 2019-11-05 | 2019-07-24 |  |  | No
21INR0398 | MykawaAlta | SS Completed, FIS Started, No IA | Alta Power LLC | tap 138kV 42741 Gulfgate - 43052 Pearland | Harris | HOUSTON | 2021-11-30 | GAS | GT | 300 |  | 2019-08-13 | 2019-11-05 | 2019-07-24 |  |  | No
21INR0403 | Cane Flats Solar | SS Completed, FIS Started, No IA | Cane Flats Solar Project, LLC | 78280 Bevo 138kV | Dimmit | SOUTH | 2022-12-31 | SOL | PV | 127.5 |  | 2019-07-29 | 2019-10-30 | 2019-07-17 |  |  | No |  |  | Not Required
21INR0404 | Cane Flats Storage | SS Completed, FIS Started, No IA | Cane Flats Solar Project, LLC | 78280 Bevo 138kV | Dimmit | SOUTH | 2022-12-31 | OTH | BA | 40.6 |  | 2019-07-29 | 2019-10-30 | 2019-07-17 |  |  | No |  |  | Not Required
21INR0405 | CullenAlta | SS Completed, FIS Started, No IA | ALTA POWER LLC | tap 138kV 42680 Garden Villas - 47210 Holmes | Harris | HOUSTON | 2021-11-30 | GAS | GT | 300 |  | 2019-08-13 | 2019-11-05 | 2019-07-24 |  |  | No
21INR0406 | Old 300 Solar Center | SS Completed, FIS Started, No IA | Lincoln Clean Energy Development | tap 345kV 44200 Hillje - 44000 WA Parish | Fort Bend | HOUSTON | 2021-12-31 | SOL | PV | 400 |  | 2019-08-01 | 2019-10-30 | 2019-07-31 |  |  | No |  |  | Not Required
21INR0411 | Galloway 2 Storage | SS Completed, FIS Started, No IA | 224WB 8ME LLC | tap 345kV 76009 Twin Buttes - 1444 Brown | Concho | WEST | 2021-12-01 | OTH | BA | 110 |  | 2019-08-05 | 2019-10-30 | 2019-07-30 |  |  | No |  |  | Not Required
21INR0412 | Dexter Storage | SS Completed, FIS Started, No IA | 241BB 8ME LLC | tap 345kV 60040 Bluff Creek - 6444 Red Creek | Runnels | WEST | 2022-06-01 | OTH | BA | 325 |  | 2019-08-05 | 2019-10-31 | 2019-07-30 |  |  | No |  |  | Not Required
21INR0413 | Big Star Solar | SS Completed, FIS Started, No IA | EC&R Solar Development, LLC | Tap 345kV 9074 Lytton - 9073 Holman | Bastrop | SOUTH | 2021-12-15 | SOL | PV | 220.61 |  | 2019-08-27 | 2019-11-08 | 2019-12-20 |  |  | No |  |  | Not Required
21INR0414 | Jayhawk Solar | SS Completed, FIS Started, No IA | Renewable Energy Ventures, LLC | tap 345kV 1030 Morgan - 76030 Gasconades | Mitchell | WEST | 2022-02-28 | SOL | PV | 101.5 |  | 2019-08-05 | 2019-10-31 | 2020-01-17 |  |  | No |  |  | Not Required
21INR0419 | Mockingbird Solar | SS Completed, FIS Started, No IA | Lincoln Clean Energy Development | tap 138kV 3522 Hillsboro - 3546 Whitney | Hill | NORTH | 2021-12-31 | SOL | PV | 200 |  | 2019-08-26 | 2019-11-11 | 2019-08-06 |  |  | No |  |  | Not Required
21INR0421 | Armadillo Solar | SS Completed, FIS Started, No IA | Lincoln Clean Energy Development | 3478 Navarro 138kV | Navarro | NORTH | 2021-12-31 | SOL | PV | 200 |  | 2019-08-28 | 2019-11-22 | 2019-08-28 |  |  | No |  |  | Not Required
21INR0428 | Nabatoto Solar 2 | SS Completed, FIS Started, No IA | ConnectGEN West LLC | tap 345kV 967 Gibbons Creek - 46020 Limestone. | Leon | NORTH | 2021-07-01 | SOL | PV | 500 |  | 2019-09-23 | 2019-12-10 | 2019-09-11 |  |  | No |  |  | Not Required
21INR0430 | Holstein 2 Energy Storage | SS Completed, FIS Started, No IA | 229HD 8me LLC | 11406 Central Bluff 345kV | Nolan | WEST | 2022-06-01 | OTH | BA | 102.5 | MW Size COD | 2019-08-26 | 2019-11-12 | 2019-08-16 |  |  | No |  |  | Not Required
21INR0431 | Galloway 2 Solar | SS Completed, FIS Started, IA | 224WB 8me LLC | tap 345kV 76009 Twin Buttes - 1444 Brown | Concho | WEST | 2021-06-01 | SOL | PV | 110 |  | 2019-08-28 | 2017-10-02 | 2019-08-28 |  | 2019-12-20 | No |  |  | Not Required
21INR0434 | Golinda Solar | SS Completed, FIS Started, No IA | OCI SOL LLC | Tap 138kV 3420 Temple Pecan Creek - 3410 Lake Creek | Falls | NORTH | 2021-06-15 | SOL | PV | 100 | Proj Name | 2019-09-23 | 2019-12-10 | 2019-09-03 |  |  | No |  |  | Not Required
21INR0445 | Brushy Creek Storage | SS Started, FIS Started, No IA | Brushy Creek Solar LLC | 6444 Red Creek 345kV | Tom Green | WEST | 2021-12-15 | OTH | BA | 25.14 |  | 2019-12-12 |  | 2019-12-05 |  |  | No |  |  | Not Required
21INR0446 | Knickerbocker Storage | SS Started, FIS Started, No IA | Knickerbocker Solar LLC | Tap 345kV 76003 Big Hill - 76009 Twin Buttes | Tom Green | WEST | 2022-11-01 | OTH | BA | 25 |  | 2019-12-19 |  | 2019-12-05 |  |  | No |  |  | Not Required
21INR0448 | Ennis-Tractebel (Config 1) Repower | SS Completed, FIS Started, No IA | Ennis Power Company LLC | 12241 Ennis Tractabel 138kV | Ellis | NORTH | 2021-06-15 | GAS | CC | 40.3 |  | 2019-11-01 | 2020-01-23 | 2019-10-16 |  |  | No
21INR0449 | Panther Creek III Repower | SS Completed, FIS Started, No IA | Panther Creek Wind Farm Three, LLC | 1058 Longshore 345kV | Howard | WEST | 2021-12-20 | WIN | WT | 15.96 |  | 2019-11-27 | 2020-02-14 | 2019-11-19 |  |  | No |  |  | Not Required
21INR0455 | Independence Trail Storage | SS Completed, FIS Started, No IA | KCE TX 16, LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2021-08-01 | OTH | BA | 100 |  | 2019-12-03 | 2020-02-24 | 2019-10-22 |  |  | No |  |  | Not Required
21INR0459 | DeCordova BESS addition | SS Completed, FIS Started, No IA | Luminant Generation Company LLC | 1891 Decordova 138kV | Hood | NORTH | 2021-02-28 | OTH | BA | 263.3 |  | 2019-11-18 | 2020-01-31 | 2019-10-29 |  |  | No |  |  | Not Required
21INR0460 | Republic Road Storage | SS Completed, FIS Started, No IA | KCE TX 11, LLC | 35 Hearne 138kV | Robertson | NORTH | 2021-06-01 | OTH | BA | 50 |  | 2019-12-06 | 2020-02-25 | 2019-11-14 |  |  | No |  |  | Not Required
21INR0461 | Cowboy Solar | SS Completed, FIS Started, No IA | AP Solar 1 LLC | 8241 Razorback 138kV | Medina | SOUTH | 2021-12-31 | SOL | PV | 207.69 |  | 2019-11-13 | 2020-01-23 | 2019-11-01 |  |  | No |  |  | Not Required
21INR0464 | Old 300 Storage | SS Completed, FIS Started, No IA | Old 300 Solar Center, LLC | tap 345kV 44200 Hillje - 44000 WA Parish | Fort Bend | HOUSTON | 2021-12-31 | OTH | BA | 50 |  | 2019-11-18 | 2020-01-28 | 2019-11-01 |  |  | No |  |  | Not Required
21INR0467 | Apogee Wind | SS Started, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345kV 6235 Mulberry - 6076 Foxtail | Haskell | WEST | 2021-12-31 | WIN | WT | 451.5 | COD | 2019-12-03 |  | 2019-11-18 |  |  | No |  |  | Not Required
21INR0473 | Vortex BESS | SS Started, FIS Started, No IA | Azure Sky Wind Project, LLC | loop 345kV 60515 Clear Crossing - 1421 WillowCr 345kV | Throckmorton | WEST | 2021-12-31 | OTH | BA | 120 |  | 2019-12-03 |  | 2019-11-18 |  |  | No |  |  | Not Required
21INR0474 | Anchor BESS | SS Completed, FIS Started, No IA | Ranchland Wind Project,LLC | Tap 345kV 68005 Sam Switch Reactor - 68050 Romney | Eastland | NORTH | 2021-12-01 | OTH | BA | 105 |  | 2019-12-03 | 2020-02-25 | 2019-11-18 |  |  | No |  |  | Not Required
21INR0476 | Azure Sky BESS | SS Started, FIS Started, No IA | Azure Sky Solar Project, LLC | 60515 Clear Crossing 345kV | Haskell | WEST | 2021-06-01 | OTH | BA | 78.3 | MW Size | 2019-12-12 |  | 2019-12-12 |  |  | No |  |  | Not Required
21INR0477 | Azure Sky Solar | SS Started, FIS Started, No IA | Azure Sky Solar Project, LLC | 60515 Clear Crossing 345kV | Haskell | WEST | 2021-06-01 | SOL | PV | 227.4 |  | 2019-12-12 |  | 2019-12-12 |  |  | No |  |  | Not Required
21INR0479 | Endurance Park Storage | SS Completed, FIS Started, No IA | KCE TX 13, LLC | 11306 Dermott 138kV | Scurry | WEST | 2021-08-01 | OTH | BA | 52.25 |  | 2019-11-27 | 2020-02-14 | 2019-11-22 |  |  | No |  |  | Not Required
21INR0480 | Juanita Hill Storage | SS Completed, FIS Started, No IA | KCE TX 20, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2021-12-01 | OTH | BA | 208.96 |  | 2019-11-27 | 2020-02-12 | 2019-11-22 |  |  | No |  |  | Not Required
21INR0481 | Lunar Solar | SS Started, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 5133 Elm Creek - 5915 STP | Wharton | SOUTH | 2021-12-01 | SOL | PV | 610.64 |  | 2019-12-17 |  | 2019-12-17 |  |  | No |  |  | Not Required
21INR0482 | Sisters Storage | SS Started, FIS Started, No IA | Oberon Solar | A new switching station within the Wolf Switch (#11010) – Moss Switch (#1018) / Odessa EHV Switch (#1029) Double-Circuit 345 kV Line | Ector | WEST | 2021-06-01 | OTH | BA | 504.44 |  | 2019-12-18 |  | 2019-12-18 |  |  | No |  |  | Not Required
21INR0486 | Pandora Solar | SS Started, FIS Started, No IA | Pandora | Tap 345kV 5915 STP - 5133 Elm Creek, c1 | Wilson | SOUTH | 2023-12-01 | SOL | PV | 252 |  | 2020-01-03 |  | 2020-01-03 |  |  | No |  |  | Not Required
21INR0487 | Nickel Prairie Storage | SS Started, FIS Started, No IA | KCE TX 17, LLC | 44600 Rosharon 138kV | Brazoria | COASTAL | 2021-12-31 | OTH | BA | 208.96 |  | 2019-12-23 |  | 2019-12-23 |  |  | No |  |  | Not Required
21INR0488 | Cottage Meadow Storage | SS Started, FIS Started, No IA | KCE TX 18, LLC | 8319 Rio Hondo - La Palma 138kV Line | Cameron | COASTAL | 2021-10-31 | OTH | BA | 208.96 |  | 2020-01-14 |  | 2020-01-14 |  |  | No |  |  | Not Required
21INR0490 | Delilah Solar 1A | SS Completed, FIS Started, No IA | Samson Solar Energy II LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 |  | 2020-01-13 | 2019-01-04 | 2020-01-13 |  |  | No |  |  | Not Required
21INR0491 | Delilah Solar 1B | SS Completed, FIS Started, No IA | Samson Solar Energy III LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2021-12-31 | SOL | PV | 250 |  | 2020-01-13 | 2019-01-04 | 2020-01-13 |  |  | No |  |  | Not Required
21INR0492 | Stockyard Grid | SS Started, FIS Started, No IA | Stockyard Grid, LLC | 2082 Hicks 138kV | Tarrant | NORTH | 2021-05-31 | OTH | BA | 100 | FIS Request | 2020-01-13 |  | 2020-01-13 |  |  | No |  |  | Not Required
21INR0493 | Ellis Solar | SS Started, FIS Started, No IA | Ellis Solar, LLC | tap 138kV 2300 COTTONWD_T - 2304 COTTONWD | Ellis | NORTH | 2021-11-01 | SOL | PV | 81 | FIS Request | 2020-01-30 |  | 2020-01-28 |  |  | No |  |  | Not Required
22INR0001 | Samson Solar 3 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2022-12-31 | SOL | PV | 200 |  |  | 2018-06-12 | 2018-10-23 |  |  | No | Not Required | Not Required | Not Required
22INR0202 | Delilah Solar 2 | SS Completed, FIS Started, No IA | Samson Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2022-06-30 | SOL | PV | 500 |  | 2018-11-20 | 2019-01-03 | 2019-05-03 |  |  | No | Not Required | Not Required | Not Required
22INR0203 | Delilah Solar 3 | SS Completed, FIS Started, No IA | Samson Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2022-12-31 | SOL | PV | 400 |  | 2018-11-20 | 2019-01-03 | 2019-05-03 |  |  | No | Not Required | Not Required | Not Required
22INR0205 | Sbranch Solar Project | SS Completed, FIS Started, No IA | CG Wharton County LLC | Tap 138kV 44190 East Bernard - 44130 Caney | Wharton | SOUTH | 2021-06-01 | SOL | PV | 154 | MW Size | 2019-01-03 | 2019-03-13 | 2019-03-29 |  |  | No | Not Required | Not Required | Not Required
22INR0209 | Crescent Solar | SS Completed, FIS Started, No IA | Crescent Solar | 6101 Riley 345kV | Wilbarger | WEST | 2022-12-31 | SOL | PV | 253.68 |  | 2019-01-17 | 2019-04-02 | 2019-09-20 |  |  | No | Not Required | Not Required | Not Required
22INR0211 | Schoolhouse Solar | SS Completed, FIS Started, No IA | Schoolhouse Solar, LLC | tap 345kV 7040 Austrop - 13429 Sandow | Williamson | SOUTH | 2022-06-01 | SOL | PV | 150.84 | MW Size | 2019-01-30 | 2019-04-09 | 2019-10-02 |  |  | No | Not Required | Not Required | Not Required
22INR0213 | Dexter Solar | SS Completed, FIS Started, No IA | 241BB 8me LLC | tap 345kV 60040 Bluff Creek - 6444 Red Creek | Runnels | WEST | 2022-06-01 | SOL | PV | 330.12 |  | 2019-03-05 | 2019-05-28 | 2019-02-18 |  |  | No | Not Required | Not Required | Not Required
22INR0215 | TEXAS SOLAR NOVA 3 | SS Completed, FIS Started, No IA | Texas Solar Nova 1, LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2023-01-31 | SOL | PV | 200.2 |  | 2019-06-24 | 2015-12-30 | 2019-06-19 |  |  | No |  |  | Not Required
22INR0218 | Greyhound Solar 2 | SS Completed, FIS Started, No IA | Greyhound Solar 2 | tap 345kV dbl ckt 11010 Wolf - 1018 Moss and 11008 Wolf - 11028 Odessa | Ector | WEST | 2022-12-15 | SOL | PV | 500 |  | 2019-05-14 | 2019-08-05 | 2019-05-10 |  |  | No |  |  | Not Required
22INR0223 | Eiffel Solar | SS Completed, FIS Started, No IA | Paris Farm Solar, LLC | Tap 138kV 1693 Paris Switch - 1769 Paris East Tap | Lamar | NORTH | 2022-03-25 | SOL | PV | 200 |  | 2019-07-11 | 2019-09-05 | 2019-07-11 |  |  | No |  |  | Not Required
22INR0224 | PetroLogistics PDH | SS Completed, FIS Started, No IA | PetroLogistics PDH LLC | 42100 Hudson POI 138kV | Brazoria | COASTAL | 2022-02-01 | GAS | ST | 60 |  | 2019-08-28 | 2019-11-22 | 2019-12-03 |  |  | No
22INR0225 | Lazy J Solar | SS Completed, FIS Started, No IA | ConnectGen Operating LLC | 47 Hilltop Lakes 138kV | Leon | NORTH | 2021-06-30 | SOL | PV | 300 |  | 2019-07-16 | 2019-09-17 | 2019-08-16 |  |  | No | Not Required |  | Not Required
22INR0236 | Point Mountain Solar | SS Completed, FIS Started, No IA | Hecate Energy Point Mountain LLC | 76000 North McCamey 345kV | Crane | WEST | 2022-06-01 | SOL | PV | 500 |  | 2019-08-26 | 2019-11-08 | 2019-08-19 |  |  | No |  |  | Not Required
22INR0237 | Dragan Solar | SS Completed, FIS Started, No IA | Hecate Comanche Solar LLC | 1440 Comanche 345kV | Comanche | NORTH | 2022-05-01 | SOL | PV | 411 |  | 2019-11-11 | 2020-02-17 | 2019-08-23 |  |  | No |  |  | Not Required
22INR0247 | Pradera Solar | SS Completed, FIS Started, No IA | Pradera Solar, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2022-12-31 | SOL | PV | 300 |  | 2019-10-15 | 2020-01-02 | 2019-10-24 |  |  | No |  |  | Not Required
22INR0251 | Shaula I Solar | SS Started, FIS Started, No IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5915 STP | DeWitt | SOUTH | 2022-01-31 | SOL | PV | 205.2 |  | 2019-12-03 |  | 2019-11-20 |  |  | No |  |  | Not Required
22INR0254 | Pisgah Ridge Solar | SS Completed, FIS Started, No IA | Duke Energy Renewables Solar, LLC | tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2022-12-31 | SOL | PV | 203.25 |  | 2019-11-01 | 2020-02-07 | 2019-10-21 |  |  | No |  |  | Not Required
22INR0257 | Corazon Solar Phase II | SS Started, FIS Started, No IA | BAYWA R.E. SOLAR PROJECTS | 80219 Lobo 345kV | Webb | SOUTH | 2022-05-31 | SOL | PV | 203.9 |  | 2019-12-19 |  | 2019-12-04 |  |  | No |  |  | Not Required
22INR0263 | Pisgah Ridge Storage | SS Started, FIS Started, No IA | Duke Energy Renewables Solar, LLC | tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2022-12-31 | OTH | BA | 50.6 |  | 2019-12-03 |  | 2019-11-20 |  |  | No |  |  | Not Required
22INR0267 | Shaula II Solar | SS Started, FIS Started, No IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5915 STP | DeWitt | SOUTH | 2022-05-09 | SOL | PV | 205.2 |  | 2019-12-18 |  | 2019-12-18 |  |  | No |  |  | Not Required
22INR0279 | Clutch City Solar | SS Started, FIS Started, No IA | HZ Solar I | 42960 Mustang Bayou – 42100 HUDSON 138 kV Line. | Brazoria | COASTAL | 2022-12-31 | SOL | PV | 204.17 | FIS Request | 2020-01-22 |  | 2020-02-11 11:32 |  |  | No |  |  | Not Required
22INR0280 | Roseland Storage | SS Started, FIS Started, No IA | Hecate Energy Roseland Storage 1 LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2022-12-31 | OTH | BA | 100 |  | 2019-12-26 |  | 2019-12-26 |  |  | No |  |  | Not Required
22INR0291 | Estonian Storage | SS Started, FIS Started, No IA | 249RD 8ME | 6834 Enloe Sw 138kV | Delta | NORTH | 2022-12-13 | OTH | BA | 100 | FIS Request | 2020-01-30 |  | 2020-01-28 |  |  | No |  |  | Not Required
23INR0007 | Outpost Solar | SS Completed, FIS Started, No IA | Hecate Energy Outpost Solar LLC | Tap 345kV 80219 Lobo - 5709 Fowlerton | Webb | SOUTH | 2023-05-01 | SOL | PV | 513.7 | MW Size | 2019-12-06 | 2020-02-25 | 2019-12-02 |  |  | No |  |  | Not Required
23INR0008 | Harley Hand Solar | SS Started, FIS Started, No IA | Hecate Energy Harley Hand LLC | 11420 Sweetwater East 345kV | Nolan | WEST | 2023-05-01 | SOL | PV | 513.7 |  | 2019-12-16 |  | 2019-12-06 |  |  | No |  |  | Not Required
23INR0009 | Shaula III Solar | SS Started, FIS Started, No IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5915 STP | DeWitt | SOUTH | 2023-01-31 | SOL | PV | 205.2 |  | 2019-12-18 |  | 2019-12-18 |  |  | No |  |  | Not Required
23INR0018 | Brangus Solar | SS Started, FIS Started, No IA | 245CK 8me LLC | 8252 Brackett 138kV | Kinney | SOUTH | 2023-06-01 | SOL | PV | 204.75 | FIS Request | 2019-12-27 |  | 2019-12-27 |  |  | No |  |  | Not Required
23INR0021 | Hornet Solar | SS Started, FIS Started, No IA | Hornet Solar LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala | Swisher | PANHANDLE | 2023-05-31 | SOL | PV | 500 | FIS Request | 2020-02-04 |  | 2020-02-04 |  |  | No |  |  | Not Required
23INR0022 | Brangus Storage | SS Started, FIS Started, No IA | 245CK 8me LLC | 8252 Brackett 138kV | Kinney | SOUTH | 2023-06-01 | OTH | BA | 200 |  | 2020-01-30 |  | 2020-01-28 |  |  | No |  |  | Not Required
25INR0002 | Barcelona TxHSR TPSS HN-4 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 45885 HocklyC - 46220 Peters | Harris | HOUSTON | 2026-04-30 | OTH | OT | 50 |  | 2019-01-30 | 2019-04-17 | 2019-08-09 |  |  | No | Not Required | Not Required
25INR0005 | Tokyo TxHSR TPSS EW-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2241 Ennis W - 2321 Waxahachie | Ellis | NORTH | 2026-04-30 | OTH | OT | 50 |  | 2019-01-30 | 2019-04-17 | 2019-08-09 |  |  | No | Not Required | Not Required
25INR0006 | Atlanta TxHSR TPSS DS-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2429 Watermill E - 3083 Wilmer | Dallas | NORTH | 2026-04-30 | OTH | OT | 50 |  | 2019-01-30 | 2019-04-17 | 2019-08-09 09:25 |  |  | No | Not Required | Not Required
26INR0001 | Turin TxHSR TPSS HN-6 | SS Started, FIS Started, No IA | Texas Central Rail Holdings, LLC | 8 Crutchfield 138kV | Grimes | NORTH | 2026-04-30 | OTH | OT | 50 |  |  |  | 2019-09-27 |  |  | No

## GINR Trends
GINR Trends
Reflects all projects for which a Security Screening Study has been requested.
Excludes projects that have a status of Suspended (status = INA).
Nameplate capacity will change across time due to additional projects, cancelations, expirations, adjustments from study results, and projects being placed into service.
| Year | Month | Total Projects | Project Count | [5 empty] | Project Capacity (MW)
|  |  |  | GINR milestones | [5 empty] | Fuel Type
|  |  |  | Initial Screening Study | Screening Study Complete | In Full Study | Completed Full Study | Signed Interconnection Agreement | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Battery | Other
| 2017 | Feb | 263 | 8 | 33 | 127 | 2 | 93 | 5 | 26512 | 14958 | 19016 | 0 | 240 | 0 | 30 | 0
| 2017 | Mar | 264 | 11 | 27 | 131 | 3 | 92 | 3 | 26593 | 15338 | 16750 | 0 | 240 | 0 | 0 | 0
| 2017 | Apr | 284 | 28 | 28 | 136 | 3 | 89 | 5 | 28470 | 17054 | 19316 | 0 | 240 | 0 | 0 | 0
| 2017 | May | 287 | 23 | 35 | 139 | 3 | 87 | 4 | 28259 | 18012 | 17620 | 0 | 240 | 0 | 0 | 0
| 2017 | Jun | 320 | 33 | 45 | 154 | 3 | 85 | 4 | 31835 | 22275 | 15656 | 0 | 240 | 0 | 30 | 0
| 2017 | Jul | 323 | 38 | 44 | 155 | 3 | 83 | 7 | 30279 | 21974 | 15656 | 0 | 0 | 0 | 30 | 0
| 2017 | Aug | 333 | 32 | 61 | 155 | 5 | 80 | 11 | 30068 | 23814 | 14357 | 0 | 0 | 0 | 0 | 0
| 2017 | Sep | 336 | 35 | 60 | 157 | 5 | 79 | 18 | 29915 | 24089 | 12001 | 0 | 0 | 0 | 0 | 0
| 2017 | Oct | 339 | 25 | 66 | 163 | 9 | 76 | 6 | 30090 | 24729 | 14201 | 0 | 0 | 0 | 0 | 0
| 2017 | Nov | 340 | 14 | 64 | 172 | 15 | 75 | 17 | 29882 | 24893 | 13747 | 0 | 0 | 0 | 0 | 0
| 2017 | Dec | 337 | 7 | 57 | 166 | 19 | 73 | 8 | 30198 | 24123 | 13969 | 0 | 0 | 0 | 30 | 0
| 2018 | Jan | 335 | 15 | 56 | 169 | 21 | 74 | 17 | 31420 | 22739 | 12768 | 0 | 0 | 0 | 0 | 0
| 2018 | Feb | 334 | 11 | 46 | 177 | 27 | 73 | 9 | 32258 | 22413 | 12727 | 0 | 0 | 0 | 0 | 0
| 2018 | Mar | 340 | 14 | 41 | 179 | 27 | 79 | 8 | 32897 | 23515 | 12065 | 0 | 0 | 0 | 0 | 0
| 2018 | Apr | 349 | 18 | 48 | 172 | 30 | 81 | 4 | 33427 | 24709 | 13484 | 0 | 0 | 0 | 0 | 0
| 2018 | May | 369 | 33 | 36 | 180 | 34 | 86 | 13 | 33799 | 27766 | 13442 | 0 | 0 | 0 | 200 | 0
| 2018 | Jun | 379 | 32 | 42 | 190 | 27 | 88 | 6 | 34376 | 28448 | 13674 | 0 | 0 | 0 | 522 | 0
| 2018 | Jul | 404 | 34 | 60 | 197 | 25 | 88 | 6 | 37708 | 30518 | 11668 | 0 | 0 | 0 | 522 | 0
| 2018 | Aug | 417 | 26 | 57 | 220 | 26 | 88 | 11 | 40851 | 29649 | 10814 | 0 | 0 | 0 | 2177 | 0
| 2018 | Sep | 426 | 30 | 67 | 212 | 26 | 91 | 15 | 40327.45 | 31655.3 | 8589.6 | 0 | 0 | 0 | 1889 | 0
| 2018 | Oct | 429 | 26 | 60 | 221 | 24 | 98 | 4 | 40237.59 | 32248.91 | 9073.6 | 0 | 0 | 0 | 1889 | 0
| 2018 | Nov | 443 | 23 | 59 | 235 | 26 | 100 | 7 | 40283.09 | 36682.4 | 7503.4 | 0 | 0 | 0 | 2048.35 | 0
| 2018 | Dec | 465 | 31 | 67 | 237 | 27 | 103 | 9 | 39596.45 | 40732.49 | 9249.4 | 0 | 0 | 0 | 2342.82 | 0
| 2019 | Jan | 489 | 43 | 69 | 244 | 26 | 107 | 20 | 39222.25 | 43504.49 | 10824.6 | 0 | 45 | 0 | 3147.38 | 0
| 2019 | Feb | 493 | 38 | 70 | 246 | 24 | 115 | 12 | 37419.7 | 47140.55 | 10528.6 | 0 | 45 | 0 | 3011.92 | 300
| 2019 | Mar | 505 | 42 | 68 | 247 | 33 | 115 | 18 | 35555.28 | 50999.9 | 10536.6 | 0 | 45 | 0 | 3265.2 | 441.8
| 2019 | Apr | 527 | 38 | 79 | 260 | 30 | 120 | 9 | 35644.28 | 54655.45 | 10102.6 | 0 | 45 | 0 | 3501.24 | 300
| 2019 | May | 563 | 60 | 68 | 279 | 26 | 130 | 11 | 35689.38 | 58579.47 | 9736.6 | 0 | 45 | 0 | 4120.39 | 300
| 2019 | Jun | 568 | 53 | 68 | 285 | 27 | 135 | 19 | 35739.18 | 59160.69 | 9739.6 | 0 | 0 | 0 | 3956.79 | 300
| 2019 | Jul | 586 | 36 | 87 | 295 | 25 | 143 | 11 | 36048.46 | 62356.08 | 9282.6 | 13 | 0 | 0 | 3970.39 | 300
| 2019 | Aug | 583 | 30 | 91 | 303 | 27 | 132 | 12 | 35275.72 | 64579.48 | 8206.8 | 13 | 0 | 0 | 4199.79 | 340.6
| 2019 | Sep | 575 | 30 | 91 | 298 | 26 | 130 | 15 | 34553.51 | 64343.73 | 7405.2 | 13 | 0 | 0 | 4452.39 | 300
| 2019 | Oct | 582 | 36 | 88 | 294 | 29 | 135 | 16 | 31683.23 | 64789.75 | 7445.5 | 13 | 0 | 0 | 5627.39 | 350
| 2019 | Nov | 589 | 38 | 89 | 300 | 29 | 133 | 11 | 32252.73 | 64664.04 | 5898 | 13 | 0 | 0 | 7214.39 | 350
| 2019 | Dec | 584 | 31 | 78 | 325 | 21 | 129 | 19 | 30173.96 | 67807.94 | 5607 | 13 | 0 | 0 | 7790.29 | 350
| 2020 | Jan | 613 | 47 | 78 | 333 | 23 | 132 | 3 | 30573.34 | 73636.8 | 5607 | 13 | 0 | 0 | 8965.62 | 558.96
| 2020 | Feb | 633 | 48 | 87 | 334 | 27 | 137 | 1 | 30514.72 | 77699.12 | 5507 | 13 | 0 | 0 | 9978.58 | 350
Note: Other contains all Fuel and Technology Types not in the Solar, Wind, Gas or Battery categories.

## data_GINR Trends_1 (hidden)
| # Signed Interconnect Agreement | # Completed Full Study | # in Full Study | # Screening Study Complete | # Initial Screening study | GW Capacity
Feb-19 | 115 | 24 | 246 | 70 | 38 | 98.1048
Mar-19 | 115 | 33 | 247 | 68 | 42 | 100.8368
Apr-19 | 120 | 30 | 260 | 79 | 38 | 103.9696
May-19 | 130 | 26 | 279 | 68 | 60 | 108.4708
Jun-19 | 135 | 27 | 285 | 68 | 53 | 108.8963
Jul-19 | 143 | 25 | 295 | 87 | 36 | 111.9705
Aug-19 | 132 | 27 | 303 | 91 | 30 | 112.6154
Sep-19 | 130 | 26 | 298 | 91 | 30 | 111.0678
Oct-19 | 135 | 29 | 294 | 88 | 36 | 109.9089
Nov-19 | 133 | 29 | 300 | 89 | 38 | 110.3922
Dec-19 | 129 | 21 | 325 | 78 | 31 | 112.1498
Jan-20 | 132 | 23 | 333 | 78 | 47 | 119.3547
Feb-20 | 137 | 27 | 334 | 87 | 48 | 124.0624

## data_GINR Trends_2 (hidden)
| Natural Gas | Nuclear | Coal | Wind | Solar | Biomass | Battery | Other | Total Project Count | Cancelled Project Count
Feb-19 | 10.5286 | 0 | 0.045 | 37.4197 | 47.1405 | 0 | 3.0119 | 0.3 | 493 | 12
Mar-19 | 10.5366 | 0 | 0.045 | 35.5553 | 50.9999 | 0 | 3.2652 | 0.4418 | 505 | 18
Apr-19 | 10.1026 | 0 | 0.045 | 35.6443 | 54.6555 | 0 | 3.5012 | 0.3 | 527 | 9
May-19 | 9.7366 | 0 | 0.045 | 35.6894 | 58.5795 | 0 | 4.1204 | 0.3 | 563 | 11
Jun-19 | 9.7396 | 0 | 0 | 35.7392 | 59.1607 | 0 | 3.9568 | 0.3 | 568 | 19
Jul-19 | 9.2826 | 0.013 | 0 | 36.0485 | 62.3561 | 0 | 3.9704 | 0.3 | 586 | 11
Aug-19 | 8.2068 | 0.013 | 0 | 35.2757 | 64.5795 | 0 | 4.1998 | 0.3406 | 583 | 12
Sep-19 | 7.4052 | 0.013 | 0 | 34.5535 | 64.3437 | 0 | 4.4524 | 0.3 | 575 | 15
Oct-19 | 7.4455 | 0.013 | 0 | 31.6832 | 64.7897 | 0 | 5.6274 | 0.35 | 582 | 16
Nov-19 | 5.898 | 0.013 | 0 | 32.2527 | 64.664 | 0 | 7.2144 | 0.35 | 589 | 11
Dec-19 | 5.607 | 0.013 | 0 | 30.174 | 67.8079 | 0 | 7.7903 | 0.35 | 584 | 19
Jan-20 | 5.607 | 0.013 | 0 | 30.5733 | 73.6368 | 0 | 8.9656 | 0.55896 | 613 | 3
Feb-20 | 5.507 | 0.013 | 0 | 30.5147 | 77.6991 | 0 | 9.9786 | 0.35 | 633 | 1

## data_GINR Trends_3 (hidden)
|  | Gas | Wind | Solar | Battery | Other
COASTAL | 2020 | 0.336 | 2.0828 | 0.27 |  | 0.013
| 2021 | 0.117 | 1.2522 | 3.3601 | 1.065
| 2022 | 0.06 | 0.159 | 1.1842 | 0.2
| 2023 |  |  | 0.25
HOUSTON | 2018 | 0.012
| 2020 | 0.5136
| 2021 | 2.2072 |  | 1.9466 | 0.05
| 2022 | 0.484 | 0.4 | 0.448
| 2025 |  |  |  |  | 0.05
| 2026 |  |  |  |  | 0.05
WEST | 2019 |  | 0
| 2020 | 0.083 | 6.2714 | 4.3711 | 0.15526
| 2021 |  | 7.7837 | 13.9284 | 1.7756
| 2022 |  | 1.354 | 9.8553 | 1.2935
| 2023 |  |  | 1.1639
NORTH | 2020 | 0.065 | 0.47288 | 0.82655 | 0.31012
| 2021 | 0.8403 | 2.7502 | 9.6696 | 1.112
| 2022 |  |  | 6.0883 | 0.7758
| 2023 | 0.3244 |  | 0.9839
| 2024 |  |  | 0.40058 | 0.1001
| 2025 |  |  |  |  | 0.1
| 2026 |  |  |  |  | 0.15
PANHANDLE | 2020 |  | 1.771 | 0.2408
| 2021 | 0.0815 | 0.8854 | 1.9792 | 0.1
| 2022 |  |  | 1.1194
| 2023 |  |  | 0.68
| 2024 |  |  | 0.345
SOUTH | 2020 | 0.064 | 1.0361 | 0.8218 | 0.1882
| 2021 | 0.319 | 2.983 | 12.2212 | 2.3422
| 2022 |  | 1.313 | 3.8346 | 0.3107
| 2023 |  |  | 1.7107 | 0.2

## Commissioning Update
Commissioning Approvals During February 2020
Commissioning Category | INR | Project Name | Fuel | County | Approval Date * | MW **
Commercial Operation Approved by ERCOT* | 18INR0035 | CityVict | Gas | Refugio | 2020-02-06 | 100
Synchronization Approved by ERCOT | 18INR0038 | Barrow Ranch | Wind | Andrews | 2020-02-26 | 160
Synchronization Approved by ERCOT | 20INR0262 | High Lonesome Wind Phase II | Wind | Crockett | 2020-02-28 | 50.6
Energization Approved by ERCOT | 19INR0014 | Formosa Increase | Gas | Calhoun | 2020-02-10 | 240
Energization Approved by ERCOT | 20INR0262 | High Lonesome Wind Phase II | Wind | Crockett | 2020-02-18 | 50.6
Energization Approved by ERCOT | 18INR0038 | Barrow Ranch | Wind | Andrews | 2020-02-06 | 160
Energization Approved by ERCOT | 15INR0064b | Harald (BearKat Wind B) | Wind | Glasscock | 2020-02-10 | 162.1
* For projects approved for commercial operations, the approval date is the Resource Commissioning Date defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a
Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative
values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.

## Inactive Projects
Inactive Projects as of end of February 2020*
INR | Project Name | Fuel | County | Inactive Date | MW **
20INR0025 | Spinel Solar | Solar | Medina | 2019-08-13 16:03 | 30
20INR0023 | Agate Solar | Solar | Ellis | 2019-08-13 16:05 | 60
20INR0024 | Fluorite Solar | Solar | Uvalde | 2019-08-19 18:20 | 25
16INR0044 | Halyard Wharton | Gas | Wharton | 2019-08-30 13:26 | 484
17INR0053 | HHGT repower Horse13+CallD | Wind | Taylor | 2019-08-30 13:32 | 44
13INR0025 | Northdraw Wind | Wind | Randall | 2019-08-30 13:38 | 150
16INR0014b | Cattleman Wind B | Wind | Castro | 2019-08-30 13:40 | 201.6
17INR0010 | FGE Texas 2 Gas | Gas | Mitchell | 2019-08-30 13:41 | 742.9
16INR0112 | Loma Pinta Wind | Wind | La Salle | 2019-08-30 13:44 | 200
16INR0014 | Cattleman Wind A | Wind | Castro | 2019-08-30 13:48 | 201.6
12INR0059b | HOVEY (Barilla Solar 1B) | Solar | Pecos | 2019-08-30 13:50 | 7.4
16INR0099 | Hecate Solar | Solar | Brewster | 2019-08-30 14:57 | 33
16INR0101 | Chatee Solar | Solar | Pecos | 2019-08-30 14:59 | 57
16INR0102 | Owego Solar | Solar | Pecos | 2019-08-30 15:01 | 74
17INR0043 | Vaquero 1 Wind | Wind | Zapata | 2019-08-30 15:02 | 400
13INR0010a | Mariah Del Este Wind | Wind | Parmer | 2019-09-09 10:19 | 152.5
14INR0030c | Panhandle Wind 3 | Wind | Carson | 2019-09-24 09:41 | 248
20INR0021 | Garnet Solar | Solar | Williamson | 2019-10-01 08:30 | 20
19INR0055 | Monte Cristo 2 Wind | Wind | Hidalgo | 2019-10-24 18:00 | 236.9
19INR0133 | La Joya II Wind | Wind | Hidalgo | 2019-10-24 18:05 | 236.9
17INR0036 | Grandview 4 Phase A Wind | Wind | Carson | 2019-10-31 10:59 | 200.5
15INR0034 | El Algodon Alto W | Wind | San Patricio | 2019-10-31 11:05 | 201
20INR0096 | Desert Rose Solar | Solar | Andrews | 2019-11-12 13:44 | 200
15INR0051 | Tierra Blanca W | Wind | Randall | 2019-11-12 14:45 | 200
18INR0009 | Eagle Pines Gas | Gas | Cherokee | 2019-11-19 10:20 | 1173.5
21INR0363 | Carol Battery | Other | Potter | 2019-11-25 16:33 | 168
13INR0038 | Wildrose Wind | Wind | Swisher | 2019-12-20 13:53 | 302.5
20INR0081 | Strategic Energy | Solar | Ellis | 2020-01-17 08:15 | 135
20INR0082 | Vision Solar | Solar | Navarro | 2020-01-22 08:38 | 127.2
21INR0361 | Becard Solar | Solar | Ellis | 2020-01-22 11:24 | 80
20INR0261 | Kellam Solar | Solar | Van Zandt | 2020-02-27 09:22 | 60
20INR0031 | Rippey Solar | Solar | Cooke | 2020-02-27 10:44 | 60
* Includes only those projects designated as Inactive by ERCOT or the project developer after the developer makes a Full Interconnection Study (FIS) request.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.

## Cancellation Update
Projects Cancelled by the Developer during February 2020*
INR | Project Name | Fuel | County | Cancel Date | MW **
20INR0055 | Vaquero 2 Wind | Wind | Zapata | 2020-02-27 14:58 | 201.6
* Includes only those projects cancelled after the developer makes a Full Interconnection Study (FIS) request.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.