## Contents
GINR Activity: Jul 01, 2021 to Jul 31, 2021
Table of Contents
Disclaimer and References | Disclaimer on the use of this report, and references to associated ERCOT Binding Documents ***Please read***
Acronyms | A list of the various acronyms used throughout the report
Summary | Tables that provide project aggregate counts and megawatt capacities by GINR phase and fuel type
Project Details | A table that lists project details; only includes projects for which a Full Interconnection Study has been requested
GINR Trends | Charts and tables that show historical and projected interconnection study trends
Commissioning Update | A table listing project commissioning approval milestones met for the month: energization, synchronization, and commercial operations approval
Inactive Projects | A table listing Inactive projects
Cancellation Update | A table listing the projects cancelled for the month
Time of Report Run: Aug 1, 2021 8:04:08 AM

## Disclaimer and References
Generator Interconnection Status Report - Disclaimer
FOR PLANNING PURPOSES ONLY
This ERCOT Working Paper has been prepared for specific ERCOT and Market Participant purposes, and has been
developed from data provided by Interconnecting Entities and Transmission Service Providers that has been entered into the online GINR system.
The data may contain errors or be obsolete depending on when the data was entered. ERCOT MAKES NO WARRANTY, EXPRESS
OR IMPLIED,INCLUDING ANY WARRANTY OF MERCHANTABILITY OR FITNESS FOR ANY PARTICULAR PURPOSE,
AND DISCLAIMS ANY AND ALL LIABILITY WITH RESPECT TO THE ACCURACY OF SAME OR THE FITNESS OR
APPROPRIATENESS OF SAME FOR ANY PARTICULAR USE. THIS ERCOT WORKING PAPER IS SUPPLIED WITH ALL FAULTS.
References
The links below provide more information on the ERCOT interconnection process:
http://www.ercot.com/mktrules/guides/planning/current
See the Resource Interconnection Handbook, available on ERCOT’s Resource Integration webpage:
http://www.ercot.com/services/rq/integration

## Acronyms
Acronyms
GINR = Generation Interconnection or Change Request
COD = Commercial Operation Date
SS = Security Screening Study
FIS = Full Interconnection Study
IA = Interconnection Agreement; can be either of the following:
- Standard Generation Interconnection Agreement (SGIA)
- Public financially binding agreement
- An official letter from a Municipally Owned Utility or Electric Cooperative signifying developer intent to build and operate generation facilities and
interconnect with the MOU or EC
POI = Point of lnterconnection
INR = Interconnection Request Number
TSP = Transmission Service Provider
NtP = Notice-to-Proceed given to the TSP for interconnection construction
CDR = Capacity, Demand and Reserves Report
SFS = Sufficient Financial Security provided to the TSP for construction of the interconnection facilities
QSA = Quarterly Stability Assessment
INA = Inactive status
PLN = Planned status
Fuel Types | Technology Types
BIO = Biomass | BA = Battery Energy Storage
COA = Coal | CC = Combined-Cycle
GAS = Gas | CE = Compressed Air Energy Storage
GEO = Geothermal | CP = Concentrated Solar Power
HYD = Hydrogen | EN = Energy Storage
NUC = Nuclear | FC = Fuel Cell
OIL = Fuel Oil | GT = Combustion (gas) Turbine, but not part of a Combined-Cycle
OTH = Other | HY = Hydroelectric Turbine
PET = Petcoke | IC = Internal Combustion Engine, eg. Reciprocating
SOL = Solar | OT = Other
WAT = Water | PV = Photovoltaic Solar
WIN = Wind | ST = Steam Turbine other than Combined-Cycle
WT = Wind Turbine

## Summary
Summary |  |  | Major GINR Milestone Status by Fuel/Technology Type, MW
Currently tracking 832 generation interconnection or change requests as of Jul 31, 2021 |  |  | Includes only those projects for which a Screening Study (SS) has been requested and are not Inactive.
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  |  | Fuel | Technology | SS Started | SS Started | SS Completed | SS Completed | SS Completed | SS Started | SS Started | SS Completed | SS Completed | SS Completed | TOTAL
Includes only those projects for which a Screening Study (SS) has been requested |  |  | Type | Type | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed
and are not Inactive |  |  |  |  | No IA | No IA | No IA | No IA | No IA | IA | IA | IA | IA | IA
Status of SS, FIS, and IA | Project Count | % of Total | Gas | Combined-Cycle |  | 18 | 1350 | 904 |  |  |  |  | 45 | 414 | 2731
SS Started, FIS Not Started, No IA | 40 | 4.808% | Gas | Combustion Turbine | 3159 |  | 450 | 582.68 | 548.46 |  |  |  | 312 | 1435 | 6487.14
SS Started, FIS Started, No IA | 26 | 3.125% | Gas | Internal Combustion Engine |  |  |  | 162.5 | [6 empty] | 162.5
SS Completed, FIS Not Started, No IA | 125 | 15.02% | Gas | Compressed Air Energy Storage |  |  | 324.4 | [7 empty] | 324.4
SS Completed, FIS Started, No IA | 369 | 44.35% | Gas | Steam Turbine |  |  | 680 | [6 empty] | 14 | 694
SS Completed, FIS Completed, No IA | 36 | 4.327% | Gas | Fuel Cell
SS Started, FIS Not Started, IA | 0 | 0% | Gas | Total gas | 3159 | 18 | 2804.4 | 1649.18 | 548.46 |  |  |  | 357 | 1863 | 10399.04
SS Started, FIS Started, IA | 0 | 0% | Coal
SS Completed, FIS Not Started, IA | 0 | 0% | Wind |  | 47.25 |  | 2264.6 | 5708.07 | 1349.5 |  |  |  | 3608.9 | 8955.55 | 21933.87
SS Completed, FIS Started, IA | 53 | 6.37% | Solar |  | 4502.49 | 1238.62 | 14676.75 | 44392.5 | 3748.32 |  |  |  | 7429.24 | 18480.23 | 94468.15
SS Completed, FIS Completed, IA | 183 | 22% | Biomass
Total Interconnection Requests | 832 |  | Other | Battery | 1911.69 | 2915.37 | 6349.44 | 20323.48 | 1781 |  |  |  | 881.89 | 2790.67 | 36953.54
Inactive (since last month) | 4 |  | Other* |  |  |  | 150 | 200 | [6 empty] | 350
Cancelled (since last month) | 4 |  | TOTAL |  | 9620.43 | 4171.99 | 26245.19 | 72273.23 | 7427.28 | 0 | 0 | 0 | 12277.03 | 32089.45 | 164104.6
Capacity, MW
Total Capacity Under Study | 164104.6
Interconnection Agreements Executed | 44366.48
Inactive (since last month) | 741.44
Inactive changed to Planned (since last month) | 169.12
Inactive changed to Cancelled (since last month) | 0
Cancelled (since last month) | 623
* Other includes petroleum coke (pet coke), hydroelectric, fuel oil, geothermal energy, other miscellaneous fuels reported by developers, and fuel cells that use fuels other than natural gas.

## Project Details
GINR Project Details
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study has been requested are included.
Excludes projects that have a status of Inactive (status = INA).
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GINR system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not been obtained or reported to ERCOT yet.
A developer may split a project into two or more additional projects with different INR numbers during the interconnection request process. Due to current RIOO interface limitations,
the new projects do not inherit certain milestone dates entered for the original project. As a result, dates may be blank even though the milestones have been met.
A “1-1-1900” date is used to signify that an actual date for a project milestone is not available. This typically occurs for project data migrated from the legacy GINR database to the RIOO system.
Project Attributes | [10 empty] | Changes from Last Report | GINR Project Milestone Dates
INR | Project Name | GINR Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | Economic Study Required | IA Signed |  | Air Permit | GHG Permit | Water Availability | Meets Planning | Meets All Planning |  | Construction Start | Construction End | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Change indicators: Proj Name, MW | Approval Date for | [6 empty] | Financial Security |  |  |  | Guide Section 6.9(1) | Guide Section 6.9 | Meets Planning Guide
[11 empty] | Size, COD, SFS/NtP, FIS Request, | Submission of Proof of | [6 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[11 empty] | Status Change INA-to-PLN | Site Control | [6 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[23 empty] | Models | Models
14INR0033 | Goodnight Wind | SS Completed, FIS Started, IA | FGE Power | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | PANHANDLE | 2022-07-23 | WIN | WT | 506.6 |  | 1899-12-31 | 2012-07-24 | 2012-09-19 | 2013-03-04 |  | No | 2018-03-07 | No | Not Required | Not Required | Not Required
15INR0034 | El Algodon Alto W | SS Completed, FIS Completed, IA | Eon | tap 345kV 8455 Lon Hill -8606 Goddard | San Patricio | COASTAL | 2021-12-15 | WIN | WT | 201 |  |  | 2013-02-04 | 2013-03-25 | 2013-08-16 | 2021-04-30 | No | 2020-04-02 | Yes | Not Required | Not Required | Not Required | 2020-04-17 | 2021-04-29 | 2021-04-30 | 2021-07-16
15INR0044 | Corazon Solar | SS Completed, FIS Completed, IA | Corazon Energy, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2021-08-31 | SOL | PV | 202.64 | COD | 1899-12-31 | 2013-09-06 | 2013-09-16 | 2013-08-20 | 2020-10-28 | No | 2020-01-09 | Yes | Not Required | Not Required | Not Required | 2020-07-11 | 2020-09-28 | 2020-10-30 |  |  | 2021-05-25 | 2021-06-23
15INR0059 | Emerald Grove Solar | SS Completed, FIS Completed, IA | Emerald Grove Solar, LLC | 76602 Horse Crossing 138kV | Pecos | WEST | 2022-04-22 | SOL | PV | 108 | COD | 2013-11-12 | 2013-11-13 | 2013-12-23 | 2013-11-12 | 2021-04-29 | No | 2017-12-04 | Yes | Not Required | Not Required | Not Required | 1899-12-31 | 2019-04-17 | 2021-04-29
15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2021-12-15 | WIN | WT | 162.1 | COD |  | 2013-11-27 | 2014-01-27 | 2014-04-15 | 2017-09-27 | No | 2018-05-30 | Yes | Not Required | Not Required | Not Required | 2018-05-30 | 2018-09-19 | 2019-01-22 |  |  | 2020-02-10 | 2020-05-12
15INR0090 | East Blackland Solar | SS Completed, FIS Completed, IA | East Blackland Holdings LLC | tap 138kV 7336 Gillie - 3650 Elgin | Travis | SOUTH | 2021-07-23 | SOL | PV | 144 |  | 2015-09-30 | 2015-04-28 | 2015-07-01 | 2015-09-30 | 2020-01-31 | No | 2017-06-13 | Yes | Not Required | Not Required | Not Required | 2020-04-28 | 2020-05-01 | 2020-05-01 |  |  | 2021-03-25 | 2021-04-13
16INR0033 | Hart Wind | SS Completed, FIS Started, IA | Orion | 23912 Ogallala 345kV | Castro | PANHANDLE | 2022-12-31 | WIN | WT | 151.5 |  | 2014-10-27 | 2014-02-10 | 2014-03-20 | 2014-10-27 |  | No | 2018-08-06 | No | Not Required | Not Required | Not Required
16INR0049 | Nazareth Solar | SS Completed, FIS Started, IA | Lendlease Energy | 23912 Ogallala 345kV | Castro | PANHANDLE | 2023-06-01 | SOL | PV | 201 |  | 2014-07-07 | 2014-06-19 | 2014-07-25 | 2014-07-01 |  | No | 2018-05-10 | No | Not Required | Not Required | Not Required
16INR0054 | NASA | SS Completed, FIS Completed, IA | NASA | 42970 Nasa 138kV | Harris | HOUSTON | 2021-09-01 | GAS | CC | 12 |  |  | 2015-03-10 | 2015-04-01 | 2015-03-10 | 2016-01-26 | No | 2016-10-27 | Yes | Not Required | Not Required |  | 2016-11-10 | 2018-09-28 | 2018-09-28 |  |  |  | 2017-11-27
16INR0081 | Mesteno Wind | SS Completed, FIS Completed, IA | Mesteno Windpower, LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2021-07-01 | WIN | WT | 201.6 |  | 1899-12-31 | 2014-12-30 | 2015-03-09 | 2014-12-30 | 2018-01-29 | No | 2018-04-25 | Yes | Not Required | Not Required | Not Required | 2018-04-25 | 2019-03-28 | 2019-04-01 |  |  | 2019-11-26 | 2019-12-12
16INR0085 | Priddy Wind | SS Completed, FIS Completed, IA | ENGIE North America | tap 345kV 1444 Brown – 3422 Killeen | Mills | NORTH | 2021-11-30 | WIN | WT | 302.4 |  | 2015-03-06 | 2015-01-14 | 2015-02-10 | 2015-03-06 | 2021-04-30 | No | 2020-08-13 | Yes | Not Required | Not Required | Not Required | 2021-03-29 | 2021-04-30 | 2021-04-30
16INR0086 | Cactus Flats Wind | SS Completed, FIS Completed, IA | Southern Power Company | tap 138kV 6480 SAPS - 6365 Yellow Jacket | Concho | WEST | 2021-10-31 | WIN | WT | 148.4 | COD |  | 2015-02-02 | 2015-03-27 | 2015-02-02 | 2017-10-20 | No | 2017-03-15 | Yes | Not Required | Not Required | Not Required | 1899-12-31 | 2018-09-05 | 2017-11-01 |  |  | 2018-05-24 | 2018-06-11
16INR0111 | Venado Wind | SS Completed, FIS Completed, IA | Las Lomas Wind Energy, LLC | 8957 Lopeno 138kV | Starr | SOUTH | 2021-08-31 | WIN | WT | 201.6 | COD |  | 2015-05-18 | 2015-06-25 | 2015-05-18 | 2020-05-01 | No | 2018-12-22 | Yes | Not Required | Not Required | Not Required | 2019-01-29 | 2020-05-01 | 2020-05-01 |  |  | 2020-11-17 | 2020-12-08
16INR0112 | Loma Pinta Wind | SS Completed, FIS Started, IA | Enerverse | 5705 Fowlerton 138kV | La Salle | SOUTH | 2022-09-01 | WIN | WT | 200 |  |  | 2015-05-18 | 2015-07-02 | 2015-05-18 |  | No | 2017-12-13 | No | Not Required | Not Required | Not Required
17INR0020a | RE Maplewood 2a Solar | SS Completed, FIS Completed, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2021-08-16 | SOL | PV | 222 |  | 2014-10-22 | 2014-10-17 | 2014-12-01 | 2014-10-22 | 2020-07-22 | No | 2019-05-06 | Yes | Not Required | Not Required | Not Required | 2020-08-04 | 2020-08-04 | 2020-08-04 |  |  | 2021-01-25 | 2021-04-16
17INR0020b | RE Maplewood 2b Solar | SS Completed, FIS Completed, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2021-07-29 | SOL | PV | 28 |  | 2014-10-22 | 2014-10-17 | 2014-12-01 | 2014-10-22 | 2020-07-22 | No | 2019-05-06 | Yes | Not Required | Not Required | Not Required | 2020-08-04 | 2020-08-04 | 2020-08-04 |  |  | 2021-01-25 | 2021-03-29
17INR0022 | MIRAGE | SS Completed, FIS Completed, IA | Net Power | 111161 Mirage 13.8kV | Harris | HOUSTON | 2022-03-07 | GAS | GT | 11 | COD |  | 2015-02-17 | 2015-05-01 | 2015-05-20 | 2016-09-13 | No | 2016-08-31 | Yes | 2015-05-08 | Not Required | 2017-10-12 | 2016-10-11 | 2018-09-28 | 2018-09-28 |  |  | 2017-02-06
17INR0025 | Reloj Del Sol Wind | SS Completed, FIS Completed, IA | EDP Renewables | 80220 Cenizo 345kV | Zapata | SOUTH | 2021-07-31 | WIN | WT | 209.4 | COD | 2015-09-14 | 2015-03-24 | 2015-05-05 | 2015-09-14 | 2020-04-26 | Yes | 2018-12-21 | Yes | Not Required | Not Required | Not Required | 2019-03-04 | 2020-05-01 | 2020-05-01 |  |  | 2020-12-21 | 2020-12-29
17INR0027b | Coyote Wind | SS Completed, FIS Completed, IA | Coyote Wind | 11305 Dermott 345kV | Scurry | WEST | 2021-08-03 | WIN | WT | 242.6 | COD |  | 2015-04-22 | 2015-05-22 | 2015-06-11 | 2020-01-31 | No | 2016-08-09 | Yes | Not Required | Not Required | Not Required | 2016-08-09 | 2020-01-28 | 2020-01-31 |  |  | 2020-08-24 | 2020-11-25
17INR0035 | Las Majadas Wind | SS Completed, FIS Completed, IA | EDF Renewable Energy | 8318 Rio Hondo 345kV plus 12.5mi gentie | Willacy | COASTAL | 2021-07-09 | WIN | WT | 272.6 | COD | 2015-12-09 | 2015-10-30 | 2015-12-14 | 2015-12-09 | 2020-01-30 | Yes | 2018-04-13 | Yes | Not Required | Not Required | Not Required | 2019-07-22 | 2020-01-30 | 2020-01-30 |  |  | 2020-09-02 | 2020-10-21
17INR0052 | Horse13 CallD repower | SS Completed, FIS Completed, IA | Nextera | 6216 Bluff Creek 138kV | Taylor | WEST | 2021-11-30 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2018-04-10 | No | 2019-05-22 | Yes | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13 |  |  |  | 2021-03-16
17INR0053 | HHGT repower Horse13+CallD | SS Completed, FIS Completed, IA | Nextera | 7046 Kendal 345kV | Taylor | WEST | 2019-11-01 | WIN | WT | 44 | Status Change INA-to-PLN | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2017-07-06 | No | 2009-06-26 | No | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13
17INR0054 | Capricorn I & III repower | SS Completed, FIS Completed, IA | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WEST | 2021-12-31 | WIN | WT | 32 |  | 2017-03-09 | 2017-03-09 | 2017-04-24 | 2017-03-09 | 2018-02-26 | No | 2006-11-14 | No | Not Required | Not Required | Not Required | 2021-02-28 | 2021-02-28 | 2021-02-28 |  |  |  | 2021-03-04
17INR0061 | Capricorn IV repower | SS Completed, FIS Completed, IA | Nextera | 76090 Divide 345kV | Sterling | WEST | 2021-12-31 | WIN | WT | 9 |  | 2017-08-23 | 2017-08-23 | 2017-09-15 | 2017-08-23 | 2018-02-06 | No | 2008-01-15 | No | Not Required | Not Required | Not Required | 2020-08-28 | 2020-08-28 | 2018-03-30 |  |  |  | 2020-08-19
17INR0068 | Sweetwater 2 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2021-07-31 | WIN | WT | 7.3 |  | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-11-10 | No | 2003-06-27 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2017-12-20
17INR0069 | Trent repower | SS Completed, FIS Completed, IA | Invenergy | 1338 Eskota 138kV | Nolan | WEST | 2021-09-30 | WIN | WT | 6.4 | COD | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-03-01 | No | 2018-10-19 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-05-09
17INR0070 | Desert Sky repower | SS Completed, FIS Completed, IA | Invenergy | two LCRA 138kV | Pecos | WEST | 2021-08-30 | WIN | WT | 7.2 | COD | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-02-06 | No | 2018-10-18 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-09-06
18INR0030 | Canyon Wind | SS Completed, FIS Started, IA | TriGlobal | 11319 ScurryCounty 138kV | Scurry | WEST | 2022-10-31 | WIN | WT | 201.8 | COD | 2017-03-02 | 2016-05-09 | 2016-07-22 | 2017-03-02 |  | No | 2018-09-20 | Yes | Not Required | Not Required | Not Required | 2020-02-07
18INR0031 | Maryneal Wind | SS Completed, FIS Completed, IA | Maryneal Windpower, LLC | 71050 Bitter Creek 345kV | Nolan | WEST | 2021-10-01 | WIN | WT | 182.4 |  | 2016-07-22 | 2016-05-26 | 2016-07-21 | 2016-07-22 | 2020-01-31 | No | 2020-01-31 | Yes | Not Required | Not Required | Not Required | 2020-01-31 | 2020-01-31 | 2020-01-31 |  |  | 2021-01-08 | 2021-04-23
18INR0033 | Oveja Wind | SS Completed, FIS Completed, IA | Invenergy | 76005 Schneeman Draw 345kV | Irion | WEST | 2021-07-15 | WIN | WT | 300 |  |  | 2016-07-12 | 2016-09-07 | 2016-10-21 | 2018-07-11 | No | 2018-07-24 | Yes | Not Required | Not Required | Not Required | 2018-07-30 | 2018-09-28 | 2018-07-30 |  |  | 2019-03-28 | 2019-04-05
18INR0038 | Barrow Ranch Wind | SS Completed, FIS Completed, IA | Engie | 1134 Littman 138kV | Andrews | WEST | 2021-06-15 | WIN | WT | 160 |  |  | 2016-10-02 | 2016-12-12 | 2017-06-19 | 2019-07-30 | No | 2018-06-26 | Yes | Not Required | Not Required | Not Required | 2018-09-04 | 2019-05-01 | 2019-08-01 |  |  | 2020-02-06 | 2020-02-26
18INR0043 | Edmondson Ranch Wind | SS Completed, FIS Completed, IA | Edmondson Ranch Wind Holdings, LLC | 59907 Bernoulli 345kV | Glasscock | WEST | 2022-10-31 | WIN | WT | 301.3 |  | 2017-02-01 | 2016-10-26 | 2016-12-22 | 2017-02-01 | 2018-01-30 | Yes | 2017-09-28 | Yes | Not Required | Not Required | Not Required | 2017-10-04 | 2018-09-05 | 2019-09-17
18INR0045 | Misae Solar | SS Completed, FIS Completed, IA | CIP | 60501 Tesla 345kV | Childress | PANHANDLE | 2021-06-25 | SOL | PV | 240.8 |  | 2016-10-20 | 2016-10-20 | 2017-01-06 | 2016-10-20 | 2019-01-28 | No | 2018-07-18 | Yes | Not Required | Not Required | Not Required | 2019-01-28 | 2019-01-30 | 2019-01-31 |  |  | 2019-08-21 | 2020-01-16
18INR0050 | Mustang Creek Solar | SS Completed, FIS Completed, IA | Sunchase Power | tap 138kV 5523 ETP - 78104 Ricebird new sub Galow | Jackson | SOUTH | 2022-10-31 | SOL | PV | 152.25 |  | 2017-03-22 | 2016-11-16 | 2016-12-20 | 2017-03-22 | 2020-08-25 | No | 2019-01-04 | Yes | Not Required | Not Required | Not Required | 2019-10-04 | 2020-03-11
18INR0053 | Fort Bend Solar | SS Completed, FIS Completed, IA | Fort Bend Solar LLC | tap 138kV 44541 Orchard - 44190 E Bernard | Fort Bend | HOUSTON | 2022-04-26 | SOL | PV | 240 |  |  | 2016-12-19 | 2017-02-15 | 2017-09-08 | 2021-04-21 | No | 2019-06-30 | Yes | Not Required | Not Required | Not Required | 2021-04-29 | 2021-04-30 | 2021-04-29
18INR0055 | Long Draw Solar | SS Completed, FIS Completed, IA | ENGIE | 59906 Long Draw 138kV | Borden | WEST | 2021-08-31 | SOL | PV | 226.73 | COD |  | 2016-12-15 | 2017-02-02 | 2017-02-28 | 2019-12-19 | No | 2018-08-16 | Yes | Not Required | Not Required | Not Required | 2019-02-28 | 2019-12-31 | 2020-01-31 |  |  | 2020-10-21 | 2020-11-20
18INR0058 | Texana Solar | SS Completed, FIS Completed, IA | Sunchase Power | tap 138kV 8102 El Campo - 8117 Ganado | Wharton | SOUTH | 2022-12-15 | SOL | PV | 152.34 |  | 2017-03-22 | 2016-12-23 | 2017-02-14 | 2017-03-22 | 2020-12-01 | No | 2021-06-30 | No | Not Required | Not Required | Not Required
18INR0060 | Brightside Solar | SS Completed, FIS Completed, IA | Brightside Solar, LLC | tap 69kV 8198 Beeville - 8400 Three River | Bee | SOUTH | 2021-12-14 | SOL | PV | 50 | COD |  | 2017-02-17 | 2017-03-20 | 2017-02-21 | 2020-10-28 | No | 2020-06-11 | Yes | Not Required | Not Required | Not Required | 2020-07-01 | 2020-10-29 | 2020-10-29
18INR0062 | Wagyu Solar | SS Completed, FIS Completed, IA | Cypress Creek Renewables | tap 138kV 43380 West Columbia - 44010 WA Parish | Brazoria | COASTAL | 2021-09-30 | SOL | PV | 120 |  | 2017-02-21 | 2017-02-22 | 2017-04-03 | 2017-02-22 | 2018-11-01 | No | 2019-06-03 | Yes | Not Required | Not Required | Not Required | 2019-10-23 | 2019-10-31 | 2019-10-31 |  |  | 2020-05-14 | 2020-05-22
18INR0064 | Silver Star repower | SS Completed, FIS Completed, IA | Silver Star I Power Partners, LLC | 1642 Flat Creek 138kV | Eastland | NORTH | 2021-08-13 | WIN | WT | -7.2 | COD | 2017-07-06 | 2017-04-05 | 2017-05-08 | 2017-07-06 | 2018-04-26 | No | 2018-10-16 | Yes | Not Required | Not Required | Not Required | 2019-10-23 | 2019-10-23 | 2019-10-28 |  |  |  | 2020-07-28
18INR0068 | Loraine Windpark Phase III | SS Completed, FIS Started, IA | Third Planet Wind Power | 181153 Lonewolf 345kV | Mitchell | WEST | 2023-05-10 | WIN | WT | 100 |  | 2017-10-20 | 2017-08-14 | 2017-10-05 | 2017-10-20 |  | No | 2018-04-10 | Yes | Not Required | Not Required | Not Required | 2018-04-12 | 2018-09-12 | 2018-05-01
18INR0069 | Indian Mesa repower | SS Completed, FIS Completed, IA | Nextera | 76019 Indian NWP 138kV | Pecos | WEST | 2021-12-31 | WIN | WT | 0 |  | 2018-05-22 | 2018-05-22 | 1899-12-31 | 2018-05-22 | 2018-10-03 | No | 2018-12-04 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2018-11-02
18INR0073 | Sweetwater 1 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2021-08-31 | WIN | WT | 3 | COD | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-12-27 | No | 2002-10-23 | No | Not Required | Not Required | Not Required
18INR0076 | Wolf Hollow 2 repower | SS Completed, FIS Started, No IA | Exelon | 1877 Mitchell Bend 345kV | Hood | NORTH | 2021-09-30 | GAS | CC | 44 |  | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 |  | No |  | No | Not Required | Not Required |  | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-19
18INR0077 | Colorado Bend 2 repower | SS Completed, FIS Started, IA | Exelon | 44040 Bailey 345kV | Wharton | SOUTH | 2021-09-30 | GAS | CC | 45 |  | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 |  | No | 2015-12-17 | No | Not Required | Not Required |  | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-19
18INR0079 | Woodward I repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2021-12-31 | WIN | WT | 0 |  | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2019-01-09 | No | 2018-12-12 | Yes | Not Required | Not Required | Not Required | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2019-11-07 | 2019-11-13
18INR0080 | Woodward 2 repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2021-12-31 | WIN | WT | 0 |  | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-11-27 | No | 2018-12-18 | Yes | Not Required | Not Required | Not Required | 2018-11-29 | 2018-11-29 | 2020-10-30 |  |  |  | 2018-12-19
19INR0001 | Texas Solar Nova | SS Completed, FIS Started, IA | Clearway Energy | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2023-01-31 | SOL | PV | 252.2 |  | 2016-07-06 | 2015-11-17 | 2015-12-30 | 2016-07-06 |  | No | 2019-07-01 | Yes | Not Required | Not Required | Not Required | 2019-11-08
19INR0014 | Formosa Increase | SS Completed, FIS Completed, IA | Formosa Plastics | 8126 Formosa 138kV | Calhoun | COASTAL | 2021-09-30 | GAS | CC | 240 |  |  | 2016-09-12 | 2016-11-14 | 2017-06-08 | 2019-02-20 | No | 2019-04-30 | Yes | 2017-04-17 | 2017-07-12 | 2019-02-22 | 2019-04-30 | 2019-04-30 | 2019-04-30 |  |  | 2020-02-10 | 2020-03-04
19INR0017 | Tri-County Solar | SS Completed, FIS Started, No IA | First Solar | tap 138kV 1027 Odessa - 1107 Monahans2T | Crane | WEST | 2022-04-30 | SOL | PV | 177.75 |  |  | 2016-10-10 | 2016-11-29 | 2017-02-22 |  | No |  | No | Not Required | Not Required | Not Required
19INR0022 | Monte Alto I | SS Completed, FIS Started, IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2022-12-31 | WIN | WT | 223.8 |  |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  | No | 2020-02-13 | No | Not Required | Not Required | Not Required
19INR0023 | Monte Alto 2 Wind | SS Completed, FIS Started, No IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2022-12-31 | WIN | WT | 236.9 |  |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  | No |  | No | Not Required | Not Required | Not Required
19INR0026 | Holstein 2 Solar | SS Completed, FIS Completed, No IA | 8minutenergy | 11406 Central Bluff 345kV | Nolan | WEST | 2022-10-04 | SOL | PV | 100 | COD | 2017-02-13 | 2016-12-21 | 2017-02-02 | 2017-02-13 | 2021-06-28 |  |  | No | Not Required | Not Required | Not Required
19INR0035 | Norton Solar | SS Completed, FIS Completed, IA | 8minutenergy | 60451 Garnet 138kV | Runnels | WEST | 2023-06-01 | SOL | PV | 125 |  | 2017-11-08 | 2017-03-06 | 2017-04-20 | 2017-11-08 | 2020-12-15 | No | 2019-06-20 | Yes | Not Required | Not Required | Not Required | 2019-07-12
19INR0041 | Myrtle Solar | SS Completed, FIS Started, IA | Myrtle Solar, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2022-12-15 | SOL | PV | 240 |  |  | 2017-03-15 | 2017-04-28 | 2017-05-09 |  |  | 2019-11-13 | Yes | Not Required | Not Required | Not Required | 2019-11-30 | 2020-05-06
19INR0042 | Long Point Solar | SS Completed, FIS Started, IA | SunChase Power | tap 138kV 44010 WAP - 42981 Nash98 | Brazoria | COASTAL | 2023-04-01 | SOL | PV | 101.25 | COD | 2017-11-02 | 2017-03-15 | 2017-04-20 | 2017-11-13 |  |  | 2019-10-24 | No | Not Required | Not Required | Not Required
19INR0044 | Lily Solar | SS Completed, FIS Completed, IA | Lily Solar, LLC | tap 138kV 6904 CombinRC - 6908 ScuryRC | Kaufman | NORTH | 2021-08-21 | SOL | PV | 147.63 | COD | 1899-12-31 | 2017-03-28 | 2017-04-28 | 2017-05-30 | 2020-07-28 | No | 2019-03-29 | Yes | Not Required | Not Required | Not Required | 2020-07-10 | 2020-07-14 | 2020-07-30 |  |  | 2021-04-08 | 2021-04-26
19INR0045 | Nebula Solar | SS Completed, FIS Completed, IA | Rayos Del Sol Solar Project, LLC | tap 138kV 8554 Mesquite - 80103 Rangerville | Cameron | COASTAL | 2021-12-31 | SOL | PV | 137.45 |  |  | 2017-03-28 | 2017-05-22 | 2017-03-28 | 2021-01-21 | No | 2018-11-06 | Yes | Not Required | Not Required | Not Required | 2019-01-23 | 2020-03-17 | 2021-01-29
19INR0052 | TG East Wind | SS Completed, FIS Completed, IA | Northrenew | 60722 Coulomb 345kV | Knox | WEST | 2021-12-07 | WIN | WT | 336 | COD | 2017-06-13 | 2017-04-04 | 2017-05-18 | 2017-06-13 | 2021-01-22 | No | 2018-10-22 | Yes | Not Required | Not Required | Not Required | 2020-04-28 | 2021-01-25 | 2021-01-25
19INR0056 | Chamon 2 | SS Completed, FIS Completed, IA | Castleman Power | 40260 Chamon 138kV | Harris | HOUSTON | 2021-10-01 | GAS | GT | 100 |  |  | 2017-04-24 | 2017-06-09 | 2017-07-06 | 2019-08-02 | No | 2019-09-20 | Yes | 2019-03-18 | Not Required | 2021-01-21 | 2021-02-01 | 2021-02-01 | 2021-02-01
19INR0057 | Old Bloomington Road | SS Completed, FIS Completed, IA | Castleman Power | 8143 Dupont 138kV | Victoria | SOUTH | 2021-08-31 | GAS | GT | 100 | COD |  | 2017-04-18 | 2017-05-22 | 2017-11-29 | 2019-03-06 | No | 2020-05-20 | Yes | 2018-08-10 | Not Required | 2020-07-11 | 2021-02-01 | 2021-02-01 | 2021-02-01
19INR0073 | Shakes Solar | SS Completed, FIS Completed, IA | Cypress Creek Renewables | 8283 Asherton 138kV | Zavala | SOUTH | 2022-08-01 | SOL | PV | 206 |  |  | 2017-05-03 | 2017-06-15 | 2017-05-03 | 2019-09-19 | No | 2018-10-26 | Yes | Not Required | Not Required | Not Required | 2019-03-04
19INR0075 | Horseshoe Bend Solar | SS Completed, FIS Started, No IA | Clenera | 1444 Brown 345kV | Brown | NORTH | 2023-05-31 | SOL | PV | 300 |  | 2018-02-09 | 2017-06-23 | 2017-08-07 | 2018-02-09 |  | No |  | No | Not Required | Not Required | Not Required
19INR0080 | Whitehorse Wind | SS Completed, FIS Completed, IA | MESQUITE STAR SPECIAL LLC | 68001 Clayton 345kV | Fisher | WEST | 2020-09-30 | WIN | WT | 418.9 |  |  | 2017-06-23 | 2017-08-07 | 2018-02-16 | 2019-01-22 | No | 2018-12-05 | Yes | Not Required | Not Required | Not Required | 2019-03-12 | 2019-04-02 | 2019-05-01 |  |  | 2019-12-12 | 2019-12-27
19INR0081 | Anson Solar 1 | SS Completed, FIS Completed, IA | Anson Solar Center, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2021-08-31 | SOL | PV | 201.53 | COD | 2018-02-15 | 2017-06-23 | 2017-08-07 | 2018-02-15 | 2020-03-27 | No | 2019-06-05 | Yes | Not Required | Not Required | Not Required | 2019-11-18 | 2020-04-15 | 2020-04-20 |  |  | 2020-12-03 | 2020-12-30
19INR0085 | Blue Jay Solar | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2022-01-31 | SOL | PV | 141.05 |  | 2018-02-15 | 2017-05-30 | 2017-08-11 | 2018-02-15 | 2021-04-26 | No | 2020-10-26 | Yes | Not Required | Not Required | Not Required | 2020-12-02 | 2021-04-26 | 2021-04-29
19INR0088 | Aragorn Solar | SS Completed, FIS Completed, IA | IP Aragorn, LLC | tap 138kV 71097 LCulberson - 7387 Kunitz (71097 LCRA Culberson 138kV) | Culberson | WEST | 2021-09-02 | SOL | PV | 187.2 |  | 2017-08-08 | 2017-05-30 | 2017-07-21 | 2017-08-08 | 2019-12-13 | No | 2018-05-31 | Yes | Not Required | Not Required | Not Required | 2020-03-17 | 2020-07-27 | 2020-07-27 |  |  | 2021-03-11
19INR0091 | Phoenix Solar | SS Completed, FIS Completed, IA | G.S.E. ONE LLC | 1808 Bonham 138kV | Fannin | NORTH | 2021-08-10 | SOL | PV | 82.3 |  | 2017-08-09 | 2017-06-23 | 2017-08-23 | 2017-08-09 | 2020-07-27 | No | 2019-10-22 | Yes | Not Required | Not Required | Not Required | 2020-05-06 | 2020-07-15 | 2020-07-16 |  |  | 2021-03-04 | 2021-04-13
19INR0093 | Solemio | SS Completed, FIS Started, IA | SOLEMIO LLC | tap 138kV 1698 Sulphur Springs - 1814 Sulspg | Hopkins | NORTH | 2023-01-10 | SOL | PV | 81.4 |  |  | 2017-06-23 | 2017-08-23 | 2017-08-09 |  | No | 2020-10-22 | No | Not Required | Not Required | Not Required
19INR0099a | Kontiki 1 Wind (ERIK) | SS Completed, FIS Started, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2023-03-01 | WIN | WT | 250.1 |  |  | 2017-06-22 | 2017-08-04 | 2017-09-28 |  | No | 2018-05-07 | Yes | Not Required | Not Required | Not Required | 2018-05-07
19INR0099b | Kontiki 2 Wind (ERNEST) | SS Completed, FIS Started, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2023-03-01 | WIN | WT | 250.1 |  |  | 2017-06-22 | 2017-08-04 | 2017-09-28 |  | No | 2018-05-07 | Yes | Not Required | Not Required | Not Required | 2018-05-07
19INR0100 | Prairie Hill Wind | SS Completed, FIS Completed, IA | Prairie Hill LLC | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | McLennan | NORTH | 2021-09-30 | WIN | WT | 300 | COD | 2017-06-19 | 2017-06-19 | 2017-08-11 | 2017-06-19 | 2020-04-03 | No | 2018-09-17 | Yes | Not Required | Not Required | Not Required | 2018-11-27 | 2020-04-21 | 2020-04-21 |  |  | 2020-10-19 | 2020-11-12
19INR0110 | Azalea Springs Solar | SS Completed, FIS Started, No IA | EDP Renewables | 3349 TMPLinla 138kV | Angelina | NORTH | 2023-06-30 | SOL | PV | 180 |  |  | 2017-07-26 | 2017-09-15 | 2018-03-15 |  | No |  | No | Not Required | Not Required | Not Required
19INR0112 | Cranel Wind | SS Completed, FIS Completed, IA | Eon | tap 345kV 8164 Coleto - 8455 Lon Hill | Refugio | COASTAL | 2021-09-30 | WIN | WT | 220 |  |  | 2017-09-12 | 2017-11-01 | 2017-11-30 | 2018-08-30 | No | 2018-10-12 | Yes | Not Required | Not Required | Not Required | 2018-10-12 | 2019-02-27 | 2019-03-26 |  |  | 2020-05-11 | 2020-05-19
19INR0117 | Roadrunner Crossing Wind | SS Completed, FIS Started, IA | RWE Renewables Development, LLC | 68051 Reata 345kV | Eastland | NORTH | 2022-12-15 | WIN | WT | 200.2 |  | 2018-03-01 | 2017-09-08 | 2017-11-07 | 2018-03-05 |  | No | 2020-04-17 | Yes | Not Required | Not Required | Not Required | 2020-09-17
19INR0120 | Sherbino II Wind repower | SS Completed, FIS Completed, IA | Sherbino II Wind Farm LLC | 38430 TN White Baker 138kV | Pecos | WEST | 2021-08-11 | WIN | WT | -18 | COD | 2017-09-21 | 2017-08-18 | 2017-09-28 | 2017-09-21 | 2018-12-04 | No | 2008-02-28 | Yes | Not Required | Not Required | Not Required | 2019-10-28 | 2019-10-28 | 2019-10-28 |  |  |  | 2020-06-09
19INR0121 | Galloway Solar | SS Completed, FIS Completed, IA | 8minutenergy | 7077 Amos Cr 345kV | Concho | WEST | 2021-10-10 | SOL | PV | 250 |  | 2017-08-25 | 2017-08-25 | 2017-10-02 | 2017-08-25 | 2020-07-30 | No | 2019-12-20 | Yes | Not Required | Not Required | Not Required | 2020-07-10 | 2020-07-23 | 2020-07-30 |  |  | 2021-01-25 | 2021-05-25
19INR0128 | White Mesa Wind | SS Completed, FIS Completed, IA | White Mesa Wind, LLC | 76005 Schneeman Draw 345kV | Crockett | WEST | 2021-11-30 | WIN | WT | 152.3 | COD |  | 2017-09-08 | 2017-11-20 | 2018-01-29 | 2019-04-24 | No | 2018-12-13 | Yes | Not Required | Not Required | Not Required | 2019-06-03 | 2020-10-29 | 2020-10-29 |  |  | 2021-04-28 | 2021-05-12
19INR0131 | Cutlass Solar | SS Completed, FIS Completed, IA | Cutlass Solar LLC | tap 345kV 44005 WAP - 44090 Cedar Creek | Fort Bend | HOUSTON | 2022-08-01 | SOL | PV | 300 |  | 2018-05-15 | 2017-09-21 | 2017-11-20 | 2018-05-15 | 2020-03-27 | No | 2020-09-23 | No | Not Required | Not Required | Not Required
19INR0134 | Cottonwood Bayou Solar | SS Completed, FIS Started, IA | Cottonwood Bayou Solar, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2023-01-01 | SOL | PV | 150 |  |  | 2017-09-22 | 2017-11-17 | 2018-02-15 |  | No | 2019-11-13 | No | Not Required | Not Required | Not Required
19INR0135 | Hill Solar | SS Completed, FIS Started, No IA | Sunchase Power | tap 69kV 3523 Hillsboro - 3532 Itasca | Hill | NORTH | 2022-12-15 | SOL | PV | 80 |  | 2018-05-10 | 2017-09-22 | 2017-11-17 | 2018-05-10 |  |  |  | No | Not Required | Not Required | Not Required
19INR0145 | Aquilla Lake Wind | SS Completed, FIS Completed, IA | Nextera | 68090 Sam Switch 345 kV | Hill | NORTH | 2021-11-12 | WIN | WT | 202 |  | 2018-07-18 | 2018-07-18 | 2018-09-20 | 2018-07-18 | 2020-01-17 | No | 2020-06-30 | Yes | Not Required | Not Required | Not Required | 2020-07-23 | 2021-01-07 | 2021-01-25
19INR0151 | Impact Solar | SS Completed, FIS Completed, IA | IMPACT SOLAR 1 LLC | tap 345kV 1695 Moses - 1692 Paris | Lamar | NORTH | 2021-07-15 | SOL | PV | 198.55 |  | 2018-05-04 | 2017-12-18 | 2018-02-01 | 2018-05-04 | 2019-09-19 | No | 2019-07-02 | Yes | Not Required | Not Required | Not Required | 2019-09-12 | 2019-10-28 | 2019-10-28 |  |  | 2020-08-10 | 2020-09-02
19INR0155 | Morrow Lake Solar | SS Completed, FIS Completed, IA | Sunchase Power | 5895 Pearsall 138kV | Frio | SOUTH | 2022-08-01 | SOL | PV | 204 |  | 2018-02-15 | 2017-12-05 | 2018-01-15 | 2018-02-15 | 2020-04-15 | No | 2019-08-29 | Yes | Not Required | Not Required | Not Required | 2019-11-18 | 2020-04-15
19INR0159 | Reiher Solar | SS Completed, FIS Started, No IA | EnergieKontor US Texas SP 7 LLC | 76597 Robb Sw 138kV | Upton | WEST | 2022-10-01 | SOL | PV | 120 |  | 2018-08-14 | 2018-01-29 | 2018-03-27 | 2018-08-14 |  | No |  | No | Not Required | Not Required | Not Required
19INR0163 | Sage Draw Wind | SS Completed, FIS Completed, IA | Lincoln Clean | 23924 Farmland 345kV | Lynn | WEST | 2020-12-31 | WIN | WT | 338 |  |  | 2016-03-14 | 2016-03-23 | 2016-04-22 | 2019-04-17 | No | 2018-01-03 | Yes | Not Required | Not Required | Not Required | 2019-03-22 | 2019-04-30 | 2019-04-30 |  |  | 2019-12-03 | 2019-12-12
19INR0165 | Barranca Wind | SS Completed, FIS Started, No IA | Lincoln Clean Energy, LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2024-01-30 | WIN | WT | 201.6 |  |  | 2018-05-09 | 2018-05-25 | 2018-02-28 |  |  |  | No | Not Required | Not Required | Not Required
19INR0169 | Sun Valley Solar | SS Completed, FIS Started, IA | Sun Valley Solar LLC | tap 345kV 68090 Sam Sw - 3405 Tradinghouse | Hill | NORTH | 2022-12-29 | SOL | PV | 252 |  | 2018-11-09 | 2018-03-02 | 2018-04-17 | 2018-07-19 |  | No | 2020-03-15 | No | Not Required | Not Required | Not Required
19INR0174 | Elbow Creek repower | SS Completed, FIS Completed, IA | NRG | 1058 Longshore 345kV | Howard | WEST | 2021-02-12 | WIN | WT | 0 |  | 2018-07-19 | 2018-05-04 | 2018-05-18 | 2018-07-19 | 2018-09-17 | No | 2007-11-30 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-27
19INR0175 | Shifting Gale Wind | SS Completed, FIS Started, No IA | SEAWAY WIND ENERGY LLC | 23912 Ogallala 345kV | Castro | PANHANDLE | 2024-12-31 | WIN | WT | 289 |  | 2018-12-06 | 2018-04-26 | 2018-06-12 | 2018-12-06 |  | No |  | No | Not Required | Not Required | Not Required
19INR0176 | Roughneck Storage | SS Completed, FIS Completed, IA | KCE TX 23, LLC | 43380 W Columbia 138kV | Brazoria | COASTAL | 2021-12-01 | OTH | BA | 50 | COD | 2018-11-07 | 2018-05-09 | 2018-07-13 | 2018-11-07 | 2020-10-23 | No | 2020-05-13 | Yes | Not Required | Not Required | Not Required | 2020-10-28 | 2020-10-28 | 2020-10-28 |  |  | 2021-06-15
19INR0177 | Crawfish | SS Completed, FIS Started, IA | Prarie Switch Wind, LLC | 8104 Lane City PM 138kV | Wharton | SOUTH | 2022-12-31 | WIN | WT | 153.3 | SFS/NtP |  | 2018-05-09 | 2018-06-21 | 2018-05-09 |  | No | 2021-07-06 | Yes | Not Required | Not Required | Not Required
19INR0179 | Barranca Wind II | SS Completed, FIS Started, No IA | Lincoln Clean Energy, LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2024-12-31 | WIN | WT | 201.6 |  |  | 2018-05-15 | 2018-06-01 | 2018-05-15 |  |  |  | No | Not Required | Not Required | Not Required
19INR0189 | SP TX-12B Phase III | SS Completed, FIS Started, No IA | ConEd Development | 76040 Castillo 138kV | Upton | WEST | 2022-12-01 | SOL | PV | 40 |  | 2019-01-29 | 2018-09-12 | 2018-10-03 |  |  | No |  | No | Not Required | Not Required | Not Required
19INR0203 | Angelo Solar | SS Completed, FIS Started, No IA | ANGELO SOLAR LLC | 76009 Twin Buttes 345kV | Tom Green | WEST | 2023-08-31 | SOL | PV | 195 | COD | 2019-01-17 | 2018-11-20 | 2019-02-05 | 2019-01-21 |  | No |  | No |  |  | Not Required
20INR0012 | Lueders Solar | SS Completed, FIS Started, No IA | Innovative Solar | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | WEST | 2022-05-15 | SOL | PV | 40 |  |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  | No |  | No | Not Required | Not Required | Not Required
20INR0013 | Basalt Solar | SS Completed, FIS Started, No IA | Innovative Solar | tap 138kV 8234 Uvalde - 8241 Razorback | Uvalde | SOUTH | 2022-05-15 | SOL | PV | 20 |  | 2017-10-20 | 2017-07-11 | 2017-09-01 | 2017-10-20 |  | No |  | No | Not Required | Not Required | Not Required
20INR0014 | Obsidian Solar | SS Completed, FIS Started, No IA | Innovative Solar | 6131 Padr 69kV | Cottle | WEST | 2022-05-15 | SOL | PV | 60 |  | 2017-10-20 | 2017-07-11 | 2017-08-28 | 2017-10-20 |  | No |  | No | Not Required | Not Required | Not Required
20INR0015 | Citrine Solar | SS Completed, FIS Started, No IA | Innovative Solar | Tap 138kV 6135 Paducah Clare - 6117 E Munday | Cottle | WEST | 2022-05-15 | SOL | PV | 45 |  | 2017-10-20 | 2017-07-11 | 2017-08-28 | 2017-10-20 |  | No |  | No | Not Required | Not Required | Not Required
20INR0016 | Opal Solar | SS Completed, FIS Completed, No IA | Innovative Solar | tap 345kV 60501 Tesla - 60500 Edith Clark | Hardeman | WEST | 2022-05-15 | SOL | PV | 45 |  |  | 2017-07-11 | 2017-08-28 | 2017-10-20 | 2021-07-01 | No |  | No | Not Required | Not Required | Not Required
20INR0019 | Trinity Hills Wind repower | SS Completed, FIS Completed, IA | Trinity Hills Wind Farm LLC | 17002 Garvey Rd 345kV | Young | WEST | 2021-08-13 | WIN | WT | -27 | COD | 2017-09-21 | 2017-07-20 | 2017-09-08 | 2017-09-21 | 2018-08-02 | No | 2018-10-17 | No | Not Required | Not Required | Not Required | 2019-10-29 | 2019-10-29 | 2019-10-29 |  |  |  | 2020-05-22
20INR0032 | Titan Solar | SS Completed, FIS Completed, IA | SE Titan, LLC | 71097 LCRA Culberson 138kV | Culberson | WEST | 2021-09-03 | SOL | PV | 270 |  | 2018-01-19 | 2017-10-12 | 2017-12-08 | 2018-01-19 | 2019-12-13 | No | 2019-02-04 | Yes | Not Required | Not Required | Not Required | 2020-03-17 | 2020-04-14 | 2020-04-14 |  |  | 2020-11-16 | 2021-03-18
20INR0033 | WILDWIND | SS Completed, FIS Completed, IA | Wildcat Creek | tap 345kV 1730 KrumW - 2373 Anna | Cooke | NORTH | 2021-08-18 | WIN | WT | 180.08 | COD | 2018-06-14 | 2017-10-18 | 2017-12-11 | 2018-06-14 | 2019-11-25 | No | 2020-02-21 | Yes | Not Required | Not Required | Not Required | 2020-03-23 | 2020-04-30 | 2020-04-30 |  |  | 2020-12-22 | 2021-02-10
20INR0035 | Angus Solar | SS Completed, FIS Completed, No IA | Cypress Creek Renewables | tap 138kV 177 Bosque - 181 Cayote | Bosque | NORTH | 2022-05-01 | SOL | PV | 113 |  | 2017-11-13 | 2017-11-13 | 2018-01-02 | 2017-11-13 | 2020-07-20 |  |  | No | Not Required | Not Required | Not Required
20INR0037 | Coniglio Solar | SS Completed, FIS Completed, IA | BT Coniglio Solar, LLC | 1809 Boistret 138kV | Fannin | NORTH | 2021-06-30 | SOL | PV | 125.68 |  | 2018-05-25 | 2017-11-28 | 2018-01-23 | 2018-05-25 | 2019-05-15 | No | 2019-08-03 | Yes | Not Required | Not Required | Not Required | 2020-03-30 | 2020-06-26 | 2020-06-26 |  |  | 2021-05-21 | 2021-06-15
20INR0038 | Red Mud Creek | SS Completed, FIS Started, No IA | Eon | tap 345kV 11318 Scurry - 59905 Faraday or 11318-59900 Long Draw | Borden | WEST | 2022-12-15 | WIN | WT | 201 |  |  | 2017-11-29 | 2018-02-05 | 2018-03-15 |  |  |  | No | Not Required | Not Required | Not Required
20INR0040 | Montgomery Ranch Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 60500 EdithC - 60700 Gauss | Foard | WEST | 2022-12-15 | WIN | WT | 200.2 |  | 2018-06-20 | 2017-12-18 | 2018-02-06 | 2018-06-20 |  |  |  | No | Not Required | Not Required | Not Required
20INR0044 | French Goldston Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV 1430 Graham - 1445 Burwick Switch | Young | WEST | 2023-12-15 | SOL | PV | 144 |  | 2018-09-19 | 2018-01-03 | 2018-03-12 | 2018-09-19 |  | No |  | No | Not Required | Not Required | Not Required
20INR0045 | Maverick Creek I Wind | SS Completed, FIS Completed, IA | Maverick Creek Wind, LLC | 7077 Amos Cr 345kV | Concho | WEST | 2021-09-30 | WIN | WT | 373.2 |  | 2018-03-05 | 2018-01-05 | 2018-02-20 | 2018-03-05 | 2019-04-03 | No | 2018-07-30 | Yes | Not Required | Not Required | Not Required | 2019-10-31 | 2019-10-31 | 2019-10-31 |  |  | 2020-08-11 | 2020-09-01
20INR0046 | Maverick Creek II Wind | SS Completed, FIS Completed, IA | Maverick Creek Wind, LLC | 7077 Amos Cr 345kV | Concho | WEST | 2021-09-30 | WIN | WT | 118.8 |  | 2018-03-05 | 2018-01-05 | 2018-02-20 | 2018-03-05 | 2020-04-30 | No | 2018-07-30 | Yes | Not Required | Not Required | Not Required | 2020-04-30 | 2020-05-01 | 2020-05-01 |  |  | 2020-09-29 | 2020-11-02
20INR0047 | Siete | SS Completed, FIS Started, No IA | Apex Clean | 80219 Lobo 345kV | Webb | SOUTH | 2023-10-31 | WIN | WT | 375.06 |  | 2019-06-13 | 2018-10-23 | 2018-12-11 | 2019-06-12 |  | No |  | No | Not Required | Not Required | Not Required
20INR0048 | Century Oak Wind | SS Completed, FIS Started, No IA | Engie | 6670 Putnam 138kV | Callahan | WEST | 2023-06-01 | WIN | WT | 126 |  | 2018-05-17 | 2018-01-29 | 2018-02-28 | 2018-05-17 |  |  |  | No | Not Required | Not Required | Not Required
20INR0050 | Castro Solar | SS Completed, FIS Completed, IA | Oaktree Development | 23912 Ogallala 345kV | Castro | PANHANDLE | 2022-09-15 | SOL | PV | 222.95 |  | 2018-05-15 | 2018-02-08 | 2018-04-09 | 2018-05-15 | 2020-04-23 | No | 2020-11-30 | No | Not Required | Not Required | Not Required
20INR0052 | Griffin Trail Wind | SS Completed, FIS Completed, IA | Innergex | 60506 AVOGADRO 345 kV | Knox | WEST | 2021-08-19 | WIN | WT | 225.6 | COD | 2018-11-07 | 2018-03-05 | 2018-05-04 | 2018-11-07 | 2020-10-28 | No | 2019-03-04 | Yes | Not Required | Not Required | Not Required | 2020-06-30 | 2020-10-28 | 2020-10-28 |  |  | 2021-06-10 | 2021-06-24
20INR0053 | Bravepost Solar | SS Completed, FIS Started, IA | Recurrent Energy | 6444 Red Creek 345kV | Tom Green | WEST | 2023-05-31 | SOL | PV | 200 |  | 2018-06-07 | 2018-02-22 | 2018-04-13 | 2018-06-07 |  |  | 2019-10-30 | Yes | Not Required | Not Required | Not Required | 2019-11-18
20INR0068 | Blackjack Creek Wind | SS Completed, FIS Completed, IA | Eon | 8624 Grissom 345kV | Bee | SOUTH | 2022-01-07 | WIN | WT | 240.5 | COD |  | 2018-04-02 | 2018-05-18 | 2018-11-07 | 2021-01-29 | No | 2019-10-24 | Yes | Not Required | Not Required | Not Required | 2019-11-24 | 2021-01-29 | 2021-01-29
20INR0069 | Danish Fields Solar | SS Completed, FIS Completed, IA | Danish Fields Solar, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2023-06-15 | SOL | PV | 201 |  |  | 2018-04-12 | 2018-06-05 | 2018-08-21 | 2020-01-21 | No | 2020-02-24 | Yes | Not Required | Not Required | Not Required | 2020-03-19
20INR0070 | Monte Bueno | SS Completed, FIS Started, No IA | Terra-Gen | tap 138kV 8392 Bates - 8394 Liston | Hidalgo | SOUTH | 2022-12-31 | WIN | WT | 129.2 |  |  | 2018-04-12 | 2018-05-30 | 2018-10-10 |  | No |  | No | Not Required | Not Required | Not Required
20INR0074 | Pitts Dudik Solar | SS Completed, FIS Completed, IA | Belltown Power | tap 138kV Hillsoboro 3522- Navarro 3478 | Hill | NORTH | 2022-05-30 | SOL | PV | 50 |  |  | 2018-04-12 | 2018-05-18 | 2018-05-25 | 2021-01-20 | No | 2021-05-10 | No | Not Required | Not Required | Not Required
20INR0075 | Howle Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV 1906 Venus - 68090 Sam Sw | Ellis | NORTH | 2023-05-31 | SOL | PV | 60 |  | 2018-08-09 | 2018-05-15 | 2018-07-02 | 2018-08-14 |  | No |  | No | Not Required | Not Required | Not Required
20INR0080 | Frye Solar | SS Completed, FIS Completed, IA | Hecate Energy | new 345kV sub Kress connecting both 23912 Ogallala - 23914 Tule Canyon circuits | Swisher | PANHANDLE | 2022-09-30 | SOL | PV | 514.1 |  | 2018-10-23 | 2018-05-17 | 2018-07-02 | 2018-11-20 | 2021-01-25 | No | 2021-02-06 | No | Not Required | Not Required | Not Required
20INR0081 | Strategic Solar 1 | SS Completed, FIS Completed, IA | Elm Branch Solar 1, LLC | tap 345kV 2435 Watermill - 68091 Navarro | Ellis | NORTH | 2021-11-05 | SOL | PV | 136.85 |  | 2018-07-18 | 2018-04-26 | 2018-06-05 | 2018-07-18 | 2020-09-25 | No | 2020-01-13 | Yes | Not Required | Not Required | Not Required | 2020-07-10 | 2020-09-29 | 2020-10-27 |  |  | 2021-07-20
20INR0082 | Vision Solar 1 | SS Completed, FIS Completed, IA | Briar Creek Solar 1, LLC | tap 345kV 2428 Watermill - 68091 Navarro | Navarro | NORTH | 2021-11-09 | SOL | PV | 129.24 |  | 2018-05-17 | 2018-04-26 | 2018-06-05 | 2018-05-17 | 2020-09-29 | No | 2020-01-13 | Yes | Not Required | Not Required | Not Required | 2020-10-27 | 2020-10-27 | 2020-10-27 |  |  | 2021-07-21
20INR0083 | Baird North Wind | SS Completed, FIS Completed, IA | BMP Wind, LLC | 68008 Latimer 345kV | Callahan | WEST | 2021-09-30 | WIN | WT | 350 |  |  | 2018-05-04 | 2018-06-12 | 2018-08-20 | 2020-10-30 | No | 2019-05-31 | Yes | Not Required | Not Required | Not Required | 2019-07-19 | 2020-10-30 | 2020-11-01
20INR0086 | Arroyo Solar | SS Completed, FIS Started, No IA | Belltown Power | 8318 Rio Hondo 345kV | Cameron | COASTAL | 2022-12-15 | SOL | PV | 180 |  | 2018-10-10 | 2018-05-09 | 2018-07-09 | 2018-10-10 |  | No |  | No | Not Required | Not Required | Not Required
20INR0088 | West Raymond (El Trueno) Wind | SS Completed, FIS Completed, IA | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2021-09-27 | WIN | WT | 239.8 | COD |  | 2018-05-14 | 2018-07-09 | 2018-07-06 | 2020-01-31 | No | 2019-05-20 | Yes | Not Required | Not Required | Not Required | 2019-06-06 | 2019-07-30 | 2020-01-31 |  |  | 2020-12-14 | 2021-01-20
20INR0089 | Chisholm Grid | SS Completed, FIS Completed, IA | Chisholm Grid, LLC | 2082 Hicks 138kV | Tarrant | NORTH | 2021-08-06 | OTH | BA | 101.7 | COD |  | 2018-05-14 | 2018-06-19 | 2018-05-14 | 2020-10-30 | No | 2019-08-16 | Yes | Not Required | Not Required | Not Required | 2019-11-04 | 2020-10-30 | 2020-10-30 |  |  | 2021-03-31 | 2021-06-15
20INR0091 | Fagus Solar Park | SS Completed, FIS Completed, IA | Misae Solar Park II | 60501 Tesla 345kV | Childress | PANHANDLE | 2023-07-31 | SOL | PV | 517.35 | Proj Name | 2018-05-15 | 2018-05-15 | 2018-07-06 | 2018-05-15 | 2021-06-14 | No | 2019-02-21 | Yes | Not Required | Not Required | Not Required | 2021-01-15
20INR0097 | El Suaz Ranch | SS Completed, FIS Started, IA | El Sauz Ranch Wind, LLC | 8601 Cebolla 345kV | Willacy | COASTAL | 2022-09-30 | WIN | WT | 301.5 |  | 2019-02-01 | 2018-06-19 | 2018-08-22 | 2019-01-31 |  |  | 2021-01-27 | Yes | Not Required | Not Required | Not Required
20INR0098 | Danciger Solar | SS Completed, FIS Completed, IA | Brazoria County Solar Project, LLC | tap 138kV 43120 Pledger - 43380 W Columbia | Brazoria | COASTAL | 2022-06-01 | SOL | PV | 203.2 |  | 2018-10-23 | 2018-06-06 | 2018-08-01 | 2018-10-23 | 2020-05-21 | No | 2020-03-20 | Yes | Not Required | Not Required | Not Required | 2020-11-09 | 2021-07-26
20INR0101 | Westoria Solar | SS Completed, FIS Completed, IA | Brazoria West Solar Project,LLC | tap 138kV 42410 Burke - 43380 W Columbia | Brazoria | COASTAL | 2021-12-31 | SOL | PV | 203.35 |  | 2018-10-23 | 2018-06-07 | 2018-07-30 | 2018-10-23 | 2020-06-01 | No | 2020-03-20 | Yes | Not Required | Not Required | Not Required | 2020-07-10 | 2021-04-30 | 2021-04-30
20INR0104 | GoodAlta GT | SS Completed, FIS Completed, IA | Alta Power | tap 138kV 3483 Goodloe - 3127 Trinidad SES | Navarro | NORTH | 2021-04-01 | GAS | GT | 150 |  |  | 2018-07-26 | 2018-09-18 | 2018-10-23 | 2019-08-29 | No | 2020-03-16 | No | 2019-06-13 | Not Required
20INR0106 | Wang Solar DCC | SS Completed, FIS Started, No IA | BT Yixin Solar, LLC | tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2022-12-31 | SOL | PV | 120 | Proj Name | 2018-08-29 | 2018-06-14 | 2018-08-13 | 2018-08-29 |  | No |  | No | Not Required | Not Required | Not Required
20INR0112 | Walstrom | SS Completed, FIS Completed, No IA | Castleman Power | 46220 Peters 138kV | Austin | SOUTH | 2022-05-30 | GAS | GT | 200 |  | 2018-11-29 | 2018-07-03 | 2018-09-18 | 2018-11-29 | 2021-07-14 | No |  | No | 2019-03-17 | 2019-03-17 | 2020-07-11
20INR0120 | Vortex Wind | SS Completed, FIS Completed, IA | AZURE SKY WIND PROJECT LLC | loop 345kV 60515 Clear Crossing - 1421 WillowCr 345kV | Throckmorton | WEST | 2022-04-13 | WIN | WT | 350.15 |  | 2019-02-28 | 2018-06-29 | 2018-08-27 | 2019-02-20 | 2021-04-30 | No | 2020-12-01 | Yes | Not Required | Not Required | Not Required | 2021-03-25 | 2021-04-29 | 2021-04-30
20INR0125 | Alwest | SS Completed, FIS Started, No IA | Castleman Power | 3114 Paltalco 138kV | Anderson | NORTH | 2023-01-01 | GAS | GT | 200 |  |  | 2018-07-18 | 2018-10-02 |  |  | No |  | No | 2019-03-13 | 2019-03-13 | 2020-07-11
20INR0127 | Milam Solar 1 | SS Completed, FIS Started, No IA | Sandow Lakes Ranch Solar I, LLC | tap one 345kV 7040 Austrop - 13429 Sandow line | Milam | SOUTH | 2024-05-16 | SOL | PV | 217.23 |  | 2019-08-13 | 2018-07-03 | 2018-09-18 |  |  |  |  | No | Not Required | Not Required | Not Required
20INR0128 | EK Tipton Solar | SS Completed, FIS Started, No IA | EnergieKontor US Texas SP 1 LLC | 6673 Musquiz 138kV | Reeves | WEST | 2023-12-29 | SOL | PV | 120 | COD | 2018-09-27 | 2018-09-27 | 2018-11-19 | 2018-09-27 |  | No |  | No | Not Required | Not Required | Not Required
20INR0129 | Foxtrot Wind | SS Completed, FIS Completed, IA | Lincoln Clean | AEP 8689 Tango 345kV station | Bee | SOUTH | 2022-04-01 | WIN | WT | 268.2 |  |  | 2018-07-26 | 2018-09-14 | 2018-07-26 | 2021-07-30 | No | 2020-05-05 | Yes | Not Required | Not Required | Not Required | 2021-07-30 | 2021-07-30 | 2021-07-30
20INR0130 | Plainview Solar | SS Completed, FIS Completed, IA | Hecate Energy | 44200 Hillje 345kV | Wharton | SOUTH | 2022-01-07 | SOL | PV | 514 |  | 2018-07-18 | 2018-10-10 | 2018-11-21 | 2018-10-10 | 2020-10-26 | No | 2020-05-29 | Yes | Not Required | Not Required | Not Required | 2020-10-07 | 2020-10-26 | 2020-10-26 |  |  | 2021-07-17 | 2021-07-26
20INR0134 | Half Moon Solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2023-12-29 | SOL | PV | 151.2 |  |  | 2018-09-13 | 2018-11-09 | 2018-11-06 |  | No |  | No | Not Required | Not Required | Not Required
20INR0135 | Half Moon Battery | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2023-12-29 | OTH | BA | 30.2 |  |  | 2018-09-13 | 2018-11-09 | 2018-11-06 |  | No |  | No | Not Required | Not Required | Not Required
20INR0142 | Ajax Wind | SS Completed, FIS Completed, IA | Lincoln Clean | tap 345kV 6101 Riley - 1422 Bowman | Wilbarger | WEST | 2021-08-13 | WIN | WT | 366.6 |  |  | 2018-08-14 | 2018-10-19 | 2018-08-14 | 2021-01-28 | No | 2020-07-14 | Yes | Not Required | Not Required | Not Required | 2020-08-03 | 2021-02-01 | 2021-02-01 |  |  | 2021-06-11 | 2021-06-16
20INR0143 | Soda Lake Solar 2 | SS Completed, FIS Started, IA | Arrington Solar | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | WEST | 2023-05-31 | SOL | PV | 202.99 |  | 2020-09-08 |  | 2016-11-08 | 2017-02-10 |  | No | 2018-08-20 | No | Not Required | Not Required | Not Required
20INR0155 | Peyton Creek Wind II | SS Completed, FIS Started, No IA | RWE Renewables Development, LLC | 42400 Refuge 345kV | Matagorda | COASTAL | 2022-12-15 | WIN | WT | 242 |  | 2019-01-30 | 2018-08-21 | 2018-11-02 | 2019-03-14 |  | No |  | No | Not Required | Not Required | Not Required
20INR0162 | Diamondback solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Starr | SOUTH | 2022-12-31 | SOL | PV | 201.6 |  |  | 2018-09-13 | 2018-12-06 | 2018-11-07 |  | No |  | No | Not Required | Not Required | Not Required
20INR0164 | BPL Files Solar | SS Completed, FIS Completed, IA | BPL Files Solar | tap 345kV 1907 Venus - 68090 Sam | Hill | NORTH | 2022-12-30 | SOL | PV | 175 |  |  | 2018-08-29 | 2018-11-08 | 2018-11-07 | 2021-01-20 | No | 2021-03-10 | No | Not Required | Not Required | Not Required
20INR0203 | Pine Forest Solar | SS Completed, FIS Completed, IA | Telios Corporation | Monticello Switch – Allen Switch 345 kV Line | Hopkins | NORTH | 2022-07-31 | SOL | PV | 284.29 |  | 2019-03-26 | 2018-10-04 | 2018-11-20 |  | 2020-06-16 | No | 2020-07-29 | No | Not Required | Not Required | Not Required
20INR0205 | Roseland Solar | SS Completed, FIS Started, IA | Enel Green Power Roseland Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2022-07-14 | SOL | PV | 513 |  | 2018-11-05 | 2018-11-30 | 2019-02-04 | 2019-02-04 |  | No | 2020-12-10 | No | Not Required | Not Required | Not Required
20INR0208 | Signal Solar | SS Completed, FIS Completed, IA | Adapture Renewables, Inc | tap 138kV 6879 Weiland - 6883 Quinlan N | Hunt | NORTH | 2023-05-30 | SOL | PV | 50 |  | 2019-04-02 | 2018-11-07 | 2018-12-20 |  | 2020-06-17 | No | 2020-10-23 | No | Not Required | Not Required | Not Required
20INR0210 | Hopkins Solar | SS Completed, FIS Started, IA | Hopkins Energy LLC | tap 345kV 1685 Farmersvl - 1695 Moses (Circuit #2) | Hopkins | NORTH | 2022-12-29 | SOL | PV | 252 |  | 2019-03-15 | 2018-11-20 | 2019-02-06 | 2019-03-14 |  | No | 2020-09-25 | No | Not Required | Not Required | Not Required
20INR0213 | Brushy Creek Solar | SS Completed, FIS Started, No IA | Brushy Creek Solar LLC | 6444 Red Creek 345kV | Tom Green | WEST | 2023-05-01 | SOL | PV | 177.09 |  | 2019-03-26 | 2019-01-07 | 2019-03-26 | 2019-03-05 |  | No |  | No | Not Required | Not Required | Not Required
20INR0214 | Noble Solar | SS Completed, FIS Completed, IA | BT Noble Solar, LLC | 1730 Krum 345kV | Denton | NORTH | 2022-05-30 | SOL | PV | 279 |  | 2018-11-06 | 2018-11-06 | 2018-12-17 | 2018-11-06 | 2021-05-28 | No | 2020-10-10 | Yes |  |  | Not Required
20INR0216 | Starr Solar Ranch | SS Completed, FIS Completed, IA | Starr Solar Ranch LLC | 8795 Roma 138kV | Starr | SOUTH | 2022-12-30 | SOL | PV | 135.99 |  | 2018-11-07 | 2018-11-07 | 2018-12-14 | 2018-11-07 | 2020-04-01 | No | 2020-10-01 | Yes | Not Required | Not Required | Not Required | 2020-11-19
20INR0217 | CAROL wind | SS Completed, FIS Completed, IA | Goat Mountain Renewables, LLC | 23906 AJ Swope 345kV | Potter | PANHANDLE | 2022-05-30 | WIN | WT | 169.2 |  | 2019-06-10 | 2018-12-06 | 2019-01-18 | 2019-06-05 | 2020-07-14 | No | 2020-09-11 | No | Not Required | Not Required | Not Required
20INR0219 | Eunice Solar | SS Completed, FIS Completed, IA | 2W Permian Solar LLC | tap 345kV 79650 Clearfork - 79630 Telephone Rd | Andrews | WEST | 2021-08-19 | SOL | PV | 426.7 | COD |  | 2018-12-06 | 2019-01-30 | 2018-11-30 | 2020-05-01 | No | 2019-12-11 | Yes | Not Required | Not Required | Not Required | 2020-02-06 | 2020-04-13 | 2020-05-01 |  |  | 2020-11-09 | 2020-12-01
20INR0221 | Braes Power Plant | SS Completed, FIS Completed, IA | ProEnergy Services LLC | 44650 Smithers 345kV | Fort Bend | HOUSTON | 2022-03-07 | GAS | GT | 408 |  | 2018-12-06 | 2018-12-06 | 2019-01-30 | 2018-12-01 | 2020-09-25 | No | 2020-11-18 | Yes | 2018-12-04 | Not Required | 2020-11-11 | 2021-04-01 | 2021-06-03 | 2021-07-27
20INR0222 | Tyson Nick Solar | SS Completed, FIS Completed, IA | Tyson Nick Solar Project, LLC | 1700 Toco 138kV | Lamar | NORTH | 2023-05-31 | SOL | PV | 90 | COD | 2019-02-25 | 2018-12-12 | 2019-02-15 | 2019-01-14 | 2020-07-06 | No | 2020-08-28 | No | Not Required | Not Required | Not Required
20INR0230 | Markum Solar | SS Completed, FIS Completed, IA | Glory Leasing LLC | 177 Bosque 138kV | McLennan | NORTH | 2022-06-30 | SOL | PV | 161 |  | 2018-12-17 | 2018-12-18 | 2019-01-03 | 2018-12-18 | 2020-08-24 |  | 2021-06-30 | No | Not Required | Not Required | Not Required
20INR0231 | Topaz Power Plant | SS Completed, FIS Completed, IA | Topaz Generating, LLC | 38745 TN Attwater 138kV | Galveston | HOUSTON | 2021-07-15 | GAS | GT | 510 |  | 2019-02-26 | 2019-02-01 | 2019-04-26 | 2019-02-22 | 2020-04-02 | No | 2020-04-28 | Yes | 2019-03-11 | Not Required | 2020-03-16 | 2020-07-10 | 2020-07-10 | 2020-07-10 |  |  | 2021-06-22 | 2021-06-24
20INR0232 | Mars Solar | SS Completed, FIS Started, No IA | ABEI ENERGY&INFRASTRUCTURE LLC | 6030 Childress 138kV | Childress | PANHANDLE | 2022-11-22 | SOL | PV | 52.75 |  | 2019-10-21 | 2019-02-06 | 2019-04-29 |  |  | No |  | No | Not Required | Not Required | Not Required
20INR0233 | Impala Flats Wind | SS Completed, FIS Started, No IA | Antelope Flats Wind, LLC | 79641 Farmland 345kV | Lynn | WEST | 2023-06-03 | WIN | WT | 282 |  | 2019-01-15 | 2019-01-11 | 2019-04-03 | 2018-12-21 |  |  |  | No |  |  | Not Required
20INR0235 | Knickerbocker Solar | SS Completed, FIS Started, No IA | Knickerbocker Solar LLC | Tap 345kV 76003 Big Hill - 76009 Twin Buttes | Tom Green | WEST | 2023-05-01 | SOL | PV | 202.87 |  | 2019-03-12 | 2019-01-07 | 2019-03-15 | 2019-03-04 |  |  |  | No | Not Required | Not Required | Not Required
20INR0236 | Old Hickory Solar | SS Completed, FIS Completed, IA | Old Hickory Solar LLC | tap 345kV 5133 Elmcreek - 5915 STP c2 | Jackson | SOUTH | 2023-05-31 | SOL | PV | 206 |  | 2019-08-27 | 2019-01-25 | 2019-04-19 | 2019-08-12 | 2020-10-09 |  | 2020-06-30 | Yes | Not Required | Not Required | Not Required | 2021-04-12
20INR0238 | Voyager Storage | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2022-12-01 | OTH | BA | 50.14 |  | 2019-04-30 | 2019-01-14 | 2019-03-19 | 2019-04-26 |  |  |  | No | Not Required | Not Required | Not Required
20INR0241 | Crowded Star Solar | SS Completed, FIS Started, IA | Jones City Solar, LLC | tap 345kV 68000 West Shack - 68001 Clayton c2 | Jones | WEST | 2023-10-23 | SOL | PV | 217.6 |  | 2019-05-23 | 2019-01-21 | 2019-04-19 | 2019-05-22 |  | No | 2019-12-17 | No | Not Required | Not Required | Not Required
20INR0242 | Anson Solar Center, Phase II | SS Completed, FIS Started, No IA | Anson Solar Center, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2023-12-29 | SOL | PV | 200 |  | 2018-02-15 | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  |  | No | Not Required | Not Required | Not Required
20INR0244 | Montezuma Storage | SS Completed, FIS Started, No IA | Montezuma Storage LLC | 7258 Glidden 138kV | Colorado | SOUTH | 2023-04-15 | OTH | BA | 47.12 |  | 2019-01-08 | 2019-01-15 | 2019-07-02 | 2019-03-15 |  |  |  | No | Not Required | Not Required | Not Required
20INR0245 | Volunteer Storage | SS Completed, FIS Started, No IA | Blackjack Storage LLC | 7216 Lockhart 138kV | Caldwell | SOUTH | 2023-04-15 | OTH | BA | 47.12 |  | 2019-01-16 | 2019-01-15 | 2019-07-02 | 2019-03-15 |  |  |  | No | Not Required | Not Required | Not Required
20INR0246 | Ryan Energy Storage | SS Completed, FIS Completed, IA | Ryan Storage LLC | 37580 TNPancake 69kV | Coryell | NORTH | 2023-01-09 | OTH | BA | 50 |  | 2019-02-08 | 2019-01-15 | 2019-04-05 | 2019-03-15 | 2020-08-16 | No | 2021-02-18 | No | Not Required | Not Required | Not Required
20INR0247 | Water Valley Wind Energy | SS Completed, FIS Started, No IA | Water Valley Wind Energy, LLC | 76011 Twin Buttes 138kV | Tom Green | WEST | 2021-12-31 | WIN | WT | 150 |  | 2019-01-10 | 2019-01-15 | 2019-03-29 | 2019-01-10 |  |  |  | No |  |  | Not Required
20INR0248 | Second Division Solar | SS Completed, FIS Completed, IA | TX Gulf Solar 1 LLC | tap 138kV 43120 Pledger - 43380 W Columbia c4 | Brazoria | COASTAL | 2022-12-31 | SOL | PV | 100 |  | 2019-08-06 | 2019-03-28 | 2019-06-18 | 2019-07-29 | 2020-02-06 | No | 2020-10-14 | No | Not Required | Not Required | Not Required
20INR0249 | Appaloosa Run Wind_ | SS Completed, FIS Started, IA | Appaloosa Run Wind, LLC | tap 138kV 60361 Santarita - 76032 NMcCamey | Upton | WEST | 2023-03-01 | WIN | WT | 175 |  | 2019-02-19 | 2019-01-17 | 2019-04-02 | 2019-01-15 |  |  | 2021-04-12 | Yes |  |  | Not Required
20INR0250 | Aguayo Wind | SS Completed, FIS Completed, No IA | Castle Gap Wind Power | tap 345kV 1444 Brown - 3422 Killeen | Mills | NORTH | 2022-12-31 | WIN | WT | 196 |  | 2019-02-05 | 2019-02-05 | 2019-05-03 | 2019-03-05 | 2020-07-13 |  |  | No |  |  | Not Required
20INR0255 | Dawn Solar | SS Completed, FIS Completed, IA | Renegade Renewable LLC | Tap 345kV 23910 Windmill - 23906 AJ Swope | Deaf Smith | PANHANDLE | 2022-09-30 | SOL | PV | 515.66 | COD | 2019-04-01 | 2019-02-26 | 2019-05-17 | 2019-02-07 | 2020-12-07 |  | 2021-01-04 | No | Not Required | Not Required | Not Required
20INR0256 | Aquilla Lake 2 Wind | SS Completed, FIS Completed, IA | NextEra Energy | 68090 Sam Switch 345 kV | Hill | NORTH | 2021-11-12 | WIN | WT | 100 |  | 2019-03-05 | 2019-05-23 | 2019-08-13 | 2019-02-28 | 2020-01-17 | No | 2020-06-30 | Yes | Not Required | Not Required | Not Required | 2020-07-23 | 2021-01-07 | 2021-01-25
20INR0263 | Myrtle Solar II | SS Completed, FIS Completed, IA | Myrtle Solar II, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2022-12-15 | SOL | PV | 100 |  |  | 2019-03-25 | 2019-06-03 | 2019-06-10 | 2020-07-19 | No | 2021-02-01 | No |  |  | Not Required
20INR0266 | Tres Bahias Solar | SS Completed, FIS Started, IA | Tres Bahias Solar Power LLC | 8140 Joslin 138kV | Calhoun | COASTAL | 2022-11-21 | SOL | PV | 195 | COD | 2019-06-03 | 2019-03-26 | 2019-06-11 | 2019-06-03 |  |  | 2020-08-07 | Yes | Not Required | Not Required | Not Required | 2020-10-07
20INR0268 | Pyron BESS II | SS Completed, FIS Started, No IA | Pyron Wind Farm, LLC | 1048 Tonkawas 345kV | Nolan | WEST | 2022-04-30 | OTH | BA | 30.2 | COD | 2019-09-09 | 2019-06-03 | 2019-08-30 | 2019-08-19 |  | No |  | No |  |  | Not Required
20INR0269 | Texas Solar Nova 2 | SS Completed, FIS Started, No IA | Texas Solar Nova 1, LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2022-09-30 | SOL | PV | 200.2 |  | 2016-07-06 | 2019-06-24 | 2015-12-30 | 2019-06-19 |  |  |  | No |  |  | Not Required
20INR0271 | Blue Hills Wind | SS Completed, FIS Started, No IA | GH America Energy LLC | Tap 138kV 8683 Comstock - 60389 Corral | Val Verde | WEST | 2023-10-01 | WIN | WT | 276 |  | 2019-12-03 | 2019-05-07 | 2019-07-26 | 2019-11-21 |  |  |  | No |  |  | Not Required
20INR0274 | SIXTY SIX Solar | SS Completed, FIS Completed, No IA | MERIT SI DEVELOPMENT, LLC | 38212 TNMONMNTDC0 138kv TNMP’s Monument Draw switching station | Winkler | WEST | 2022-08-01 | SOL | PV | 3.75 |  | 2019-05-31 | 2019-06-20 | 2019-09-17 | 2019-06-17 | 2021-06-25 |  |  | No | Not Required | Not Required | Not Required
20INR0276 | North Fork Energy Storage | SS Completed, FIS Completed, IA | North Fork Energy Storage | 7522 Andice 138kV | Williamson | SOUTH | 2021-08-03 | OTH | BA | 100.49 | COD | 2019-05-16 | 2019-05-17 | 2019-08-13 | 2019-05-14 | 2020-10-21 | No | 2020-04-28 | Yes | Not Required | Not Required | Not Required | 2020-07-11 | 2020-10-15 | 2020-10-21 |  |  | 2021-04-13 | 2021-04-16
20INR0279 | SHIELD Solar | SS Completed, FIS Started, No IA | MERIT SI DEVELOPMENT, LLC | 60441 OLLIN4A | Crane | WEST | 2022-08-01 | SOL | PV | 1.88 |  | 2019-05-31 | 2019-06-17 | 2019-09-05 | 2019-06-13 |  |  |  | No |  |  | Not Required
20INR0280 | High Lonesome BESS | SS Completed, FIS Completed, IA | High Lonesome Storage, LLC | tap 345kV 76002 Bakersfield - 7053 Noelke | Crockett | WEST | 2022-06-01 | OTH | BA | 51.06 |  | 2019-06-12 | 2019-06-11 | 2019-08-30 | 2019-06-07 | 2021-07-27 |  | 2020-08-26 | Yes | Not Required | Not Required | Not Required | 2021-06-09 | 2021-07-13 | 2021-07-30
20INR0281 | Queen BESS | SS Completed, FIS Completed, IA | Roadrunner Storage, LLC | 842 GPL King Mountain 345kV | Upton | WEST | 2022-05-31 | OTH | BA | 51.06 |  | 2019-06-04 | 2019-06-11 | 2019-10-23 | 2019-06-07 | 2021-07-29 |  | 2020-08-06 | Yes | Not Required | Not Required | Not Required | 2021-06-28 | 2021-07-30 | 2021-07-30
20INR0282 | Odessa-Ector Unit 2 (Block 2) Uprate Repower | SS Completed, FIS Completed, IA | LA FRONTERA HOLDINGS LLC | 1026 Odessa 345kV | Ector | WEST | 2020-12-31 | GAS | CC | 83 |  |  | 2019-06-18 | 2019-10-23 | 2019-06-14 | 2019-11-01 | No | 2019-11-01 | Yes | 2019-09-30 |  | 2019-10-01 | 2019-11-01 | 2019-11-01 | 2019-11-01
20INR0283 | CITY WEST Solar | SS Completed, FIS Started, No IA | MERIT SI DEVELOPMENT, LLC | 8507 Schottky 69kV | Live Oak | SOUTH | 2022-08-01 | SOL | PV | 4.13 |  | 2019-07-12 | 2019-07-15 | 2019-10-07 | 2019-07-12 |  |  |  | No |  |  | Not Required
20INR0286 | Wise County Power Repower (CT1, CT2) | SS Completed, FIS Completed, IA | Wise County Power Company LLC | 1421 Willow Creek 345kV | Wise | NORTH | 2020-12-01 | GAS | CC | 21 |  | 2019-07-15 | 2019-07-25 | 2019-10-23 | 2019-07-16 | 2019-10-23 | No | 2001-03-19 | Yes | 2020-01-21 | Not Required | 2019-12-05 | 2020-01-22 | 2020-01-27 | 2020-01-27
20INR0290 | River Valley Storage 1 | SS Completed, FIS Started, No IA | KCE TX 19, LLC | 3650 Elgin SS 138kV | Williamson | SOUTH | 2022-05-30 | OTH | BA | 51.9 |  | 2019-11-01 | 2019-10-15 | 2020-01-07 | 2019-10-21 |  | No |  | No |  |  | Not Required
20INR0291 | Silicon Hill Storage | SS Completed, FIS Completed, IA | KCE TX 12, LLC | 7336 L_GILLCR8_1Y 138kV | Travis | SOUTH | 2022-02-01 | OTH | BA | 104.62 | COD | 2019-10-29 | 2019-10-15 | 2020-01-07 | 2019-10-22 | 2020-10-30 |  | 2020-03-27 | Yes | Not Required | Not Required | Not Required | 2020-04-03 | 2020-07-10 | 2020-10-30
20INR0293 | River Valley Storage 2 | SS Completed, FIS Started, No IA | KCE TX 21, LLC | 3650 Elgin SS 138kV | Williamson | SOUTH | 2022-05-30 | OTH | BA | 51.9 |  | 2019-10-25 | 2019-10-15 | 2020-01-07 | 2019-10-21 |  | No |  | No |  |  | Not Required
20INR0294 | Lily Storage | SS Completed, FIS Completed, IA | Lily Solar, LLC | tap 138kV 6904 CombinRC - 6908 ScuryRC | Kaufman | NORTH | 2021-08-21 | OTH | BA | 51.74 | COD | 2020-01-30 | 2019-09-23 | 2019-12-11 | 2020-01-10 | 2020-07-28 |  | 2020-07-14 | Yes | Not Required | Not Required | Not Required | 2020-07-22 | 2020-07-27 | 2020-07-30 |  |  | 2021-04-26 | 2021-04-30
20INR0296 | Sand Bluff Wind Repower | SS Completed, FIS Started, No IA | RWE Renewables Development, LLC | 1333 McDonald 138kV | Glasscock | WEST | 2022-12-15 | WIN | WT | -0.58 | COD | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-19 |  | No |  | No |  |  | Not Required
21INR0005 | Hutt Wind | SS Completed, FIS Started, IA | Pioneer Natural Resources | tap 345kV 11028 Odessa - 59901 Grelton | Midland | WEST | 2022-11-16 | WIN | WT | 336 |  | 2019-04-02 | 2017-09-06 | 2019-08-19 | 2020-01-15 |  |  | 2020-05-26 | No | Not Required | Not Required | Not Required
21INR0006 | Giddings Wind | SS Completed, FIS Started, No IA | Pioneer Natural Resources | 71212 Upton 138kV | Upton | WEST | 2022-11-30 | WIN | WT | 240 |  | 2019-04-02 | 2017-09-06 | 2019-08-19 | 2020-01-15 |  |  |  | No | Not Required | Not Required | Not Required
21INR0008 | Cunningham Solar 1 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 |  |  | 2018-04-12 | 2018-06-12 | 2018-10-23 |  | No |  | No | Not Required | Not Required | Not Required
21INR0012 | Air Products GCA | SS Completed, FIS Completed, IA | Air Products | 39140 TNTxCityMain 69kV (Will be upgraded to 138kV) | Galveston | HOUSTON | 2022-05-15 | GAS | ST | 14 |  | 2019-03-26 | 2018-06-07 | 2018-08-01 |  | 2020-05-14 |  | 2020-08-07 | Yes | 2019-07-08 | Not Required | 2020-03-31 | 2020-08-21
21INR0016 | Danish Fields II Solar | SS Completed, FIS Completed, IA | Danish Fields Solar, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2023-06-15 | SOL | PV | 201 |  |  | 2018-05-10 | 2018-07-11 | 2018-08-21 | 2020-01-21 | No | 2020-02-24 | Yes | Not Required | Not Required | Not Required | 2020-03-23
21INR0017 | Danish Fields III Solar | SS Completed, FIS Completed, IA | Danish Fields Solar, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2023-06-15 | SOL | PV | 201 |  |  | 2018-05-10 | 2018-07-11 | 2018-08-27 | 2020-01-21 | No | 2020-02-24 | Yes | Not Required | Not Required | Not Required | 2020-03-19
21INR0019 | Zier Solar | SS Completed, FIS Started, IA | Cypress Creek Renewables | 78255 Pinto Creek 138kV | Kinney | SOUTH | 2022-09-01 | SOL | PV | 162.99 |  |  | 2018-05-24 | 2018-07-20 | 2018-05-24 |  | No | 2020-10-22 | No | Not Required | Not Required | Not Required
21INR0021 | Green Holly Solar | SS Completed, FIS Completed, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2023-03-31 | SOL | PV | 413.6 |  |  | 2018-07-11 | 2018-08-16 | 2018-07-11 | 2020-05-06 | No | 2020-05-19 | No | Not Required | Not Required | Not Required
21INR0022 | Red Holly Solar | SS Completed, FIS Completed, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2023-08-01 | SOL | PV | 260 |  |  | 2018-07-11 | 2018-08-16 | 2018-07-11 | 2020-04-02 | No | 2020-10-19 | No | Not Required | Not Required | Not Required
21INR0024 | Cunningham Solar 2 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 |  | 2018-10-23 |  | 2018-06-12 | 2018-10-23 |  | No |  | No | Not Required | Not Required | Not Required
21INR0027 | Zier Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 78255 Pinto Creek 138kV | Kinney | SOUTH | 2022-09-01 | OTH | BA | 20 |  |  | 2018-05-24 | 2018-07-20 | 2018-05-24 |  | No |  | No | Not Required | Not Required | Not Required
21INR0029 | Green Holly Storage | SS Completed, FIS Completed, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2023-08-01 | OTH | BA | 50 |  |  | 2018-07-11 | 2018-08-16 | 2018-07-11 | 2020-05-06 | No | 2020-10-19 | No | Not Required | Not Required | Not Required
21INR0031 | Indigo Solar | SS Completed, FIS Completed, IA | Innovative Solar, LLC | tap 345kV 68001 Clayton 345kV - 68000 WShack | Fisher | WEST | 2021-12-15 | SOL | PV | 125 |  | 2019-05-16 | 2018-09-27 | 2018-11-20 | 2019-05-15 | 2020-03-28 | No | 2020-10-15 | No | Not Required | Not Required | Not Required
21INR0033 | Red Holly Storage | SS Completed, FIS Completed, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2023-08-01 | OTH | BA | 50 |  |  | 2018-09-27 | 2018-12-18 | 2018-12-11 | 2020-04-02 | No | 2020-10-19 | No | Not Required | Not Required | Not Required
21INR0201 | Brandon | SS Completed, FIS Completed, IA | City of Lubbock, by and through Lubbock Power and Light (RE) | Brandon 12.47 kV | Lubbock | PANHANDLE | 2021-07-23 | GAS | GT | 21 |  | 2019-05-23 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2020-10-23 | No | 2020-10-30 | Yes | 2007-01-01 | Not Required | 2020-08-09 | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2021-07-02 | 2021-07-19
21INR0202 | R Massengale | SS Completed, FIS Completed, IA | City of Lubbock, by and through Lubbock Power and Light | Mackenzie 115 kV | Lubbock | PANHANDLE | 2021-07-23 | GAS | CC | 58 |  | 2020-08-10 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2020-10-23 | No | 2020-10-30 | Yes | 2000-01-03 | Not Required | 2020-08-09 | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2021-07-23 | 2021-07-26
21INR0203 | Eastbell Milam Solar | SS Completed, FIS Started, No IA | EDP RENEWABLES NORTH AMERICA LLC | tap 345kV 3687 Bell E - 39950 TNP One | Milam | SOUTH | 2023-06-30 | SOL | PV | 240 |  | 2019-04-23 | 2018-10-10 | 2018-12-09 | 2019-04-23 |  | No |  | No |  |  | Not Required
21INR0205 | Radian Solar | SS Completed, FIS Started, IA | IP Radian, LLC | 1444 Brown 345kV | Brown | NORTH | 2022-11-30 | SOL | PV | 374.4 |  |  | 2018-09-27 | 2018-11-08 | 2018-11-07 |  | No | 2021-01-08 | Yes | Not Required | Not Required | Not Required | 2021-02-02
21INR0207 | Quantum Solar | SS Completed, FIS Started, No IA | IP Quantum, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2023-05-31 | SOL | PV | 374.4 |  | 2018-11-07 | 2018-09-27 | 2018-11-14 | 2018-11-07 |  | No |  | No |  |  | Not Required
21INR0209 | Adamstown Storage | SS Completed, FIS Completed, No IA | Adams Creek Solar Project, LLC | tap 345kV 1730 West Krum - 6101 Riley | Wichita | WEST | 2023-09-30 | OTH | BA | 116.9 | MW Size | 2019-05-22 | 2018-11-20 | 2019-02-04 | 2019-05-16 | 2021-01-19 | No |  | No |  |  | Not Required
21INR0210 | Adamstown Solar | SS Completed, FIS Completed, No IA | Adams Creek Solar Project, LLC | tap 345kV 1730 West Krum - 6101 Riley | Wichita | WEST | 2023-09-30 | SOL | PV | 254.15 | MW Size | 2019-05-22 | 2018-11-20 | 2019-02-04 | 2019-05-16 | 2021-01-19 | No |  | No |  |  | Not Required
21INR0213 | Vancourt Solar | SS Completed, FIS Completed, IA | Rayos Del Sol Solar Project, LLC | 8656 Luna 138kV | Cameron | COASTAL | 2021-12-31 | SOL | PV | 45.73 |  | 2018-11-07 | 2018-11-07 | 2018-12-12 | 2018-11-07 | 2020-10-16 | No | 2020-06-11 | Yes | Not Required | Not Required | Not Required | 2020-06-29 | 2021-01-29 | 2021-01-29
21INR0220 | Maleza Solar | SS Completed, FIS Completed, IA | Brush Solar LLC | tap 345kV 44200 Hillje - 44040 Bailey | Wharton | SOUTH | 2023-06-01 | SOL | PV | 254.94 |  | 2019-03-07 | 2018-12-06 | 2019-01-18 |  | 2020-07-27 | No | 2021-01-27 | No |  |  | Not Required
21INR0221 | Samson Solar 1 | SS Completed, FIS Completed, IA | Samson Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2022-03-31 | SOL | PV | 250 |  | 2019-05-13 | 2018-11-20 | 2019-01-04 | 2019-05-03 | 2020-06-09 | No | 2020-08-26 | Yes | Not Required | Not Required | Not Required | 2020-08-26 | 2020-10-15 | 2020-10-26 |  |  | 2021-06-30
21INR0223 | Tulsita Solar | SS Completed, FIS Started, No IA | Tulsita Solar LLC | 8590 Tuleta 138kV | Goliad | SOUTH | 2023-06-01 | SOL | PV | 258.35 |  | 2019-05-20 | 2018-12-05 | 2019-02-21 | 2019-05-17 |  | No |  | No | Not Required | Not Required | Not Required
21INR0226 | Equinox Solar 1 | SS Completed, FIS Started, IA | Invenergy Solar Project Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2025-12-01 | SOL | PV | 200 | COD | 2019-08-14 | 2018-12-11 | 2019-01-23 | 2019-07-30 |  | No | 2021-01-28 | No | Not Required | Not Required | Not Required
21INR0227 | Equinox Solar 2 | SS Completed, FIS Started, No IA | Invenergy Solar Project Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2025-12-01 | SOL | PV | 200 | COD | 2019-08-05 | 2018-12-11 | 2019-01-31 | 2019-07-30 |  | No |  | No | Not Required | Not Required | Not Required
21INR0228 | Cottonwood Bayou Solar II | SS Completed, FIS Started, IA | Cottonwood Bayou Solar, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2023-01-01 | SOL | PV | 200 |  | 2019-06-19 | 2018-12-06 | 2019-02-07 | 2019-06-14 |  | No | 2021-03-25 | No | Not Required | Not Required | Not Required
21INR0229 | Prospero Solar II | SS Completed, FIS Completed, IA | Prospero Solar II, LLC | 11270 Dog House Switch 345 kv | Andrews | WEST | 2021-07-23 | SOL | PV | 250 | COD |  | 2018-11-29 | 2019-02-12 | 2018-12-10 | 2020-10-27 | No | 2020-01-17 | Yes | Not Required | Not Required | Not Required | 2020-05-27 | 2020-11-01 | 2020-11-01 |  |  | 2021-03-31 | 2021-04-16
21INR0233 | Taygete II Solar | SS Completed, FIS Completed, IA | Taygete Energy Project II, LLC | 60393 Pig Creek 138kV | Pecos | WEST | 2021-12-06 | SOL | PV | 203.8 |  | 2018-12-06 | 2018-12-17 | 2019-01-15 | 2018-12-13 | 2020-07-24 | No | 2019-03-27 | Yes | Not Required | Not Required | Not Required | 2019-05-06 | 2020-07-29 | 2020-07-30 |  |  | 2021-04-28
21INR0237 | Voyager Solar | SS Completed, FIS Completed, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2022-12-30 | SOL | PV | 303.9 | COD | 2019-04-30 | 2019-01-04 | 2019-03-19 | 2019-04-26 | 2021-04-05 |  |  | No | Not Required | Not Required | Not Required
21INR0240 | La Casa Wind | SS Completed, FIS Completed, No IA | EC&R development, LLC | New switching station: 138kV Graham Plant Switch - Breckenridge - Leon Switch | Stephens | NORTH | 2022-12-15 | WIN | WT | 201 |  |  | 2018-12-28 | 2019-03-12 | 2018-12-29 | 2021-07-08 |  |  | No | Not Required | Not Required | Not Required
21INR0244 | Madero Grid | SS Completed, FIS Completed, IA | Madero Grid, LLC | 8824 Railroad 138kV | Hidalgo | SOUTH | 2022-01-13 | OTH | BA | 101.52 |  | 2018-12-19 | 2018-12-20 | 2019-03-12 | 2018-12-19 | 2020-10-29 | No | 2019-12-06 | Yes | Not Required | Not Required | Not Required | 2020-01-13 | 2020-10-29 | 2020-10-30
21INR0247 | Anson Solar Center, Phase III | SS Completed, FIS Started, No IA | Anson Solar Center, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2024-06-03 | SOL | PV | 200 |  | 2018-02-15 | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  |  | No |  |  | Not Required
21INR0253 | Ulysses Solar | SS Completed, FIS Started, No IA | Ulysses Solar LLC | tap 345kV 6444 Red Creek - 60040 Bluff Creek | Coke | WEST | 2023-06-30 | SOL | PV | 150 |  | 2019-05-14 | 2019-01-25 | 2019-04-05 | 2019-05-10 |  |  |  | No | Not Required | Not Required | Not Required
21INR0254 | Blue Cut Solar | SS Completed, FIS Started, No IA | Blue Cut Solar, LLC | tap 138kV 7064 Lampasas - 260 Kempner | Lampasas | NORTH | 2023-06-01 | SOL | PV | 150 |  | 2019-10-10 | 2019-01-30 | 2019-04-12 | 2019-10-08 |  |  |  | No | Not Required | Not Required | Not Required
21INR0256 | Amsterdam Solar | SS Completed, FIS Started, No IA | Cottonwood Bayou Solar II, LLC | tap 345kV 43035 Oasis - 42500 Dow c27 | Brazoria | COASTAL | 2023-04-01 | SOL | PV | 509.88 | COD | 2019-10-18 | 2019-02-07 | 2019-04-29 | 2019-07-31 |  |  |  | No | Not Required | Not Required | Not Required
21INR0257 | Mercury Solar | SS Completed, FIS Started, No IA | Mercury Solar, LLC | 68090 Sam Sw 345kV | Hill | NORTH | 2022-10-31 | SOL | PV | 206.11 |  | 2019-02-07 | 2019-02-14 | 2019-05-03 | 2019-02-07 |  |  |  | No | Not Required | Not Required | Not Required
21INR0258 | Mercury Storage | SS Completed, FIS Started, No IA | Mercury Storage, LLC | 68090 Sam Sw 345kV | Hill | NORTH | 2023-12-01 | OTH | BA | 205.9 |  | 2019-02-07 | 2019-02-14 | 2019-05-03 | 2019-02-07 |  |  |  | No | Not Required | Not Required | Not Required
21INR0259 | Sunshine Solar | SS Completed, FIS Started, No IA | Sunshine Energy LLC | tap 138kV 8125 Lolita - 8172 Victoria | Victoria | SOUTH | 2022-07-30 | SOL | PV | 172.83 |  | 2019-02-14 | 2019-02-14 | 2019-03-29 | 2019-02-08 |  |  |  | No |  |  | Not Required
21INR0260 | Chariot Storage | SS Completed, FIS Started, No IA | Chariot Storage LLC | tap 69kV 99 Ben Hur - 107 Prairie Hill | Limestone | NORTH | 2023-04-15 | OTH | BA | 47.12 |  | 2019-02-19 | 2019-03-06 | 2019-05-24 | 2019-02-11 |  | No |  | No | Not Required | Not Required | Not Required
21INR0261 | Horizon Solar | SS Completed, FIS Started, IA | Horizon Solar, LLC | tap 138kV 5895 Pearsall - 5827 Moore | Frio | SOUTH | 2023-12-15 | SOL | PV | 204.09 |  | 2019-03-05 | 2019-03-05 | 2019-05-20 | 2019-03-01 |  | No | 2019-07-12 | Yes | Not Required | Not Required | Not Required | 2019-08-09 | 2019-12-09
21INR0262 | Grandfalls Storage | SS Completed, FIS Started, No IA | King Mountain Storage LLC | tap 345kV 11028 Odessa - 76000 North McCamey | Upton | WEST | 2022-12-01 | OTH | BA | 205.9 |  | 2019-02-14 | 2019-03-25 | 2019-06-17 | 2019-02-14 |  |  |  | No |  |  | Not Required
21INR0263 | Monarch Creek Wind | SS Completed, FIS Started, IA | EDF Renewables Development, Inc. | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek Switch (North Circuit) | Throckmorton | WEST | 2021-12-31 | WIN | WT | 209 |  | 2019-10-28 | 2019-04-25 | 2019-07-19 | 2019-08-05 |  | No | 2020-08-24 | No | Not Required | Not Required | Not Required
21INR0264 | Monarch Creek Wind (B) | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek Switch (North Circuit) | Haskell | WEST | 2022-12-01 | WIN | WT | 451.5 |  | 2019-11-20 | 2019-04-25 | 2019-07-19 | 2019-11-15 |  |  |  | No |  |  | Not Required
21INR0265 | Sisters Solar | SS Completed, FIS Started, No IA | Oberon Solar LLC | 345kV line 11010 Wolf Sw-1018 Moss Sw | Ector | WEST | 2023-09-15 | SOL | PV | 303.09 |  | 2019-02-28 | 2019-02-28 | 2019-03-29 | 2019-02-20 |  | Yes |  | No | Not Required | Not Required | Not Required
21INR0268 | Greyhound Solar | SS Completed, FIS Started, No IA | Rockhound Solar 2, LLC dba "Greyhound Solar" | tap 345kV 11010 Wolf - 1018 Moss | Ector | WEST | 2022-12-15 | SOL | PV | 608.7 |  | 2019-03-14 | 2019-03-28 | 2019-06-05 | 2019-03-21 |  |  |  | No |  |  | Not Required
21INR0271 | TERRANOVA SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY&INFRASTRUCTURE LLC | 345kV Avogadro Station | Knox | WEST | 2022-03-04 | SOL | PV | 152.32 |  | 2019-12-05 | 2019-04-01 | 2019-06-10 | 2019-12-12 |  |  |  | No |  |  | Not Required
21INR0274 | Carol Solar | SS Completed, FIS Completed, IA | Goat Mountain Renewables, LLC | 23906 AJ Swope 345kV | Potter | PANHANDLE | 2022-05-30 | SOL | PV | 223.2 |  | 2019-06-11 | 2019-03-26 | 2019-06-11 | 2019-06-07 | 2020-07-24 | No | 2020-09-11 | No | Not Required | Not Required | Not Required
21INR0276 | Elara Solar | SS Completed, FIS Completed, IA | Elara Energy Project, LLC | 5866 PaloduroSw 138kV | Frio | SOUTH | 2021-12-27 | SOL | PV | 132.4 |  | 2019-03-26 | 2019-03-26 | 2019-06-19 | 2019-03-15 | 2020-07-28 | No | 2019-07-12 | Yes | Not Required | Not Required | Not Required | 2019-09-27 | 2020-08-03 | 2020-10-28 |  |  | 2021-06-08
21INR0278 | Fighting Jays Solar | SS Completed, FIS Completed, IA | AP Solar Holdings, LLC | tap 345kV 44000 WA Parish - 44200 Hillje c64 | Fort Bend | HOUSTON | 2022-07-19 | SOL | PV | 351.29 | COD | 2019-04-30 | 2019-03-26 | 2019-06-17 | 2019-03-20 | 2021-06-30 | No | 2020-06-22 | Yes | Not Required | Not Required | Not Required | 2021-07-29 | 2021-07-29 | 2021-07-29
21INR0280 | Edgewater Storage | SS Completed, FIS Completed, No IA | Edgewater Battery Storage LLC | 210 Reagor Springs 69kV | Ellis | NORTH | 2023-04-15 | OTH | BA | 47.12 |  | 2019-04-02 | 2019-04-08 | 2019-07-04 | 2019-03-24 | 2021-05-28 | No |  | No | Not Required | Not Required | Not Required
21INR0281 | Byrd Ranch Storage | SS Completed, FIS Completed, IA | Byrd Ranch Storage LLC | 39700 TNSweeny 138kV | Brazoria | COASTAL | 2022-06-01 | OTH | BA | 50.6 | MW Size | 2019-04-02 | 2019-04-08 | 2019-07-04 | 2019-03-24 | 2020-06-17 | No | 2020-12-14 | Yes | Not Required | Not Required | Not Required
21INR0285 | LARISA SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY & INFRASTRUCTURE LLC | Tap 345kV 6235 Mulberry - 6076 Foxtail | Jones | WEST | 2022-06-01 | SOL | PV | 405.09 |  | 2020-01-13 | 2019-04-24 | 2019-07-01 | 2019-12-23 |  |  |  | No |  |  | Not Required
21INR0294 | Mountaineer Solar | SS Completed, FIS Completed, No IA | BN Wind Project LLC | 1444 Brown 345 kV | Brown | NORTH | 2023-09-29 | SOL | PV | 332 |  | 2019-12-11 | 2019-04-16 | 2019-06-11 | 2019-12-08 | 2021-03-22 | No |  | No |  |  | Not Required
21INR0295 | Sterling Prairie Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 8608 Pavlov A 138kV | Matagorda | COASTAL | 2022-03-01 | SOL | PV | 119.91 |  | 2020-01-22 | 2019-04-24 | 2019-07-23 | 2020-01-21 |  | No |  | No |  |  | Not Required
21INR0302 | Aureola Solar | SS Completed, FIS Started, No IA | Ben Milam Solar 1 LLC | tap 345kV 3687 Bell E - 39950 TNTNP One, one-third from Bell | Milam | SOUTH | 2023-01-30 | SOL | PV | 203 |  | 2020-07-15 | 2019-12-19 | 2020-03-12 | 2020-07-06 |  |  |  | No |  |  | Not Required
21INR0303 | Mandorla Solar | SS Completed, FIS Started, No IA | Ben Milam Solar 2 LLC | tap 345kV 3687 Bell E - 39950 TNTNP One, one-half from Bell | Milam | SOUTH | 2023-01-30 | SOL | PV | 254 |  | 2020-07-15 | 2020-01-22 | 2020-04-13 | 2020-07-06 |  |  |  | No |  |  | Not Required
21INR0304 | Halo Solar | SS Completed, FIS Started, No IA | Ben Milam Solar 3 LLC | tap 345kV 3687 Bell E - 39950 TNTNP One, one-fourth from Bell | Bell | NORTH | 2023-01-30 | SOL | PV | 254 |  | 2020-08-10 | 2020-01-22 | 2020-04-13 | 2020-07-06 |  |  |  | No |  |  | Not Required
21INR0314 | AQUAMARINE SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY & INFRASTRUCTURE LLC | 6150 Spur 138kV | Dickens | PANHANDLE | 2023-12-01 | SOL | PV | 151.69 |  | 2020-02-13 | 2019-05-10 | 2019-07-31 | 2020-01-27 |  |  |  | No |  |  | Not Required
21INR0320 | Ion Solar | SS Completed, FIS Started, No IA | GSE Group LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2023-05-31 | SOL | PV | 384 |  | 2020-02-03 | 2019-05-17 | 2019-08-01 | 2020-01-28 |  |  |  | No |  |  | Not Required
21INR0321 | Pin Oak Wind | SS Completed, FIS Started, No IA | Limestone Wind Project, LLC | tap 138kV 3515 Hubbard - 213 Haney | Navarro | NORTH | 2023-06-15 | WIN | WT | 99.99 |  | 2020-03-23 | 2019-05-31 | 2019-08-15 | 2020-03-09 |  | No |  | No |  |  | Not Required
21INR0323 | Spanish Crown | SS Completed, FIS Completed, IA | OCI Alamo 9 LLC | Tap 138kV 3420 Temple Pecan Creek - 3410 Lake Creek (138 kV Cow Bayou Switch, a new switching station) | Falls | NORTH | 2023-02-10 | SOL | PV | 103.1 |  | 2019-05-10 | 2019-05-13 | 2019-07-31 | 2019-05-10 | 2020-05-29 |  | 2021-01-13 | Yes | Not Required | Not Required | Not Required | 2021-01-28 | 2021-05-17
21INR0324 | Board Creek WP | SS Completed, FIS Completed, No IA | Limestone Wind Project, LLC | tap 345kV 68091 Navarro - 46020 Limestone c2 | Navarro | NORTH | 2022-09-01 | WIN | WT | 301 |  | 2019-11-08 | 2019-04-24 | 2019-07-22 | 2019-11-05 | 2021-04-05 | No |  | No |  |  | Not Required
21INR0325 | Sheep Creek Wind | SS Completed, FIS Completed, No IA | Century Oak Wind Project, LLC | 68051 Reata 345kV | Callahan | WEST | 2023-06-01 | WIN | WT | 151.5 |  | 2020-02-05 | 2019-05-30 | 2019-08-15 | 2020-01-29 | 2021-07-22 | No |  | No |  |  | Not Required
21INR0326 | Dove Run Solar | SS Completed, FIS Started, No IA | Dove Run Solar Project, LLC | tap 138kV 8510 Falfurrias - 8695 Crestonio | Duval | SOUTH | 2024-12-31 | SOL | PV | 101.25 |  | 2019-05-07 | 2019-05-07 | 2019-07-23 | 2019-05-02 |  |  |  | No |  |  | Not Required
21INR0334 | NIGHTFALL SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY & INFRASTRUCTURE LLC | Tap 138kV 8241 Razorback - 8234 Uvalde | Uvalde | SOUTH | 2023-01-25 | SOL | PV | 152.1 |  | 2020-09-24 | 2019-05-10 | 2019-07-31 | 2020-01-24 |  |  |  | No |  |  | Not Required
21INR0341 | Space City Solar | SS Completed, FIS Completed, IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2022-12-30 | SOL | PV | 609.74 | COD | 2019-10-28 | 2019-11-01 | 2020-03-06 | 2019-10-15 | 2021-01-04 |  | 2021-01-06 | Yes | Not Required | Not Required | Not Required | 2021-01-11
21INR0344 | Lunis Creek Solar 1 | SS Completed, FIS Started, No IA | Lunis Creek Solar Project, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2023-12-31 | SOL | PV | 202.5 |  | 2019-05-02 | 2019-05-02 | 2019-07-03 | 2019-05-02 |  |  |  | No |  |  | Not Required
21INR0345 | Lunis Creek Storage 1 | SS Completed, FIS Started, No IA | Lunis Creek Solar Project, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2023-12-31 | OTH | BA | 81.2 |  | 2019-05-02 | 2019-05-02 | 2019-07-03 | 2019-05-07 |  |  |  | No |  |  | Not Required
21INR0346 | Lunis Creek Solar 2 | SS Completed, FIS Started, No IA | Lunis Creek Solar Project II, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2023-12-31 | SOL | PV | 202.5 |  | 2019-05-02 | 2019-05-02 | 2019-07-30 | 2019-05-02 |  |  |  | No |  |  | Not Required
21INR0347 | Lunis Creek Storage 2 | SS Completed, FIS Started, No IA | Lunis Creek Solar Project II, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2023-12-31 | OTH | BA | 81.2 |  | 2019-05-02 | 2019-05-02 | 2019-07-30 | 2019-05-02 |  |  |  | No |  |  | Not Required
21INR0349 | Pearl Crescent Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 7640 Rock Island 138kV | Colorado | SOUTH | 2023-06-15 | SOL | PV | 208.35 | COD | 2019-06-04 | 2019-05-31 | 2019-08-26 | 2019-09-30 |  |  |  | No |  |  | Not Required
21INR0351 | 7V Solar | SS Completed, FIS Completed, IA | 7V Solar Ranch, LLC | tap 138kV 7248 Flatonia - 7274 Plum | Fayette | SOUTH | 2023-03-31 | SOL | PV | 246.3 |  | 2019-10-16 | 2019-04-16 | 2019-07-03 | 2019-08-16 | 2021-02-24 |  | 2020-09-01 | No | Not Required | Not Required | Not Required
21INR0353 | Big Elm Solar | SS Completed, FIS Started, No IA | Big Elm Solar, LLC | tap 345kV 3414 Temple - 3409 Lake Creek | Bell | NORTH | 2022-10-31 | SOL | PV | 222.6 |  | 2020-03-25 | 2019-06-27 | 2019-09-23 | 2020-03-23 |  |  |  | No |  |  | Not Required
21INR0354 | Kochab Solar | SS Completed, FIS Started, No IA | Kochab Energy Project, LLC | 8241 Razorback 138kV | Uvalde | SOUTH | 2023-07-01 | SOL | PV | 204 |  | 2019-05-14 | 2019-05-14 | 2019-08-10 | 2019-05-13 |  |  |  | No |  |  | Not Required
21INR0355 | Wilmeth Solar | SS Completed, FIS Started, No IA | Wilmeth Solar, LLC | tap 138kV 8212 Dilley - 8613 Big Well | Frio | SOUTH | 2023-10-31 | SOL | PV | 160 |  | 2020-03-05 | 2019-06-17 | 2019-08-08 | 2020-02-05 |  |  |  | No |  |  | Not Required
21INR0356 | Welder Solar | SS Completed, FIS Started, No IA | Welder Solar, LLC | tap 345kV 8624 Grissom - 8455 Lon Hill | Bee | SOUTH | 2023-10-31 | SOL | PV | 300 |  | 2020-07-08 | 2019-06-18 | 2019-09-13 | 2020-03-16 |  |  |  | No |  |  | Not Required
21INR0357 | SP TX-12B BESS | SS Completed, FIS Completed, IA | CED Upton County BESS, LLC | 132943 SPTX12B 138kV | Upton | WEST | 2021-11-22 | OTH | BA | 25.12 | Status Change INA-to-PLN | 2019-05-31 | 2019-06-17 | 2019-09-09 | 2019-06-12 | 2021-01-31 | No | 2020-05-01 | Yes | Not Required | Not Required | Not Required | 2021-01-31 | 2021-02-01 | 2021-02-01
21INR0359 | Hickerson Solar | SS Completed, FIS Started, No IA | Hickerson Solar | tap 345kV 68091 Navarro - 68040 Kopperl | Bosque | NORTH | 2022-12-31 | SOL | PV | 310.4 |  | 2020-05-13 | 2019-05-29 | 2019-08-23 | 2020-02-19 |  |  |  | No |  |  | Not Required
21INR0362 | Oystercatcher Solar | SS Completed, FIS Completed, No IA | Oystercatcher Solar, LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2024-08-20 | SOL | PV | 220.33 | COD | 2020-01-15 | 2019-05-30 | 2019-08-07 | 2019-12-20 | 2021-07-07 | Yes |  | No | Not Required | Not Required | Not Required
21INR0365 | Bat Cave Energy Storage | SS Completed, FIS Completed, IA | Bat Cave Energy Storage | 76390 Fort Mason 138kV | Mason | SOUTH | 2021-07-30 | OTH | BA | 100.49 | COD | 2019-05-31 | 2019-05-31 | 2019-08-15 | 2019-05-30 | 2020-10-29 | No | 2020-02-21 | Yes | Not Required | Not Required | Not Required | 2020-10-29 | 2020-10-29 | 2020-10-30 |  |  | 2021-04-30 | 2021-06-17
21INR0368 | Eliza Solar | SS Completed, FIS Started, No IA | Ables Springs Solar, LLC | tap 345kV 2478 Royse - 3103 Shamburger | Kaufman | NORTH | 2024-02-15 | SOL | PV | 151.28 |  | 2020-05-04 | 2019-06-21 | 2019-08-30 | 2020-02-24 |  |  |  | No |  |  | Not Required
21INR0371 | HIP Solar Project | SS Completed, FIS Started, No IA | ConnectGen Operating LLC | tap 345kV 967 Gibbons Creek - 46020 Limestone ckt 18 | Leon | NORTH | 2022-11-30 | SOL | PV | 135 |  | 2019-08-27 | 2019-08-16 | 2019-11-05 | 2019-08-22 |  |  |  | No |  |  | Not Required
21INR0375 | Grizzly Ridge Solar | SS Completed, FIS Started, IA | Grizzly Ridge Solar LLC | tap 69kV 273 Gustine - 258 Hamilton | Hamilton | NORTH | 2022-05-30 | SOL | PV | 100 | Status Change INA-to-PLN | 2019-07-08 | 2019-07-08 | 2019-10-01 | 2019-07-08 |  | No | 2021-06-09 | Yes | Not Required | Not Required | Not Required | 2021-06-09
21INR0376 | Barranca Wind III | SS Completed, FIS Started, No IA | Barranca Wind Energy, LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2024-12-31 | WIN | WT | 205 |  | 2019-07-12 | 2019-06-26 | 2019-09-23 | 2019-07-11 |  |  |  | No |  |  | Not Required
21INR0377 | Wagon Wheel Solar | SS Completed, FIS Started, No IA | Orion Power Generation, LLC | tap 138kV 60399 WEISS – 6340 Ballinger | Runnels | WEST | 2023-12-31 | SOL | PV | 144.76 |  | 2019-07-22 | 2019-07-17 | 2019-10-08 | 2019-07-16 |  |  |  | No |  |  | Not Required
21INR0378 | Twin Mountain Solar | SS Completed, FIS Started, No IA | Orion Renewable Resources LLC | tap 138kV 1649 Hasse - 290 Shilo | Comanche | NORTH | 2023-12-31 | SOL | PV | 83.86 |  | 2020-02-25 | 2019-07-29 | 2019-10-25 | 2019-07-19 |  |  |  | No |  |  | Not Required
21INR0379 | Ash Creek Solar | SS Completed, FIS Started, No IA | Ash Creek Solar LLC | 68090 SAM SW 345kV | Hill | NORTH | 2023-12-31 | SOL | PV | 408.85 |  | 2020-10-27 | 2019-07-29 | 2019-10-25 | 2019-07-19 |  |  |  | No |  |  | Not Required
21INR0380 | Charolais Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 44000 W A Parish - 5915 STP | Matagorda | COASTAL | 2023-12-15 | SOL | PV | 261.63 |  | 2020-05-11 | 2019-08-05 | 2019-10-31 | 2020-04-27 |  | Yes |  | No |  |  | Not Required
21INR0384 | Concho Valley Solar | SS Completed, FIS Completed, IA | MERIT SI, LLC | The crossing of SAPS to Live Oak and SAPS to Yellowjacket 138 kV lines. | Tom Green | WEST | 2022-09-15 | SOL | PV | 159.8 | COD | 2019-10-17 | 2019-07-08 | 2019-12-18 | 2019-06-27 | 2021-01-27 | No | 2020-09-28 | Yes | Not Required | Not Required | Not Required | 2021-04-08 | 2021-04-08 | 2021-04-21
21INR0387 | Anchor Wind | SS Completed, FIS Completed, IA | Ranchland Wind Project,LLC | Tap 345kV 68008 Latimer - 68010 Romney | Eastland | NORTH | 2021-12-24 | WIN | WT | 114.9 |  | 2019-06-26 | 2019-08-26 | 2019-11-12 | 2019-08-13 | 2021-04-30 | No | 2020-11-30 | Yes | Not Required | Not Required | Not Required | 2020-12-02 | 2021-04-30 | 2021-04-30
21INR0389 | Red-tailed Hawk Solar | SS Completed, FIS Completed, IA | AP Solar 6, LLC | tap 345kV 44200 Hillje - 44000 WA Parish | Wharton | SOUTH | 2022-05-31 | SOL | PV | 355.27 |  | 2019-07-01 | 2019-07-08 | 2019-10-02 | 2019-07-01 | 2020-03-13 |  | 2020-08-28 | Yes | Not Required | Not Required | Not Required | 2020-08-28
21INR0391 | Grandslam Solar | SS Completed, FIS Completed, IA | Grandslam Solar | 5700 Miracle Lake 138kV | Atascosa | SOUTH | 2022-12-30 | SOL | PV | 228.23 |  | 2019-09-03 | 2019-07-29 | 2019-10-30 | 2019-07-26 | 2020-08-03 |  | 2021-01-29 | No |  |  | Not Required
21INR0393 | Talitha Solar | SS Completed, FIS Started, No IA | Talitha Energy Project, LLC | 5660 Orange Grove 138kV | Jim Wells | SOUTH | 2023-05-01 | SOL | PV | 131.03 |  | 2019-07-12 | 2019-07-12 | 2019-09-09 | 2019-07-08 |  |  |  | No |  |  | Not Required
21INR0395 | SunRay | SS Completed, FIS Completed, IA | OCI SunRay LLC | tap 138kV 8234 Uvalde - 8241 Razorback | Uvalde | SOUTH | 2023-08-01 | SOL | PV | 200 |  | 2019-09-13 | 2019-07-17 | 2019-10-14 | 2019-07-15 | 2021-01-04 | No | 2021-07-06 | No | Not Required | Not Required | Not Required
21INR0401 | Young Wind | SS Completed, FIS Completed, No IA | Young Wind, LLC | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek | Young | WEST | 2022-12-31 | WIN | WT | 500 |  | 2020-04-13 | 2019-07-29 | 2019-10-25 | 2020-03-27 | 2021-05-28 | No |  | No | Not Required | Not Required | Not Required
21INR0406 | Buffalo Creek | SS Completed, FIS Completed, IA | Lincoln Clean Energy Development | tap 345kV 44000 WA Parish – 44040 BAILEY | Fort Bend | HOUSTON | 2022-03-15 | SOL | PV | 438.75 | Proj Name | 2019-08-06 | 2019-08-01 | 2019-10-30 | 2019-07-31 | 2021-04-23 | No | 2020-04-16 | Yes | Not Required | Not Required | Not Required | 2020-05-06 | 2021-04-15 | 2021-04-23
21INR0413 | Big Star Solar | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | Tap 345kV 9074 Lytton - 9073 Holman | Bastrop | SOUTH | 2022-03-31 | SOL | PV | 203.1 | MW Size | 2020-01-02 | 2019-08-27 | 2019-11-08 | 2019-12-20 | 2021-07-19 |  | 2020-10-02 | Yes |  |  | Not Required | 2020-12-04 | 2021-07-19 | 2021-07-30
21INR0414 | Jayhawk Solar | SS Completed, FIS Started, No IA | Renewable Energy Ventures, LLC | tap 345kV 1030 Morgan - 76030 Gasconades | Mitchell | WEST | 2023-02-28 | SOL | PV | 101.5 |  | 2020-06-22 | 2019-08-05 | 2019-10-31 | 2020-01-17 |  |  |  | No |  |  | Not Required
21INR0421 | Armadillo Solar | SS Completed, FIS Completed, IA | Lincoln Clean Energy Development | 3478 Navarro 138kV | Navarro | NORTH | 2022-12-31 | SOL | PV | 204 |  | 2019-09-05 | 2019-08-28 | 2019-11-22 | 2019-08-28 | 2020-10-09 | No | 2021-02-02 | No |  |  | Not Required
21INR0424 | Tierra Bonita Solar | SS Completed, FIS Started, No IA | Greasewood II, LLC | 844 Nevilesw 345kV | Pecos | WEST | 2023-04-30 | SOL | PV | 309.79 |  | 2020-09-18 | 2019-10-15 | 2020-01-02 | 2020-06-26 |  |  |  | No |  |  | Not Required
21INR0428 | Nabatoto Solar North | SS Completed, FIS Completed, IA | ConnectGEN West LLC | tap 345kV 967 Gibbons Creek - 46020 Limestone ckt 50 | Leon | NORTH | 2022-06-30 | SOL | PV | 400 |  | 2019-08-16 | 2019-09-23 | 2019-12-10 | 2019-09-11 | 2021-03-10 |  | 2021-02-26 | No |  |  | Not Required
21INR0430 | Holstein 2 Energy Storage | SS Completed, FIS Started, No IA | 229HD 8me LLC | 11406 Central Bluff 345kV | Nolan | WEST | 2022-10-04 | OTH | BA | 102.5 | COD | 2019-09-16 | 2019-08-26 | 2019-11-12 | 2019-08-16 |  |  |  | No |  |  | Not Required
21INR0431 | Galloway 2 Solar | SS Completed, FIS Completed, IA | 224WB 8me LLC | 7077 Amos Cr 345kV | Concho | WEST | 2022-05-04 | SOL | PV | 110 |  | 2019-08-28 | 2019-08-28 | 2017-10-02 | 2019-08-28 | 2021-04-30 |  | 2019-12-20 | Yes | Not Required | Not Required | Not Required | 2020-07-27 | 2021-03-23 | 2021-04-30
21INR0432 | Diversion Wind | SS Completed, FIS Started, No IA | Diversion Wind Development LLC | 6101 Riley 345kV | Baylor | WEST | 2024-12-30 | WIN | WT | 300 |  | 2020-07-15 | 2019-09-10 | 2019-12-04 | 2020-06-04 |  |  |  | No |  |  | Not Required
21INR0434 | Golinda Solar | SS Completed, FIS Started, IA | OCI SOL LLC | Tap 138kV 3420 Temple Pecan Creek - 3410 Lake Creek | Falls | NORTH | 2023-02-10 | SOL | PV | 103.1 |  | 2019-08-26 | 2019-09-23 | 2019-12-10 | 2019-09-03 |  | No | 2021-03-21 | Yes |  |  | Not Required
21INR0440 | Wren Solar | SS Completed, FIS Started, No IA | Wren Solar, LLC | 8601 Cebolla 345kV | Willacy | COASTAL | 2023-12-29 | SOL | PV | 170 |  | 2020-10-27 | 2019-10-15 | 2020-01-02 | 2020-07-28 |  |  |  | No |  |  | Not Required
21INR0442 | Myrtle Storage | SS Completed, FIS Started, No IA | Myrtle Storage, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2022-12-15 | OTH | BA | 150.83 |  | 2020-08-03 | 2019-11-04 | 2020-02-07 | 2020-07-30 |  |  |  | No |  |  | Not Required
21INR0443 | Cottonwood Bayou Storage | SS Completed, FIS Completed, No IA | Cottonwood Bayou Storage, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2023-01-01 | OTH | BA | 150.83 |  | 2020-07-20 | 2019-10-31 | 2020-01-23 | 2020-07-17 | 2021-07-21 | No |  | No |  |  | Not Required
21INR0444 | Long Point Storage | SS Completed, FIS Started, No IA | Long Point Storage, LLC | tap 138kV 44010 WAP - 42980 Nash. | Brazoria | COASTAL | 2023-04-01 | OTH | BA | 100.62 | COD | 2020-09-17 | 2019-11-01 | 2020-02-05 | 2020-09-01 |  |  |  | No |  |  | Not Required
21INR0446 | Knickerbocker Storage | SS Completed, FIS Started, No IA | Knickerbocker Solar LLC | Tap 345kV 76003 Big Hill - 76009 Twin Buttes | Tom Green | WEST | 2023-05-01 | OTH | BA | 25 |  | 2020-01-10 | 2019-12-19 | 2020-03-06 | 2019-12-05 |  |  |  | No |  |  | Not Required
21INR0449 | Panther Creek III Repower | SS Completed, FIS Completed, IA | Panther Creek Wind Farm Three, LLC | 1058 Longshore 345kV | Howard | WEST | 2021-11-08 | WIN | WT | 15.96 | COD | 2019-12-02 | 2019-11-27 | 2020-02-14 | 2019-11-19 | 2020-04-24 | No | 2009-03-19 | No | Not Required | Not Required | Not Required | 2020-08-03 | 2020-08-03 | 2020-08-03 |  |  |  | 2021-04-07
21INR0450 | Danish Fields Storage | SS Completed, FIS Started, No IA | Danish Fields Storage, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2023-06-15 | OTH | BA | 150.83 |  | 2020-07-20 | 2019-10-31 | 2020-01-24 | 2020-07-17 |  |  |  | No |  |  | Not Required
21INR0454 | Racetrack Solar | SS Completed, FIS Started, No IA | Innergex Renewables USA, LLC | tap 138kV 8234 Uvalde - 8236 West Batesville | Uvalde | SOUTH | 2022-05-01 | SOL | PV | 120 |  | 2020-09-08 | 2019-11-18 | 2020-01-28 | 2020-07-09 |  |  |  | No |  |  | Not Required
21INR0455 | Independence Trail Storage | SS Completed, FIS Started, No IA | KCE TX 16, LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2023-05-01 | OTH | BA | 100 |  | 2019-11-11 | 2019-12-03 | 2020-02-24 | 2019-10-22 |  |  |  | No |  |  | Not Required
21INR0456 | Maleza Storage | SS Completed, FIS Started, No IA | Brush Storage, LLC | tap 345kV 44200 Hillje - 44040 Bailey | Wharton | SOUTH | 2023-06-01 | OTH | BA | 150.83 |  | 2020-08-24 | 2019-10-31 | 2020-01-24 | 2020-08-18 |  |  |  | No |  |  | Not Required
21INR0458 | Porter Solar | SS Completed, FIS Started, No IA | Lantana Solar, LLC | tap 345kv 1429 Jacksboro - 1730 Krum West | Denton | NORTH | 2023-04-13 | SOL | PV | 276.7 |  | 2020-08-24 | 2020-01-30 | 2020-04-17 | 2020-08-06 |  |  |  | No |  |  | Not Required
21INR0459 | DeCordova BESS addition | SS Completed, FIS Completed, IA | Luminant Generation Company LLC | 1891 Decordova 138kV | Hood | NORTH | 2022-05-03 | OTH | BA | 263.08 | SFS/NtP | 2019-11-11 | 2019-11-18 | 2020-01-31 | 2019-10-29 | 2021-05-20 |  | 2021-07-02 | Yes | Not Required | Not Required | Not Required | 2021-07-08 | 2021-07-08 | 2021-07-15
21INR0460 | Republic Road Storage | SS Completed, FIS Completed, IA | KCE TX 11, LLC | 35 Hearne 138kV | Robertson | NORTH | 2021-10-29 | OTH | BA | 51.75 |  | 2020-01-16 | 2019-12-06 | 2020-02-25 | 2019-11-14 | 2021-01-28 | No | 2020-10-29 | Yes | Not Required | Not Required | Not Required | 2020-12-14 | 2021-01-06 | 2021-02-01
21INR0467 | Apogee Wind | SS Completed, FIS Completed, IA | EDF Renewables Development, Inc. | Tap 345kV 6235 Mulberry - 6076 Foxtail | Haskell | WEST | 2022-03-01 | WIN | WT | 393.24 |  | 2019-11-27 | 2019-12-03 | 2020-03-08 | 2019-11-18 | 2021-04-30 | No | 2020-03-10 | Yes | Not Required | Not Required | Not Required | 2020-03-27 | 2021-04-30 | 2021-04-30
21INR0469 | Big Star Storage | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | Tap 345kV 9074 Lytton - 9073 Holman | Bastrop | SOUTH | 2022-03-31 | OTH | BA | 80 | MW Size | 2020-10-23 | 2020-01-02 | 2020-03-26 | 2020-08-28 | 2021-07-19 |  | 2020-10-02 | No |  |  | Not Required |  |  | 2021-07-30
21INR0470 | Pearl Crescent Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 7640 Rock Island 138kV | Colorado | SOUTH | 2022-12-15 | OTH | BA | 50.26 |  | 2020-09-18 | 2019-12-20 | 2020-03-12 | 2020-04-10 |  |  |  | No |  |  | Not Required
21INR0473 | Vortex BESS | SS Completed, FIS Completed, IA | AZURE SKY WIND STORAGE LLC | loop 345kV 60515 Clear Crossing - 1421 WillowCr 345kV | Throckmorton | WEST | 2021-12-31 | OTH | BA | 121.83 |  | 2019-11-27 | 2019-12-03 | 2020-03-08 | 2019-11-18 | 2021-04-30 | No | 2021-04-23 | Yes | Not Required | Not Required | Not Required | 2021-04-27 | 2021-04-30 | 2021-04-30
21INR0474 | Anchor BESS | SS Completed, FIS Completed, IA | Ranchland Wind Project,LLC | Tap 345kV 68008 Latimer - 68010 Romney | Eastland | NORTH | 2021-12-24 | OTH | BA | 71.45 |  | 2019-11-27 | 2019-12-03 | 2020-02-25 | 2019-11-18 | 2021-04-30 | No | 2021-03-15 | Yes | Not Required | Not Required | Not Required | 2021-04-16 | 2021-04-30 | 2021-04-30
21INR0476 | Azure Sky BESS | SS Completed, FIS Completed, IA | Azure Sky Solar Project, LLC | 60515 Clear Crossing 345kV | Haskell | WEST | 2021-11-06 | OTH | BA | 77.6 | COD | 2019-12-27 | 2019-12-12 | 2020-03-05 | 2019-12-12 | 2020-10-13 | No | 2020-04-01 | Yes | Not Required | Not Required | Not Required | 2020-04-14 | 2020-10-27 | 2020-10-27
21INR0477 | Azure Sky Solar | SS Completed, FIS Completed, IA | Azure Sky Solar Project, LLC | 60515 Clear Crossing 345kV | Haskell | WEST | 2021-08-29 | SOL | PV | 228.4 | COD | 2020-01-31 | 2019-12-12 | 2020-03-05 | 2019-12-12 | 2020-10-13 | No | 2020-04-01 | Yes | Not Required | Not Required | Not Required | 2020-04-15 | 2020-10-27 | 2020-10-27 |  |  | 2021-06-04 | 2021-06-18
21INR0479 | Endurance Park Storage | SS Completed, FIS Completed, IA | KCE TX 13, LLC | 11306 Dermott 138kV | Scurry | WEST | 2022-06-30 | OTH | BA | 52.25 |  | 2019-12-03 | 2019-11-27 | 2020-02-14 | 2019-11-22 | 2020-12-07 |  | 2021-02-13 | No | Not Required | Not Required | Not Required
21INR0480 | Juanita Hill Storage | SS Completed, FIS Completed, No IA | KCE TX 20, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2022-07-30 | OTH | BA | 103.8 |  | 2019-12-03 | 2019-11-27 | 2020-02-12 | 2019-11-22 | 2021-04-16 | No |  | No |  |  | Not Required
21INR0481 | Lunar Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 5133 Elm Creek - 5915 STP (CKT 1) | Wharton | SOUTH | 2024-12-01 | SOL | PV | 609.74 | COD | 2020-03-30 | 2019-12-17 | 2020-03-11 | 2019-12-17 |  |  |  | Yes |  |  | Not Required
21INR0482 | Sisters Storage | SS Completed, FIS Started, No IA | 174 Power Global Properties | loop station on double circuit 345kV line 1018 Moss Sw/1029 Odessa Ehv Sw - 11010 Wolf Sw | Ector | WEST | 2022-10-15 | OTH | BA | 205 |  | 2020-03-30 | 2019-12-18 | 2020-03-11 | 2019-12-18 |  |  |  | No |  |  | Not Required
21INR0483 | Morrow Lake Storage | SS Completed, FIS Started, No IA | Morrow Lake Storage, LLC | 5895 Pearsall 138kV | Frio | SOUTH | 2022-08-01 | OTH | BA | 201.13 |  | 2020-11-10 | 2020-02-07 | 2020-04-30 | 2020-10-26 |  |  |  | No |  |  | Not Required
21INR0484 | Mustang Creek Storage | SS Completed, FIS Started, No IA | Ganado Storage, LLC | tap 138kV 5523 ETP - 78104 Ricebird new sub Galow | Jackson | SOUTH | 2022-10-31 | OTH | BA | 150.83 |  | 2020-09-22 | 2020-01-02 | 2020-03-23 | 2020-09-11 |  |  |  | No |  |  | Not Required
21INR0486 | Pandora Solar | SS Completed, FIS Started, No IA | Pandora | Tap 345kV 5915 STP - 5133 Elm Creek, c1 | Wilson | SOUTH | 2023-12-01 | SOL | PV | 252 |  | 2020-11-09 | 2020-01-03 | 2020-03-23 | 2020-01-03 |  |  |  | No |  |  | Not Required
21INR0487 | Nickel Prairie Storage | SS Completed, FIS Started, No IA | KCE TX 17, LLC | 44600 Rosharon 138kV | Brazoria | COASTAL | 2023-05-01 | OTH | BA | 208.96 |  | 2020-01-15 | 2019-12-23 | 2020-03-13 | 2019-12-23 |  | No |  | No |  |  | Not Required
21INR0490 | Samson Solar 2 | SS Completed, FIS Completed, IA | Samson Solar Energy II LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 |  | 2020-01-14 | 2020-01-13 | 2019-01-04 | 2020-01-13 | 2020-06-09 |  | 2020-08-27 | Yes | Not Required | Not Required | Not Required | 2021-04-12
21INR0491 | Samson Solar 3 | SS Completed, FIS Completed, IA | Samson Solar Energy III LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2022-03-31 | SOL | PV | 250 |  | 2020-01-14 | 2020-01-13 | 2019-01-04 | 2020-01-13 | 2020-06-09 |  | 2020-08-27 | Yes | Not Required | Not Required | Not Required | 2020-08-27 | 2020-10-15 | 2020-10-26 |  |  | 2021-06-30
21INR0492 | Stockyard Grid Batt | SS Completed, FIS Started, No IA | Stockyard Grid, LLC | 2082 Hicks 138kV | Tarrant | NORTH | 2022-08-01 | OTH | BA | 101.7 | COD | 2020-02-05 | 2020-01-13 | 2020-03-30 | 2020-01-13 |  |  |  | No |  |  | Not Required
21INR0493 | Ellis Solar | SS Completed, FIS Completed, No IA | Ellis Solar, LLC | tap 138kV 2300 Cottonwd_T- 2310 Midlothian_Txi | Ellis | NORTH | 2022-06-30 | SOL | PV | 81 |  | 2020-02-26 | 2020-01-30 | 2020-03-03 | 2020-01-28 | 2021-03-02 | No |  | No |  |  | Not Required
21INR0495 | Belding 2 Batt | SS Completed, FIS Started, No IA | Triple Butte II LLC | 38490 TNBelding 69kV | Pecos | WEST | 2022-06-01 | OTH | BA | 51.48 |  | 2020-05-20 | 2020-03-26 | 2020-06-11 | 2020-05-01 |  |  |  | No |  |  | Not Required
21INR0496 | Flower Valley II Batt | SS Completed, FIS Completed, IA | Flower Valley II, LLC | 38069 TN Flat Top 138kV | Reeves | WEST | 2021-10-21 | OTH | BA | 100.98 |  | 2020-05-20 | 2020-03-26 | 2020-06-11 | 2020-05-01 | 2021-01-29 |  | 2021-01-12 | Yes | Not Required | Not Required | Not Required | 2021-01-29 | 2021-02-01 | 2021-02-01
21INR0497 | Swoose II | SS Completed, FIS Completed, IA | Swoose II, LLC | 38001 TNPyote 138kV | Ward | WEST | 2021-11-17 | OTH | BA | 100.98 |  | 2020-05-20 | 2020-03-26 | 2020-06-11 | 2020-04-30 | 2021-01-29 |  | 2021-01-12 | Yes | Not Required | Not Required | Not Required | 2021-01-29 | 2021-02-01 | 2021-02-01
21INR0499 | Neptune Solar | SS Completed, FIS Completed, No IA | Matagorda Solar LLC | 110471 Formosa 138 kV | Jackson | SOUTH | 2022-03-20 | SOL | PV | 204.65 |  | 2020-04-16 | 2020-04-13 | 2020-07-07 | 2020-03-26 | 2021-07-27 | No |  | No |  |  | Not Required
21INR0500 | SkySealy | SS Completed, FIS Started, No IA | Sky Global Power Two, LLC | tap 138kV 44700 Gebhardt - 44740 Wallis circuit 65 | Austin | SOUTH | 2022-06-01 | GAS | IC | 143 |  | 2020-06-19 | 2020-05-01 | 2020-07-15 | 2020-03-20 |  | No |  | No | 2020-04-15 | Not Required
21INR0501 | Juno Solar (Phase II) | SS Completed, FIS Completed, IA | SE Juno, LLC | 59906 Long Draw 138 kV | Borden | WEST | 2021-07-15 | SOL | PV | 147.09 |  |  | 2020-03-23 | 2018-10-25 |  | 2019-12-12 |  | 2018-12-22 | Yes | Not Required | Not Required | Not Required | 2020-03-23 | 2020-04-06 | 2020-04-24 |  |  | 2020-12-14 | 2021-05-25
21INR0502 | LUND STORAGE | SS Completed, FIS Started, No IA | RRE POWER STORAGE 1 LLC | tap 138kV 7336 Gillie - 3650 Elgin | Travis | SOUTH | 2023-02-01 | OTH | BA | 60 |  | 2020-08-18 | 2020-05-01 | 2020-07-15 | 2020-07-21 |  |  |  | No |  |  | Not Required
21INR0505 | Ramsey Storage | SS Completed, FIS Started, No IA | Hecate Energy Ramsey Storage LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2022-05-01 | OTH | BA | 500 |  | 2021-01-20 | 2020-05-20 | 2020-07-30 | 2020-12-23 |  |  |  | No |  |  | Not Required
21INR0506 | Ty Cooke | SS Completed, FIS Completed, IA | City of Lubbock, by and through Lubbock Power and Light | 59166 LP Holly 69kV | Lubbock | PANHANDLE | 2021-07-27 | GAS | GT | 33 |  | 2020-10-23 | 2020-08-21 |  | 2020-08-10 | 2020-10-23 |  | 2020-10-30 | Yes | 2004-02-27 | Not Required | 2020-10-05 | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2021-07-09 | 2021-07-14
21INR0507 | Arana Creek Batt | SS Completed, FIS Started, No IA | Arana Creek LLC | 5648 Loyola 138kV | Kleberg | COASTAL | 2022-05-31 | OTH | BA | 153.5 |  | 2020-10-12 | 2020-06-03 | 2020-08-10 | 2020-10-06 |  |  |  | No |  |  | Not Required
21INR0508 | Angels Creek | SS Completed, FIS Started, No IA | Angels Creek LLC | 5888 Bruni 69kV | Webb | SOUTH | 2022-06-01 | OTH | BA | 31.68 |  | 2020-07-27 | 2020-06-03 | 2020-08-18 | 2020-07-23 |  | No |  | No |  |  | Not Required
21INR0509 | McClure Solar | SS Completed, FIS Started, No IA | Belltown Power Texas | tap 69kV 785 Oran - 343 Morris Sheppard | Palo Pinto | NORTH | 2022-12-30 | SOL | PV | 50 |  | 2021-03-18 | 2020-06-03 | 2020-08-18 | 2021-02-24 |  |  |  | No |  |  | Not Required
21INR0510 | Crossett Power Batt | SS Completed, FIS Completed, IA | Crossett Power Management LLC | 76026 Soda Lake 138kV | Crane | WEST | 2021-09-16 | OTH | BA | 203 |  | 2020-06-09 | 2020-06-03 | 2020-08-18 | 2020-05-28 | 2021-01-29 | No | 2020-08-05 | Yes | Not Required | Not Required | Not Required | 2021-02-01 | 2021-02-01 | 2021-02-01 |  |  | 2021-07-20
21INR0511 | Wolf Ridge Repower | SS Completed, FIS Started, No IA | Wolf Ridge Wind, LLC | 730 Wolf Ridge 138kV | Cooke | NORTH | 2022-01-31 | WIN | WT | 9 |  | 2020-10-09 | 2020-06-26 | 2020-09-14 | 2020-10-08 |  | No |  | No |  |  | Not Required
21INR0512 | Colorado Bend I Expansion | SS Completed, FIS Started, No IA | Colorado Bend I Power, LLC | 42985 Dyann 138kV | Wharton | SOUTH | 2022-07-01 | GAS | GT | 84 |  | 2021-05-12 | 2020-09-11 | 2020-11-30 | 2021-04-21 |  |  |  | No
21INR0515 | Roadrunner Crossing Wind II | SS Completed, FIS Started, No IA | RWE Renewables Development, LLC | tap 345kV 68005 WShack - 68050 Romney | Eastland | NORTH | 2022-12-15 | WIN | WT | 105.6 |  | 2020-10-27 | 2020-07-02 | 2020-09-14 | 2020-07-09 |  |  |  | No |  |  | Not Required
21INR0517 | Tidwell Prairie Storage 1 | SS Completed, FIS Started, No IA | Tidwell Prairie LLC | 39950 TNP ONE PLANT 345kV - 3400 TWIN OAK | Robertson | NORTH | 2022-09-01 | OTH | BA | 304.78 |  | 2020-07-23 | 2020-07-24 | 2020-10-20 | 2020-07-16 |  |  |  | No |  |  | Not Required
21INR0520 | Viking Solar | SS Completed, FIS Started, No IA | Yellow Viking Development One LLC | tap 345kV 1900 Comanche Peak - 11885 Everman | Hood | NORTH | 2022-12-26 | SOL | PV | 288.99 |  | 2020-10-09 | 2020-10-23 | 2021-01-12 | 2020-08-20 |  |  |  | No |  |  | Not Required
21INR0521 | White Mesa 2 Wind | SS Completed, FIS Completed, IA | White Mesa Wind, LLC | 76005 Schneeman Draw 345kV | Coke | WEST | 2021-11-30 | WIN | WT | 348 |  | 2020-11-23 | 2020-09-11 | 2020-11-30 | 2020-11-09 | 2021-02-01 |  | 2018-12-13 | Yes |  |  | Not Required | 2021-02-01 | 2021-02-01 | 2021-02-01
21INR0522 | Ignacio Grid | SS Completed, FIS Completed, IA | Ignacio Grid, LLC | 8824 Railroad 138kV | Hidalgo | SOUTH | 2022-03-03 | OTH | BA | 101.52 |  | 2020-10-01 | 2020-10-07 | 2019-03-12 | 2020-09-16 | 2020-10-28 |  | 2020-10-27 | Yes | Not Required | Not Required | Not Required | 2020-10-30 | 2020-10-31 | 2020-10-30
21INR0527 | Hays Energy Unit 3 Repower | SS Completed, FIS Started, No IA | HAYS ENERGY, LLC | 7043 Hays 345kV | Hays | SOUTH | 2022-02-01 | GAS | CC | 18 |  | 2021-02-09 | 2020-10-07 | 2020-12-30 | 2021-02-05 |  |  |  | No
21INR0529 | Topaz Energy Storage | SS Completed, FIS Started, No IA | Topaz Energy Storage, LLC | 38745 TN Attwater 138kV | Galveston | HOUSTON | 2022-06-01 | OTH | BA | 202.32 |  | 2020-11-25 | 2020-12-03 | 2021-02-19 | 2020-11-25 |  |  |  | No |  |  | Not Required
21INR0532 | Brazos Wind Repower | SS Completed, FIS Started, No IA | BRAZOS WIND VENTURES, LLC | 1064 Sun 138kV | Scurry | WEST | 2022-12-31 | WIN | WT | 15 |  | 2020-12-18 | 2020-12-22 | 2021-03-10 | 2020-11-30 |  |  |  | No |  |  | Not Required
21INR0534 | Midlothian Unit 2 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1939 Midlothian ELP 345kV | Ellis | NORTH | 2022-02-01 | GAS | CC | 18 |  | 2021-04-28 | 2021-01-25 | 2021-04-30 | 2021-02-08 |  |  |  | No
21INR0538 | Blue Jay Solar II | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2022-01-31 | SOL | PV | 68.95 |  | 2018-02-15 | 2021-04-13 |  |  | 2021-04-26 | No | 2020-10-26 | Yes |  |  | Not Required | 2020-12-02 | 2021-04-26 | 2021-04-29
21INR0539 | Anchor Wind II | SS Completed, FIS Completed, IA | Ranchland Wind Project II, LLC | tap 345kV 68008 LATIMER - 68010 ROMNEY | Eastland | NORTH | 2021-12-24 | WIN | WT | 148.02 |  | 2019-06-26 | 2021-04-13 |  |  | 2021-04-30 | No | 2020-11-30 | Yes |  |  | Not Required | 2021-04-30 | 2021-04-30 | 2021-04-30
21INR0541 | Bastrop Energy Center AGP repower Phase I | SS Completed, FIS Started, No IA | Bastrop Energy Partners, LP | 7049 Bastrop 345kV | Bastrop | SOUTH | 2022-04-30 | GAS | CC | 21 | COD | 2021-04-28 | 2021-04-13 | 2021-07-02 | 2021-04-19 |  |  |  | No
22INR0001 | Cunningham Solar 3 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 |  | 2018-10-23 |  | 2018-06-12 | 2018-10-23 |  | No |  | No | Not Required | Not Required | Not Required
22INR0202 | Delilah Solar 1 | SS Completed, FIS Completed, IA | Delilah Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2022-06-01 | SOL | PV | 300 |  | 2019-05-13 | 2018-11-20 | 2019-01-03 | 2019-05-03 | 2020-06-09 | No | 2020-12-22 | Yes | Not Required | Not Required | Not Required | 2021-03-23 | 2021-03-23 | 2021-04-27
22INR0203 | Delilah Solar 2 | SS Completed, FIS Completed, IA | Delilah Solar Energy II LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2023-06-30 | SOL | PV | 310 |  | 2019-05-13 | 2018-11-20 | 2019-01-03 | 2019-05-03 | 2020-06-09 | No | 2020-12-22 | Yes | Not Required | Not Required | Not Required | 2021-03-23
22INR0205 | Sbranch Solar | SS Completed, FIS Completed, IA | CG Wharton County LLC | Tap 138kV 44190 East Bernard - 44130 Caney | Wharton | SOUTH | 2022-04-01 | SOL | PV | 233.52 |  | 2019-04-01 | 2019-01-03 | 2019-03-13 | 2019-03-29 | 2021-07-29 | No | 2020-07-26 | Yes | Not Required | Not Required | Not Required | 2020-10-07 | 2021-07-06 | 2021-07-29
22INR0209 | Crescent Solar | SS Completed, FIS Started, No IA | Crescent Solar | 6101 Riley 345kV | Wilbarger | WEST | 2023-12-29 | SOL | PV | 253.68 |  | 2019-09-23 | 2019-01-17 | 2019-04-02 | 2019-09-20 |  |  |  | No | Not Required | Not Required | Not Required
22INR0211 | Schoolhouse Solar | SS Completed, FIS Completed, IA | Schoolhouse Solar, LLC | tap 345kV 7040 Austrop - 13429 Sandow | Lee | SOUTH | 2023-05-31 | SOL | PV | 150.84 |  | 2019-10-08 | 2019-01-30 | 2019-04-09 | 2019-10-02 | 2020-12-07 | No | 2021-07-11 | No | Not Required | Not Required | Not Required
22INR0215 | TEXAS SOLAR NOVA 3 | SS Completed, FIS Started, No IA | Texas Solar Nova 1, LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2023-01-31 | SOL | PV | 200.2 |  | 2019-05-28 | 2019-06-24 | 2015-12-30 | 2019-06-19 |  |  |  | No |  |  | Not Required
22INR0218 | Greyhound Solar 2 | SS Completed, FIS Started, No IA | Greyhound Solar 2 | tap 345kV dbl ckt 11010 Wolf - 1018 Moss and 11008 Wolf - 11028 Odessa | Ector | WEST | 2022-12-15 | SOL | PV | 500 |  | 2019-05-23 | 2019-05-14 | 2019-08-05 | 2019-05-10 |  |  |  | No |  |  | Not Required
22INR0220 | Lamkin Solar | SS Completed, FIS Started, No IA | Commanche Solar I, LLC | tap 69kV 258 Hamilton - 273 Gustine | Comanche | NORTH | 2022-12-31 | SOL | PV | 101.5 |  | 2020-05-11 | 2019-06-24 | 2019-09-18 | 2020-03-13 |  |  |  | No |  |  | Not Required
22INR0223 | Eiffel Solar | SS Completed, FIS Completed, IA | Paris Farm Solar, LLC | Tap 138kV 1693 Paris Switch - 1769 Paris East Tap | Lamar | NORTH | 2023-03-31 | SOL | PV | 200 |  | 2019-08-26 | 2019-07-11 | 2019-09-05 | 2019-07-11 | 2020-08-26 | No | 2021-03-19 | No |  |  | Not Required
22INR0236 | Point Mountain Solar | SS Completed, FIS Started, No IA | Hecate Energy Point Mountain LLC | 76000 North McCamey 345kV | Crane | WEST | 2022-07-01 | SOL | PV | 514 |  | 2019-08-13 | 2019-08-26 | 2019-11-08 | 2019-08-19 |  |  |  | No |  |  | Not Required
22INR0237 | Dragan Solar | SS Completed, FIS Started, No IA | Hecate Comanche Solar LLC | 1440 Comanche 345kV | Comanche | NORTH | 2024-05-01 | SOL | PV | 411 |  | 2019-11-11 | 2019-11-11 | 2020-02-17 | 2019-08-23 |  |  |  | No |  |  | Not Required
22INR0238 | Rockefeller Solar SLF | SS Completed, FIS Started, No IA | Photosol US Renewable Energy LLC | 76003 Big Hill 345kV | Schleicher | WEST | 2023-02-01 | SOL | PV | 207.48 |  | 2020-08-20 | 2019-10-31 | 2020-01-24 | 2020-07-21 |  |  |  | No |  |  | Not Required
22INR0239 | Rockefeller Storage SLF | SS Completed, FIS Started, No IA | Photosol US Renewable Energy LLC | 76003 Big Hill 345kV | Schleicher | WEST | 2023-02-01 | OTH | BA | 207.48 |  | 2020-08-20 | 2019-10-31 | 2020-01-24 | 2020-07-21 |  |  |  | No |  |  | Not Required
22INR0242 | Bright Arrow Solar | SS Completed, FIS Started, IA | RWE Solar Development, LLC | tap 345kV 1685 Farmersville - 1695 Monticello ckt 2 | Hopkins | NORTH | 2022-12-15 | SOL | PV | 349.2 |  | 2020-03-09 | 2020-02-12 | 2020-05-01 | 2020-03-04 |  | No | 2021-02-18 | Yes |  |  | Not Required | 2021-03-01
22INR0243 | Painted Horse Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Wilson | SOUTH | 2022-12-15 | SOL | PV | 200.58 |  | 2021-01-13 | 2020-02-12 | 2020-05-06 | 2020-11-05 |  |  |  | No |  |  | Not Required
22INR0244 | Razorbill Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP to 44200 Hillje 345kV Ckt 64 | Matagorda | COASTAL | 2023-12-15 | SOL | PV | 240 |  | 2020-10-23 | 2020-01-02 | 2020-03-26 | 2020-09-16 |  |  |  | No |  |  | Not Required
22INR0251 | Shaula I Solar | SS Completed, FIS Started, No IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 2 | DeWitt | SOUTH | 2023-08-01 | SOL | PV | 205.2 |  | 2019-11-27 | 2019-12-03 | 2020-03-08 | 2019-11-20 |  |  |  | No |  |  | Not Required
22INR0254 | Pisgah Ridge Solar | SS Completed, FIS Started, IA | Pisgah Ridge Solar, LLC | tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2022-12-15 | SOL | PV | 253.85 | COD | 2019-11-01 | 2019-11-01 | 2020-02-07 | 2019-10-21 |  | No | 2021-01-27 | No |  |  | Not Required
22INR0257 | Corazon Solar Phase II | SS Completed, FIS Started, IA | BAYWA R.E. SOLAR PROJECTS | 80219 Lobo 345kV | Webb | SOUTH | 2022-05-31 | SOL | PV | 203.9 |  | 2019-12-16 | 2019-12-19 | 2020-03-12 | 2019-12-04 |  | No | 2020-08-04 | No | Not Required | Not Required | Not Required
22INR0260 | Eliza Storage | SS Completed, FIS Started, No IA | Ables Springs Storage, LLC | tap 345kV 2478 Royse - 3103 Shamburger | Kaufman | NORTH | 2024-02-15 | OTH | BA | 100.62 |  | 2020-08-21 | 2019-12-03 | 2020-02-25 | 2020-08-19 |  |  |  | No |  |  | Not Required
22INR0261 | Dorado Solar | SS Completed, FIS Started, No IA | Eldorado Solar Power LLC | 68051 Reata 345kV | Callahan | WEST | 2023-01-01 | SOL | PV | 406.25 |  | 2020-09-02 | 2020-01-09 | 2020-03-30 | 2020-08-27 |  |  |  | No |  |  | Not Required
22INR0262 | Deville Solar | SS Completed, FIS Started, No IA | Deville Solar LLC | 68051 Reata 345kV | Callahan | WEST | 2023-01-01 | SOL | PV | 556.25 |  | 2020-09-02 | 2020-01-22 | 2020-04-08 | 2020-08-27 |  |  |  | No |  |  | Not Required
22INR0266 | Creekfield Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 44000 WA Parish - 44200 Hillje | Fort Bend | HOUSTON | 2023-12-15 | SOL | PV | 161.34 | COD | 2020-10-28 | 2020-01-29 | 2020-04-20 | 2020-10-16 |  |  |  | No |  |  | Not Required
22INR0267 | Shaula II Solar | SS Completed, FIS Started, No IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 2 | DeWitt | SOUTH | 2023-08-02 | SOL | PV | 205.2 |  | 2019-12-27 | 2019-12-18 | 2020-03-12 | 2019-12-18 |  |  |  | No |  |  | Not Required
22INR0269 | Shinnery Hill Solar | SS Completed, FIS Completed, No IA | EDF Renewables Development, Inc. | tap 345kV 6111 Riley7B - 1730 W Krum | Wichita | WEST | 2022-12-01 | SOL | PV | 502.54 |  | 2020-04-23 | 2019-12-17 | 2020-03-06 | 2020-04-09 | 2021-03-12 | No |  | No |  |  | Not Required
22INR0270 | Brass Fork Solar | SS Completed, FIS Started, IA | EDF Renewables Development, Inc. | tap 345kV 60703 Gauss7D - 60515 Clear Crossing | Haskell | WEST | 2023-05-01 | SOL | PV | 513.19 |  | 2020-08-27 | 2019-12-17 | 2020-03-06 | 2020-06-19 |  |  | 2021-06-14 | Yes |  |  | Not Required | 2021-06-25
22INR0271 | Bronze Fork Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek | Haskell | WEST | 2022-12-01 | SOL | PV | 515.89 |  | 2020-08-27 | 2019-12-17 | 2020-03-06 | 2020-06-19 |  |  |  | No |  |  | Not Required
22INR0272 | Brinton Fork Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 60791 Perigee 345kV | Haskell | WEST | 2022-12-01 | SOL | PV | 513.5 |  | 2020-08-27 | 2019-12-17 | 2020-03-10 | 2020-06-19 |  |  |  | No |  |  | Not Required
22INR0274 | Crowded Star Solar II | SS Completed, FIS Started, IA | Jones City Solar II, LLC | tap 345kV 68000 West Shack - 68001 Clayton c2 | Jones | WEST | 2023-10-23 | SOL | PV | 188.8 |  | 2019-05-23 | 2020-03-26 | 2020-06-05 | 2021-03-24 |  | No | 2019-12-17 | No | Not Required | Not Required | Not Required
22INR0275 | Coleto Creek ESS Addition | SS Completed, FIS Started, No IA | COLETO CREEK POWER LLC | 8162 Coleto Creek 138kV | Goliad | SOUTH | 2022-03-14 | OTH | BA | 100.1 |  | 2021-04-15 | 2019-12-11 | 2020-03-05 | 2020-09-17 |  |  |  | No |  |  | Not Required
22INR0276 | Trinidad ESS Addition | SS Completed, FIS Started, No IA | LUMINANT GENERATION COMPANY LLC | 3127 Trinidad 138kV | Henderson | NORTH | 2024-04-22 | OTH | BA | 110 | COD | 2021-04-16 | 2019-12-11 | 2020-03-06 | 2020-09-17 |  |  |  | No |  |  | Not Required
22INR0279 | Clutch City Solar | SS Completed, FIS Started, No IA | HZ Solar I | tap 138kV 42960 Mustang Bayou – 42100 Hudson | Brazoria | COASTAL | 2022-12-31 | SOL | PV | 204.17 |  | 2020-03-16 | 2020-01-22 | 2020-04-08 | 2020-02-11 |  | No |  | No |  |  | Not Required
22INR0280 | Roseland Storage | SS Completed, FIS Started, No IA | Enel Green Power Roseland Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2022-09-01 | OTH | BA | 51.63 |  | 2020-01-17 | 2019-12-26 | 2020-03-24 | 2019-12-26 |  |  |  | No |  |  | Not Required
22INR0281 | Pink Solar | SS Completed, FIS Started, No IA | General Solar, LLC | 971 Pruitt 138kV | Hunt | NORTH | 2022-10-31 | SOL | PV | 151 |  | 2020-10-21 | 2020-01-30 | 2020-04-20 | 2020-10-16 |  |  |  | No |  |  | Not Required
22INR0283 | Peregrine Solar | SS Completed, FIS Started, IA | SP-Peregrine Solar LLC | tap 345kV 8624 Grissom – 8164 Coleto Creek | Goliad | SOUTH | 2023-03-31 | SOL | PV | 303.36 | Proj Name SFS/NtP | 2020-07-29 | 2020-01-07 | 2020-03-30 | 2020-05-27 |  | No | 2021-06-19 | Yes |  |  | Not Required
22INR0295 | Coral Solar | SS Completed, FIS Started, No IA | Copperhead Solar, LLC | tap 138kV 3410 Lake Creek Switch - 3582 Falls County | Falls | NORTH | 2023-06-01 | SOL | PV | 152 |  | 2020-08-17 | 2020-06-03 | 2020-06-16 | 2020-07-30 |  |  |  | No |  |  | Not Required
22INR0301 | Fortuna Wind | SS Completed, FIS Started, No IA | RWE Renewables Development, LLC | Tap 345kV 1429 Jacksboro - 1730 WKrum | Jack | NORTH | 2023-12-15 | WIN | WT | 250 |  | 2021-01-18 | 2020-03-06 | 2020-05-27 | 2020-11-24 |  |  |  | No |  |  | Not Required
22INR0302 | Bright Arrow Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 1685 Farmersville - 1695 Monticello ckt 2 | Hopkins | NORTH | 2022-12-15 | OTH | BA | 106.7 |  | 2021-01-11 | 2020-03-06 | 2020-05-05 | 2020-11-02 |  |  |  | No |  |  | Not Required
22INR0307 | Desert Vine Solar | SS Completed, FIS Started, No IA | J&R Power DevCo, LLC | 8299 Zapata 138kV | Zapata | SOUTH | 2023-06-30 | SOL | PV | 121.64 |  |  | 2020-05-01 | 2020-07-13 | 2021-02-03 |  |  |  | No |  |  | Not Required
22INR0314 | Lan Solar | SS Completed, FIS Started, No IA | General Solar, LLC | 1833 Brookstone tap 138kV | Lamar | NORTH | 2022-10-31 | SOL | PV | 182.2 |  |  | 2020-05-01 | 2020-07-07 | 2021-01-04 |  |  |  | No |  |  | Not Required
22INR0322 | BRP Paleo BESS | SS Completed, FIS Completed, IA | BRP Paleo BESS LLC | 23920 Blackwater Draw 345kV | Hale | PANHANDLE | 2022-09-30 | OTH | BA | 202.36 |  | 2020-04-09 | 2020-04-13 | 2020-06-25 | 2020-03-25 | 2020-12-11 |  | 2021-02-05 | Yes | Not Required | Not Required | Not Required | 2021-02-05
22INR0325 | BRP Dickens BESS | SS Completed, FIS Started, IA | BRP Dickens BESS LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2022-05-30 | OTH | BA | 202.33 |  | 2020-04-16 | 2020-04-22 | 2020-07-09 | 2020-04-06 |  |  | 2020-11-03 | Yes | Not Required | Not Required | Not Required | 2021-01-14
22INR0326 | Inertia Wind | SS Completed, FIS Started, IA | Inertia Wind Project, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2022-12-31 | WIN | WT | 350 |  | 2020-08-31 | 2020-06-03 | 2021-02-02 | 2020-05-27 |  |  | 2021-05-04 | No |  |  | Not Required
22INR0327 | Hummingbird Storage | SS Completed, FIS Completed, No IA | KCE TX 10, LLC | 1730 Krum 345kV | Denton | NORTH | 2022-12-26 | OTH | BA | 103.8 | MW Size | 2020-05-29 | 2020-05-20 | 2020-07-30 | 2020-04-24 | 2021-07-09 | No |  | No |  |  | Not Required
22INR0328 | Inertia BESS | SS Completed, FIS Started, IA | Inertia Wind Project, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2022-12-31 | OTH | BA | 121.45 |  | 2020-08-24 | 2020-06-03 | 2021-02-02 | 2020-05-27 |  |  | 2021-05-04 | No | Not Required | Not Required | Not Required
22INR0330 | Old Aqueduct Batt | SS Completed, FIS Started, No IA | Old Aqueduct LLC | 23920 Blackwater 345kV | Hale | PANHANDLE | 2022-12-17 | OTH | BA | 302.94 |  | 2020-07-24 | 2020-05-01 | 2020-07-13 | 2020-06-29 |  |  |  | No |  |  | Not Required
22INR0332 | Brantley Branch Batt | SS Completed, FIS Started, No IA | Brantley Branch LLC | 3116 Mt. Enterprise 345kV | Rusk | NORTH | 2022-06-30 | OTH | BA | 300 |  | 2020-12-07 | 2020-05-01 | 2020-07-15 | 2020-11-24 |  |  |  | No |  |  | Not Required
22INR0335 | Estonian Solar Farm | SS Completed, FIS Completed, No IA | 249RD 8ME | tap 138kV 1801 Paris Pump Tap – 17011 LKCRK_P8 | Delta | NORTH | 2023-06-01 | SOL | PV | 204.47 |  | 2020-01-17 | 2020-04-22 | 2020-06-29 |  | 2021-07-20 | No |  | No |  |  | Not Required
22INR0336 | Estonian Energy Storage | SS Completed, FIS Completed, No IA | 249RD 8ME | tap 138kV 1801 Paris Pump Tap – 17011 LKCRK_P8 | Delta | NORTH | 2023-06-01 | OTH | BA | 102.5 |  | 2020-02-26 | 2020-04-22 | 2020-06-29 |  | 2021-07-20 | No |  | No |  |  | Not Required
22INR0337 | Skylab Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 5915 STP - 8249 Angstrom | Wharton | SOUTH | 2024-12-01 | SOL | PV | 609.74 | COD | 2020-08-10 | 2020-06-03 | 2020-08-11 | 2020-05-27 |  | No |  | No |  |  | Not Required
22INR0338 | Limousin Oak Storage | SS Completed, FIS Started, No IA | KCE TX 15, LLC | 44645 Singleton 345kV | Grimes | NORTH | 2023-05-01 | OTH | BA | 104.62 |  | 2020-05-14 | 2020-05-20 | 2020-07-30 | 2020-04-24 |  | No |  | No |  |  | Not Required
22INR0342 | Archer Solar | SS Completed, FIS Started, No IA | Leeward Renewable Energy Development, LLC | 5555 Shropshire 69kV | Matagorda | COASTAL | 2023-12-28 | SOL | PV | 101 |  | 2020-12-08 | 2020-05-01 | 2020-07-15 | 2020-11-05 |  |  |  | No |  |  | Not Required
22INR0346 | Clybourn Solar | SS Completed, FIS Started, No IA | Leeward Renewable Energy Development, LLC | 8121 Blessing 138kV + 14 mile gen-tie | Matagorda | COASTAL | 2022-12-31 | SOL | PV | 201.5 |  | 2020-07-20 | 2020-05-20 | 2020-07-30 | 2020-05-07 |  |  |  | No |  |  | Not Required
22INR0347 | BRP Crater BESS | SS Completed, FIS Completed, No IA | BRP Crater BESS LLC | tap 345kV 1025 Falcon Seaboard - 1021 Midland East | Howard | WEST | 2022-11-30 | OTH | BA | 303.53 |  | 2020-05-18 | 2020-05-20 | 2020-07-30 | 2020-04-30 | 2021-05-26 |  |  | No |  |  | Not Required
22INR0349 | BRP Antlia BESS | SS Completed, FIS Completed, IA | BRP Antlia BESS LLC | tap 138kV 8998 Maxwell – 8261 Whiting | Val Verde | WEST | 2022-10-30 | OTH | BA | 70.95 |  | 2020-06-18 | 2020-06-03 | 2020-08-11 | 2020-05-14 | 2021-05-21 | No | 2021-06-05 | Yes |  |  | Not Required
22INR0350 | Milam Solar 2 | SS Completed, FIS Started, No IA | Sandow Lakes Ranch Solar II, LLC | tap one 345kV 7040 Austrop - 13429 Sandow line | Milam | SOUTH | 2024-05-16 | SOL | PV | 290.21 |  | 2020-08-24 | 2020-09-11 | 2021-02-08 | 2020-05-28 |  |  |  | No |  |  | Not Required
22INR0352 | Sparta Solar | SS Completed, FIS Completed, IA | Sparta Solar | AEP 8689 Tango 345kV station | Bee | SOUTH | 2022-05-02 | SOL | PV | 252.35 | MW Size | 2020-06-25 | 2020-05-20 | 2020-07-30 | 2020-05-07 | 2021-07-29 | No | 2020-08-14 | Yes | Not Required | Not Required | Not Required | 2020-08-17 |  | 2021-07-30
22INR0353 | BRP Carina BESS | SS Completed, FIS Completed, No IA | BRP Carina BESS LLC | 8479 Clarkwood 138kV | Nueces | COASTAL | 2022-10-30 | OTH | BA | 151.85 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 | 2020-06-22 | 2021-07-06 |  |  | No |  |  | Not Required
22INR0354 | XE MURAT Solar | SS Completed, FIS Started, No IA | Liberty 1 Solar | tap 138kV 40391 Crosby C66 - 40130 Atascocita | Harris | HOUSTON | 2022-12-31 | SOL | PV | 60.8 |  | 2021-01-20 | 2020-08-04 | 2020-10-16 | 2021-01-05 |  |  |  | No |  |  | Not Required
22INR0356 | Jungmann Solar | SS Completed, FIS Started, No IA | BT Jungmann LLC | Tap 69kV 3643 Temp SS - 3689 Marak c1 | Milam | SOUTH | 2023-09-01 | SOL | PV | 40 |  | 2021-02-05 | 2020-06-03 | 2020-08-11 | 2021-02-05 |  |  |  | No |  |  | Not Required
22INR0357 | Loma Pinta Solar | SS Completed, FIS Started, No IA | Loma Pinta Wind Energy, LLC | 5705 Fowlerton 138kV | La Salle | SOUTH | 2022-12-01 | SOL | PV | 203.06 |  | 2020-09-08 | 2020-06-03 | 2020-08-18 | 2020-05-28 |  |  |  | No |  |  | Not Required
22INR0358 | XE RHODA Solar | SS Completed, FIS Started, No IA | Milam 2 Solar | tap 138kV 32 Robertson - 64 Milano | Milam | SOUTH | 2023-07-13 | SOL | PV | 86.23 |  | 2021-01-20 | 2020-07-10 | 2020-09-28 | 2021-01-05 |  |  |  | No |  |  | Not Required
22INR0359 | Dileo Solar | SS Completed, FIS Started, No IA | Belltown Power Texas LLC | tap 69kV 37470 TN Olsen - 37420 TN Lake Whitney | Bosque | NORTH | 2023-05-11 | SOL | PV | 72 |  | 2020-11-23 | 2020-06-19 | 2020-09-08 | 2020-11-10 |  | No |  | No |  |  | Not Required
22INR0360 | Jade Solar | SS Completed, FIS Started, IA | IP RENEWABLE ENERGY HOLDINGS LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Scurry | WEST | 2022-12-31 | SOL | PV | 374.4 |  | 2020-07-15 | 2020-06-26 | 2020-09-14 | 2020-06-15 |  | No | 2021-01-22 | Yes |  |  | Not Required
22INR0361 | Sibyl Power Station | SS Completed, FIS Started, No IA | Sibyl Generating, LLC | Tap 138kV 43261 Southwyck - 44552 Telview | Fort Bend | HOUSTON | 2023-08-01 | GAS | GT | 298.68 |  | 2020-08-26 | 2020-09-02 | 2020-11-12 | 2020-08-18 |  |  |  | No
22INR0362 | Pluto Solar | SS Completed, FIS Started, No IA | Pluto Solar, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2022-11-30 | SOL | PV | 252.8 |  | 2020-07-28 | 2020-06-26 | 2020-09-14 | 2020-06-23 |  |  |  | No |  |  | Not Required
22INR0363 | Hayhurst Texas Solar | SS Completed, FIS Started, No IA | CHEVRON USA, INC. | tap 138kV 11103 Rust Hills - 11190 Horseshoe Springs Switch | Culberson | WEST | 2023-02-15 | SOL | PV | 46.2 |  | 2020-10-23 | 2020-08-21 | 2020-11-04 | 2020-08-13 |  |  |  | No |  |  | Not Required
22INR0364 | Painted Horse Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Wilson | SOUTH | 2022-12-15 | OTH | BA | 50 |  | 2021-03-17 | 2020-07-02 | 2020-09-14 | 2021-03-07 |  |  |  | No |  |  | Not Required
22INR0365 | BRP Mensa BESS | SS Completed, FIS Started, No IA | BRP Mensa BESS LLC | 60718 Pecos Valley 138kV | Pecos | WEST | 2022-12-30 | OTH | BA | 202.79 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 | 2020-06-22 |  |  |  | No | Not Required | Not Required | Not Required
22INR0366 | BRP Libra BESS | SS Completed, FIS Started, No IA | BRP Libra BESS LLC | 5133 Elm Creek 345kV | Guadalupe | SOUTH | 2022-11-30 | OTH | BA | 202.38 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 | 2020-06-22 |  | No |  | No |  |  | Not Required
22INR0367 | BRP Lyra BESS | SS Completed, FIS Started, No IA | BRP Lyra BESS LLC | 60718 Pecos Valley 138kV | Pecos | WEST | 2022-11-30 | OTH | BA | 202.79 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 | 2020-06-22 |  |  |  | No |  |  | Not Required
22INR0368 | Padua Grid BESS | SS Completed, FIS Completed, No IA | Padua Grid, LLC | 5395 O.W Sommers 138kV | Bexar | SOUTH | 2022-12-31 | OTH | BA | 202.6 |  | 2020-07-23 | 2020-07-10 | 2020-09-28 | 2020-06-29 | 2021-07-21 | No |  | No |  |  | Not Required
22INR0369 | Mark One Power Station | SS Completed, FIS Started, IA | Mark One Generating, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2022-06-25 | GAS | GT | 312 | COD SFS/NtP | 2020-07-20 | 2020-07-10 | 2020-09-28 | 2020-07-03 |  | No | 2021-07-21 | Yes | 2020-12-16 | Not Required | 2021-06-11 | 2021-07-28
22INR0371 | PES 2 Power Station | SS Completed, FIS Completed, IA | HO CLARKE GENERATING LLC | 47150 H.O. Clarke 138kV | Harris | HOUSTON | 2021-09-01 | GAS | GT | 102 |  | 2020-07-21 | 2020-07-24 | 2020-10-20 | 2020-07-14 | 2020-07-31 | No | 2019-12-17 | Yes | 2019-04-10 | Not Required | 2020-11-12 | 2020-10-30 | 2020-10-30 | 2020-10-30
22INR0372 | BRP Hydra BESS | SS Completed, FIS Started, IA | BRP Hydra BESS LLC | 76002 Bakersfield 345kV | Pecos | WEST | 2022-10-30 | OTH | BA | 202.46 |  | 2020-07-27 | 2020-07-24 | 2020-10-20 | 2020-07-06 |  | No | 2021-05-08 | Yes | Not Required | Not Required | Not Required
22INR0374 | Inertia Solar | SS Completed, FIS Started, IA | Inertia Solar Project, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2022-12-31 | SOL | PV | 258.35 |  | 2020-10-26 |  | 2021-02-02 | 2020-10-13 |  |  | 2021-05-04 | No |  |  | Not Required
22INR0375 | Inertia BESS 2 | SS Completed, FIS Started, IA | Inertia Solar Project, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2022-12-31 | OTH | BA | 100.77 |  | 2020-10-26 |  | 2021-02-02 | 2020-10-13 |  |  | 2021-05-04 | No | Not Required | Not Required | Not Required
22INR0379 | Creekfield Storage | SS Started, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 44000 WA Parish - 44200 Hillje | Fort Bend | HOUSTON | 2023-12-15 | OTH | BA | 69 |  | 2021-06-29 | 2020-11-18 |  | 2021-06-17 |  |  |  | No |  |  | Not Required
22INR0382 | Razorbill Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP to 44200 Hillje 345kV Ckt 64 | Matagorda | COASTAL | 2023-12-15 | OTH | BA | 120 | COD | 2021-06-25 | 2020-08-04 | 2020-10-28 | 2021-06-11 |  |  |  | No | Not Required | Not Required | Not Required
22INR0383 | BRP Musca BESS | SS Completed, FIS Started, No IA | BRP Musca BESS LLC | 60361 Santa Rita 138kV | Reagan | WEST | 2022-11-30 | OTH | BA | 101.28 |  | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  |  |  | No |  |  | Not Required
22INR0384 | BRP Pavo BESS | SS Completed, FIS Completed, IA | BRP Pavo BESS LLC | 38430 TN White Baker 138kV | Pecos | WEST | 2022-02-01 | OTH | BA | 176.85 | SFS/NtP | 2020-08-19 | 2020-07-24 | 2020-10-08 | 2020-08-17 | 2021-07-30 | No | 2021-07-15 | Yes | Not Required | Not Required | Not Required | 2021-07-29 | 2021-07-29 | 2021-07-30
22INR0385 | BRP Pictor BESS | SS Completed, FIS Started, No IA | BRP Pictor BESS LLC | 60400 Lynx 138kV | Crane | WEST | 2022-12-30 | OTH | BA | 202.7 |  | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  |  |  | No |  |  | Not Required
22INR0386 | BRP Octans BESS | SS Completed, FIS Started, No IA | BRP OCTANS BESS LLC | 6671 Tombstone 138kV | Pecos | WEST | 2022-11-30 | OTH | BA | 126.63 |  | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  |  |  | No |  |  | Not Required
22INR0387 | Val Vista Grid BESS | SS Completed, FIS Started, No IA | Val Vista Grid, LLC | 8380 North Edinburg 138kV | Hidalgo | SOUTH | 2023-03-01 | OTH | BA | 202.85 |  | 2020-08-04 | 2020-08-04 | 2020-10-16 | 2020-07-21 |  |  |  | No |  |  | Not Required
22INR0388 | BRP Cachi BESS | SS Completed, FIS Started, IA | BRP Cachi BESS LLC | 7680 Clear Springs 138kV | Guadalupe | SOUTH | 2022-12-30 | OTH | BA | 202.46 |  | 2020-10-14 | 2020-08-21 | 2020-11-10 | 2020-08-26 |  |  | 2021-06-11 | No | Not Required | Not Required | Not Required
22INR0390 | BRP Perseus BESS | SS Completed, FIS Started, No IA | BRP Perseus BESS LLC | 8452 Lon Hill 138kV | Nueces | COASTAL | 2022-12-30 | OTH | BA | 202.5 |  | 2020-08-19 | 2020-08-21 | 2020-11-10 | 2020-08-17 |  |  |  | No |  |  | Not Required
22INR0392 | Kalina Solar | SS Completed, FIS Started, No IA | Aurora Solar LLC | 8606 Goddard 345kV | San Patricio | COASTAL | 2023-12-31 | SOL | PV | 120 |  | 2021-03-31 | 2020-08-04 | 2020-10-28 | 2021-03-29 |  |  |  | No |  |  | Not Required
22INR0396 | HATHOR SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY & INFRASTRUCTURE | Tap 138kV 960 Shelby - 811 Nevada | Hunt | NORTH | 2023-08-22 | SOL | PV | 67.56 | MW Size | 2021-03-15 | 2020-09-11 | 2020-11-30 | 2021-02-24 |  |  |  | No |  |  | Not Required
22INR0397 | Buckeye Corpus Fuels Solar | SS Completed, FIS Started, No IA | Corpus Fuels, LLC | 8858 McKenzie 138kV | Nueces | COASTAL | 2022-09-01 | SOL | PV | 57.59 |  | 2020-10-06 | 2020-08-21 | 2020-11-10 | 2020-08-13 |  |  |  | No |  |  | Not Required
22INR0398 | Sabal Storage | SS Completed, FIS Started, No IA | Cameron Wind I, LLC | 5761 Paredes 138kV | Cameron | COASTAL | 2022-10-31 | OTH | BA | 24 |  | 2021-06-22 | 2020-09-11 | 2020-11-30 | 2021-05-28 |  |  |  | No |  |  | Not Required
22INR0400 | Dragan Storage | SS Completed, FIS Started, No IA | Hecate Grid Dragan Storage LLC | 1440 Comanche 345kV | Comanche | NORTH | 2022-10-15 | OTH | BA | 408.3 |  | 2020-10-02 | 2020-08-21 | 2020-11-04 | 2020-08-13 |  |  |  | No |  |  | Not Required
22INR0401 | Eval Storage | SS Completed, FIS Started, No IA | Hecate Grid East Valley Storage LLC | 80229 Cavazos 138kV | Cameron | COASTAL | 2022-05-31 | OTH | BA | 255 |  | 2020-12-29 | 2020-10-23 | 2021-01-12 | 2020-11-03 |  |  |  | No |  |  | Not Required
22INR0402 | Frye Storage | SS Completed, FIS Started, No IA | Hecate Grid Frye Storage LLC | new 345kV sub Kress connecting both 23912 Ogallala - 23914 Tule Canyon circuits | Swisher | PANHANDLE | 2023-05-31 | OTH | BA | 510 |  | 2020-08-26 | 2020-09-02 | 2020-11-19 | 2020-08-17 |  |  |  | No |  |  | Not Required
22INR0404 | Fence Post Solar | SS Completed, FIS Completed, No IA | Fence Post Solar Project, LLC | tap 138kV 3127 Trinidad – 3483 Goodloe | Navarro | NORTH | 2022-12-30 | SOL | PV | 243.36 |  | 2020-10-02 | 2020-11-05 | 2021-01-20 | 2020-10-21 | 2021-07-27 |  |  | No |  |  | Not Required
22INR0405 | Fence Post BESS | SS Completed, FIS Completed, No IA | Fence Post Solar Project, LLC | tap 138kV 3127 Trinidad – 3483 Goodloe | Navarro | NORTH | 2022-12-30 | OTH | BA | 90.76 |  | 2020-10-02 | 2020-11-05 | 2021-01-20 | 2020-10-13 | 2021-07-27 |  |  | No |  |  | Not Required
22INR0408 | BRP Pular BESS | SS Completed, FIS Started, No IA | BRP Pular BESS LLC | 8963 Hidalgo Energy Center 138kV | Hidalgo | SOUTH | 2022-10-30 | OTH | BA | 233.1 |  | 2020-09-02 | 2020-09-11 | 2021-06-10 | 2020-08-25 |  |  |  | No |  |  | Not Required
22INR0409 | Stampede Solar | SS Completed, FIS Started, No IA | Stampede Solar Project, LLC | tap 345kV 1685 Farmersville - 1695 Monticello ckt 1 | Hopkins | NORTH | 2022-12-30 | SOL | PV | 258.35 |  | 2020-10-16 | 2020-11-05 | 2021-01-20 | 2020-10-21 |  |  |  | No |  |  | Not Required
22INR0410 | Stampede BESS | SS Completed, FIS Started, No IA | Stampede Solar Project, LLC | tap 345kV 1685 Farmersville - 1695 Monticello ckt 1 | Hopkins | NORTH | 2022-12-30 | OTH | BA | 100.77 |  | 2020-10-16 | 2020-11-05 | 2021-01-20 | 2020-10-21 |  |  |  | No |  |  | Not Required
22INR0412 | Andromeda Solar | SS Completed, FIS Started, IA | IP Renewable Energy Holdings LLC | Tap 345kV 11305 Dermott - 60706 Kirchhoff C | Scurry | WEST | 2023-03-31 | SOL | PV | 374.4 |  | 2020-09-22 | 2020-09-11 | 2020-11-30 | 2020-09-02 |  | No | 2021-04-01 | No |  |  | Not Required
22INR0417 | Amsterdam Storage | SS Completed, FIS Started, No IA | Cottonwood Bayou II Storage, LLC | tap 345kV 43035 Oasis - 42500 Dow c27 | Brazoria | COASTAL | 2023-04-01 | OTH | BA | 201.13 |  | 2020-09-30 | 2020-10-07 | 2020-12-30 | 2020-09-11 |  |  |  | No |  |  | Not Required
22INR0422 | Ferdinand Grid BESS | SS Completed, FIS Started, No IA | Ferdinand Grid, LLC | 5260 Leon Creek 138kV | Bexar | SOUTH | 2023-05-31 | OTH | BA | 202.65 |  | 2021-01-28 | 2021-03-01 | 2021-05-12 | 2021-01-28 |  |  |  | No |  |  | Not Required
22INR0423 | BRP Quela BESS | SS Completed, FIS Started, No IA | BRP Quela BESS LLC | Tap 138kV 5110 J.T. Deely - 5294 Martinez | Bexar | SOUTH | 2022-12-30 | OTH | BA | 303.74 |  | 2020-09-25 | 2020-09-25 | 2020-12-16 | 2020-09-15 |  |  |  | No |  |  | Not Required
22INR0424 | BRP Denali BESS | SS Completed, FIS Started, No IA | BRP Denali BESS LLC | Tap 138kV 5395 Sommers - 5030 Braunig East | Bexar | SOUTH | 2022-11-30 | OTH | BA | 258.41 |  | 2020-09-25 | 2020-09-25 | 2020-12-16 | 2020-09-17 |  |  |  | No |  |  | Not Required
22INR0426 | LUBIO SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY INFRASTRUCTURE | tap 138kV 2732 Marshall - 2434 Seagoville | Kaufman | NORTH | 2023-10-22 | SOL | PV | 54.47 | MW Size | 2021-07-01 | 2020-10-07 | 2020-12-28 | 2021-06-28 |  |  |  | No |  |  | Not Required
22INR0427 | BRP Kabru BESS | SS Completed, FIS Started, No IA | BRP Kabru BESS LLC | 1159 Andrew North - 11284 Blackbird 138kV | Andrews | WEST | 2023-03-30 | OTH | BA | 202.45 |  | 2020-09-28 | 2020-10-07 | 2020-12-28 | 2020-09-22 |  |  |  | No |  |  | Not Required
22INR0429 | Sun Valley BESS | SS Completed, FIS Started, No IA | Sun Valley Solar LLC | tap 345kV 68090 Sam Sw - 3405 Tradinghouse | Hill | NORTH | 2023-05-31 | OTH | BA | 187.5 |  | 2021-02-09 | 2020-10-07 | 2020-12-28 | 2021-01-20 |  |  |  | No |  |  | Not Required
22INR0431 | Raoul Solar | SS Completed, FIS Started, No IA | Leeward Renewable Energy Development, LLC | tap 138kV 44010 W.A. Parish - 42980 Nash. | Fort Bend | HOUSTON | 2023-12-28 | SOL | PV | 201.5 |  |  | 2020-10-07 | 2020-12-28 | 2021-06-22 |  |  |  | No |  |  | Not Required
22INR0436 | Noble Storage | SS Completed, FIS Completed, IA | Noble Storage, LLC | 1730 Krum West 345kV | Denton | NORTH | 2022-06-01 | OTH | BA | 127 |  | 2020-11-16 | 2020-10-23 | 2021-01-12 | 2020-11-10 | 2021-07-23 | No | 2021-05-13 | No |  |  | Not Required
22INR0437 | TORMES SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY | tap 345kV 1907 Venus - 68091 Navarro | Navarro | NORTH | 2023-12-15 | SOL | PV | 380.65 | FIS Request | 2021-07-26 | 2020-10-23 | 2021-01-12 | 2021-07-19 07:31 |  |  |  | No |  |  | Not Required
22INR0439 | Kirkwall Solar | SS Completed, FIS Started, No IA | ABEI ENERGY | tap 138kV 3659 Thorndale - 3658 Taylor | Williamson | SOUTH | 2023-12-27 | SOL | PV | 73.06 | FIS Request | 2021-07-30 | 2020-11-05 | 2021-01-12 | 2021-07-21 02:25 |  |  |  | No |  |  | Not Required
22INR0441 | Milwaukee Solar | SS Completed, FIS Started, No IA | Leeward Renewable Energy Development, LLC | tap 138kV 8608 Pavlov to 8127 South Lane City | Matagorda | COASTAL | 2022-12-30 | SOL | PV | 201.5 |  | 2021-03-15 | 2020-11-05 | 2021-01-12 | 2021-02-25 |  |  |  | No |  |  | Not Required
22INR0443 | Bowstring BESS | SS Completed, FIS Started, No IA | Longbow Energy Storage, LLC | 8961 White Point 138kV | San Patricio | COASTAL | 2022-12-31 | OTH | BA | 158.69 |  | 2021-04-01 | 2020-11-18 | 2021-02-09 | 2021-03-24 |  |  |  | No |  |  | Not Required
22INR0445 | SPC Bloom BESS | SS Completed, FIS Started, No IA | Victoria Battery LLC | 8911 Black Bayou 138kV | Victoria | SOUTH | 2023-06-01 | OTH | BA | 100 | COD | 2021-02-04 | 2020-12-03 | 2021-02-19 | 2020-11-13 |  |  |  | No |  |  | Not Required
22INR0447 | Mark One Energy Storage | SS Completed, FIS Started, No IA | Mark One Energy Storage, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2022-10-01 | OTH | BA | 202.32 | COD | 2020-11-25 | 2020-12-03 | 2021-02-19 | 2020-11-25 |  |  |  | No |  |  | Not Required
22INR0448 | Brotman Energy Storage | SS Completed, FIS Completed, No IA | Brotman Energy Storage, LLC | tap 138kV 44600 Rosharon - 44410 Karsten | Brazoria | COASTAL | 2022-06-01 | OTH | BA | 50.8 |  | 2020-11-25 | 2020-12-03 | 2021-03-10 | 2020-11-25 | 2021-05-21 | No |  | No |  |  | Not Required
22INR0449 | Sibyl Energy Storage | SS Completed, FIS Started, No IA | Sibyl Energy Storage, LLC | Tap 138kV 43261 Southwyck - 44552 Telview | Fort Bend | HOUSTON | 2023-08-01 | OTH | BA | 202.32 |  | 2020-11-25 | 2020-12-03 | 2021-02-18 | 2020-11-25 |  |  |  | No |  |  | Not Required
22INR0450 | PES Energy Storage | SS Completed, FIS Started, No IA | HO Clarke Energy Storage, LLC | 47150 H.O. Clarke 138kV | Harris | HOUSTON | 2022-06-01 | OTH | BA | 100.8 |  | 2020-11-25 | 2021-02-09 | 2021-05-06 | 2020-12-03 |  |  |  | No |  |  | Not Required
22INR0454 | DR Solar | SS Completed, FIS Started, No IA | Chevron USA, Inc | tap 138kV 11112 Chimney Well - 11271 Owl Hill | Culberson | WEST | 2023-06-02 | SOL | PV | 45 |  | 2020-11-04 | 2020-12-22 | 2021-03-10 | 2020-12-17 |  |  |  | No |  |  | Not Required
22INR0455 | Blue Sky Sol | SS Completed, FIS Started, No IA | UKA North America, LLC | 6562 Friends Ranch 138kV | Crockett | WEST | 2022-12-15 | SOL | PV | 101.2 |  | 2020-12-09 | 2020-12-03 | 2021-02-16 | 2020-11-10 |  |  |  | No |  |  | Not Required
22INR0461 | Daltus DG | SS Completed, FIS Started, No IA | Duke Energy One, Inc. | 60721 Cryo4A 138kV | Reeves | WEST | 2023-01-01 | GAS | IC | 19.5 |  | 2021-05-24 | 2021-03-16 | 2021-05-28 | 2021-05-18 |  |  |  | No
22INR0462 | Old Aqueduct Solar | SS Completed, FIS Started, No IA | Old Aqueduct Solar | 23920 Blackwater 345kV | Hale | PANHANDLE | 2023-06-01 | SOL | PV | 511.63 | FIS Request | 2021-07-09 | 2020-12-03 | 2021-02-19 | 2021-06-29 |  |  |  | No |  |  | Not Required
22INR0480 | Pachanga Wind | SS Completed, FIS Started, No IA | Big Wind, LLC | tap 345kV 5966 Palmito - 80137 Stewart Rd | Cameron | COASTAL | 2023-07-01 | WIN | WT | 300 |  | 2021-06-28 | 2021-02-09 | 2021-05-06 | 2021-04-05 |  |  |  | No |  |  | Not Required
22INR0482 | Cutlass Solar II | SS Completed, FIS Started, No IA | Cutlass Solar II LLC | tap 345kV 44005 WAP - 44090 Cedar Creek | Fort Bend | HOUSTON | 2022-08-01 | SOL | PV | 200.33 |  | 2020-12-29 | 2020-12-23 | 2017-11-20 | 2020-12-28 |  |  |  | No |  |  | Not Required
22INR0485 | House Mountain 2 Batt | SS Completed, FIS Started, IA | House Mountain LLC | 6674 Bronco 69kV | Brewster | WEST | 2023-02-01 | OTH | BA | 52.42 | SFS/NtP | 2020-12-23 | 2021-01-26 | 2021-04-12 | 2020-12-23 |  |  | 2021-07-07 | Yes |  |  | Not Required
22INR0488 | Venture Hill Storage | SS Completed, FIS Started, No IA | KCE TX 24, LLC | 7336 Gilleland Creek 138kV | Travis | SOUTH | 2022-12-01 | OTH | BA | 51.8 |  | 2021-01-08 | 2021-02-09 | 2021-05-06 | 2020-12-29 |  |  |  | No |  |  | Not Required
22INR0489 | Christoval Solar | SS Completed, FIS Started, No IA | Bridgelink Renewable Energy Investments | 76003 Big Hills 345kV | Tom Green | WEST | 2022-10-30 | SOL | PV | 324 |  | 2021-05-07 | 2021-02-04 | 2021-04-19 | 2021-04-30 |  |  |  | No |  |  | Not Required
22INR0490 | Saracen I Energy Storage | SS Completed, FIS Started, No IA | Saracen I Energy Storage LLC | 47150 HO Clarke 138kV | Harris | HOUSTON | 2022-12-01 | OTH | BA | 101.63 |  | 2021-03-05 | 2021-03-16 | 2021-05-28 | 2021-03-05 |  |  |  | No |  |  | Not Required
22INR0491 | Saracen II Energy Storage | SS Completed, FIS Started, No IA | Saracen II Energy Storage LLC | 47150 HO Clarke 138kV | Harris | HOUSTON | 2022-12-01 | OTH | BA | 101.63 |  | 2021-03-03 | 2021-03-16 | 2021-05-28 | 2021-03-05 |  |  |  | No |  |  | Not Required
22INR0495 | TIMBERWOLF BESS 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 76635 King Mt 138kV | Upton | WEST | 2022-06-01 | OTH | BA | 150 |  | 2021-01-28 | 2021-04-01 | 2021-06-10 | 2021-03-15 |  |  |  | No |  |  | Not Required
22INR0499 | Aquilla Lake 3 Wind | SS Completed, FIS Started, No IA | Aquilla Lake 3 Wind | 68090 Sam Switch 345 kV | Hill | NORTH | 2022-12-31 | WIN | WT | 305 |  | 2021-03-05 | 2021-03-08 | 2021-05-28 | 2021-02-18 |  |  |  | No |  |  | Not Required
22INR0502 | White Mesa 3 Wind | SS Completed, FIS Started, No IA | White Mesa III Wind, LLC | 76005 Schneeman Draw 345kV | Crockett | WEST | 2022-11-30 | WIN | WT | 310 |  | 2021-02-23 | 2021-03-01 | 2021-05-13 | 2021-02-24 |  |  |  | No |  |  | Not Required
22INR0503 | Tidwell Prairie II Batt | SS Completed, FIS Started, No IA | TIDWELL PRAIRIE LLC | Tap 345kV 3400 Twin Oak - 39950 TNP One | Robertson | NORTH | 2023-06-01 | OTH | BA | 101.63 |  | 2021-03-02 | 2021-03-16 | 2021-05-28 | 2021-02-17 |  |  |  | No |  |  | Not Required
22INR0504 | Tidwell Prairie III Batt | SS Completed, FIS Started, No IA | Tidwell Prairie LLC | Tap 345kV 3400 Twin Oak - 39950 TNP One | Robertson | NORTH | 2023-06-01 | OTH | BA | 101.63 |  | 2021-03-02 | 2021-03-16 | 2021-05-28 | 2021-02-17 |  |  |  | No |  |  | Not Required
22INR0509 | Turquoise Storage | SS Completed, FIS Started, No IA | Belltown Power Texas | 6950 Wallace Switch 138kV | Hunt | NORTH | 2022-12-31 | OTH | BA | 190 |  | 2021-03-19 | 2021-03-18 | 2021-06-11 | 2021-03-18 |  |  |  | No |  |  | Not Required
22INR0511 | Gransolar Texas One | SS Completed, FIS Started, No IA | Gransolar Texas One, LLC | Tap 138kV 3659 Thorndale North - 116 Salty | Milam | SOUTH | 2023-11-23 | SOL | PV | 60.86 |  | 2021-03-10 | 2021-03-16 | 2021-06-11 | 2021-03-08 |  |  |  | No |  |  | Not Required
22INR0515 | Flagtail BESS | SS Completed, FIS Started, No IA | Flagtail LLC | Tap 138kV 5 Sandy Switch - 7 Sandy | Grimes | NORTH | 2023-03-01 | OTH | BA | 203.8 |  | 2021-03-15 | 2021-04-05 | 2021-06-24 | 2021-03-15 |  |  |  | No |  |  | Not Required
22INR0516 | Amber Storage | SS Completed, FIS Started, No IA | Belltown Power Texas | 730 Wolf Ridge 138kV | Cooke | NORTH | 2022-12-31 | OTH | BA | 50 |  | 2021-03-19 | 2021-03-19 | 2021-06-11 | 2021-03-19 |  |  |  | No |  |  | Not Required
22INR0517 | Ray Gulf Wind | SS Completed, FIS Started, No IA | Lane City Wind, LLC | 44040 Bailey 345kV | Wharton | SOUTH | 2022-12-31 | WIN | WT | 207 |  | 2021-05-05 | 2021-04-26 | 2021-07-28 | 2021-04-26 |  |  |  | No |  |  | Not Required
22INR0523 | Midlothian 4 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1940 Midlothian ANP 345kV | Ellis | NORTH | 2022-02-01 | GAS | CC | 18 |  | 2021-04-28 | 2021-04-26 | 2021-07-28 | 2021-04-21 |  |  |  | No
22INR0524 | St. Gall I Energy Storage | SS Completed, FIS Started, No IA | St. Gall Energy Storage LLC | 38355 TNLeon Creek 138kV | Pecos | WEST | 2022-06-01 | OTH | BA | 127.04 |  | 2021-04-15 | 2021-04-13 | 2021-07-02 | 2021-04-08 |  |  |  | No |  |  | Not Required
22INR0525 | St. Gall II Energy Storage | SS Completed, FIS Started, No IA | St. Gall Energy Storage LLC | 38355 TNLeon Creek 138kV | Pecos | WEST | 2023-06-01 | OTH | BA | 127.04 |  | 2021-04-15 | 2021-04-13 | 2021-07-02 | 2021-04-08 |  |  |  | No |  |  | Not Required
22INR0526 | Pine Forest BESS | SS Completed, FIS Started, No IA | Pine Forest Hybrid I, LLC | tap 345kV 1696 Monticello SES - 2514 Allen Switch | Hopkins | NORTH | 2023-01-27 | OTH | BA | 400 | FIS Request | 2021-07-30 | 2021-05-04 | 2021-07-30 | 2021-07-19 |  |  |  | No |  |  | Not Required
22INR0527 | Lily Solar (Close Boze - I20 - Rosehill) | SS Completed, FIS Started, No IA | Lily Solar, LLC | 6903 Boze Switch (Close Path to Rosehill via I20_RC) | Kaufman | NORTH | 2022-05-01 | SOL | PV | 0 | COD | 2021-05-05 | 2021-05-10 | 2021-05-17 | 2021-04-29 |  |  |  | No |  |  | Not Required | [7 empty] | This project is for the purposes of studying a different transmission configuration for the facility study and isn't actually an interconnection request. No additional MWs added. Refer to 19INR0044, Lily Solar.
22INR0528 | Lily Storage (Close Boze - I20 - Rosehill) | SS Completed, FIS Started, No IA | Lily Solar, LLC | 6903 Boze Switch (Close Path to Rosehill via I20_RC) | Kaufman | NORTH | 2022-05-01 | OTH | BA | 0 | COD | 2021-05-05 | 2021-05-10 | 2021-05-17 | 2021-04-29 |  |  |  | No |  |  | Not Required | [7 empty] | This project is for the purposes of studying a different transmission configuration for the facility study and isn't actually an interconnection request. No additional MWs added. Refer to 20INR0294, Lily Storage.
22INR0533 | Temple Generation I Repower | SS Completed, FIS Started, No IA | Panda Temple Power | 3413 Knob Creek 345kV | Bell | NORTH | 2022-06-15 | GAS | CC | 67 |  | 2021-04-26 | 2021-04-26 | 2021-05-13 | 2021-04-22 |  |  |  | No
22INR0535 | Bastrop Energy Center AGP repower Phase II | SS Completed, FIS Started, No IA | Bastrop Energy Partners LP | 7049 Bastrop 345kV | Bastrop | SOUTH | 2022-04-30 | GAS | CC | 21 | COD | 2021-06-17 | 2021-04-26 | 2021-07-28 | 2021-06-14 |  |  |  | No
22INR0540 | Walstrom BESS | SS Started, FIS Started, No IA | Castleman Power | 46220 Peters 138kV | Austin | SOUTH | 2022-12-01 | OTH | BA | 200 |  | 2021-05-17 | 2021-07-08 |  | 2021-06-03 |  |  |  | No |  |  | Not Required
22INR0543 | Midlothian Unit 3 repower | SS Started, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1940 Midlothian ELP 345kV | Ellis | NORTH | 2022-02-01 | GAS | CC | 18 |  | 2021-05-21 | 2021-05-21 |  | 2021-05-11 |  |  |  | No
23INR0006 | Sierra Madre Solar | SS Completed, FIS Started, No IA | Rancho Verde Solar | tap 345kV 80307 Del Sol - 80225 Cenizo | Zapata | SOUTH | 2023-12-01 | SOL | PV | 255.15 |  | 2020-10-07 | 2020-01-22 | 2020-04-08 | 2020-10-05 |  |  |  | No |  |  | Not Required
23INR0007 | Outpost Solar | SS Completed, FIS Started, No IA | Hecate Energy Outpost Solar LLC | Tap 345kV 80219 Lobo - 5709 Fowlerton | Webb | SOUTH | 2023-12-01 | SOL | PV | 513.7 |  | 2020-02-11 | 2019-12-06 | 2020-02-25 | 2019-12-02 |  |  |  | No |  |  | Not Required
23INR0008 | Harley Hand Solar | SS Completed, FIS Started, No IA | HECTATE ENERGY HARLEY HAND SOLAR LLC | 11420 Sweetwater East 345kV | Nolan | WEST | 2023-12-01 | SOL | PV | 513.7 |  | 2019-12-12 | 2019-12-16 | 2020-03-11 | 2019-12-06 |  |  |  | No |  |  | Not Required
23INR0009 | Shaula III Solar | SS Completed, FIS Started, No IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 2 | DeWitt | SOUTH | 2024-06-01 | SOL | PV | 205.2 |  | 2020-01-13 | 2019-12-18 | 2020-03-11 | 2019-12-18 |  |  |  | No |  |  | Not Required
23INR0010 | Plateau Solar | SS Completed, FIS Started, No IA | Innovative Solar 206, LLC | tap 345kV 68000 West Shackelford - 68001 Claytonville | Jones | WEST | 2023-04-13 | SOL | PV | 300 |  | 2020-09-04 | 2019-12-06 | 2020-02-25 | 2020-08-20 |  |  |  | No |  |  | Not Required
23INR0014 | Hedgehog Solar | SS Completed, FIS Started, No IA | Innovative Solar 408, LLC | tap 138kV 8234 Uvalde - 8241 Razorback | Medina | SOUTH | 2023-04-20 | SOL | PV | 85 |  | 2020-09-16 | 2019-12-11 | 2020-03-06 | 2020-08-31 |  |  |  | No |  |  | Not Required
23INR0015 | Scarlet Solar | SS Completed, FIS Started, No IA | Innovative Solar 416, LLC | tap 345kV 23912 Ogallala - 23910 Windmill | Castro | PANHANDLE | 2023-04-20 | SOL | PV | 180 |  | 2020-09-16 | 2019-12-11 | 2020-03-06 | 2020-08-31 |  |  |  | No |  |  | Not Required
23INR0019 | Blue Jay BESS | SS Completed, FIS Started, No IA | Blue Jay Solar I, LLC | 4 IOLA 138kV | Grimes | NORTH | 2022-11-17 | OTH | BA | 51.63 |  | 2021-04-15 | 2020-01-06 | 2020-03-30 | 2021-04-05 |  |  |  | No |  |  | Not Required
23INR0021 | Hornet Solar | SS Completed, FIS Started, No IA | Hornet Solar LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala | Swisher | PANHANDLE | 2023-12-31 | SOL | PV | 503.21 |  | 2020-05-15 | 2020-02-04 | 2020-04-29 | 2020-02-04 |  |  |  | No |  |  | Not Required
23INR0026 | Baker Branch Solar | SS Completed, FIS Started, No IA | Mockingbird Solar Center, LLC | tap 345kV 1692 Paris - 1690 Valley | Lamar | NORTH | 2023-02-28 | SOL | PV | 400 |  | 2020-04-09 | 2020-03-26 | 2020-06-04 | 2020-03-05 |  |  |  | No |  |  | Not Required
23INR0029 | Cedar Bayou5 | SS Completed, FIS Started, No IA | NRG Cedar Bayou 5 LLC | 40000 Cedar Bayou 345kV | Chambers | HOUSTON | 2023-06-01 | GAS | CC | 697 |  | 2020-03-31 | 2020-03-26 | 2020-06-04 | 2020-03-18 |  | No |  | No
23INR0030 | Langer Solar | SS Completed, FIS Started, No IA | Langer Solar LLC | tap 345kV 68040 Kopperl - 68091 Navarro | Bosque | NORTH | 2023-08-31 | SOL | PV | 249.8 |  | 2020-11-06 | 2020-06-03 | 2020-08-18 | 2020-10-30 |  |  |  | No |  |  | Not Required
23INR0031 | Solace Solar | SS Completed, FIS Completed, No IA | IP QUANTUM, LLC. | tap 345kV 1430 Graham - 1048 Tonkawas | Haskell | WEST | 2023-05-31 | SOL | PV | 374.4 |  | 2020-04-21 | 2020-04-22 | 2020-07-09 | 2020-04-03 | 2021-03-02 |  |  | No |  |  | Not Required
23INR0035 | Starling Solar | SS Completed, FIS Started, No IA | Starling Solar, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2023-10-30 | SOL | PV | 123 |  | 2021-02-09 | 2020-06-26 | 2020-09-14 | 2021-01-22 |  |  |  | No |  |  | Not Required
23INR0040 | Dore BQ Solar | SS Completed, FIS Started, No IA | Sunnyside Energy, LLC | tap 138kV 47210 Holmes – 42680 Garden Villas | Harris | HOUSTON | 2023-01-15 | SOL | PV | 50.42 |  | 2021-02-10 | 2020-06-09 | 2020-08-18 | 2021-01-29 |  |  |  | No |  |  | Not Required
23INR0042 | Delilah Solar 3 | SS Completed, FIS Completed, IA | Delilah Solar Energy III LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 |  | 2019-05-13 | 2020-06-03 | 2018-01-03 |  | 2020-06-09 |  | 2020-12-22 | Yes |  |  | Not Required | 2021-03-23
23INR0044 | Parliament Solar | SS Completed, FIS Completed, No IA | AP Solar 8, LLC | Tap 345kV 44900 Zenith - 967 Gibbons Creek ckt 18 | Waller | HOUSTON | 2023-05-31 | SOL | PV | 406.4 |  | 2020-08-03 | 2020-06-19 | 2020-09-08 | 2020-06-08 | 2021-06-23 |  |  | No |  |  | Not Required
23INR0045 | GP Solar | SS Completed, FIS Started, No IA | HEP Aquamarine Holdings LLC | Tap 138kV 6829 Glen Pine - 6833 Explorer | Van Zandt | NORTH | 2023-06-01 | SOL | PV | 121.97 |  | 2016-02-23 | 2020-09-25 | 2020-12-16 | 2021-02-22 |  |  |  | No |  |  | Not Required
23INR0047 | Charger Solar | SS Completed, FIS Started, IA | AP Solar 4, LLC | tap 345kV 8249 Angstrom – 5915 STP | Refugio | COASTAL | 2023-03-31 | SOL | PV | 406.77 |  | 2020-07-29 | 2020-06-19 | 2020-09-08 | 2020-06-07 |  | No | 2021-06-05 | Yes |  |  | Not Required
23INR0048 | Equinox Storage | SS Completed, FIS Started, No IA | Invenergy Storage Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2025-12-31 | OTH | BA | 101.2 | COD | 2021-03-23 | 2020-06-26 | 2020-09-14 | 2021-03-12 |  |  |  | No |  |  | Not Required
23INR0054 | Tanglewood Solar | SS Completed, FIS Started, No IA | Brazoria Solar, LLC | tap 345kV 42500 Dow - 43035 Oasis | Brazoria | COASTAL | 2023-10-01 | SOL | PV | 408.01 |  | 2021-01-15 | 2020-07-10 | 2020-09-28 | 2020-11-24 |  |  |  | No |  |  | Not Required
23INR0055 | Tabor Solar | SS Completed, FIS Started, No IA | Quanah Solar LLC | tap 345kV 60504 Tesla - 61001 Jim Treece | Hardeman | WEST | 2023-05-15 | SOL | PV | 506.4 |  | 2020-08-31 | 2020-09-02 | 2020-11-19 | 2020-07-07 |  | No |  | No |  |  | Not Required
23INR0056 | Caliche Mound Solar | SS Completed, FIS Started, No IA | Tierra Blanco Solar LLC | tap 345kV 23906 AJSwope - 23910 Windmill | Deaf Smith | PANHANDLE | 2023-05-15 | SOL | PV | 405.74 |  | 2020-08-27 | 2020-07-24 | 2020-09-08 | 2020-07-07 |  |  |  | No |  |  | Not Required
23INR0057 | Duffy Solar | SS Completed, FIS Started, No IA | VDA Solar Texas 1 LLC | Tap 345kV 5915 STP - 44000 W_A_Parrish c39 | Matagorda | COASTAL | 2023-06-01 | SOL | PV | 545.21 |  | 2021-02-05 | 2020-09-11 | 2020-11-19 | 2021-02-04 |  |  |  | No |  |  | Not Required
23INR0058 | Erin Solar | SS Completed, FIS Started, No IA | Erin Solar LLC | Tap 345kV 44040 Bailey - 44200 Hillje, c72 | Wharton | SOUTH | 2023-06-01 | SOL | PV | 202.5 |  | 2021-02-15 | 2020-07-24 | 2020-10-08 | 2021-01-26 |  |  |  | No |  |  | Not Required
23INR0059 | Briggs Solar | SS Completed, FIS Started, No IA | Briggs Solar, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2024-05-31 | SOL | PV | 309.6 |  | 2021-03-15 | 2020-08-04 | 2020-10-28 | 2021-03-04 |  |  |  | No |  |  | Not Required
23INR0060 | Delilah Solar 4 | SS Completed, FIS Completed, IA | Delilah Solar Energy IV LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2023-06-30 | SOL | PV | 90 |  | 2019-05-13 |  | 2019-01-03 |  | 2020-06-09 |  | 2020-12-22 | Yes | Not Required | Not Required | Not Required | 2021-03-23
23INR0061 | Noria Solar DCC | SS Completed, FIS Started, No IA | Noria Hondo Solar, LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2023-06-30 | SOL | PV | 145 |  | 2021-03-15 | 2020-08-04 | 2020-10-28 | 2021-03-10 |  |  |  | No |  |  | Not Required
23INR0062 | Noria Storage | SS Completed, FIS Started, No IA | Noria Hondo Solar, LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2023-06-30 | OTH | BA | 75 |  | 2021-04-01 | 2020-08-04 | 2020-10-28 | 2021-03-30 |  |  |  | No |  |  | Not Required
23INR0065 | Bonita Creek Solar | SS Completed, FIS Started, No IA | Invenergy Solar Development North America LLC | tap 345kV 5133 Elm Creek - 5901 San Miguel | Atascosa | SOUTH | 2024-06-01 | SOL | PV | 200 |  | 2021-07-16 | 2020-12-03 | 2021-03-10 | 2021-06-16 |  |  |  | No |  |  | Not Required
23INR0066 | Accalia Point Solar | SS Completed, FIS Started, No IA | South Wolf Solar LLC | Tap 345kV 5966 Palmito - 80137 Stewart | Cameron | COASTAL | 2023-06-01 | SOL | PV | 158.76 |  | 2021-02-10 | 2020-10-23 | 2021-01-12 | 2021-01-27 |  |  |  | No |  |  | Not Required
23INR0069 | Corbin Grid BESS | SS Completed, FIS Completed, No IA | Corbin Grid, LLC | 44510 Obrien 138kV | Fort Bend | HOUSTON | 2023-05-31 | OTH | BA | 202.76 |  | 2020-08-28 | 2020-08-04 | 2020-11-02 | 2020-07-24 | 2021-04-30 |  |  | No |  |  | Not Required
23INR0070 | Chillingham Solar | SS Completed, FIS Completed, No IA | 250LB 8me | 3687 Bell County East 345kV | Bell | NORTH | 2023-06-01 | SOL | PV | 359.37 |  | 2020-09-02 | 2020-08-04 | 2020-10-28 | 2020-08-26 | 2021-07-22 |  |  | No | Not Required | Not Required | Not Required
23INR0071 | BRP Volans BESS | SS Completed, FIS Started, No IA | BRP Volans BESS LLC | 11189 Quarry Field SW - 1074 Wink 138kV | Winkler | WEST | 2023-03-31 | OTH | BA | 202.47 |  | 2020-08-26 | 2020-08-04 | 2020-10-28 | 2020-08-24 |  |  |  | No |  |  | Not Required
23INR0072 | BRP Tortolas BESS | SS Completed, FIS Completed, IA | BRP Tortolas BESS LLC | 39030 Alvin 138kV | Brazoria | COASTAL | 2022-02-01 | OTH | BA | 50.67 | SFS/NtP | 2020-08-27 | 2020-08-04 | 2020-10-28 | 2020-08-24 | 2021-07-30 |  | 2021-07-15 | Yes | Not Required | Not Required | Not Required | 2021-07-30 | 2021-07-30 | 2021-07-30
23INR0073 | BRP Galan BESS | SS Completed, FIS Started, No IA | BRP Galan BESS LLC | 5007 Alamo One 138kV | Bexar | SOUTH | 2023-03-31 | OTH | BA | 75.97 |  | 2020-08-20 | 2020-08-04 | 2020-10-28 | 2020-08-17 |  |  |  | No |  |  | Not Required
23INR0074 | BRP Ampato BESS | SS Completed, FIS Started, No IA | BRP Ampato BESS LLC | 10002 NS Crane Switch 138kV | Crane | WEST | 2023-03-31 | OTH | BA | 121.56 |  | 2020-08-26 | 2020-08-04 | 2020-10-28 | 2020-08-24 |  |  |  | No |  |  | Not Required
23INR0075 | BRP Rhine BESS | SS Completed, FIS Started, No IA | BRP Rhine BESS LLC | Tap 345kV 11188 QUARRYFLD - 11010 WOLF | Ward | WEST | 2023-03-31 | OTH | BA | 202.47 |  | 2020-09-22 | 2020-08-04 | 2020-11-02 | 2020-09-17 |  |  |  | No |  |  | Not Required
23INR0076 | Cannon Solar SLF | SS Completed, FIS Started, No IA | Duke Energy Renewables Solar, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2023-12-31 | SOL | PV | 152.5 |  | 2020-09-21 | 2020-09-11 | 2020-12-07 | 2020-09-11 |  |  |  | No |  |  | Not Required
23INR0078 | Shaw Solar | SS Completed, FIS Started, No IA | Montague Solar, LLC | 7438 L Bandera 138kV | Bandera | SOUTH | 2023-10-31 | SOL | PV | 123 |  | 2021-05-21 | 2020-10-23 | 2021-01-12 | 2021-05-11 |  |  |  | No |  |  | Not Required
23INR0079 | Chillingham Storage | SS Completed, FIS Completed, No IA | 250LB 8me | 3687 Bell County East 345kV | Bell | NORTH | 2023-06-01 | OTH | BA | 153.75 |  | 2020-09-04 | 2020-09-11 | 2020-11-30 | 2020-08-26 | 2021-07-22 |  |  | No | Not Required | Not Required | Not Required
23INR0080 | Soda Lake Solar 1 | SS Completed, FIS Started, No IA | Crane Solar Generating 2 | 76026 Soda Lake 138kV | Crane | WEST | 2023-05-22 | SOL | PV | 202.59 |  | 2020-09-08 | 2020-09-11 | 2020-11-30 | 2020-08-24 |  |  |  | No |  |  | Not Required
23INR0082 | Bottom Grass Solar | SS Completed, FIS Started, No IA | Bottom Grass Solar Project, LLC | tap 345 kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2023-12-31 | SOL | PV | 508.61 |  | 2020-10-19 | 2020-11-05 | 2021-02-02 | 2020-10-21 |  |  |  | No |  |  | Not Required
23INR0083 | Bottom Grass BESS | SS Completed, FIS Started, No IA | Bottom Grass Solar Project, LLC | tap 345 kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2023-12-31 | OTH | BA | 202.21 |  | 2020-10-19 | 2020-11-05 | 2021-02-02 | 2020-10-21 |  |  |  | No |  |  | Not Required
23INR0084 | Lavaca Bay Solar | SS Completed, FIS Started, No IA | Lavaca Bay Solar Project LLC | Tap 345kV 5915 STP - 47531 Jones Creek ckt 18 | Matagorda | COASTAL | 2023-08-15 | SOL | PV | 243.46 |  | 2021-03-05 | 2020-09-11 | 2020-11-19 | 2021-03-05 |  |  |  | No |  |  | Not Required
23INR0086 | Hanson Solar | SS Completed, FIS Started, No IA | Hanson Solar, LLC | tap 345kV 1444 Brown - 11406 Central Bluff | Coleman | WEST | 2024-05-31 | SOL | PV | 396 |  | 2021-03-30 | 2020-10-23 | 2021-02-02 | 2021-03-25 |  |  |  | No |  |  | Not Required
23INR0087 | Kinenos Solar | SS Completed, FIS Started, No IA | Encino del Sol Energy, LLC | tap 345kV 8905 North Edinburg - 8455 Lon Hill | Brooks | SOUTH | 2023-12-31 | SOL | PV | 203.17 |  | 2020-08-28 | 2020-12-22 | 2021-03-10 | 2020-12-03 |  |  |  | No |  |  | Not Required
23INR0088 | Nockenut Springs Solar 1 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Guadalupe | SOUTH | 2023-12-31 | SOL | PV | 203.17 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No |  |  | Not Required
23INR0089 | Donegal Solar | SS Completed, FIS Started, No IA | HE-Cottonwood Solar, LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2023-09-30 | SOL | PV | 204.2 |  | 2020-10-08 | 2020-10-07 | 2020-12-28 | 2020-09-11 |  |  |  | No |  |  | Not Required
23INR0090 | Iguala Solar | SS Completed, FIS Started, No IA | Igualla LLC | tap 345kV 5915 STP - 8249 Angstrom | Victoria | SOUTH | 2023-06-01 | SOL | PV | 250 |  | 2021-06-11 | 2020-10-07 | 2020-12-28 | 2021-06-07 |  |  |  | No |  |  | Not Required
23INR0091 | Cascade Solar | SS Completed, FIS Started, No IA | Oyster Creek LLC | tap 345kV 42500 Dow - 43035 Oasis | Brazoria | COASTAL | 2023-12-01 | SOL | PV | 250 | COD | 2021-05-05 | 2021-02-09 | 2021-05-06 | 2021-04-28 |  |  |  | No |  |  | Not Required
23INR0093 | Alila Solar | SS Completed, FIS Started, No IA | Electra Energy Project, LLC | 8249 Angstrom 345kV | San Patricio | COASTAL | 2023-05-05 | SOL | PV | 256.5 |  | 2020-10-19 | 2020-10-07 | 2020-12-30 | 2020-09-11 |  |  |  | No |  |  | Not Required
23INR0094 | BRP Pyxis BESS | SS Completed, FIS Started, No IA | BRP Pyxis BESS LLC | tap 138kV 1009 Yucca - 11197 Sand Tank Pod | Ward | WEST | 2023-03-01 | OTH | BA | 202.45 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No |  |  | Not Required
23INR0095 | Brotman Power Station | SS Completed, FIS Completed, No IA | Brotman Generating, LLC | tap 138kV 44600 Rosharon - 44410 Karsten | Brazoria | COASTAL | 2023-05-01 | GAS | GT | 348.46 |  | 2020-10-09 | 2020-10-23 | 2021-02-02 | 2020-10-06 | 2021-05-21 | No |  | No
23INR0100 | Evergreen Solar | SS Completed, FIS Started, No IA | Bucks Bayou LLC | 8111 Magilla 138kV | Matagorda | COASTAL | 2023-12-29 | SOL | PV | 150 |  | 2021-07-02 | 2020-12-03 | 2021-02-18 | 2021-06-07 |  |  |  | No |  |  | Not Required
23INR0101 | Atria Solar | SS Completed, FIS Started, No IA | Atria Energy Project, LLC | 40770 Hacher 138kV | Chambers | HOUSTON | 2023-04-19 | SOL | PV | 112.4 |  | 2020-10-19 | 2020-10-23 | 2021-01-12 | 2020-09-28 |  |  |  | No |  |  | Not Required
23INR0103 | Donegal BESS | SS Completed, FIS Started, No IA | HE-Cottonwood Solar, LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2023-11-20 | OTH | BA | 101.3 |  | 2020-10-12 | 2020-10-23 | 2021-01-12 | 2020-09-28 |  |  |  | No |  |  | Not Required
23INR0104 | BRP Kamet BESS | SS Completed, FIS Started, No IA | BRP Kamet BESS LLC | Andrews North – McKenzie Draw Switch 138 kV | Andrews | WEST | 2023-04-30 | OTH | BA | 202.46 |  | 2020-09-28 | 2020-10-07 | 2020-12-30 | 2020-09-23 |  |  |  | No |  |  | Not Required
23INR0106 | Vorsavio Grid BESS | SS Completed, FIS Started, No IA | Vorsavio Grid, LLC | 80013 Laredo VFT 138kV | Webb | SOUTH | 2023-07-31 | OTH | BA | 100.67 |  | 2021-05-21 | 2020-10-07 | 2020-12-30 | 2021-05-13 |  |  |  | No |  |  | Not Required
23INR0111 | G-STAR Solar | SS Completed, FIS Started, No IA | GulfStar Power, LLC | tap 345kV 44040 Bailey - 42530 Jones Creek ckt 62 | Wharton | SOUTH | 2023-04-01 | SOL | PV | 608.76 |  | 2020-12-03 | 2020-10-23 | 2021-02-02 | 2020-11-24 |  | No |  | No |  |  | Not Required
23INR0113 | Cannon Storage SLF | SS Completed, FIS Started, No IA | Duke Energy Renewables Solar, LLC | Tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2023-12-31 | OTH | BA | 0 |  | 2020-10-19 | 2020-11-05 | 2020-12-07 | 2020-10-29 |  |  |  | No |  |  | Not Required
23INR0115 | BRP Pobeda BESS | SS Completed, FIS Started, No IA | BRP Pobeda BESS LLC | 44645 Singleton 345kV | Grimes | NORTH | 2023-06-01 | OTH | BA | 301.44 |  | 2020-11-06 | 2020-11-18 | 2021-02-08 | 2020-10-27 |  |  |  | No |  |  | Not Required
23INR0116 | Cantaloupe Solar | SS Completed, FIS Started, No IA | Saragosa Del Sol Energy LLC | 60716 Saragosa 138kV | Reeves | WEST | 2023-12-01 | SOL | PV | 303.13 |  | 2020-10-28 | 2020-12-22 | 2021-03-09 | 2020-12-01 |  |  |  | No |  |  | Not Required
23INR0117 | Cantaloupe Storage | SS Completed, FIS Started, No IA | Saragosa Del Sol Energy LLC | 60716 Saragosa 138kV | Reeves | WEST | 2023-12-01 | OTH | BA | 251.05 |  | 2020-10-28 | 2020-12-22 | 2021-03-09 | 2020-12-01 |  |  |  | No |  |  | Not Required
23INR0118 | Blevins Solar | SS Completed, FIS Started, No IA | Blevins Solar, LLC | tap 345kV 3414 Temple Switch - 3409 Lake Creek | Falls | NORTH | 2023-06-01 | SOL | PV | 304.5 |  | 2021-02-18 | 2021-02-04 | 2021-04-19 | 2021-02-12 |  |  |  | No |  |  | Not Required
23INR0119 | Blevins Storage | SS Completed, FIS Started, No IA | Blevins Solar, LLC | tap 345kV 3414 Temple Switch - 3409 Lake Creek | Falls | NORTH | 2023-06-01 | OTH | BA | 182.4 |  | 2021-02-19 | 2021-02-04 | 2021-04-19 | 2021-02-12 |  |  |  | No |  |  | Not Required
23INR0124 | Coral Storage | SS Completed, FIS Started, No IA | Copperhead Solar, LLC | tap 138kV 3410 Lake Creek Switch - 3582 Falls County | Falls | NORTH | 2023-06-01 | OTH | BA | 101 |  | 2021-02-26 | 2021-03-01 | 2021-05-13 | 2021-02-01 |  |  |  | No |  |  | Not Required
23INR0130 | Ocee Creek Solar | SS Completed, FIS Started, No IA | OCI LoneSun LLC | 173 Crawford 138kV | McLennan | NORTH | 2023-07-15 | SOL | PV | 101.52 | MW Size | 2021-01-25 | 2021-02-09 | 2021-05-06 | 2020-12-22 |  |  |  | No |  |  | Not Required
23INR0131 | BRP Batura BESS | SS Completed, FIS Started, No IA | BRP Batura BESS LLC | 5260 Leon Creek 138kV | Bexar | SOUTH | 2023-06-01 | OTH | BA | 251.65 |  | 2020-11-12 | 2020-12-03 | 2021-02-16 | 2020-11-12 |  |  |  | No |  |  | Not Required
23INR0132 | BRP Bonete BESS | SS Completed, FIS Started, No IA | BRP Bonete BESS LLC | 8951 Stewart Road 138kV | Hidalgo | SOUTH | 2023-05-01 | OTH | BA | 201.13 |  | 2020-11-17 | 2020-12-03 | 2021-02-16 | 2020-11-18 |  |  |  | No |  |  | Not Required
23INR0134 | BRP Kailas BESS | SS Completed, FIS Started, No IA | BRP Kailas BESS LLC | 6216 Bluff Creek 138kV | Taylor | WEST | 2023-05-01 | OTH | BA | 201.29 |  | 2020-11-20 | 2020-12-03 | 2021-02-16 | 2020-11-20 |  |  |  | No |  |  | Not Required
23INR0135 | BRP Elbus BESS | SS Completed, FIS Started, No IA | BRP Elbus BESS LLC | 9075 Lytton 138kV | Caldwell | SOUTH | 2023-05-01 | OTH | BA | 201.11 |  | 2020-11-30 | 2020-12-03 | 2021-02-18 | 2020-11-25 |  |  |  | No |  |  | Not Required
23INR0137 | BRP Diran BESS | SS Completed, FIS Started, No IA | BRP Diran BESS LLC | 43190 South Lane City 138kV | Wharton | SOUTH | 2023-05-01 | OTH | BA | 100.63 |  | 2020-11-30 | 2020-12-03 | 2021-02-18 | 2020-11-25 |  |  |  | No |  |  | Not Required
23INR0139 | BRP Passu BESS | SS Completed, FIS Started, No IA | BRP Passu BESS LLC | 6111 Riley 345kV | Wilbarger | WEST | 2023-10-01 | OTH | BA | 301.82 |  | 2020-11-30 | 2020-12-03 | 2021-02-19 | 2020-11-27 |  |  |  | No |  |  | Not Required
23INR0140 | BRP Seine BESS | SS Completed, FIS Started, No IA | BRP Seine BESS LLC | 60500 Edith Clarke 345kV | Foard | WEST | 2023-10-01 | OTH | BA | 301.69 |  | 2020-11-30 | 2020-12-03 | 2021-02-19 | 2020-11-27 |  |  |  | No |  |  | Not Required
23INR0143 | BRP Sepik BESS | SS Completed, FIS Started, No IA | BRP Sepik BESS LLC | tap 138kV 11342 Loraine South – 1032 Morgan Creek | Mitchell | WEST | 2023-09-01 | OTH | BA | 201.87 |  | 2020-12-08 | 2020-12-22 | 2021-03-15 | 2020-12-01 |  |  |  | No |  |  | Not Required
23INR0144 | Galactic Solar | SS Completed, FIS Started, No IA | UKA North America, LLC | tap 138kV 1744 Gordonville - 11704 Sherman West | Grayson | NORTH | 2024-03-01 | SOL | PV | 205.2 |  | 2020-12-08 | 2020-12-22 | 2021-03-10 | 2020-12-01 |  |  |  | No |  |  | Not Required
23INR0148 | Thunderbird Solar SLF | SS Completed, FIS Started, No IA | Thunderbird Solar, LLC | tap 138kV 32 Robertson - 64 Milano | Milam | SOUTH | 2024-04-25 | SOL | PV | 204.08 |  | 2021-03-16 | 2020-12-23 | 2021-03-09 | 2021-03-05 |  |  |  | No |  |  | Not Required
23INR0149 | Pequin BESS Alt#1 | SS Completed, FIS Started, No IA | Pequin Energy Storage, LLC | 43380 West Columbia 138kV | Brazoria | COASTAL | 2023-02-28 | OTH | BA | 111.09 |  | 2021-06-29 | 2021-01-25 | 2021-04-12 | 2021-06-14 |  |  |  | No |  |  | Not Required
23INR0150 | New Found Solar | SS Completed, FIS Started, No IA | NFP Brazoria Solar, LP | tap 345kV 42500 Dow - 43035 Oasis ckt 27 | Brazoria | COASTAL | 2023-08-31 | SOL | PV | 225 |  | 2021-03-26 | 2021-02-04 | 2021-04-21 | 2021-03-15 |  |  |  | No |  |  | Not Required
23INR0152 | Madrone Energy Storage | SS Completed, FIS Started, No IA | Madrone Energy Storage, LLC | 5051 Bulverde 138kV | Comal | SOUTH | 2023-05-01 | OTH | BA | 102.49 |  | 2021-02-03 | 2021-01-26 | 2021-04-12 | 2021-01-20 |  |  |  | No |  |  | Not Required
23INR0153 | Mercury II Solar | SS Completed, FIS Started, No IA | Mercury II Solar, LLC | 68090 Sam Sw 345kV | Hill | NORTH | 2022-10-31 | SOL | PV | 206.11 |  | 2020-12-22 | 2021-01-26 | 2021-04-12 | 2020-12-11 |  |  |  | No |  |  | Not Required
23INR0154 | Ebony Energy Storage | SS Completed, FIS Started, No IA | Ebony Energy Storage, LLC | 5180 Green Mountain 138kV | Comal | SOUTH | 2023-05-01 | OTH | BA | 204.97 |  | 2021-02-03 | 2021-02-04 | 2021-04-21 | 2021-01-20 |  |  |  | No |  |  | Not Required
23INR0155 | Umbra (Stockyard) Solar | SS Completed, FIS Started, No IA | Stockyard Solar Project, LLC | tap 345kV 1695 Monticello - 11699 Woodard | Franklin | NORTH | 2023-12-29 | SOL | PV | 210 |  | 2021-05-20 | 2021-01-25 | 2021-04-12 | 2020-12-31 |  |  |  | No |  |  | Not Required
23INR0156 | Umbra (Stockyard) BESS | SS Completed, FIS Started, No IA | Stockyard Solar Project, LLC | tap 345kV 1695 Monticello - 11699 Woodard | Franklin | NORTH | 2023-12-29 | OTH | BA | 73 |  | 2021-05-20 | 2021-01-25 | 2021-04-12 | 2020-12-31 |  |  |  | No |  |  | Not Required
23INR0157 | High Chaparral Solar | SS Completed, FIS Started, No IA | High Chaparral Solar Project, LLC | tap 138kV 42110 Angleton - 42870 Liverpool c04 | Brazoria | COASTAL | 2023-12-31 | SOL | PV | 147.63 |  | 2021-03-01 | 2021-01-26 | 2021-04-12 | 2020-12-31 |  |  |  | No |  |  | Not Required
23INR0158 | High Chaparral BESS | SS Completed, FIS Started, No IA | High Chaparral Solar Project, LLC | tap 138kV 42110 Angleton - 42870 Liverpool c04 | Brazoria | COASTAL | 2023-12-31 | OTH | BA | 51.74 |  | 2021-03-01 | 2021-01-26 | 2021-04-12 | 2020-12-31 |  |  |  | No |  |  | Not Required
23INR0159 | Five Wells Storage | SS Completed, FIS Started, No IA | Five Wells Solar Center LLC | 3687 Bell Country East 345kV | Bell | NORTH | 2023-12-29 | OTH | BA | 262.5 |  | 2021-03-01 | 2021-02-04 | 2021-04-21 | 2021-01-22 |  |  |  | No |  |  | Not Required
23INR0160 | Grimes County Solar | SS Completed, FIS Started, No IA | Grimes County Solar Project, LLC | 2 Keith Switch 138kV | Grimes | NORTH | 2023-09-30 | SOL | PV | 210 |  | 2020-12-16 | 2021-01-26 | 2021-04-12 | 2020-12-16 |  |  |  | No |  |  | Not Required
23INR0163 | Ringtail Ridge Storage | SS Completed, FIS Started, No IA | KCE TX 26, LLC | 7150 Kendall 138kV | Kendall | SOUTH | 2023-05-01 | OTH | BA | 103.8 |  | 2021-01-08 | 2021-01-25 | 2021-04-16 | 2020-12-29 |  |  |  | No |  |  | Not Required
23INR0164 | Steppe Reserve Storage | SS Completed, FIS Started, No IA | KCE TX 25, LLC | 8283 Asherton 138 kV | Dimmit | SOUTH | 2023-06-01 | OTH | BA | 51.8 | COD | 2021-01-08 | 2021-01-25 | 2021-04-16 | 2020-12-29 |  |  |  | No |  |  | Not Required
23INR0168 | Charolais Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 44000 W A Parish - 5915 STP | Matagorda | COASTAL | 2023-12-15 | OTH | BA | 150 |  | 2021-06-25 | 2021-02-09 | 2021-05-06 | 2021-06-11 18:21 |  |  |  | No |  |  | Not Required
23INR0171 | Goodalta Solar | SS Completed, FIS Started, No IA | GoodAlta Power Center LLC | tap 138kV 3483 Goodloe - 3127 Trinidad SES | Navarro | NORTH | 2023-02-28 | SOL | PV | 185 |  |  | 2021-01-25 | 2021-04-12 | 2021-01-07 |  |  |  | No |  |  | Not Required
23INR0180 | Jackalope Solar | SS Completed, FIS Started, No IA | Peacock Energy Project, LLC | 8173 Gibbs 138kV | San Patricio | COASTAL | 2023-07-01 | SOL | PV | 156.4 |  | 2021-01-29 | 2021-02-09 | 2021-05-06 | 2021-02-02 |  |  |  | No |  |  | Not Required
23INR0187 | Leitrim 1 Solar | SS Completed, FIS Started, No IA | Leitsol LLC | tap 138kV 3522 Hillsboro - 3546 Whitney | Hill | NORTH | 2023-06-01 | SOL | PV | 91.2 |  | 2021-03-23 | 2021-01-26 | 2021-04-12 | 2021-03-18 |  |  |  | No |  |  | Not Required
23INR0189 | Bayside Solar | SS Completed, FIS Started, No IA | Bayside Solar, LLC | Tap 345kV 5915 STP - 5133 Elm Creek ckt #1 | Victoria | SOUTH | 2023-12-31 | SOL | PV | 509.4 |  | 2021-01-25 | 2021-02-09 | 2021-05-06 | 2021-01-25 |  |  |  | No |  |  | Not Required
23INR0190 | Cosmos Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 9073 Holman - 44200 Hillje | Wharton | SOUTH | 2024-12-01 | SOL | PV | 609.74 | COD | 2021-02-10 | 2021-03-01 | 2021-05-13 | 2021-03-01 |  |  |  | No |  |  | Not Required
23INR0192 | Utica Solar | SS Completed, FIS Started, No IA | Utica Solar, LLC | Tap 345kV 7050 Clear Springs - 7047 Hornsby Bend | Guadalupe | SOUTH | 2023-12-31 | SOL | PV | 204.5 |  |  | 2021-04-21 | 2021-07-14 | 2021-02-22 |  |  |  | No |  |  | Not Required
23INR0193 | Stockdale Solar | SS Completed, FIS Started, No IA | Stockdale Solar, LLC | tap 345kV 5133 Elm Creek - 5323 Old Hickory Ckt 2 | Wilson | SOUTH | 2023-12-31 | SOL | PV | 152.5 |  | 2021-01-15 | 2021-04-01 | 2021-07-02 | 2021-02-22 |  |  |  | No |  |  | Not Required
23INR0194 | Pequin BESS Alt#2 | SS Completed, FIS Started, No IA | Pequin Energy Storage, LLC | 39500 TN West Columbia 138kV | Brazoria | COASTAL | 2023-02-28 | OTH | BA | 111.09 |  | 2021-06-29 | 2021-01-25 | 2021-04-16 | 2021-06-14 |  |  |  | No |  |  | Not Required
23INR0195 | Desert Willow BESS | SS Completed, FIS Started, No IA | Desert Willow Energy Storage, LLC | tap 345kV 1907 Venus - 1921 Liggett | Ellis | NORTH | 2023-02-28 | OTH | BA | 151.92 | MW Size | 2021-06-29 | 2021-02-04 | 2021-04-22 | 2021-06-14 |  |  |  | No |  |  | Not Required
23INR0202 | Erath County Solar | SS Completed, FIS Started, No IA | Erath Solar, LLC | tap 345kV 68020 Romney1E - 68030 KopperlW | Erath | NORTH | 2023-11-30 | SOL | PV | 226.8 |  | 2021-01-20 | 2021-03-08 | 2021-05-28 | 2021-03-06 |  |  |  | No |  |  | Not Required
23INR0209 | Outpost Storage | SS Completed, FIS Started, No IA | Hecate Energy Outpost Storage LLC | Tap 345kV 80219 Lobo - 5709 Fowlerton | Webb | SOUTH | 2023-12-01 | OTH | BA | 508.1 |  | 2021-02-15 | 2021-03-01 | 2021-05-13 | 2021-02-15 |  |  |  | No |  |  | Not Required
23INR0210 | Cornwall Solar | SS Completed, FIS Started, No IA | Cornwall Solar, LLC | Tap 138kV 3659 Thorndale North - 3658 Taylor | Williamson | SOUTH | 2023-12-31 | SOL | PV | 204.5 |  |  | 2021-03-01 | 2021-05-13 | 2021-02-25 |  |  |  | No |  |  | Not Required
23INR0211 | Rosscommon Solar | SS Completed, FIS Started, No IA | Roscsol LLC | 1833 Brookstone 138kV | Lamar | NORTH | 2023-11-01 | SOL | PV | 91 |  | 2021-01-30 | 2021-03-01 | 2021-05-13 | 2021-02-01 |  |  |  | No |  |  | Not Required
23INR0215 | Big River Solar | SS Completed, FIS Started, No IA | Photosol US Renewable Energy, LLC | 8299 Zapata 138kV | Zapata | SOUTH | 2024-12-01 | SOL | PV | 104.35 |  | 2021-04-09 | 2021-05-04 | 2021-07-27 | 2021-04-15 |  |  |  | No |  |  | Not Required
23INR0217 | Snap Jaw BESS | SS Completed, FIS Started, No IA | Moccasin Pointe Grid, LLC | tap 138kV 40941 La Porte - 40200 Bimont (Air Liquide) | Harris | HOUSTON | 2023-06-01 | OTH | BA | 201.28 |  | 2021-04-02 | 2021-04-05 | 2021-07-02 | 2021-03-16 |  |  |  | No |  |  | Not Required
23INR0218 | Stump Tail BESS | SS Completed, FIS Started, No IA | Moccasin Pointe Grid, LLC | Tap 345kV 42000 PH Robinson – 40240 Center | Harris | HOUSTON | 2023-06-01 | OTH | BA | 301.69 |  | 2021-04-02 | 2021-04-05 | 2021-07-02 | 2021-03-17 |  |  |  | No |  |  | Not Required
23INR0227 | Maleza Solar II | SS Completed, FIS Started, No IA | Brush Solar, LLC | tap 345kV 44200 Hillje - 44040 Bailey | Wharton | SOUTH | 2023-06-01 | SOL | PV | 254.94 |  | 2021-05-24 | 2021-04-06 | 2021-06-24 | 2021-05-19 |  |  |  | No |  |  | Not Required
23INR0229 | Solterra Solar | SS Completed, FIS Started, No IA | Belltown Power Texas | 1796 Sulphur Bluff 138kV | Hopkins | NORTH | 2023-05-15 | SOL | PV | 143 |  | 2021-03-17 | 2021-03-19 | 2021-06-11 | 2021-03-18 |  |  |  | No |  |  | Not Required
23INR0231 | Rocinante Solar | SS Completed, FIS Started, No IA | Brush Country Solar Project, LLC | tap 138kV 7595 Deer Creek - 7621 Nixon | Gonzales | SOUTH | 2023-12-31 | SOL | PV | 95 |  | 2021-04-28 | 2021-04-22 | 2021-07-14 | 2021-04-22 |  |  |  | No |  |  | Not Required
23INR0232 | Rocinante BESS | SS Completed, FIS Started, No IA | Brush Country Solar Project, LLC | tap 138kV 7595 Deer Creek - 7621 Nixon | Gonzales | SOUTH | 2023-12-31 | OTH | BA | 33 |  | 2021-04-28 | 2021-04-22 | 2021-07-14 | 2021-04-22 |  |  |  | No |  |  | Not Required
23INR0235 | Hoyte Solar | SS Completed, FIS Started, No IA | Milano Solar, LLC | 64 Milano 138kV | Milam | SOUTH | 2023-12-31 | SOL | PV | 203.97 |  | 2021-04-02 | 2021-04-01 | 2021-07-02 | 2021-03-25 |  |  |  | No |  |  | Not Required
23INR0237 | Big River BESS | SS Completed, FIS Started, No IA | Photosol US Renewable Energy, LLC | 8299 Zapata 138KV | Zapata | SOUTH | 2024-12-01 | OTH | BA | 51.26 |  | 2021-04-09 | 2021-05-04 | 2021-07-27 | 2021-04-15 |  |  |  | No |  |  | Not Required
23INR0238 | Thunderbird Storage SLF | SS Completed, FIS Started, No IA | Thunderbird Solar, LLC | tap 138kV 32 Robertson - 64 Milano | Milam | SOUTH | 2024-04-25 | OTH | BA | 0 |  | 2021-04-07 | 2021-04-08 | 2021-06-30 | 2021-04-08 |  |  |  | No |  |  | Not Required
23INR0239 | Giga Texas Energy Storage | SS Completed, FIS Started, No IA | Giga Texas Energy, LLC. | 7047 Hornsby 345kV | Travis | SOUTH | 2023-05-26 | OTH | BA | 250 | FIS Request | 2021-07-22 | 2021-04-20 | 2021-07-02 | 2021-07-22 13:56 |  |  |  | No |  |  | Not Required
23INR0244 | Tiger Solar | SS Completed, FIS Started, No IA | Vaca Del Sol LLC | 68004 PHANTOM HILL 345KV | Jones | WEST | 2023-12-01 | SOL | PV | 306.24 |  | 2021-04-21 | 2021-04-29 | 2021-07-22 | 2021-04-29 |  |  |  | No |  |  | Not Required
23INR0245 | Tiger Storage | SS Completed, FIS Started, No IA | Vaca Del Sol LLC | 68004 PHANTOM HILL 345kV | Jones | WEST | 2023-12-01 | OTH | BA | 251.04 |  | 2021-04-21 | 2021-04-29 | 2021-07-22 | 2021-04-29 |  |  |  | No |  |  | Not Required
23INR0259 | Noria Storage DCC | SS Started, FIS Started, No IA | Noria Hondo Solar, LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2023-06-30 | OTH | BA | 0 |  | 2021-04-28 | 2021-04-22 |  | 2021-04-22 |  |  |  | No |  |  | Not Required
23INR0260 | Flatland Solar Project | SS Completed, FIS Started, No IA | Flatland Solar Project, LLC | 11319 Scurry County 138kV | Scurry | WEST | 2023-06-01 | SOL | PV | 182.5 |  | 2021-05-04 | 2021-05-10 | 2021-07-30 | 2021-04-28 |  |  |  | No |  |  | Not Required
23INR0272 | BRP Aras BESS | SS Started, FIS Started, No IA | BRP Aras BESS LLC | 76595 North McCamey 138kV | Upton | WEST | 2023-10-01 | OTH | BA | 303.59 |  | 2021-05-27 | 2021-05-31 |  | 2021-05-10 |  |  |  | No | Not Required | Not Required | Not Required
23INR0274 | BRP Parana BESS | SS Started, FIS Started, No IA | BRP Parana BESS | 7178 Marion 138kV | Guadalupe | SOUTH | 2023-10-01 | OTH | BA | 303.67 |  | 2021-06-01 | 2021-05-31 |  | 2021-05-10 |  |  |  | No | Not Required | Not Required | Not Required
23INR0275 | BRP Nile BESS | SS Started, FIS Started, No IA | BRP Nile BESS LLC | 80220 Cenizo 345kV | Webb | SOUTH | 2023-08-01 | OTH | BA | 202.34 |  | 2021-06-01 | 2021-05-31 |  | 2021-05-10 |  |  |  | No |  |  | Not Required
23INR0276 | BRP Tigris BESS | SS Started, FIS Started, No IA | BRP Tigris BESS LLC | 2374 Anna Switch 138kV | Collin | NORTH | 2023-08-01 | OTH | BA | 202.43 |  | 2021-06-01 | 2021-06-03 |  | 2021-05-10 |  |  |  | No |  |  | Not Required
23INR0278 | BRP Tucana BESS | SS Started, FIS Started, No IA | BRP Tucana BESS LLC | 23876 Clearfork 345kV | Andrews | WEST | 2023-08-01 | OTH | BA | 202.32 |  | 2021-06-01 | 2021-06-03 |  | 2021-05-10 |  |  |  | No |  |  | Not Required
23INR0279 | BRP Trivor BESS | SS Started, FIS Started, No IA | BRP Trivor BESS LLC | 1272 Fullerton 138kV | Andrews | WEST | 2023-08-01 | OTH | BA | 202.34 |  | 2021-06-01 | 2021-06-03 |  | 2021-05-10 |  |  |  | No |  |  | Not Required
23INR0282 | BAYSIDE II SOLAR | SS Started, FIS Started, No IA | Bayside II Solar, LLC | Tap 345kV 5323 Old Hickory - 5133 Elm Creek ckt #2 | DeWitt | SOUTH | 2023-12-31 | SOL | PV | 252.8 |  | 2021-06-02 |  |  | 2021-06-09 |  |  |  | No |  |  | Not Required
23INR0283 | Kota Battery | SS Started, FIS Started, No IA | National Grid Renewables LLC | 23900 Alibates 345kV | Carson | PANHANDLE | 2023-06-01 | OTH | BA | 202 |  | 2021-06-02 | 2021-06-07 |  | 2021-06-02 |  |  |  | No |  |  | Not Required
23INR0284 | Las Moras Battery | SS Started, FIS Started, No IA | National Grid Renewables, LLC | 8252 Brackett 138kV | Kinney | SOUTH | 2023-06-01 | OTH | BA | 101 |  | 2021-06-01 | 2021-06-07 |  | 2021-06-02 |  |  |  | No |  |  | Not Required
23INR0287 | BRP Avila BESS | SS Started, FIS Started, No IA | BRP Avila BESS LLC | 38340 TN Airport 138kV | Pecos | WEST | 2023-06-15 | OTH | BA | 101.24 |  | 2021-06-02 | 2021-05-31 |  | 2021-05-20 |  |  |  | No |  |  | Not Required
23INR0290 | BRP Zeya BESS | SS Started, FIS Started, No IA | BRP Zeya BESS LLC | 38740 Heights 138kV | Galveston | HOUSTON | 2023-06-15 | OTH | BA | 101.24 |  | 2021-06-02 | 2021-05-31 |  | 2021-05-20 |  |  |  | No |  |  | Not Required
23INR0292 | Howle Storage | SS Started, FIS Started, No IA | BT Howle Solar, LLC | tap 345kV 1906 Venus - 68090 Sam Sw Same location as 20INR0075 - Howle Solar | Ellis | NORTH | 2023-05-31 | OTH | BA | 30 |  | 2021-06-02 | 2021-06-07 |  | 2021-06-03 |  |  |  | No |  |  | Not Required
23INR0295 | Sultan Solar | SS Started, FIS Started, No IA | Lake Whitney Solar, LLC | tap 345kV 68080 Sam Switch – 68090 Kopperl | Bosque | NORTH | 2023-10-31 | SOL | PV | 206.11 |  | 2021-06-03 | 2021-07-01 |  | 2021-06-29 |  |  |  | No |  |  | Not Required
23INR0296 | Trojan Solar | SS Started, FIS Started, No IA | Compadre Cattle Solar, LLC | tap 345kV 1730 Krum West Switch – 2373 Anna Switch | Cooke | NORTH | 2023-10-31 | SOL | PV | 206.11 |  | 2021-06-03 | 2021-07-01 |  | 2021-06-30 |  |  |  | No |  |  | Not Required
23INR0299 | Anole BESS | SS Started, FIS Started, No IA | Anole Energy Storage, LLC | 2432 Tri-Corner 345kV | Dallas | NORTH | 2023-02-28 | OTH | BA | 227.84 |  | 2021-06-30 | 2021-07-01 |  | 2021-06-14 |  |  |  | No |  |  | Not Required
23INR0300 | Greater Bryant G Solar | SS Started, FIS Started, No IA | Chevron USA, Inc. | Oncor Trail Junction (TRLJNCTN_8) at existing Chevron Holzer substation, bus number 11138 | Midland | WEST | 2023-06-02 | SOL | PV | 41.6 |  | 2021-06-09 | 2021-06-17 |  | 2021-06-16 |  |  |  | No |  |  | Not Required
23INR0317 | Kingfisher Energy Storage | SS Started, FIS Started, No IA | Nopalosa Energy Storage, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2023-03-31 | OTH | BA | 204.97 | FIS Request | 2021-07-01 | 2021-07-08 |  | 2021-07-02 |  |  |  | No |  |  | Not Required
23INR0331 | Talitha BESS | SS Started, FIS Started, No IA | Talitha Energy Project, LLC | 5660 Orange Grove Switching Station 138 kV | Jim Wells | SOUTH | 2023-05-01 | OTH | BA | 61.39 | FIS Request | 2021-07-20 | 2021-07-15 |  | 2021-07-15 |  |  |  | No |  |  | Not Required
24INR0003 | Stem Solar | SS Completed, FIS Started, No IA | Innovative Solar 134, LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala | Swisher | PANHANDLE | 2024-04-24 | SOL | PV | 200 |  | 2020-12-03 | 2020-02-04 | 2020-04-27 | 2020-10-22 |  |  |  | No |  |  | Not Required
24INR0004 | Ponil Solar | SS Completed, FIS Started, No IA | Innovative Solar 377, LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2024-04-20 | SOL | PV | 145 |  | 2020-12-03 | 2020-02-04 | 2020-04-29 | 2020-10-22 |  |  |  | No |  |  | Not Required
24INR0007 | Nockenut Springs Solar 2 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Guadalupe | SOUTH | 2024-12-31 | SOL | PV | 203.26 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No |  |  | Not Required
24INR0010 | Pinnington Solar | SS Completed, FIS Started, No IA | Hecate Energy Pinnington Solar 1 LLC | tap both 345kV 1430 Graham - 1436 Parker 345kV lines | Jack | NORTH | 2024-06-01 | SOL | PV | 666.1 |  | 2020-11-03 | 2020-12-03 | 2021-02-17 | 2020-11-10 |  |  |  | No |  |  | Not Required
24INR0011 | Pinnington Storage | SS Completed, FIS Started, No IA | Hecate Energy Pinnington Solar & Storage 1 LLC | tap both 345kV 1430 Graham - 1436 Parker 345kV lines | Jack | NORTH | 2024-06-01 | OTH | BA | 508.7 |  | 2020-11-10 | 2020-12-03 | 2021-02-17 | 2020-11-10 |  |  |  | No |  |  | Not Required
24INR0015 | Five Wells Solar | SS Completed, FIS Started, No IA | Five Wells Solar Center LLC | 3687 Bell Country East 345kV | Bell | NORTH | 2023-12-29 | SOL | PV | 355.4 |  | 2021-02-18 | 2021-02-04 | 2021-04-21 | 2021-01-22 |  |  |  | No |  |  | Not Required
24INR0020 | Percy Farm Solar | SS Completed, FIS Started, No IA | AELIUS SOLAR CORP | Tap 345kV 8123 Blessing - 5915 STP | Matagorda | COASTAL | 2024-03-01 | SOL | PV | 102.06 | FIS Request |  | 2021-03-16 | 2021-06-11 | 2021-07-21 |  |  |  | No |  |  | Not Required
24INR0022 | Boxcar Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345kV 1907 Venus N - 68091 Navarro | Ellis | NORTH | 2024-05-15 | SOL | PV | 355.82 |  | 2021-03-25 | 2021-03-31 | 2021-06-17 | 2021-03-17 |  |  |  | No |  |  | Not Required
24INR0023 | Compadre Solar | SS Completed, FIS Started, No IA | Hill Solar I, LLC | tap 345kV 68090 Sam Switch - 1907 Venus | Hill | NORTH | 2024-10-01 | SOL | PV | 405.31 |  | 2021-03-29 | 2021-03-16 | 2021-05-28 | 2021-03-08 |  |  |  | No |  |  | Not Required
24INR0038 | SP Jaguar Solar | SS Completed, FIS Started, No IA | SP-Jaguar Solar LLC | 3405 Tradinghouse 345kV | McLennan | NORTH | 2024-04-30 | SOL | PV | 300 | FIS Request | 2021-07-23 | 2021-03-18 | 2021-06-11 | 2021-07-15 |  |  |  | No |  |  | Not Required
24INR0039 | SP Jaguar BESS | SS Completed, FIS Started, No IA | SP-Jaguar Solar LLC | 3405 Tradinghouse 345kV | McLennan | NORTH | 2024-04-30 | OTH | BA | 300 | FIS Request |  | 2021-03-18 | 2021-06-11 | 2021-07-15 |  |  |  | No |  |  | Not Required
24INR0056 | Pradera Solar | SS Started, FIS Started, No IA | Pradera Solar, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2024-10-31 | SOL | PV | 118 | FIS Request | 2021-06-02 | 2021-07-08 |  | 2021-06-23 |  |  |  | No |  |  | Not Required
24INR0065 | Clip Road Solar 1 | SS Started, FIS Started, No IA | Clip Road Solar, LLC | Tap 345kV 8624 Grissom - 8164 Coleto Creek | Grimes | NORTH | 2024-07-31 | SOL | PV | 200 | FIS Request |  | 2021-06-17 |  | 2021-07-29 15:47 |  |  |  | No |  |  | Not Required
24INR0081 | SANJAC BESS | SS Started, FIS Started, No IA | Castleman Power | 40270 Riverside 138kV | Harris | HOUSTON | 2023-01-01 | OTH | BA | 200 | FIS Request | 2021-07-08 | 2021-07-08 |  | 2021-07-08 |  |  |  | No |  |  | Not Required
24INR0099 | Two Rivers Solar | SS Started, FIS Started, No IA | Two Rivers Solar, LLC | Tap 138kV 64 Milano – 32 Robertson | Milam | SOUTH | 2024-09-30 | SOL | PV | 214 | FIS Request | 2021-07-27 |  |  | 2021-07-22 |  |  |  | No |  |  | Not Required
25INR0002 | Barcelona TxHSR TPSS HN-4 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 45885 HocklyC - 46220 Peters | Harris | HOUSTON | 2028-07-15 | OTH | OT | 50 |  | 2019-10-11 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  | No |  | No | Not Required | Not Required
25INR0005 | Tokyo TxHSR TPSS EW-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2241 Ennis W - 2321 Waxahachie | Ellis | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-09-13 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  |  |  | No | Not Required | Not Required
25INR0006 | Atlanta TxHSR TPSS DS-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2429 Watermill E - 3083 Wilmer | Dallas | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-10-11 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  |  |  | No | Not Required | Not Required
25INR0010 | Nockenut Springs Solar 3 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Gonzales | SOUTH | 2025-12-31 | SOL | PV | 203.39 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No |  |  | Not Required
26INR0001 | Turin TxHSR TPSS HN-6 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | 8 Crutchfield 138kV | Grimes | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-10-22 | 2019-09-27 | 2021-04-28 | 2019-09-27 |  |  |  | No

## GINR Trends
GINR Trends
Reflects all projects for which a Security Screening Study has been requested.
Excludes projects that have a status of Inactive (status = INA).
Nameplate capacity will change across time due to additional projects, cancelations, expirations, adjustments from study results, and projects being placed into service.
| Year | Month | Total Projects | Project Count | [5 empty] | Project Capacity (MW)
|  |  |  | GINR milestones | [5 empty] | Fuel Type
|  |  |  | Initial Screening Study | Screening Study Complete | In Full Study | Completed Full Study | Signed Interconnection Agreement | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Battery | Other
| 2018 | Jul | 404 | 34 | 60 | 197 | 25 | 88 | 6 | 37708 | 30518 | 11668 | 0 | 0 | 0 | 522 | 0
| 2018 | Aug | 417 | 26 | 57 | 220 | 26 | 88 | 11 | 40851 | 29649 | 10814 | 0 | 0 | 0 | 2177 | 0
| 2018 | Sep | 426 | 30 | 67 | 212 | 26 | 91 | 15 | 40327.45 | 31655.3 | 8589.6 | 0 | 0 | 0 | 1889 | 0
| 2018 | Oct | 429 | 26 | 60 | 221 | 24 | 98 | 4 | 40237.59 | 32248.91 | 9073.6 | 0 | 0 | 0 | 1889 | 0
| 2018 | Nov | 443 | 23 | 59 | 235 | 26 | 100 | 7 | 40283.09 | 36682.4 | 7503.4 | 0 | 0 | 0 | 2048.35 | 0
| 2018 | Dec | 465 | 31 | 67 | 237 | 27 | 103 | 9 | 39596.45 | 40732.49 | 9249.4 | 0 | 0 | 0 | 2342.82 | 0
| 2019 | Jan | 489 | 43 | 69 | 244 | 26 | 107 | 20 | 39222.25 | 43504.49 | 10824.6 | 0 | 45 | 0 | 3147.38 | 0
| 2019 | Feb | 493 | 38 | 70 | 246 | 24 | 115 | 12 | 37419.7 | 47140.55 | 10528.6 | 0 | 45 | 0 | 3011.92 | 300
| 2019 | Mar | 505 | 42 | 68 | 247 | 33 | 115 | 18 | 35555.28 | 50999.9 | 10536.6 | 0 | 45 | 0 | 3265.2 | 441.8
| 2019 | Apr | 527 | 38 | 79 | 260 | 30 | 120 | 9 | 35644.28 | 54655.45 | 10102.6 | 0 | 45 | 0 | 3501.24 | 300
| 2019 | May | 563 | 60 | 68 | 279 | 26 | 130 | 11 | 35689.38 | 58579.47 | 9736.6 | 0 | 45 | 0 | 4120.39 | 300
| 2019 | Jun | 568 | 53 | 68 | 285 | 27 | 135 | 19 | 35739.18 | 59160.69 | 9739.6 | 0 | 0 | 0 | 3956.79 | 300
| 2019 | Jul | 586 | 36 | 87 | 295 | 25 | 143 | 11 | 36048.46 | 62356.08 | 9282.6 | 13 | 0 | 0 | 3970.39 | 300
| 2019 | Aug | 583 | 30 | 91 | 303 | 27 | 132 | 12 | 35275.72 | 64579.48 | 8206.8 | 13 | 0 | 0 | 4199.79 | 340.6
| 2019 | Sep | 575 | 30 | 91 | 298 | 26 | 130 | 15 | 34553.51 | 64343.73 | 7405.2 | 13 | 0 | 0 | 4452.39 | 300
| 2019 | Oct | 582 | 36 | 88 | 294 | 29 | 135 | 16 | 31683.23 | 64789.75 | 7445.5 | 13 | 0 | 0 | 5627.39 | 350
| 2019 | Nov | 589 | 38 | 89 | 300 | 29 | 133 | 11 | 32252.73 | 64664.04 | 5898 | 13 | 0 | 0 | 7214.39 | 350
| 2019 | Dec | 584 | 31 | 78 | 325 | 21 | 129 | 19 | 30173.96 | 67807.94 | 5607 | 13 | 0 | 0 | 7790.29 | 350
| 2020 | Jan | 613 | 47 | 78 | 333 | 23 | 132 | 3 | 30573.34 | 73636.8 | 5607 | 13 | 0 | 0 | 8965.62 | 558.96
| 2020 | Feb | 633 | 48 | 87 | 334 | 27 | 137 | 1 | 30514.72 | 77699.12 | 5507 | 13 | 0 | 0 | 9978.58 | 350
| 2020 | Mar | 621 | 35 | 101 | 320 | 21 | 144 | 21 | 28888.4 | 76238.17 | 5749 | 13 | 493 | 0 | 10381.08 | 350
| 2020 | Apr | 619 | 15 | 117 | 304 | 26 | 157 | 6 | 27779.79 | 76252.21 | 5083.8 | 13 | 493 | 0 | 10899.04 | 350
| 2020 | May | 595 | 20 | 89 | 300 | 27 | 159 | 40 | 25958.39 | 72191.13 | 5083.8 | 13 | 420 | 0 | 12380.59 | 480.95
| 2020 | Jun | 602 | 30 | 84 | 295 | 38 | 155 | 20 | 26271.99 | 73655.09 | 5416.8 | 13 | 420 | 0 | 13041.64 | 410
| 2020 | Jul | 615 | 27 | 84 | 298 | 48 | 158 | 9 | 25477.63 | 75322.06 | 5373.88 | 13 | 420 | 0 | 14475.7 | 350
| 2020 | Aug | 644 | 25 | 83 | 316 | 54 | 166 | 5 | 25886.17 | 76960.74 | 7024.02 | 13 | 420 | 0 | 17436.1 | 350
| 2020 | Sep | 633 | 28 | 65 | 318 | 40 | 182 | 37 | 23678.97 | 77073.76 | 6818.72 | 13 | 420 | 0 | 18109.14 | 350
| 2020 | Oct | 666 | 39 | 69 | 331 | 29 | 198 | 3 | 23926.34 | 81301.63 | 7197.18 | 13 | 0 | 0 | 19459.46 | 350
| 2020 | Nov | 673 | 37 | 78 | 332 | 27 | 199 | 5 | 23897.86 | 81156.75 | 7197.18 | 13 | 0 | 0 | 21404.05 | 350
| 2020 | Dec | 708 | 40 | 86 | 352 | 28 | 202 | 10 | 23619.61 | 88031.55 | 7178.58 | 13 | 0 | 0 | 23550.04 | 350
| 2021 | Jan | 738 | 57 | 84 | 354 | 27 | 216 | 9 | 23334.25 | 89895.91 | 7224.34 | 13 | 0 | 0 | 26107.2 | 350
| 2021 | Feb | 769 | 54 | 95 | 374 | 20 | 226 | 4 | 24552.13 | 92012.3 | 7236.54 | 13 | 0 | 0 | 28352.55 | 400
| 2021 | Mar | 778 | 73 | 66 | 392 | 17 | 230 | 33 | 23859.29 | 88856.46 | 7897.04 | 13 | 0 | 0 | 30300.62 | 400
| 2021 | Apr | 804 | 63 | 92 | 399 | 19 | 231 | 12 | 23640.17 | 91546.69 | 7894.04 | 0 | 0 | 0 | 32002.39 | 500
| 2021 | May | 807 | 37 | 120 | 395 | 27 | 228 | 11 | 23764.26 | 91769.36 | 7606.04 | 0 | 0 | 0 | 33671.49 | 350
| 2021 | Jun | 818 | 43 | 114 | 409 | 26 | 226 | 16 | 22518.72 | 92814.52 | 8341.04 | 0 | 0 | 0 | 36206.58 | 350
| 2021 | Jul | 832 | 40 | 125 | 395 | 36 | 236 | 4 | 21933.87 | 94468.15 | 10399.04 | 0 | 0 | 0 | 36953.54 | 350
Note: Other contains all Fuel and Technology Types not in the Solar, Wind, Gas or Battery categories.

## data_GINR Trends_1 (hidden)
| # Signed Interconnect Agreement | # Completed Full Study | # in Full Study | # Screening Study Complete | # Initial Screening study | GW Capacity
Jul-20 | 158 | 48 | 298 | 84 | 27 | 121.4323
Aug-20 | 166 | 54 | 316 | 83 | 25 | 128.09
Sep-20 | 182 | 40 | 318 | 65 | 28 | 126.4636
Oct-20 | 198 | 29 | 331 | 69 | 39 | 132.2476
Nov-20 | 199 | 27 | 332 | 78 | 37 | 134.0188
Dec-20 | 202 | 28 | 352 | 86 | 40 | 142.7428
Jan-21 | 216 | 27 | 354 | 84 | 57 | 146.9247
Feb-21 | 226 | 20 | 374 | 95 | 54 | 152.5665
Mar-21 | 230 | 17 | 392 | 66 | 73 | 151.3264
Apr-21 | 231 | 19 | 399 | 92 | 63 | 155.5833
May-21 | 228 | 27 | 395 | 120 | 37 | 157.1611
Jun-21 | 226 | 26 | 409 | 114 | 43 | 160.2309
Jul-21 | 236 | 36 | 395 | 125 | 40 | 164.1046

## data_GINR Trends_2 (hidden)
| Natural Gas | Nuclear | Coal | Wind | Solar | Biomass | Battery | Other | Total Project Count | Cancelled Project Count
Jul-20 | 5.3739 | 0.013 | 0.42 | 25.4776 | 75.3221 | 0 | 14.4757 | 0.35 | 615 | 9
Aug-20 | 7.024 | 0.013 | 0.42 | 25.8862 | 76.9607 | 0 | 17.4361 | 0.35 | 644 | 5
Sep-20 | 6.8187 | 0.013 | 0.42 | 23.679 | 77.0738 | 0 | 18.1091 | 0.35 | 633 | 37
Oct-20 | 7.1972 | 0.013 | 0 | 23.9263 | 81.3016 | 0 | 19.4595 | 0.35 | 666 | 3
Nov-20 | 7.1972 | 0.013 | 0 | 23.8979 | 81.1568 | 0 | 21.4041 | 0.35 | 673 | 5
Dec-20 | 7.1786 | 0.013 | 0 | 23.6196 | 88.0315 | 0 | 23.55 | 0.35 | 708 | 10
Jan-21 | 7.2243 | 0.013 | 0 | 23.3343 | 89.8959 | 0 | 26.1072 | 0.35 | 738 | 9
Feb-21 | 7.2365 | 0.013 | 0 | 24.5521 | 92.0123 | 0 | 28.3526 | 0.4 | 769 | 4
Mar-21 | 7.897 | 0.013 | 0 | 23.8593 | 88.8565 | 0 | 30.3006 | 0.4 | 778 | 33
Apr-21 | 7.894 | 0 | 0 | 23.6402 | 91.5467 | 0 | 32.0024 | 0.5 | 804 | 12
May-21 | 7.606 | 0 | 0 | 23.7643 | 91.7694 | 0 | 33.6715 | 0.35 | 807 | 11
Jun-21 | 8.341 | 0 | 0 | 22.5187 | 92.8145 | 0 | 36.2066 | 0.35 | 818 | 16
Jul-21 | 10.399 | 0 | 0 | 21.9339 | 94.4681 | 0 | 36.9535 | 0.35 | 832 | 4

## data_GINR Trends_3 (hidden)
|  | Gas | Wind | Solar | Battery | Other
COASTAL | 2021 | 0.24 | 0.9334 | 0.50653 | 0.05
| 2022 | 0.312 | 1.0042 | 1.8794 | 1.7008
| 2023 | 0.34846 | 0.425 | 5.8573 | 1.6815
| 2024 |  |  | 0.91414
HOUSTON | 2021 | 0.724
| 2022 | 0.433 |  | 1.7411 | 0.50638
| 2023 | 0.99568 |  | 0.93206 | 2.2983
| 2025 |  |  |  |  | 0.05
| 2028 |  |  |  |  | 0.05
WEST | 2019 |  | 0.044
| 2020 | 0.083 | 0.7569
| 2021 |  | 3.9049 | 2.7664 | 0.62951
| 2022 | 0.68 | 4.0496 | 5.9814 | 3.5792
| 2023 | 0.0195 | 1.6107 | 11.5917 | 5.2946
| 2024 |  | 0.34725 | 0.9991 | 0.32
| 2025 | 1.35 |  | 0.77453
NORTH | 2020 | 0.021
| 2021 | 0.194 | 1.3402 | 0.82025 | 0.27664
| 2022 | 0.121 | 1.3178 | 10.053 | 2.4533
| 2023 | 2.756 | 2.2896 | 14.462 | 4.0666
| 2024 |  |  | 4.7445 | 1.5208
| 2025 | 0.3244 |  | 0.15 |  | 0.1
| 2028 |  |  |  |  | 0.15
PANHANDLE | 2021 | 0.112 |  | 0.2408
| 2022 |  | 0.8273 | 1.5287 | 0.70763
| 2023 |  |  | 2.6748 | 0.9133
| 2024 |  | 0.289 | 0.345 | 0.1
SOUTH | 2021 | 0.145 | 0.6126 | 0.52904 | 0.20098
| 2022 | 0.487 | 1.1982 | 5.927 | 3.8422
| 2023 | 1.053 | 0.37506 | 13.0772 | 6.6295
| 2024 |  | 0.6082 | 5.3687 | 0.08126
| 2025 |  |  | 0.60339 | 0.1012

## Commissioning Update
Commissioning Approvals during July 2021
Commissioning Category | INR | Project Name | Fuel | County | Approval Date * | MW **
Commercial Operation Approved by ERCOT* | 20INR0220 | Eunice Storage | Other | Andrews | 2021-07-14 | 40.26
Commercial Operation Approved by ERCOT* | 19INR0038 | High Lonesome Wind | Wind | Crockett | 2021-07-01 | 449.5
Commercial Operation Approved by ERCOT* | 20INR0262 | High Lonesome Wind Phase II | Wind | Crockett | 2021-07-01 | 50.6
Commercial Operation Approved by ERCOT* | 19INR0053 | Hidalgo II Wind | Wind | Hidalgo | 2021-07-30 | 51
Synchronization Approved by ERCOT | 21INR0202 | R Massengale | Gas | Lubbock | 2021-07-26 | 58
Synchronization Approved by ERCOT | 21INR0201 | Brandon | Gas | Lubbock | 2021-07-19 | 21
Synchronization Approved by ERCOT | 21INR0506 | Ty Cooke | Gas | Lubbock | 2021-07-14 | 33
Synchronization Approved by ERCOT | 20INR0130 | Plainview Solar | Solar | Wharton | 2021-07-26 | 514
Energization Approved by ERCOT | 21INR0510 | Crossett Power Batt | Other | Crane | 2021-07-20 | 203
Energization Approved by ERCOT | 21INR0506 | Ty Cooke | Gas | Lubbock | 2021-07-09 | 33
Energization Approved by ERCOT | 20INR0081 | Strategic Solar 1 | Solar | Ellis | 2021-07-20 | 136.85
Energization Approved by ERCOT | 21INR0201 | Brandon | Gas | Lubbock | 2021-07-02 | 21
Energization Approved by ERCOT | 20INR0082 | Vision Solar 1 | Solar | Navarro | 2021-07-21 | 129.24
Energization Approved by ERCOT | 21INR0202 | R Massengale | Gas | Lubbock | 2021-07-23 | 58
Energization Approved by ERCOT | 20INR0130 | Plainview Solar | Solar | Wharton | 2021-07-17 | 514
* For projects approved for commercial operations, the approval date is the Resource Commissioning Date defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a
Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative
values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.

## Inactive Projects
Inactive Projects as of end of July 2021*
INR | Project Name | Fuel | County | Inactive Date | MW **
16INR0044 | Halyard Wharton | Gas | Wharton | 2019-08-30 13:26 | 484
13INR0025 | Northdraw Wind | Wind | Randall | 2019-08-30 13:38 | 150
16INR0014b | Cattleman Wind B | Wind | Castro | 2019-08-30 13:40 | 201.6
17INR0010 | FGE Texas 2 Gas | Gas | Mitchell | 2019-08-30 13:41 | 742.9
16INR0014 | Cattleman Wind A | Wind | Castro | 2019-08-30 13:48 | 201.6
16INR0099 | Hecate Solar | Solar | Brewster | 2019-08-30 14:57 | 33
16INR0101 | Chatee Solar | Solar | Pecos | 2019-08-30 14:59 | 57
16INR0102 | Owego Solar | Solar | Pecos | 2019-08-30 15:01 | 74
13INR0010a | Mariah Del Este Wind | Wind | Parmer | 2019-09-09 10:19 | 152.5
20INR0025 | Spinel Solar | Solar | Medina | 2019-09-10 14:02 | 30
20INR0024 | Fluorite Solar | Solar | Uvalde | 2019-09-11 13:32 | 25
14INR0030c | Panhandle Wind 3 | Wind | Carson | 2019-09-24 09:41 | 248
19INR0055 | Monte Cristo 2 Wind | Wind | Hidalgo | 2019-10-24 18:00 | 236.9
17INR0036 | Grandview 4 Phase A Wind | Wind | Carson | 2019-10-31 10:59 | 200.5
20INR0096 | Desert Rose Solar | Solar | Andrews | 2019-11-12 13:44 | 200
15INR0051 | Tierra Blanca W | Wind | Randall | 2019-11-12 14:45 | 200
18INR0009 | Eagle Pines Gas | Gas | Cherokee | 2019-11-19 10:20 | 1173.5
21INR0363 | Carol Battery | Other | Potter | 2019-11-25 16:33 | 168
13INR0038 | Wildrose Wind | Wind | Swisher | 2019-12-20 13:53 | 302.5
19INR0031 | Bestla Solar | Solar | Winkler | 2020-03-04 16:50 | 180
08INR0019b | Grandview 5 W | Wind | Gray | 2020-03-09 16:21 | 249
16INR0012 | Stella 2 Wind | Wind | Kenedy | 2020-03-09 16:22 | 201
19INR0002 | Grandfalls Solar | Solar | Upton | 2020-04-01 11:39 | 350
19INR0054 | Monte Cristo 1 Wind | Wind | Hidalgo | 2020-04-28 17:01 | 236.9
20INR0146 | Angus Storage | Other | Bosque | 2020-05-04 11:36 | 63
19INR0150 | Millhouse Solar | Solar | Jim Wells | 2020-05-04 11:37 | 75
19INR0188 | Millhouse Storage | Other | Jim Wells | 2020-05-04 11:37 | 38
22INR0329 | Girasol | Solar | Zavala | 2020-05-22 08:29 | 200
20INR0023 | Agate Solar | Solar | Ellis | 2020-05-22 15:12 | 60
19INR0101 | Tehuacana Wind | Wind | Limestone | 2020-05-28 10:23 | 600
21INR0503 | Celeste Energy Storage | Other | Pecos | 2020-06-03 10:35 | 60.89
19INR0030 | San Bernard Solar | Solar | Wharton | 2020-06-18 11:51 | 100
16INR0074 | Chocolate Bayou Wind | Wind | Brazoria | 2020-06-19 09:49 | 149.5
17INR0043 | Vaquero 1 Wind | Wind | Zapata | 2020-07-01 18:45 | 400
21INR0015 | Arroyo Del Bisonte Solar | Solar | Wharton | 2020-07-06 16:03 | 300
20INR0299 | Sparkl BESS | Other | Guadalupe | 2020-09-16 12:30 | 20
21INR0305 | Frio Flat Wind | Wind | Deaf Smith | 2020-09-16 16:12 | 305
21INR0292 | Slama Solar | Solar | Wichita | 2020-10-15 14:32 | 251.65
20INR0021 | Garnet Solar | Solar | Williamson | 2020-11-03 09:18 | 20
19INR0142 | Bacon Switch Solar | Solar | Wichita | 2020-11-04 04:38 | 180
21INR0293 | Hat Creek Solar | Solar | Archer | 2020-11-04 09:04 | 251.67
22INR0433 | SBranch Expansion Solar | Solar | Wharton | 2021-01-11 08:16 | 76
20INR0257 | Snyder Wind Repower | Wind | Scurry | 2021-01-13 15:29 | -15
20INR0259 | San Bernard Solar II | Solar | Wharton | 2021-03-01 11:43 | 102
16INR0104 | Big Sampson Wind | Wind | Crockett | 2021-03-01 17:42 | 400
20INR0258 | Snyder BESS | Other | Scurry | 2021-03-12 12:30 | 17.58
19INR0161 | Pierce Wind | Wind | Wharton | 2021-03-16 10:13 | 300
20INR0029 | Lutum Wind | Wind | Clay | 2021-04-02 08:51 | 242
20INR0043 | Gulf Wind 2 | Wind | Kenedy | 2021-04-02 08:54 | 226.5
20INR0061 | Pflugerville 2 Solar | Solar | Travis | 2021-04-02 12:06 | 120
21INR0485 | Texana Storage | Other | Wharton | 2021-04-05 22:27 | 150.94
20INR0267 | Greens Bayou Expansion | Gas | Harris | 2021-04-17 01:08 | 140
18INR0072 | Blue Summit repower | Wind | Wilbarger | 2021-04-28 15:42 | 9.9
20INR0202 | Rueter Solar | Solar | Bosque | 2021-05-10 13:52 | 200
23INR0067 | Wekiva Grid | Other | Titus | 2021-05-10 15:55 | 202.61
21INR0465 | San Bernard Storage | Other | Wharton | 2021-06-14 17:46 | 100.62
19INR0103 | Rodeo Solar | Solar | Andrews | 2021-06-16 09:32 | 200
18INR0056 | Hallmark Solar | Solar | Hunt | 2021-06-21 09:12 | 43
20INR0026 | Longbow Solar | Solar | Brazoria | 2021-07-14 14:44 | 80
21INR0343 | Flag City Solar | Solar | Jackson | 2021-07-19 06:02 | 150
23INR0027 | Cachena Solar | Solar | Wilson | 2021-07-26 11:23 | 408.94
23INR0077 | Cachena Storage | Other | Wilson | 2021-07-26 11:23 | 102.5
* Includes only those projects designated as Inactive by ERCOT or the project developer after the developer makes a Full Interconnection Study (FIS) request.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.

## Cancellation Update
Projects Cancelled by the Developer during July 2021*
INR | Project Name | Fuel | County | Cancel Date | MW **
19INR0173 | Magnet Wind | Wind | Wharton | 2021-07-01 09:28 | 125
20INR0312 | Barney Davis IPAC #4 repower | Gas | Nueces | 2021-07-19 11:44 | 48
* Includes only those projects cancelled after the developer makes a Full Interconnection Study (FIS) request.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.