## Contents
GIM Activity: Jun 01, 2022 to Jun 30, 2022
Table of Contents
Disclaimer and References | Disclaimer on the use of this report, and references to associated ERCOT Binding Documents ***Please read***
Acronyms | A list of the various acronyms used throughout the report
Summary | Tables that provide project aggregate counts and megawatt capacities by GIM phase and fuel type
Project Details - Large Gen | A table that list project details for Large Generators as defined in ERCOT Planning Guide Section 5.2.1(3); only include projects for which a Full Interconnection Study has been requested
Project Details - Small Gen | A table that list project details for Small Generators as defined in ERCOT Planning Guide 5.2.1(3); only include projects for which the Resource Registration form has been approved by ERCOT
GIM Trends | Charts and tables that show historical and projected interconnection study trends
Commissioning Update | A table listing project commissioning approval milestones met for the month: energization, synchronization, and commercial operations approval
Inactive Projects | A table listing Inactive projects
Cancellation Update | A table listing the projects cancelled for the month
Time of Report Run: Jul 1, 2022 8:03:51 AM

## Disclaimer and References
Generator Interconnection Status Report - Disclaimer
FOR PLANNING PURPOSES ONLY
This ERCOT Working Paper has been prepared for specific ERCOT and Market Participant purposes, and has been
developed from data provided by Interconnecting Entities and Transmission Service Providers that has been entered into the online RIOO system.
The data may contain errors or be obsolete depending on when the data was entered. ERCOT MAKES NO WARRANTY, EXPRESS
OR IMPLIED,INCLUDING ANY WARRANTY OF MERCHANTABILITY OR FITNESS FOR ANY PARTICULAR PURPOSE,
AND DISCLAIMS ANY AND ALL LIABILITY WITH RESPECT TO THE ACCURACY OF SAME OR THE FITNESS OR
APPROPRIATENESS OF SAME FOR ANY PARTICULAR USE. THIS ERCOT WORKING PAPER IS SUPPLIED WITH ALL FAULTS.
References
The links below provide more information on the ERCOT interconnection process:
http://www.ercot.com/mktrules/guides/planning/current
See the Resource Interconnection Handbook, available on ERCOT’s Resource Integration webpage:
http://www.ercot.com/services/rq/integration

## Acronyms
Acronyms
GIM = Generator Interconnection or Modification request
GINR = Generation Interconnection or Change Request
COD = Commercial Operation Date
SS = Security Screening Study
FIS = Full Interconnection Study
IA = Interconnection Agreement; can be either of the following:
- Standard Generation Interconnection Agreement (SGIA)
- Public financially binding agreement
- An official letter from a Municipally Owned Utility or Electric Cooperative signifying developer intent to build and operate generation facilities and
interconnect with the MOU or EC
POI = Point of lnterconnection
INR = Interconnection Request Number
TSP = Transmission Service Provider
NtP = Notice-to-Proceed given to the TSP for interconnection construction
CDR = Capacity, Demand and Reserves Report
SFS = Sufficient Financial Security provided to the TSP for construction of the interconnection facilities
QSA = Quarterly Stability Assessment
INA = Inactive status
PLN = Planned status
Fuel Types | Technology Types
BIO = Biomass | BA = Battery Energy Storage
COA = Coal | CC = Combined-Cycle
GAS = Gas | CE = Compressed Air Energy Storage
GEO = Geothermal | CP = Concentrated Solar Power
HYD = Hydrogen | EN = Energy Storage
NUC = Nuclear | FC = Fuel Cell
OIL = Fuel Oil | GT = Combustion (gas) Turbine, but not part of a Combined-Cycle
OTH = Other | HY = Hydroelectric Turbine
PET = Petcoke | IC = Internal Combustion Engine, eg. Reciprocating
SOL = Solar | OT = Other
WAT = Water | PV = Photovoltaic Solar
WIN = Wind | ST = Steam Turbine other than Combined-Cycle
WT = Wind Turbine

## Summary
Summary |  |  | Major GIM Milestone Status by Fuel/Technology Type, MW
Currently tracking 1068 generation interconnection or change requests as of Jun 30, 2022 |  |  | Includes only those (1) Large Generator projects for which a Screening Study has been requested, (2) Small Generators for which an interconnection request has been made, and (3) projects that are not Inactive
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  |  | Fuel | Technology | SS Started | SS Started | SS Completed | SS Completed | SS Completed | SS Started | SS Started | SS Completed | SS Completed | SS Completed | Small Generator | Small Generator | TOTAL
Includes only those (1) Large Generator projects for which a Screening Study has been requested, |  |  | Type | Type | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | Not Model Ready | Model Ready
(2) Small Generators for which an interconnection request has been made and |  |  |  |  | No IA | No IA | No IA | No IA | No IA | IA | IA | IA | IA | IA
and (3) projects that are not Inactive
Status of SS, FIS and IA | Project Count | % of Total | Gas | Combined-Cycle | 51 |  | 258 | 1990 | 21 |  |  |  | 697 | 502 | 3.1 |  | 3522.1
LARGE GENERATORS |  |  | Gas | Combustion Turbine |  |  | 4512 | 1607.5 | 1104.92 |  |  |  |  | 500 |  |  | 7724.42
SS Started, FIS Not Started, No IA | 63 | 5.915% | Gas | Internal Combustion Engine |  |  | 330 | 149.4 | [8 empty] | 479.4
SS Started, FIS Started, No IA | 52 | 4.883% | Gas | Compressed Air Energy Storage |  |  | 324.4 | [9 empty] | 324.4
SS Completed, FIS Not Started, No IA | 87 | 8.169% | Gas | Steam Turbine |  |  |  |  | 680 |  |  |  |  | 14 |  |  | 694
SS Completed, FIS Started, No IA | 513 | 48.17% | Gas | Fuel Cell | [12 empty] | 0
SS Completed, FIS Completed, No IA | 64 | 6.009% | Gas | Total gas | 51 |  | 5424.4 | 3746.9 | 1805.92 |  |  |  | 697 | 1016 | 3.1 |  | 12744.32
SS Started, FIS Not Started, IA | 0 | 0% | Coal | [13 empty] | 0
SS Started, FIS Started, IA | 0 | 0% | Wind |  | 4155 | 456.8 | 576 | 5422.57 | 175.58 |  |  |  | 3126.46 | 8330.78 |  |  | 22243.19
SS Completed, FIS Not Started, IA | 3 | 0.2817% | Solar |  | 7724.16 | 2962.86 | 10275.85 | 51537.08 | 7767.06 |  |  | 591.19 | 10812.01 | 20052.89 |  | 7.4 | 111730.5
SS Completed, FIS Started, IA | 71 | 6.667% | Biomass |  |  |  |  | 53 | [8 empty] | 53
SS Completed, FIS Completed, IA | 201 | 18.87% | Other | Battery | 6211.77 | 5276.15 | 3109.28 | 39224.36 | 4547.98 |  |  |  | 2442.88 | 4463.62 | 29.93 | 59.7 | 65365.67
SMALL GENERATORS |  |  | Other* |  |  | 18.03 | 1248.8 | 200 | [8 empty] | 1466.83
Not Model Ready* | 4 | 0.3756% | TOTAL |  | 18141.93 | 8713.84 | 20634.33 | 100183.91 | 14296.54 | 0 | 0 | 591.19 | 17078.35 | 33863.29 | 33.03 | 67.1 | 213603.51
Model Ready* | 7 | 0.6573% | * Other includes petroleum coke (pet coke), hydroelectric, fuel oil, geothermal energy, other miscellaneous fuels reported by developers, and fuel cells that use fuels other than natural gas.
Total Interconnection Requests | 1065
Inactive (since last month) | 6
Cancelled (since last month) | 3
Capacity, MW
Total Capacity Under Study | 213603.51
Interconnection Agreements Executed | 51834.48
Inactive (since last month) | 1026.57
Inactive changed to Planned (since last month) | 2150.81
Inactive changed to Cancelled (since last month) | 0
Cancelled (since last month) | 437
* "Not Model Ready" means that a Small Generator's data has not yet been loaded into the Network
Operations Model. "Model Ready" means that the data has been loaded into the NOM, and the Resource is
ready to begin the commissioning process.

## Project Details - Large Gen
GIM Project Details - Large Generators
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study has been requested are included.
Excludes projects that have a status of Inactive (status = INA).
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GIM system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not been obtained or reported to ERCOT yet.
A developer may split a project into two or more additional projects with different INR numbers during the interconnection request process. Due to current RIOO interface limitations,
the new projects do not inherit certain milestone dates entered for the original project. As a result, dates may be blank even though the milestones have been met.
A “1-1-1900” date is used to signify that an actual date for a project milestone is not available. This typically occurs for project data migrated from the legacy GINR database to the RIOO system.
Project Attributes | [10 empty] | Changes from Last Report | GIM Project Milestone Dates
INR | Project Name | GIM Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | Economic Study Required | IA Signed |  | Air Permit | GHG Permit | Water Availability | Meets Planning | Meets All Planning |  | Construction Start | Construction End | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Change indicators: Proj Name, MW | Approval Date for | [6 empty] | Financial Security |  |  |  | Guide Section 6.9(1) | Guide Section 6.9 | Meets Planning Guide
[11 empty] | Size, COD, SFS/NtP, FIS Request, | Submission of Proof of | [6 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[11 empty] | Status Change INA-to-PLN | Site Control | [6 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[23 empty] | Models | Models
14INR0033 | Goodnight Wind | SS Completed, FIS Started, IA | FGE Power | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | PANHANDLE | 2023-12-30 | WIN | WT | 531 | MW Size COD | 1899-12-31 | 2012-07-24 | 2012-09-19 | 2013-03-04 |  | No | 2018-03-07 | No | Not Required | Not Required | Not Required
15INR0059 | Emerald Grove Solar | SS Completed, FIS Completed, IA | Emerald Grove Solar, LLC | 76602 Horse Crossing 138kV | Pecos | WEST | 2022-08-06 | SOL | PV | 108 | COD | 2013-11-12 | 2013-11-13 | 2013-12-23 | 2013-11-12 | 2021-04-29 | No | 2017-12-04 | Yes | Not Required | Not Required | Not Required | 1899-12-31 | 2019-04-17 | 2021-04-29 |  |  | 2021-12-10 | 2022-01-04
15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2022-06-30 | WIN | WT | 162.1 |  |  | 2013-11-27 | 2014-01-27 | 2014-04-15 | 2017-09-27 | No | 2018-05-30 | Yes | Not Required | Not Required | Not Required | 2018-05-30 | 2018-09-19 | 2019-01-22 |  |  | 2020-02-10 | 2020-05-12
16INR0033 | Hart Wind | SS Completed, FIS Started, IA | Orion | 23912 Ogallala 345kV | Castro | PANHANDLE | 2023-12-31 | WIN | WT | 151.5 |  | 2014-10-27 | 2014-02-10 | 2014-03-20 | 2014-10-27 |  | No | 2018-08-06 | No | Not Required | Not Required | Not Required
16INR0049 | Nazareth Solar | SS Completed, FIS Started, IA | Lendlease Energy | tap 345kV 23914 Tule Canyon - 23912 Ogallala' | Castro | PANHANDLE | 2025-03-24 | SOL | PV | 204 | MW Size COD | 2014-07-07 | 2014-06-19 | 2014-07-25 | 2014-07-01 |  | No | 2018-05-10 | No | Not Required | Not Required | Not Required
16INR0054 | NASA | SS Completed, FIS Completed, IA | NASA | 42970 Nasa 138kV | Harris | HOUSTON | 2022-12-01 | GAS | CC | 12 |  |  | 2015-03-10 | 2015-04-01 | 2015-03-10 | 2016-01-26 | No | 2016-10-27 | Yes | Not Required | Not Required |  | 2016-11-10 | 2018-09-28 | 2018-09-28 |  |  | 2017-10-15 | 2017-11-27
16INR0081 | Mesteno Wind | SS Completed, FIS Completed, IA | Mesteno Windpower, LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2022-09-01 | WIN | WT | 201.6 |  | 1899-12-31 | 2014-12-30 | 2015-03-09 | 2014-12-30 | 2018-01-29 | No | 2018-04-25 | Yes | Not Required | Not Required | Not Required | 2018-04-25 | 2019-03-28 | 2019-04-01 |  |  | 2019-11-26 | 2019-12-12
16INR0085 | Priddy Wind | SS Completed, FIS Completed, IA | ENGIE North America | tap 345kV 1444 Brown – 3422 Killeen | Mills | NORTH | 2022-07-29 | WIN | WT | 302.4 | COD | 2015-03-06 | 2015-01-14 | 2015-02-10 | 2015-03-06 | 2021-04-30 | No | 2020-08-13 | Yes | Not Required | Not Required | Not Required | 2021-03-29 | 2021-04-30 | 2021-04-30 |  |  | 2021-10-13 | 2021-11-19
16INR0104 | Big Sampson Wind | SS Completed, FIS Started, IA | Infinity Renewables | tap 345kV 76015 Cedar Canyon - 7053 Noelke | Crockett | WEST | 2024-10-01 | WIN | WT | 400 |  |  | 2015-05-11 | 2015-06-17 | 2015-05-11 |  | No | 2019-11-08 | No | Not Required | Not Required | Not Required
16INR0112 | Loma Pinta Wind | SS Completed, FIS Started, IA | Enerverse | 5705 Fowlerton 138kV | La Salle | SOUTH | 2023-09-01 | WIN | WT | 200 |  |  | 2015-05-18 | 2015-07-02 | 2015-05-18 |  | No | 2017-12-13 | No | Not Required | Not Required | Not Required
17INR0022 | MIRAGE | SS Completed, FIS Completed, IA | Net Power | 111161 Mirage 13.8kV | Harris | HOUSTON | 2023-12-01 | GAS | GT | 11 |  |  | 2015-02-17 | 2015-05-01 | 2015-05-20 | 2016-09-13 | No | 2016-08-31 | Yes | 2015-05-08 | Not Required | 2017-10-12 | 2016-10-11 | 2018-09-28 | 2018-09-28 |  |  | 2017-02-06
17INR0025 | Reloj Del Sol Wind | SS Completed, FIS Completed, IA | EDP Renewables | 80220 Cenizo 345kV | Zapata | SOUTH | 2022-06-16 | WIN | WT | 209.4 |  | 2015-09-14 | 2015-03-24 | 2015-05-05 | 2015-09-14 | 2020-04-26 | Yes | 2018-12-21 | Yes | Not Required | Not Required | Not Required | 2019-03-04 | 2020-05-01 | 2020-05-01 |  |  | 2020-12-21 | 2020-12-29
17INR0027b | Coyote Wind | SS Completed, FIS Completed, IA | Coyote Wind | 11305 Dermott 345kV | Scurry | WEST | 2022-06-30 | WIN | WT | 242.6 |  |  | 2015-04-22 | 2015-05-22 | 2015-06-11 | 2020-01-31 | No | 2016-08-09 | Yes | Not Required | Not Required | Not Required | 2016-08-09 | 2020-01-28 | 2020-01-31 |  |  | 2020-08-24 | 2020-11-25
17INR0035 | Las Majadas Wind | SS Completed, FIS Completed, IA | EDF Renewable Energy | 8318 Rio Hondo 345kV plus 12.5mi gentie | Willacy | COASTAL | 2022-06-01 | WIN | WT | 272.6 |  | 2015-12-09 | 2015-10-30 | 2015-12-14 | 2015-12-09 | 2020-01-30 | Yes | 2018-04-13 | Yes | Not Required | Not Required | Not Required | 2019-07-22 | 2020-01-30 | 2020-01-30 |  |  | 2020-09-02 | 2020-10-21
17INR0052 | Horse13 CallD repower | SS Completed, FIS Completed, IA | Nextera | 6216 Bluff Creek 138kV | Taylor | WEST | 2022-06-30 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2018-04-10 | No | 2019-05-22 | Yes | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13 |  |  |  | 2021-03-16
17INR0053 | HHGT repower Horse13+CallD | SS Completed, FIS Completed, IA | Nextera | 7046 Kendal 345kV | Taylor | WEST | 2022-06-30 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2017-07-06 | No | 2009-06-26 | No | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13 |  |  |  | 2021-09-10
17INR0054 | Capricorn I & III repower | SS Completed, FIS Completed, IA | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WEST | 2022-07-30 | WIN | WT | 32 |  | 2017-03-09 | 2017-03-09 | 2017-04-24 | 2017-03-09 | 2018-02-26 | No | 2006-11-14 | No | Not Required | Not Required | Not Required | 2021-02-28 | 2021-02-28 | 2021-02-28 |  |  |  | 2021-03-04
17INR0061 | Capricorn IV repower | SS Completed, FIS Completed, IA | Nextera | 76090 Divide 345kV | Sterling | WEST | 2022-05-31 | WIN | WT | 9 |  | 2017-08-23 | 2017-08-23 | 2017-09-15 | 2017-08-23 | 2018-02-06 | No | 2008-01-15 | No | Not Required | Not Required | Not Required | 2020-08-28 | 2020-08-28 | 2018-03-30 |  |  |  | 2020-08-19
17INR0068 | Sweetwater 2 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2022-05-31 | WIN | WT | 7.3 |  | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-11-10 | No | 2003-06-27 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2017-12-20
17INR0069 | Trent repower | SS Completed, FIS Completed, IA | TRENT WIND FARM LLC | 1338 Eskota 138kV | Nolan | WEST | 2022-07-01 | WIN | WT | 6.4 |  | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-03-01 | No | 2018-10-19 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-05-09
17INR0070 | Desert Sky repower | SS Completed, FIS Completed, IA | DESERT SKY WIND FARM LLC | two LCRA 138kV | Pecos | WEST | 2022-07-01 | WIN | WT | 7.2 |  | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-02-06 | No | 2018-10-18 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-09-06
18INR0031 | Maryneal Wind | SS Completed, FIS Completed, IA | Maryneal Windpower, LLC | 71050 Bitter Creek 345kV | Nolan | WEST | 2022-06-30 | WIN | WT | 182.4 |  | 2016-07-22 | 2016-05-26 | 2016-07-21 | 2016-07-22 | 2020-01-31 | No | 2020-01-31 | Yes | Not Required | Not Required | Not Required | 2020-01-31 | 2020-01-31 | 2020-01-31 |  |  | 2021-01-08 | 2021-04-23
18INR0043 | Lacy Creek wind | SS Completed, FIS Completed, IA | Lacy Creek Wind, LLC | 59907 Bernoulli 345kV | Glasscock | WEST | 2022-12-31 | WIN | WT | 301.3 |  | 2017-02-01 | 2016-10-26 | 2016-12-22 | 2017-02-01 | 2021-11-04 | Yes | 2017-09-28 | Yes | Not Required | Not Required | Not Required | 2022-04-21 | 2022-04-21 | 2022-04-21
18INR0050 | Mustang Creek Solar | SS Completed, FIS Completed, IA | Ganado Solar, LLC | tap 138kV 5523 ETP - 78104 Ricebird new sub Galow | Jackson | SOUTH | 2023-01-24 | SOL | PV | 150.5 |  | 2017-03-22 | 2016-11-16 | 2016-12-20 | 2017-03-22 | 2022-01-19 | No | 2019-01-04 | Yes | Not Required | Not Required | Not Required | 2019-10-04 | 2020-03-11 | 2022-01-26
18INR0053 | TAVNER | SS Completed, FIS Completed, IA | Fort Bend Solar LLC | tap 138kV 44541 Orchard - 44190 E Bernard | Fort Bend | HOUSTON | 2023-07-30 | SOL | PV | 240 |  |  | 2016-12-19 | 2017-02-15 | 2017-09-08 | 2021-04-21 | No | 2019-06-30 | Yes | Not Required | Not Required | Not Required | 2021-04-29 | 2021-04-30 | 2021-04-29 |  |  | 2022-06-07
18INR0058 | Texana Solar | SS Completed, FIS Completed, IA | Sunchase Power | tap 138kV 8102 El Campo - 8117 Ganado | Wharton | SOUTH | 2024-09-27 | SOL | PV | 152.34 |  | 2017-03-22 | 2016-12-23 | 2017-02-14 | 2017-03-22 | 2020-12-01 | No | 2021-06-30 | No | Not Required | Not Required | Not Required
18INR0064 | Silver Star repower | SS Completed, FIS Completed, IA | Silver Star I Power Partners, LLC | 1642 Flat Creek 138kV | Eastland | NORTH | 2022-06-18 | WIN | WT | -7.2 | COD | 2017-07-06 | 2017-04-05 | 2017-05-08 | 2017-07-06 | 2018-04-26 | No | 2018-10-16 | Yes | Not Required | Not Required | Not Required | 2019-10-23 | 2019-10-23 | 2019-10-28 |  |  |  | 2020-07-28
18INR0068 | Loraine Windpark Phase III | SS Completed, FIS Started, IA | Third Planet Wind Power | 181153 Lonewolf 345kV | Mitchell | WEST | 2024-05-10 | WIN | WT | 100 |  | 2017-10-20 | 2017-08-14 | 2017-10-05 | 2017-10-20 |  | No | 2018-04-10 | Yes | Not Required | Not Required | Not Required | 2018-04-12 | 2018-09-12 | 2018-05-01
18INR0069 | Indian Mesa repower | SS Completed, FIS Completed, IA | Nextera | 76019 Indian NWP 138kV | Pecos | WEST | 2022-04-30 | WIN | WT | 82.5 | MW Size COD | 2018-05-22 | 2018-05-22 | 1899-12-31 | 2018-05-22 | 2018-10-03 | No | 2018-12-04 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2018-11-02
18INR0073 | Sweetwater 1 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2022-05-31 | WIN | WT | 3 |  | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-12-27 | No | 2002-10-23 | No | Not Required | Not Required | Not Required
18INR0076 | Wolf Hollow 2 repower | SS Completed, FIS Started, No IA | Exelon | 1877 Mitchell Bend 345kV | Hood | NORTH | 2022-03-01 | GAS | CC | 44 |  | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 |  | No |  | No | Not Required | Not Required |  | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-19
18INR0079 | Woodward I repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2022-07-30 | WIN | WT | 0 |  | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2019-01-09 | No | 2018-12-12 | Yes | Not Required | Not Required | Not Required | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2019-11-07 | 2019-11-13
18INR0080 | Woodward 2 repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2022-07-30 | WIN | WT | 0 |  | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-11-27 | No | 2018-12-18 | Yes | Not Required | Not Required | Not Required | 2018-11-29 | 2018-11-29 | 2020-10-30 |  |  |  | 2018-12-19
19INR0001 | Texas Solar Nova | SS Completed, FIS Completed, IA | Clearway Energy | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2023-03-15 | SOL | PV | 256.11 |  | 2016-07-06 | 2015-11-17 | 2015-12-30 | 2016-07-06 | 2022-06-03 | No | 2019-07-01 | Yes | Not Required | Not Required | Not Required | 2019-11-08 | 2022-06-28
19INR0002 | Grandfalls Solar | SS Completed, FIS Started, No IA | Nextera | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | WEST | 2023-12-31 | SOL | PV | 350 |  | 2016-05-24 | 2016-05-24 | 2016-06-06 | 2016-05-24 |  |  |  | No | Not Required | Not Required | Not Required
19INR0014 | Formosa Increase | SS Completed, FIS Completed, IA | Formosa Plastics | 8126 Formosa 138kV | Calhoun | COASTAL | 2022-08-15 | GAS | CC | 240 |  |  | 2016-09-12 | 2016-11-14 | 2017-06-08 | 2019-02-20 | No | 2019-04-30 | Yes | 2017-04-17 | 2017-07-12 | 2019-02-22 | 2019-04-30 | 2019-04-30 | 2019-04-30 |  |  | 2020-02-10 | 2020-03-04
19INR0017 | Tri-County Solar | SS Completed, FIS Started, No IA | Crane Solar, LLC | tap 138kV 1027 Odessa - 1107 Monahans2T | Crane | WEST | 2025-01-15 | SOL | PV | 177.75 |  |  | 2016-10-10 | 2016-11-29 | 2017-02-22 |  | No |  | No | Not Required | Not Required | Not Required
19INR0022 | Monte Alto I | SS Completed, FIS Completed, IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2023-12-31 | WIN | WT | 223.8 |  |  | 2016-11-04 | 2017-01-10 | 2017-03-23 | 2022-03-14 | No | 2020-02-13 | No | Not Required | Not Required | Not Required
19INR0023 | Monte Alto 2 Wind | SS Completed, FIS Completed, IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2023-12-31 | WIN | WT | 236.9 |  |  | 2016-11-04 | 2017-01-10 | 2017-03-23 | 2022-03-14 | No | 2022-03-22 | No | Not Required | Not Required | Not Required
19INR0026 | Holstein 2 Solar | SS Completed, FIS Started, No IA | 229HD 8me LLC | 11406 Central Bluff 345kV | Nolan | WEST | 2024-04-26 | SOL | PV | 100 |  | 2017-02-13 | 2016-12-21 | 2017-02-02 | 2017-02-13 |  |  |  | No | Not Required | Not Required | Not Required
19INR0035 | Norton Solar | SS Completed, FIS Completed, IA | 231RC 8me LLC | 60451 Garnet 138kV | Runnels | WEST | 2024-01-31 | SOL | PV | 125 | COD | 2017-11-08 | 2017-03-06 | 2017-04-20 | 2017-11-08 | 2020-12-15 | No | 2019-06-20 | Yes | Not Required | Not Required | Not Required | 2019-07-12
19INR0041 | Myrtle Solar | SS Completed, FIS Completed, IA | Myrtle Solar, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2023-05-05 | SOL | PV | 321.2 | COD |  | 2017-03-15 | 2017-04-28 | 2017-05-09 | 2022-01-25 |  | 2019-11-13 | Yes | Not Required | Not Required | Not Required | 2019-11-30 | 2020-05-06 | 2022-02-01
19INR0042 | Long Point Solar | SS Completed, FIS Started, IA | Long Point Solar LLC | tap 138kV 44010 WAP - 42980 Nash | Brazoria | COASTAL | 2023-05-19 | SOL | PV | 101.25 |  | 2017-11-02 | 2017-03-15 | 2017-04-20 | 2017-11-13 |  |  | 2019-10-24 | No | Not Required | Not Required | Not Required
19INR0045 | Nebula Solar | SS Completed, FIS Completed, IA | Rayos Del Sol Solar Project, LLC | tap 138kV 8554 Mesquite - 80103 Rangerville | Cameron | COASTAL | 2022-07-01 | SOL | PV | 137.45 | COD |  | 2017-03-28 | 2017-05-22 | 2017-03-28 | 2021-01-21 | No | 2018-11-06 | Yes | Not Required | Not Required | Not Required | 2019-01-23 | 2020-03-17 | 2021-01-29 |  |  | 2022-01-18 | 2022-04-12
19INR0052 | TG East Wind | SS Completed, FIS Completed, IA | Northrenew | 60722 Coulomb 345kV | Knox | WEST | 2022-07-15 | WIN | WT | 336 | COD | 2017-06-13 | 2017-04-04 | 2017-05-18 | 2017-06-13 | 2021-01-22 | No | 2018-10-22 | Yes | Not Required | Not Required | Not Required | 2020-04-28 | 2021-01-25 | 2021-01-25 |  |  | 2021-08-10 | 2021-09-27
19INR0054 | Monte Cristo 1 Wind | SS Completed, FIS Started, No IA | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | SOUTH | 2024-12-31 | WIN | WT | 236.9 |  | 2017-07-28 | 2017-04-11 | 2017-05-03 | 2017-07-28 |  |  |  | No | Not Required | Not Required | Not Required
19INR0073 | McLean (Shakes) Solar | SS Completed, FIS Completed, IA | Cypress Creek Renewables | 8283 Asherton 138kV | Zavala | SOUTH | 2022-10-15 | SOL | PV | 206 |  |  | 2017-05-03 | 2017-06-15 | 2017-05-03 | 2019-09-19 | No | 2018-10-26 | Yes | Not Required | Not Required | Not Required | 2019-03-04 | 2021-10-20 | 2021-10-26
19INR0075 | Horseshoe Bend Solar | SS Completed, FIS Started, No IA | Clenera | 1444 Brown 345kV | Brown | NORTH | 2024-05-31 | SOL | PV | 330.75 | MW Size | 2018-02-09 | 2017-06-23 | 2017-08-07 | 2018-02-09 |  | No |  | No | Not Required | Not Required | Not Required
19INR0080 | Whitehorse Wind | SS Completed, FIS Completed, IA | MESQUITE STAR SPECIAL LLC | 68001 Clayton 345kV | Fisher | WEST | 2022-12-01 | WIN | WT | 418.9 |  |  | 2017-06-23 | 2017-08-07 | 2018-02-16 | 2019-01-22 | No | 2018-12-05 | Yes | Not Required | Not Required | Not Required | 2019-03-12 | 2019-04-02 | 2019-05-01 |  |  | 2019-12-12 | 2019-12-27
19INR0085 | Blue Jay Solar | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2023-03-14 | SOL | PV | 141.05 | COD | 2018-02-15 | 2017-05-30 | 2017-08-11 | 2018-02-15 | 2021-04-26 | No | 2020-10-26 | Yes | Not Required | Not Required | Not Required | 2020-12-02 | 2021-04-26 | 2021-04-29 |  |  | 2021-11-11 | 2022-06-28
19INR0100 | Prairie Hill Wind | SS Completed, FIS Completed, IA | Prairie Hill LLC | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | McLennan | NORTH | 2022-08-31 | WIN | WT | 300 |  | 2017-06-19 | 2017-06-19 | 2017-08-11 | 2017-06-19 | 2020-04-03 | No | 2018-09-17 | Yes | Not Required | Not Required | Not Required | 2018-11-27 | 2020-04-21 | 2020-04-21 |  |  | 2020-10-19 | 2020-11-12
19INR0103 | Rodeo Solar | SS Completed, FIS Started, IA | Core Solar SPV I, LLC | tap 138kV 1134 Littman - 1135 Gasland | Andrews | WEST | 2023-11-01 | SOL | PV | 200 | Status Change INA-to-PLN | 2018-02-19 | 2017-06-29 | 2017-08-04 | 2018-02-19 |  |  | 2019-08-20 | Yes | Not Required | Not Required | Not Required | 2021-03-10
19INR0110 | Azalea Springs Solar | SS Completed, FIS Started, No IA | EDP Renewables | tap 138kV Jim English – Lufkin Chipper Mill | Angelina | NORTH | 2024-10-31 | SOL | PV | 180 |  |  | 2017-07-26 | 2017-09-15 | 2018-03-15 |  | No |  | No | Not Required | Not Required | Not Required
19INR0117 | Roadrunner Crossing Wind | SS Completed, FIS Started, IA | NextEra Energy Resources, LLC | 68051 Reata 345kV | Eastland | NORTH | 2024-01-31 | WIN | WT | 128 | MW Size | 2018-03-01 | 2017-09-08 | 2017-11-07 | 2018-03-05 |  | No | 2020-04-17 | Yes | Not Required | Not Required | Not Required | 2020-09-17
19INR0120 | Sherbino II Wind repower | SS Completed, FIS Completed, IA | Sherbino II Wind Farm LLC | 38430 TN White Baker 138kV | Pecos | WEST | 2022-06-30 | WIN | WT | -18 | COD | 2017-09-21 | 2017-08-18 | 2017-09-28 | 2017-09-21 | 2018-12-04 | No | 2008-02-28 | Yes | Not Required | Not Required | Not Required | 2019-10-28 | 2019-10-28 | 2019-10-28 |  |  |  | 2020-06-09
19INR0128 | White Mesa Wind | SS Completed, FIS Completed, IA | White Mesa Wind, LLC | 76005 Schneeman Draw 345kV | Crockett | WEST | 2022-03-31 | WIN | WT | 152.3 |  |  | 2017-09-08 | 2017-11-20 | 2018-01-29 | 2019-04-24 | No | 2018-12-13 | Yes | Not Required | Not Required | Not Required | 2019-06-03 | 2020-10-29 | 2020-10-29 |  |  | 2021-04-28 | 2021-05-12
19INR0131 | Rowland Solar I | SS Completed, FIS Completed, IA | Cutlass Solar LLC | tap 345kV 44005 WAP - 44090 Cedar Creek | Fort Bend | HOUSTON | 2022-10-04 | SOL | PV | 101.75 |  | 2018-05-15 | 2017-09-21 | 2017-11-20 | 2018-05-15 | 2020-03-27 | No | 2020-09-23 | Yes | Not Required | Not Required | Not Required | 2021-10-27 | 2021-10-29 | 2021-10-29 |  |  | 2022-05-24 | 2022-06-13
19INR0134 | Cottonwood Bayou Solar | SS Completed, FIS Started, IA | Cottonwood Bayou Solar, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2024-03-31 | SOL | PV | 150 |  |  | 2017-09-22 | 2017-11-17 | 2018-02-15 |  | No | 2019-11-13 | No | Not Required | Not Required | Not Required
19INR0145 | Aquilla Lake Wind | SS Completed, FIS Completed, IA | Nextera | 68090 Sam Switch 345 kV | Hill | NORTH | 2022-06-30 | WIN | WT | 202 |  | 2018-07-18 | 2018-07-18 | 2018-09-20 | 2018-07-18 | 2020-01-17 | No | 2020-06-30 | Yes | Not Required | Not Required | Not Required | 2020-07-23 | 2021-01-07 | 2021-01-25 |  |  | 2021-08-12 | 2021-09-09
19INR0155 | Morrow Lake Solar | SS Completed, FIS Completed, IA | Sunchase Power | 5895 Pearsall 138kV | Frio | SOUTH | 2023-05-19 | SOL | PV | 204 |  | 2018-02-15 | 2017-12-05 | 2018-01-15 | 2018-02-15 | 2020-04-15 | No | 2019-08-29 | Yes | Not Required | Not Required | Not Required | 2019-11-18 | 2020-04-15
19INR0159 | Reiher Solar | SS Completed, FIS Started, No IA | EnergieKontor US Texas SP 7 LLC | 76597 Robb Sw 138kV | Upton | WEST | 2023-06-30 | SOL | PV | 120 |  | 2018-08-14 | 2018-01-29 | 2018-03-27 | 2018-08-14 |  | No |  | No | Not Required | Not Required | Not Required
19INR0165 | Barranca Wind | SS Completed, FIS Started, No IA | Lincoln Clean Energy, LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2024-01-30 | WIN | WT | 201.6 |  |  | 2018-05-09 | 2018-05-25 | 2018-02-28 |  |  |  | No | Not Required | Not Required | Not Required
19INR0169 | Sun Valley Solar | SS Completed, FIS Completed, IA | Sun Valley Solar LLC | tap 345kV 68090 Sam Sw - 3405 Tradinghouse | Hill | NORTH | 2022-12-29 | SOL | PV | 252 |  | 2018-11-09 | 2018-03-02 | 2018-04-17 | 2018-07-19 | 2022-01-29 | No | 2020-03-15 | Yes | Not Required | Not Required | Not Required | 2021-08-13 | 2021-12-21 | 2022-02-01
19INR0174 | Elbow Creek repower | SS Completed, FIS Completed, IA | NRG | 1058 Longshore 345kV | Howard | WEST | 2022-11-01 | WIN | WT | 0 |  | 2018-07-19 | 2018-05-04 | 2018-05-18 | 2018-07-19 | 2018-09-17 | No | 2007-11-30 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-27
19INR0175 | Shifting Gale Wind | SS Completed, FIS Started, No IA | SEAWAY WIND ENERGY LLC | 23912 Ogallala 345kV | Castro | PANHANDLE | 2025-12-31 | WIN | WT | 289 |  | 2018-12-06 | 2018-04-26 | 2018-06-12 | 2018-12-06 |  | No |  | No | Not Required | Not Required | Not Required
19INR0176 | Roughneck Storage | SS Completed, FIS Completed, IA | KCE TX 23, LLC | 43380 W Columbia 138kV | Brazoria | COASTAL | 2022-06-30 | OTH | BA | 50 | Status Change INA-to-PLN | 2018-11-07 | 2018-05-09 | 2018-07-13 | 2018-11-07 | 2020-10-23 | No | 2020-05-13 | Yes | Not Required | Not Required | Not Required | 2020-10-28 | 2020-10-28 | 2020-10-28 |  |  | 2021-06-15 | 2022-05-12
19INR0177 | Crawfish | SS Completed, FIS Started, IA | Prairie Switch Wind, LLC | 8679 Arroz4A 138kV | Wharton | SOUTH | 2023-07-31 | WIN | WT | 163.2 |  |  | 2018-05-09 | 2018-06-21 | 2018-05-09 |  | No | 2021-07-06 | Yes | Not Required | Not Required | Not Required
19INR0179 | Barranca Wind II | SS Completed, FIS Started, No IA | Lincoln Clean Energy, LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2024-12-31 | WIN | WT | 201.6 |  |  | 2018-05-15 | 2018-06-01 | 2018-05-15 |  |  |  | No | Not Required | Not Required | Not Required
19INR0189 | SP TX-12B Phase III | SS Completed, FIS Started, No IA | ConEd Development | 76040 Castillo 138kV | Upton | WEST | 2023-12-01 | SOL | PV | 40 |  | 2019-01-29 | 2018-09-12 | 2018-10-03 |  |  | No |  | No | Not Required | Not Required | Not Required
19INR0203 | Angelo Solar | SS Completed, FIS Started, IA | ANGELO SOLAR LLC | 76009 Twin Buttes 345kV | Tom Green | WEST | 2023-08-31 | SOL | PV | 195 |  | 2019-01-17 | 2018-11-20 | 2019-02-05 | 2019-01-21 |  | No | 2021-12-03 | No |  |  | Not Required
20INR0012 | Lueders Solar | SS Completed, FIS Started, No IA | Innovative Solar 75 | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | WEST | 2024-06-30 | SOL | PV | 40 |  |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  | No |  | No | Not Required | Not Required | Not Required
20INR0014 | Obsidian Solar | SS Completed, FIS Started, No IA | Innovative Solar 144 | 6131 Padr 69kV | Cottle | WEST | 2023-10-31 | SOL | PV | 60 |  | 2017-10-20 | 2017-07-11 | 2017-08-28 | 2017-10-20 |  | No |  | No | Not Required | Not Required | Not Required
20INR0015 | Citrine Solar | SS Completed, FIS Started, No IA | Innovative Solar 145 | 138kV 6135 Paducah Clare | Cottle | WEST | 2023-09-30 | SOL | PV | 45 |  | 2017-10-20 | 2017-07-11 | 2017-08-28 | 2017-10-20 |  | No |  | No | Not Required | Not Required | Not Required
20INR0016 | Opal Solar | SS Completed, FIS Started, No IA | Innovative Solar 165 | tap 345kV 60501 Tesla - 60500 Edith Clark | Hardeman | WEST | 2023-12-31 | SOL | PV | 45 |  |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  | No |  | No | Not Required | Not Required | Not Required
20INR0019 | Trinity Hills Wind repower | SS Completed, FIS Completed, IA | Trinity Hills Wind Farm LLC | 17002 Garvey Rd 345kV | Young | WEST | 2022-06-25 | WIN | WT | -27 | COD | 2017-09-21 | 2017-07-20 | 2017-09-08 | 2017-09-21 | 2018-08-02 | No | 2018-10-17 | No | Not Required | Not Required | Not Required | 2019-10-29 | 2019-10-29 | 2019-10-29 |  |  |  | 2020-05-22
20INR0026 | Longbow Solar | SS Completed, FIS Completed, IA | Longbow Solar, LLC | 42110 Angelton - 42870 Liverpool 138kV | Brazoria | COASTAL | 2022-09-12 | SOL | PV | 78.15 |  |  | 2017-08-16 | 2017-10-13 | 2017-08-16 | 2021-10-15 | No | 2021-01-06 | Yes | Not Required | Not Required | Not Required | 2021-11-01 | 2021-11-01 | 2021-11-01
20INR0029 | Lutum Wind | SS Completed, FIS Started, No IA | EDF Renewable Energy | tap 345kV 6101 Riley - 1730 W Krum | Clay | WEST | 2024-07-11 | WIN | WT | 241.5 |  |  | 2017-09-12 | 2017-11-07 | 2018-05-08 |  | No |  | No | Not Required | Not Required | Not Required
20INR0033 | WILDWIND | SS Completed, FIS Completed, IA | Wildcat Creek | tap 345kV 1730 KrumW - 2373 Anna | Cooke | NORTH | 2022-07-30 | WIN | WT | 180.08 |  | 2018-06-14 | 2017-10-18 | 2017-12-11 | 2018-06-14 | 2019-11-25 | No | 2020-02-21 | Yes | Not Required | Not Required | Not Required | 2020-03-23 | 2020-04-30 | 2020-04-30 |  |  | 2020-12-22 | 2021-02-10
20INR0035 | Angus Solar | SS Completed, FIS Started, IA | Angus Solar, LLC | tap 138kV 177 Bosque - 181 Cayote | Bosque | NORTH | 2023-11-01 | SOL | PV | 112 |  | 2017-11-13 | 2017-11-13 | 2018-01-02 | 2017-11-13 |  |  | 2021-12-06 | Yes | Not Required | Not Required | Not Required
20INR0038 | Red Mud Creek | SS Completed, FIS Started, No IA | RWE Renewables Development, LLC | tap 345kV 11318 Scurry - 59905 Faraday or 11318-59900 Long Draw | Borden | WEST | 2024-12-12 | WIN | WT | 201 |  |  | 2017-11-29 | 2018-02-05 | 2018-03-15 |  |  |  | No | Not Required | Not Required | Not Required
20INR0040 | Montgomery Ranch Wind | SS Completed, FIS Started, IA | RWE Renewables Development, LLC | tap 345kV 60500 Edith Clark – 60506 Avogrado | Foard | WEST | 2023-12-15 | WIN | WT | 200.2 |  | 2018-06-20 | 2017-12-18 | 2018-02-06 | 2018-06-20 |  |  | 2022-03-22 | Yes | Not Required | Not Required | Not Required
20INR0047 | Siete | SS Completed, FIS Started, IA | Apex Clean | 345 kV Lobo (80219) - Fowlerton (5709) | Webb | SOUTH | 2024-10-31 | WIN | WT | 375.06 |  | 2019-06-13 | 2018-10-23 | 2018-12-11 | 2019-06-12 |  | No | 2022-06-30 | No | Not Required | Not Required | Not Required
20INR0050 | Castro Solar | SS Completed, FIS Started, IA | Castro Solar One, LLC | 23912 Ogallala 345kV | Castro | PANHANDLE | 2023-10-23 | SOL | PV | 222.95 |  | 2018-05-15 | 2018-02-08 | 2018-04-09 | 2018-05-15 |  | No | 2020-11-30 | No | Not Required | Not Required | Not Required
20INR0053 | Bravepost Solar | SS Completed, FIS Started, No IA | Recurrent Energy | 6444 Red Creek 345kV | Tom Green | WEST | 2024-12-31 | SOL | PV | 200 |  | 2018-06-07 | 2018-02-22 | 2018-04-13 | 2018-06-07 |  |  |  | No | Not Required | Not Required | Not Required
20INR0061 | Pflugerville 2 Solar | SS Completed, FIS Started, No IA | RRE Power LLC 1 | tap 138kV 7336 Gillie - 3650 Elgin | Travis | SOUTH | 2023-04-30 | SOL | PV | 120 |  | 2018-10-10 | 2018-03-05 | 2018-04-19 | 2018-10-10 |  |  |  | No | Not Required | Not Required | Not Required
20INR0068 | Blackjack Creek Wind | SS Completed, FIS Completed, IA | RWE Renewables Development, LLC | 8624 Grissom 345kV | Bee | SOUTH | 2022-04-15 | WIN | WT | 240.5 |  |  | 2018-04-02 | 2018-05-18 | 2018-11-07 | 2021-01-29 | No | 2019-10-24 | Yes | Not Required | Not Required | Not Required | 2019-11-24 | 2021-01-29 | 2021-01-29 |  |  | 2021-09-15 | 2022-02-15
20INR0069 | Danish Fields Solar | SS Completed, FIS Started, IA | Danish Fields Solar, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2023-11-13 | SOL | PV | 619.1 |  |  | 2018-04-12 | 2018-06-05 | 2018-08-21 |  | No | 2020-02-24 | Yes | Not Required | Not Required | Not Required
20INR0074 | Pitts Dudik Solar | SS Completed, FIS Completed, IA | Elawan Pitts Dudik Solar, LLC | tap 138kV Hillsoboro 3522- Navarro 3478 | Hill | NORTH | 2022-12-31 | SOL | PV | 50 |  |  | 2018-04-12 | 2018-05-18 | 2018-05-25 | 2021-01-20 | No | 2021-05-10 | Yes | Not Required | Not Required | Not Required | 2022-04-27 | 2022-04-27 | 2022-04-27
20INR0075 | Howle Solar | SS Completed, FIS Completed, IA | Belltown Power | tap 345kV 1907 Venus - 68090 Sam Sw | Ellis | NORTH | 2023-12-31 | SOL | PV | 60 |  | 2018-08-09 | 2018-05-15 | 2018-07-02 | 2018-08-14 | 2022-03-22 | No | 2022-06-13 | No | Not Required | Not Required | Not Required
20INR0080 | Frye Solar | SS Completed, FIS Started, IA | Hecate Energy | new 345kV sub Kress connecting both 23912 Ogallala - 23914 Tule Canyon circuits | Swisher | PANHANDLE | 2023-05-20 | SOL | PV | 514.1 |  | 2018-10-23 | 2018-05-17 | 2018-07-02 | 2018-11-20 |  | No | 2021-02-06 | Yes | Not Required | Not Required | Not Required
20INR0081 | Strategic Solar 1 | SS Completed, FIS Completed, IA | Elm Branch Solar 1, LLC | tap 345kV 2435 Watermill - 68091 Navarro | Ellis | NORTH | 2022-06-25 | SOL | PV | 136.85 | COD | 2018-07-18 | 2018-04-26 | 2018-06-05 | 2018-07-18 | 2020-09-25 | No | 2020-01-13 | Yes | Not Required | Not Required | Not Required | 2020-07-10 | 2020-09-29 | 2020-10-27 |  |  | 2021-07-20 | 2021-10-06
20INR0082 | Vision Solar 1 | SS Completed, FIS Completed, IA | Briar Creek Solar 1, LLC | tap 345kV 2428 Watermill - 68091 Navarro | Navarro | NORTH | 2022-06-25 | SOL | PV | 129.24 | COD | 2018-05-17 | 2018-04-26 | 2018-06-05 | 2018-05-17 | 2020-09-29 | No | 2020-01-13 | Yes | Not Required | Not Required | Not Required | 2020-10-27 | 2020-10-27 | 2020-10-27 |  |  | 2021-07-21 | 2021-10-08
20INR0083 | Baird North Wind | SS Completed, FIS Completed, IA | BMP Wind, LLC | 68008 Latimer 345kV | Callahan | WEST | 2022-12-01 | WIN | WT | 350 |  |  | 2018-05-04 | 2018-06-12 | 2018-08-20 | 2020-10-30 | No | 2019-05-31 | Yes | Not Required | Not Required | Not Required | 2019-07-19 | 2020-10-30 | 2020-11-01 |  |  | 2021-08-09 | 2021-08-20
20INR0086 | Arroyo Solar | SS Completed, FIS Completed, IA | BT Cantwell Solar, LLC | 345 KV Tap #8318 Rio Hondo - #8317 La Palma | Cameron | COASTAL | 2024-03-15 | SOL | PV | 180 |  | 2018-10-10 | 2018-05-09 | 2018-07-09 | 2018-10-10 | 2021-09-27 | No | 2021-09-28 | No | Not Required | Not Required | Not Required
20INR0091 | Fagus Solar Park | SS Completed, FIS Started, IA | Excel Advantage Services, LLC dba Misae Solar Park II | 60501 Tesla 345kV | Childress | PANHANDLE | 2023-12-31 | SOL | PV | 517.35 |  | 2018-05-15 | 2018-05-15 | 2018-07-06 | 2018-05-15 |  | No | 2019-02-21 | Yes | Not Required | Not Required | Not Required | 2021-01-15
20INR0097 | El Sauz Ranch | SS Completed, FIS Completed, IA | El Sauz Ranch Wind, LLC | 8663 EL SAUZ POI 345kV | Willacy | COASTAL | 2022-10-01 | WIN | WT | 301.5 |  | 2019-02-01 | 2018-06-19 | 2018-08-22 | 2019-01-31 | 2021-10-29 |  | 2021-01-27 | Yes | Not Required | Not Required | Not Required | 2021-10-14 | 2022-01-26 | 2022-01-26
20INR0098 | Danciger Solar | SS Completed, FIS Completed, IA | Brazoria County Solar Project, LLC | tap 138kV 43120 Pledger - 43380 W Columbia | Brazoria | COASTAL | 2022-12-01 | SOL | PV | 203.2 |  | 2018-10-23 | 2018-06-06 | 2018-08-01 | 2018-10-23 | 2020-05-21 | No | 2020-03-20 | Yes | Not Required | Not Required | Not Required | 2020-11-09 | 2021-07-26 | 2021-10-29 |  |  | 2022-06-30
20INR0101 | Westoria Solar | SS Completed, FIS Completed, IA | Brazoria West Solar Project, LLC | tap 138kV 42410 Burke - 43380 W Columbia | Brazoria | COASTAL | 2022-09-06 | SOL | PV | 203.35 |  | 2018-10-23 | 2018-06-07 | 2018-07-30 | 2018-10-23 | 2020-06-01 | No | 2020-03-20 | Yes | Not Required | Not Required | Not Required | 2020-07-10 | 2021-04-30 | 2021-04-30 |  |  | 2022-04-04 | 2022-05-13
20INR0106 | Wang Solar DCC | SS Completed, FIS Started, No IA | BT Yixin Solar, LLC | tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2022-12-31 | SOL | PV | 141.75 |  | 2018-08-29 | 2018-06-14 | 2018-08-13 | 2018-08-29 |  | No |  | No | Not Required | Not Required | Not Required
20INR0120 | Vortex Wind | SS Completed, FIS Completed, IA | AZURE SKY WIND PROJECT LLC | loop 345kV 60515 Clear Crossing - 1421 WillowCr 345kV | Throckmorton | WEST | 2022-06-29 | WIN | WT | 350 |  | 2019-02-28 | 2018-06-29 | 2018-08-27 | 2019-02-20 | 2021-04-30 | No | 2020-12-01 | Yes | Not Required | Not Required | Not Required | 2021-03-25 | 2021-04-29 | 2021-04-30 |  |  | 2021-11-19 | 2022-02-23
20INR0127 | Milam Solar 1 | SS Completed, FIS Started, No IA | Sandow Lakes Ranch Solar I, LLC | tap one 345kV 7040 Austrop - 13429 Sandow line | Milam | SOUTH | 2024-05-16 | SOL | PV | 217.23 |  | 2019-08-13 | 2018-07-03 | 2018-09-18 |  |  |  |  | No | Not Required | Not Required | Not Required
20INR0128 | EK Tipton Solar | SS Completed, FIS Started, No IA | EnergieKontor US Texas SP 1 LLC | 6673 Musquiz 138kV | Reeves | WEST | 2023-12-29 | SOL | PV | 120 |  | 2018-09-27 | 2018-09-27 | 2018-11-19 | 2018-09-27 |  | No |  | No | Not Required | Not Required | Not Required
20INR0129 | Foxtrot Wind | SS Completed, FIS Completed, IA | Lincoln Clean | AEP 88689 Tango 345kV station | Bee | SOUTH | 2022-07-30 | WIN | WT | 268.2 | COD |  | 2018-07-26 | 2018-09-14 | 2018-07-26 | 2021-07-30 | No | 2020-05-05 | Yes | Not Required | Not Required | Not Required | 2021-07-30 | 2021-07-30 | 2021-07-30 |  |  | 2022-02-23 | 2022-03-09
20INR0130 | Plainview Solar | SS Completed, FIS Completed, IA | Hecate Energy Ramsey LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2023-07-31 | SOL | PV | 514 | COD | 2018-07-18 | 2018-10-10 | 2018-11-21 | 2018-10-10 | 2020-10-26 | No | 2020-05-29 | Yes | Not Required | Not Required | Not Required | 2020-10-07 | 2020-10-26 | 2020-10-26 |  |  | 2021-07-17 | 2021-07-26
20INR0134 | Half Moon Solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2023-12-29 | SOL | PV | 151.2 |  |  | 2018-09-13 | 2018-11-09 | 2018-11-06 |  | No |  | No | Not Required | Not Required | Not Required
20INR0135 | Half Moon Battery | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2023-12-29 | OTH | BA | 30.2 |  |  | 2018-09-13 | 2018-11-09 | 2018-11-06 |  | No |  | No | Not Required | Not Required | Not Required
20INR0143 | Soda Lake Solar 2 | SS Completed, FIS Started, IA | Arrington Solar | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | WEST | 2023-05-31 | SOL | PV | 202.99 |  | 2020-09-08 | 2016-11-07 | 2016-11-08 | 2017-02-10 |  | No | 2018-08-20 | No | Not Required | Not Required | Not Required
20INR0155 | Peyton Creek Wind II | SS Completed, FIS Started, No IA | RWE Renewables Development, LLC | 42400 Refuge 345kV | Matagorda | COASTAL | 2023-12-15 | WIN | WT | 242 | COD | 2019-01-30 | 2018-08-21 | 2018-11-02 | 2019-03-14 |  | No |  | No | Not Required | Not Required | Not Required
20INR0162 | Diamondback solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Starr | SOUTH | 2024-07-31 | SOL | PV | 201.6 |  |  | 2018-09-13 | 2018-12-06 | 2018-11-07 |  | No |  | No | Not Required | Not Required | Not Required
20INR0164 | BPL Files Solar | SS Completed, FIS Completed, IA | BPL Files Solar | tap 345kV 1906 Venus - 68090 Sam | Hill | NORTH | 2023-03-31 | SOL | PV | 148.7 |  |  | 2018-08-29 | 2018-11-08 | 2018-11-07 | 2021-01-20 | No | 2021-03-10 | Yes | Not Required | Not Required | Not Required | 2022-02-10 | 2022-05-02 | 2022-05-02
20INR0202 | Rueter Solar | SS Completed, FIS Completed, IA | Reuter Solar | New 345kV LST Skydancer Station (tap 345kV line between West Shackelford #68000 to Navarro #68091) | Bosque | NORTH | 2022-12-31 | SOL | PV | 200 |  | 2018-10-10 | 2018-09-19 | 2018-10-03 | 2018-10-10 | 2020-02-24 | No | 2020-10-15 | No | Not Required | Not Required | Not Required
20INR0203 | Pine Forest Solar | SS Completed, FIS Not Started, IA | Pine Forest Solar I, LLC | Monticello Switch – Allen Switch 345 kV Line | Hopkins | NORTH | 2024-01-15 | SOL | PV | 286.25 | MW Size | 2019-03-26 | 2018-10-04 | 2018-11-20 |  |  | No | 2020-07-29 | No | Not Required | Not Required | Not Required
20INR0205 | Roseland Solar | SS Completed, FIS Completed, IA | Enel Green Power Roseland Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2023-03-01 | SOL | PV | 254 |  | 2018-11-05 | 2018-11-30 | 2019-02-04 | 2019-02-04 | 2021-10-25 | No | 2020-12-10 | Yes | Not Required | Not Required | Not Required | 2021-08-18 | 2021-11-01 | 2021-10-25 |  |  | 2022-06-07
20INR0208 | Signal Solar | SS Completed, FIS Not Started, IA | Adapture Renewables, Inc | tap 138kV 6879 Weiland - 6883 Quinlan N | Hunt | NORTH | 2024-06-14 | SOL | PV | 50 | COD | 2019-04-02 | 2018-11-07 | 2018-12-20 |  |  | No | 2020-10-23 | No | Not Required | Not Required | Not Required
20INR0210 | Hopkins Solar | SS Completed, FIS Completed, IA | Hopkins Energy LLC | tap 345kV 11688 THORNTRE - 11689 CYCLONE | Hopkins | NORTH | 2023-10-01 | SOL | PV | 252 |  | 2019-03-15 | 2018-11-20 | 2019-02-06 | 2019-03-14 | 2022-01-03 | No | 2020-09-25 | No | Not Required | Not Required | Not Required
20INR0213 | Brushy Creek Solar SLF | SS Completed, FIS Started, No IA | Brushy Creek Solar LLC | 6444 Red Creek 345kV | Tom Green | WEST | 2024-09-15 | SOL | PV | 177.09 |  | 2019-03-26 | 2019-01-07 | 2019-03-26 | 2019-03-05 |  | No |  | No | Not Required | Not Required | Not Required
20INR0214 | Noble Solar | SS Completed, FIS Completed, IA | BT Noble Solar, LLC | 1730 Krum 345kV | Denton | NORTH | 2022-05-30 | SOL | PV | 279 |  | 2018-11-06 | 2018-11-06 | 2018-12-17 | 2018-11-06 | 2021-05-28 | No | 2020-10-10 | Yes |  |  | Not Required | 2021-08-17 | 2021-08-17 | 2021-08-17 |  |  | 2021-12-21 | 2022-02-18
20INR0216 | Starr Solar Ranch | SS Completed, FIS Completed, IA | Starr Solar Ranch LLC | 8795 Roma 138kV | Starr | SOUTH | 2023-05-31 | SOL | PV | 135.99 |  | 2018-11-07 | 2018-11-07 | 2018-12-14 | 2018-11-07 | 2020-04-01 | No | 2020-10-01 | Yes | Not Required | Not Required | Not Required | 2020-11-19
20INR0222 | Tyson Nick Solar | SS Completed, FIS Completed, IA | Tyson Nick Solar Project, LLC | 1700 Toco 138kV | Lamar | NORTH | 2023-12-31 | SOL | PV | 90 |  | 2019-02-25 | 2018-12-12 | 2019-02-15 | 2019-01-14 | 2020-07-06 | No | 2020-08-28 | No | Not Required | Not Required | Not Required
20INR0230 | Markum Solar | SS Completed, FIS Completed, IA | Glory Leasing LLC | 177 Bosque 138kV | McLennan | NORTH | 2024-02-05 | SOL | PV | 161 |  | 2018-12-17 | 2018-12-18 | 2019-01-03 | 2018-12-18 | 2020-08-24 |  | 2021-06-28 | Yes | Not Required | Not Required | Not Required | 2021-10-04
20INR0233 | Impala Flats Wind | SS Completed, FIS Started, No IA | Antelope Flats Wind, LLC | 79641 Farmland 345kV | Lynn | WEST | 2023-06-03 | WIN | WT | 282 |  | 2019-01-15 | 2019-01-11 | 2019-04-03 | 2018-12-21 |  |  |  | No |  |  | Not Required
20INR0235 | Knickerbocker Solar SLF | SS Completed, FIS Started, No IA | Knickerbocker Solar LLC | Tap 345kV 76003 Big Hill - 76009 Twin Buttes | Tom Green | WEST | 2025-01-15 | SOL | PV | 241.26 |  | 2019-03-12 | 2019-01-07 | 2019-03-15 | 2019-03-04 |  |  |  | No | Not Required | Not Required | Not Required
20INR0236 | Old Hickory Solar | SS Completed, FIS Completed, IA | Old Hickory Solar LLC | tap 345kV 5133 Elmcreek - 5915 STP c2 | Jackson | SOUTH | 2023-05-31 | SOL | PV | 206 |  | 2019-08-27 | 2019-01-25 | 2019-04-19 | 2019-08-12 | 2020-10-09 |  | 2020-06-30 | Yes | Not Required | Not Required | Not Required | 2021-04-12
20INR0238 | Voyager Storage | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2024-03-01 | OTH | BA | 50.14 |  | 2019-04-30 | 2019-01-14 | 2019-03-19 | 2019-04-26 |  |  |  | No | Not Required | Not Required | Not Required
20INR0241 | Crowded Star Solar | SS Completed, FIS Completed, IA | Jones City Solar, LLC | tap 345kV 68000 West Shack - 68001 Clayton c2 | Jones | WEST | 2024-10-03 | SOL | PV | 217.6 |  | 2019-05-23 | 2019-01-21 | 2019-04-19 | 2019-05-22 | 2021-11-19 | No | 2019-12-17 | Yes | Not Required | Not Required | Not Required | 2021-12-01
20INR0242 | Anson Solar Center, Phase II | SS Completed, FIS Started, No IA | Anson Solar Center 2, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2023-12-29 | SOL | PV | 200 |  | 2018-02-15 | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  |  | No | Not Required | Not Required | Not Required
20INR0244 | Montezuma Storage | SS Completed, FIS Started, No IA | Montezuma Storage LLC | 7258 Glidden 138kV | Colorado | SOUTH | 2023-06-15 | OTH | BA | 50.6 |  | 2019-01-08 | 2019-01-15 | 2019-07-02 | 2019-03-15 |  |  |  | No | Not Required | Not Required | Not Required
20INR0245 | Volunteer Storage | SS Completed, FIS Started, No IA | Blackjack Storage LLC | 7216 Lockhart 138kV | Caldwell | SOUTH | 2023-06-15 | OTH | BA | 50.6 |  | 2019-01-16 | 2019-01-15 | 2019-07-02 | 2019-03-15 |  |  |  | No | Not Required | Not Required | Not Required
20INR0246 | Ryan Energy Storage | SS Completed, FIS Completed, IA | Ryan Storage LLC | 37580 TNPancake 69kV | Coryell | NORTH | 2023-01-09 | OTH | BA | 50 |  | 2019-02-08 | 2019-01-15 | 2019-04-05 | 2019-03-15 | 2020-08-16 | No | 2021-02-18 | Yes | Not Required | Not Required | Not Required
20INR0247 | Water Valley Wind Energy | SS Completed, FIS Started, No IA | Water Valley Wind Energy, LLC | 76011 Twin Buttes 138kV | Tom Green | WEST | 2023-11-15 | WIN | WT | 150 |  | 2019-01-10 | 2019-01-15 | 2019-03-29 | 2019-01-10 |  |  |  | No |  |  | Not Required
20INR0248 | Second Division Solar | SS Completed, FIS Started, IA | TX Gulf Solar 1 LLC | Tap 138 kV SANBER_POI_8 (Bus# 43110) to WEST COLUMBIA (Bus# 43380) Ckt 60 Line | Brazoria | COASTAL | 2024-01-15 | SOL | PV | 100.59 | MW Size COD | 2019-08-06 | 2019-03-28 | 2019-06-18 | 2019-07-29 |  | No | 2020-10-14 | No | Not Required | Not Required | Not Required
20INR0249 | Appaloosa Run Wind_ | SS Completed, FIS Completed, IA | Appaloosa Run Wind, LLC | tap 138kV 60361 Santarita - 76032 NMcCamey | Upton | WEST | 2023-03-01 | WIN | WT | 175 |  | 2019-02-19 | 2019-01-17 | 2019-04-02 | 2019-01-15 | 2022-04-06 |  | 2021-04-12 | Yes |  |  | Not Required | 2022-04-21 | 2022-04-21 | 2022-04-25
20INR0250 | Aguayo Wind | SS Completed, FIS Completed, IA | Castle Gap Wind Power | tap 345kV 1444 Brown - 3422 Killeen | Mills | NORTH | 2022-11-30 | WIN | WT | 196 |  | 2019-02-05 | 2019-02-05 | 2019-05-03 | 2019-03-05 | 2022-05-02 | No | 2022-04-29 | Yes | Not Required | Not Required | Not Required | 2022-05-02 | 2022-05-02 | 2022-05-02
20INR0255 | Dawn Solar | SS Completed, FIS Started, IA | Renegade Renewable LLC | Tap 345kV 23910 Windmill - 23906 AJ Swope | Deaf Smith | PANHANDLE | 2023-08-25 | SOL | PV | 515.66 |  | 2019-04-01 | 2019-02-26 | 2019-05-17 | 2019-02-07 |  |  | 2021-01-04 | No | Not Required | Not Required | Not Required
20INR0256 | Aquilla Lake 2 Wind | SS Completed, FIS Completed, IA | NextEra Energy | 68090 Sam Switch 345 kV | Hill | NORTH | 2022-06-30 | WIN | WT | 100 |  | 2019-03-05 | 2019-05-23 | 2019-08-13 | 2019-02-28 | 2020-01-17 | No | 2020-06-30 | Yes | Not Required | Not Required | Not Required | 2020-07-23 | 2021-01-07 | 2021-01-25 |  |  | 2021-09-09 | 2021-09-24
20INR0266 | Tres Bahias Solar | SS Completed, FIS Completed, IA | Tres Bahias Solar Power LLC | 8140 Joslin 138kV | Calhoun | COASTAL | 2023-11-30 | SOL | PV | 195 |  | 2019-06-03 | 2019-03-26 | 2019-06-11 | 2019-06-03 | 2022-01-21 |  | 2020-08-07 | Yes | Not Required | Not Required | Not Required | 2020-10-07
20INR0268 | Pyron BESS II | SS Completed, FIS Completed, IA | Pyron Wind Farm, LLC | 1048 Tonkawas 345kV | Nolan | WEST | 2022-07-30 | OTH | BA | 30.2 |  | 2019-09-09 | 2019-06-03 | 2019-08-30 | 2019-08-19 | 2022-01-26 | No | 2007-10-15 | Yes |  |  | Not Required | 2022-01-28 | 2022-01-28 | 2022-01-28
20INR0269 | Texas Solar Nova 2 | SS Completed, FIS Completed, No IA | Texas Solar Nova 1, LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2023-03-06 | SOL | PV | 202.9 |  | 2016-07-06 | 2019-06-24 | 2015-12-30 | 2019-06-19 | 2022-05-19 |  |  | Yes |  |  | Not Required
20INR0271 | Blue Hills Wind | SS Completed, FIS Started, No IA | Babcock & Wilcox Blue Hills, LLC | Tap 138kV 8683 Comstock - 60389 Corral | Val Verde | WEST | 2024-01-01 | WIN | WT | 276 |  | 2019-12-03 | 2019-05-07 | 2019-07-26 | 2019-11-21 |  |  |  | No | Not Required | Not Required | Not Required
20INR0279 | SHIELD Solar | SS Completed, FIS Started, No IA | MERIT SI DEVELOPMENT, LLC | 60441 OLLIN4A | Crane | WEST | 2023-06-01 | SOL | PV | 1.88 |  | 2019-05-31 | 2019-06-17 | 2019-09-05 | 2019-06-13 |  |  |  | No | Not Required | Not Required | Not Required
20INR0280 | High Lonesome BESS | SS Completed, FIS Completed, IA | High Lonesome Storage, LLC | tap 345kV 76002 Bakersfield - 7053 Noelke | Crockett | WEST | 2022-07-27 | OTH | BA | 51.06 |  | 2019-06-12 | 2019-06-11 | 2019-08-30 | 2019-06-07 | 2021-07-27 |  | 2020-08-26 | Yes | Not Required | Not Required | Not Required | 2021-06-09 | 2021-07-13 | 2021-07-30 |  |  | 2022-05-19 | 2022-06-01
20INR0281 | Queen BESS | SS Completed, FIS Completed, IA | Roadrunner Storage, LLC | 842 GPL King Mountain 345kV | Upton | WEST | 2022-07-26 | OTH | BA | 51.06 | COD | 2019-06-04 | 2019-06-11 | 2019-10-23 | 2019-06-07 | 2021-07-29 |  | 2020-08-06 | Yes | Not Required | Not Required | Not Required | 2021-06-28 | 2021-07-30 | 2021-07-30 |  |  | 2022-03-02 | 2022-04-12
20INR0282 | Odessa-Ector Unit 2 (Block 2) Uprate Repower | SS Completed, FIS Completed, IA | LA FRONTERA HOLDINGS LLC | 1026 Odessa 345kV | Ector | WEST | 2022-10-01 | GAS | CC | 83 | COD |  | 2019-06-18 | 2019-10-23 | 2019-06-14 | 2019-11-01 | No | 2019-11-01 | Yes | 2019-09-30 |  | 2019-10-01 | 2019-11-01 | 2019-11-01 | 2019-11-01
20INR0283 | CITY WEST Solar | SS Completed, FIS Started, No IA | MERIT SI DEVELOPMENT, LLC | 8507 Schottky 69kV | Live Oak | SOUTH | 2023-06-01 | SOL | PV | 4.13 |  | 2019-07-12 | 2019-07-15 | 2019-10-07 | 2019-07-12 |  |  |  | No | Not Required | Not Required | Not Required
20INR0286 | Wise County Power Repower (CT1, CT2) | SS Completed, FIS Completed, IA | Wise County Power Company LLC | 1421 Willow Creek 345kV | Wise | NORTH | 2022-11-01 | GAS | CC | 21 | COD | 2019-07-15 | 2019-07-25 | 2019-10-23 | 2019-07-16 | 2019-10-23 | No | 2001-03-19 | Yes | 2020-01-21 | Not Required | 2019-12-05 | 2020-01-22 | 2020-01-27 | 2020-01-27
20INR0290 | River Valley Storage 1 | SS Completed, FIS Completed, IA | KCE TX 19, LLC | 3650 Elgin SS 138kV | Williamson | SOUTH | 2022-11-01 | OTH | BA | 51.5 |  | 2019-11-01 | 2019-10-15 | 2020-01-07 | 2019-10-21 | 2022-04-27 | No | 2021-08-25 | Yes | Not Required | Not Required | Not Required | 2021-11-01 | 2021-11-01 | 2022-04-28
20INR0291 | Silicon Hill Storage | SS Completed, FIS Completed, IA | KCE TX 12, LLC | 7336 L_GILLCR8_1Y 138kV | Travis | SOUTH | 2022-07-13 | OTH | BA | 104.62 |  | 2019-10-29 | 2019-10-15 | 2020-01-07 | 2019-10-22 | 2020-10-30 |  | 2020-03-27 | Yes | Not Required | Not Required | Not Required | 2020-04-03 | 2020-07-10 | 2020-10-30 |  |  | 2022-05-16 | 2022-06-02
20INR0293 | River Valley Storage 2 | SS Completed, FIS Completed, IA | KCE TX 21, LLC | 3650 Elgin SS 138kV | Williamson | SOUTH | 2022-11-01 | OTH | BA | 51.5 |  | 2019-10-25 | 2019-10-15 | 2020-01-07 | 2019-10-21 | 2022-04-27 | No | 2021-08-25 | Yes | Not Required | Not Required | Not Required | 2021-11-01 | 2021-11-01 | 2022-04-28
20INR0296 | Sand Bluff Wind Repower | SS Completed, FIS Completed, IA | RWE Renewables Development, LLC | 1333 McDonald 138kV | Glasscock | WEST | 2022-12-15 | WIN | WT | 89.5 |  | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-19 | 2022-04-18 | No | 2006-11-11 | No | Not Required | Not Required | Not Required | 2022-05-02 | 2022-05-02 | 2022-05-02
21INR0006 | Giddings Wind | SS Completed, FIS Started, No IA | Pioneer Natural Resources | 71212 Upton 138kV | Upton | WEST | 2024-10-23 | WIN | WT | 240 |  | 2019-04-02 | 2017-09-06 | 2019-08-19 | 2020-01-15 |  |  |  | No | Not Required | Not Required | Not Required
21INR0008 | Cunningham Solar 1 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 |  |  | 2018-04-12 | 2018-06-12 | 2018-10-23 |  | No |  | No | Not Required | Not Required | Not Required
21INR0012 | Air Products GCA | SS Completed, FIS Completed, IA | Air Products | 39140 TNTxCityMain 69kV (Will be upgraded to 138kV) | Galveston | HOUSTON | 2023-03-31 | GAS | ST | 14 |  | 2019-03-26 | 2018-06-07 | 2018-08-01 |  | 2020-05-14 |  | 2020-08-07 | Yes | Not Required | Not Required | 2020-03-31 | 2020-08-21
21INR0019 | Zier Solar | SS Completed, FIS Started, IA | Cypress Creek Renewables | 78255 Pinto Creek 138kV | Kinney | SOUTH | 2023-08-01 | SOL | PV | 162.99 |  |  | 2018-05-24 | 2018-07-20 | 2018-05-24 |  | No | 2020-10-22 | No | Not Required | Not Required | Not Required
21INR0021 | Green Holly Solar | SS Completed, FIS Completed, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2024-12-31 | SOL | PV | 413.6 |  |  | 2018-07-11 | 2018-08-16 | 2018-07-11 | 2020-05-06 | No | 2020-05-19 | No | Not Required | Not Required | Not Required
21INR0022 | Red Holly Solar | SS Completed, FIS Completed, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2024-05-31 | SOL | PV | 260 |  |  | 2018-07-11 | 2018-08-16 | 2018-07-11 | 2020-04-02 | No | 2020-10-19 | No | Not Required | Not Required | Not Required
21INR0024 | Cunningham Solar 2 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 |  | 2018-10-23 | 2018-08-29 | 2018-06-12 | 2018-10-23 |  | No |  | No | Not Required | Not Required | Not Required
21INR0027 | Zier Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 78255 Pinto Creek 138kV | Kinney | SOUTH | 2023-08-01 | OTH | BA | 40.41 |  |  | 2018-05-24 | 2018-07-20 | 2018-05-24 |  | No |  | No | Not Required | Not Required | Not Required
21INR0029 | Green Holly Storage | SS Completed, FIS Completed, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2024-05-31 | OTH | BA | 50 |  |  | 2018-07-11 | 2018-08-16 | 2018-07-11 | 2020-05-06 | No | 2020-10-19 | No | Not Required | Not Required | Not Required
21INR0031 | Indigo Solar | SS Completed, FIS Completed, IA | Innovative Solar, LLC | tap 345kV 68001 Clayton 345kV - 68000 WShack | Fisher | WEST | 2023-10-26 | SOL | PV | 125 |  | 2019-05-16 | 2018-09-27 | 2018-11-20 | 2019-05-15 | 2020-03-28 | No | 2020-10-15 | No | Not Required | Not Required | Not Required
21INR0033 | Red Holly Storage | SS Completed, FIS Completed, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2024-05-31 | OTH | BA | 50 |  |  | 2018-09-27 | 2018-12-18 | 2018-12-11 | 2020-04-02 | No | 2020-10-19 | No | Not Required | Not Required | Not Required
21INR0201 | Brandon | SS Completed, FIS Completed, IA | City of Lubbock, by and through Lubbock Power and Light (RE) | Brandon 12.47 kV | Lubbock | PANHANDLE | 2021-11-15 | GAS | GT | 21 |  | 2019-05-23 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2020-10-23 | No | 2020-10-30 | Yes | 2007-01-01 | Not Required | 2020-08-09 | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2021-07-02 | 2021-07-19
21INR0202 | R Massengale | SS Completed, FIS Completed, IA | City of Lubbock, by and through Lubbock Power and Light | Mackenzie 115 kV | Lubbock | PANHANDLE | 2021-11-15 | GAS | CC | 58 |  | 2020-08-10 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2020-10-23 | No | 2020-10-30 | Yes | 2000-01-03 | Not Required | 2020-08-09 | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2021-07-23 | 2021-07-26
21INR0203 | Eastbell Milam Solar | SS Completed, FIS Started, No IA | EDP RENEWABLES NORTH AMERICA LLC | 345 kV Bell County East Switch (bus# 3687) - TNP One (bus# 39950) circuit 2 | Milam | SOUTH | 2023-10-31 | SOL | PV | 240 |  | 2019-04-23 | 2018-10-10 | 2018-12-09 | 2019-04-23 |  | No |  | No |  |  | Not Required
21INR0205 | Radian Solar | SS Completed, FIS Completed, IA | IP Radian, LLC | 1444 Brown 345kV | Brown | NORTH | 2023-01-19 | SOL | PV | 327.42 |  |  | 2018-09-27 | 2018-11-08 | 2018-11-07 | 2021-08-16 | No | 2021-01-08 | Yes | Not Required | Not Required | Not Required | 2021-02-02 | 2021-10-27 | 2021-10-27 |  |  | 2022-06-20
21INR0207 | Quantum Solar | SS Completed, FIS Started, No IA | IP Quantum, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2023-05-31 | SOL | PV | 374.4 |  | 2018-11-07 | 2018-09-27 | 2018-11-14 | 2018-11-07 |  | No |  | No |  |  | Not Required
21INR0209 | Adamstown Storage | SS Completed, FIS Started, No IA | Adams Creek Solar Project, LLC | tap 345kV 1730 West Krum - 6101 Riley | Wichita | WEST | 2025-05-31 | OTH | BA | 116.9 |  | 2019-05-22 | 2018-11-20 | 2019-02-04 | 2019-05-16 |  | No |  | No |  |  | Not Required
21INR0210 | Adamstown Solar | SS Completed, FIS Completed, No IA | Adams Creek Solar Project, LLC | tap 345kV 1730 West Krum - 6101 Riley | Wichita | WEST | 2025-05-31 | SOL | PV | 254.15 |  | 2019-05-22 | 2018-11-20 | 2019-02-04 | 2019-05-16 | 2022-01-11 | No |  | No |  |  | Not Required
21INR0213 | Vancourt Solar | SS Completed, FIS Completed, IA | Rayos Del Sol Solar Project, LLC | 8656 Luna 138kV | Cameron | COASTAL | 2022-10-13 | SOL | PV | 45.73 | COD | 2018-11-07 | 2018-11-07 | 2018-12-12 | 2018-11-07 | 2020-10-16 | No | 2020-06-11 | Yes | Not Required | Not Required | Not Required | 2020-06-29 | 2021-01-29 | 2021-01-29
21INR0220 | Maleza Solar | SS Completed, FIS Not Started, IA | Brush Solar LLC | tap 345kV 44200 Hillje - 44040 Bailey | Wharton | SOUTH | 2023-06-01 | SOL | PV | 254.94 |  | 2019-03-07 | 2018-12-06 | 2019-01-18 |  |  | No | 2021-01-27 | No |  |  | Not Required
21INR0221 | Samson Solar 1 | SS Completed, FIS Completed, IA | Samson Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2022-07-20 | SOL | PV | 250 | COD | 2019-05-13 | 2018-11-20 | 2019-01-04 | 2019-05-03 | 2020-06-09 | No | 2020-08-26 | Yes | Not Required | Not Required | Not Required | 2020-08-26 | 2020-10-15 | 2020-10-26 |  |  | 2021-06-30 | 2021-08-31
21INR0223 | Tulsita Solar | SS Completed, FIS Started, No IA | Tulsita Solar LLC | Tap 138kV 8590 Tuleta - 8595 Euler | Goliad | SOUTH | 2023-06-01 | SOL | PV | 260.99 |  | 2019-05-20 | 2018-12-05 | 2019-02-21 | 2019-05-17 |  | No |  | No | Not Required | Not Required | Not Required
21INR0226 | Equinox Solar 1 | SS Completed, FIS Started, IA | Invenergy Solar Project Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2025-12-01 | SOL | PV | 200 |  | 2019-08-14 | 2018-12-11 | 2019-01-23 | 2019-07-30 |  | No | 2021-01-28 | No | Not Required | Not Required | Not Required
21INR0227 | Equinox Solar 2 | SS Completed, FIS Started, No IA | Invenergy Solar Project Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2025-12-01 | SOL | PV | 200 |  | 2019-08-05 | 2018-12-11 | 2019-01-31 | 2019-07-30 |  | No |  | No | Not Required | Not Required | Not Required
21INR0228 | Cottonwood Bayou Solar II | SS Completed, FIS Started, IA | Cottonwood Bayou Solar, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2024-03-31 | SOL | PV | 200 |  | 2019-06-19 | 2018-12-06 | 2019-02-07 | 2019-06-14 |  | No | 2021-03-25 | No | Not Required | Not Required | Not Required
21INR0233 | Taygete II Solar | SS Completed, FIS Completed, IA | West Texas Solar Project II LLC | 60393 Pig Creek 138kV | Pecos | WEST | 2022-11-21 | SOL | PV | 203.8 | COD | 2018-12-06 | 2018-12-17 | 2019-01-15 | 2018-12-13 | 2020-07-24 | No | 2019-03-27 | Yes | Not Required | Not Required | Not Required | 2019-05-06 | 2020-07-29 | 2020-07-30 |  |  | 2021-04-28
21INR0237 | Voyager Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2024-12-01 | SOL | PV | 303.9 |  | 2019-04-30 | 2019-01-04 | 2019-03-19 | 2019-04-26 |  |  |  | No | Not Required | Not Required | Not Required
21INR0240 | La Casa Wind | SS Completed, FIS Completed, No IA | Nextera Energy Resources LLC | New switching station: 138kV Graham Plant Switch - Breckenridge - Leon Switch | Stephens | NORTH | 2023-12-31 | WIN | WT | 148.78 | MW Size COD |  | 2018-12-28 | 2019-03-12 | 2018-12-29 | 2021-07-08 |  |  | No | Not Required | Not Required | Not Required
21INR0244 | Madero Grid | SS Completed, FIS Completed, IA | Madero Grid, LLC | 8824 Railroad 138kV | Hidalgo | SOUTH | 2022-07-08 | OTH | BA | 101.52 | COD | 2018-12-19 | 2018-12-20 | 2019-03-12 | 2018-12-19 | 2020-10-29 | No | 2019-12-06 | Yes | Not Required | Not Required | Not Required | 2020-01-13 | 2020-10-29 | 2020-10-30 |  |  | 2022-05-06 | 2022-05-26
21INR0247 | Anson Solar Center, Phase III | SS Completed, FIS Started, No IA | Anson Solar Center 3, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2024-06-03 | SOL | PV | 200 |  | 2018-02-15 | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  |  | No |  |  | Not Required
21INR0253 | Ulysses Solar | SS Completed, FIS Started, No IA | BNB Tennyson Solar LLC | tap 345kV 6444 Red Creek - 60040 Bluff Creek | Coke | WEST | 2023-06-30 | SOL | PV | 150 |  | 2019-05-14 | 2019-01-25 | 2019-04-05 | 2019-05-10 |  |  |  | No | Not Required | Not Required | Not Required
21INR0254 | Blue Cut Solar | SS Completed, FIS Started, No IA | Blue Cut Solar, LLC | tap 138kV 7064 Lampasas - 260 Kempner | Lampasas | NORTH | 2023-08-17 | SOL | PV | 150 | COD | 2019-10-10 | 2019-01-30 | 2019-04-12 | 2019-10-08 |  |  |  | No | Not Required | Not Required | Not Required
21INR0256 | Amsterdam Solar | SS Completed, FIS Completed, IA | Cottonwood Bayou Solar II, LLC | tap 345kV 43035 Oasis - 42500 Dow c27 | Brazoria | COASTAL | 2023-05-19 | SOL | PV | 509.88 |  | 2019-10-18 | 2019-02-07 | 2019-04-29 | 2019-07-31 | 2022-03-22 |  | 2022-02-17 | No | Not Required | Not Required | Not Required
21INR0257 | Mercury Solar | SS Completed, FIS Completed, IA | Mercury Solar, LLC | 68090 Sam Sw 345kV | Hill | NORTH | 2022-12-31 | SOL | PV | 206.11 |  | 2019-02-07 | 2019-02-14 | 2019-05-03 | 2019-02-07 | 2021-10-14 |  | 2021-10-18 | Yes | Not Required | Not Required | Not Required | 2022-03-21 | 2022-04-29 | 2022-04-29
21INR0258 | Mercury Storage | SS Completed, FIS Started, No IA | Mercury Storage, LLC | 68090 Sam Sw 345kV | Hill | NORTH | 2023-12-01 | OTH | BA | 205.9 |  | 2019-02-07 | 2019-02-14 | 2019-05-03 | 2019-02-07 |  |  |  | No | Not Required | Not Required | Not Required
21INR0260 | Chariot Storage | SS Completed, FIS Started, No IA | Chariot Storage LLC | tap 69kV 99 Ben Hur - 107 Prairie Hill | Limestone | NORTH | 2023-04-15 | OTH | BA | 50.6 |  | 2019-02-19 | 2019-03-06 | 2019-05-24 | 2019-02-11 |  | No |  | No | Not Required | Not Required | Not Required
21INR0261 | Horizon Solar | SS Completed, FIS Started, IA | Horizon Solar, LLC | 5897 Horizon Switch 138kV | Frio | SOUTH | 2023-12-15 | SOL | PV | 203.5 |  | 2019-03-05 | 2019-03-05 | 2019-05-20 | 2019-03-01 |  | No | 2019-07-12 | Yes | Not Required | Not Required | Not Required | 2019-08-09 | 2019-12-09
21INR0262 | Grandfalls Storage | SS Completed, FIS Started, No IA | King Mountain Storage LLC | tap 345kV 11028 Odessa - 76000 North McCamey | Upton | WEST | 2022-12-01 | OTH | BA | 205.9 |  | 2019-02-14 | 2019-03-25 | 2019-06-17 | 2019-02-14 |  |  |  | No |  |  | Not Required
21INR0263 | Monarch Creek Wind | SS Completed, FIS Started, IA | EDF Renewables Development, Inc. | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek Switch (North Circuit) | Throckmorton | WEST | 2023-12-01 | WIN | WT | 209 |  | 2019-10-28 | 2019-04-25 | 2019-07-19 | 2019-08-05 |  | No | 2020-08-24 | No | Not Required | Not Required | Not Required
21INR0264 | Monarch Creek Wind (B) | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek Switch (North Circuit) | Haskell | WEST | 2023-12-01 | WIN | WT | 451.5 |  | 2019-11-20 | 2019-04-25 | 2019-07-19 | 2019-11-15 |  |  |  | No |  |  | Not Required
21INR0265 | Sisters Solar | SS Completed, FIS Started, No IA | Oberon Solar LLC | 345kV line 11010 Wolf Sw-1018 Moss Sw | Ector | WEST | 2023-09-15 | SOL | PV | 303.09 |  | 2019-02-28 | 2019-02-28 | 2019-03-29 | 2019-02-20 |  | Yes |  | No | Not Required | Not Required | Not Required
21INR0268 | Greyhound Solar | SS Completed, FIS Completed, IA | Rockhound Solar 2, LLC dba "Greyhound Solar" | tap 345kV 11010 Wolf - 1018 Moss | Ector | WEST | 2023-12-30 | SOL | PV | 608.7 |  | 2019-03-14 | 2019-03-28 | 2019-06-05 | 2019-03-21 | 2021-12-17 | No | 2022-01-15 | No | Not Required | Not Required | Not Required
21INR0271 | TERRANOVA SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY&INFRASTRUCTURE LLC | 345kV Avogadro Station | Knox | WEST | 2024-03-01 | SOL | PV | 152.32 |  | 2019-12-05 | 2019-04-01 | 2019-06-10 | 2019-12-12 |  |  |  | No |  |  | Not Required
21INR0274 | Carol Solar | SS Completed, FIS Started, IA | Goat Mountain Renewables, LLC | 23906 AJ Swope 345kV | Potter | PANHANDLE | 2024-12-31 | SOL | PV | 223.2 |  | 2019-06-11 | 2019-03-26 | 2019-06-11 | 2019-06-07 |  | No | 2020-09-11 | No | Not Required | Not Required | Not Required
21INR0278 | Fighting Jays Solar | SS Completed, FIS Completed, IA | AP Solar Holdings, LLC | tap 345kV 44000 WA Parish - 44200 Hillje c64 | Fort Bend | HOUSTON | 2022-11-21 | SOL | PV | 351.29 |  | 2019-04-30 | 2019-03-26 | 2019-06-17 | 2019-03-20 | 2021-06-30 | No | 2020-06-22 | Yes | Not Required | Not Required | Not Required | 2021-07-29 | 2021-07-29 | 2021-07-29 |  |  | 2022-03-18 | 2022-03-31
21INR0280 | Edgewater Storage | SS Completed, FIS Completed, No IA | Edgewater Battery Storage LLC | 210 Reagor Springs 69kV | Ellis | NORTH | 2023-04-15 | OTH | BA | 50.6 |  | 2019-04-02 | 2019-04-08 | 2019-07-04 | 2019-03-24 | 2021-05-28 | No |  | No | Not Required | Not Required | Not Required
21INR0281 | Byrd Ranch Energy Storage Plant | SS Completed, FIS Completed, IA | Byrd Ranch Storage LLC | 39700 TNSweeny 138kV | Brazoria | COASTAL | 2022-08-30 | OTH | BA | 50.6 | COD | 2019-04-02 | 2019-04-08 | 2019-07-04 | 2019-03-24 | 2020-06-17 | No | 2020-12-14 | Yes | Not Required | Not Required | Not Required | 2021-10-27 | 2021-10-29 | 2021-10-29
21INR0285 | LARISA SOLAR | SS Completed, FIS Completed, No IA | ABEI ENERGY & INFRASTRUCTURE LLC | Mulberry Creek – Perigee 345 kV line | Jones | WEST | 2024-12-19 | SOL | PV | 408.34 | COD | 2020-01-13 | 2019-04-24 | 2019-07-01 | 2019-12-23 | 2022-06-21 |  |  | No |  |  | Not Required
21INR0294 | Mountaineer Solar | SS Completed, FIS Completed, No IA | BN Wind Project LLC | 1444 Brown 345 kV | Brown | NORTH | 2023-09-29 | SOL | PV | 332 |  | 2019-12-11 | 2019-04-16 | 2019-06-11 | 2019-12-08 | 2021-03-22 | No |  | No | Not Required | Not Required | Not Required
21INR0295 | Sterling Prairie Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 8608 Pavlov A 138kV | Matagorda | COASTAL | 2023-12-15 | SOL | PV | 119.91 |  | 2020-01-22 | 2019-04-24 | 2019-07-23 | 2020-01-21 |  | No |  | No |  |  | Not Required
21INR0302 | Aureola Solar | SS Completed, FIS Completed, No IA | Ben Milam Solar 1 | tap 345kV 3687 Bell E - 39950 TNTNP One, one-third from Bell | Milam | SOUTH | 2024-01-02 | SOL | PV | 203 |  | 2020-07-15 | 2019-12-19 | 2020-03-12 | 2020-07-06 | 2021-08-05 |  |  | No |  |  | Not Required
21INR0303 | Mandorla Solar | SS Completed, FIS Completed, No IA | Ben Milam Solar 2 | tap 345kV 3687 Bell E - 39950 TNTNP One, one-half from Bell | Milam | SOUTH | 2024-01-02 | SOL | PV | 254 |  | 2020-07-15 | 2020-01-22 | 2020-04-13 | 2020-07-06 | 2021-08-05 |  |  | No |  |  | Not Required
21INR0304 | Halo Solar | SS Completed, FIS Completed, No IA | Ben Milam Solar 3 | tap 345kV 3687 Bell E - 39950 TNTNP One, one-fourth from Bell | Bell | NORTH | 2023-11-11 | SOL | PV | 254 |  | 2020-08-10 | 2020-01-22 | 2020-04-13 | 2020-07-06 | 2021-08-05 |  |  | No |  |  | Not Required
21INR0314 | AQUAMARINE SOLAR | SS Completed, FIS Started, No IA | BdPU Texas Solar Project II, LLC | tap 138kV 720 Salt Creek Reactor – 6150 Spur | Dickens | PANHANDLE | 2023-12-01 | SOL | PV | 151.69 |  | 2020-02-13 | 2019-05-10 | 2019-07-31 | 2020-01-27 |  |  |  | No | Not Required | Not Required | Not Required
21INR0320 | Ion Solar | SS Completed, FIS Started, No IA | GSE Group LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2023-05-31 | SOL | PV | 384 |  | 2020-02-03 | 2019-05-17 | 2019-08-01 | 2020-01-28 |  |  |  | No |  |  | Not Required
21INR0323 | Spanish Crown | SS Completed, FIS Completed, IA | BPL Crown Solar | Tap 138kV 3420 Temple Pecan Creek - 3410 Lake Creek (138 kV Cow Bayou Switch, a new switching station) | Falls | NORTH | 2023-02-10 | SOL | PV | 103.1 |  | 2019-05-10 | 2019-05-13 | 2019-07-31 | 2019-05-10 | 2021-07-07 | No | 2021-01-13 | Yes | Not Required | Not Required | Not Required | 2021-01-28 | 2021-05-17 | 2022-04-29
21INR0324 | Board Creek Wind | SS Completed, FIS Completed, IA | Limestone Wind Project, LLC | 345kV 3386 Outlaw Switch | Navarro | NORTH | 2022-11-04 | WIN | WT | 299.2 |  | 2019-11-08 | 2019-04-24 | 2019-07-22 | 2019-11-05 | 2022-04-26 | No | 2021-08-19 | Yes | Not Required | Not Required | Not Required | 2022-04-05 | 2022-04-21 | 2022-04-26
21INR0325 | Sheep Creek Wind | SS Completed, FIS Started, IA | Century Oak Wind Project, LLC | 68051 Reata 345kV | Callahan | WEST | 2023-06-01 | WIN | WT | 151.5 |  | 2020-02-05 | 2019-05-30 | 2019-08-15 | 2020-01-29 |  | No | 2021-10-01 | No |  |  | Not Required
21INR0326 | Dove Run Solar | SS Completed, FIS Started, No IA | Dove Run Solar Project, LLC | tap 138kV 8510 Falfurrias - 8695 Crestonio | Duval | SOUTH | 2024-10-31 | SOL | PV | 121.5 |  | 2019-05-07 | 2019-05-07 | 2019-07-23 | 2019-05-02 |  |  |  | No |  |  | Not Required
21INR0334 | NIGHTFALL SOLAR | SS Completed, FIS Completed, No IA | ABEI ENERGY & INFRASTRUCTURE LLC | Tap 138kV 8241 Razorback - 8234 Uvalde | Uvalde | SOUTH | 2023-06-23 | SOL | PV | 152.1 |  | 2020-09-24 | 2019-05-10 | 2019-07-31 | 2020-01-24 | 2021-08-10 |  |  | No |  |  | Not Required
21INR0341 | Space City Solar | SS Completed, FIS Completed, IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2024-05-30 | SOL | PV | 609.74 | COD | 2019-10-28 | 2019-11-01 | 2020-03-06 | 2019-10-15 | 2021-01-04 |  | 2021-01-06 | Yes | Not Required | Not Required | Not Required | 2021-01-11
21INR0343 | Flag City Solar | SS Completed, FIS Started, No IA | Flag City Solar Project, LLC | tap 138kV 5588 Red Bluff - 5546 Danevang c1 | Jackson | SOUTH | 2024-05-31 | SOL | PV | 167.3 |  | 2019-05-07 | 2019-05-07 | 2019-07-29 | 2019-05-02 |  |  |  | No | Not Required | Not Required | Not Required
21INR0344 | Lunis Creek Solar SLF | SS Completed, FIS Started, IA | Lunis Creek Solar Project, LLC | tap 345 kV Static (#8676) - South Texas Project (#5915) | Jackson | SOUTH | 2024-06-01 | SOL | PV | 617.12 |  | 2019-05-02 | 2019-05-02 | 2019-07-03 | 2019-05-02 |  |  | 2021-10-29 | No |  |  | Not Required
21INR0347 | Lunis Creek Storage SLF | SS Completed, FIS Started, No IA | Lunis Creek Solar Project, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2024-06-01 | OTH | BA | 0 |  | 2019-05-02 | 2019-05-02 | 2019-07-30 | 2019-05-02 |  |  |  | No |  |  | Not Required
21INR0349 | Pearl Crescent Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 7640 Rock Island 138kV | Colorado | SOUTH | 2025-12-08 | SOL | PV | 208.35 |  | 2019-06-04 | 2019-05-31 | 2019-08-26 | 2019-09-30 |  |  |  | No |  |  | Not Required
21INR0351 | 7V Solar | SS Completed, FIS Completed, IA | 7V Solar Ranch, LLC | tap 138kV 7248 Flatonia - 7274 Plum | Fayette | SOUTH | 2023-09-30 | SOL | PV | 246.3 |  | 2019-10-16 | 2019-04-16 | 2019-07-03 | 2019-08-16 | 2021-02-24 |  | 2020-09-01 | Yes | Not Required | Not Required | Not Required
21INR0353 | Big Elm Solar | SS Completed, FIS Completed, No IA | Big Elm Solar, LLC | tap 345kV 3414 Temple - 3409 Lake Creek | Bell | NORTH | 2023-10-31 | SOL | PV | 221.76 |  | 2020-03-25 | 2019-06-27 | 2019-09-23 | 2020-03-23 | 2022-03-08 | No |  | No |  |  | Not Required
21INR0354 | Kochab Solar | SS Completed, FIS Started, No IA | Kochab Energy Project LLC | 8241 Razorback 138kV | Uvalde | SOUTH | 2023-07-01 | SOL | PV | 204 |  | 2019-05-14 | 2019-05-14 | 2019-08-10 | 2019-05-13 |  |  |  | No |  |  | Not Required
21INR0355 | Wilmeth Solar | SS Completed, FIS Completed, No IA | Wilmeth Solar, LLC | tap 138kV 8212 Dilley - 8613 Big Well | Frio | SOUTH | 2023-10-31 | SOL | PV | 160 |  | 2020-03-05 | 2019-06-17 | 2019-08-08 | 2020-02-05 | 2021-12-01 |  |  | No |  |  | Not Required
21INR0356 | Welder Solar | SS Completed, FIS Started, No IA | Welder Solar, LLC | tap 345kV 8624 Grissom - 8455 Lon Hill | Bee | SOUTH | 2023-10-31 | SOL | PV | 300 |  | 2020-07-08 | 2019-06-18 | 2019-09-13 | 2020-03-16 |  |  |  | No | Not Required | Not Required | Not Required
21INR0357 | SP TX-12B BESS | SS Completed, FIS Completed, IA | VESI Upton County BESS, LLC | 132943 SPTX12B 138kV | Upton | WEST | 2022-08-19 | OTH | BA | 25.12 |  | 2019-05-31 | 2019-06-17 | 2019-09-09 | 2019-06-12 | 2021-01-31 | No | 2020-05-01 | Yes | Not Required | Not Required | Not Required | 2021-01-31 | 2021-02-01 | 2021-02-01
21INR0359 | Hickerson Solar | SS Completed, FIS Started, No IA | Hickerson Solar | tap 345kV 68091 Navarro - 68040 Kopperl | Bosque | NORTH | 2022-12-31 | SOL | PV | 310.4 |  | 2020-05-13 | 2019-05-29 | 2019-08-23 | 2020-02-19 |  |  |  | No |  |  | Not Required
21INR0362 | Oystercatcher Solar | SS Completed, FIS Completed, IA | Oystercatcher Solar, LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2024-08-20 | SOL | PV | 220.33 |  | 2020-01-15 | 2019-05-30 | 2019-08-07 | 2019-12-20 | 2021-07-07 | Yes | 2021-08-20 | No | Not Required | Not Required | Not Required
21INR0368 | Eliza Solar | SS Completed, FIS Completed, No IA | Ables Springs Solar, LLC | tap 345kV 2478 Royse - 3103 Shamburger | Kaufman | NORTH | 2024-02-15 | SOL | PV | 151.28 |  | 2020-05-04 | 2019-06-21 | 2019-08-30 | 2020-02-24 | 2022-04-18 | No |  | No |  |  | Not Required
21INR0371 | HIP Solar Project | SS Completed, FIS Started, No IA | ConnectGen Operating LLC | tap 345kV 967 Gibbons Creek - 46020 Limestone ckt 18 | Leon | NORTH | 2023-07-31 | SOL | PV | 135 |  | 2019-08-27 | 2019-08-16 | 2019-11-05 | 2019-08-22 |  |  |  | No |  |  | Not Required
21INR0375 | Grizzly Ridge Solar | SS Completed, FIS Completed, IA | Grizzly Ridge Solar LLC | 69kV 178 Pottsville | Hamilton | NORTH | 2022-11-21 | SOL | PV | 101.68 | COD | 2019-07-08 | 2019-07-08 | 2019-10-01 | 2019-07-08 | 2022-02-01 | No | 2021-06-09 | Yes | Not Required | Not Required | Not Required | 2021-06-09 | 2022-01-03 | 2022-02-01
21INR0376 | Barranca Wind III | SS Completed, FIS Started, No IA | Barranca Wind Energy, LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2024-12-31 | WIN | WT | 205 |  | 2019-07-12 | 2019-06-26 | 2019-09-23 | 2019-07-11 |  |  |  | No |  |  | Not Required
21INR0379 | Ash Creek Solar | SS Completed, FIS Started, No IA | Ash Creek Solar LLC | 68090 SAM SW 345kV | Hill | NORTH | 2023-12-31 | SOL | PV | 408.85 |  | 2020-10-27 | 2019-07-29 | 2019-10-25 | 2019-07-19 |  | No |  | No |  |  | Not Required
21INR0380 | Charolais Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 44000 W A Parish - 5915 STP | Matagorda | COASTAL | 2023-12-15 | SOL | PV | 261.63 |  | 2020-05-11 | 2019-08-05 | 2019-10-31 | 2020-04-27 |  | Yes |  | No |  |  | Not Required
21INR0384 | Ratliff (Concho Valley) Solar | SS Completed, FIS Completed, IA | MERIT SI, LLC | The crossing of SAPS to Live Oak and SAPS to Yellowjacket 138 kV lines. | Tom Green | WEST | 2022-08-29 | SOL | PV | 159.8 | Proj Name COD | 2019-10-17 | 2019-07-08 | 2019-12-18 | 2019-06-27 | 2021-01-27 | No | 2020-09-28 | Yes | Not Required | Not Required | Not Required | 2021-04-08 | 2021-04-08 | 2021-04-21 |  |  | 2022-06-09
21INR0387 | Anchor Wind | SS Completed, FIS Completed, IA | Ranchland Wind Project,LLC | 345 kV Aspire Station (68011) | Eastland | NORTH | 2022-08-03 | WIN | WT | 98.9 |  | 2019-06-26 | 2019-08-26 | 2019-11-12 | 2019-08-13 | 2021-04-30 | No | 2020-11-30 | Yes | Not Required | Not Required | Not Required | 2020-12-02 | 2021-04-30 | 2021-04-30 |  |  | 2021-11-29 | 2022-02-11
21INR0389 | Red Tailed Hawk Solar | SS Completed, FIS Completed, IA | Red Tailed Hawk Solar LLC | tap 345kV 44200 Bailey-44040 Hillje ckt 72 | Wharton | SOUTH | 2024-03-31 | SOL | PV | 353.41 | MW Size | 2019-07-01 | 2019-07-08 | 2019-10-02 | 2019-07-01 | 2020-03-13 | No | 2020-08-28 | Yes | Not Required | Not Required | Not Required
21INR0391 | Grandslam Solar | SS Completed, FIS Started, IA | Grandslam Solar | 5700 Miracle Lake 138kV | Atascosa | SOUTH | 2023-12-31 | SOL | PV | 121.89 | COD | 2019-09-03 | 2019-07-29 | 2019-10-30 | 2019-07-26 |  |  | 2021-01-29 | No | Not Required | Not Required | Not Required
21INR0393 | Talitha Solar | SS Completed, FIS Completed, IA | Talitha Energy Project, LLC | 5660 Orange Grove 138kV | Jim Wells | SOUTH | 2023-05-01 | SOL | PV | 131.03 |  | 2019-07-12 | 2019-07-12 | 2019-09-09 | 2019-07-08 | 2021-12-07 | No | 2022-06-08 | No |  |  | Not Required
21INR0395 | SunRay | SS Completed, FIS Completed, IA | OCI SunRay LLC | tap 138kV 8234 Uvalde - 8241 Razorback | Uvalde | SOUTH | 2023-08-01 | SOL | PV | 204.09 |  | 2019-09-13 | 2019-07-17 | 2019-10-14 | 2019-07-15 | 2021-09-07 | No | 2021-07-06 | Yes | Not Required | Not Required | Not Required
21INR0401 | Young Wind | SS Completed, FIS Completed, IA | Young Wind, LLC | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek | Young | WEST | 2022-12-31 | WIN | WT | 499.14 |  | 2020-04-13 | 2019-07-29 | 2019-10-25 | 2020-03-27 | 2021-05-28 | No | 2022-02-18 | Yes | Not Required | Not Required | Not Required | 2022-03-31 | 2022-04-22 | 2022-04-22
21INR0406 | Buffalo Creek | SS Completed, FIS Completed, IA | Lincoln Clean Energy Development | tap 345kV 44000 WA Parish – 44040 BAILEY | Fort Bend | HOUSTON | 2022-02-28 | SOL | PV | 438.75 |  | 2019-08-06 | 2019-08-01 | 2019-10-30 | 2019-07-31 | 2021-04-23 | No | 2020-04-16 | Yes | Not Required | Not Required | Not Required | 2020-05-06 | 2021-04-15 | 2021-04-23 |  |  | 2021-12-08 | 2022-01-06
21INR0413 | Big Star Solar | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | Tap 345kV 9074 Lytton - 9073 Holman | Bastrop | SOUTH | 2022-12-01 | SOL | PV | 203.1 |  | 2020-01-02 | 2019-08-27 | 2019-11-08 | 2019-12-20 | 2021-07-19 |  | 2020-10-02 | Yes |  |  | Not Required | 2020-12-04 | 2021-07-19 | 2021-07-30
21INR0414 | Jayhawk Solar | SS Completed, FIS Started, No IA | Renewable Energy Ventures, LLC | tap 345kV 1030 Morgan - 76030 Gasconades | Mitchell | WEST | 2023-06-30 | SOL | PV | 101.5 |  | 2020-06-22 | 2019-08-05 | 2019-10-31 | 2020-01-17 |  |  |  | No |  |  | Not Required
21INR0421 | Armadillo Solar | SS Completed, FIS Started, IA | Lincoln Clean Energy Development | 3478 Navarro 138kV | Navarro | NORTH | 2023-09-28 | SOL | PV | 204 |  | 2019-09-05 | 2019-08-28 | 2019-11-22 | 2019-08-28 |  | No | 2021-02-02 | Yes | Not Required | Not Required | Not Required
21INR0424 | Tierra Bonita Solar | SS Completed, FIS Started, No IA | Greasewood II, LLC | 844 Nevilesw 345kV | Pecos | WEST | 2023-05-23 | SOL | PV | 309.68 |  | 2020-09-18 | 2019-10-15 | 2020-01-02 | 2020-06-26 |  |  |  | No | Not Required | Not Required | Not Required
21INR0428 | Nabatoto Solar North | SS Completed, FIS Started, IA | ConnectGEN West LLC | tap 345kV 967 Gibbons Creek - 46020 Limestone ckt 50 | Leon | NORTH | 2025-02-01 | SOL | PV | 365.7 |  | 2019-08-16 | 2019-09-23 | 2019-12-10 | 2019-09-11 |  |  | 2021-02-26 | No |  |  | Not Required
21INR0430 | Holstein 2 Energy Storage | SS Completed, FIS Started, No IA | 229HD 8me LLC | 11406 Central Bluff 345kV | Nolan | WEST | 2024-04-26 | OTH | BA | 102.5 |  | 2019-09-16 | 2019-08-26 | 2019-11-12 | 2019-08-16 |  |  |  | No |  |  | Not Required
21INR0431 | Galloway 2 Solar | SS Completed, FIS Started, IA | 224WB 8me LLC | 7077 Amos Cr 345kV | Concho | WEST | 2023-10-01 | SOL | PV | 113.88 | COD | 2019-08-28 | 2019-08-28 | 2017-10-02 | 2019-08-28 |  |  | 2019-03-28 | Yes | Not Required | Not Required | Not Required | 2020-07-27 | 2021-03-23
21INR0432 | Diversion Wind | SS Completed, FIS Started, No IA | Diversion Wind Development LLC | 6101 Riley 345kV | Baylor | WEST | 2024-12-30 | WIN | WT | 300 |  | 2020-07-15 | 2019-09-10 | 2019-12-04 | 2020-06-04 |  |  |  | No |  |  | Not Required
21INR0434 | Golinda Solar | SS Completed, FIS Completed, IA | BPL Sol Solar | Tap 138kV 3420 Temple Pecan Creek - 3410 Lake Creek | Falls | NORTH | 2023-02-10 | SOL | PV | 103.1 |  | 2019-08-26 | 2019-09-23 | 2019-12-10 | 2019-09-03 | 2021-07-07 | No | 2021-03-21 | Yes | Not Required | Not Required | Not Required | 2021-01-28 | 2021-08-05 | 2022-04-29
21INR0440 | Wren Solar | SS Completed, FIS Started, No IA | Wren Solar, LLC | 8601 Cebolla 345kV | Willacy | COASTAL | 2023-12-29 | SOL | PV | 170 |  | 2020-10-27 | 2019-10-15 | 2020-01-02 | 2020-07-28 |  |  |  | No | Not Required | Not Required | Not Required
21INR0442 | Myrtle Storage | SS Completed, FIS Completed, No IA | Myrtle Storage, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2023-04-15 | OTH | BA | 150.83 |  | 2020-08-03 | 2019-11-04 | 2020-02-07 | 2020-07-30 | 2021-10-11 |  |  | No |  |  | Not Required
21INR0443 | Cottonwood Bayou Storage | SS Completed, FIS Completed, IA | Cottonwood Bayou Storage, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2024-03-31 | OTH | BA | 150.83 |  | 2020-07-20 | 2019-10-31 | 2020-01-23 | 2020-07-17 | 2021-07-21 | No | 2022-03-18 | No |  |  | Not Required
21INR0444 | Long Point Storage | SS Completed, FIS Started, No IA | Long Point Storage, LLC | tap 138kV 44010 WAP - 42980 Nash. | Brazoria | COASTAL | 2023-05-19 | OTH | BA | 100.62 |  | 2020-09-17 | 2019-11-01 | 2020-02-05 | 2020-09-01 |  |  |  | No | Not Required | Not Required | Not Required
21INR0446 | Knickerbocker Storage SLF | SS Completed, FIS Started, No IA | Knickerbocker Solar LLC | Tap 345kV 76003 Big Hill - 76009 Twin Buttes | Tom Green | WEST | 2025-01-15 | OTH | BA | 0 |  | 2020-01-10 | 2019-12-19 | 2020-03-06 | 2019-12-05 |  |  |  | No |  |  | Not Required
21INR0450 | Danish Fields Storage | SS Completed, FIS Completed, No IA | Danish Fields Storage, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2023-06-15 | OTH | BA | 150.83 |  | 2020-07-20 | 2019-10-31 | 2020-01-24 | 2020-07-17 | 2021-12-29 | No |  | No |  |  | Not Required
21INR0454 | Racetrack Solar | SS Completed, FIS Started, No IA | Innergex Renewables USA, LLC | tap 138kV 8234 Uvalde - 8236 West Batesville | Uvalde | SOUTH | 2024-05-01 | SOL | PV | 120 |  | 2020-09-08 | 2019-11-18 | 2020-01-28 | 2020-07-09 |  |  |  | No |  |  | Not Required
21INR0455 | Independence Trail Storage | SS Completed, FIS Started, No IA | KCE TX 16, LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2024-12-11 | OTH | BA | 100 | COD | 2019-11-11 | 2019-12-03 | 2020-02-24 | 2019-10-22 |  |  |  | No | Not Required | Not Required | Not Required
21INR0456 | Maleza Storage | SS Completed, FIS Started, No IA | Brush Storage, LLC | tap 345kV 44200 Hillje - 44040 Bailey | Wharton | SOUTH | 2023-08-17 | OTH | BA | 150.83 | COD | 2020-08-24 | 2019-10-31 | 2020-01-24 | 2020-08-18 |  |  |  | No |  |  | Not Required
21INR0458 | Porter Solar | SS Completed, FIS Completed, IA | Lantana Solar, LLC | tap 345kv 1429 Jacksboro - 1730 Krum West | Denton | NORTH | 2023-08-01 | SOL | PV | 245 |  | 2020-08-24 | 2020-01-30 | 2020-04-17 | 2020-08-06 | 2021-10-21 | No | 2022-02-03 | No |  |  | Not Required
21INR0459 | DeCordova BESS addition | SS Completed, FIS Completed, IA | Luminant Generation Company LLC | 1891 Decordova 138kV | Hood | NORTH | 2022-07-15 | OTH | BA | 263.08 | COD | 2019-11-11 | 2019-11-18 | 2020-01-31 | 2019-10-29 | 2021-05-20 |  | 2021-07-02 | Yes | Not Required | Not Required | Not Required | 2021-07-08 | 2021-07-08 | 2021-07-15 |  |  | 2021-12-15 | 2022-01-31
21INR0467 | Apogee Wind | SS Completed, FIS Completed, IA | EDF Renewables Development, Inc. | Tap 345kV 6235 Mulberry - 6076 Foxtail | Haskell | WEST | 2022-06-30 | WIN | WT | 393.24 |  | 2019-11-27 | 2019-12-03 | 2020-03-08 | 2019-11-18 | 2021-04-30 | No | 2022-05-13 | Yes | Not Required | Not Required | Not Required | 2020-03-27 | 2021-04-30 | 2021-04-30 |  |  | 2021-12-22 | 2022-01-11
21INR0469 | Big Star Storage | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | Tap 345kV 9074 Lytton - 9073 Holman | Bastrop | SOUTH | 2022-12-01 | OTH | BA | 80 |  | 2020-10-23 | 2020-01-02 | 2020-03-26 | 2020-08-28 | 2021-07-19 |  | 2020-10-02 | Yes |  |  | Not Required | 2021-08-18 | 2021-08-18 | 2021-07-30
21INR0470 | Pearl Crescent Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 7640 Rock Island 138kV | Colorado | SOUTH | 2025-12-08 | OTH | BA | 50.26 |  | 2020-09-18 | 2019-12-20 | 2020-03-12 | 2020-04-10 |  |  |  | No |  |  | Not Required
21INR0473 | Vortex BESS | SS Completed, FIS Completed, IA | AZURE SKY WIND STORAGE LLC | loop 345kV 60515 Clear Crossing - 1421 WillowCr 345kV | Throckmorton | WEST | 2021-12-23 | OTH | BA | 121.83 |  | 2019-11-27 | 2019-12-03 | 2020-03-08 | 2019-11-18 | 2021-04-30 | No | 2021-04-23 | Yes | Not Required | Not Required | Not Required | 2021-04-27 | 2021-04-30 | 2021-04-30 |  |  | 2021-12-16 | 2022-05-23
21INR0474 | Anchor BESS | SS Completed, FIS Completed, IA | Ranchland Wind Project,LLC | 345 kV Aspire Station (68011) | Eastland | NORTH | 2022-09-27 | OTH | BA | 71.45 |  | 2019-11-27 | 2019-12-03 | 2020-02-25 | 2019-11-18 | 2021-04-30 | No | 2021-03-15 | Yes | Not Required | Not Required | Not Required | 2021-04-16 | 2021-04-30 | 2021-04-30 |  |  | 2022-05-18
21INR0479 | Endurance Park Storage | SS Completed, FIS Completed, IA | KCE TX 13, LLC | 11306 Dermott 138kV | Scurry | WEST | 2022-09-07 | OTH | BA | 51.5 | COD | 2019-12-03 | 2019-11-27 | 2020-02-14 | 2019-11-22 | 2022-04-27 |  | 2021-02-13 | Yes | Not Required | Not Required | Not Required | 2021-08-23 | 2021-10-05 | 2022-04-28
21INR0480 | Juanita Hill Storage | SS Completed, FIS Started, No IA | KCE TX 20, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2023-05-20 | OTH | BA | 103.8 |  | 2019-12-03 | 2019-11-27 | 2020-02-12 | 2019-11-22 |  | No |  | No |  |  | Not Required
21INR0481 | Lunar Solar | SS Completed, FIS Completed, No IA | EDF Renewables Development, Inc. | tap 345kV 5133 Elm Creek - 5915 STP (CKT 1) | Wharton | SOUTH | 2024-12-01 | SOL | PV | 609.74 |  | 2020-03-30 | 2019-12-17 | 2020-03-11 | 2019-12-17 | 2021-12-22 | No |  | No | Not Required | Not Required | Not Required
21INR0482 | Sisters Storage | SS Completed, FIS Started, No IA | 174 Power Global Properties | loop station on double circuit 345kV line 1018 Moss Sw/1029 Odessa Ehv Sw - 11010 Wolf Sw | Ector | WEST | 2026-03-15 | OTH | BA | 208.89 |  | 2020-03-30 | 2019-12-18 | 2020-03-11 | 2019-12-18 |  |  |  | No |  |  | Not Required
21INR0483 | Morrow Lake Storage | SS Completed, FIS Started, No IA | Morrow Lake Storage, LLC | 5895 Pearsall 138kV | Frio | SOUTH | 2023-05-19 | OTH | BA | 201.13 |  | 2020-11-10 | 2020-02-07 | 2020-04-30 | 2020-10-26 |  |  |  | No |  |  | Not Required
21INR0484 | Mustang Creek Storage | SS Completed, FIS Completed, IA | Ganado Solar, LLC | tap 138kV 5523 ETP - 78104 Ricebird new sub Galow | Jackson | SOUTH | 2023-03-29 | OTH | BA | 70.5 |  | 2020-09-22 | 2020-01-02 | 2020-03-23 | 2020-09-11 | 2022-01-20 | No | 2022-02-21 | Yes |  |  | Not Required | 2022-02-21 | 2022-02-21 | 2022-04-06
21INR0486 | Pandora Solar | SS Completed, FIS Started, No IA | Pandora | Tap 345kV 5915 STP - 5133 Elm Creek, c1 | Wilson | SOUTH | 2023-12-01 | SOL | PV | 252 |  | 2020-11-09 | 2020-01-03 | 2020-03-23 | 2020-01-03 |  |  |  | No |  |  | Not Required
21INR0490 | Samson Solar 2 | SS Completed, FIS Completed, IA | Samson Solar Energy II LLC | 345 kV TTRSW 11688 | Lamar | NORTH | 2023-06-30 | SOL | PV | 203 |  | 2020-01-14 | 2020-01-13 | 2019-01-04 | 2020-01-13 | 2020-06-09 |  | 2020-08-27 | Yes | Not Required | Not Required | Not Required | 2021-04-12
21INR0491 | Samson Solar 3 | SS Completed, FIS Completed, IA | Samson Solar Energy III LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2022-08-31 | SOL | PV | 250 | COD | 2020-01-14 | 2020-01-13 | 2019-01-04 | 2020-01-13 | 2020-06-09 |  | 2020-08-27 | Yes | Not Required | Not Required | Not Required | 2020-08-27 | 2020-10-15 | 2020-10-26 |  |  | 2021-06-30 | 2021-10-26
21INR0492 | Stockyard Grid Batt | SS Completed, FIS Started, No IA | Stockyard Grid, LLC | 2082 Hicks 138kV | Tarrant | NORTH | 2023-07-01 | OTH | BA | 150.89 |  | 2020-02-05 | 2020-01-13 | 2020-03-30 | 2020-01-13 |  | No |  | No |  |  | Not Required
21INR0493 | Ellis Solar | SS Completed, FIS Completed, IA | Ellis Solar, LLC | tap 138kV 2300 Cottonwd_T- 2310 Midlothian_Txi | Ellis | NORTH | 2022-12-15 | SOL | PV | 81 |  | 2020-02-26 | 2020-01-30 | 2020-03-03 | 2020-01-28 | 2021-03-02 | No | 2021-04-15 | Yes | Not Required | Not Required | Not Required | 2021-10-26 | 2021-10-26 | 2021-10-26
21INR0495 | Belding 2 Batt | SS Completed, FIS Started, No IA | Triple Butte II LLC | 38490 TNBelding 69kV | Pecos | WEST | 2023-06-01 | OTH | BA | 51.48 |  | 2020-05-20 | 2020-03-26 | 2020-06-11 | 2020-05-01 |  | No |  | No |  |  | Not Required
21INR0497 | Swoose II | SS Completed, FIS Completed, IA | Swoose II, LLC | 38001 TNPyote 138kV | Ward | WEST | 2022-07-01 | OTH | BA | 100.98 | COD | 2020-05-20 | 2020-03-26 | 2020-06-11 | 2020-04-30 | 2021-01-29 |  | 2021-01-12 | Yes | Not Required | Not Required | Not Required | 2021-01-29 | 2021-02-01 | 2021-02-01 |  |  | 2021-10-26 | 2022-03-14
21INR0499 | Neptune Solar | SS Completed, FIS Completed, IA | Matagorda Solar LLC | 110471 Formosa 138 kV | Jackson | SOUTH | 2022-12-20 | SOL | PV | 204.65 |  | 2020-04-16 | 2020-04-13 | 2020-07-07 | 2020-03-26 | 2021-07-27 | No | 2000-05-30 | Yes |  |  | Not Required | 2022-04-11 | 2022-04-11 | 2022-03-31
21INR0500 | SkySealy | SS Completed, FIS Started, No IA | Sky Global Power Two, LLC | tap 138kV 44700 Gebhardt - 44740 Wallis circuit 65 | Austin | SOUTH | 2023-06-01 | GAS | IC | 149.4 | MW Size | 2020-06-19 | 2020-05-01 | 2020-07-15 | 2020-03-20 |  | No |  | No | 2020-04-15 | Not Required
21INR0505 | Ramsey Storage | SS Completed, FIS Completed, No IA | Hecate Energy Ramsey Storage LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2023-05-01 | OTH | BA | 510.4 |  | 2021-01-20 | 2020-05-20 | 2020-07-30 | 2020-12-23 | 2022-02-25 | No |  | No |  |  | Not Required
21INR0506 | Ty Cooke | SS Completed, FIS Completed, IA | City of Lubbock, by and through Lubbock Power and Light | 59166 LP Holly 69kV | Lubbock | PANHANDLE | 2021-11-15 | GAS | GT | 33 |  | 2020-10-23 | 2020-08-21 | 2020-08-22 | 2020-08-10 | 2020-10-23 |  | 2020-10-30 | Yes | 2004-02-27 | Not Required | 2020-10-05 | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2021-07-09 | 2021-07-14
21INR0507 | Arana Creek Batt | SS Completed, FIS Completed, No IA | Arana Creek LLC | 5648 Loyola 138kV | Kleberg | COASTAL | 2023-05-31 | OTH | BA | 153.5 |  | 2020-10-12 | 2020-06-03 | 2020-08-10 | 2020-10-06 | 2021-09-27 |  |  | No |  |  | Not Required
21INR0508 | Angels Creek | SS Completed, FIS Completed, No IA | Angels Creek LLC | 5888 Bruni 69kV | Webb | SOUTH | 2023-05-31 | OTH | BA | 31.68 |  | 2020-07-27 | 2020-06-03 | 2020-08-18 | 2020-07-23 | 2021-06-22 | No |  | No |  |  | Not Required
21INR0509 | McClure Solar | SS Completed, FIS Started, No IA | Belltown Power Texas | tap 69kV 785 Oran - 343 Morris Sheppard | Palo Pinto | NORTH | 2023-05-31 | SOL | PV | 105.73 |  | 2021-03-18 | 2020-06-03 | 2020-08-18 | 2021-02-24 |  |  |  | No |  |  | Not Required
21INR0511 | Wolf Ridge Repower | SS Completed, FIS Started, No IA | Wolf Ridge Wind, LLC | 730 Wolf Ridge 138kV | Cooke | NORTH | 2022-12-31 | WIN | WT | 9 |  | 2020-10-09 | 2020-06-26 | 2020-09-14 | 2020-10-08 |  | No |  | No |  |  | Not Required
21INR0512 | Colorado Bend I Expansion | SS Completed, FIS Completed, IA | Colorado Bend I Power, LLC | 42985 Dyann 138kV | Wharton | SOUTH | 2022-11-01 | GAS | GT | 78 |  | 2021-05-12 | 2020-09-11 | 2020-11-30 | 2021-04-21 | 2021-11-10 |  | 2021-12-08 | Yes | 2020-11-23 | Not Required | 2022-01-18 | 2022-01-24 | 2022-01-28 | 2022-01-28
21INR0515 | Roadrunner Crossing Wind II | SS Completed, FIS Started, No IA | Nextera Energy Resources LLC | tap 345kV 68005 WShack - 68050 Romney | Eastland | NORTH | 2024-01-31 | WIN | WT | 126.72 | MW Size | 2020-10-27 | 2020-07-02 | 2020-09-14 | 2020-07-09 |  |  |  | No |  |  | Not Required
21INR0517 | Tidwell Prairie Storage 1 | SS Completed, FIS Started, No IA | Tidwell Prairie LLC | 39950 TNP ONE PLANT 345kV - 3400 TWIN OAK | Robertson | NORTH | 2023-11-01 | OTH | BA | 304.78 |  | 2020-07-23 | 2020-07-24 | 2020-10-20 | 2020-07-16 |  |  |  | No |  |  | Not Required
21INR0520 | Viking Solar | SS Completed, FIS Started, No IA | Yellow Viking Development One LLC | ap 345kV 1900 Comanche Peak - 11886 Timberview Switch | Hood | NORTH | 2024-07-26 | SOL | PV | 288.99 |  | 2020-10-09 | 2020-10-23 | 2021-01-12 | 2020-08-20 |  |  |  | No |  |  | Not Required
21INR0521 | White Mesa 2 Wind | SS Completed, FIS Completed, IA | White Mesa Wind, LLC | 76005 Schneeman Draw 345kV | Crockett | WEST | 2022-03-14 | WIN | WT | 348 |  | 2020-11-23 | 2020-09-11 | 2020-11-30 | 2020-11-09 | 2021-02-01 |  | 2018-12-13 | Yes |  |  | Not Required | 2021-02-01 | 2021-02-01 | 2021-02-01 |  |  | 2021-09-07 | 2021-10-07
21INR0522 | Madero Unit2 | SS Completed, FIS Completed, IA | Ignacio Grid, LLC | 8824 Railroad 138kV | Hidalgo | SOUTH | 2022-07-08 | OTH | BA | 101.52 | COD | 2020-10-01 | 2020-10-07 | 2019-03-12 | 2020-09-16 | 2020-10-28 |  | 2020-10-27 | Yes | Not Required | Not Required | Not Required | 2020-10-30 | 2020-10-31 | 2020-10-30 |  |  | 2022-05-06 | 2022-05-26
21INR0527 | Hays Energy Unit 3 Repower | SS Completed, FIS Started, No IA | HAYS ENERGY, LLC | 7043 Hays 345kV | Hays | SOUTH | 2023-06-15 | GAS | CC | 18 | COD | 2021-02-09 | 2020-10-07 | 2020-12-30 | 2021-02-05 |  |  |  | No
21INR0529 | Topaz Energy Storage | SS Completed, FIS Started, No IA | WattBridge Energy, LLC | 38745 TN Attwater 138kV | Galveston | HOUSTON | 2023-06-01 | OTH | BA | 202.32 |  | 2020-11-25 | 2020-12-03 | 2021-02-19 | 2020-11-25 |  |  |  | No |  |  | Not Required
21INR0532 | Brazos Wind Repower | SS Completed, FIS Completed, No IA | BRAZOS WIND VENTURES, LLC | 1064 Sun 138kV | Scurry | WEST | 2023-05-31 | WIN | WT | 22.4 |  | 2020-12-18 | 2020-12-22 | 2021-03-10 | 2020-11-30 | 2022-04-01 |  |  | Yes |  |  | Not Required
21INR0534 | Midlothian Unit 2 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1939 Midlothian ELP 345kV | Ellis | NORTH | 2022-08-01 | GAS | CC | 18 |  | 2021-04-28 | 2021-01-25 | 2021-04-30 | 2021-02-08 |  |  |  | No
21INR0538 | Blue Jay Solar II | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2022-11-18 | SOL | PV | 68.95 |  | 2018-02-15 | 2021-04-13 | 2021-04-14 |  | 2021-04-26 | No | 2020-10-26 | Yes |  |  | Not Required | 2020-12-02 | 2021-04-26 | 2021-04-29 |  |  | 2021-11-11 | 2021-11-19
21INR0539 | Anchor Wind II | SS Completed, FIS Completed, IA | Ranchland Wind Project II, LLC | tap 345kV 68008 LATIMER - 68010 ROMNEY | Eastland | NORTH | 2022-08-03 | WIN | WT | 128.7 |  | 2019-06-26 | 2021-04-13 | 2021-04-14 |  | 2021-04-30 | No | 2020-11-30 | Yes |  |  | Not Required | 2021-04-30 | 2021-04-30 | 2021-04-30 |  |  | 2021-11-29 | 2022-02-11
21INR0541 | Bastrop Energy Center AGP repower Phase I | SS Completed, FIS Completed, No IA | Bastrop Energy Partners, LP | 7049 Bastrop 345kV | Bastrop | SOUTH | 2022-07-15 | GAS | CC | 21 |  | 2021-04-28 | 2021-04-13 | 2021-07-02 | 2021-04-19 | 2021-10-29 |  |  | No |  |  |  | 2021-10-28 | 2021-10-28 | 2021-11-01 |  |  |  | 2022-04-27
21INR0543 | Jefferson Enterprise Energy | SS Completed, FIS Started, No IA | ONCOR | 3118 LUFKIN SWITCH 138kV | Angelina | NORTH | 2023-07-01 | BIO | ST | 53 | MW Size | 2022-06-08 | 2021-09-24 | 2021-12-02 | 2022-05-26 |  |  |  | No
21INR0546 | Anchor Wind III | SS Completed, FIS Completed, IA | RANCHLAND WIND PROJECT LLC | 345 kV Aspire Station (68011) | Eastland | NORTH | 2022-10-11 | WIN | WT | 16 |  | 2019-06-26 | 2021-12-03 | 2022-03-01 |  | 2021-04-30 | No | 2020-11-30 | Yes | Not Required | Not Required | Not Required | 2020-12-02 | 2021-04-30 | 2021-04-30 |  |  | 2021-11-29 |  | This project is a split off of Anchor Wind 21INR0387
22INR0001 | Cunningham Solar 3 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 |  | 2018-10-23 | 2018-08-29 | 2018-06-12 | 2018-10-23 |  | No |  | No | Not Required | Not Required | Not Required
22INR0202 | Delilah Solar 1 | SS Completed, FIS Completed, IA | Delilah Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2023-02-15 | SOL | PV | 300 | COD | 2019-05-13 | 2018-11-20 | 2019-01-03 | 2019-05-03 | 2020-06-09 | No | 2020-12-22 | Yes | Not Required | Not Required | Not Required | 2021-03-23 | 2021-03-23 | 2021-04-27
22INR0203 | Delilah Solar 2 | SS Completed, FIS Completed, IA | Delilah Solar Energy II LLC | 345 kV TTRSW 11688 | Lamar | NORTH | 2023-06-30 | SOL | PV | 317.58 |  | 2019-05-13 | 2018-11-20 | 2019-01-03 | 2019-05-03 | 2020-06-09 | No | 2020-12-22 | Yes | Not Required | Not Required | Not Required | 2021-03-23
22INR0205 | Sbranch Solar | SS Completed, FIS Completed, IA | CG Wharton County LLC | Tap 138kV 44190 East Bernard - 44130 Caney | Wharton | SOUTH | 2023-03-03 | SOL | PV | 233.52 |  | 2019-04-01 | 2019-01-03 | 2019-03-13 | 2019-03-29 | 2021-07-29 | No | 2020-07-26 | Yes | Not Required | Not Required | Not Required | 2020-10-07 | 2021-07-06 | 2021-07-29
22INR0209 | Crescent Solar | SS Completed, FIS Started, No IA | Crescent Solar | 6101 Riley 345kV | Wilbarger | WEST | 2023-12-26 | SOL | PV | 250 |  | 2019-09-23 | 2019-01-17 | 2019-04-02 | 2019-09-20 |  |  |  | No | Not Required | Not Required | Not Required
22INR0211 | Schoolhouse Solar | SS Completed, FIS Completed, IA | Schoolhouse Solar, LLC | tap 345kV 7040 Austrop - 13429 Sandow | Lee | SOUTH | 2024-03-10 | SOL | PV | 150.84 | COD | 2019-10-08 | 2019-01-30 | 2019-04-09 | 2019-10-02 | 2020-12-07 | No | 2021-07-11 | No | Not Required | Not Required | Not Required
22INR0215 | TEXAS SOLAR NOVA 3 | SS Completed, FIS Started, No IA | Texas Solar Nova 1, LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2026-01-31 | SOL | PV | 200.2 |  | 2019-05-28 | 2019-06-24 | 2015-12-30 | 2019-06-19 |  |  |  | No |  |  | Not Required
22INR0218 | Greyhound Solar 2 | SS Completed, FIS Started, No IA | Greyhound Solar 2 | tap 345kV dbl ckt 11010 Wolf - 1018 Moss and 11008 Wolf - 11028 Odessa | Ector | WEST | 2025-12-31 | SOL | PV | 500 |  | 2019-05-23 | 2019-05-14 | 2019-08-05 | 2019-05-10 |  |  |  | No | Not Required | Not Required | Not Required
22INR0220 | Lamkin Solar | SS Completed, FIS Started, No IA | Commanche Solar I, LLC | tap 69kV 258 Hamilton - 273 Gustine | Comanche | NORTH | 2023-12-31 | SOL | PV | 101.5 |  | 2020-05-11 | 2019-06-24 | 2019-09-18 | 2020-03-13 |  |  |  | No |  |  | Not Required
22INR0223 | Eiffel Solar | SS Completed, FIS Completed, IA | Paris Farm Solar, LLC | POI changed to Double Tap 138kV 1693 Paris SW - 11770 Lamar Blossom Tap and 1693 Paris SW - 1768 Deport Rea | Lamar | NORTH | 2023-05-15 | SOL | PV | 200 | COD | 2019-08-26 | 2019-07-11 | 2019-09-05 | 2019-07-11 | 2020-08-26 | No | 2021-03-19 | No |  |  | Not Required
22INR0236 | Point Mountain Solar | SS Completed, FIS Started, No IA | Hecate Energy Point Mountain LLC | 76000 North McCamey 345kV | Crane | WEST | 2023-07-01 | SOL | PV | 514 |  | 2019-08-13 | 2019-08-26 | 2019-11-08 | 2019-08-19 |  |  |  | No |  |  | Not Required
22INR0237 | Dragan Solar | SS Completed, FIS Completed, No IA | Hecate Comanche Solar LLC | 1440 Comanche 345kV | Comanche | NORTH | 2024-05-01 | SOL | PV | 411 |  | 2019-11-11 | 2019-11-11 | 2020-02-17 | 2019-08-23 | 2022-04-25 | No |  | No |  |  | Not Required
22INR0238 | Rockefeller Solar SLF | SS Completed, FIS Started, No IA | Photosol US Renewable Energy LLC | 76003 Big Hill 345kV | Schleicher | WEST | 2024-12-01 | SOL | PV | 207.48 |  | 2020-08-20 | 2019-10-31 | 2020-01-24 | 2020-07-21 |  |  |  | No |  |  | Not Required
22INR0239 | Rockefeller Storage SLF | SS Completed, FIS Started, No IA | Photosol US Renewable Energy LLC | 76003 Big Hill 345kV | Schleicher | WEST | 2024-12-01 | OTH | BA | 0 |  | 2020-08-20 | 2019-10-31 | 2020-01-24 | 2020-07-21 |  |  |  | No | Not Required | Not Required | Not Required
22INR0242 | Bright Arrow Solar | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | 11689 CYCLONE 345 KV | Hopkins | NORTH | 2022-12-15 | SOL | PV | 305.07 |  | 2020-03-09 | 2020-02-12 | 2020-05-01 | 2020-03-04 | 2022-04-19 | No | 2021-02-18 | Yes |  |  | Not Required | 2021-03-01 | 2022-04-28 | 2022-04-28
22INR0243 | Painted Horse Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Wilson | SOUTH | 2023-12-15 | SOL | PV | 200.58 |  | 2021-01-13 | 2020-02-12 | 2020-05-06 | 2020-11-05 |  |  |  | No |  |  | Not Required
22INR0244 | Razorbill Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP to 44200 Hillje 345kV Ckt 64 | Matagorda | COASTAL | 2023-12-15 | SOL | PV | 240 |  | 2020-10-23 | 2020-01-02 | 2020-03-26 | 2020-09-16 |  |  |  | No | Not Required | Not Required | Not Required
22INR0251 | Shaula I Solar | SS Completed, FIS Started, IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5323 Old Hickory ckt 2 | DeWitt | SOUTH | 2024-06-28 | SOL | PV | 205.2 |  | 2019-11-27 | 2019-12-03 | 2020-03-08 | 2019-11-20 |  | No | 2022-02-16 | Yes |  |  | Not Required
22INR0254 | Pisgah Ridge Solar | SS Completed, FIS Completed, IA | Pisgah Ridge Solar, LLC | tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2022-12-22 | SOL | PV | 253.85 |  | 2019-11-01 | 2019-11-01 | 2020-02-07 | 2019-10-21 | 2022-04-29 | No | 2021-01-27 | Yes | Not Required | Not Required | Not Required | 2022-02-28 | 2022-02-28 | 2022-04-27 |  |  | 2022-06-27
22INR0257 | Corazon Solar Phase II | SS Completed, FIS Started, IA | BAYWA R.E. SOLAR PROJECTS | 80219 Lobo 345kV | Webb | SOUTH | 2025-01-12 | SOL | PV | 203.9 |  | 2019-12-16 | 2019-12-19 | 2020-03-12 | 2019-12-04 |  | No | 2020-08-04 | No | Not Required | Not Required | Not Required
22INR0260 | Eliza Storage | SS Completed, FIS Completed, No IA | Ables Springs Storage, LLC | tap 345kV 2478 Royse - 3103 Shamburger | Kaufman | NORTH | 2024-02-15 | OTH | BA | 100.62 |  | 2020-08-21 | 2019-12-03 | 2020-02-25 | 2020-08-19 | 2022-06-03 |  |  | No |  |  | Not Required
22INR0261 | Dorado Solar | SS Completed, FIS Started, No IA | Eldorado Solar Power LLC | 68051 Reata 345kV | Callahan | WEST | 2024-05-31 | SOL | PV | 406.25 | Status Change INA-to-PLN | 2020-09-02 | 2020-01-09 | 2020-03-30 | 2020-08-27 |  |  |  | No | Not Required | Not Required | Not Required
22INR0262 | Deville Solar | SS Completed, FIS Started, No IA | Deville Solar LLC | 68051 Reata 345kV | Callahan | WEST | 2025-05-31 | SOL | PV | 425.02 | Status Change INA-to-PLN | 2020-09-02 | 2020-01-22 | 2020-04-08 | 2020-08-27 |  |  |  | No |  |  | Not Required
22INR0267 | Shaula II Solar | SS Completed, FIS Started, IA | Shaula Energy Project II, LLC | tap 345kV 5133 Elm Creek - 5323 Old Hickory ckt 2 | DeWitt | SOUTH | 2024-09-18 | SOL | PV | 205.2 |  | 2019-12-27 | 2019-12-18 | 2020-03-12 | 2019-12-18 |  | No | 2022-04-27 | Yes |  |  | Not Required
22INR0269 | Shinnery Hill Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 6111 Riley7B - 1730 W Krum | Wichita | WEST | 2025-03-28 | SOL | PV | 502.54 |  | 2020-04-23 | 2019-12-17 | 2020-03-06 | 2020-04-09 |  | No |  | No |  |  | Not Required
22INR0270 | Brass Fork Solar 1 | SS Completed, FIS Started, IA | EDF Renewables Development, Inc. | Tap 345kV 60703 Gauss - 60514 Clear Crossing (60712 QUASAR) | Haskell | WEST | 2024-06-01 | SOL | PV | 304.78 |  | 2020-08-27 | 2019-12-17 | 2020-03-06 | 2020-06-19 |  |  | 2021-06-14 | Yes |  |  | Not Required | 2021-06-25
22INR0272 | Brinton Fork Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 60791 Perigee 345kV | Haskell | WEST | 2023-12-01 | SOL | PV | 513.5 |  | 2020-08-27 | 2019-12-17 | 2020-03-10 | 2020-06-19 |  |  |  | No |  |  | Not Required
22INR0274 | Crowded Star Solar II | SS Completed, FIS Started, IA | Jones City Solar II, LLC | tap 345kV 68000 West Shack - 68001 Clayton c2 | Jones | WEST | 2025-02-03 | SOL | PV | 188.8 |  | 2019-05-23 | 2020-03-26 | 2020-06-05 | 2021-03-24 |  | No | 2019-12-17 | No | Not Required | Not Required | Not Required
22INR0275 | Coleto Creek ESS Addition | SS Completed, FIS Started, No IA | COLETO CREEK POWER LLC | 8162 Coleto Creek 138kV | Goliad | SOUTH | 2023-03-15 | OTH | BA | 100.1 |  | 2021-04-15 | 2019-12-11 | 2020-03-05 | 2020-09-17 |  |  |  | No |  |  | Not Required
22INR0276 | Trinidad ESS Addition | SS Completed, FIS Started, No IA | LUMINANT GENERATION COMPANY LLC | 3127 Trinidad 138kV | Henderson | NORTH | 2024-04-22 | OTH | BA | 110 |  | 2021-04-16 | 2019-12-11 | 2020-03-06 | 2020-09-17 |  |  |  | No |  |  | Not Required
22INR0279 | Clutch City Solar | SS Completed, FIS Completed, No IA | HZ Solar I, LLC | tap 138kV 42960 Mustang Bayou – 42100 Hudson | Brazoria | COASTAL | 2024-03-21 | SOL | PV | 204.17 | Status Change INA-to-PLN | 2020-03-16 | 2020-01-22 | 2020-04-08 | 2020-02-11 | 2022-03-04 | No |  | No |  |  | Not Required
22INR0280 | Roseland Storage | SS Completed, FIS Completed, IA | Enel Green Power Roseland Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2022-12-05 | OTH | BA | 51.63 |  | 2020-01-17 | 2019-12-26 | 2020-03-24 | 2019-12-26 | 2022-01-24 |  | 2022-01-26 | Yes | Not Required | Not Required | Not Required | 2022-01-31 | 2022-01-31 | 2022-01-31
22INR0281 | Pink Solar | SS Completed, FIS Started, No IA | General Solar, LLC | 971 Pruitt 138kV | Hunt | NORTH | 2023-12-16 | SOL | PV | 151 | COD | 2020-10-21 | 2020-01-30 | 2020-04-20 | 2020-10-16 |  |  |  | No | Not Required | Not Required | Not Required
22INR0283 | Peregrine Solar | SS Completed, FIS Started, IA | SP-Peregrine Solar LLC | tap 345kV 8624 Grissom – 8164 Coleto Creek | Goliad | SOUTH | 2024-03-01 | SOL | PV | 303.36 |  | 2020-07-29 | 2020-01-07 | 2020-03-30 | 2020-05-27 |  | No | 2021-06-19 | Yes |  |  | Not Required | 2021-07-02
22INR0295 | Coral Solar | SS Completed, FIS Completed, IA | Copperhead Solar, LLC | tap 138kV 3410 Lake Creek Switch - 3582 Falls County | Falls | NORTH | 2023-12-15 | SOL | PV | 152 |  | 2020-08-17 | 2020-06-03 | 2020-06-16 | 2020-07-30 | 2021-10-22 | No | 2021-12-29 | No |  |  | Not Required
22INR0301 | Fortuna Wind | SS Completed, FIS Started, No IA | RWE Renewables Development, LLC | Tap 345kV 1429 Jacksboro - 1730 WKrum | Jack | NORTH | 2023-12-15 | WIN | WT | 250 |  | 2021-01-18 | 2020-03-06 | 2020-05-27 | 2020-11-24 |  |  |  | No |  |  | Not Required
22INR0302 | Bright Arrow Storage | SS Completed, FIS Started, IA | RWE Solar Development, LLC | 11689 CYCLONE 345 KV | Hopkins | NORTH | 2023-02-28 | OTH | BA | 103.56 |  | 2021-01-11 | 2020-03-06 | 2020-05-05 | 2020-11-02 |  |  | 2022-03-17 | Yes |  |  | Not Required
22INR0307 | Desert Vine Solar | SS Completed, FIS Started, No IA | J&R Power DevCo, LLC | 8299 Zapata 138kV | Zapata | SOUTH | 2023-06-30 | SOL | PV | 121.29 |  | 2021-10-06 | 2020-05-01 | 2020-07-13 | 2021-02-03 |  |  |  | No |  |  | Not Required
22INR0314 | Lan Solar | SS Completed, FIS Started, No IA | General Solar, LLC | Tap 345kV 1729 Valley South – 1692 Paris Switch | Lamar | NORTH | 2024-08-16 | SOL | PV | 182.2 |  | 2021-10-12 | 2020-05-01 | 2020-07-07 | 2021-01-04 |  |  |  | No | Not Required | Not Required | Not Required
22INR0322 | BRP Paleo BESS | SS Completed, FIS Completed, IA | BRP Paleo BESS LLC | 23920 Blackwater Draw 345kV | Hale | PANHANDLE | 2023-03-15 | OTH | BA | 202.36 |  | 2020-04-09 | 2020-04-13 | 2020-06-25 | 2020-03-25 | 2021-10-29 |  | 2021-02-05 | Yes | Not Required | Not Required | Not Required | 2021-02-05 | 2021-09-27 | 2021-10-29
22INR0325 | BRP Dickens BESS | SS Completed, FIS Completed, IA | BRP Dickens BESS LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2023-03-15 | OTH | BA | 202.33 |  | 2020-04-16 | 2020-04-22 | 2020-07-09 | 2020-04-06 | 2021-09-01 |  | 2020-11-03 | Yes | Not Required | Not Required | Not Required | 2021-01-14 | 2021-10-11 | 2021-10-29
22INR0326 | Inertia Wind | SS Completed, FIS Completed, IA | Inertia WS Holdings, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2022-12-31 | WIN | WT | 350 |  | 2020-08-31 | 2020-06-03 | 2021-02-02 | 2020-05-27 | 2022-02-07 |  | 2021-05-04 | Yes |  |  | Not Required | 2021-10-08 | 2022-04-26 | 2022-04-26
22INR0327 | Hummingbird Storage | SS Completed, FIS Started, IA | KCE TX 10, LLC | 1730 Krum 345kV | Denton | NORTH | 2023-07-11 | OTH | BA | 103.8 |  | 2020-05-29 | 2020-05-20 | 2020-07-30 | 2020-04-24 |  | No | 2022-02-23 | No |  |  | Not Required
22INR0328 | Inertia BESS | SS Completed, FIS Started, IA | Inertia WS Holdings, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2023-05-31 | OTH | BA | 121.45 |  | 2020-08-24 | 2020-06-03 | 2021-02-02 | 2020-05-27 |  | No | 2021-05-04 | Yes | Not Required | Not Required | Not Required | 2021-10-08
22INR0330 | Old Aqueduct Batt | SS Completed, FIS Completed, No IA | Old Aqueduct LLC | 23920 Blackwater 345kV | Hale | PANHANDLE | 2024-03-01 | OTH | BA | 302.94 |  | 2020-07-24 | 2020-05-01 | 2020-07-13 | 2020-06-29 | 2021-10-06 |  |  | No |  |  | Not Required
22INR0332 | Brantley Branch Batt | SS Completed, FIS Started, No IA | Brantley Branch LLC | Mt. Enterprise (Bus # 3116) – Martin Lake 345kv Line (Bus # 3100 | Rusk | NORTH | 2024-01-30 | OTH | BA | 305.1 |  | 2020-12-07 | 2020-05-01 | 2020-07-15 | 2020-11-24 |  |  |  | No |  |  | Not Required
22INR0335 | Estonian Solar Farm | SS Completed, FIS Completed, IA | Enel Green Power Estonian Solar Project, LLC | tap 138kV 1801 Paris Pump Tap – 17011 LKCRK_P8 | Delta | NORTH | 2023-06-01 | SOL | PV | 204.47 |  | 2020-01-17 | 2020-04-22 | 2020-06-29 |  | 2022-06-13 | No | 2021-08-12 | Yes |  |  | Not Required | 2022-04-21
22INR0336 | Estonian Energy Storage | SS Completed, FIS Completed, IA | Enel Green Power Estonian Solar Project, LLC | tap 138kV 1801 Paris Pump Tap – 17011 LKCRK_P8 | Delta | NORTH | 2023-06-01 | OTH | BA | 102.5 |  | 2020-02-26 | 2020-04-22 | 2020-06-29 |  | 2022-06-13 | No | 2021-08-12 | Yes | Not Required | Not Required | Not Required | 2022-04-21
22INR0337 | Skylab Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 5915 STP - 8249 Angstrom | Wharton | SOUTH | 2024-12-01 | SOL | PV | 609.74 |  | 2020-08-10 | 2020-06-03 | 2020-08-11 | 2020-05-27 |  | No |  | No |  |  | Not Required
22INR0338 | Limousin Oak Storage | SS Completed, FIS Started, IA | KCE TX 15, LLC | 44645 Singleton 345kV | Grimes | NORTH | 2023-08-01 | OTH | BA | 104.62 |  | 2020-05-14 | 2020-05-20 | 2020-07-30 | 2020-04-24 |  | No | 2022-04-01 | No |  |  | Not Required
22INR0342 | Matagorda Solar | SS Completed, FIS Completed, IA | Leeward Renewable Energy Development, LLC | 5555 Shropshire 69kV | Matagorda | COASTAL | 2023-12-28 | SOL | PV | 101 |  | 2020-12-08 | 2020-05-01 | 2020-07-15 | 2020-11-05 | 2021-09-14 |  | 2022-06-08 | No |  |  | Not Required
22INR0347 | BRP Crater BESS | SS Completed, FIS Started, No IA | BRP Crater BESS LLC | tap 345kV 1025 Falcon Seaboard - 1021 Midland East | Howard | WEST | 2024-06-01 | OTH | BA | 310.31 |  | 2020-05-18 | 2020-05-20 | 2020-07-30 | 2020-04-30 |  |  |  | No |  |  | Not Required
22INR0349 | BRP Antlia BESS | SS Completed, FIS Completed, IA | BRP Antlia BESS LLC | tap 138kV 8998 Maxwell – 8261 Whiting | Val Verde | WEST | 2023-05-05 | OTH | BA | 70.95 |  | 2020-06-18 | 2020-06-03 | 2020-08-11 | 2020-05-14 | 2021-05-21 | No | 2021-06-05 | Yes | Not Required | Not Required | Not Required
22INR0350 | Milam Solar 2 | SS Completed, FIS Started, No IA | Sandow Lakes Ranch Solar II, LLC | tap one 345kV 7040 Austrop - 13429 Sandow line | Milam | SOUTH | 2024-05-16 | SOL | PV | 290.21 |  | 2020-08-24 | 2020-09-11 | 2021-02-08 | 2020-05-28 |  |  |  | No |  |  | Not Required
22INR0352 | Sparta Solar | SS Completed, FIS Completed, IA | Sparta Solar | AEP 8689 Tango 345kV station | Bee | SOUTH | 2022-12-24 | SOL | PV | 252.35 |  | 2020-06-25 | 2020-05-20 | 2020-07-30 | 2020-05-07 | 2021-07-29 | No | 2020-08-14 | Yes | Not Required | Not Required | Not Required | 2020-08-17 | 2021-08-02 | 2021-07-30
22INR0353 | BRP Carina BESS | SS Completed, FIS Completed, IA | BRP Carina BESS LLC | 8479 Clarkwood 138kV | Nueces | COASTAL | 2023-06-01 | OTH | BA | 151.85 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 | 2020-06-22 | 2021-07-06 |  | 2021-08-03 | Yes | Not Required | Not Required | Not Required
22INR0354 | XE MURAT Solar | SS Completed, FIS Completed, IA | Liberty 1 Solar | tap 138kV 40391 Crosby C66 - 40130 Atascocita | Harris | HOUSTON | 2024-01-04 | SOL | PV | 60.8 |  | 2021-01-20 | 2020-08-04 | 2020-10-16 | 2021-01-05 | 2021-12-06 |  | 2022-03-04 | No |  |  | Not Required
22INR0356 | Jungmann Solar | SS Completed, FIS Completed, IA | BT Jungmann LLC | Tap 69kV 3643 Temp SS - 3689 Marak c1 | Milam | SOUTH | 2023-09-01 | SOL | PV | 40 |  | 2021-02-05 | 2020-06-03 | 2020-08-11 | 2021-02-05 | 2021-10-26 |  | 2022-02-15 | No |  |  | Not Required
22INR0357 | Loma Pinta Solar | SS Completed, FIS Completed, No IA | Loma Pinta Wind Energy, LLC | 5705 Fowlerton 138kV | La Salle | SOUTH | 2023-02-02 | SOL | PV | 203.06 |  | 2020-09-08 | 2020-06-03 | 2020-08-18 | 2020-05-28 | 2021-11-11 | No |  | No |  |  | Not Required
22INR0358 | XE RHODA Solar | SS Completed, FIS Started, No IA | Milam 2 Solar | Tap 138kV 32 Robertson - 64 Milano | Milam | SOUTH | 2024-02-28 | SOL | PV | 33.7 |  | 2021-01-20 | 2020-07-10 | 2020-09-28 | 2021-01-05 |  |  |  | No | Not Required | Not Required | Not Required
22INR0359 | Dileo Solar | SS Completed, FIS Completed, IA | Elawan Dileo Solar | tap 69kV 37470 TN Olsen - 37420 TN Lake Whitney | Bosque | NORTH | 2023-03-01 | SOL | PV | 72 | SFS/NtP | 2020-11-23 | 2020-06-19 | 2020-09-08 | 2020-11-10 | 2021-08-17 | No | 2021-09-17 | Yes | Not Required | Not Required | Not Required
22INR0360 | Jade Solar | SS Completed, FIS Completed, IA | IP RENEWABLE ENERGY HOLDINGS LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Scurry | WEST | 2023-06-30 | SOL | PV | 326.6 | MW Size | 2020-07-15 | 2020-06-26 | 2020-09-14 | 2020-06-15 | 2021-11-16 | Yes | 2021-01-22 | Yes |  |  | Not Required | 2021-05-03
22INR0361 | Sibyl Power Station | SS Completed, FIS Completed, No IA | WattBridge Energy, LLC | Tap 138kV 43261 Southwyck - 44552 Telview | Fort Bend | HOUSTON | 2023-08-01 | GAS | GT | 298.68 |  | 2020-08-26 | 2020-09-02 | 2020-11-12 | 2020-08-18 | 2021-11-02 |  |  | No
22INR0362 | Pluto Solar | SS Completed, FIS Started, No IA | Pluto Solar, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2024-07-31 | SOL | PV | 252.8 |  | 2020-07-28 | 2020-06-26 | 2020-09-14 | 2020-06-23 |  |  |  | No |  |  | Not Required
22INR0363 | Hayhurst Texas Solar | SS Completed, FIS Completed, IA | CHEVRON USA, INC. | tap 138kV 11103 Rust Hills - 11190 Horseshoe Springs Switch | Culberson | WEST | 2023-02-15 | SOL | PV | 25.68 |  | 2020-10-23 | 2020-08-21 | 2020-11-04 | 2020-08-13 | 2021-10-21 |  | 2021-09-09 | Yes |  |  | Not Required | 2022-04-29 | 2022-04-29 | 2022-04-29
22INR0364 | Painted Horse Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Wilson | SOUTH | 2023-12-15 | OTH | BA | 53.22 |  | 2021-03-17 | 2020-07-02 | 2020-09-14 | 2021-03-07 |  |  |  | No |  |  | Not Required
22INR0365 | BRP Mensa BESS | SS Completed, FIS Started, No IA | BRP Mensa BESS LLC | 60718 Pecos Valley 138kV | Pecos | WEST | 2024-06-01 | OTH | BA | 404.99 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 | 2020-06-22 |  |  |  | No | Not Required | Not Required | Not Required
22INR0366 | BRP Libra BESS | SS Completed, FIS Completed, IA | BRP Libra BESS LLC | 5133 Elm Creek 345kV | Guadalupe | SOUTH | 2023-03-31 | OTH | BA | 202.38 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 | 2020-06-22 | 2021-08-23 | No | 2022-02-16 | Yes |  |  | Not Required
22INR0368 | Padua Grid BESS | SS Completed, FIS Started, IA | Padua Grid, LLC | 5395 O.W Sommers 138kV | Bexar | SOUTH | 2024-03-31 | OTH | BA | 202.6 | Status Change INA-to-PLN | 2020-07-23 | 2020-07-10 | 2020-09-28 | 2020-06-29 |  | No | 2021-11-16 | Yes | Not Required | Not Required | Not Required
22INR0369 | Beachwood Power Station (Mark One) | SS Completed, FIS Completed, IA | WattBridge Energy, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2022-09-30 | GAS | GT | 306 |  | 2020-07-20 | 2020-07-10 | 2020-09-28 | 2020-07-03 | 2021-10-07 | No | 2021-07-21 | Yes | 2020-12-16 | Not Required | 2021-06-11 | 2021-07-28 | 2021-10-20 | 2021-10-20
22INR0372 | BRP Hydra BESS | SS Completed, FIS Completed, IA | BRP Hydra BESS LLC | 76002 Bakersfield 345kV | Pecos | WEST | 2023-03-15 | OTH | BA | 202.31 |  | 2020-07-27 | 2020-07-24 | 2020-10-20 | 2020-07-06 | 2021-10-28 | No | 2021-05-08 | Yes | Not Required | Not Required | Not Required | 2021-09-21 | 2021-10-29 | 2021-10-29
22INR0374 | Inertia Solar | SS Completed, FIS Started, IA | Inertia WS Holdings, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2023-12-31 | SOL | PV | 258.35 |  | 2020-10-26 |  | 2021-02-02 | 2020-10-13 |  |  | 2021-05-04 | Yes |  |  | Not Required | 2021-10-08
22INR0375 | Inertia BESS 2 | SS Completed, FIS Started, IA | Inertia WS Holdings, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2022-12-31 | OTH | BA | 100.77 |  | 2020-10-26 |  | 2021-02-02 | 2020-10-13 |  |  | 2021-05-04 | Yes | Not Required | Not Required | Not Required | 2021-10-08
22INR0382 | Razorbill Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP to 44200 Hillje 345kV Ckt 64 | Matagorda | COASTAL | 2023-12-15 | OTH | BA | 120 |  | 2021-06-25 | 2020-08-04 | 2020-10-28 | 2021-06-11 |  |  |  | No | Not Required | Not Required | Not Required
22INR0383 | BRP Musca BESS | SS Completed, FIS Started, No IA | BRP Musca BESS LLC | 60361 Santa Rita 138kV | Reagan | WEST | 2024-02-01 | OTH | BA | 101.28 |  | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  | No |  | No |  |  | Not Required
22INR0384 | BRP Pavo BESS | SS Completed, FIS Completed, IA | BRP Pavo BESS LLC | 38430 TN White Baker 138kV | Pecos | WEST | 2023-03-15 | OTH | BA | 176.85 |  | 2020-08-19 | 2020-07-24 | 2020-10-08 | 2020-08-17 | 2021-07-30 | No | 2021-07-15 | Yes | Not Required | Not Required | Not Required | 2021-07-29 | 2021-07-29 | 2021-07-30
22INR0385 | BRP Pictor BESS | SS Completed, FIS Completed, No IA | BRP Pictor BESS LLC | 60400 Lynx 138kV | Crane | WEST | 2023-06-01 | OTH | BA | 202.7 |  | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 | 2022-03-22 | No |  | No |  |  | Not Required
22INR0386 | BRP Octans BESS | SS Completed, FIS Completed, No IA | BRP OCTANS BESS LLC | 6671 Tombstone 138kV | Pecos | WEST | 2023-06-01 | OTH | BA | 126.63 |  | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 | 2022-01-31 |  |  | No |  |  | Not Required
22INR0388 | BRP Cachi BESS | SS Completed, FIS Started, IA | BRP Cachi BESS LLC | 7680 Clear Springs 138kV | Guadalupe | SOUTH | 2023-06-03 | OTH | BA | 202.46 | COD | 2020-10-14 | 2020-08-21 | 2020-11-10 | 2020-08-26 |  |  | 2021-06-11 | No | Not Required | Not Required | Not Required
22INR0390 | BRP Perseus BESS | SS Completed, FIS Started, No IA | BRP Perseus BESS LLC | 8452 Lon Hill 138kV | Nueces | COASTAL | 2024-12-01 | OTH | BA | 202.5 |  | 2020-08-19 | 2020-08-21 | 2020-11-10 | 2020-08-17 |  |  |  | No |  |  | Not Required
22INR0392 | Kalina Solar | SS Completed, FIS Started, No IA | Aurora Solar LLC | 8606 Goddard 345kV | San Patricio | COASTAL | 2023-12-31 | SOL | PV | 120 |  | 2021-03-31 | 2020-08-04 | 2020-10-28 | 2021-03-29 |  |  |  | No |  |  | Not Required
22INR0397 | Buckeye Corpus Fuels Solar | SS Completed, FIS Started, No IA | Corpus Fuels, LLC | 8858 McKenzie 138kV | Nueces | COASTAL | 2023-12-31 | SOL | PV | 57.59 |  | 2020-10-06 | 2020-08-21 | 2020-11-10 | 2020-08-13 |  | No |  | No |  |  | Not Required
22INR0398 | Sabal Storage | SS Completed, FIS Completed, IA | II Battery Storage US LLC | 5761 Paredes 138kV | Cameron | COASTAL | 2023-01-15 | OTH | BA | 24 |  | 2021-06-22 | 2020-09-11 | 2020-11-30 | 2021-05-28 | 2022-05-02 | No | 2022-05-02 | Yes | Not Required | Not Required | Not Required | 2022-05-02 | 2022-05-02 | 2022-05-02
22INR0400 | Dragan Storage | SS Completed, FIS Started, No IA | Hecate Grid Dragan Storage LLC | 1440 Comanche 345kV | Comanche | NORTH | 2024-09-01 | OTH | BA | 408.3 | COD | 2020-10-02 | 2020-08-21 | 2020-11-04 | 2020-08-13 |  |  |  | No |  |  | Not Required
22INR0401 | Eval Storage | SS Completed, FIS Started, IA | Hecate Grid East Valley Storage LLC | 80229 Cavazos 138kV | Cameron | COASTAL | 2023-05-01 | OTH | BA | 255 |  | 2020-12-29 | 2020-10-23 | 2021-01-12 | 2020-11-03 |  |  | 2022-02-03 | Yes | Not Required | Not Required | Not Required
22INR0402 | Frye Storage | SS Completed, FIS Completed, No IA | Hecate Grid Frye Storage LLC | new 345kV sub Kress connecting both 23912 Ogallala - 23914 Tule Canyon circuits | Swisher | PANHANDLE | 2024-05-30 | OTH | BA | 510 |  | 2020-08-26 | 2020-09-02 | 2020-11-19 | 2020-08-17 | 2022-01-28 | No |  | No |  |  | Not Required
22INR0404 | Fence Post Solar | SS Completed, FIS Completed, IA | Fence Post Solar Project, LLC | tap 138kV 3127 Trinidad – 3483 Goodloe | Navarro | NORTH | 2023-02-14 | SOL | PV | 240.92 | COD | 2020-10-02 | 2020-11-05 | 2021-01-20 | 2020-10-21 | 2022-04-25 |  | 2021-08-12 | Yes | Not Required | Not Required | Not Required | 2022-04-28 | 2022-04-28 | 2022-04-28
22INR0405 | Fence Post BESS | SS Completed, FIS Completed, IA | Fence Post Solar Project, LLC | tap 138kV 3127 Trinidad – 3483 Goodloe | Navarro | NORTH | 2023-03-03 | OTH | BA | 73.11 | COD | 2020-10-02 | 2020-11-05 | 2021-01-20 | 2020-10-13 | 2022-04-25 |  | 2021-08-12 | Yes | Not Required | Not Required | Not Required | 2022-04-27 | 2022-04-27 | 2022-04-27
22INR0408 | BRP Pular BESS | SS Completed, FIS Started, No IA | BRP Pular BESS LLC | 8963 Hidalgo Energy Center 138kV | Hidalgo | SOUTH | 2025-02-01 | OTH | BA | 233.1 |  | 2020-09-02 | 2020-09-11 | 2021-06-10 | 2020-08-25 |  |  |  | No |  |  | Not Required
22INR0409 | Stampede Solar | SS Completed, FIS Completed, IA | Stampede Solar Project, LLC | tap 345kV 1685 Farmersville - 11688 Thorn Tree ckt 1 | Hopkins | NORTH | 2023-02-03 | SOL | PV | 259.07 | COD | 2020-10-16 | 2020-11-05 | 2021-01-20 | 2020-10-21 | 2022-04-27 |  | 2021-12-15 | Yes |  |  | Not Required | 2022-04-11 | 2022-04-27 | 2022-04-27
22INR0410 | Stampede BESS | SS Completed, FIS Completed, IA | Stampede Solar Project, LLC | tap 345kV 1685 Farmersville - 11688 Thorn Tree ckt 1 | Hopkins | NORTH | 2023-03-03 | OTH | BA | 73.11 | COD | 2020-10-16 | 2020-11-05 | 2021-01-20 | 2020-10-21 | 2022-04-27 |  | 2021-12-15 | Yes |  |  | Not Required | 2022-04-11 | 2022-04-27 | 2022-04-27
22INR0412 | Andromeda Solar | SS Completed, FIS Completed, IA | IP Renewable Energy Holdings LLC | Tap 345kV 11305 Dermott - 60706 Kirchhoff C | Scurry | WEST | 2023-06-30 | SOL | PV | 326.6 | MW Size | 2020-09-22 | 2020-09-11 | 2020-11-30 | 2020-09-02 | 2021-08-30 | No | 2021-04-01 | Yes |  |  | Not Required | 2022-04-12
22INR0417 | Amsterdam Storage | SS Completed, FIS Completed, IA | Cottonwood Bayou II Storage, LLC | tap 345kV 43035 Oasis - 42500 Dow c27 | Brazoria | COASTAL | 2023-05-19 | OTH | BA | 201.13 |  | 2020-09-30 | 2020-10-07 | 2020-12-30 | 2020-09-11 | 2021-08-23 |  | 2022-04-14 | No |  |  | Not Required
22INR0423 | BRP Quela BESS | SS Completed, FIS Started, No IA | BRP Quela BESS LLC | Tap 138kV 5110 J.T. Deely - 5294 Martinez | Bexar | SOUTH | 2024-05-01 | OTH | BA | 303.74 |  | 2020-09-25 | 2020-09-25 | 2020-12-16 | 2020-09-15 |  |  |  | No |  |  | Not Required
22INR0424 | BRP Denali BESS | SS Completed, FIS Started, No IA | BRP Denali BESS LLC | Tap 138kV 5395 Sommers - 5030 Braunig East | Bexar | SOUTH | 2024-06-01 | OTH | BA | 258.41 |  | 2020-09-25 | 2020-09-25 | 2020-12-16 | 2020-09-17 |  |  |  | No | Not Required | Not Required | Not Required
22INR0425 | MAKALU SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY INFRASTRUCTURES | Tap 138kV 977 Pruitt - 971 Greenville | Hunt | NORTH | 2023-12-18 | SOL | PV | 50.16 |  | 2021-08-17 | 2021-01-21 | 2021-01-28 | 2021-08-10 |  |  |  | No |  |  | Not Required
22INR0426 | LUBIO SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY INFRASTRUCTURE | tap 138kV 2732 Marshall - 2434 Seagoville | Kaufman | NORTH | 2024-05-10 | SOL | PV | 54.47 |  | 2021-07-01 | 2020-10-07 | 2020-12-28 | 2021-06-28 |  |  |  | No |  |  | Not Required
22INR0427 | BRP Kabru BESS | SS Completed, FIS Started, No IA | BRP Kabru BESS LLC | 1159 Andrew North - 11284 Blackbird 138kV | Andrews | WEST | 2023-07-01 | OTH | BA | 202.45 |  | 2020-09-28 | 2020-10-07 | 2020-12-28 | 2020-09-22 |  | No |  | No |  |  | Not Required
22INR0429 | Sun Valley BESS | SS Completed, FIS Started, No IA | Sun Valley Solar LLC | tap 345kV 68090 Sam Sw - 3405 Tradinghouse | Hill | NORTH | 2023-05-31 | OTH | BA | 101.4 |  | 2021-02-09 | 2020-10-07 | 2020-12-28 | 2021-01-20 |  |  |  | No |  |  | Not Required
22INR0436 | Noble Storage | SS Completed, FIS Completed, IA | BT NOBLE SOLAR, LLC | 1730 Krum West 345kV | Denton | NORTH | 2022-08-15 | OTH | BA | 127 | COD | 2020-11-16 | 2020-10-23 | 2021-01-12 | 2020-11-10 | 2021-11-01 | No | 2021-10-29 | Yes | Not Required | Not Required | Not Required | 2021-11-08 | 2021-11-08 | 2021-11-08 |  |  | 2022-04-27
22INR0437 | TORMES SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY | tap 345kV 1906 Venus - 68091 Navarro | Navarro | NORTH | 2023-12-15 | SOL | PV | 380.65 |  | 2021-07-26 | 2020-10-23 | 2021-01-12 | 2021-07-19 |  |  |  | No |  |  | Not Required
22INR0443 | Bowstring BESS | SS Completed, FIS Started, No IA | Longbow Energy Storage, LLC | 8961 White Point 138kV | San Patricio | COASTAL | 2024-07-15 | OTH | BA | 158.69 |  | 2021-04-01 | 2020-11-18 | 2021-02-09 | 2021-03-24 |  |  |  | No |  |  | Not Required
22INR0444 | Liberty Senate Solar 1 | SS Completed, FIS Started, No IA | Senate Solar LLC | 1445 Burwick 345kV | Jack | NORTH | 2025-03-24 | SOL | PV | 202 |  | 2021-09-16 | 2021-03-01 | 2021-05-13 | 2021-09-10 |  |  |  | No | Not Required | Not Required | Not Required
22INR0445 | SPC Bloom BESS | SS Completed, FIS Started, No IA | Victoria Battery LLC | 8911 Black Bayou 138kV | Victoria | SOUTH | 2023-06-01 | OTH | BA | 100 |  | 2021-02-04 | 2020-12-03 | 2021-02-19 | 2020-11-13 |  |  |  | No |  |  | Not Required
22INR0447 | Beachwood Energy Storage (Mark One BESS) | SS Completed, FIS Started, No IA | Mark One Energy Storage, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2023-11-01 | OTH | BA | 202.32 | COD | 2020-11-25 | 2020-12-03 | 2021-02-19 | 2020-11-25 |  |  |  | No |  |  | Not Required
22INR0449 | Sibyl Energy Storage | SS Completed, FIS Started, No IA | WattBridge Energy, LLC | Tap 138kV 43261 Southwyck - 44552 Telview | Fort Bend | HOUSTON | 2023-08-01 | OTH | BA | 202.32 |  | 2020-11-25 | 2020-12-03 | 2021-02-18 | 2020-11-25 |  |  |  | No |  |  | Not Required
22INR0450 | PRO Energy Storage (PES) | SS Completed, FIS Started, No IA | WattBridge Energy, LLC | 47150 H.O. Clarke 138kV | Harris | HOUSTON | 2023-06-01 | OTH | BA | 100.8 |  | 2020-11-25 | 2021-02-09 | 2021-05-06 | 2020-12-03 |  |  |  | No |  |  | Not Required
22INR0454 | DR Solar | SS Completed, FIS Completed, IA | Chevron USA, Inc | tap 138kV 11112 Chimney Well - 11271 Owl Hill | Culberson | WEST | 2023-06-02 | SOL | PV | 46.02 |  | 2020-11-04 | 2020-12-22 | 2021-03-10 | 2020-12-17 | 2021-12-16 |  | 2022-02-07 | Yes |  |  | Not Required
22INR0455 | Blue Sky Sol | SS Completed, FIS Started, IA | Blue Sky Solar LLC | 6562 Friends Ranch 138kV | Crockett | WEST | 2023-11-24 | SOL | PV | 101.2 |  | 2020-12-09 | 2020-12-03 | 2021-02-16 | 2020-11-10 |  | No | 2022-02-01 | Yes |  |  | Not Required
22INR0457 | Anson BAT | SS Completed, FIS Started, No IA | Anson Solar Center, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2023-12-29 | OTH | BA | 152.39 |  | 2022-03-03 | 2020-12-03 | 2021-02-19 | 2022-02-23 |  |  |  | No |  |  | Not Required
22INR0462 | Old Aqueduct Solar | SS Completed, FIS Started, No IA | Old Aqueduct Solar | 23920 Blackwater 345kV | Hale | PANHANDLE | 2024-03-01 | SOL | PV | 511.63 |  | 2021-07-09 | 2020-12-03 | 2021-02-19 | 2021-06-29 |  |  |  | No |  |  | Not Required
22INR0466 | Pajarita BESS | SS Completed, FIS Started, No IA | VESI 29 LLC | 8266 Marconi 138kV | Cameron | COASTAL | 2024-08-01 | OTH | BA | 205.5 |  | 2021-12-15 | 2021-01-25 | 2021-04-12 | 2021-12-01 |  |  |  | No | Not Required | Not Required | Not Required
22INR0467 | Bird Dog BESS | SS Completed, FIS Started, No IA | VESI 37 LLC | 5668 Mathis 69kV | Live Oak | SOUTH | 2024-08-01 | OTH | BA | 60 | COD | 2022-06-02 | 2021-02-04 | 2021-04-19 | 2022-05-19 |  |  |  | No |  |  | Not Required
22INR0468 | Lower Rio BESS | SS Completed, FIS Started, No IA | VESI 38 LLC | 5792 Sioux 138kV | Hidalgo | SOUTH | 2023-08-01 | OTH | BA | 60 |  | 2021-11-10 | 2021-02-09 | 2021-05-06 | 2021-11-08 |  |  |  | No | Not Required | Not Required | Not Required
22INR0469 | Harper Energy Storage | SS Completed, FIS Started, No IA | VESI 31 LLC | Tap 138kV 8314 La Palma - 80229 Villa Cavazos | Cameron | COASTAL | 2024-06-01 | OTH | BA | 82.42 |  | 2022-02-10 | 2021-12-03 | 2022-03-01 | 2022-01-27 |  |  |  | No |  |  | Not Required
22INR0471 | MARATUA SOLAR | SS Completed, FIS Started, No IA | Abei Energy | tap 345kV 44645 Singleton - 3391 Jewett | Grimes | NORTH | 2024-01-15 | SOL | PV | 217.07 |  | 2021-08-19 | 2020-12-03 | 2021-02-19 | 2021-08-13 |  |  |  | No |  |  | Not Required
22INR0473 | TAIN SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY | tap 138kV 7216 Lockhart - 7224 Luling City | Caldwell | SOUTH | 2024-01-15 | SOL | PV | 37.54 |  | 2021-11-02 | 2020-12-03 | 2021-02-17 | 2021-10-20 |  |  |  | No |  |  | Not Required
22INR0480 | Pachanga Wind | SS Completed, FIS Started, No IA | Pachanga Wind LLC | tap 345kV 5966 Palmito - 80137 Stewart Rd | Cameron | COASTAL | 2024-07-01 | WIN | WT | 300 |  | 2021-06-28 | 2021-02-09 | 2021-05-06 | 2021-04-05 |  |  |  | No |  |  | Not Required
22INR0482 | Rowland Solar II | SS Completed, FIS Started, IA | Cutlass Solar II LLC | tap 345kV 44005 WAP - 44090 Cedar Creek | Fort Bend | HOUSTON | 2023-04-15 | SOL | PV | 202.81 |  | 2020-12-29 | 2020-12-23 | 2017-11-20 | 2020-12-28 |  | No | 2020-09-23 | Yes | Not Required | Not Required | Not Required | 2021-10-27
22INR0485 | House Mountain 2 Batt | SS Completed, FIS Started, IA | House Mountain LLC | 6674 Bronco 69kV | Brewster | WEST | 2023-02-01 | OTH | BA | 63 |  | 2020-12-23 | 2021-01-26 | 2021-04-12 | 2020-12-23 |  |  | 2021-07-07 | Yes | Not Required | Not Required | Not Required | 2022-04-21
22INR0488 | Venture Hill Storage | SS Completed, FIS Started, No IA | KCE TX 24, LLC | 7336 Gilleland Creek 138kV | Travis | SOUTH | 2023-12-01 | OTH | BA | 51.9 |  | 2021-01-08 | 2021-02-09 | 2021-05-06 | 2020-12-29 |  |  |  | No |  |  | Not Required
22INR0489 | Christoval Solar | SS Completed, FIS Started, No IA | Bridgelink Renewable Energy Investments | 76003 Big Hills 345kV | Tom Green | WEST | 2024-06-30 | SOL | PV | 324 |  | 2021-05-07 | 2021-02-04 | 2021-04-19 | 2021-04-30 |  |  |  | No |  |  | Not Required
22INR0490 | Callisto I Energy Center | SS Completed, FIS Started, No IA | Saracen I Energy Storage LLC | 47150 HO Clarke 138kV | Harris | HOUSTON | 2023-10-05 | OTH | BA | 101.52 | Proj Name COD | 2021-03-05 | 2021-03-16 | 2021-05-28 | 2021-03-05 |  |  |  | No |  |  | Not Required
22INR0491 | Callisto II Energy Center | SS Completed, FIS Started, No IA | Saracen II Energy Storage LLC | 47150 HO Clarke 138kV | Harris | HOUSTON | 2023-10-05 | OTH | BA | 101.52 | Proj Name COD | 2021-03-03 | 2021-03-16 | 2021-05-28 | 2021-03-05 |  |  |  | No |  |  | Not Required
22INR0493 | Oscar Storage Project | SS Completed, FIS Started, No IA | Woodlands Energy Renewables LLC | 3413 Knob Creek 345kV | Bell | NORTH | 2024-06-01 | OTH | BA | 50 |  | 2022-06-07 | 2021-03-01 | 2021-05-13 | 2022-05-18 |  |  |  | No |  |  | Not Required
22INR0494 | Quail Run Storage System | SS Completed, FIS Started, No IA | to be determined | 11016 Quail Run Switch 345kV | Ector | WEST | 2023-12-01 | OTH | BA | 50 |  | 2022-01-21 | 2021-02-09 | 2021-05-06 | 2021-12-28 |  |  |  | No | Not Required | Not Required | Not Required
22INR0497 | TEXPO | SS Completed, FIS Completed, No IA | Oklaunion Power Station, LLC | 6100 Oklaunion 345kV | Wilbarger | WEST | 2023-02-15 | GAS | ST | 680 |  | 2021-11-30 | 2021-03-16 | 2021-05-28 | 2021-11-23 | 2022-05-02 | No |  | No | 2022-05-02 |  | 2022-05-02
22INR0499 | Aquilla Lake 3 Wind | SS Completed, FIS Started, No IA | Aquilla Lake 3 Wind | 68090 Sam Switch 345 kV | Hill | NORTH | 2023-10-31 | WIN | WT | 305 |  | 2021-03-05 | 2021-03-08 | 2021-05-28 | 2021-02-18 |  |  |  | No |  |  | Not Required
22INR0502 | Shamrock | SS Completed, FIS Started, IA | SHAMROCK WIND LLC | 76005 Schneeman Draw 345kV | Crockett | WEST | 2023-12-30 | WIN | WT | 310 |  | 2021-02-23 | 2021-03-01 | 2021-05-13 | 2021-02-24 |  |  | 2022-05-13 | No |  |  | Not Required
22INR0503 | Tidwell Prairie II Batt | SS Completed, FIS Started, No IA | TIDWELL PRAIRIE LLC | Tap 345kV 3400 Twin Oak - 39950 TNP One | Robertson | NORTH | 2023-06-01 | OTH | BA | 101.63 |  | 2021-03-02 | 2021-03-16 | 2021-05-28 | 2021-02-17 |  |  |  | No |  |  | Not Required
22INR0504 | Tidwell Prairie III Batt | SS Completed, FIS Started, No IA | Tidwell Prairie LLC | Tap 345kV 3400 Twin Oak - 39950 TNP One | Robertson | NORTH | 2023-06-01 | OTH | BA | 101.63 |  | 2021-03-02 | 2021-03-16 | 2021-05-28 | 2021-02-17 |  |  |  | No |  |  | Not Required
22INR0506 | Roseland Solar II | SS Completed, FIS Completed, IA | Enel Green Power Roseland Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2023-03-01 | SOL | PV | 254 |  | 2018-11-05 | 2021-10-05 |  |  | 2021-10-25 |  | 2020-12-10 | Yes |  |  | Not Required | 2021-10-26 | 2021-10-26 | 2021-10-26 |  |  | 2022-06-07
22INR0509 | Turquoise Storage | SS Completed, FIS Completed, IA | BT Cunningham Storage, LLC | 6950 Wallace Switch 138kV | Hunt | NORTH | 2022-12-31 | OTH | BA | 196.21 |  | 2021-03-19 | 2021-03-18 | 2021-06-11 | 2021-03-18 | 2022-04-04 | No | 2021-10-22 | Yes |  |  | Not Required | 2022-04-27 | 2022-04-27 | 2022-04-27
22INR0511 | Gransolar Texas One | SS Completed, FIS Completed, IA | Gransolar Texas One, LLC | Tap 138kV 3659 Thorndale North - 116 Salty | Milam | SOUTH | 2023-11-23 | SOL | PV | 60.86 |  | 2021-03-10 | 2021-03-16 | 2021-06-11 | 2021-03-08 | 2022-01-24 |  | 2022-02-09 | No |  |  | Not Required
22INR0515 | Flagtail BESS | SS Completed, FIS Started, No IA | Flagtail LLC | Tap 138kV 5 Sandy Switch - 7 Sandy | Grimes | NORTH | 2023-03-01 | OTH | BA | 203.8 |  | 2021-03-15 | 2021-04-05 | 2021-06-24 | 2021-03-15 |  |  |  | No |  |  | Not Required
22INR0516 | Amber Storage | SS Completed, FIS Started, No IA | Belltown Power Texas | 730 Wolf Ridge 138kV | Cooke | NORTH | 2023-12-31 | OTH | BA | 50 | COD | 2021-03-19 | 2021-03-19 | 2021-06-11 | 2021-03-19 |  | No |  | No | Not Required | Not Required | Not Required
22INR0517 | Ray Gulf Wind | SS Completed, FIS Started, IA | Lane City Wind, LLC | 44040 Bailey 345kV | Wharton | SOUTH | 2022-12-31 | WIN | WT | 207 |  | 2021-05-05 | 2021-04-26 | 2021-07-28 | 2021-04-26 |  | No | 2022-05-13 | No | Not Required | Not Required | Not Required
22INR0523 | Midlothian 4 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1940 Midlothian ANP 345kV | Ellis | NORTH | 2022-08-01 | GAS | CC | 18 |  | 2021-04-28 | 2021-04-26 | 2021-07-28 | 2021-04-21 |  |  |  | No
22INR0524 | St. Gall I Energy Storage | SS Completed, FIS Completed, No IA | St. Gall Energy Storage LLC | 38355 TNLeon Creek 138kV | Pecos | WEST | 2023-05-01 | OTH | BA | 127.4 |  | 2021-04-15 | 2021-04-13 | 2021-07-02 | 2021-04-08 | 2022-04-11 | No |  | No | Not Required | Not Required | Not Required
22INR0525 | St. Gall II Energy Storage | SS Completed, FIS Completed, No IA | St. Gall Energy Storage LLC | 38355 TNLeon Creek 138kV | Pecos | WEST | 2023-06-01 | OTH | BA | 127.4 |  | 2021-04-15 | 2021-04-13 | 2021-07-02 | 2021-04-08 | 2022-04-11 | No |  | No |  |  | Not Required
22INR0526 | Pine Forest BESS | SS Completed, FIS Started, No IA | Pine Forest Hybrid I, LLC | tap 345kV 1696 Monticello SES - 2514 Allen Switch | Hopkins | NORTH | 2024-01-15 | OTH | BA | 421 | MW Size | 2021-07-30 | 2021-05-04 | 2021-07-30 | 2021-07-19 |  |  |  | No |  |  | Not Required
22INR0527 | Lily Solar (Close Boze - I20 - Rosehill) | SS Completed, FIS Completed, IA | Lily Solar, LLC | 6903 Boze Switch (Close Path to Rosehill via I20_RC) | Kaufman | NORTH | 2022-12-31 | SOL | PV | 0 |  | 2021-05-05 | 2021-05-10 | 2021-05-17 | 2021-04-29 | 2022-05-02 |  | 2019-03-29 | Yes | Not Required | Not Required | Not Required | 2022-05-02 | 2022-05-02 | 2022-05-02 |  |  |  |  | This project is for the purposes of studying a different transmission configuration for the facility study and isn't actually an interconnection request. No additional MWs added. Refer to 19INR0044, Lily Solar.
22INR0528 | Lily Storage (Close Boze - I20 - Rosehill) | SS Completed, FIS Completed, IA | Lily Solar, LLC | 6903 Boze Switch (Close Path to Rosehill via I20_RC) | Kaufman | NORTH | 2022-12-31 | OTH | BA | 0 |  | 2021-05-05 | 2021-05-10 | 2021-05-17 | 2021-04-29 | 2022-05-02 |  | 2019-03-29 | Yes |  |  | Not Required | 2022-05-02 | 2022-05-02 | 2022-05-02 |  |  |  |  | This project is for the purposes of studying a different transmission configuration for the facility study and isn't actually an interconnection request. No additional MWs added. Refer to 20INR0294, Lily Storage.
22INR0533 | Temple Generation I Repower | SS Completed, FIS Completed, IA | Panda Temple Power | 3413 Knob Creek 345kV | Bell | NORTH | 2022-06-15 | GAS | CC | 67 |  | 2021-04-26 | 2021-04-26 | 2021-05-13 | 2021-04-22 | 2021-09-30 |  | 2012-06-21 | Yes |  |  |  | 2021-10-26 | 2021-10-26 | 2021-10-26
22INR0535 | Bastrop Energy Center AGP repower Phase II | SS Completed, FIS Completed, IA | Bastrop Energy Partners, LP | 7049 Bastrop 345kV | Bastrop | SOUTH | 2022-07-15 | GAS | CC | 21 |  | 2021-06-17 | 2021-04-26 | 2021-07-28 | 2021-06-14 | 2021-10-29 |  | 2000-09-20 | No |  |  |  | 2021-10-28 | 2021-10-28 | 2021-11-01 |  |  |  | 2022-04-27
22INR0540 | Walstrom BESS | SS Completed, FIS Started, No IA | Castleman Power | 46220 Peters 138kV | Austin | SOUTH | 2024-03-01 | OTH | BA | 200 |  | 2021-05-17 | 2021-07-08 | 2021-10-04 | 2021-06-03 |  |  |  | No |  |  | Not Required
22INR0541 | ALWEST BESS | SS Completed, FIS Started, No IA | Castleman Power | 3114 Paltalco 138kV | Anderson | NORTH | 2024-02-01 | OTH | BA | 208.63 |  | 2021-05-17 | 2021-08-24 | 2021-11-15 | 2021-06-03 |  |  |  | No |  |  | Not Required
22INR0543 | Midlothian Unit 3 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1940 Midlothian ELP 345kV | Ellis | NORTH | 2022-08-01 | GAS | CC | 18 |  | 2021-05-21 | 2021-05-24 | 2021-08-06 | 2021-05-11 |  |  |  | No
22INR0549 | Tanzanite Storage | SS Completed, FIS Completed, No IA | Belltown Power Texas | 6867 NORTH ATHENS 138kV | Henderson | NORTH | 2023-12-31 | OTH | BA | 257.72 | COD | 2021-07-27 | 2021-09-01 | 2021-11-18 | 2021-08-16 | 2022-02-09 | No |  | No | Not Required | Not Required | Not Required
22INR0550 | BLUE SUMMIT I REPOWER | SS Completed, FIS Completed, No IA | Blue Summit Wind LLC | 61001 JIM TREECE 345kV | Wilbarger | WEST | 2022-12-31 | WIN | WT | 4.4 |  | 2021-08-27 | 2021-11-01 | 2022-01-28 | 2021-09-27 | 2022-04-29 |  |  | No | Not Required | Not Required | Not Required | 2022-04-29 | 2022-04-29 | 2022-05-02
22INR0551 | Wolf Tank Storage | SS Completed, FIS Completed, IA | Lobo Storage | 80221 LOBO 138kV | Webb | SOUTH | 2022-12-01 | OTH | BA | 155.48 |  | 2021-08-25 | 2021-07-28 | 2021-10-11 | 2021-08-24 | 2022-04-29 | No | 2021-11-04 | Yes | Not Required | Not Required | Not Required | 2022-04-29 | 2022-04-29 | 2022-04-29
22INR0552 | Sowers Storage | SS Completed, FIS Completed, IA | Belltown Power Texas | 6894 Rose Hill_RC Sub 138 kV | Kaufman | NORTH | 2023-09-30 | OTH | BA | 203 | COD | 2021-08-17 | 2021-08-18 | 2021-11-05 | 2021-08-18 | 2021-12-17 | No | 2022-04-22 | No | Not Required | Not Required | Not Required
22INR0553 | Amethyst Storage | SS Completed, FIS Started, No IA | Belltown Power Texas | 6865 FORNEY WEST_RC 138kV | Kaufman | NORTH | 2023-12-31 | OTH | BA | 303.5 | COD | 2021-08-20 | 2021-08-30 | 2021-11-18 | 2021-08-26 |  |  |  | No | Not Required | Not Required | Not Required
22INR0554 | Platinum Storage | SS Completed, FIS Started, No IA | Belltown Power Texas | 1729 Valley South 345kV | Fannin | NORTH | 2023-12-31 | OTH | BA | 303.5 |  | 2021-08-20 | 2021-09-02 | 2021-11-18 | 2021-08-31 |  |  |  | No | Not Required | Not Required | Not Required
22INR0555 | Guevara Storage | SS Completed, FIS Started, No IA | Belltown Power Texas | 2483 Royse Switch 345kV | Rockwall | NORTH | 2023-12-31 | OTH | BA | 405 |  | 2021-08-24 | 2021-09-02 | 2021-11-18 | 2021-08-26 |  |  |  | No | Not Required | Not Required | Not Required
22INR0558 | Saracen III Energy Storage | SS Completed, FIS Started, No IA | Saracen III Energy Storage LLC | 47150 HO Clarke 138kV | Harris | HOUSTON | 2023-12-01 | OTH | BA | 406.08 |  | 2021-10-07 | 2021-10-07 | 2021-12-08 | 2021-09-29 |  |  |  | No |  |  | Not Required
22INR0559 | Honeycomb Solar | SS Completed, FIS Started, No IA | Tynan Solar, LLC | 69 kV Tynan Substation (#8107) | Bee | SOUTH | 2024-06-01 | SOL | PV | 61.1 | COD | 2021-10-26 | 2021-11-16 | 2022-01-17 | 2021-11-02 |  |  |  | No | Not Required | Not Required | Not Required
22INR0562 | Anchor Wind IV | SS Completed, FIS Completed, IA | Ranchland Wind Project,LLC | 345 kV Aspire Station (68011) | Eastland | NORTH | 2022-08-03 | WIN | WT | 19.32 | SFS/NtP | 2019-06-26 | 2021-12-03 | 2022-03-01 |  | 2021-04-30 |  | 2020-11-30 | Yes | Not Required | Not Required | Not Required | 2021-04-30 | 2021-04-30 | 2021-04-30 |  |  | 2021-11-29 | 2022-05-05
22INR0592 | Cross Trails Gravitational Storage | SS Started, FIS Started, No IA | Cross Trails Energy Storage Project, LLC | 60090 WKN Breaker 69kV | Scurry | WEST | 2023-12-31 | OTH | EN | 18.03 | MW Size | 2022-05-04 | 2022-05-10 |  | 2022-05-04 |  |  |  | No
22INR0598 | Noble Storage (BESS1) | SS Completed, FIS Completed, IA | BT Noble Solar, LLC | 1730 Krum West 345kV | Denton | NORTH | 2022-08-15 | OTH | BA | 62.5 | Proj Name COD | 2020-11-16 | 2022-04-15 | 2021-01-12 |  | 2021-11-01 |  | 2021-10-29 | No | Not Required | Not Required | Not Required |  |  | 2021-11-08
23INR0006 | Sierra Madre Solar | SS Completed, FIS Started, No IA | Rancho Verde Solar | tap 345kV 80307 Del Sol - 80225 Cenizo | Zapata | SOUTH | 2025-12-01 | SOL | PV | 255.15 |  | 2020-10-07 | 2020-01-22 | 2020-04-08 | 2020-10-05 |  |  |  | No |  |  | Not Required
23INR0007 | Outpost Solar | SS Completed, FIS Started, IA | Hecate Energy Outpost Solar LLC | Tap 345kV 80219 Lobo - 5709 Fowlerton | Webb | SOUTH | 2024-04-01 | SOL | PV | 513.7 |  | 2020-02-11 | 2019-12-06 | 2020-02-25 | 2019-12-02 |  |  | 2022-01-11 | No |  |  | Not Required
23INR0008 | Harley Hand Solar | SS Completed, FIS Started, No IA | HECTATE ENERGY HARLEY HAND SOLAR LLC | 11420 Sweetwater East 345kV | Nolan | WEST | 2024-12-01 | SOL | PV | 513.7 | COD | 2019-12-12 | 2019-12-16 | 2020-03-11 | 2019-12-06 |  | No |  | No | Not Required | Not Required | Not Required
23INR0009 | Shaula III Solar | SS Completed, FIS Started, No IA | Shaula Energy Project III, LLC | tap 345kV 5133 Elm Creek - 5323 Old Hickory ckt 2 | DeWitt | SOUTH | 2025-12-24 | SOL | PV | 205.2 |  | 2020-01-13 | 2019-12-18 | 2020-03-11 | 2019-12-18 |  |  |  | No |  |  | Not Required
23INR0010 | Plateau Solar | SS Completed, FIS Completed, No IA | Innovative Solar 206, LLC | tap 345kV 68000 West Shackelford - 68001 Claytonville | Jones | WEST | 2024-03-14 | SOL | PV | 300 |  | 2020-09-04 | 2019-12-06 | 2020-02-25 | 2020-08-20 | 2022-03-22 | No |  | No | Not Required | Not Required | Not Required
23INR0014 | Hedgehog Solar | SS Completed, FIS Started, No IA | Innovative Solar 408, LLC | tap 138kV 8234 Uvalde - 8241 Razorback | Medina | SOUTH | 2024-05-24 | SOL | PV | 85 |  | 2020-09-16 | 2019-12-11 | 2020-03-06 | 2020-08-31 |  |  |  | No |  |  | Not Required
23INR0015 | Scarlet Solar | SS Completed, FIS Started, No IA | Innovative Solar 416, LLC | tap 345kV 23912 Ogallala - 23910 Windmill | Castro | PANHANDLE | 2024-05-28 | SOL | PV | 180 |  | 2020-09-16 | 2019-12-11 | 2020-03-06 | 2020-08-31 |  |  |  | No |  |  | Not Required
23INR0019 | Blue Jay BESS | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 IOLA 138kV | Grimes | NORTH | 2022-11-17 | OTH | BA | 51.63 |  | 2021-04-15 | 2020-01-06 | 2020-03-30 | 2021-04-05 | 2022-01-31 | No | 2022-01-24 | Yes |  |  | Not Required | 2022-01-31 | 2022-01-31 | 2022-01-31
23INR0021 | Hornet Solar | SS Completed, FIS Completed, IA | Hornet Solar LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala | Swisher | PANHANDLE | 2023-12-31 | SOL | PV | 611 | MW Size | 2020-05-15 | 2020-02-04 | 2020-04-29 | 2020-02-04 | 2021-10-06 | No | 2021-12-06 | Yes |  |  | Not Required
23INR0026 | Baker Branch Solar | SS Completed, FIS Completed, IA | Mockingbird Solar Center, LLC | tap 345kV 1692 Paris - 1690 Valley | Lamar | NORTH | 2023-12-30 | SOL | PV | 400 | SFS/NtP | 2020-04-09 | 2020-03-26 | 2020-06-04 | 2020-03-05 | 2022-04-05 |  | 2022-02-14 | Yes |  |  | Not Required
23INR0027 | Cachena Solar SLF | SS Completed, FIS Started, IA | Clear Fork Creek Solar LLC | Tap 345kV 5915 STP - 5133 Elm Creek ckt 2 | Wilson | SOUTH | 2024-06-01 | SOL | PV | 440 |  | 2020-08-19 | 2020-05-01 | 2020-07-13 | 2020-08-17 |  |  | 2021-11-23 | Yes | Not Required | Not Required | Not Required | 2021-11-29
23INR0029 | Cedar Bayou5 | SS Completed, FIS Started, IA | NRG Cedar Bayou 5 LLC | 40000 Cedar Bayou 345kV | Chambers | HOUSTON | 2023-06-01 | GAS | CC | 697 |  | 2020-03-31 | 2020-03-26 | 2020-06-04 | 2020-03-18 |  | No | 2022-01-10 | No
23INR0030 | Langer Solar | SS Completed, FIS Started, No IA | Langer Solar LLC | tap 345kV 68040 Kopperl - 68091 Navarro | Bosque | NORTH | 2024-01-11 | SOL | PV | 249.8 |  | 2020-11-06 | 2020-06-03 | 2020-08-18 | 2020-10-30 |  |  |  | No |  |  | Not Required
23INR0031 | Solace Solar | SS Completed, FIS Completed, No IA | IP QUANTUM, LLC. | tap 345kV 1430 Graham - 1048 Tonkawas | Haskell | WEST | 2023-05-31 | SOL | PV | 374.4 |  | 2020-04-21 | 2020-04-22 | 2020-07-09 | 2020-04-03 | 2021-03-02 |  |  | No |  |  | Not Required
23INR0035 | Starling Solar | SS Completed, FIS Started, IA | Starling Solar, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2023-10-30 | SOL | PV | 123 |  | 2021-02-09 | 2020-06-26 | 2020-09-14 | 2021-01-22 |  |  | 2021-12-03 | No |  |  | Not Required
23INR0040 | Dori BQ Solar | SS Completed, FIS Completed, No IA | Sunnyside Energy, LLC | tap 138kV 47210 Holmes – 42680 Garden Villas | Harris | HOUSTON | 2023-07-01 | SOL | PV | 50.42 |  | 2021-02-10 | 2020-06-09 | 2020-08-18 | 2021-01-29 | 2022-04-26 | Yes |  | No | Not Required | Not Required | Not Required
23INR0042 | Delilah Solar 3 | SS Completed, FIS Completed, IA | Delilah Solar Energy III LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 |  | 2019-05-13 | 2020-06-03 | 2018-01-03 |  | 2020-06-09 |  | 2020-12-22 | Yes |  |  | Not Required | 2021-03-23
23INR0044 | Parliament Solar | SS Completed, FIS Started, IA | AP Solar 8, LLC | Tap 345kV 44900 Zenith - 967 Gibbons Creek ckt 18 | Waller | HOUSTON | 2023-12-04 | SOL | PV | 482.69 |  | 2020-08-03 | 2020-06-19 | 2020-09-08 | 2020-06-08 |  | No | 2022-05-26 | No | Not Required | Not Required | Not Required
23INR0045 | GP Solar | SS Completed, FIS Completed, IA | HEP Aquamarine Holdings LLC | Tap 138kV 6829 Glen Pine - 6833 Explorer | Van Zandt | NORTH | 2023-06-01 | SOL | PV | 121.97 |  | 2016-02-23 | 2020-09-25 | 2020-12-16 | 2021-02-22 | 2021-11-10 | No | 2021-12-29 | Yes |  |  | Not Required | 2021-12-13 | 2021-12-13
23INR0047 | Charger Solar | SS Completed, FIS Completed, IA | AP Solar 4, LLC | tap 345kV 8249 Angstrom – 5915 STP | Refugio | COASTAL | 2023-03-31 | SOL | PV | 406.77 |  | 2020-07-29 | 2020-06-19 | 2020-09-08 | 2020-06-07 | 2022-04-04 | No | 2021-06-05 | Yes |  |  | Not Required | 2022-04-04
23INR0048 | Equinox Storage | SS Completed, FIS Started, No IA | Invenergy Storage Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2025-12-31 | OTH | BA | 101.2 |  | 2021-03-23 | 2020-06-26 | 2020-09-14 | 2021-03-12 |  |  |  | No |  |  | Not Required
23INR0054 | Tanglewood Solar | SS Completed, FIS Completed, No IA | Brazoria Solar, LLC | tap 345kV 42500 Dow - 43035 Oasis | Brazoria | COASTAL | 2023-10-01 | SOL | PV | 257 |  | 2021-01-15 | 2020-07-10 | 2020-09-28 | 2020-11-24 | 2022-03-22 | Yes |  | No |  |  | Not Required
23INR0055 | Tabor Solar | SS Completed, FIS Started, No IA | Quanah Solar LLC | Tap 345kV 60504 Tesla - 61001 Jim Treece | Hardeman | WEST | 2024-05-01 | SOL | PV | 506.4 |  | 2020-08-31 | 2020-09-02 | 2020-11-19 | 2020-07-07 |  | No |  | No |  |  | Not Required
23INR0056 | Caliche Mound Solar | SS Completed, FIS Started, No IA | Tierra Blanco Solar LLC | tap 345kV 23906 AJSwope - 23910 Windmill | Deaf Smith | PANHANDLE | 2024-05-13 | SOL | PV | 408.21 |  | 2020-08-27 | 2020-07-24 | 2020-09-08 | 2020-07-07 |  |  |  | No |  |  | Not Required
23INR0057 | Duffy Solar | SS Completed, FIS Completed, No IA | VDA Solar Texas 1 LLC | Tap 345kV 44200 Hilje and 5915 STP c64 | Matagorda | COASTAL | 2025-05-31 | SOL | PV | 545.21 |  | 2021-02-05 | 2020-09-11 | 2020-11-19 | 2021-02-04 | 2022-01-05 | Yes |  | No |  |  | Not Required
23INR0058 | Erin Solar | SS Completed, FIS Completed, No IA | Erin Solar LLC | 44040 Bailey 345 kV | Wharton | SOUTH | 2025-05-31 | SOL | PV | 202.5 |  | 2021-02-15 | 2020-07-24 | 2020-10-08 | 2021-01-26 | 2022-05-24 | No |  | No | Not Required | Not Required | Not Required
23INR0059 | Briggs Solar | SS Completed, FIS Started, No IA | Briggs Solar, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2024-05-31 | SOL | PV | 309.6 |  | 2021-03-15 | 2020-08-04 | 2020-10-28 | 2021-03-04 |  |  |  | No |  |  | Not Required
23INR0060 | Delilah Solar 4 | SS Completed, FIS Completed, IA | Delilah Solar Energy IV LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2023-06-30 | SOL | PV | 90 |  | 2019-05-13 | 2020-07-31 | 2019-01-03 |  | 2020-06-09 |  | 2020-12-22 | Yes | Not Required | Not Required | Not Required | 2021-03-23
23INR0061 | Noria Solar DCC | SS Completed, FIS Started, No IA | Noria Hondo Solar, LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2024-09-01 | SOL | PV | 145 |  | 2021-03-15 | 2020-08-04 | 2020-10-28 | 2021-03-10 |  |  |  | No |  |  | Not Required
23INR0062 | Noria Storage | SS Completed, FIS Started, No IA | Noria Hondo Solar, LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2024-09-01 | OTH | BA | 75 |  | 2021-04-01 | 2020-08-04 | 2020-10-28 | 2021-03-30 |  |  |  | No |  |  | Not Required
23INR0065 | Bonita Creek Solar | SS Completed, FIS Started, No IA | Invenergy Solar Development North America LLC | tap 345kV 5133 Elm Creek - 5901 San Miguel | Atascosa | SOUTH | 2025-12-31 | SOL | PV | 200 |  | 2021-07-16 | 2020-12-03 | 2021-03-10 | 2021-06-16 |  |  |  | No |  |  | Not Required
23INR0066 | Accalia Point Solar | SS Completed, FIS Started, No IA | Accalia Point Solar LLC | Tap 345kV 79500 Palmito - 80137 Stewart | Cameron | COASTAL | 2025-05-31 | SOL | PV | 190.5 |  | 2021-02-10 | 2020-10-23 | 2021-01-12 | 2021-01-27 |  |  |  | No |  |  | Not Required
23INR0069 | Corbin Grid BESS | SS Completed, FIS Completed, No IA | Corbin Grid, LLC | 44510 Obrien 138kV | Fort Bend | HOUSTON | 2023-05-31 | OTH | BA | 202.76 | Status Change INA-to-PLN | 2020-08-28 | 2020-08-04 | 2020-11-02 | 2020-07-24 | 2021-04-30 |  |  | No | Not Required | Not Required | Not Required
23INR0070 | Chillingham Solar | SS Completed, FIS Completed, IA | 250LB 8me | 3687 Bell County East 345kV | Bell | NORTH | 2023-09-19 | SOL | PV | 359.37 |  | 2020-09-02 | 2020-08-04 | 2020-10-28 | 2020-08-26 | 2021-07-22 |  | 2022-02-04 | No | Not Required | Not Required | Not Required
23INR0071 | BRP Volans BESS | SS Completed, FIS Completed, No IA | BRP Volans BESS LLC | 11189 Quarry Field SW - 1074 Wink 138kV | Winkler | WEST | 2024-12-01 | OTH | BA | 206.88 |  | 2020-08-26 | 2020-08-04 | 2020-10-28 | 2020-08-24 | 2021-10-11 | No |  | No |  |  | Not Required
23INR0072 | BRP Tortolas BESS | SS Completed, FIS Completed, IA | BRP Tortolas BESS LLC | 39030 Alvin 138kV | Brazoria | COASTAL | 2023-03-15 | OTH | BA | 50.67 |  | 2020-08-27 | 2020-08-04 | 2020-10-28 | 2020-08-24 | 2021-07-30 |  | 2021-07-15 | Yes | Not Required | Not Required | Not Required | 2021-07-30 | 2021-07-30 | 2021-07-30
23INR0073 | BRP Galan BESS | SS Completed, FIS Started, No IA | BRP Galan BESS LLC | 5007 Alamo One 138kV | Bexar | SOUTH | 2023-03-31 | OTH | BA | 75.97 |  | 2020-08-20 | 2020-08-04 | 2020-10-28 | 2020-08-17 |  |  |  | No |  |  | Not Required
23INR0074 | BRP Ampato BESS | SS Completed, FIS Started, No IA | BRP Ampato BESS LLC | 10002 NS Crane Switch 138kV | Crane | WEST | 2023-03-31 | OTH | BA | 121.56 |  | 2020-08-26 | 2020-08-04 | 2020-10-28 | 2020-08-24 |  |  |  | No |  |  | Not Required
23INR0075 | BRP Rhine BESS | SS Completed, FIS Completed, No IA | BRP Rhine BESS LLC | Tap 345kV 11188 QUARRYFLD - 11010 WOLF | Ward | WEST | 2024-08-01 | OTH | BA | 206.89 |  | 2020-09-22 | 2020-08-04 | 2020-11-02 | 2020-09-17 | 2021-09-29 |  |  | No |  |  | Not Required
23INR0076 | Cannon Solar SLF | SS Completed, FIS Started, No IA | Cannon Solar, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2024-12-01 | SOL | PV | 152.5 |  | 2020-09-21 | 2020-09-11 | 2020-12-07 | 2020-09-11 |  |  |  | No | Not Required | Not Required | Not Required
23INR0077 | Cachena Storage SLF | SS Completed, FIS Started, No IA | Clear Fork Creek Solar LLC | Tap 345kV 5915 STP - 5133 Elm Creek ckt 2 | Wilson | SOUTH | 2024-06-01 | OTH | BA | 0 |  | 2020-08-21 | 2020-08-21 | 2020-10-16 | 2020-08-17 |  |  |  | No |  |  | Not Required
23INR0078 | Shaw Solar | SS Completed, FIS Started, No IA | Montague Solar, LLC | Tap 138kV 7146 Verde Creek - 7438 Bandera | Bandera | SOUTH | 2023-10-31 | SOL | PV | 123 |  | 2021-05-21 | 2020-10-23 | 2021-01-12 | 2021-05-11 |  |  |  | No |  |  | Not Required
23INR0079 | Chillingham Storage | SS Completed, FIS Completed, IA | 250LB 8me | 3687 Bell County East 345kV | Bell | NORTH | 2023-09-19 | OTH | BA | 153.75 |  | 2020-09-04 | 2020-09-11 | 2020-11-30 | 2020-08-26 | 2021-07-22 |  | 2022-02-04 | No | Not Required | Not Required | Not Required
23INR0080 | Soda Lake Solar 1 | SS Completed, FIS Started, No IA | Crane Solar Generating 2 | 76026 Soda Lake 138kV | Crane | WEST | 2023-05-22 | SOL | PV | 202.59 |  | 2020-09-08 | 2020-09-11 | 2020-11-30 | 2020-08-24 |  |  |  | No |  |  | Not Required
23INR0082 | Bottom Grass Solar | SS Completed, FIS Started, No IA | Bottom Grass Solar Project, LLC | tap 345 kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2024-03-01 | SOL | PV | 508.61 |  | 2020-10-19 | 2020-11-05 | 2021-02-02 | 2020-10-21 |  |  |  | No |  |  | Not Required
23INR0083 | Bottom Grass BESS | SS Completed, FIS Started, No IA | Bottom Grass Solar Project, LLC | tap 345 kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2024-03-01 | OTH | BA | 202.21 |  | 2020-10-19 | 2020-11-05 | 2021-02-02 | 2020-10-21 |  |  |  | No |  |  | Not Required
23INR0084 | Lavaca Bay Solar | SS Completed, FIS Completed, No IA | Lavaca Bay Solar Project LLC | tap 345 kV REFUGE 42400 - JONES CREEK 47532 ckt 27 | Matagorda | COASTAL | 2023-08-15 | SOL | PV | 243.46 |  | 2021-03-05 | 2020-09-11 | 2020-11-19 | 2021-03-05 | 2022-03-21 | Yes |  | No |  |  | Not Required
23INR0086 | Hanson Solar | SS Completed, FIS Started, No IA | Hanson Solar, LLC | tap 345kV 1444 Brown - 11406 Central Bluff | Coleman | WEST | 2024-05-31 | SOL | PV | 396 |  | 2021-03-30 | 2020-10-23 | 2021-02-02 | 2021-03-25 |  |  |  | No |  |  | Not Required
23INR0087 | Kinenos Solar | SS Completed, FIS Started, No IA | Encino del Sol Energy, LLC | tap 345kV 8905 North Edinburg - 8455 Lon Hill | Brooks | SOUTH | 2023-12-31 | SOL | PV | 203.17 |  | 2020-08-28 | 2020-12-22 | 2021-03-10 | 2020-12-03 |  | No |  | No |  |  | Not Required
23INR0088 | Nockenut Springs Solar 1 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Guadalupe | SOUTH | 2023-12-31 | SOL | PV | 203.17 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No |  |  | Not Required
23INR0089 | Donegal Solar | SS Completed, FIS Started, No IA | HE-Cottonwood Solar, LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2024-11-30 | SOL | PV | 204.2 | COD | 2020-10-08 | 2020-10-07 | 2020-12-28 | 2020-09-11 |  |  |  | No |  |  | Not Required
23INR0090 | Iguala Solar | SS Completed, FIS Started, No IA | Igualla LLC | tap 345kV 5915 STP - 8249 Angstrom | Victoria | SOUTH | 2023-06-01 | SOL | PV | 250 |  | 2021-06-11 | 2020-10-07 | 2020-12-28 | 2021-06-07 |  |  |  | No |  |  | Not Required
23INR0091 | Cascade Solar | SS Completed, FIS Completed, No IA | Oyster Creek LLC | tap 345kV 42500 Dow - 43035 Oasis Ckt 18 | Brazoria | COASTAL | 2024-12-31 | SOL | PV | 254.2 |  | 2021-05-05 | 2021-02-09 | 2021-05-06 | 2021-04-28 | 2021-12-06 | No |  | No |  |  | Not Required
23INR0093 | Alila Solar | SS Completed, FIS Started, No IA | Electra Energy Project, LLC | 8249 Angstrom 345kV | San Patricio | COASTAL | 2024-05-03 | SOL | PV | 256.5 |  | 2020-10-19 | 2020-10-07 | 2020-12-30 | 2020-09-11 |  |  |  | No |  |  | Not Required
23INR0094 | BRP Pyxis BESS | SS Completed, FIS Completed, No IA | BRP Pyxis BESS LLC | tap 138kV 1009 Yucca - 11197 Sand Tank Pod | Ward | WEST | 2024-08-01 | OTH | BA | 206.87 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 | 2021-09-23 |  |  | No |  |  | Not Required
23INR0095 | Brotman Power Station | SS Completed, FIS Completed, No IA | Brotman Generating, LLC | tap 138kV 44600 Rosharon - 44410 Karsten | Brazoria | COASTAL | 2023-06-01 | GAS | GT | 398.24 |  | 2020-10-09 | 2020-10-23 | 2021-02-02 | 2020-10-06 | 2022-06-13 | No |  | No | 2021-02-09 |  | 2021-09-22
23INR0100 | Evergreen Solar | SS Completed, FIS Started, No IA | Bucks Bayou LLC | 8111 Magilla 138kV | Matagorda | COASTAL | 2023-12-29 | SOL | PV | 150 |  | 2021-07-02 | 2020-12-03 | 2021-02-18 | 2021-06-07 |  |  |  | No |  |  | Not Required
23INR0101 | Atria Solar | SS Completed, FIS Completed, No IA | Atria Energy Project, LLC | 40770 Hacher 138kV | Chambers | HOUSTON | 2024-01-25 | SOL | PV | 112.4 |  | 2020-10-19 | 2020-10-23 | 2021-01-12 | 2020-09-28 | 2021-12-15 |  |  | No |  |  | Not Required
23INR0103 | Donegal BESS | SS Completed, FIS Started, No IA | HE-Cottonwood Solar, LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2024-11-30 | OTH | BA | 101.3 | COD | 2020-10-12 | 2020-10-23 | 2021-01-12 | 2020-09-28 |  |  |  | No |  |  | Not Required
23INR0104 | BRP Kamet BESS | SS Completed, FIS Started, No IA | BRP Kamet BESS LLC | Andrews North – McKenzie Draw Switch 138 kV | Andrews | WEST | 2023-08-01 | OTH | BA | 202.46 |  | 2020-09-28 | 2020-10-07 | 2020-12-30 | 2020-09-23 |  | No |  | No |  |  | Not Required
23INR0111 | GULF STAR SOLAR SLF | SS Completed, FIS Started, IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2023-11-15 | SOL | PV | 451.6 |  | 2020-12-03 | 2020-10-23 | 2021-02-02 | 2020-11-24 |  | No | 2021-10-01 | Yes |  |  | Not Required | 2021-11-05
23INR0113 | Cannon Storage SLF | SS Completed, FIS Started, No IA | Cannon Solar, LLC | Tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2024-12-01 | OTH | BA | 0 |  | 2020-10-19 | 2020-11-05 | 2020-12-07 | 2020-10-29 |  |  |  | No | Not Required | Not Required | Not Required
23INR0114 | True North Solar | SS Completed, FIS Started, No IA | Aurora Solar LLC | tap 345kV 3399 Ratsnake - 3390 Jewett | Falls | NORTH | 2024-05-31 | SOL | PV | 240 |  | 2021-09-27 | 2021-01-25 | 2021-04-12 | 2021-09-21 |  |  |  | No |  |  | Not Required
23INR0115 | BRP Pobeda BESS | SS Completed, FIS Started, No IA | BRP Pobeda BESS LLC | 44645 Singleton 345kV | Grimes | NORTH | 2023-12-01 | OTH | BA | 301.41 | MW Size | 2020-11-06 | 2020-11-18 | 2021-02-08 | 2020-10-27 |  |  |  | No |  |  | Not Required
23INR0116 | Cantaloupe Solar | SS Completed, FIS Started, No IA | Saragosa Del Sol Energy, LLC | 60716 Saragosa 138kV | Reeves | WEST | 2023-12-01 | SOL | PV | 303.13 |  | 2020-10-28 | 2020-12-22 | 2021-03-09 | 2020-12-01 |  |  |  | No | Not Required | Not Required | Not Required
23INR0117 | Cantaloupe Storage | SS Completed, FIS Started, No IA | Saragosa Del Sol Energy, LLC | 60716 Saragosa 138kV | Reeves | WEST | 2023-12-01 | OTH | BA | 251.05 |  | 2020-10-28 | 2020-12-22 | 2021-03-09 | 2020-12-01 |  |  |  | No | Not Required | Not Required | Not Required
23INR0118 | Blevins Solar | SS Completed, FIS Started, No IA | Blevins Solar, LLC | tap 345kV 3414 Temple Switch - 3409 Lake Creek | Falls | NORTH | 2025-06-01 | SOL | PV | 304.5 | COD | 2021-02-18 | 2021-02-04 | 2021-04-19 | 2021-02-12 |  |  |  | No |  |  | Not Required
23INR0119 | Blevins Storage | SS Completed, FIS Started, No IA | Blevins Solar, LLC | tap 345kV 3414 Temple Switch - 3409 Lake Creek | Falls | NORTH | 2025-06-01 | OTH | BA | 182.4 | COD | 2021-02-19 | 2021-02-04 | 2021-04-19 | 2021-02-12 |  |  |  | No |  |  | Not Required
23INR0123 | Vaca Storage | SS Completed, FIS Started, No IA | Long Mount Storage, LLC | tap 138kV 8140 Joslin - 8155 Sand Crab | Calhoun | COASTAL | 2025-06-01 | OTH | BA | 101 |  | 2022-06-01 | 2021-03-26 | 2021-06-14 | 2022-05-11 |  |  |  | No | Not Required | Not Required | Not Required
23INR0124 | Coral Storage | SS Completed, FIS Started, No IA | Copperhead Solar, LLC | tap 138kV 3410 Lake Creek Switch - 3582 Falls County | Falls | NORTH | 2023-12-15 | OTH | BA | 101 |  | 2021-02-26 | 2021-03-01 | 2021-05-13 | 2021-02-01 |  |  |  | No |  |  | Not Required
23INR0126 | Sigma Storage | SS Completed, FIS Started, No IA | AES Distributed Energy, Inc | 40460 Deepwater 138kV | Harris | HOUSTON | 2024-12-31 | OTH | BA | 408.4 |  | 2022-02-17 | 2021-05-11 | 2021-07-30 | 2022-02-04 |  |  |  | No |  |  | Not Required
23INR0127 | Beacon Storage | SS Completed, FIS Started, No IA | AES Distributed Energy, Inc | 40450 Deepwater 345kV | Harris | HOUSTON | 2024-12-31 | OTH | BA | 408.7 |  | 2022-03-23 | 2021-05-05 | 2021-07-27 | 2022-02-28 |  |  |  | No |  |  | Not Required
23INR0130 | Ocee Creek Solar | SS Completed, FIS Started, No IA | OCI LoneSun LLC | 173 Crawford 138kV | McLennan | NORTH | 2024-06-01 | SOL | PV | 101.52 | COD | 2021-01-25 | 2021-02-09 | 2021-05-06 | 2020-12-22 |  |  |  | No | Not Required | Not Required | Not Required
23INR0131 | BRP Batura BESS | SS Completed, FIS Started, No IA | BRP Batura BESS LLC | 5260 Leon Creek 138kV | Bexar | SOUTH | 2023-06-01 | OTH | BA | 251.65 |  | 2020-11-12 | 2020-12-03 | 2021-02-16 | 2020-11-12 |  |  |  | No |  |  | Not Required
23INR0132 | BRP Bonete BESS | SS Completed, FIS Started, No IA | BRP Bonete BESS LLC | 8951 Stewart Road 138kV | Hidalgo | SOUTH | 2024-06-01 | OTH | BA | 201.13 | COD | 2020-11-17 | 2020-12-03 | 2021-02-16 | 2020-11-18 |  | No |  | No |  |  | Not Required
23INR0134 | BRP Kailas BESS | SS Completed, FIS Started, No IA | BRP Kailas BESS LLC | 6216 Bluff Creek 138kV | Taylor | WEST | 2023-05-01 | OTH | BA | 201.29 |  | 2020-11-20 | 2020-12-03 | 2021-02-16 | 2020-11-20 |  |  |  | No |  |  | Not Required
23INR0135 | BRP Elbus BESS | SS Completed, FIS Started, No IA | BRP Elbus BESS LLC | 9075 Lytton 138kV | Caldwell | SOUTH | 2023-05-01 | OTH | BA | 201.11 |  | 2020-11-30 | 2020-12-03 | 2021-02-18 | 2020-11-25 |  |  |  | No |  |  | Not Required
23INR0137 | BRP Diran BESS | SS Completed, FIS Completed, No IA | BRP Diran BESS LLC | 43190 South Lane City 138kV | Wharton | SOUTH | 2023-05-01 | OTH | BA | 100.63 |  | 2020-11-30 | 2020-12-03 | 2021-02-18 | 2020-11-25 | 2022-04-15 | No |  | No |  |  | Not Required
23INR0139 | BRP Passu BESS | SS Completed, FIS Started, No IA | BRP Passu BESS LLC | 6111 Riley 345kV | Wilbarger | WEST | 2023-10-01 | OTH | BA | 301.82 |  | 2020-11-30 | 2020-12-03 | 2021-02-19 | 2020-11-27 |  | No |  | No |  |  | Not Required
23INR0140 | BRP Seine BESS | SS Completed, FIS Started, No IA | BRP Seine BESS LLC | 60500 Edith Clarke 345kV | Foard | WEST | 2023-10-01 | OTH | BA | 301.69 |  | 2020-11-30 | 2020-12-03 | 2021-02-19 | 2020-11-27 |  | No |  | No |  |  | Not Required
23INR0143 | BRP Sepik BESS | SS Completed, FIS Started, No IA | BRP Sepik BESS LLC | tap 138kV 11342 Loraine South – 1032 Morgan Creek | Mitchell | WEST | 2024-12-01 | OTH | BA | 201.87 | COD | 2020-12-08 | 2020-12-22 | 2021-03-15 | 2020-12-01 |  |  |  | No |  |  | Not Required
23INR0144 | Galactic Solar | SS Completed, FIS Completed, No IA | UKA North America, LLC | tap 138kV 1744 Gordonville - 11704 Sherman West | Grayson | NORTH | 2024-03-01 | SOL | PV | 205.2 |  | 2020-12-08 | 2020-12-22 | 2021-03-10 | 2020-12-01 | 2021-12-21 | No |  | No |  |  | Not Required
23INR0150 | Cradle Solar | SS Completed, FIS Completed, No IA | NFP Holdings | tap 345kV 42500 Dow - 43035 Oasis ckt 18 | Brazoria | COASTAL | 2023-08-31 | SOL | PV | 225 |  | 2021-03-26 | 2021-02-04 | 2021-04-21 | 2021-03-15 | 2022-06-14 | No |  | No |  |  | Not Required
23INR0153 | Mercury II Solar | SS Completed, FIS Completed, IA | Mercury II Solar, LLC | 68090 Sam Sw 345kV | Hill | NORTH | 2022-12-31 | SOL | PV | 206.11 |  | 2020-12-22 | 2021-01-26 | 2021-04-12 | 2020-12-11 | 2021-10-14 |  | 2021-10-18 | Yes | Not Required | Not Required | Not Required | 2022-03-21 | 2022-04-29 | 2022-04-29
23INR0154 | Ebony Energy Storage | SS Completed, FIS Started, IA | Ebony Energy Storage, LLC | 5180 Green Mountain 138kV | Comal | SOUTH | 2023-05-01 | OTH | BA | 204.97 | SFS/NtP | 2021-02-03 | 2021-02-04 | 2021-04-21 | 2021-01-20 |  |  | 2022-05-31 | Yes |  |  | Not Required
23INR0155 | Umbra (Stockyard) Solar | SS Completed, FIS Started, No IA | Stockyard Solar Project, LLC | tap 345kV 1695 Monticello - 11699 Woodard | Franklin | NORTH | 2023-12-29 | SOL | PV | 210 |  | 2021-05-20 | 2021-01-25 | 2021-04-12 | 2020-12-31 |  | No |  | No |  |  | Not Required
23INR0156 | Umbra (Stockyard) BESS | SS Completed, FIS Started, No IA | Stockyard Solar Project, LLC | tap 345kV 1695 Monticello - 11699 Woodard | Franklin | NORTH | 2023-12-29 | OTH | BA | 73 |  | 2021-05-20 | 2021-01-25 | 2021-04-12 | 2020-12-31 |  | No |  | No |  |  | Not Required
23INR0159 | Five Wells Storage | SS Completed, FIS Started, No IA | Five Wells Solar Center LLC | 3687 Bell Country East 345kV | Bell | NORTH | 2023-12-29 | OTH | BA | 262.5 |  | 2021-03-01 | 2021-02-04 | 2021-04-21 | 2021-01-22 |  |  |  | No |  |  | Not Required
23INR0160 | Grimes County Solar | SS Completed, FIS Started, IA | Grimes County Solar Project, LLC | 2 Keith Switch 138kV | Grimes | NORTH | 2023-09-30 | SOL | PV | 210 | SFS/NtP | 2020-12-16 | 2021-01-26 | 2021-04-12 | 2020-12-16 |  |  | 2022-06-23 | Yes |  |  | Not Required
23INR0162 | Redonda Solar | SS Completed, FIS Started, IA | J&R Power DevCo, LLC | tap 345kV 80307 Del Sol - 80225 Cenizo | Zapata | SOUTH | 2024-02-08 | SOL | PV | 253.21 |  | 2021-08-19 | 2021-01-25 | 2021-04-12 | 2021-08-11 |  |  | 2021-12-28 | Yes | Not Required | Not Required | Not Required | 2022-04-27
23INR0163 | Ringtail Ridge Storage | SS Completed, FIS Started, No IA | KCE TX 26, LLC | 7150 Kendall 138kV | Kendall | SOUTH | 2025-02-11 | OTH | BA | 103.51 | Status Change INA-to-PLN | 2021-01-08 | 2021-01-25 | 2021-04-16 | 2020-12-29 |  |  |  | No |  |  | Not Required
23INR0164 | Steppe Reserve Storage | SS Completed, FIS Started, No IA | KCE TX 25, LLC | 8283 Asherton 138 kV | Dimmit | SOUTH | 2023-06-01 | OTH | BA | 51.9 | Status Change INA-to-PLN | 2021-01-08 | 2021-01-25 | 2021-04-16 | 2020-12-29 |  |  |  | No |  |  | Not Required
23INR0166 | Great Kiskadee Storage | SS Completed, FIS Started, IA | Great Kiskadee Storage, LLC | 8951 Stewart Rd 138kV | Hidalgo | SOUTH | 2023-08-02 | OTH | BA | 103.05 | SFS/NtP | 2021-10-08 | 2021-01-26 | 2021-04-12 | 2021-08-24 |  |  | 2022-06-30 | Yes |  |  | Not Required
23INR0168 | Charolais Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 44000 W A Parish - 5915 STP | Matagorda | COASTAL | 2023-12-15 | OTH | BA | 150 |  | 2021-06-25 | 2021-02-09 | 2021-05-06 | 2021-06-11 |  |  |  | No |  |  | Not Required
23INR0171 | Goodalta Solar | SS Completed, FIS Started, No IA | GoodAlta Power Center LLC | tap 138kV 3127 Trinidad - 212 Winkler | Navarro | NORTH | 2024-04-15 | SOL | PV | 180 |  | 2021-08-03 | 2021-01-25 | 2021-04-12 | 2021-01-07 |  | No |  | No |  |  | Not Required
23INR0174 | Lutum Wind Alt. POI 1 | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 1458 Cobb - 1429 Jacksboro | Jack | NORTH | 2024-07-11 | WIN | WT | 241.5 |  | 2021-09-28 | 2021-02-09 | 2021-05-06 | 2021-09-01 |  |  |  | No |  |  | Not Required
23INR0177 | Wren Storage | SS Completed, FIS Started, No IA | Wren Storage, LLC | 8601 Cebolla 345kV | Willacy | COASTAL | 2023-12-29 | OTH | BA | 170 |  | 2021-08-30 | 2021-01-25 | 2021-04-16 | 2021-08-26 |  |  |  | No | Not Required | Not Required | Not Required
23INR0180 | Jackalope Solar | SS Completed, FIS Completed, IA | Peacock Energy Project, LLC | 8173 Gibbs 138kV | San Patricio | COASTAL | 2023-07-01 | SOL | PV | 156.4 |  | 2021-01-29 | 2021-02-09 | 2021-05-06 | 2021-02-02 | 2021-11-18 |  | 2021-09-30 | Yes | Not Required | Not Required | Not Required | 2021-10-18
23INR0181 | Starling Storage | SS Completed, FIS Started, No IA | Starling Storage, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2023-10-30 | OTH | BA | 63.6 |  | 2021-10-20 | 2021-01-25 | 2021-04-16 | 2021-10-07 |  |  |  | No | Not Required | Not Required | Not Required
23INR0182 | Welder Storage | SS Completed, FIS Started, No IA | Welder Storage, LLC | tap 345kV 8624 Grissom - 8455 Lon Hill | San Patricio | COASTAL | 2023-10-31 | OTH | BA | 100 |  | 2021-10-18 | 2021-01-25 | 2021-04-16 | 2021-10-07 |  |  |  | No | Not Required | Not Required | Not Required
23INR0183 | Pradera Storage | SS Completed, FIS Started, No IA | Pradera Storage, LLC | tap 345 kV Lobo 80219 - Fowlerton 5709 | Webb | SOUTH | 2023-10-31 | OTH | BA | 153.11 |  | 2021-10-18 | 2021-01-25 | 2021-04-16 | 2021-10-13 |  |  |  | No |  |  | Not Required
23INR0187 | Leitrim 1 Solar | SS Completed, FIS Completed, No IA | Leitsol LLC | tap 138kV 3522 Hillsboro - 3546 Whitney | Hill | NORTH | 2024-03-31 | SOL | PV | 91.2 |  | 2021-03-23 | 2021-01-26 | 2021-04-12 | 2021-03-18 | 2022-02-01 | No |  | No |  |  | Not Required
23INR0189 | Bayside Solar | SS Completed, FIS Started, No IA | Bayside Solar, LLC | Tap 345kV 5915 STP - 5133 Elm Creek ckt #1 | Victoria | SOUTH | 2023-12-31 | SOL | PV | 509.4 |  | 2021-01-25 | 2021-02-09 | 2021-05-06 | 2021-01-25 |  |  |  | No |  |  | Not Required
23INR0190 | Cosmos Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 9073 Holman - 44200 Hillje | Wharton | SOUTH | 2024-12-01 | SOL | PV | 609.74 |  | 2021-02-10 | 2021-03-01 | 2021-05-13 | 2021-03-01 |  |  |  | No | Not Required | Not Required | Not Required
23INR0192 | Utica Solar | SS Completed, FIS Started, No IA | Utica Solar, LLC | Tap 345kV 7050 Clear Springs - 7047 Hornsby Bend | Guadalupe | SOUTH | 2025-12-31 | SOL | PV | 204.5 |  | 2022-02-16 | 2021-04-21 | 2021-07-14 | 2021-02-22 |  |  |  | No |  |  | Not Required
23INR0193 | Stockdale Solar | SS Completed, FIS Started, No IA | Stockdale Solar, LLC | tap 345kV 5133 Elm Creek - 5323 Old Hickory Ckt 2 | Wilson | SOUTH | 2023-12-31 | SOL | PV | 152.5 |  | 2021-01-15 | 2021-04-01 | 2021-07-02 | 2021-02-22 |  |  |  | No |  |  | Not Required
23INR0194 | Pequin Energy Storage | SS Completed, FIS Started, No IA | Pequin Energy Storage, LLC | 39500 TN West Columbia 138kV | Brazoria | COASTAL | 2023-08-24 | OTH | BA | 103.4 | MW Size | 2021-06-29 | 2021-01-25 | 2021-04-16 | 2021-06-14 |  |  |  | No |  |  | Not Required
23INR0195 | Desert Willow BESS | SS Completed, FIS Started, No IA | Desert Willow Energy Storage, LLC | tap 345kV 1906 Venus_S5 - 1916 LiggettA1_5 | Ellis | NORTH | 2024-03-20 | OTH | BA | 151.32 |  | 2021-06-29 | 2021-02-04 | 2021-04-22 | 2021-06-14 |  |  |  | No |  |  | Not Required
23INR0197 | Ponta Power Station | SS Completed, FIS Started, No IA | WattBridge Energy, LLC | Tap 345kV 3109 Stryker Creek - 3123 Trinidad | Cherokee | NORTH | 2024-04-01 | GAS | GT | 458.67 |  | 2021-12-02 | 2021-03-01 | 2021-05-13 | 2021-11-22 |  |  |  | No
23INR0200 | Paradiso BESS | SS Completed, FIS Started, No IA | VESI 13 | 8203 Pleasanton 138kV | Atascosa | SOUTH | 2023-06-01 | OTH | BA | 100.92 |  | 2021-09-03 | 2021-03-01 | 2021-05-13 | 2021-08-20 |  |  |  | No | Not Required | Not Required | Not Required
23INR0202 | Erath County Solar | SS Completed, FIS Started, No IA | Erath Solar, LLC | tap 345kV 68020 Romney1E - 68030 KopperlW | Erath | NORTH | 2023-11-30 | SOL | PV | 226.8 |  | 2021-01-20 | 2021-03-08 | 2021-05-28 | 2021-03-06 |  |  |  | No |  |  | Not Required
23INR0204 | GALVANIC BESS | SS Completed, FIS Started, No IA | CED Development Inc | 8252 Bracketville 138kV | Kinney | SOUTH | 2024-05-31 | OTH | BA | 100 |  | 2022-06-15 | 2021-02-09 | 2021-05-06 | 2022-05-13 |  |  |  | No |  |  | Not Required
23INR0205 | SUNSETTER BESS | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2024-05-31 | OTH | BA | 100 |  | 2022-05-27 | 2021-02-09 | 2021-05-06 | 2022-05-13 |  |  |  | No |  |  | Not Required
23INR0206 | PEREGRINE BESS | SS Completed, FIS Started, No IA | CED Development Inc. | tap 345kV 8624 Grissom - 8164 Coleto Creek | Goliad | SOUTH | 2025-05-01 | OTH | BA | 150 |  | 2022-06-15 | 2021-02-10 | 2021-05-06 | 2022-05-13 |  |  |  | No |  |  | Not Required
23INR0207 | El Patrimonio Solar | SS Completed, FIS Started, No IA | Heritage Solar LLC | tap 138kV 5429 Trumbo - 5260 Leon Creek | Bexar | SOUTH | 2024-08-30 | SOL | PV | 145 |  | 2022-03-02 | 2021-03-16 | 2021-05-28 | 2021-11-23 |  |  |  | No |  |  | Not Required
23INR0209 | Outpost Storage | SS Completed, FIS Started, No IA | Hecate Energy Outpost Storage LLC | Tap 345kV 80219 Lobo - 5709 Fowlerton | Webb | SOUTH | 2023-12-01 | OTH | BA | 508.1 |  | 2021-02-15 | 2021-03-01 | 2021-05-13 | 2021-02-15 |  |  |  | No |  |  | Not Required
23INR0210 | Cornwall Solar | SS Completed, FIS Started, No IA | Cornwall Solar, LLC | Tap 138kV 3659 Thorndale North - 3658 Taylor | Williamson | SOUTH | 2023-12-31 | SOL | PV | 204.5 |  | 2022-02-14 | 2021-03-01 | 2021-05-13 | 2021-02-25 |  |  |  | No | Not Required | Not Required | Not Required
23INR0211 | Rosscommon Solar | SS Completed, FIS Started, No IA | Roscsol LLC | tap 138kV 1691 Valley Switch - 1776 Paris Switch | Lamar | NORTH | 2024-03-31 | SOL | PV | 91 |  | 2021-01-30 | 2021-03-01 | 2021-05-13 | 2021-02-01 |  |  |  | No |  |  | Not Required
23INR0214 | Harley Hand Storage | SS Completed, FIS Started, No IA | Harley Hand Storage | 11420 Sweetwater East 345kV | Nolan | WEST | 2024-12-01 | OTH | BA | 513.7 |  | 2022-04-04 | 2021-03-01 | 2021-05-13 | 2022-03-22 |  |  |  | No |  |  | Not Required
23INR0215 | Big River Solar | SS Completed, FIS Started, No IA | Photosol US Renewable Energy, LLC | 8299 Zapata 138kV | Zapata | SOUTH | 2025-12-01 | SOL | PV | 104.35 |  | 2021-04-09 | 2021-05-04 | 2021-07-27 | 2021-04-15 |  |  |  | No |  |  | Not Required
23INR0216 | Venus Mill Storage | SS Completed, FIS Started, No IA | KCE TX 14, LLC | 138 kV Tap #442 Rail Port - #1905 Griffith | Ellis | NORTH | 2025-03-24 | OTH | BA | 103.51 | Status Change INA-to-PLN | 2022-02-11 | 2022-03-14 | 2022-06-09 | 2022-03-04 |  |  |  | No | Not Required | Not Required | Not Required
23INR0219 | Dogfish BESS | SS Completed, FIS Started, No IA | Momentum LRC Holdco LLC | tap 138kV 38330 TN Alamo St – 38455 TN Holiday | Pecos | WEST | 2023-09-01 | OTH | BA | 75 |  | 2021-09-23 | 2021-03-16 | 2021-05-28 | 2021-09-14 |  |  |  | No | Not Required | Not Required | Not Required
23INR0220 | HOPSLAM BESS | SS Completed, FIS Started, No IA | Momentum LRC Holdco LLC | 38430 White Baker TNP 138kV | Pecos | WEST | 2024-02-01 | OTH | BA | 156.75 |  | 2021-11-15 | 2021-03-16 | 2021-05-28 | 2021-11-09 |  |  |  | No | Not Required | Not Required | Not Required
23INR0222 | Sunbelt Solar | SS Completed, FIS Started, No IA | Belltown Power Texas | tap 138kV 6902 Talty - 6801 Patton | Kaufman | NORTH | 2023-12-31 | SOL | PV | 81.5 |  | 2021-10-05 | 2021-03-16 | 2021-05-28 | 2021-09-30 |  |  |  | No |  |  | Not Required
23INR0223 | Garcitas Creek Solar | SS Completed, FIS Started, IA | Garcitas Creek Solar LLC | Tap 345 kV 5915 South Texas Project – 8249 Angstrom | Jackson | SOUTH | 2023-12-08 | SOL | PV | 201.94 |  | 2021-10-18 | 2021-10-05 | 2021-12-08 | 2021-10-08 |  |  | 2022-06-30 | No |  |  | Not Required
23INR0224 | Morning Glory Solar | SS Completed, FIS Started, No IA | Armadillo Solar, LLC | tap 345kV 7077 Amos Creek - 76009 Twin Buttes | Tom Green | WEST | 2024-03-01 | SOL | PV | 122.4 |  | 2022-05-31 | 2021-06-16 | 2021-09-07 | 2022-05-17 |  |  |  | No |  |  | Not Required
23INR0225 | MRG GOODY SOLAR | SS Completed, FIS Started, No IA | MRG GOODY SOLAR PROJECT, LLC | 1700 Toco 138kV | Lamar | NORTH | 2024-06-30 | SOL | PV | 126.36 |  | 2022-04-04 | 2021-03-16 | 2021-06-11 | 2022-03-22 |  |  |  | No |  |  | Not Required
23INR0227 | Maleza Solar II | SS Completed, FIS Started, No IA | Brush Solar, LLC | tap 345kV 44200 Hillje - 44040 Bailey | Wharton | SOUTH | 2023-08-17 | SOL | PV | 254.94 | COD | 2021-05-24 | 2021-04-06 | 2021-06-24 | 2021-05-19 |  |  |  | No |  |  | Not Required
23INR0228 | Hiru Solar | SS Completed, FIS Started, No IA | Hecate Energy Hazel LLC | Tap 345kV 6111 Riley - 1730 West Krum ckt 2 | Clay | WEST | 2024-12-16 | SOL | PV | 614.4 |  | 2021-09-08 | 2021-04-21 | 2021-07-14 | 2021-08-30 |  |  |  | No | Not Required | Not Required | Not Required
23INR0229 | Solterra Solar | SS Completed, FIS Completed, No IA | Bridgelink Investments LLC | Tap 138kV 11796 White Oak POI - 11797 Brinker POI | Hopkins | NORTH | 2024-03-27 | SOL | PV | 143 |  | 2021-03-17 | 2021-03-19 | 2021-06-11 | 2021-03-18 | 2022-03-23 | No |  | No | Not Required | Not Required | Not Required
23INR0231 | Rocinante Solar | SS Completed, FIS Started, IA | Brush Country Solar Project, LLC | tap 138kV 7595 Deer Creek - 7621 Nixon | Gonzales | SOUTH | 2023-12-31 | SOL | PV | 95 |  | 2021-04-28 | 2021-04-22 | 2021-07-14 | 2021-04-22 |  |  | 2022-04-25 | No |  |  | Not Required
23INR0232 | Rocinante BESS | SS Completed, FIS Started, IA | Brush Country Solar Project, LLC | tap 138kV 7595 Deer Creek - 7621 Nixon | Gonzales | SOUTH | 2023-12-31 | OTH | BA | 33 |  | 2021-04-28 | 2021-04-22 | 2021-07-14 | 2021-04-22 |  |  | 2022-04-25 | No |  |  | Not Required
23INR0233 | Earthwise Solar | SS Completed, FIS Started, No IA | Quanah Solar 2 | Tap 345kV 60504 Tesla - 61001 Jim Treece | Hardeman | WEST | 2024-12-29 | SOL | PV | 310.66 |  | 2022-02-23 | 2022-03-14 | 2022-06-09 | 2022-02-25 |  |  |  | No |  |  | Not Required
23INR0234 | Chiltepin Solar | SS Completed, FIS Started, No IA | Chiltepin Solar-Storage | 6673 Musquiz 138kV | Reeves | WEST | 2023-12-01 | SOL | PV | 200 |  | 2021-11-09 | 2021-04-22 | 2021-07-14 | 2021-10-31 |  |  |  | No |  |  | Not Required
23INR0235 | Hoyte Solar | SS Completed, FIS Completed, No IA | Milano Solar, LLC | Tap 138kV 64 Milano - 32 Robertson | Milam | SOUTH | 2023-12-31 | SOL | PV | 203.97 |  | 2021-04-02 | 2021-04-01 | 2021-07-02 | 2021-03-25 | 2022-06-07 | No |  | No |  |  | Not Required
23INR0237 | Big River BESS | SS Completed, FIS Started, No IA | Photosol US Renewable Energy, LLC | 8299 Zapata 138KV | Zapata | SOUTH | 2025-12-01 | OTH | BA | 51.26 |  | 2021-04-09 | 2021-05-04 | 2021-07-27 | 2021-04-15 |  |  |  | No |  |  | Not Required
23INR0239 | Giga Texas Energy Storage | SS Completed, FIS Started, IA | Giga Texas Energy, LLC. | 7047 Hornsby 345kV | Travis | SOUTH | 2023-06-15 | OTH | BA | 131.05 |  | 2021-07-22 | 2021-04-20 | 2021-07-02 | 2021-07-22 |  | No | 2021-12-03 | No |  |  | Not Required
23INR0240 | Welder Solar II | SS Completed, FIS Started, No IA | Welder Solar, LLC | tap 345kV 8624 Grissom - 8249 Angstrom | San Patricio | COASTAL | 2024-04-29 | SOL | PV | 300 |  | 2022-01-03 | 2021-04-09 | 2021-06-30 | 2021-12-15 |  |  |  | No |  |  | Not Required
23INR0241 | Welder Storage II | SS Completed, FIS Started, No IA | Welder Storage, LLC | tap 345kV 8624 Grissom - 8249 Angstrom | San Patricio | COASTAL | 2024-04-29 | OTH | BA | 100 |  | 2022-01-17 | 2021-04-09 | 2021-06-30 | 2021-12-15 |  |  |  | No | Not Required | Not Required | Not Required
23INR0244 | Tiger Solar | SS Completed, FIS Started, No IA | Vaca Del Sol, LLC | 68004 PHANTOM HILL 345KV | Jones | WEST | 2023-12-01 | SOL | PV | 306.24 |  | 2021-04-21 | 2021-04-29 | 2021-07-22 | 2021-04-29 |  |  |  | No |  |  | Not Required
23INR0245 | Tiger Storage | SS Completed, FIS Started, No IA | Vaca Del Sol, LLC | 68004 PHANTOM HILL 345kV | Jones | WEST | 2023-12-01 | OTH | BA | 251.04 |  | 2021-04-21 | 2021-04-29 | 2021-07-22 | 2021-04-29 |  |  |  | No |  |  | Not Required
23INR0248 | Limewood Storage | SS Completed, FIS Started, No IA | Woodlands Energy Renewables LLC | 3420 Temple Pecan Creek 138kV | Bell | NORTH | 2024-08-19 | OTH | BA | 50 |  | 2021-11-03 | 2021-04-30 | 2021-07-22 | 2021-10-06 |  |  |  | No | Not Required | Not Required | Not Required
23INR0249 | Limewood Solar | SS Completed, FIS Started, No IA | Woodlands Energy Renewables LLC | 3420 Temple Pecan Creek 138kV | Bell | NORTH | 2024-08-19 | SOL | PV | 204 |  | 2021-11-03 | 2021-04-30 | 2021-07-22 | 2021-10-06 |  |  |  | No | Not Required | Not Required | Not Required
23INR0250 | Cody Solar | SS Completed, FIS Started, No IA | Woodlands Energy Renewables LLC | 3607 Temple 138kV | Bell | NORTH | 2023-08-01 | SOL | PV | 150 |  | 2022-02-03 | 2021-04-26 | 2021-07-20 | 2022-01-17 |  |  |  | No |  |  | Not Required
23INR0251 | Cody Storage | SS Completed, FIS Started, No IA | Woodlands Energy Renewables LLC | 3607 Temple 138kV | Bell | NORTH | 2023-09-15 | OTH | BA | 50 |  | 2022-02-08 | 2021-04-26 | 2021-07-20 | 2022-01-17 |  |  |  | No |  |  | Not Required
23INR0259 | Noria Storage DCC | SS Completed, FIS Started, No IA | Noria Hondo Solar, LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2024-09-01 | OTH | BA | 0 |  | 2021-04-28 | 2021-04-22 | 2021-04-23 | 2021-04-22 |  |  |  | No |  |  | Not Required
23INR0260 | Flatland Solar Project | SS Completed, FIS Completed, No IA | Flatland Solar Project, LLC | 11319 Scurry County 138kV | Scurry | WEST | 2023-06-01 | SOL | PV | 182.2 |  | 2021-05-04 | 2021-05-10 | 2021-07-30 | 2021-04-28 | 2022-01-28 | No |  | No | Not Required | Not Required | Not Required
23INR0261 | Dodd Solar I | SS Completed, FIS Started, No IA | Forest Grove Solar LLC | 3131 Forest Grove 138kV | Henderson | NORTH | 2023-05-01 | SOL | PV | 202.9 |  | 2022-04-12 | 2021-06-24 | 2021-09-20 | 2022-04-04 |  |  |  | No |  |  | Not Required
23INR0266 | Langer Storage | SS Completed, FIS Started, No IA | Langer Solar, LLC | tap 345kV 68040 Kopperl - 68091 Navarro | Bosque | NORTH | 2024-12-01 | OTH | BA | 61.92 |  | 2022-03-22 | 2021-05-10 | 2021-07-30 | 2022-02-25 |  |  |  | No |  |  | Not Required
23INR0272 | BRP Aras BESS | SS Completed, FIS Started, No IA | BRP Aras BESS LLC | 76595 North McCamey 138kV | Upton | WEST | 2024-12-01 | OTH | BA | 303.59 |  | 2021-05-27 | 2021-05-31 | 2021-08-19 | 2021-05-10 |  |  |  | No | Not Required | Not Required | Not Required
23INR0273 | Poco Trail Solar | SS Completed, FIS Started, No IA | Eastern Trail Solar Center, LLC | Tap 345kV 6101 Riley - 1422 Bowman | Wilbarger | WEST | 2025-03-15 | SOL | PV | 438.75 |  | 2021-06-02 | 2021-09-14 | 2021-11-30 | 2021-07-12 |  |  |  | No | Not Required | Not Required | Not Required
23INR0274 | BRP Parana BESS | SS Completed, FIS Started, No IA | BRP Parana BESS | 7178 Marion 138kV | Guadalupe | SOUTH | 2024-06-15 | OTH | BA | 303.67 |  | 2021-06-01 | 2021-05-31 | 2021-08-19 | 2021-05-10 |  |  |  | No | Not Required | Not Required | Not Required
23INR0275 | BRP Nile BESS | SS Completed, FIS Started, No IA | BRP Nile BESS LLC | 80220 Cenizo 345kV | Webb | SOUTH | 2023-08-01 | OTH | BA | 202.34 |  | 2021-06-01 | 2021-05-31 | 2021-08-19 | 2021-05-10 |  |  |  | No |  |  | Not Required
23INR0278 | BRP Tucana BESS | SS Completed, FIS Started, No IA | BRP Tucana BESS LLC | 1157 Andrews County South 138kV | Andrews | WEST | 2024-12-01 | OTH | BA | 206.98 | COD | 2021-06-01 | 2021-06-03 | 2021-08-19 | 2021-05-10 |  | No |  | No |  |  | Not Required
23INR0279 | BRP Trivor BESS | SS Completed, FIS Started, No IA | BRP Trivor BESS LLC | 1272 Fullerton 138kV | Andrews | WEST | 2023-08-01 | OTH | BA | 202.34 |  | 2021-06-01 | 2021-06-03 | 2022-03-15 | 2021-05-10 |  | No |  | No |  |  | Not Required
23INR0282 | BAYSIDE II SOLAR | SS Completed, FIS Started, No IA | Bayside II Solar, LLC | Tap 345kV 5323 Old Hickory - 5133 Elm Creek ckt #2 | DeWitt | SOUTH | 2023-12-31 | SOL | PV | 252.8 |  | 2021-06-02 | 2021-07-28 | 2021-10-11 | 2021-06-09 |  |  |  | No |  |  | Not Required
23INR0283 | Kota Battery | SS Completed, FIS Started, No IA | National Grid Renewables LLC | 23900 Alibates 345kV | Carson | PANHANDLE | 2023-06-01 | OTH | BA | 202 |  | 2021-06-02 | 2021-06-07 | 2021-08-27 | 2021-06-02 |  |  |  | No |  |  | Not Required
23INR0284 | Las Moras Battery | SS Completed, FIS Started, No IA | National Grid Renewables, LLC | 8252 Brackett 138kV | Kinney | SOUTH | 2025-06-01 | OTH | BA | 101 | COD | 2021-06-01 | 2021-06-07 | 2021-08-27 | 2021-06-02 |  | No |  | No |  |  | Not Required
23INR0285 | BRP Chena BESS | SS Completed, FIS Started, No IA | BRP Chena BESS LLC | Tap 138 kV 1951 Handley SES – 2246 Lakewood | Tarrant | NORTH | 2024-02-01 | OTH | BA | 202.32 |  | 2021-06-02 | 2021-08-05 | 2021-10-18 | 2021-08-05 |  |  |  | No | Not Required | Not Required | Not Required
23INR0286 | Dry Creek Solar I | SS Completed, FIS Started, No IA | OAK HILL SOLAR LLC | tap 345kV 3100 Martin Lake - 3102 Tyler Grande | Rusk | NORTH | 2025-03-30 | SOL | PV | 202.54 | COD | 2022-04-04 | 2021-08-18 | 2021-11-05 | 2022-03-30 |  |  |  | No | Not Required | Not Required | Not Required
23INR0287 | BRP Avila BESS | SS Completed, FIS Completed, No IA | BRP Avila BESS LLC | 38340 TN Airport 138kV | Pecos | WEST | 2023-12-01 | OTH | BA | 164.95 |  | 2021-06-02 | 2021-05-31 | 2022-01-17 | 2021-05-20 | 2022-06-22 | No |  | No |  |  | Not Required
23INR0289 | Skull Creek Solar | SS Completed, FIS Started, No IA | HEP AQUAMARINE HOLDINGS | Tap 138kV 3281 Tennessee Colony - 3499 Blackfoot | Anderson | NORTH | 2024-06-01 | SOL | PV | 136.08 |  | 2022-01-10 | 2021-05-28 | 2021-08-19 | 2021-12-16 |  |  |  | No | Not Required | Not Required | Not Required
23INR0290 | BRP Zeya BESS | SS Completed, FIS Completed, No IA | BRP Zeya BESS LLC | 38740 Heights 138kV | Galveston | HOUSTON | 2023-12-01 | OTH | BA | 256.83 |  | 2021-06-02 | 2021-05-31 | 2022-03-09 | 2021-05-20 | 2022-06-22 | No |  | No | Not Required | Not Required | Not Required
23INR0292 | Howle Storage | SS Completed, FIS Completed, No IA | BT Howle Solar, LLC | tap 345kV 1907 Venus - 68090 Sam Sw Same location as 20INR0075 - Howle Solar | Ellis | NORTH | 2023-12-31 | OTH | BA | 30 |  | 2021-06-02 | 2021-06-07 | 2021-08-27 | 2021-06-03 | 2022-05-06 | No |  | No |  |  | Not Required
23INR0295 | Sultan Solar | SS Completed, FIS Started, No IA | Lake Whitney Solar, LLC | tap 345kV 68080 Sam Switch – 68090 Kopperl | Bosque | NORTH | 2023-10-31 | SOL | PV | 206.11 |  | 2021-06-03 | 2021-07-01 | 2021-09-27 | 2021-06-29 |  |  |  | No |  |  | Not Required
23INR0296 | Trojan Solar | SS Completed, FIS Started, No IA | Trojan Solar, LLC | 11735 Cedar Elm Switch 345kV | Cooke | NORTH | 2023-12-31 | SOL | PV | 206.11 |  | 2021-06-03 | 2021-07-01 | 2021-09-22 | 2021-06-30 |  |  |  | No |  |  | Not Required
23INR0299 | Anole BESS | SS Completed, FIS Started, No IA | Anole Energy Storage, LLC | 2432 Tri-Corner 345kV | Dallas | NORTH | 2024-05-18 | OTH | BA | 242.71 |  | 2021-06-30 | 2021-07-01 | 2021-09-22 | 2021-06-14 |  | No |  | No |  |  | Not Required
23INR0300 | Greater Bryant G Solar | SS Completed, FIS Started, No IA | Chevron USA, Inc. | Tap 138kV 1124 Midessa S – 1023 Midland E Circuit 1 | Midland | WEST | 2024-01-02 | SOL | PV | 41.6 |  | 2021-06-09 | 2021-06-17 | 2021-09-01 | 2021-06-16 |  | No |  | No |  |  | Not Required
23INR0308 | Fowler Ranch Storage | SS Completed, FIS Started, No IA | Crane BESS, LLC | 76025 Castle Mountain 138kV | Crane | WEST | 2023-12-01 | OTH | BA | 26.44 | MW Size | 2022-06-03 | 2021-06-21 | 2021-09-07 | 2022-05-18 |  |  |  | No |  |  | Not Required
23INR0309 | Peeler Solar | SS Completed, FIS Started, No IA | Peeler Solar, LLC | 5704 San Miguel 138kV | Atascosa | SOUTH | 2023-06-01 | SOL | PV | 209.81 |  | 2021-11-17 | 2021-07-01 | 2021-09-22 | 2021-11-12 |  |  |  | No | Not Required | Not Required | Not Required
23INR0310 | Dunkel BESS | SS Started, FIS Started, No IA | Momentum Energy Storage Partners | 59156 Yellow House Canyon 345kV | Lubbock | PANHANDLE | 2024-07-08 | OTH | BA | 225 | FIS Request | 2022-06-10 | 2022-06-27 |  | 2022-06-20 |  |  |  | No |  |  | Not Required
23INR0312 | Hofbrau BESS | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners, LLC | 6442 Redcreek 138kV | Tom Green | WEST | 2023-10-01 | OTH | BA | 188.1 |  | 2021-09-22 | 2021-09-22 | 2021-12-09 | 2021-09-22 |  | No |  | No |  |  | Not Required
23INR0317 | Kingfisher Energy Storage | SS Completed, FIS Started, No IA | Nopalosa Energy Storage, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2023-03-31 | OTH | BA | 204.97 |  | 2021-07-01 | 2021-07-08 | 2021-09-28 | 2021-07-02 |  |  |  | No |  |  | Not Required
23INR0318 | Marcelina Storage | SS Completed, FIS Started, No IA | Marcelina Solar, LLC | Tap 345 kV 5133 Elm Creek - 5901 San Miguel | Wilson | SOUTH | 2024-06-01 | OTH | BA | 203.21 |  | 2022-05-03 | 2021-08-09 | 2021-10-29 | 2022-04-22 |  |  |  | No |  |  | Not Required
23INR0320 | Redding Tech West | SS Completed, FIS Started, No IA | Redding Tech West | 1250 Yukon 138kV | Ector | WEST | 2024-07-01 | GAS | GT | 130 |  |  | 2021-09-01 | 2021-11-22 | 2022-05-20 17:42 |  |  |  | No
23INR0322 | Columbus Storage | SS Completed, FIS Started, No IA | EDP Renewables North America LLC | 78103 Nada Substation 138kV | Colorado | SOUTH | 2023-11-30 | OTH | BA | 51.3 |  | 2022-04-20 | 2021-08-12 | 2021-10-29 | 2022-04-06 |  |  |  | No |  |  | Not Required
23INR0324 | Fox Pen Storage | SS Completed, FIS Started, No IA | EDP Renewables North America LLC | 138 kV Tap 3110 Stryker Creek - 3147 Troup | Cherokee | NORTH | 2025-03-14 | OTH | BA | 51.3 | COD | 2022-04-20 | 2021-08-12 | 2021-10-29 | 2022-04-06 |  |  |  | No |  |  | Not Required
23INR0330 | BRP Snowdon BESS | SS Completed, FIS Started, No IA | BRP SNOWDON BESS LLC | 23914 Tule Canyon Substation 345kV | Briscoe | PANHANDLE | 2024-02-16 | OTH | BA | 410.94 |  | 2021-09-15 | 2021-09-15 | 2021-11-29 | 2021-09-08 |  |  |  | No |  |  | Not Required
23INR0331 | Talitha BESS | SS Completed, FIS Completed, No IA | Talitha Energy Project, LLC | 5660 Orange Grove Switching Station 138 kV | Jim Wells | SOUTH | 2023-05-01 | OTH | BA | 61.39 |  | 2021-07-20 | 2021-07-15 | 2021-09-28 | 2021-07-15 | 2022-05-03 | No |  | No |  |  | Not Required
23INR0332 | Backwater Solar | SS Completed, FIS Started, No IA | Backwater Solar LLC | Tap 138 kV line from Spring (#684) - Leo(#685) | Cooke | NORTH | 2024-05-31 | SOL | PV | 80 |  | 2021-09-17 | 2021-08-24 | 2021-11-15 | 2021-08-24 |  |  |  | No |  |  | Not Required
23INR0334 | Liberty Senate Energy Storage 1 | SS Completed, FIS Started, No IA | Senate Solar LLC | 1445 Burwick 345kV | Jack | NORTH | 2025-03-24 | OTH | BA | 207.4 |  | 2021-09-16 | 2021-10-05 | 2021-12-08 | 2021-10-03 |  |  |  | No | Not Required | Not Required | Not Required
23INR0335 | BRP Bachman BESS | SS Completed, FIS Started, No IA | BRP Bachman BESS LLC | 44040 BAILEY 345kV | Wharton | SOUTH | 2023-11-01 | OTH | BA | 411.04 |  | 2021-10-05 | 2021-10-05 | 2021-12-08 | 2021-09-14 |  |  |  | No |  |  | Not Required
23INR0336 | Bypass Battery Storage | SS Completed, FIS Started, No IA | Parish Storage | 44000 W_A_P__POI5A 345 kV | Fort Bend | HOUSTON | 2024-09-01 | OTH | BA | 206.9 |  | 2022-02-18 | 2021-08-18 | 2021-11-05 | 2022-02-03 |  |  |  | No | Not Required | Not Required | Not Required
23INR0339 | Remy Jade Power Station | SS Completed, FIS Completed, No IA | Remy Jade Generating, LLC | Tap 138 kV line from Crosby (#40390) to Highlands (#40811)” | Harris | HOUSTON | 2024-04-01 | GAS | GT | 408 |  | 2021-08-24 | 2021-08-24 | 2021-11-15 | 2021-08-13 | 2022-02-23 |  |  | No
23INR0340 | Larkspur Energy Storage | SS Completed, FIS Started, No IA | Larkspur Energy Storage | 71213 Benedum 138kV | Upton | WEST | 2023-05-31 | OTH | BA | 307.46 |  | 2021-07-30 | 2021-08-02 | 2021-10-25 | 2021-07-27 |  |  |  | No | Not Required | Not Required | Not Required
23INR0342 | BRP Brizo BESS | SS Completed, FIS Started, No IA | BRP Brizo BESS LLC | 138 kV Loop 463 Substation (#5680) | Victoria | SOUTH | 2024-12-01 | OTH | BA | 143.85 | COD | 2021-10-05 | 2021-10-05 | 2021-12-22 | 2021-09-24 |  |  |  | No |  |  | Not Required
23INR0343 | Guajillo Energy Storage | SS Completed, FIS Started, IA | Guajillo Energy Storage LLC | 80219 Lobo Substation 345kV | Webb | SOUTH | 2023-06-11 | OTH | BA | 201.09 | Status Change INA-to-PLN | 2021-08-02 | 2021-08-09 | 2021-11-01 | 2021-07-27 |  | No | 2021-12-21 | Yes | Not Required | Not Required | Not Required | 2022-06-27
23INR0344 | XE Hermes Solar | SS Completed, FIS Started, No IA | Bell Solar 1 LLC | 3675 Rogers Substation 138kV | Bell | NORTH | 2024-12-31 | SOL | PV | 101.01 | FIS Request | 2022-06-14 | 2021-09-21 | 2021-12-09 | 2022-06-01 |  |  |  | No |  |  | Not Required
23INR0345 | Elmax Power Station | SS Completed, FIS Started, No IA | Elmax Generating, LLC | Tap 138 kV Lake Houston (#40820) - Atascocita (#40130) ckt 66 | Harris | HOUSTON | 2024-06-01 | GAS | GT | 518.83 |  | 2021-09-14 | 2021-09-14 | 2021-11-30 | 2021-09-14 |  |  |  | No | Not Required | Not Required
23INR0348 | Aggie Energy storage | SS Completed, FIS Started, No IA | KINGFISHER ENERGY STORAGE LLC | TABOR RD (#32882) | Brazos | NORTH | 2023-06-30 | OTH | BA | 102.49 |  | 2021-08-13 | 2021-08-16 | 2021-11-05 | 2021-08-13 |  |  |  | No |  |  | Not Required
23INR0349 | Tokio Solar | SS Completed, FIS Started, No IA | Gransolar Texas Eight, LLC | Tap 138kV 3592 Waco Atco - 170 Cotton Belt | McLennan | NORTH | 2024-10-31 | SOL | PV | 175 |  | 2022-05-04 | 2021-08-12 | 2021-11-01 | 2022-04-14 |  |  |  | No |  |  | Not Required
23INR0351 | Seven Flags BESS | SS Completed, FIS Started, No IA | Seven Flags BESS LLC | 8295 Wormser Substation 138kV | Webb | SOUTH | 2023-06-01 | OTH | BA | 106.15 |  | 2021-09-01 | 2021-09-01 | 2021-11-22 | 2021-08-19 |  |  |  | No | Not Required | Not Required | Not Required
23INR0352 | Blue Valley Solar | SS Completed, FIS Started, No IA | Blue Valley Solar, LLC | Tap on the 138 kV Comstock(#8683) - Corral Line(#60389) | Val Verde | WEST | 2023-12-29 | SOL | PV | 147.99 |  | 2021-11-12 | 2021-11-16 | 2022-01-17 | 2021-11-04 |  |  |  | No | Not Required | Not Required | Not Required
23INR0354 | Bordertown BESS | SS Completed, FIS Started, No IA | Bordertown BESS LLC | 8796 Roma 138kV | Starr | SOUTH | 2023-06-01 | OTH | BA | 106.15 |  | 2021-08-17 | 2021-09-01 | 2021-11-22 | 2021-08-19 |  |  |  | No | Not Required | Not Required | Not Required
23INR0357 | BRP Yarra BESS | SS Completed, FIS Started, No IA | BRP Yarra BESS LLC | 138 kV Lake Crest bus #(12492) | Dallas | NORTH | 2024-03-01 | OTH | BA | 205.36 |  | 2021-10-05 | 2021-10-05 | 2021-12-22 | 2021-09-24 |  |  |  | No |  |  | Not Required
23INR0358 | BRP Castor BESS | SS Completed, FIS Started, No IA | BRP Castor BESS LLC | 138 kV West Columbia Local Substation (#39530) | Brazoria | COASTAL | 2023-12-01 | OTH | BA | 205.35 |  | 2021-10-01 | 2021-10-04 | 2021-12-22 | 2021-09-24 |  |  |  | No | Not Required | Not Required | Not Required
23INR0359 | BRP Crios BESS | SS Completed, FIS Started, No IA | BRP Crios BESS LLC | Tap 138 kV 1649 HASSE_P8 - 1684 SABANA_8 | Comanche | NORTH | 2024-06-16 | OTH | BA | 87.37 |  | 2021-10-18 | 2021-10-18 | 2022-01-07 | 2021-09-30 |  |  |  | No |  |  | Not Required
23INR0360 | BRP Charon BESS | SS Completed, FIS Started, No IA | BRP Charon BESS LLC | 44000 WA Parish 345kV | Fort Bend | HOUSTON | 2023-11-01 | OTH | BA | 410.81 |  | 2021-10-08 | 2021-10-08 | 2021-12-22 | 2021-09-24 |  |  |  | No |  |  | Not Required
23INR0361 | Third Coast BESS | SS Completed, FIS Started, No IA | Third Coast BESS LLC | 8125 Lolita substation 138kV | Jackson | SOUTH | 2023-06-01 | OTH | BA | 101.21 |  | 2021-09-16 | 2021-08-24 | 2021-11-16 | 2021-09-01 |  |  |  | No | Not Required | Not Required | Not Required
23INR0363 | Brazos Bend BESS | SS Completed, FIS Completed, No IA | Brazos Bend BESS LLC | 138 kV Fort Bend Switch (#44280) | Fort Bend | HOUSTON | 2023-06-01 | OTH | BA | 101.21 |  | 2021-09-17 | 2021-08-24 | 2021-11-16 | 2021-09-01 | 2022-06-23 |  |  | No |  |  | Not Required
23INR0364 | Tierra Seca BESS | SS Completed, FIS Started, No IA | Tierra Seca BESS LLC | 138kV 8255 HAMILTON4A (Hamilton Road Substation) | Val Verde | WEST | 2023-06-01 | OTH | BA | 101.21 |  | 2021-09-14 | 2021-08-24 | 2021-11-16 | 2021-09-01 |  |  |  | No | Not Required | Not Required | Not Required
23INR0366 | Amsterdam Solar II | SS Completed, FIS Started, No IA | Amsterdam Solar II, LLC | tap 345kV 43035 Oasis - 42500 Dow c27 (Same POI as 21INR0256) | Brazoria | COASTAL | 2023-08-17 | SOL | PV | 509.88 | COD | 2021-12-02 | 2021-08-12 | 2021-10-29 | 2021-11-18 |  |  |  | No |  |  | Not Required
23INR0367 | Fewell Solar | SS Completed, FIS Started, No IA | Belltown Power Texas | Tap 138kV 3597 Groesbeck - 3634 Groesbeck Main | Limestone | NORTH | 2024-05-31 | SOL | PV | 203.5 |  | 2022-02-28 | 2021-08-19 | 2021-11-05 | 2022-02-17 |  |  |  | No |  |  | Not Required
23INR0369 | Anemoi Energy Storage | SS Completed, FIS Started, IA | Anemoi Energy Storage, LLC | 8574 POMELO 345kV | Hidalgo | SOUTH | 2023-05-31 | OTH | BA | 205 |  | 2021-09-03 | 2021-09-03 | 2021-11-18 | 2021-08-24 |  |  | 2022-01-05 | Yes |  |  | Not Required
23INR0371 | Rodeo Ranch Energy Storage | SS Completed, FIS Started, IA | Rodeo Ranch Energy Storage, LLC | 38021 WORSHAM 138kV | Reeves | WEST | 2023-05-31 | OTH | BA | 307.46 | SFS/NtP | 2021-09-07 | 2021-09-07 | 2021-11-18 | 2021-08-27 |  |  | 2022-02-01 | Yes |  |  | Not Required
23INR0372 | Cross Trails Storage | SS Completed, FIS Started, No IA | Cross Trails Energy Storage Project, LLC | 60090 WKN Breaker 69kV | Scurry | WEST | 2023-12-31 | OTH | BA | 41.33 |  | 2021-11-03 | 2021-11-03 | 2022-01-17 | 2021-10-29 |  |  |  | No |  |  | Not Required
23INR0373 | Fronton Solar 1 | SS Completed, FIS Started, No IA | Meshek USA Inc. | 8796 Roma Substation 138kV | Starr | SOUTH | 2023-07-01 | SOL | PV | 132.7 |  | 2021-10-05 | 2021-10-05 | 2021-12-22 | 2021-09-17 |  |  |  | No | Not Required | Not Required | Not Required
23INR0374 | Grand Acres | SS Completed, FIS Started, No IA | Meshek USA Inc. | 8359 South Santa Rosa 138 kV | Cameron | COASTAL | 2023-07-01 | SOL | PV | 153.03 |  | 2021-10-06 | 2021-10-07 | 2021-12-22 | 2021-10-06 |  |  |  | No | Not Required | Not Required | Not Required
23INR0375 | Backwater Storage | SS Completed, FIS Started, No IA | Backwater Solar LLC | Tap 138 kV 684 Spring - 685 Leo | Cooke | NORTH | 2024-05-31 | OTH | BA | 100 |  | 2021-09-02 | 2021-09-17 | 2021-12-06 | 2021-09-17 |  |  |  | No |  |  | Not Required
23INR0376 | Cascade Storage | SS Completed, FIS Started, No IA | Oyster Creek LLC | Tap 345kV 42500 Dow - 43035 Oasis Ckt 18 | Brazoria | COASTAL | 2024-05-31 | OTH | BA | 250 |  | 2021-09-09 | 2021-09-09 | 2021-11-29 | 2021-09-09 |  |  |  | No |  |  | Not Required
23INR0378 | Heartfield Storage | SS Completed, FIS Started, No IA | Belltown Power Texas | 138kV Weslaco Unit (Bus #8348) | Hidalgo | SOUTH | 2023-05-31 | OTH | BA | 152 |  | 2021-09-10 | 2021-09-10 | 2021-11-29 | 2021-09-01 |  |  |  | No | Not Required | Not Required | Not Required
23INR0381 | Soportar ESS | SS Completed, FIS Started, No IA | Bexar ESS LLC | 5007 Alamo One 138kV | Bexar | SOUTH | 2024-08-30 | OTH | BA | 102.11 |  | 2022-01-05 | 2021-09-21 | 2021-12-06 |  |  |  |  | No |  |  | Not Required
23INR0382 | Outer Loop BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage | 40700 Greens Bayou 345kV | Harris | HOUSTON | 2024-11-01 | OTH | BA | 201.2 |  | 2022-05-02 | 2021-09-29 | 2021-12-06 | 2022-04-19 |  |  |  | No |  |  | Not Required
23INR0385 | Camp Creek Solar SLF | SS Completed, FIS Started, No IA | White Rock Solar, LLC | TAP 345 KV 3400 TWIN OAK SWITCH - 46020 LIMESTONE PLANT CIRCUIT 1 | Robertson | NORTH | 2023-11-30 | SOL | PV | 165.6 |  | 2021-12-17 | 2021-12-24 | 2022-03-17 | 2021-12-09 |  |  |  | No |  |  | Not Required
23INR0387 | Pioneer DJ Wind | SS Completed, FIS Started, No IA | Pioneer Hutt Wind Energy LLC | 138 kV Driver station (Bus #: 23863) | Midland | WEST | 2023-09-20 | WIN | WT | 160 |  | 2021-10-11 | 2021-10-11 | 2021-12-22 | 2021-10-07 |  |  |  | No | Not Required | Not Required | Not Required
23INR0388 | White Wing I Energy Storage | SS Completed, FIS Started, No IA | White Wing I Energy Storage LLC | 8418 Rincon Station 138 kV | San Patricio | COASTAL | 2023-03-01 | OTH | BA | 101.63 |  | 2021-10-05 | 2021-10-05 | 2021-12-10 | 2021-09-28 |  |  |  | No | Not Required | Not Required | Not Required
23INR0389 | White Wing II Energy Storage | SS Completed, FIS Started, No IA | White Wing II Energy Storage LLC | 8418 Rincon Station 138 kV | San Patricio | COASTAL | 2023-03-01 | OTH | BA | 101.63 |  | 2021-10-05 | 2021-10-05 | 2021-12-10 | 2021-09-28 |  |  |  | No | Not Required | Not Required | Not Required
23INR0391 | THUNDER ROAD ENERGY STORAGE | SS Completed, FIS Started, No IA | Hecate Grid Thunder Road Storage LLC | 12491 FISH CREEK 138KV | Wood | NORTH | 2023-10-01 | OTH | BA | 184 | MW Size | 2021-12-29 | 2021-10-22 | 2022-01-17 | 2021-12-17 |  |  |  | No |  |  | Not Required
23INR0392 | Honeycomb Storage SLF | SS Completed, FIS Started, No IA | Tynan Solar, LLC | 69 kV Tynan Substation (#8107) | Bee | SOUTH | 2024-06-01 | OTH | BA | 0 | COD | 2021-10-26 | 2021-11-16 | 2022-01-17 | 2021-11-02 |  |  |  | No | Not Required | Not Required | Not Required
23INR0401 | Headcamp | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners | tap 138kV 38330 TN Alamo St – 38455 TN Holiday | Pecos | WEST | 2024-01-24 | OTH | BA | 150 |  | 2022-02-11 | 2021-12-03 | 2022-02-28 | 2022-01-21 |  |  |  | No | Not Required | Not Required | Not Required
23INR0403 | Connolly Storage | SS Completed, FIS Started, No IA | Belltown Power Texas | Tap 138kV 1568 Allison – 11568 Flatwood | Wise | NORTH | 2024-05-31 | OTH | BA | 203 |  | 2021-10-27 | 2021-10-27 | 2021-12-29 | 2021-10-27 |  |  |  | No |  |  | Not Required
23INR0408 | TECO GTG2 | SS Completed, FIS Started, No IA | Thermal Energy Corp. | 47430 TECO 138 kV | Harris | HOUSTON | 2023-05-01 | GAS | GT | 50 |  | 2021-12-09 | 2021-11-04 | 2022-01-31 | 2021-12-01 |  | No |  | No | 2022-06-22 | Not Required | 2022-06-22
23INR0409 | Sunbelt Storage | SS Completed, FIS Started, No IA | Belltown Power Texas | Tap 138kV 6902 Talty - 6894 Rose Hill | Kaufman | NORTH | 2023-12-31 | OTH | BA | 52 |  | 2021-11-09 | 2021-11-12 | 2022-02-08 | 2021-11-09 |  |  |  | No |  |  | Not Required
23INR0414 | Flag City Storage SLF | SS Completed, FIS Started, No IA | Flag City Storage | tap 138kV 5588 Red Bluff - 5546 Danevang | Jackson | SOUTH | 2024-05-31 | OTH | BA | 0 |  | 2021-11-16 | 2021-11-18 | 2022-02-08 | 2021-11-18 |  |  |  | No | Not Required | Not Required | Not Required
23INR0418 | Angelo Storage | SS Completed, FIS Started, No IA | Angelo Storage, LLC | 76009 Twin Buttes 345kV | Tom Green | WEST | 2023-10-31 | OTH | BA | 175.65 |  | 2021-11-15 | 2021-11-22 | 2022-02-15 | 2021-11-16 |  |  |  | No |  |  | Not Required
23INR0419 | SOHO BESS | SS Completed, FIS Completed, No IA | Black Mountain Energy Storage | 43035 Oasis 345kV | Brazoria | COASTAL | 2024-06-01 | OTH | BA | 206.32 | COD | 2021-12-13 | 2021-12-03 | 2022-02-28 | 2021-12-03 | 2022-06-28 | No |  | No | Not Required | Not Required | Not Required
23INR0421 | Tidwell Prairie IV Energy Storage | SS Completed, FIS Started, No IA | Tidwell Prairie IV Energy Storage LLC | Tap TNP ONE 39950 and Twin Oak 3400 | Robertson | NORTH | 2023-12-01 | OTH | BA | 304.9 |  | 2021-11-15 | 2021-11-15 | 2022-02-11 | 2021-11-09 |  |  |  | No |  |  | Not Required
23INR0422 | Masroor Storage | SS Completed, FIS Started, No IA | Belltown Power Texas | Bus #1760 Bonham 138kV | Fannin | NORTH | 2024-05-31 | OTH | BA | 203 |  | 2021-11-16 | 2021-11-16 | 2022-02-12 | 2021-11-16 |  |  |  | No |  |  | Not Required
23INR0423 | Camp creek storage SLF | SS Completed, FIS Started, No IA | White Rock Solar | TAP 345 KV 3400 TWIN OAK SWITCH - 46020 LIMESTONE PLANT CIRCUIT 1 | Robertson | NORTH | 2024-08-31 | OTH | BA | 82.8 |  | 2021-12-24 | 2021-12-24 | 2022-03-17 | 2021-12-21 |  |  |  | No |  |  | Not Required
23INR0429 | Shaw Storage | SS Completed, FIS Started, No IA | Montague Solar, LLC | Tap 138kV 7146 Verde Creek - 7438 Bandera | Bandera | SOUTH | 2024-05-31 | OTH | BA | 28 |  | 2022-01-10 | 2022-01-13 | 2022-04-11 | 2021-12-29 |  |  |  | No | Not Required | Not Required | Not Required
23INR0431 | BRP Pollux BESS | SS Completed, FIS Started, No IA | BRP Pollux BESS LLC | 138 kV Olsen Switching Station (#37460) | Bosque | NORTH | 2024-06-01 | OTH | BA | 163.42 |  | 2021-12-20 | 2022-01-06 | 2022-03-16 | 2022-01-04 |  |  |  | No | Not Required | Not Required | Not Required
23INR0438 | Eiffel Solar II | SS Completed, FIS Started, No IA | PARIS SOLAR FARM, LLC | Double Tap 138kV: 1693 Paris SW - 11770 Lamar Blossom Ckt1 1693 Paris SW - 1768 Deport Rea Ckt1 | Lamar | NORTH | 2023-05-15 | SOL | PV | 41.74 | COD | 2022-01-12 | 2022-01-06 | 2022-04-01 | 2022-01-05 |  |  |  | No |  |  | Not Required
23INR0439 | Smokey Willie Solar | SS Completed, FIS Started, No IA | Smokey Willie Solar | 3114 Palestine Alcoa 138kV | Anderson | NORTH | 2023-12-30 | SOL | PV | 200.5 |  | 2021-12-29 | 2022-01-06 | 2022-03-31 | 2021-12-29 |  |  |  | No |  |  | Not Required
23INR0455 | Bessie Storage | SS Completed, FIS Started, No IA | Duke Energy Renewables Storage, LLC | Tap 345kV 80355 Del Sol - 80368 LV4 Bridge | Starr | SOUTH | 2023-12-01 | OTH | BA | 0 |  | 2022-02-08 | 2022-02-21 | 2022-05-19 | 2022-02-07 |  |  |  | No | Not Required | Not Required | Not Required
23INR0456 | Bronze Quinta Storage | SS Completed, FIS Started, No IA | KCE TX 28, LLC | S_MCALLN 8371 (S. McAllen 138kV Substation) | Hidalgo | SOUTH | 2023-12-01 | OTH | BA | 103.51 |  | 2022-01-12 | 2022-01-13 | 2022-04-11 | 2022-01-11 |  |  |  | No | Not Required | Not Required | Not Required
23INR0457 | Hive Hollows Storage | SS Completed, FIS Started, No IA | KCE TX 27, LLC | 3415 TEMPLE SWITCH 138kV | Bell | NORTH | 2023-12-01 | OTH | BA | 103.51 |  | 2022-06-30 | 2022-01-28 | 2022-04-26 | 2022-01-18 |  |  |  | No |  |  | Not Required
23INR0460 | GULF STAR STORAGE SLF | SS Started, FIS Started, No IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2023-12-31 | OTH | BA | 150.3 |  | 2022-05-18 | 2022-06-02 |  | 2022-05-11 |  |  |  | No |  |  | Not Required
23INR0462 | Palladium Storage | SS Completed, FIS Started, No IA | Belltown Power Texas | 138kV Wesmer 8347 | Hidalgo | SOUTH | 2024-05-31 | OTH | BA | 152 |  |  | 2022-02-28 | 2022-05-27 | 2022-01-21 |  |  |  | No |  |  | Not Required
23INR0466 | Shoshana Storage | SS Completed, FIS Started, No IA | HQC Solar Holdings 1, LLC | Tap 345kV 5915 South Texas Project (SO_TEX_345A) - 47531 Jones Creek (JONCRK18LR) Ckt 18 | Matagorda | COASTAL | 2023-12-31 | OTH | BA | 221.92 |  | 2022-05-31 | 2022-03-30 | 2022-06-26 | 2022-05-16 |  |  |  | No |  |  | Not Required
23INR0468 | Petunia Storage Project | SS Completed, FIS Started, No IA | HQC Solar Holdings 1, LLC | 3675 ROGERS 138kV (ROGERS1A_8) | Milam | SOUTH | 2023-12-31 | OTH | BA | 231.86 |  | 2022-04-14 | 2022-03-12 | 2022-06-02 | 2022-04-01 |  |  |  | No |  |  | Not Required
23INR0470 | BoCo BESS | SS Started, FIS Started, No IA | BoCo BESS | 59906 Long Draw 138kV | Borden | WEST | 2023-09-30 | OTH | BA | 153.34 |  | 2022-05-17 | 2022-05-10 |  | 2022-05-03 |  |  |  | No | Not Required | Not Required | Not Required
23INR0472 | Frontera Energy Center | SS Completed, FIS Started, No IA | Frontera Generation Limited Partnership | 8980 FRONTERA4A 138kV | Hidalgo | SOUTH | 2023-06-30 | GAS | CC | 524 |  | 2022-04-01 | 2022-04-01 | 2022-06-28 | 2022-04-01 |  |  |  | No
23INR0474 | AP Greenport | SS Started, FIS Started, No IA | AP Greenport | Austrop – Lost Pines 345 kV transmission line (Bus #7040 – 9041) | Travis | SOUTH |  | OTH | BA | 100 | FIS Request |  | 2022-06-10 |  | 2022-06-24 10:37 |  |  |  | No |  |  | Not Required
23INR0478 | XE Rhoda Storage | SS Started, FIS Started, No IA | Milam 2 Solar LLC | Tap 138kV 32 Robertson - 64 Milano | Milam | SOUTH | 2024-02-28 | OTH | BA | 34.67 |  | 2022-03-31 | 2022-04-18 |  | 2022-03-18 |  |  |  | No |  |  | Not Required
23INR0482 | RABBS U2 Power Station | SS Completed, FIS Completed, IA | Braes Bayou Generating, LLC | 44650 Smithers 345kV | Fort Bend | HOUSTON | 2022-07-19 | GAS | GT | 51 | Proj Name MW Size COD | 2018-12-06 |  |  |  | 2020-09-25 | No | 2020-11-18 | Yes |  |  |  | 2021-04-01 | 2021-06-03 | 2021-07-27 |  |  | 2022-02-28 | 2022-06-24
23INR0485 | Hacienda Storage | SS Started, FIS Started, No IA | Belltown Power Texas | 38745 Attwater 138kV | Galveston | HOUSTON | 2023-12-31 | OTH | BA | 203 |  | 2022-04-20 | 2022-05-10 |  | 2022-04-04 |  |  |  | No |  |  | Not Required
23INR0494 | Cartwheel BESS 1 | SS Started, FIS Started, No IA | RWE Renewables | 1697 Sulphur Springs Switch 345kV | Hopkins | NORTH | 2023-12-12 | OTH | BA | 150 |  | 2022-05-20 | 2022-06-02 |  | 2022-05-10 |  |  |  | No |  |  | Not Required
23INR0495 | Cartwheel BESS 2 | SS Started, FIS Started, No IA | RWE Renewables | 1697 Sulphur Springs Switch 345kV | Hopkins | NORTH | 2023-12-15 | OTH | BA | 150 |  | 2022-05-20 | 2022-06-02 |  | 2022-05-10 |  |  |  | No |  |  | Not Required
23INR0496 | San Perlita BESS 1 | SS Started, FIS Started, No IA | RWE Renewables | 8601 Cebolla 345kV | Willacy | COASTAL | 2023-12-15 | OTH | BA | 150 |  | 2022-05-20 | 2022-06-02 |  | 2022-05-10 |  |  |  | No |  |  | Not Required
23INR0497 | San Perlita BESS 2 | SS Started, FIS Started, No IA | RWE Renewables | 8601 Cebolla 345kV | Willacy | COASTAL | 2023-12-15 | OTH | BA | 150 |  | 2022-05-20 | 2022-06-02 |  | 2022-05-10 |  |  |  | No |  |  | Not Required
24INR0003 | Stem Solar | SS Completed, FIS Started, No IA | Innovative Solar 134, LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala | Swisher | PANHANDLE | 2024-05-28 | SOL | PV | 200 |  | 2020-12-03 | 2020-02-04 | 2020-04-27 | 2020-10-22 |  |  |  | No |  |  | Not Required
24INR0004 | Ponil Solar | SS Completed, FIS Started, No IA | Innovative Solar 377, LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2024-05-24 | SOL | PV | 145 |  | 2020-12-03 | 2020-02-04 | 2020-04-29 | 2020-10-22 |  |  |  | No |  |  | Not Required
24INR0007 | Nockenut Springs Solar 2 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Guadalupe | SOUTH | 2024-12-31 | SOL | PV | 203.26 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No |  |  | Not Required
24INR0010 | Pinnington Solar | SS Completed, FIS Started, No IA | Hecate Energy Longhorn Solar LLC | tap both 345kV 1430 Graham - 1436 Parker 345kV lines | Jack | NORTH | 2025-04-15 | SOL | PV | 666.1 |  | 2020-11-03 | 2020-12-03 | 2021-02-17 | 2020-11-10 |  |  |  | No |  |  | Not Required
24INR0011 | Pinnington Storage | SS Completed, FIS Started, No IA | Hecate Energy Longhorn Storage LLC | tap both 345kV 1430 Graham - 1436 Parker 345kV lines | Jack | NORTH | 2025-04-15 | OTH | BA | 508.7 |  | 2020-11-10 | 2020-12-03 | 2021-02-17 | 2020-11-10 |  |  |  | No |  |  | Not Required
24INR0015 | Five Wells Solar | SS Completed, FIS Completed, No IA | Five Wells Solar Center LLC | 3687 Bell Country East 345kV | Bell | NORTH | 2023-12-29 | SOL | PV | 355.4 |  | 2021-02-18 | 2021-02-04 | 2021-04-21 | 2021-01-22 | 2022-05-24 |  |  | No |  |  | Not Required
24INR0020 | Percy Farm Solar | SS Completed, FIS Started, No IA | Percy Farm Solar 1, LLC | Tap 345kV 8123 Blessing - 5915 STP | Matagorda | COASTAL | 2024-03-01 | SOL | PV | 198.63 |  | 2021-08-05 | 2021-03-16 | 2021-06-11 | 2021-07-21 |  |  |  | No | Not Required | Not Required | Not Required
24INR0022 | Boxcar Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345kV 1907 Venus N - 68091 Navarro | Ellis | NORTH | 2024-05-15 | SOL | PV | 355.82 |  | 2021-03-25 | 2021-03-31 | 2021-06-17 | 2021-03-17 |  |  |  | No |  |  | Not Required
24INR0023 | Compadre Solar | SS Completed, FIS Started, No IA | Hill Solar I, LLC | tap 345kV 68090 Sam Switch - 1907 Venus | Hill | NORTH | 2024-10-01 | SOL | PV | 405.31 |  | 2021-03-29 | 2021-03-16 | 2021-05-28 | 2021-03-08 |  |  |  | No |  |  | Not Required
24INR0025 | Clarion Solar | SS Completed, FIS Started, No IA | IBV Energy Partners LLC | 5290 Lytle 138kV | Medina | SOUTH | 2024-08-01 | SOL | PV | 180 |  | 2021-11-15 | 2021-03-01 | 2021-05-13 | 2021-11-08 |  |  |  | No |  |  | Not Required
24INR0031 | Stoneridge Solar | SS Completed, FIS Started, No IA | Stoneridge Solar, LLC | Tap 345 kV 13429 SANDOW SWITCH - 7040 AUSTROP | Milam | SOUTH | 2023-12-15 | SOL | PV | 200 |  | 2022-02-14 | 2021-10-08 | 2022-01-03 | 2022-01-31 |  |  |  | No | Not Required | Not Required | Not Required
24INR0038 | SP Jaguar Solar | SS Completed, FIS Started, No IA | SP-Jaguar Solar LLC | Tap 345kV 13405 Tradinghouse SES - 68090 Sam Switch | McLennan | NORTH | 2024-04-30 | SOL | PV | 300 |  | 2021-07-23 | 2021-03-18 | 2021-06-11 | 2021-07-15 |  |  |  | No |  |  | Not Required
24INR0039 | SP Jaguar BESS | SS Completed, FIS Started, No IA | SP-Jaguar Solar LLC | Tap 345kV 13405 Tradinghouse SES - 68090 Sam Switch | McLennan | NORTH | 2024-04-30 | OTH | BA | 300 |  | 2021-08-13 | 2021-03-18 | 2021-06-11 | 2021-07-15 |  |  |  | No |  |  | Not Required
24INR0040 | Rosebud Solar | SS Completed, FIS Started, No IA | Rosebud Solar, LLC | tap 69kV 65 Silver City - 69 Barclay | Falls | NORTH | 2024-02-29 | SOL | PV | 112.64 |  | 2022-01-12 | 2021-04-13 | 2021-07-06 | 2022-01-10 |  |  |  | No |  |  | Not Required
24INR0041 | Rock N' Roll Solar SLF | SS Completed, FIS Started, No IA | Rock N Roll Solar | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2024-12-31 | SOL | PV | 151.97 |  | 2022-02-10 | 2021-05-10 | 2021-07-30 | 2022-01-20 |  |  |  | No | Not Required | Not Required | Not Required
24INR0042 | Yaupon Solar SLF | SS Completed, FIS Started, No IA | Yaupon Solar, LLC | tap 345kV 3687 Bell Co East - 39950 TNP One | Milam | SOUTH | 2024-10-01 | SOL | PV | 204.08 |  | 2021-12-07 | 2021-03-30 | 2021-06-17 | 2021-11-23 |  |  |  | No |  |  | Not Required
24INR0044 | Brass Fork Solar 2 | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345kV 60703 Gauss - 60514 Clear Crossing (60712 QUASAR) | Haskell | WEST | 2024-12-01 | SOL | PV | 208.41 |  | 2021-11-02 | 2021-11-04 | 2020-03-06 | 2021-11-04 |  |  |  | No |  |  | Not Required
24INR0053 | Quarter Horse Solar | SS Completed, FIS Started, No IA | Quarter Horse Solar, LLC | tap 345kV 8689 Tango - 8606 Goddard | Bee | SOUTH | 2024-07-31 | SOL | PV | 204.08 |  | 2021-08-05 | 2021-05-06 | 2021-07-28 | 2021-07-21 |  |  |  | No |  |  | Not Required
24INR0056 | Pradera Solar | SS Completed, FIS Started, No IA | Pradera Solar, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2024-10-31 | SOL | PV | 118 |  | 2021-06-02 | 2021-07-08 | 2021-09-28 | 2021-06-23 |  |  |  | No |  |  | Not Required
24INR0057 | Hanson Storage | SS Completed, FIS Started, No IA | Hanson Solar, LLC | tap 345kV 1444 Brown - 11406 Central Bluff | Coleman | WEST | 2024-05-31 | OTH | BA | 101.39 |  | 2021-08-23 | 2021-06-21 | 2021-09-08 | 2021-08-19 |  |  |  | No |  |  | Not Required
24INR0058 | Briggs Storage | SS Completed, FIS Started, No IA | Briggs Solar, LLC | tap 345kV 60514 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2024-12-31 | OTH | BA | 70.39 | MW Size | 2022-03-18 | 2021-05-31 | 2021-08-18 | 2022-03-04 |  |  |  | No |  |  | Not Required
24INR0059 | Cuchillas Solar | SS Completed, FIS Started, No IA | Gransolar Texas Two, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2024-11-21 | SOL | PV | 301.6 | MW Size | 2022-02-24 | 2021-06-02 | 2021-08-18 | 2022-02-11 |  |  |  | No |  |  | Not Required
24INR0061 | Eighteenmile Solar SLF | SS Completed, FIS Started, No IA | Weser Solar, LLC | Tap 138kV 5730 Four Corners - 5728 Choate | Goliad | SOUTH | 2024-07-31 | SOL | PV | 153.06 |  | 2021-09-02 | 2021-08-18 | 2021-11-05 | 2021-08-24 |  |  |  | No |  |  | Not Required
24INR0062 | Eighteenmile Storage SLF | SS Completed, FIS Started, No IA | Weser Solar, LLC | Tap 5730 Four Corners to 5728 Choate 138 kV | Goliad | SOUTH | 2024-07-31 | OTH | BA | 0 |  | 2022-01-12 | 2021-12-29 | 2022-02-08 | 2022-01-07 |  |  |  | No |  |  | Not Required
24INR0065 | Clip Road Solar 1 SLF | SS Completed, FIS Started, No IA | Clip Road Solar, LLC | Tap 345kV 8624 Grissom - 8164 Coleto Creek | Goliad | SOUTH | 2024-07-31 | SOL | PV | 204.08 |  | 2021-08-25 | 2021-06-17 | 2021-09-01 | 2021-07-29 |  |  |  | No | Not Required | Not Required | Not Required
24INR0066 | Clip Road Storage 1 SLF | SS Completed, FIS Started, No IA | Clip Road Solar, LLC | Tap 345kV 8624 Grissom - 8164 Coleto Creek | Goliad | SOUTH | 2024-07-31 | OTH | BA | 0 |  | 2022-01-20 | 2021-06-17 | 2021-09-01 | 2022-01-10 |  |  |  | No | Not Required | Not Required | Not Required
24INR0067 | KEYS HOLLOW SOLAR SLF | SS Completed, FIS Started, No IA | Clip Road Solar, LLC | TAP 345 KV LINE FROM COLETO 8164 - RAPTOR7A 8673 | Goliad | SOUTH | 2024-07-31 | SOL | PV | 204.08 |  | 2022-03-10 | 2021-06-17 | 2021-09-01 | 2022-03-04 |  |  |  | No |  |  | Not Required
24INR0068 | KEYS HOLLOW STORAGE SLF | SS Completed, FIS Started, No IA | Clip Road Solar, LLC | TAP 345 KV LINE FROM COLETO 8164 - RAPTOR7A 8673 | Goliad | SOUTH | 2024-07-31 | OTH | BA | 0 |  | 2022-03-10 | 2021-06-17 | 2021-09-01 | 2022-03-04 |  |  |  | No |  |  | Not Required
24INR0069 | Triple B Solar Alt#2 | SS Completed, FIS Started, No IA | Triple B Solar LLC | Tap 138kV 7066 Adamsville - 7064 Lampasas | Lampasas | NORTH | 2024-09-01 | SOL | PV | 150 |  | 2021-12-15 | 2021-06-10 | 2021-09-01 | 2021-11-15 |  |  |  | No |  |  | Not Required
24INR0070 | Sypert Branch Solar Project | SS Completed, FIS Started, No IA | Sypert Branch Solar LLC | Tap 345kV 13429 Sandow Switch - 3687 Bell County East Switch Ckt 1 | Milam | SOUTH | 2024-12-01 | SOL | PV | 261.78 |  | 2022-05-10 | 2021-09-21 | 2021-12-06 | 2022-04-28 |  |  |  | No |  |  | Not Required
24INR0073 | Hyacinth Storage | SS Completed, FIS Started, No IA | Hyacinth Storage, LLC | 46500 Tomball 345 kV | Harris | HOUSTON | 2023-12-01 | OTH | BA | 103.05 |  | 2022-04-02 | 2021-07-02 | 2021-09-22 | 2022-03-21 |  |  |  | No |  |  | Not Required
24INR0075 | Blue Bird Solar | SS Completed, FIS Started, No IA | Gigawatt Solar LLC | tap 345kV 1880 Rocky Creek - 1898 Mitchell Bend Switch | Johnson | NORTH | 2024-12-31 | SOL | PV | 1004 |  | 2021-11-10 | 2021-11-10 | 2022-02-07 | 2021-07-30 |  |  |  | No |  |  | Not Required
24INR0077 | Quarter Ranch Solar | SS Completed, FIS Started, No IA | Gransolar Texas Three LLC | 80223 Cenizo Substation 345kV | Zapata | SOUTH | 2024-03-15 | SOL | PV | 152.18 | MW Size | 2022-03-28 | 2021-07-13 | 2021-09-28 | 2022-03-23 |  |  |  | No |  |  | Not Required
24INR0078 | Apogee Wind II | SS Completed, FIS Started, No IA | King Creek Wind Farm 3, LLC | 60791 Perigee Substation 345kV | Throckmorton | WEST | 2023-12-01 | WIN | WT | 47.25 |  | 2021-12-29 | 2021-07-13 | 2021-09-20 | 2021-12-14 |  |  |  | No |  |  | Not Required
24INR0079 | Boxcar Solar 2 | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345 kV 1907 Venus N - 68091 Navarro | Ellis | NORTH | 2025-03-28 | SOL | PV | 257.1 |  | 2022-06-07 | 2021-07-13 | 2021-09-28 | 2022-05-23 |  |  |  | No |  |  | Not Required
24INR0081 | SANJAC BESS | SS Completed, FIS Started, No IA | Castleman Power | 40270 Riverside 138kV | Harris | HOUSTON | 2024-01-01 | OTH | BA | 208.63 |  | 2021-07-08 | 2021-07-08 | 2021-09-28 | 2021-07-08 |  |  |  | No |  |  | Not Required
24INR0086 | Pisgah Ridge Solar II | SS Completed, FIS Started, No IA | Duke Energy Renewables Solar, LLC | Tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2024-09-01 | SOL | PV | 101.89 |  | 2021-09-07 | 2021-07-14 | 2021-10-07 | 2021-08-25 |  |  |  | No | Not Required | Not Required | Not Required
24INR0087 | Pisgah Ridge Storage II | SS Completed, FIS Started, No IA | Duke Energy Renewables Solar, LLC | Tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2024-09-01 | OTH | BA | 101.36 |  | 2021-09-07 | 2021-07-14 | 2021-10-07 | 2021-08-25 |  |  |  | No | Not Required | Not Required | Not Required
24INR0088 | Tres Margaritas Solar | SS Completed, FIS Started, No IA | Gransolar Texas Six, LLC | Tap 138kV 8613 Big Wells – 8212 Dilley Switching Station | Dimmit | SOUTH | 2024-03-01 | SOL | PV | 60.95 |  | 2022-03-08 | 2021-07-13 | 2021-10-08 | 2022-02-21 |  |  |  | No |  |  | Not Required
24INR0091 | BRP Springbok Solar | SS Completed, FIS Started, No IA | Antelope Solar LLC | 23920 Blackwater Draw Switching Station 345kV | Hale | PANHANDLE | 2024-12-15 | SOL | PV | 202.39 |  | 2021-08-25 | 2021-08-25 | 2021-11-17 | 2021-08-02 |  |  |  | No | Not Required | Not Required | Not Required
24INR0093 | Oriana Solar | SS Completed, FIS Started, No IA | Oriana Solar LLC | Tap 138kV 5502 Rayburn - 5584 Vanderbilt | Victoria | SOUTH | 2024-03-31 | SOL | PV | 201.3 |  | 2021-08-25 | 2021-08-25 | 2021-11-17 | 2021-08-13 |  |  |  | No | Not Required | Not Required | Not Required
24INR0094 | Dovetail Solar 1 | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Solar Holdings LLC | Tap 345 KV 1421 Willow Creek - 60515 Clear Crossing Ckt 2 | Jack | NORTH | 2024-06-01 | SOL | PV | 666.1 | FIS Request | 2022-06-23 | 2021-09-21 | 2021-12-09 | 2022-06-06 |  |  |  | No |  |  | Not Required
24INR0096 | BRP Volga BESS | SS Completed, FIS Started, No IA | BRP Volga BESS LLC | 138 kV Seagoville Switch Substation (#2434; ONCOR) | Dallas | NORTH | 2024-12-01 | OTH | BA | 174.63 | COD | 2021-12-13 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No | Not Required | Not Required | Not Required
24INR0098 | Dovetail Storage | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Storage LLC | Tap 345 KV 1421 Willow Creek-60515 Clear Crossing CKT#2 | Jack | NORTH | 2024-06-01 | OTH | BA | 508.7 | FIS Request | 2022-06-20 | 2021-09-28 | 2021-12-03 | 2022-05-31 |  |  |  | No |  |  | Not Required
24INR0099 | Two Rivers Solar | SS Completed, FIS Started, No IA | Two Rivers Solar, LLC | Tap 138kV 64 Milano – 32 Robertson | Milam | SOUTH | 2024-10-11 | SOL | PV | 217 |  | 2021-07-27 | 2021-07-27 | 2021-10-21 | 2021-07-22 |  |  |  | No | Not Required | Not Required | Not Required
24INR0100 | Sheep Creek Storage | SS Completed, FIS Started, No IA | ENGIE IR Holdings | 68051 Reata 345kV | Callahan | WEST | 2023-12-29 | OTH | BA | 151.75 |  | 2022-06-02 | 2021-07-26 | 2021-10-22 | 2022-05-16 |  |  |  | No | Not Required | Not Required | Not Required
24INR0101 | Lampe Solar | SS Completed, FIS Started, No IA | Gransolar Texas Seven LLC | Tap 138 kV 7572 Gay Hill - 7573 Lyons | Washington | SOUTH | 2024-03-15 | SOL | PV | 60.24 |  | 2022-04-27 | 2021-08-03 | 2021-10-18 | 2022-04-14 |  |  |  | No |  |  | Not Required
24INR0103 | Opuntia Solar SLF | SS Completed, FIS Started, No IA | Opuntia Solar, LLC | tap 138kV 5607 Warburton - 8912 Medio Creek | Refugio | COASTAL | 2024-07-01 | SOL | PV | 102.04 |  | 2021-08-24 | 2021-08-24 | 2021-11-16 | 2021-08-09 |  |  |  | No | Not Required | Not Required | Not Required
24INR0104 | Braswell Solar | SS Completed, FIS Started, No IA | Gransolar Texas Nine, LLC | Tap 69kV 147 Lorena - 3580 Eddy Substation | McLennan | NORTH | 2024-10-31 | SOL | PV | 44.72 |  | 2022-04-20 | 2021-08-30 | 2021-11-18 | 2022-04-08 |  |  |  | No | Not Required | Not Required | Not Required
24INR0106 | Payne Battlecreek | SS Completed, FIS Started, No IA | Gransolar Texas Ten, LLC | tap 138kV 213 Haney - 3515 Hubbard | Hill | NORTH | 2024-10-31 | SOL | PV | 84.99 |  | 2022-03-23 | 2021-08-12 | 2021-10-29 | 2022-03-10 |  |  |  | No | Not Required | Not Required | Not Required
24INR0108 | Louisa Energy Storage | SS Completed, FIS Started, No IA | Viridity Energy Solutions Inc. | 138 kV Helotes (#5200) | Bexar | SOUTH | 2023-08-01 | OTH | BA | 102.77 |  | 2021-11-16 | 2021-11-16 | 2022-01-17 | 2021-11-08 |  |  |  | No | Not Required | Not Required | Not Required
24INR0109 | Oriana BESS | SS Completed, FIS Started, No IA | Oriana Solar LLC | Tap 138kV 5502 Rayburn - 5584 Vanderbilt | Victoria | SOUTH | 2024-03-31 | OTH | BA | 61.39 |  | 2022-02-24 | 2021-08-25 | 2021-11-17 | 2022-02-14 |  |  |  | No | Not Required | Not Required | Not Required
24INR0110 | Kildare | SS Completed, FIS Started, No IA | Galsol, LLC | 5524 Cordele 69 Sub 69 kV | Jackson | SOUTH | 2024-01-19 | SOL | PV | 70 |  | 2022-01-19 | 2022-01-28 | 2022-04-26 | 2022-01-18 |  |  |  | No |  |  | Not Required
24INR0111 | BRP Triton BESS | SS Completed, FIS Started, No IA | BRP Triton BESS LLC | 138 kV Comanche Switch Substation (#1441) | Comanche | NORTH | 2024-11-01 | OTH | BA | 205.36 |  | 2021-10-18 | 2021-10-18 | 2022-01-12 | 2021-10-08 |  |  |  | No | Not Required | Not Required | Not Required
24INR0115 | Aster Solar | SS Completed, FIS Started, No IA | Aster Solar | 7042 Zorn 345kV | Guadalupe | SOUTH | 2024-12-29 | SOL | PV | 203.52 | MW Size | 2022-06-16 | 2021-09-21 | 2021-12-09 | 2022-05-24 |  |  |  | No |  |  | Not Required
24INR0116 | East Plains Wind | SS Completed, FIS Started, No IA | Ogallala Renewable Project LLC | Tap 345kV 23912 OGALLALA - 23920 BLACKWATER DRAW SWITCH | Castro | PANHANDLE | 2024-12-31 | WIN | WT | 165 |  | 2022-05-20 | 2021-10-21 | 2022-01-17 | 2022-05-06 |  |  |  | No |  |  | Not Required
24INR0117 | Utley Solar Project | SS Completed, FIS Started, No IA | Palmera Solar Development LLC | Tap 345kV 3380 Big Brown SES - 3390 Jewett | Freestone | NORTH | 2024-04-15 | SOL | PV | 221.27 | MW Size | 2022-03-23 | 2021-09-07 | 2021-11-29 | 2022-03-09 |  |  |  | No |  |  | Not Required
24INR0118 | Possum Kingdom Solar | SS Completed, FIS Started, No IA | Novis Renewables | Tap 345kV 1421 Willow Creek Switch – 60515 Clear Crossing | Jack | NORTH | 2024-11-22 | SOL | PV | 260 |  | 2022-06-02 | 2021-09-13 | 2021-11-29 | 2022-05-23 |  |  |  | No | Not Required | Not Required | Not Required
24INR0120 | Eytcheson Ranches Solar | SS Completed, FIS Started, No IA | Gransolar Texas Fourteen, LLC | Tap 69kV 186 Navarro Mills – 107 Prairie Hill | Navarro | NORTH | 2024-11-19 | SOL | PV | 76.42 |  | 2022-05-31 | 2021-09-14 | 2021-11-29 | 2022-05-26 |  |  |  | No |  |  | Not Required
24INR0121 | PHOTO BESS 1 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2024-12-31 | OTH | BA | 75 |  | 2022-05-31 | 2021-10-29 | 2021-12-08 | 2022-05-13 |  |  |  | No |  |  | Not Required
24INR0122 | PHOTO BESS 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2024-12-31 | OTH | BA | 150 |  | 2022-05-31 | 2021-10-29 | 2021-12-08 | 2022-05-13 |  |  |  | No |  |  | Not Required
24INR0124 | High Noon Solar | SS Completed, FIS Started, No IA | High Noon Solar Project, LLC | Tap 138kV 445 Yates - 444 Covington | Hill | NORTH | 2024-12-31 | SOL | PV | 182 |  | 2021-11-02 | 2021-11-03 | 2021-12-29 | 2021-11-02 |  |  |  | No |  |  | Not Required
24INR0125 | Grasshopper Solar | SS Completed, FIS Started, No IA | Grasshopper Solar LLC | Smoky Hill 345kV Sub (Bus #6104) Locational coordinates : 33.34414; 99.624637 | Haskell | WEST | 2024-04-05 | SOL | PV | 407.68 |  | 2021-09-28 | 2021-09-28 | 2021-12-09 | 2021-09-22 |  |  |  | No |  |  | Not Required
24INR0126 | High Noon Storage | SS Completed, FIS Started, No IA | High Noon Solar Project, LLC | Tap 138kV 445 Yates - 444 Covington | Hill | NORTH | 2024-12-31 | OTH | BA | 94 |  | 2021-11-02 | 2021-11-03 | 2021-12-29 | 2021-11-02 |  |  |  | No |  |  | Not Required
24INR0127 | Naduah Solar | SS Completed, FIS Started, No IA | Gransolar Texas Fifteen, LLC | 99 Ben Hur 69kV | Limestone | NORTH | 2024-11-30 | SOL | PV | 181.49 | FIS Request | 2022-06-17 | 2021-09-27 | 2021-12-09 | 2022-06-06 |  |  |  | No |  |  | Not Required
24INR0128 | BRP Desna BESS | SS Completed, FIS Started, No IA | BRP Desna BESS LLC | 39703 TNP FM524 138kV | Brazoria | COASTAL | 2023-12-01 | OTH | BA | 205.44 |  | 2021-12-05 | 2021-12-15 | 2022-03-11 | 2021-11-29 |  |  |  | No |  |  | Not Required
24INR0129 | BRP Rhea BESS | SS Completed, FIS Started, No IA | BRP Rhea BESS LLC | the 138 kV Royse Switch Substation (#2472; ONCOR) | Rockwall | NORTH | 2024-07-01 | OTH | BA | 414.07 |  | 2021-12-15 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No |  |  | Not Required
24INR0130 | BRP Artemis BESS | SS Completed, FIS Started, No IA | BRP Artemis BESS LLC | 40600 Roans Prairie Substation 345kV | Grimes | NORTH | 2024-02-01 | OTH | BA | 414.07 |  | 2021-12-15 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No |  |  | Not Required
24INR0131 | BRP Zelus BESS | SS Completed, FIS Started, No IA | BRP Zelus BESS LLC | the 138 kV Zapata Substation (#8299; AEP) | Zapata | SOUTH | 2024-12-01 | OTH | BA | 206.96 |  | 2021-12-15 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No |  |  | Not Required
24INR0133 | BRP Hestia BESS | SS Completed, FIS Started, No IA | BRP Hestia BESS LLC | the 69 kV Rock Springs Substation (#78238, LCRA) | Edwards | SOUTH | 2024-02-01 | OTH | BA | 29.05 |  | 2021-12-28 | 2021-12-29 | 2022-03-25 | 2021-12-28 |  |  |  | No |  |  | Not Required
24INR0134 | BRP Hemera BESS | SS Completed, FIS Started, No IA | BRP Hemera BESS LLC | 345 kV Deaf Smith Substation (#23908, Oncor) | Deaf Smith | PANHANDLE | 2024-06-18 | OTH | BA | 206.96 |  | 2021-12-20 | 2021-12-29 | 2022-03-25 | 2021-12-14 |  |  |  | No |  |  | Not Required
24INR0135 | BRP Mekong BESS | SS Completed, FIS Started, No IA | BRP Mekong BESS LLC | Tap 345 kV line from Twin Oak Switch (#3400) to TPN One Plant Switchyard (#39950) | Robertson | NORTH | 2024-12-01 | OTH | BA | 413.74 |  | 2021-12-15 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No |  |  | Not Required
24INR0136 | Eagle Springs Storage | SS Completed, FIS Started, No IA | Eagle Springs Solar, LLC | 6835 Lake Creek Substation 138 kV | Delta | NORTH | 2024-12-30 | OTH | BA | 61.46 | FIS Request | 2022-06-20 | 2021-10-18 | 2022-01-12 | 2022-06-13 |  |  |  | No |  |  | Not Required
24INR0137 | Eagle Springs Solar | SS Completed, FIS Started, No IA | Eagle Springs Solar, LLC | 6835 Lake Creek Substation 138 kV | Delta | NORTH | 2024-12-30 | SOL | PV | 119.07 | FIS Request | 2022-06-20 | 2021-10-18 | 2022-01-12 | 2022-06-13 |  |  |  | No |  |  | Not Required
24INR0138 | Midpoint Storage | SS Completed, FIS Started, No IA | Midpoint Solar, LLC | 138 KV Tap #3518 BLUM to #237 Blanton | Hill | NORTH | 2024-12-30 | OTH | BA | 52.24 |  | 2022-05-24 | 2021-10-15 | 2022-01-04 | 2022-05-11 |  |  |  | No | Not Required | Not Required | Not Required
24INR0139 | Midpoint Solar | SS Completed, FIS Started, No IA | Midpoint Solar, LLC | 138 KV Tap #3518 BLUM to #237 Blanton | Hill | NORTH | 2024-12-30 | SOL | PV | 103.8 |  | 2022-05-18 | 2021-10-15 | 2022-01-04 | 2022-05-04 |  |  |  | No |  |  | Not Required
24INR0140 | Gaia Storage | SS Completed, FIS Started, No IA | Gaia Solar, LLC | Tap 138kV 3127 Trinidad SES - 3454 Montfort Switch | Navarro | NORTH | 2024-12-30 | OTH | BA | 76.83 |  | 2022-05-23 | 2021-12-29 | 2022-03-23 | 2022-05-11 |  |  |  | No | Not Required | Not Required | Not Required
24INR0141 | Gaia Solar | SS Completed, FIS Started, No IA | Gaia Solar, LLC | Tap 138kV 3127 Trinidad SES - 3454 Montfort Switch | Navarro | NORTH | 2024-12-30 | SOL | PV | 152.65 |  | 2022-05-23 | 2021-12-29 | 2022-03-23 | 2022-05-11 |  |  |  | No | Not Required | Not Required | Not Required
24INR0142 | BRP De Los Santos BESS | SS Started, FIS Started, No IA | BRP De Los Santos BESS LLC | 78015 Rosita Creek Substation 138kV | Maverick | SOUTH | 2024-12-01 | OTH | BA | 206.87 |  | 2022-02-09 | 2022-05-10 |  | 2022-04-18 |  |  |  | No | Not Required | Not Required | Not Required
24INR0145 | Calpine Guadalupe Peakers | SS Completed, FIS Started, No IA | Guadalupe Peaking Energy Center, LLC | 7044 Marion 345kV | Guadalupe | SOUTH | 2025-05-23 | GAS | GT | 450 |  | 2021-10-26 | 2021-11-15 | 2022-02-11 | 2021-10-18 |  |  |  | No
24INR0146 | Blue Star Solar | SS Completed, FIS Started, No IA | GH America Energy, LLC | Tap 138 kV 8998 Maxwell - 8261 Whiting Line | Val Verde | WEST | 2024-01-02 | SOL | PV | 72.32 |  | 2021-11-03 | 2021-11-04 | 2022-01-31 | 2021-11-04 |  |  |  | No |  |  | Not Required
24INR0147 | Citadel BESS | SS Completed, FIS Started, No IA | Citadel BESS LLC | 40390 Crosby 138kV | Harris | HOUSTON | 2024-05-01 | OTH | BA | 206.32 | COD | 2021-11-15 | 2021-11-15 | 2022-02-11 | 2021-11-11 |  |  |  | No | Not Required | Not Required | Not Required
24INR0150 | Lupinus Solar I | SS Completed, FIS Started, No IA | Lupinus Solar I, LLC | Tap 345 kV line from Woodard Switch (WOODARD_5 #11699) to Monticello SES (MOSES_5 #1695) | Franklin | NORTH | 2024-12-30 | SOL | PV | 164.86 |  | 2022-05-23 | 2021-12-08 | 2022-03-04 | 2022-05-11 |  |  |  | No |  |  | Not Required
24INR0153 | Lupinus Storage I | SS Completed, FIS Started, No IA | Lupinus Solar I, LLC | Tap 345 kV line from Woodard Switch (WOODARD_5 #11699) to Monticello SES (MOSES_5 #1695) | Franklin | NORTH | 2024-12-30 | OTH | BA | 82.97 |  | 2022-05-23 | 2021-12-13 | 2022-03-10 | 2022-05-11 |  |  |  | No |  |  | Not Required
24INR0154 | Lupinus Solar II | SS Completed, FIS Started, No IA | Lupinus Solar II, LLC | 138 kV Monticello Tap Substation (MOSES_T8 #1794) | Franklin | NORTH | 2024-12-30 | SOL | PV | 244.24 |  | 2022-05-23 | 2021-12-13 | 2022-03-10 | 2022-05-11 |  |  |  | No | Not Required | Not Required | Not Required
24INR0155 | Lupinus Storage II | SS Completed, FIS Started, No IA | Lupinus Solar II, LLC | 138 kV Monticello Tap (MOSES_T8 #1794) | Franklin | NORTH | 2024-12-30 | OTH | BA | 122.92 |  | 2022-06-03 | 2021-12-13 | 2022-03-10 | 2022-05-11 |  |  |  | No |  |  | Not Required
24INR0156 | Moonstone Solar Project | SS Completed, FIS Started, No IA | Ignis TX Solar One LLC | Tap 138kV Eagle Creek (5132) to Floresville (5155) | Wilson | SOUTH | 2024-05-15 | SOL | PV | 145.81 | FIS Request | 2022-06-20 | 2021-10-27 | 2022-01-24 | 2022-06-07 |  |  |  | No |  |  | Not Required
24INR0157 | BRP Merope BESS | SS Completed, FIS Started, No IA | BRP Merope BESS LLC | 345 kV Corn Trail Switch Substation (#11441) | Comanche | NORTH | 2025-03-01 | OTH | BA | 413.74 |  | 2021-12-13 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No |  |  | Not Required
24INR0158 | Comet Solar | SS Completed, FIS Started, No IA | Milky Way Power LLC | Paducah 138 kV Station (PSSE Bus number 6135) | Cottle | WEST | 2025-12-19 | SOL | PV | 151.76 |  | 2022-01-05 | 2022-01-20 | 2022-04-18 | 2022-01-06 |  |  |  | No | Not Required | Not Required | Not Required
24INR0161 | Miranda Solar Project | SS Completed, FIS Started, No IA | Cactus Solar Development LLC | Tap 345kV 5709 Fowlerton - 5901 San Miguel Ckt 1 | La Salle | SOUTH | 2024-05-31 | SOL | PV | 261.42 | FIS Request | 2022-06-27 | 2021-11-03 | 2022-01-07 | 2022-06-22 |  |  |  | No |  |  | Not Required
24INR0162 | Chiltepin Storage | SS Completed, FIS Started, No IA | Chiltepin Solar-Storage, LLC | 6673 Musquiz 138kV | Reeves | WEST | 2024-12-01 | OTH | BA | 100 |  | 2021-11-09 | 2022-01-13 | 2022-04-11 | 2021-12-16 |  |  |  | No |  |  | Not Required
24INR0166 | OCI Stillhouse Solar | SS Completed, FIS Started, No IA | OCI Stillhouse LLC | tap 345kV 3687 Bell_E_5 to 39950 TNP One Plant Switchyard CKT 2 | Bell | NORTH | 2025-06-01 | SOL | PV | 215.06 |  | 2021-11-17 | 2021-11-24 | 2022-02-19 | 2021-11-23 |  |  |  | No | Not Required | Not Required | Not Required
24INR0167 | OCI SunRoper | SS Completed, FIS Started, No IA | OCI SunRoper LLC | tap138kV #43190 South Lane City to #42985 Dyann | Wharton | SOUTH | 2025-06-01 | SOL | PV | 203.53 |  | 2021-11-18 | 2021-11-24 | 2022-02-19 | 2021-11-23 |  |  |  | No |  |  | Not Required
24INR0168 | Tejano Storage | SS Completed, FIS Started, No IA | Tejano Storage, LLC | Tap 138kV 8125 Lolita - 8172 Victoria | Victoria | SOUTH | 2025-06-01 | OTH | BA | 152 |  | 2022-05-06 | 2022-03-30 | 2022-06-26 | 2022-04-18 |  |  |  | No |  |  | Not Required
24INR0169 | Yaupon Storage SLF | SS Completed, FIS Started, No IA | Yaupon Solar, LLC | Tap 345-kV from 3687 Bell Co East to 39950 TNP One CKT 1 | Milam | SOUTH | 2024-10-01 | OTH | BA | 0 |  | 2022-01-12 | 2021-11-10 | 2022-02-08 | 2022-01-10 |  |  |  | No |  |  | Not Required
24INR0171 | Hollow Branch Creek Solar | SS Completed, FIS Started, No IA | East Caney Creek Solar LLC | Jewett – Singleton 345 kV [PTI Bus # 3390 – 44645] | Leon | NORTH | 2024-12-31 | SOL | PV | 700 |  | 2021-11-09 | 2021-12-13 | 2022-02-04 | 2021-12-07 |  |  |  | No |  |  | Not Required
24INR0177 | Mitchell Plant Road Solar | SS Completed, FIS Started, No IA | DHI Power, LLC | Tap White Baker (Bus# 38430) - Oxy Century (Bus# 38431) 138 kV Line | Pecos | WEST | 2024-06-01 | SOL | PV | 202.8 |  | 2022-01-31 | 2022-02-21 | 2022-05-21 | 2022-01-28 |  |  |  | No | Not Required | Not Required | Not Required
24INR0181 | Bynum Solar Project | SS Completed, FIS Started, No IA | Gransolar Texas Eighteen LLC | Tap 69kV 37470 Olsen - 37520 Sycamore | Coryell | NORTH | 2024-05-31 | SOL | PV | 65.4 | MW Size | 2022-06-02 | 2021-12-18 | 2022-03-11 | 2022-05-23 |  |  |  | No |  |  | Not Required
24INR0182 | DeSpain Solar Project | SS Completed, FIS Started, No IA | Gransolar Texas Thirteen LLC | 7425 Odlaw Switch 138kV | Kinney | SOUTH | 2024-05-31 | SOL | PV | 236.17 | FIS Request | 2022-06-22 | 2021-12-05 | 2022-03-02 | 2022-06-16 |  |  |  | No |  |  | Not Required
24INR0185 | BRP Kotys BESS | SS Completed, FIS Started, No IA | BRP Kotys BESS LLC | 138 kV Argyle Substation (#1984) | Denton | NORTH | 2024-11-01 | OTH | BA | 163.41 |  | 2022-02-11 | 2022-02-28 | 2022-05-27 | 2022-02-24 |  |  |  | No | Not Required | Not Required | Not Required
24INR0186 | Rowdy Creek Solar | SS Completed, FIS Started, No IA | Rowdy Creek Solar LLC | Tap 345kV 1692 Paris Switch – 1690 Valley SES | Lamar | NORTH | 2024-12-31 | SOL | PV | 700 |  | 2021-12-13 | 2022-01-28 | 2022-04-27 | 2022-01-25 |  |  |  | No |  |  | Not Required
24INR0187 | Rowdy Creek BESS | SS Completed, FIS Started, No IA | Rowdy Creek Solar LLC | Tap 345kV 1692 Paris Switch – 1690 Valley SES | Lamar | NORTH | 2024-12-31 | OTH | BA | 350 |  | 2021-12-13 | 2022-01-28 | 2022-04-27 | 2022-01-25 |  |  |  | No |  |  | Not Required
24INR0188 | Tehuacana Creek Solar | SS Completed, FIS Started, No IA | Tehuacana Creek Solar LLC | Tap 345kV 3381 Big Brown – 68091 Navarro | Navarro | NORTH | 2024-12-31 | SOL | PV | 700 |  | 2021-12-15 | 2021-12-20 | 2022-03-10 | 2021-12-09 |  |  |  | No |  |  | Not Required
24INR0189 | Tehuacana Creek BESS | SS Completed, FIS Started, No IA | Tehuacana Creek Solar LLC | Tap 345kV 3381 Big Brown – 68091 Navarro | Navarro | NORTH | 2024-12-31 | OTH | BA | 350 |  | 2021-12-15 | 2021-12-20 | 2022-03-10 | 2021-12-09 |  |  |  | No |  |  | Not Required
24INR0196 | Dori BQ BESS | SS Completed, FIS Started, No IA | Sunnyside Energy LLC | 138kV line Holmes (#47210) - Garden Villas (#42680); CNP | Harris | HOUSTON | 2024-01-01 | OTH | BA | 154 |  | 2022-01-05 | 2022-02-07 | 2022-05-06 | 2022-01-19 |  |  |  | No | Not Required | Not Required | Not Required
24INR0197 | Opuntia Storage SLF | SS Completed, FIS Started, No IA | Opuntia Solar, LLC | tap 138 kV 5607 Warburton - 8912 Medio Creek | Refugio | COASTAL | 2024-07-01 | OTH | BA | 0 |  | 2022-02-01 | 2022-02-07 | 2022-05-07 | 2022-01-20 |  |  |  | No | Not Required | Not Required | Not Required
24INR0206 | Glasgow Solar | SS Completed, FIS Started, No IA | Belltown Power Texas | 345kV line between BUS #2466 Big Onion to #68091 Navarro circuit | Navarro | NORTH | 2024-05-31 | SOL | PV | 203.5 |  | 2022-02-03 | 2022-02-07 | 2022-05-07 | 2022-01-12 |  |  |  | No |  |  | Not Required
24INR0207 | Glasgow Storage | SS Completed, FIS Started, No IA | Belltown Power Texas | 345kV line between BUS #2466 Big Onion to #68091 Navarro circuit | Navarro | NORTH | 2024-05-31 | OTH | BA | 101 |  |  | 2022-02-21 | 2022-05-07 | 2022-02-02 |  |  |  | No | Not Required | Not Required | Not Required
24INR0208 | Eastbell Milam Solar II | SS Completed, FIS Started, No IA | Cattlemen Solar Park II LLC | 345 kV Bell County East Switch (bus# 3687) - TNP One (bus# 39950) circuit 2 | Milam | SOUTH | 2024-10-31 | SOL | PV | 152.52 |  | 2022-02-07 | 2022-03-07 | 2022-06-02 | 2022-02-03 |  |  |  | No |  |  | Not Required
24INR0213 | Owens Solar | SS Completed, FIS Started, No IA | Belltown Power Texas | Tap 138kV line between 177 BOSQUE and 181 Cayote | Bosque | NORTH | 2024-05-31 | SOL | PV | 203.5 |  | 2022-02-01 | 2022-02-07 | 2022-05-06 | 2022-01-12 |  |  |  | No |  |  | Not Required
24INR0231 | Llano Estacado Energy Storage | SS Started, FIS Started, No IA | VESI 40 LLC | 1324 Big Spring West 138 kV | Howard | WEST | 2025-03-01 | OTH | BA | 98 |  | 2022-03-29 | 2022-04-18 |  | 2022-03-29 |  |  |  | No | Not Required | Not Required | Not Required
24INR0233 | St. Gall Solar | SS Completed, FIS Started, No IA | St. Gall Solar LLC | 38355 Leon Creek 138kV | Pecos | WEST | 2024-12-01 | SOL | PV | 207 |  | 2022-02-07 | 2022-02-28 | 2022-05-27 | 2022-02-24 |  |  |  | No |  |  | Not Required
24INR0234 | Rock N' Roll Storage SLF | SS Completed, FIS Started, No IA | Rock N' Roll Solar, LLC | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2024-12-31 | OTH | BA | 0 |  | 2022-02-10 | 2022-02-28 | 2022-05-27 | 2022-02-11 |  |  |  | No | Not Required | Not Required | Not Required
24INR0235 | Rock N' Roll Storage Two | SS Completed, FIS Started, No IA | Rock N' Roll Solar, LLC | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2024-12-31 | OTH | BA | 206 |  | 2022-02-24 | 2022-02-28 | 2022-05-27 | 2022-02-11 |  |  |  | No | Not Required | Not Required | Not Required
24INR0236 | Bayside 2 BESS | SS Completed, FIS Started, No IA | Bayside 2 BESS | Tap 345kV 5323 Old Hickory - 5133 Elm Creek Ckt #2 | DeWitt | SOUTH | 2024-08-30 | OTH | BA | 252.3 |  | 2022-02-10 | 2022-03-07 | 2022-06-02 | 2022-03-01 |  |  |  | No |  |  | Not Required
24INR0237 | Bayside BESS | SS Completed, FIS Started, No IA | Bayside BESS | Tap 345kV 5915 STP - 5133 Elm Creek Ckt #1 | Victoria | SOUTH | 2024-08-30 | OTH | BA | 507.8 |  | 2022-02-11 | 2022-03-07 | 2022-06-02 | 2022-03-01 |  |  |  | No |  |  | Not Required
24INR0238 | Appaloosa Run BESS | SS Completed, FIS Started, No IA | Appaloosa Run BESS | New Palouse 138kV (#60278) | Upton | WEST | 2024-08-30 | OTH | BA | 200.5 |  | 2022-02-11 | 2022-03-07 | 2022-06-02 | 2022-03-01 |  |  |  | No |  |  | Not Required
24INR0239 | Trojan BESS | SS Started, FIS Started, No IA | Trojan BESS | 11735 Cedar Elm Switch 345kV | Cooke | NORTH | 2024-08-30 | OTH | BA | 201.9 |  | 2022-05-17 | 2022-06-02 |  | 2022-04-19 |  |  |  | No |  |  | Not Required
24INR0242 | Stockdale BESS | SS Completed, FIS Started, No IA | Stockdale BESS | Tap 345kV 5133 Elm Creek - 5068 Cachena Ckt 2 | Wilson | SOUTH | 2024-08-30 | OTH | BA | 203.9 |  | 2022-02-15 | 2022-03-14 | 2022-06-09 | 2022-03-01 |  |  |  | No |  |  | Not Required
24INR0244 | Cornwall BESS | SS Completed, FIS Started, No IA | Cornwall BESS | Tap 138kV 3659 Thorndale North - 3658 Taylor | Williamson | SOUTH | 2024-08-30 | OTH | BA | 203.8 |  | 2022-02-16 | 2022-03-07 | 2022-06-02 | 2022-03-01 |  |  |  | No | Not Required | Not Required | Not Required
24INR0245 | Diamondback BESS | SS Completed, FIS Started, No IA | Diamondback BESS | 80355 Del Sol 345kV | Starr | SOUTH | 2024-08-30 | OTH | BA | 203.8 |  | 2022-02-16 | 2022-03-07 | 2022-06-02 | 2022-03-01 |  |  |  | No | Not Required | Not Required | Not Required
24INR0246 | Sultan BESS | SS Completed, FIS Started, No IA | Sultan BESS | tap 345kV 68080 Sam Switch – 68090 Kopperl | Bosque | NORTH | 2024-08-30 | OTH | BA | 203.8 |  | 2022-02-16 | 2022-03-07 | 2022-06-02 | 2022-03-01 |  |  |  | No |  |  | Not Required
24INR0248 | Half Moon 2 BESS | SS Completed, FIS Started, No IA | Half Moon 2 BESS | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2024-08-30 | OTH | BA | 102 |  | 2022-02-15 | 2022-03-14 | 2022-05-11 | 2022-02-28 |  |  |  | No |  |  | Not Required
24INR0249 | Hickerson BESS | SS Completed, FIS Started, No IA | Hickerson BESS | tap 345kV 68091 Navarro - 68040 Kopperl | Bosque | NORTH | 2024-08-30 | OTH | BA | 302.4 |  | 2022-02-24 | 2022-03-07 | 2022-06-02 | 2022-02-24 |  |  |  | No |  |  | Not Required
24INR0255 | Mitchell Plant Road Storage SLF | SS Completed, FIS Started, No IA | DHI POWER, LLC | Tap White Baker (Bus# 38430) - Oxy Century (Bus# 38431) 138 kV Line | Pecos | WEST | 2024-06-01 | OTH | BA | 0 |  | 2022-02-23 | 2022-02-28 | 2022-05-21 | 2022-02-25 |  |  |  | No | Not Required | Not Required | Not Required
24INR0257 | Pruett Solar | SS Completed, FIS Started, No IA | Belltown Power Texas | Tap 138kV 587 Greenwood - 685 Leo | Wise | NORTH | 2024-05-31 | SOL | PV | 152 |  | 2022-04-13 | 2022-02-28 | 2022-05-27 | 2022-04-05 |  |  |  | No |  |  | Not Required
24INR0258 | Zeissel Solar | SS Completed, FIS Started, No IA | ZSS Power, LLC | 60700 Gauss 345 KV | Knox | WEST | 2024-06-30 | SOL | PV | 691.44 |  | 2022-05-19 | 2022-02-28 | 2022-05-27 | 2022-04-25 |  |  |  | No |  |  | Not Required
24INR0259 | Zeissel Storage SLF | SS Completed, FIS Started, No IA | ZSS Power, LLC | 60700 Gauss 345 KV | Knox | WEST | 2024-06-30 | OTH | BA | 0 |  | 2022-05-10 | 2022-02-28 | 2022-05-27 | 2022-04-25 |  |  |  | No |  |  | Not Required
24INR0260 | Lager Storage | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners,LLC | 8031 Gillrina 69kV | Nueces | COASTAL | 2024-02-10 | OTH | BA | 30 |  | 2022-02-21 | 2022-02-28 | 2022-05-27 | 2022-02-23 |  |  |  | No |  |  | Not Required
24INR0262 | Lan Battery | SS Started, FIS Started, No IA | General Solar, LLC | Tap 345kV 1729 Valley South – 1692 Paris Switch | Lamar | NORTH | 2024-02-15 | OTH | BA | 180 | FIS Request | 2022-04-04 | 2022-06-10 |  | 2022-04-27 |  |  |  | No |  |  | Not Required
24INR0263 | Cold Creek Solar | SS Started, FIS Started, No IA | Cold Creek Solar LLC | 76003 Big Hill Substation 345kV | Schleicher | WEST | 2024-06-01 | SOL | PV | 430 |  | 2022-03-30 | 2022-04-18 |  | 2022-04-13 |  |  |  | No |  |  | Not Required
24INR0264 | Goldenrod Creek Solar | SS Completed, FIS Started, No IA | Goldenrod Creek Solar LLC | Tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Jackson | SOUTH | 2024-12-31 | SOL | PV | 660 |  | 2022-02-25 | 2022-02-28 | 2022-05-27 | 2022-02-14 |  |  |  | No |  |  | Not Required
24INR0265 | SMT Ironman BESS | SS Completed, FIS Started, No IA | SMT Ironman LLC | 43035 Oasis Substation 345kV | Brazoria | COASTAL | 2024-06-30 | OTH | BA | 304.25 |  | 2022-02-28 | 2022-03-14 | 2022-04-18 | 2022-03-08 |  |  |  | No |  |  | Not Required
24INR0266 | Cold Creek Storage | SS Started, FIS Started, No IA | Cold Creek Solar LLC | 76003 Big Hill Substation 345kV | Schleicher | WEST | 2024-06-01 | OTH | BA | 170 |  | 2022-04-13 | 2022-04-18 |  | 2022-04-13 |  |  |  | No |  |  | Not Required
24INR0268 | Goldenrod Creek ESS - SLF | SS Completed, FIS Started, No IA | Goldenrod Creek Solar LLC | Tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Jackson | SOUTH | 2024-12-31 | OTH | BA | 0 |  | 2022-02-25 | 2022-02-28 | 2022-05-27 | 2022-02-14 |  |  |  | No |  |  | Not Required
24INR0270 | Cachena Solar 2 SLF | SS Completed, FIS Started, No IA | Clear Fork Solar LLC | Tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Wilson | SOUTH | 2024-06-01 | SOL | PV | 160 |  | 2022-03-21 | 2022-03-30 | 2022-06-27 | 2022-03-28 |  |  |  | No |  |  | Not Required
24INR0272 | Brushy Creek Storage SLF | SS Completed, FIS Started, No IA | Brushy Creek Solar | the 345 kV San Angelo Red Creek Substation (#6444); AEP | Tom Green | WEST | 2024-09-15 | OTH | BA | 0 |  | 2022-03-03 | 2022-03-30 | 2022-06-26 | 2022-03-08 |  |  |  | No |  |  | Not Required
24INR0273 | Al Pastor BESS | SS Completed, FIS Started, No IA | Al Pastor BESS LLC | 1163 Lamesa Substation 138kV | Dawson | WEST | 2024-09-02 | OTH | BA | 100.8 |  | 2022-03-02 | 2022-03-07 | 2022-06-02 | 2022-03-02 |  |  |  | No | Not Required | Not Required | Not Required
24INR0274 | Bufflehead BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage | 2475 Lavon Switch 138kV | Collin | NORTH | 2025-04-17 | OTH | BA | 201.2 |  | 2022-02-25 | 2022-03-07 | 2022-06-02 | 2022-02-28 |  |  |  | No | Not Required | Not Required | Not Required
24INR0275 | Picadillo BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II | 23837 Buffalo 138kV | Martin | WEST | 2024-11-01 | OTH | BA | 100.83 |  | 2022-02-25 | 2022-03-07 | 2022-06-02 | 2022-02-28 |  |  |  | No |  |  | Not Required
24INR0279 | Cachena Storage 2 SLF | SS Completed, FIS Started, No IA | Clear Fork Solar LLC | Tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Wilson | SOUTH | 2024-06-01 | OTH | BA | 0 |  | 2022-02-24 | 2022-03-14 | 2022-06-09 | 2022-03-11 |  |  |  | No |  |  | Not Required
24INR0280 | Port Bay ESC | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | 8434 Rockport Substation (ROCKPORT4A) 138kV | Aransas | COASTAL | 2024-12-31 | OTH | BA | 200 |  | 2022-03-18 | 2022-03-21 | 2022-06-16 | 2022-03-07 |  |  |  | No |  |  | Not Required
24INR0285 | APV Plumwood Storage | SS Completed, FIS Started, No IA | APV Lonestar Energy LLC | Tap 138kV 40171 Baytown - 40015Cedar Bayou Plant | Chambers | HOUSTON | 2024-07-10 | OTH | BA | 202.78 |  | 2022-03-18 | 2022-03-30 | 2022-06-26 | 2022-03-22 |  |  |  | No |  |  | Not Required
24INR0290 | Rubicon Echo Wind | SS Started, FIS Started, No IA | Rubicon Wind | Tap 345kV 1421 Willow Creek - 60515 Clear Crossing Ckt 2 | Haskell | WEST | 2024-08-30 | WIN | WT | 228.4 |  | 2022-03-28 | 2022-05-10 |  | 2022-04-15 |  |  |  | No |  |  | Not Required
24INR0291 | Rubicon Alpha Wind | SS Started, FIS Started, No IA | Rubicon Wind | Tap 345kV 60791 Perigee – 6235 Abilene Mulberry Creek | Haskell | WEST | 2024-08-30 | WIN | WT | 228.4 |  | 2022-03-28 | 2022-05-10 |  | 2022-04-15 |  |  |  | No |  |  | Not Required
24INR0292 | Urca Solar | SS Started, FIS Started, No IA | Urca Solar | George West 138kV Sub (#5688) via 4-mile gen-tie | Live Oak | SOUTH | 2024-08-30 | SOL | PV | 204.1 |  | 2022-03-28 | 2022-04-18 |  | 2022-04-15 |  |  |  | No |  |  | Not Required
24INR0294 | Citrus Flatts BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage | 80022 Oleander 138kV | Cameron | COASTAL | 2024-11-01 | OTH | BA | 100.8 |  | 2022-03-21 | 2022-03-30 | 2022-06-26 | 2022-03-24 |  |  |  | No |  |  | Not Required
24INR0295 | Lucky Bluff BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage | tap 138kV 1641 Stephenville - 1636 Dublin | Erath | NORTH | 2025-04-01 | OTH | BA | 100.8 |  | 2022-03-23 | 2022-03-30 | 2022-06-26 | 2022-03-24 |  |  |  | No |  |  | Not Required
24INR0298 | Leighton Solar SLF | SS Started, FIS Started, No IA | Deadose Solar | 99 BENHUR 69kV | Limestone | NORTH | 2024-11-04 | SOL | PV | 180 |  | 2022-04-27 | 2022-05-11 |  | 2022-03-16 |  |  |  | No |  |  | Not Required
24INR0301 | Merchant BESS | SS Started, FIS Started, No IA | BLACK MOUNTAIN ENERGY STORAGE | 46510 TOMBALL 138KV | Harris | HOUSTON | 2024-11-01 | OTH | BA | 201.2 |  | 2022-04-02 | 2022-04-18 |  | 2022-04-04 |  |  |  | No |  |  | Not Required
24INR0302 | Pintail Pass BESS | SS Completed, FIS Started, No IA | Pintail Pass BESS LLC | 8249 ANGSTROM 345KV | San Patricio | COASTAL | 2024-11-01 | OTH | BA | 201.2 |  | 2022-04-02 | 2022-04-18 | 2022-06-16 | 2022-04-07 |  |  |  | No |  |  | Not Required
24INR0305 | MRG Goody Storage | SS Started, FIS Started, No IA | MRG Goody Solar Project LLC | 1700 Toco 138kV | Lamar | NORTH | 2024-06-30 | OTH | BA | 43.2 |  | 2022-04-07 | 2022-05-10 |  | 2022-04-11 |  |  |  | No |  |  | Not Required
24INR0306 | Arroyo Storage SLF | SS Started, FIS Started, No IA | BT Cantwell Solar, LLC | Tap 345kV 8318 Rio Hondo - 8317 La Palma (New Gulch Substation ) | Cameron | COASTAL | 2024-03-15 | OTH | BA | 0 |  | 2022-05-03 | 2022-05-10 |  | 2022-04-26 |  |  |  | No |  |  | Not Required
24INR0308 | Forts Trail Solar SLF | SS Started, FIS Started, No IA | JC Central Bluff LLC | 11406 Central Bluff Switch 345kV | Taylor | WEST | 2024-06-15 | SOL | PV | 200 | FIS Request | 2022-06-07 | 2022-06-02 |  | 2022-06-03 |  |  |  | No |  |  | Not Required
24INR0312 | Wigeon Whistle BESS | SS Started, FIS Started, No IA | Wigeon Whistle BESS LLC | 811 NEVADA 138KV | Collin | NORTH | 2024-11-01 | OTH | BA | 100.8 |  | 2022-04-27 | 2022-04-18 |  | 2022-04-13 |  |  |  | No |  |  | Not Required
24INR0313 | Backbone Creek BESS | SS Started, FIS Started, No IA | Backbone Creek BESS LLC | 7351 STARCKE 138kV | Burnet | SOUTH | 2024-11-01 | OTH | BA | 100.8 |  | 2022-05-09 | 2022-04-18 |  | 2022-04-27 |  |  |  | No |  |  | Not Required
24INR0315 | Black Springs BESS | SS Started, FIS Started, No IA | BLACK MOUNTAIN ENERGY STORAGE II | 1571 ORAN 138KV | Palo Pinto | NORTH | 2025-04-14 | OTH | BA | 100.8 | COD | 2022-06-02 | 2022-04-18 |  | 2022-05-05 |  |  |  | No |  |  | Not Required
24INR0323 | Coati Solar | SS Started, FIS Started, No IA | Coati Solar, LLC | 37 Ridge 138kV | Robertson | NORTH | 2024-12-31 | SOL | PV | 296.07 | Proj Name | 2022-05-10 | 2022-05-24 |  | 2022-04-28 |  |  |  | No |  |  | Not Required
24INR0325 | Coati Storage | SS Started, FIS Started, No IA | Coati Solar, LLC | 138 kV Ridge (Bus# 37) | Robertson | NORTH | 2024-12-31 | OTH | BA | 145.97 | Proj Name | 2022-05-10 | 2022-05-24 |  | 2022-04-28 |  |  |  | No |  |  | Not Required
24INR0326 | Blarney Solar | SS Started, FIS Started, No IA | Sligsol, LLC | 1815 Cumby Tap 138kV | Hopkins | NORTH | 2024-11-01 | SOL | PV | 81 | FIS Request | 2022-04-20 |  |  | 2022-04-21 |  |  |  | No |  |  | Not Required
24INR0329 | XE Murat Storage | SS Started, FIS Started, No IA | Liberty 1 Solar LLC | tap the 138 kV CROSBY (#40390) -ATASCOCITA (#40130) Line; CNP | Harris | HOUSTON | 2024-01-04 | OTH | BA | 60.23 | MW Size COD | 2022-05-16 | 2022-06-02 |  | 2022-04-28 |  |  |  | No |  |  | Not Required
24INR0334 | North Shore Energy Storage | SS Started, FIS Started, No IA | North Shore Energy Storage LLC | Oates-19 substation (#41191) | Harris | HOUSTON | 2024-12-31 | OTH | BA | 100 |  | 2022-05-03 | 2022-05-16 |  | 2022-05-04 |  |  |  | No |  |  | Not Required
24INR0335 | Evergreen Storage | SS Started, FIS Started, No IA | Evergreen Energy LLC | 8111 Magilla 138kV | Matagorda | COASTAL | 2024-12-31 | OTH | BA | 100 |  | 2022-05-02 | 2022-06-02 |  | 2022-05-04 |  |  |  | No |  |  | Not Required
24INR0337 | Eldora Solar | SS Started, FIS Started, No IA | Eldora Energy LLC | 345 kV South Texas Project (Bus# 5915) – Hillje (Bus# 44200) Transmission Line Ckt 1 | Matagorda | COASTAL | 2024-12-31 | SOL | PV | 200.94 | FIS Request | 2022-05-31 | 2022-06-10 |  | 2022-06-01 |  |  |  | No |  |  | Not Required
24INR0338 | Eldora BESS | SS Started, FIS Started, No IA | Eldora Energy LLC | 345 kV South Texas Project (Bus# 5915) – Hillje (Bus# 44200) Transmission Line Ckt 1 | Matagorda | COASTAL | 2024-12-31 | OTH | BA | 201.31 | FIS Request | 2022-06-03 | 2022-06-10 |  | 2022-06-01 |  |  |  | No |  |  | Not Required
24INR0341 | Forts Trail BESS SLF | SS Started, FIS Started, No IA | JC Central Bluff LLC | 11406 Central Bluff Switch 345kV | Taylor | WEST | 2024-06-15 | OTH | BA | 0 | FIS Request | 2022-06-06 | 2022-06-02 |  | 2022-06-03 |  |  |  | No |  |  | Not Required
24INR0345 | Schoolhouse BESS | SS Started, FIS Started, No IA | Schoolhouse Storage, LLC | tap 345kV 7040 Austrop - 13429 Sandow | Lee | SOUTH | 2024-03-10 | OTH | BA | 150.68 | FIS Request | 2022-06-09 | 2022-06-17 |  | 2022-06-10 |  |  |  | No |  |  | Not Required
24INR0348 | Best Southwest BESS | SS Started, FIS Started, No IA | BLACK MOUNTAIN ENERGY STORAGE II | 2424 DESOTO SW 138kV | Dallas | NORTH | 2024-11-01 | OTH | BA | 201.2 |  | 2022-05-09 | 2022-05-16 |  | 2022-04-26 |  |  |  | No |  |  | Not Required
24INR0350 | Brushwood Energy Storage | SS Started, FIS Started, No IA | Flagtail LLC | Tap 345kV 44645 Singleton - 40600 Roans Prairie | Grimes | NORTH | 2024-12-31 | OTH | BA | 203.78 | FIS Request | 2022-06-06 | 2022-06-10 |  | 2022-05-27 |  |  |  | No |  |  | Not Required
24INR0353 | Exodus | SS Started, FIS Started, No IA | Exodus Solar LLC. | Tap 345kV 7040 Austrop – 7042 Zorn | Caldwell | SOUTH | 2024-07-20 | SOL | PV | 156.1 | FIS Request | 2022-05-16 | 2022-06-10 |  | 2022-05-20 |  |  |  | No |  |  | Not Required
24INR0368 | Glory Bee Solar | SS Started, FIS Started, No IA | Belltown Power Texas | Tap 345kV 1440 Comanche Switch - 1900 Comanche Peak | Erath | NORTH | 2024-05-31 | SOL | PV | 305 | FIS Request | 2022-06-06 | 2022-06-10 |  | 2022-06-06 |  |  |  | No |  |  | Not Required
24INR0369 | Glory Bee Storage | SS Started, FIS Started, No IA | Belltown Power Texas | Tap 345kV 1440 Comanche Switch - 1900 Comanche Peak | Erath | NORTH | 2024-05-31 | OTH | BA | 101 | FIS Request | 2022-06-06 | 2022-06-10 |  | 2022-06-06 |  |  |  | No |  |  | Not Required
24INR0370 | Dogwood Creek Solar | SS Started, FIS Started, No IA | Dogwood Creek Solar LLC | tap 345kV 7040 Austrop - 9041 Lost Pines | Bastrop | SOUTH | 2024-12-31 | SOL | PV | 432.02 | FIS Request | 2022-06-20 | 2022-06-27 |  | 2022-06-06 |  |  |  | No |  |  | Not Required
24INR0371 | Dogwood Creek Storage | SS Started, FIS Started, No IA | Dogwood Creek Solar LLC | tap 345kV 7040 Austrop - 9041 Lost Pines | Bastrop | SOUTH | 2024-12-31 | OTH | BA | 431.3 | FIS Request | 2022-06-20 |  |  | 2022-06-06 |  |  |  | No |  |  | Not Required
24INR0381 | Alexandrite Storage | SS Started, FIS Started, No IA | Belltown Power Texas | Santa Rosa (S_SNROSA4A) 138/XX KV Substation (Bus #8359) | Cameron | COASTAL | 2024-06-01 | OTH | BA | 203 | FIS Request | 2022-06-20 | 2022-06-27 |  | 2022-06-15 |  |  |  | No |  |  | Not Required
25INR0002 | Barcelona TxHSR TPSS HN-4 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 45885 HocklyC - 46220 Peters | Harris | HOUSTON | 2028-07-15 | OTH | OT | 50 |  | 2019-10-11 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  | No |  | No | Not Required | Not Required
25INR0005 | Tokyo TxHSR TPSS EW-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2241 Ennis W - 2321 Waxahachie | Ellis | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-09-13 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  |  |  | No | Not Required | Not Required
25INR0006 | Atlanta TxHSR TPSS DS-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2429 Watermill E - 3083 Wilmer | Dallas | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-10-11 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  |  |  | No | Not Required | Not Required
25INR0008 | BasRanch | SS Completed, FIS Started, No IA | CPV Basin Ranch, LLC | tap 345kV 11098 Sand Lake - 60404 Solstice | Reeves | WEST | 2026-01-01 | GAS | CC | 1350 |  | 2021-11-24 | 2020-08-04 | 2020-11-02 | 2021-10-28 16:25 |  |  |  | No
25INR0010 | Nockenut Springs Solar 3 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Gonzales | SOUTH | 2025-12-31 | SOL | PV | 203.39 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No |  |  | Not Required
25INR0012 | Alamosa Solar | SS Completed, FIS Started, No IA | Alamosa Solar LLC | 6100 Oklaunion 345kV | Wilbarger | WEST | 2025-01-01 | SOL | PV | 209.48 |  | 2021-08-19 | 2020-12-03 | 2021-02-17 | 2021-08-13 |  |  |  | No |  |  | Not Required
25INR0018 | Yellow Cat Wind | SS Completed, FIS Started, No IA | STEELHEAD WIND 2 LLC | Tap 345kV 1906 Venus - 68091 Navarro | Navarro | NORTH | 2024-12-23 | WIN | WT | 300 | COD | 2022-03-18 | 2021-08-17 | 2021-11-05 | 2022-03-07 |  |  |  | No | Not Required | Not Required | Not Required
25INR0021 | Findley Solar | SS Completed, FIS Started, No IA | Gransolar Texas Sixteen, LLC | 107 Prairie Hill 69 kV | Limestone | NORTH | 2025-02-25 | SOL | PV | 50.34 |  |  | 2021-10-05 | 2021-12-10 | 2022-05-24 |  |  |  | No |  |  | Not Required
25INR0022 | Alamosa Storage | SS Completed, FIS Started, No IA | Alamosa BESS West, LLC | 6100 Oklaunion 345kV | Wilbarger | WEST | 2025-01-01 | OTH | BA | 207.21 |  | 2021-10-06 | 2021-10-06 | 2021-12-13 | 2021-10-05 |  |  |  | No |  |  | Not Required
25INR0024 | Itsee Solar | SS Completed, FIS Started, No IA | Gransolar Texas Seventeen, LLC | Tap 138kV Trinidad Ses (Bus number 3127) to Goodloe Switch (Bus number 3483) | Navarro | NORTH | 2024-12-24 | SOL | PV | 53.31 | FIS Request |  | 2021-10-12 | 2022-01-03 | 2022-05-24 |  |  |  | No |  |  | Not Required
25INR0039 | Borderland ESC | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | 8368 McAllen 138kV (N_MCALLN4A) | Hidalgo | SOUTH | 2024-12-31 | OTH | BA | 200 |  | 2022-02-08 | 2022-02-21 | 2022-05-22 | 2022-02-08 |  |  |  | No |  |  | Not Required
25INR0040 | McMEXICO STORAGE | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | 8644 Trade Zone 138kV | Hidalgo | SOUTH | 2024-12-31 | OTH | BA | 201.9 |  | 2022-01-28 | 2022-02-28 | 2022-05-27 | 2022-02-15 |  |  |  | No | Not Required | Not Required | Not Required
25INR0046 | Ash Creek BESS | SS Started, FIS Started, No IA | Ash Creek Solar LLC | 68090 SAM SW 345kV | Hill | NORTH | 2024-05-15 | OTH | BA | 306 |  | 2022-04-02 | 2022-05-10 |  | 2022-04-15 |  |  |  | No |  |  | Not Required
25INR0054 | Sandman Power Storage | SS Completed, FIS Started, No IA | ALPIN HOLDING LLC | 1685 Farmersville Switch 345kV | Collin | NORTH | 2025-11-30 | OTH | BA | 100 |  | 2022-03-14 | 2022-03-21 | 2022-06-16 | 2022-03-14 |  |  |  | No |  |  | Not Required
25INR0055 | Three W Solar | SS Completed, FIS Started, No IA | Three W Solar LLC | tap 138kV 3522 Hillboro1_8 - 237 Blanton CKT 1 | Hill | NORTH | 2025-06-01 | SOL | PV | 111.6 |  | 2022-02-25 | 2022-03-07 | 2022-06-02 | 2022-02-28 |  |  |  | No |  |  | Not Required
25INR0068 | High Chap Solar | SS Started, FIS Started, No IA | HIGH CHAPARRAL SOLAR PROJECT LLC | 43035 Oasis 345kV - 42500 Dow Chemical 345 kV Ckt 27 | Brazoria | COASTAL | 2025-03-01 | SOL | PV | 152.25 | FIS Request |  |  |  | 2022-06-17 |  |  |  | No |  |  | Not Required
25INR0073 | Saltillo Storage | SS Started, FIS Started, No IA | SALTILLO STORAGE | 7331 Cedarhill Substation 138kV | Bastrop | SOUTH | 2025-06-01 | OTH | BA | 101 |  | 2022-05-10 | 2022-05-10 |  | 2022-04-25 |  |  |  | No |  |  | Not Required
25INR0079 | Sunlight Solar | SS Started, FIS Started, No IA | DG Penwell North | Tapping Red Lake Switch #11293 - Ector Harper #1292 138kV line | Ector | WEST | 2025-12-31 | SOL | PV | 203.5 | FIS Request | 2022-06-02 | 2022-06-10 |  | 2022-06-01 |  |  |  | No |  |  | Not Required
25INR0101 | Mallard BESS | SS Started, FIS Started, No IA | Black Mountain Energy Storage II | 818 Olinger 138kV | Collin | NORTH | 2025-02-17 | OTH | BA | 100.8 | FIS Request | 2022-06-22 | 2022-06-02 |  | 2022-06-17 |  |  |  | No |  |  | Not Required
25INR0109 | Sun Cactus Solar | SS Started, FIS Started, No IA | Sun Cactus Solar Project, LLC | tap 138kV 8510 Falfurrias - 8695 Crestonio | Duval | SOUTH | 2025-08-01 | SOL | PV | 121.88 | FIS Request | 2022-06-17 |  |  | 2022-06-20 |  |  |  | No |  |  | Not Required
26INR0001 | Turin TxHSR TPSS HN-6 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | 8 Crutchfield 138kV | Grimes | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-10-22 | 2019-09-27 | 2021-04-28 | 2019-09-27 |  |  |  | No
26INR0004 | GRIMES SOLAR | SS Completed, FIS Started, No IA | CG Grimes County LLC | 40600 Roans Prairie 345kV | Grimes | NORTH | 2026-02-15 | SOL | PV | 153.45 |  | 2022-03-09 | 2022-03-14 | 2022-06-03 | 2022-03-07 |  |  |  | No |  |  | Not Required

## Project Details - Small Gen
GIM Project Details - Small Generators
NOTES:
Due to Protocol confidentiality provisions, only those Small Generator projects are included for which ERCOT has (1) received written Notice from Interconnecting Entities (IE) that authorize the project
information to be made public, or (2) approved the IE's completed Resource Registration form as indicated by assignment of a “Model Ready Date".
Excludes projects that have a status of Inactive (status = INA).
INR | Project Name | Model Ready Date | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) | Change indicators: Proj Name, MW | IA Signed | Financial Security | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Size, COD, SFS. |  | Required to fund
[11 empty] | Status Change INA-to-PLN |  | Dist. Upgrades
12INR0059b | HOVEY (Barilla Solar 1B) | 2015-09-02 | First Solar | 60385 Solstice 138kV | Pecos | WEST | 2022-08-06 | SOL | PV | 7.4 | COD | 2013-12-26 | Yes
22INR0565 | Saragosa BESS1 (Matta Power Station) | 2022-04-13 | Matta Power Station | AEP Station Code: SGSA Load Transformer: 138_12_1 PTI Bus Number: 60716 138kV | Reeves | WEST | 2022-07-25 | OTH | BA | 9.95 | COD | 2022-01-05 | Yes | 2022-05-13 | 2022-06-20
22INR0572 | La Huerta BESS | 2022-05-04 | HEN Infrastructure, LLC | CATARINA/LOAD1/8970 | Dimmit | SOUTH | 2022-09-30 | OTH | BA | 9.95 |  | 2021-09-22 | No
22INR0573 | Burro BESS | 2022-05-04 | HEN Infrastructure, LLC | HOLCOMB/LOAD1/8108 | La Salle | SOUTH | 2022-09-15 | OTH | BA | 9.95 |  | 2021-09-22 | No
22INR0575 | Lonestar BESS | 2022-05-04 | HEN Infrastructure, LLC | LONESTAR/LONSTR_1/38190 | Ward | WEST | 2022-09-15 | OTH | BA | 9.95 |  |  | No
22INR0587 | Screwbean BESS | 2022-05-04 | HEN Infrastructure, LLC | SBEAN/LDLXFMR2/1090 | Culberson | WEST | 2022-09-15 | OTH | BA | 9.95 |  | 2021-10-12 | No
22INR0596 | Grizzly Ridge BESS | 2022-09-01 | Grizzly Ridge Solar LLC | Pottsville Switching Substation (Bus# 178) | Hamilton | NORTH | 2022-12-25 | OTH | BA | 9.95 |  | 2021-10-18 | Yes

## GIM Trends
GIM Trends
Reflects all Large Generator projects for which a Security Screening Study has been requested. The third table reflects all Small Generator projects whose GIM applications have been approved.
Excludes projects that have a status of Inactive (status = INA).
Nameplate capacity will change across time due to additional projects, cancelations, expirations, adjustments from study results, and projects being placed into service.
| Year | Month | Total Projects |  |  | Project Count | [5 empty] | Project Capacity (MW)
[6 empty] | GIM milestones | [5 empty] | Fuel Type
|  |  |  | Small Generator Not Model Ready | Small Generator Model Ready | Initial Screening Study | Screening Study Complete | In Full Study | Completed Full Study | Signed Interconnection Agreement | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Battery | Other
| 2019 | Jun | 568 | 0 | 0 | 53 | 68 | 285 | 27 | 135 | 19 | 35739.18 | 59160.69 | 9739.6 | 0 | 0 | 0 | 3956.79 | 300
| 2019 | Jul | 586 | 0 | 0 | 36 | 87 | 295 | 25 | 143 | 11 | 36048.46 | 62356.08 | 9282.6 | 13 | 0 | 0 | 3970.39 | 300
| 2019 | Aug | 583 | 0 | 0 | 30 | 91 | 303 | 27 | 132 | 12 | 35275.72 | 64579.48 | 8206.8 | 13 | 0 | 0 | 4199.79 | 340.6
| 2019 | Sep | 575 | 0 | 0 | 30 | 91 | 298 | 26 | 130 | 15 | 34553.51 | 64343.73 | 7405.2 | 13 | 0 | 0 | 4452.39 | 300
| 2019 | Oct | 582 | 0 | 0 | 36 | 88 | 294 | 29 | 135 | 16 | 31683.23 | 64789.75 | 7445.5 | 13 | 0 | 0 | 5627.39 | 350
| 2019 | Nov | 589 | 0 | 0 | 38 | 89 | 300 | 29 | 133 | 11 | 32252.73 | 64664.04 | 5898 | 13 | 0 | 0 | 7214.39 | 350
| 2019 | Dec | 584 | 0 | 0 | 31 | 78 | 325 | 21 | 129 | 19 | 30173.96 | 67807.94 | 5607 | 13 | 0 | 0 | 7790.29 | 350
| 2020 | Jan | 613 | 0 | 0 | 47 | 78 | 333 | 23 | 132 | 3 | 30573.34 | 73636.8 | 5607 | 13 | 0 | 0 | 8965.62 | 558.96
| 2020 | Feb | 633 | 0 | 0 | 48 | 87 | 334 | 27 | 137 | 1 | 30514.72 | 77699.12 | 5507 | 13 | 0 | 0 | 9978.58 | 350
| 2020 | Mar | 621 | 0 | 0 | 35 | 101 | 320 | 21 | 144 | 21 | 28888.4 | 76238.17 | 5749 | 13 | 493 | 0 | 10381.08 | 350
| 2020 | Apr | 619 | 0 | 0 | 15 | 117 | 304 | 26 | 157 | 6 | 27779.79 | 76252.21 | 5083.8 | 13 | 493 | 0 | 10899.04 | 350
| 2020 | May | 595 | 0 | 0 | 20 | 89 | 300 | 27 | 159 | 40 | 25958.39 | 72191.13 | 5083.8 | 13 | 420 | 0 | 12380.59 | 480.95
| 2020 | Jun | 602 | 0 | 0 | 30 | 84 | 295 | 38 | 155 | 20 | 26271.99 | 73655.09 | 5416.8 | 13 | 420 | 0 | 13041.64 | 410
| 2020 | Jul | 615 | 0 | 0 | 27 | 84 | 298 | 48 | 158 | 9 | 25477.63 | 75322.06 | 5373.88 | 13 | 420 | 0 | 14475.7 | 350
| 2020 | Aug | 644 | 0 | 0 | 25 | 83 | 316 | 54 | 166 | 5 | 25886.17 | 76960.74 | 7024.02 | 13 | 420 | 0 | 17436.1 | 350
| 2020 | Sep | 633 | 0 | 0 | 28 | 65 | 318 | 40 | 182 | 37 | 23678.97 | 77073.76 | 6818.72 | 13 | 420 | 0 | 18109.14 | 350
| 2020 | Oct | 666 | 0 | 0 | 39 | 69 | 331 | 29 | 198 | 3 | 23926.34 | 81301.63 | 7197.18 | 13 | 0 | 0 | 19459.46 | 350
| 2020 | Nov | 673 | 0 | 0 | 37 | 78 | 332 | 27 | 199 | 5 | 23897.86 | 81156.75 | 7197.18 | 13 | 0 | 0 | 21404.05 | 350
| 2020 | Dec | 708 | 0 | 0 | 40 | 86 | 352 | 28 | 202 | 10 | 23619.61 | 88031.55 | 7178.58 | 13 | 0 | 0 | 23550.04 | 350
| 2021 | Jan | 738 | 0 | 0 | 57 | 84 | 354 | 27 | 216 | 9 | 23334.25 | 89895.91 | 7224.34 | 13 | 0 | 0 | 26107.2 | 350
| 2021 | Feb | 769 | 0 | 0 | 54 | 95 | 374 | 20 | 226 | 4 | 24552.13 | 92012.3 | 7236.54 | 13 | 0 | 0 | 28352.55 | 400
| 2021 | Mar | 778 | 0 | 0 | 73 | 66 | 392 | 17 | 230 | 33 | 23859.29 | 88856.46 | 7897.04 | 13 | 0 | 0 | 30300.62 | 400
| 2021 | Apr | 804 | 0 | 0 | 63 | 92 | 399 | 19 | 231 | 12 | 23640.17 | 91546.69 | 7894.04 | 0 | 0 | 0 | 32002.39 | 500
| 2021 | May | 807 | 0 | 0 | 37 | 120 | 395 | 27 | 228 | 11 | 23764.26 | 91769.36 | 7606.04 | 0 | 0 | 0 | 33671.49 | 350
| 2021 | Jun | 818 | 0 | 0 | 43 | 114 | 409 | 26 | 226 | 16 | 22518.72 | 92814.52 | 8341.04 | 0 | 0 | 0 | 36206.58 | 350
| 2021 | Jul | 832 | 0 | 0 | 40 | 125 | 395 | 36 | 236 | 4 | 21933.87 | 94468.15 | 10399.04 | 0 | 0 | 0 | 36953.54 | 350
| 2021 | Aug | 861 | 0 | 0 | 59 | 122 | 412 | 34 | 234 | 5 | 22625.84 | 94745.6 | 12907.04 | 0 | 0 | 0 | 39488 | 984.67
| 2021 | Sep | 890 | 0 | 0 | 52 | 133 | 428 | 40 | 237 | 10 | 22536.64 | 100293.12 | 13547.04 | 0 | 0 | 50 | 42465 | 1493.24
| 2021 | Oct | 902 | 0 | 0 | 42 | 143 | 441 | 48 | 228 | 6 | 21705.98 | 99988.53 | 17560.24 | 0 | 0 | 50 | 45029.43 | 985
| 2021 | Nov | 928 | 0 | 0 | 43 | 147 | 458 | 51 | 229 | 8 | 22091.28 | 100783.54 | 18449.74 | 0 | 0 | 50 | 46945.94 | 985
| 2021 | Dec | 964 | 0 | 0 | 49 | 156 | 467 | 62 | 230 | 5 | 21939 | 103923.04 | 18449.74 | 0 | 0 | 50 | 51416 | 985
| 2022 | Jan | 983 | 0 | 0 | 44 | 168 | 470 | 53 | 238 | 8 | 21370.17 | 105880.2 | 18399.52 | 0 | 0 | 50 | 52346.02 | 985
| 2022 | Feb | 1018 | 8 | 4 | 67 | 152 | 488 | 48 | 251 | 28 | 21261.67 | 110323.3 | 17763.62 | 0 | 0 | 50 | 55336.83 | 1216.9
| 2022 | Mar | 1024 | 1 | 10 | 64 | 141 | 505 | 52 | 251 | 23 | 20364.41 | 107046.12 | 17763.62 | 0 | 0 | 50 | 57741.69 | 1902.58
| 2022 | Apr | 1047 | 2 | 10 | 59 | 138 | 518 | 55 | 265 | 8 | 21566.29 | 108666.99 | 18287.62 | 0 | 0 | 50 | 59873.93 | 1670.72
| 2022 | May | 1017 | 4 | 9 | 37 | 89 | 552 | 58 | 268 | 55 | 19543.69 | 106920.38 | 12887.62 | 0 | 0 | 50 | 58248.93 | 1468.8
| 2022 | Jun | 1065 | 4 | 7 | 63 | 87 | 565 | 64 | 275 | 7 | 22243.19 | 111730.5 | 12744.32 | 0 | 0 | 53 | 65365.67 | 1466.83
Note: Other contains all Fuel and Technology Types not in the Solar, Wind, Gas or Battery categories.

## data_GIM Trends_1 (hidden)
| # Signed Interconnect Agreement | # Completed Full Study | # in Full Study | # Screening Study Complete | # Initial Screening study | GW Capacity
Jun-21 | 226 | 26 | 409 | 114 | 43 | 160.2309
Jul-21 | 236 | 36 | 395 | 125 | 40 | 164.1046
Aug-21 | 234 | 34 | 412 | 122 | 59 | 170.7511
Sep-21 | 237 | 40 | 428 | 133 | 52 | 180.385
Oct-21 | 228 | 48 | 441 | 143 | 42 | 185.3192
Nov-21 | 229 | 51 | 458 | 147 | 43 | 189.3055
Dec-21 | 230 | 62 | 467 | 156 | 49 | 196.7628
Jan-22 | 238 | 53 | 470 | 168 | 44 | 199.0309
Feb-22 | 251 | 48 | 488 | 152 | 67 | 205.763
Mar-22 | 251 | 52 | 505 | 141 | 64 | 204.759
Apr-22 | 265 | 55 | 518 | 138 | 59 | 209.9961
May-22 | 268 | 58 | 552 | 89 | 37 | 198.9925
Jun-22 | 275 | 64 | 565 | 87 | 63 | 213.6035

## data_GIM Trends_2 (hidden)
| Natural Gas | Nuclear | Coal | Wind | Solar | Biomass | Battery | Other | Total Project Count | Cancelled Project Count
Jun-21 | 8.341 | 0 | 0 | 22.5187 | 92.8145 | 0 | 36.2066 | 0.35 | 818 | 16
Jul-21 | 10.399 | 0 | 0 | 21.9339 | 94.4681 | 0 | 36.9535 | 0.35 | 832 | 4
Aug-21 | 12.907 | 0 | 0 | 22.6258 | 94.7456 | 0 | 39.488 | 0.98467 | 861 | 5
Sep-21 | 13.547 | 0 | 0 | 22.5366 | 100.2931 | 0.05 | 42.465 | 1.4932 | 890 | 10
Oct-21 | 17.5602 | 0 | 0 | 21.706 | 99.9885 | 0.05 | 45.0294 | 0.985 | 902 | 6
Nov-21 | 18.4497 | 0 | 0 | 22.0913 | 100.7835 | 0.05 | 46.9459 | 0.985 | 928 | 8
Dec-21 | 18.4497 | 0 | 0 | 21.939 | 103.923 | 0.05 | 51.416 | 0.985 | 964 | 5
Jan-22 | 18.3995 | 0 | 0 | 21.3702 | 105.8802 | 0.05 | 52.346 | 0.985 | 983 | 8
Feb-22 | 17.7636 | 0 | 0 | 21.2617 | 110.3233 | 0.05 | 55.3368 | 1.2169 | 1018 | 28
Mar-22 | 17.7636 | 0 | 0 | 20.3644 | 107.0461 | 0.05 | 57.7417 | 1.9026 | 1024 | 23
Apr-22 | 18.2876 | 0 | 0 | 21.5663 | 108.667 | 0.05 | 59.8739 | 1.6707 | 1047 | 8
May-22 | 12.8876 | 0 | 0 | 19.5437 | 106.9204 | 0.05 | 58.2489 | 1.4688 | 1017 | 55
Jun-22 | 12.7443 | 0 | 0 | 22.2432 | 111.7305 | 0.053 | 65.3657 | 1.4668 | 1068 | 7

## data_GIM Trends_3 (hidden)
| # Not Model Ready | # Model Ready | MW Capacity
Jun-21 | 0 | 0
Jul-21 | 0 | 0
Aug-21 | 0 | 0
Sep-21 | 0 | 0
Oct-21 | 0 | 0
Nov-21 | 0 | 0
Dec-21 | 0 | 0
Jan-22 | 0 | 0
Feb-22 | 8 | 4 | 119.4
Mar-22 | 1 | 10 | 109.45
Apr-22 | 2 | 10 | 119.44
May-22 | 4 | 9 | 126.88
Jun-22 | 4 | 7 | 100.13

## data_GIM Trends_4 (hidden)
|  | Gas | Wind | Solar | Battery | Other
COASTAL | 2022 | 0.546 | 0.5741 | 0.66788 | 0.1006
| 2023 | 0.39824 | 0.7027 | 4.299 | 3.0693
| 2024 |  | 0.564 | 2.609 | 3.618
| 2025 |  |  | 2.0462 | 0.101
| 2026 |  | 2.5 | 0.20417
| 2027 |  |  | 0.20417
HOUSTON | 2022 | 0.063 |  | 0.89179
| 2023 | 1.1007 |  | 0.97592 | 2.7149
| 2024 | 0.92683 |  | 0.1732 | 2.8584
| 2025 |  |  |  |  | 0.05
| 2026 |  | 1
| 2028 |  |  |  |  | 0.05
WEST | 2021 |  |  |  | 0.12183
| 2022 | 0.083 | 4.3703 | 0.479 | 0.64644
| 2023 | 4.892 | 2.1589 | 8.6753 | 5.2009 | 0.01803
| 2024 | 0.13 | 2.8703 | 9.3409 | 4.0165
| 2025 |  |  | 5.343 | 0.57211
| 2026 | 1.35 |  | 0.5002 | 0.20889
| 2027 |  |  | 0.625
NORTH | 2022 | 0.186 | 1.8444 | 3.222 | 0.83345
| 2023 | 0.051 | 1.0158 | 11.1042 | 5.7561 | 0.2849
| 2024 | 0.45867 | 0.79622 | 17.8099 | 11.3447 | 0
| 2025 | 0.3244 |  | 6.4597 | 4.7383 | 0.1
| 2026 |  |  | 0.15345
| 2028 |  |  |  |  | 0.15
PANHANDLE | 2021 | 0.112
| 2023 |  | 0.6825 | 2.5328 | 0.60669
| 2024 |  | 0.165 | 2.327 | 1.8571
| 2025 |  | 0.289 | 0.204
SOUTH |  |  |  |  | 0.1
| 2022 | 0.12 | 1.1267 | 0.8661 | 0.66604
| 2023 | 1.5525 | 0.3632 | 10.0446 | 7.5566 | 0.2319
| 2024 |  | 1.2202 | 15.2742 | 6.2723
| 2025 | 0.45 |  | 4.6978 | 2.4053
| 2026 |  |  |  |  | 0.635

## Commissioning Update
Commissioning Approvals during June 2022
Commissioning Category | INR | Size Category | Project Name | Fuel | County | Approval Date * | MW **
Commercial Operation Approved by ERCOT* | 21INR0460 | Large | Republic Road Storage | Other | Robertson | 2022-06-15 | 51.75
Commercial Operation Approved by ERCOT* | 22INR0597 | Large | RABBS U6 Power Station | Gas | Fort Bend | 2022-06-23 | 51
Commercial Operation Approved by ERCOT* | 22INR0577 | Small | Cedarvale BESS | Other | Reeves | 2022-06-17 | 9.95
Commercial Operation Approved by ERCOT* | 18INR0077 | Large | Colorado Bend 2 repower | Gas | Wharton | 2022-06-30 | 45
Commercial Operation Approved by ERCOT* | 22INR0576 | Small | Rattlesnake BESS | Other | Ward | 2022-06-23 | 9.95
Commercial Operation Approved by ERCOT* | 22INR0574 | Small | Coyote Springs BESS | Other | Reeves | 2022-06-14 | 9.95
Commercial Operation Approved by ERCOT* | 22INR0601 | Large | RABBS U7 U8 Power Station | Gas | Fort Bend | 2022-06-23 | 102
Commercial Operation Approved by ERCOT* | 16INR0086 | Large | Cactus Flats Wind | Wind | Concho | 2022-06-13 | 148.4
Commercial Operation Approved by ERCOT* | 19INR0056 | Large | LIGNIN (SJRR) | Gas | Harris | 2022-06-20 | 100
Synchronization Approved by ERCOT | 22INR0565 | Small | Saragosa BESS1 (Matta Power Station) | Other | Reeves | 2022-06-20 | 9.95
Synchronization Approved by ERCOT | 23INR0482 | Large | RABBS U2 Power Station | Gas | Fort Bend | 2022-06-24 | 51
Synchronization Approved by ERCOT | 19INR0131 | Large | Rowland Solar I | Solar | Fort Bend | 2022-06-13 | 101.75
Synchronization Approved by ERCOT | 22INR0577 | Small | Cedarvale BESS | Other | Reeves | 2022-06-07 | 9.95
Synchronization Approved by ERCOT | 19INR0085 | Large | Blue Jay Solar | Solar | Grimes | 2022-06-28 | 141.05
Synchronization Approved by ERCOT | 20INR0291 | Large | Silicon Hill Storage | Other | Travis | 2022-06-02 | 104.62
Synchronization Approved by ERCOT | 20INR0280 | Large | High Lonesome BESS | Other | Crockett | 2022-06-01 | 51.06
Energization Approved by ERCOT | 22INR0577 | Small | Cedarvale BESS | Other | Reeves | 2022-06-01 | 9.95
Energization Approved by ERCOT | 20INR0098 | Large | Danciger Solar | Solar | Brazoria | 2022-06-30 | 203.2
Energization Approved by ERCOT | 20INR0205 | Large | Roseland Solar | Solar | Falls | 2022-06-07 | 254
Energization Approved by ERCOT | 21INR0384 | Large | Ratliff (Concho Valley) Solar | Solar | Tom Green | 2022-06-09 | 159.8
Energization Approved by ERCOT | 22INR0254 | Large | Pisgah Ridge Solar | Solar | Navarro | 2022-06-27 | 253.85
Energization Approved by ERCOT | 18INR0053 | Large | TAVNER | Solar | Fort Bend | 2022-06-07 | 240
Energization Approved by ERCOT | 22INR0506 | Large | Roseland Solar II | Solar | Falls | 2022-06-07 | 254
Energization Approved by ERCOT | 21INR0205 | Large | Radian Solar | Solar | Brown | 2022-06-20 | 327.42
* For projects approved for commercial operations, the approval date is the Resource Commissioning Date defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a
Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative
values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.

## Inactive Projects
Inactive Projects as of end of June 2022*
INR | Size Category | Project Name | Fuel | County | Inactive Date | MW **
16INR0044 | Large | Halyard Wharton | Gas | Wharton | 2019-08-30 13:26 | 484
13INR0025 | Large | Northdraw Wind | Wind | Randall | 2019-08-30 13:38 | 150
17INR0010 | Large | FGE Texas 2 Gas | Gas | Mitchell | 2019-08-30 13:41 | 742.9
16INR0099 | Large | Hecate Solar | Solar | Brewster | 2019-08-30 14:57 | 33
16INR0101 | Large | Chatee Solar | Solar | Pecos | 2019-08-30 14:59 | 57
16INR0102 | Large | Owego Solar | Solar | Pecos | 2019-08-30 15:01 | 74
13INR0010a | Large | Mariah Del Este Wind | Wind | Parmer | 2019-09-09 10:19 | 152.5
20INR0025 | Large | Spinel Solar | Solar | Medina | 2019-09-10 14:02 | 30
20INR0024 | Large | Fluorite Solar | Solar | Uvalde | 2019-09-11 13:32 | 25
19INR0055 | Large | Monte Cristo 2 Wind | Wind | Hidalgo | 2019-10-24 18:00 | 236.9
17INR0036 | Large | Grandview 4 Phase A Wind | Wind | Carson | 2019-10-31 10:59 | 200.5
20INR0096 | Large | Desert Rose Solar | Solar | Andrews | 2019-11-12 13:44 | 200
18INR0009 | Large | Eagle Pines Gas | Gas | Cherokee | 2019-11-19 10:20 | 1173.5
21INR0363 | Large | Carol Battery | Other | Potter | 2019-11-25 16:33 | 168
19INR0031 | Large | Bestla Solar | Solar | Winkler | 2020-03-04 16:50 | 180
20INR0146 | Large | Angus Storage | Other | Bosque | 2020-05-04 11:36 | 63
22INR0329 | Large | Girasol | Solar | Zavala | 2020-05-22 08:29 | 200
20INR0023 | Large | Agate Solar | Solar | Ellis | 2020-05-22 15:12 | 60
19INR0101 | Large | Tehuacana Wind | Wind | Limestone | 2020-05-28 10:23 | 600
21INR0503 | Large | Celeste Energy Storage | Other | Pecos | 2020-06-03 10:35 | 60.89
19INR0030 | Large | San Bernard Solar | Solar | Wharton | 2020-06-18 11:51 | 100
17INR0043 | Large | Vaquero 1 Wind | Wind | Zapata | 2020-07-01 18:45 | 400
21INR0015 | Large | Arroyo Del Bisonte Solar | Solar | Wharton | 2020-07-06 16:03 | 300
20INR0299 | Large | Sparkl BESS | Other | Guadalupe | 2020-09-16 12:30 | 20
21INR0292 | Large | Slama Solar | Solar | Wichita | 2020-10-15 14:32 | 251.65
19INR0142 | Large | Bacon Switch Solar | Solar | Wichita | 2020-11-04 04:38 | 180
19INR0161 | Large | Pierce Wind | Wind | Wharton | 2021-03-16 10:13 | 300
20INR0043 | Large | Gulf Wind 2 | Wind | Kenedy | 2021-04-02 08:54 | 226.5
21INR0485 | Large | Texana Storage | Other | Wharton | 2021-04-05 22:27 | 150.94
20INR0267 | Large | Greens Bayou Expansion | Gas | Harris | 2021-04-17 01:08 | 140
18INR0072 | Large | Blue Summit repower | Wind | Wilbarger | 2021-04-28 15:42 | 9.9
21INR0465 | Large | San Bernard Storage | Other | Wharton | 2021-06-14 17:46 | 100.62
18INR0056 | Large | Hallmark Solar | Solar | Hunt | 2021-06-21 09:12 | 43
20INR0013 | Large | Basalt Solar | Solar | Uvalde | 2021-08-16 09:22 | 20
23INR0152 | Large | Madrone Energy Storage | Other | Comal | 2021-08-20 09:03 | 102.49
20INR0232 | Large | Mars Solar | Solar | Childress | 2021-11-17 09:06 | 52.75
20INR0274 | Large | SIXTY SIX Solar | Solar | Winkler | 2021-12-21 11:02 | 3.75
19INR0135 | Large | Hill Solar | Solar | Hill | 2022-02-21 13:37 | 80
22INR0548 | Large | Fighting Jays Battery | Other | Fort Bend | 2022-02-25 17:43 | 53.2
19INR0099b | Large | Kontiki 2 Wind (ERNEST) | Wind | Glasscock | 2022-03-10 15:42 | 250.1
19INR0099a | Large | Kontiki 1 Wind (ERIK) | Wind | Glasscock | 2022-03-10 15:46 | 250.1
20INR0259 | Large | San Bernard Solar II | Solar | Wharton | 2022-03-11 11:26 | 102
22INR0266 | Large | Creekfield Solar | Solar | Fort Bend | 2022-03-23 11:25 | 161.34
22INR0379 | Large | Creekfield Storage | Other | Fort Bend | 2022-03-25 16:59 | 69
23INR0217 | Large | Snap Jaw BESS | Other | Harris | 2022-04-20 15:58 | 201.28
23INR0218 | Large | Stump Tail BESS | Other | Harris | 2022-04-20 15:59 | 301.69
22INR0422 | Large | Ferdinand Grid BESS | Other | Bexar | 2022-04-22 08:59 | 202.65
23INR0106 | Large | Vorsavio Grid BESS | Other | Webb | 2022-04-27 14:01 | 100.67
22INR0387 | Large | Val Vista Grid BESS | Other | Hidalgo | 2022-04-28 14:10 | 202.85
24INR0102 | Large | Seguro Grid | Other | Hidalgo | 2022-05-03 15:45 | 201.33
23INR0350 | Large | Fort Duncan BESS | Other | Maverick | 2022-05-05 11:17 | 106.15
23INR0067 | Large | Wekiva Grid | Other | Titus | 2022-05-09 21:05 | 202.61
21INR0502 | Large | LUND STORAGE | Other | Travis | 2022-05-31 12:33 | 60
20INR0217 | Large | CAROL wind | Wind | Potter | 2022-06-14 09:58 | 165.7
23INR0158 | Large | High Chaparral BESS 138kV | Other | Brazoria | 2022-06-15 15:23 | 51.74
23INR0157 | Large | High Chaparral Solar 138kV | Solar | Brazoria | 2022-06-15 15:26 | 147.63
18INR0030 | Large | Canyon Wind | Wind | Scurry | 2022-06-22 15:49 | 360.5
25INR0076 | Large | Violet Storage | Other | Nueces | 2022-06-27 10:31 | 151
22INR0495 | Large | TIMBERWOLF BESS 2 | Other | Upton | 2022-06-30 16:10 | 150
* Includes only those projects designated as Inactive by ERCOT or the project developer after the developer makes a Full Interconnection Study (FIS) request, or
in the case of Small Generators, after their Resource Registrations have been approved.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.

## Cancellation Update
Projects Cancelled by the Developer during June 2022*
INR | Size Category | Project Name | Fuel | County | Cancel Date | MW **
23INR0505 | Large | Hornet Solar 2 LLC Cancelled | Solar | Swisher | 2022-06-14 16:05 | 11
20INR0048 | Large | Century Oak Wind | Wind | Callahan | 2022-06-14 16:06 | 126
24INR0046 | Large | Milky Way Solar | Solar | Robertson | 2022-06-17 | 300
* Includes only those projects cancelled by the developer after it makes a Full Interconnection Study (FIS) request, or in the case of Small Generators, after the Resource Registrations have been approved.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.