## Contents
GIM Activity: Sep 01, 2025 to Sep 30, 2025
Table of Contents
Disclaimer and References | Disclaimer on the use of this report, and references to associated ERCOT Binding Documents ***Please read***
Acronyms | A list of the various acronyms used throughout the report
Summary | Tables that provide project aggregate counts and megawatt capacities by GIM phase and fuel type
Project Details - Large Gen | A table that list project details for Large Generators as defined in ERCOT Planning Guide Section 5.2.1(3); only include projects for which a Full Interconnection Study has been requested
Project Details - Small Gen | A table that list project details for Small Generators as defined in ERCOT Planning Guide 5.2.1(3); only include projects for which the Resource Registration form has been approved by ERCOT
GIM Trends | Charts and tables that show historical and projected interconnection study trends
Commissioning Update | A table listing project commissioning approval milestones met for the month: energization, synchronization, and commercial operations approval
Inactive Projects | A table listing Inactive projects
Cancellation Update | A table listing the projects cancelled for the month
Time of Report Run: Oct 1, 2025 8:00:39 AM

## Disclaimer and References
Generator Interconnection Status Report - Disclaimer
FOR PLANNING PURPOSES ONLY
This ERCOT Working Paper has been prepared for specific ERCOT and Market Participant purposes, and has been
developed from data provided by Interconnecting Entities and Transmission Service Providers that has been entered into the online RIOO system.
The data may contain errors or be obsolete depending on when the data was entered. ERCOT MAKES NO WARRANTY, EXPRESS
OR IMPLIED,INCLUDING ANY WARRANTY OF MERCHANTABILITY OR FITNESS FOR ANY PARTICULAR PURPOSE,
AND DISCLAIMS ANY AND ALL LIABILITY WITH RESPECT TO THE ACCURACY OF SAME OR THE FITNESS OR
APPROPRIATENESS OF SAME FOR ANY PARTICULAR USE. THIS ERCOT WORKING PAPER IS SUPPLIED WITH ALL FAULTS.
References
The links below provide more information on the ERCOT interconnection process:
http://www.ercot.com/mktrules/guides/planning/current
See the Resource Interconnection Handbook, available on ERCOT’s Resource Integration webpage:
http://www.ercot.com/services/rq/integration

## Acronyms
Acronyms
GIM = Generator Interconnection or Modification request
GINR = Generation Interconnection or Change Request
COD = Commercial Operation Date
SS = Security Screening Study
FIS = Full Interconnection Study
IA = Interconnection Agreement; can be either of the following:
- Standard Generation Interconnection Agreement (SGIA)
- Public financially binding agreement
- An official letter from a Municipally Owned Utility or Electric Cooperative signifying developer intent to build and operate generation facilities and
interconnect with the MOU or EC
POI = Point of lnterconnection
INR = Interconnection Request Number
TSP = Transmission Service Provider
NtP = Notice-to-Proceed given to the TSP for interconnection construction
CDR = Capacity, Demand and Reserves Report
SFS = Sufficient Financial Security provided to the TSP for construction of the interconnection facilities
QSA = Quarterly Stability Assessment
INA = Inactive status
PLN = Planned status
Fuel Types | Technology Types
BIO = Biomass | BA = Battery Energy Storage
COA = Coal | CC = Combined-Cycle
GAS = Gas | CE = Compressed Air Energy Storage
GEO = Geothermal | CP = Concentrated Solar Power
HYD = Hydrogen | EN = Energy Storage
NUC = Nuclear | FC = Fuel Cell
OIL = Fuel Oil | GT = Combustion (gas) Turbine, but not part of a Combined-Cycle
OTH = Other | HY = Hydroelectric Turbine
PET = Petcoke | IC = Internal Combustion Engine, eg. Reciprocating
SOL = Solar | OT = Other
WAT = Water | PV = Photovoltaic Solar
WIN = Wind | ST = Steam Turbine other than Combined-Cycle
WT = Wind Turbine

## Summary
Summary |  |  | Major GIM Milestone Status by Fuel/Technology Type, MW
Currently tracking 2042 generation interconnection or change requests as of Sep 30, 2025 |  |  | Includes only those (1) Large Generator projects for which a Screening Study has been requested, (2) Small Generators for which an interconnection request has been made, and (3) projects that are not Inactive
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  |  | Fuel | Technology | SS Started | SS Started | SS Completed | SS Completed | SS Completed | SS Started | SS Started | SS Completed | SS Completed | SS Completed | Small Generator | Small Generator | TOTAL
Includes only those (1) Large Generator projects for which a Screening Study has been requested, |  |  | Type | Type | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | Not Model Ready | Model Ready
(2) Small Generators for which an interconnection request has been made and |  |  |  |  | No IA | No IA | No IA | No IA | No IA | IA | IA | IA | IA | IA
and (3) projects that are not Inactive
Status of SS, FIS and IA | Project Count | % of Total | Gas | Combined-Cycle | 1700 | 3784.98 | 3419.5 | 6175.28 | 34.5 |  |  |  |  | 1438 |  | 9.3 | 16561.56
LARGE GENERATORS |  |  | Gas | Combustion Turbine | 2000 |  | 2824 | 11145.56 | 3099.53 |  |  |  | 518.83 | 2299.7 |  |  | 21887.62
SS Started, FIS Not Started, No IA | 20 | 0.9794% | Gas | Internal Combustion Engine | 418.2 | 1597.16 | 216 | 603.43 | 123.4 |  |  |  |  | 889.28 | 29.79 | 19.8 | 3897.06
SS Started, FIS Started, No IA | 74 | 3.624% | Gas | Compressed Air Energy Storage
SS Completed, FIS Not Started, No IA | 94 | 4.603% | Gas | Steam Turbine |  |  |  | 1335 | [5 empty] | 14 |  |  | 1349
SS Completed, FIS Started, No IA | 1122 | 54.95% | Gas | Fuel Cell
SS Completed, FIS Completed, No IA | 117 | 5.73% | Gas | Total gas | 4118.2 | 5382.14 | 6459.5 | 19259.27 | 3257.43 |  |  |  | 518.83 | 4640.98 | 29.79 | 29.1 | 43695.24
SS Started, FIS Not Started, IA | 0 | 0% | Coal
SS Started, FIS Started, IA | 0 | 0% | Wind |  |  | 4132.41 | 2543.89 | 26072.29 | 780.78 |  |  |  | 6398.14 | 6165.94 |  |  | 46093.45
SS Completed, FIS Not Started, IA | 2 | 0.09794% | Solar |  | 2216.99 | 5678.67 | 8487.48 | 79706.2 | 5796.38 |  |  | 304.94 | 30197.45 | 27506.92 | 29.39 | 7.4 | 159931.82
SS Completed, FIS Started, IA | 213 | 10.43% | Biomass
SS Completed, FIS Completed, IA | 317 | 15.52% | Other | Battery | 3552.08 | 5373.19 | 7253.35 | 114066.51 | 12962.89 |  |  |  | 13816.91 | 20382.37 | 208.29 | 437.17 | 178052.76
SMALL GENERATORS |  |  | Other* |  |  | 185.1 | 1839 | 1794 | [5 empty] | 314.5 |  | 29.85 | 4162.45
Not Model Ready* | 29 | 1.42% | TOTAL |  | 9887.27 | 20751.51 | 26583.22 | 240898.27 | 22797.48 |  |  | 304.94 | 50931.33 | 59010.71 | 267.47 | 503.52 | 431935.72
Model Ready* | 54 | 2.644% | * Other includes petroleum coke (pet coke), hydroelectric, fuel oil, geothermal energy, other miscellaneous fuels reported by developers, and fuel cells that use fuels other than natural gas.
Total Interconnection Requests | 2042
Inactive (since last month) | 9
Cancelled (since last month) | 23
Capacity, MW
Total Capacity Under Study | 431935.72
Interconnection Agreements Executed | 111575.64
Inactive (since last month) | 2102.97
Inactive changed to Planned (since last month) | 100.8
Inactive changed to Cancelled (since last month) | 0
Cancelled (since last month) | 4828.67
* "Not Model Ready" means that a Small Generator's data has not yet been loaded into the Network
Operations Model. "Model Ready" means that the data has been loaded into the NOM, and the Resource is
ready to begin the commissioning process.

## Project Details - Large Gen
GIM Project Details - Large Generators
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study has been requested are included.
Excludes projects that have a status of Inactive (status = INA).
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GIM system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not been obtained or reported to ERCOT yet.
A developer may split a project into two or more additional projects with different INR numbers during the interconnection request process. Due to current RIOO interface limitations,
the new projects do not inherit certain milestone dates entered for the original project. As a result, dates may be blank even though the milestones have been met.
A “1-1-1900” date is used to signify that an actual date for a project milestone is not available. This typically occurs for project data migrated from the legacy GINR database to the RIOO system.
Project Attributes | [10 empty] | Changes from Last Report | GIM Project Milestone Dates
INR | Project Name | GIM Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | Economic Study Required | IA Signed |  | Air Permit | GHG Permit | Water Availability | Meets Planning | Meets All Planning |  | Construction Start | Construction End | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Change indicators: Proj Name, MW | Approval Date for | [6 empty] | Financial Security |  |  |  | Guide Section 6.9(1) | Guide Section 6.9 | Meets Planning Guide
[11 empty] | Size, COD, SFS/NtP, FIS Request, | Submission of Proof of | [6 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[11 empty] | Status Change INA-to-PLN | Site Control | [6 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[23 empty] | Models | Models
15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | McCrae Wind Energy II, LLC | 59903 Bearkat 345kV | Glasscock | WEST | 2025-10-31 | WIN | WT | 162.1 | COD |  | 2013-11-27 | 2014-01-27 | 2014-04-15 | 2017-09-27 | No | 2018-05-30 | Yes | Not Required | Not Required | Not Required | 2018-05-30 | 2018-09-19 | 2019-01-22 |  |  | 2020-02-10 | 2020-05-12
16INR0049 | Nazareth Solar | SS Completed, FIS Started, IA | TX Nazareth Solar, LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala C2 | Castro | PANHANDLE | 2027-08-05 | SOL | PV | 203 |  | 2014-07-07 | 2014-06-19 | 2014-07-25 | 2014-07-01 |  | No | 2023-06-07 | Yes | Not Required | Not Required | Not Required | 2024-03-22
16INR0081 | Mesteno Wind | SS Completed, FIS Completed, IA | Mesteno Windpower, LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2025-06-30 | WIN | WT | 201.6 |  | 2014-12-30 | 2014-12-30 | 2015-03-09 | 2014-12-30 | 2018-01-29 | No | 2018-04-25 | Yes | Not Required | Not Required | Not Required | 2018-04-25 | 2019-03-28 | 2019-04-01 |  |  | 2019-11-26 | 2019-12-12
16INR0085 | Priddy Wind | SS Completed, FIS Completed, IA | ENGIE North America | tap 345kV 1444 Brown – 3422 Killeen | Mills | NORTH | 2025-12-30 | WIN | WT | 302.4 |  | 2015-03-06 | 2015-01-14 | 2015-02-10 | 2015-03-06 | 2021-04-30 | No | 2020-08-13 | Yes | Not Required | Not Required | Not Required | 2021-03-29 | 2021-04-30 | 2021-04-30 |  |  | 2021-10-13 | 2021-11-19
16INR0104 | Big Sampson Wind | SS Completed, FIS Completed, IA | Big Sampson Wind Project, LLC | tap 345kV 76015 Cedar Canyon - 7053 Noelke | Crockett | WEST | 2025-10-04 | WIN | WT | 265.4 |  |  | 2015-05-11 | 2015-06-17 | 2015-05-11 | 2024-10-30 | Yes | 2019-11-08 | Yes | Not Required | Not Required | Not Required | 2024-10-31 | 2024-11-04 | 2024-11-04 |  |  | 2025-06-04 | 2025-06-16
16INR0112 | Loma Pinta Wind | SS Completed, FIS Started, IA | Enerverse | 5705 Fowlerton 138kV | La Salle | SOUTH | 2026-12-31 | WIN | WT | 197.01 |  |  | 2015-05-18 | 2015-07-02 | 2015-05-18 |  | No | 2017-12-13 | No | Not Required | Not Required | Not Required
17INR0027b | Coyote Wind | SS Completed, FIS Completed, IA | Coyote Wind | 11305 Dermott 345kV | Scurry | WEST | 2025-12-01 | WIN | WT | 242.6 |  |  | 2015-04-22 | 2015-05-22 | 2015-06-11 | 2020-01-31 | No | 2016-08-09 | Yes | Not Required | Not Required | Not Required | 2016-08-09 | 2020-01-28 | 2020-01-31 |  |  | 2020-08-24 | 2020-11-25
17INR0043 | Vaquero 1 Wind | SS Completed, FIS Started, No IA | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Zapata | SOUTH | 2027-01-15 | WIN | WT | 400 |  | 2016-04-01 | 2016-04-01 | 2016-05-10 | 2016-04-01 |  |  |  | No | Not Required | Not Required | Not Required
17INR0052 | Horse13 CallD repower | SS Completed, FIS Completed, IA | Nextera | 6216 Bluff Creek 138kV | Taylor | WEST | 2026-09-30 | WIN | WT | 44 | COD | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2018-04-10 | No | 2019-05-22 | Yes | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13 |  |  |  | 2021-03-16
17INR0053 | HHGT repower Horse13+CallD | SS Completed, FIS Completed, IA | Nextera | 7046 Kendal 345kV | Taylor | WEST | 2026-09-30 | WIN | WT | 44 | COD | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2017-07-06 | No | 2009-06-26 | No | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13 |  |  |  | 2021-09-10
17INR0054 | Capricorn I & III repower | SS Completed, FIS Completed, IA | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WEST | 2026-05-31 | WIN | WT | 32 | COD | 2017-03-09 | 2017-03-09 | 2017-04-24 | 2017-03-09 | 2018-02-26 | No | 2006-11-14 | No | Not Required | Not Required | Not Required | 2021-02-28 | 2021-02-28 | 2021-02-28 |  |  |  | 2021-03-04
17INR0061 | Capricorn IV repower | SS Completed, FIS Completed, IA | Nextera | 76090 Divide 345kV | Sterling | WEST | 2025-10-31 | WIN | WT | 9 | COD | 2017-08-23 | 2017-08-23 | 2017-09-15 | 2017-08-23 | 2018-02-06 | No | 2008-01-15 | No | Not Required | Not Required | Not Required | 2020-08-28 | 2020-08-28 | 2018-03-30 |  |  |  | 2020-08-19
17INR0068 | Sweetwater 2 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2024-11-30 | WIN | WT | 7.3 |  | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-11-10 | No | 2003-06-27 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2017-12-20
17INR0069 | Trent repower | SS Completed, FIS Completed, IA | TRENT WIND FARM LLC | 1338 Eskota 138kV | Nolan | WEST | 2025-01-30 | WIN | WT | 6.4 |  | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-03-01 | No | 2018-10-19 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-05-09
17INR0070 | Desert Sky repower | SS Completed, FIS Completed, IA | DESERT SKY WIND FARM LLC | two LCRA 138kV | Pecos | WEST | 2023-05-16 | WIN | WT | 7.2 |  | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-02-06 | No | 2018-10-18 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-09-06
18INR0009 | Eagle Pines Gas | SS Completed, FIS Started, No IA | FGE Power | tap 345kV 3109 Stryker - 3123 Trinidad | Cherokee | NORTH | 2028-10-30 | GAS | CC | 1173.5 |  | 2015-03-24 | 2015-03-30 | 2015-06-23 | 2015-04-29 |  |  |  | No | 2017-02-14 | 2015-11-04 |  |  |  |  | 2026-01-30 | 2028-08-14
18INR0030 | Canyon Wind | SS Completed, FIS Completed, IA | Canyon Wind Energy, LLC | 11319 SCOSW ScurryCounty 138kV | Scurry | WEST | 2025-10-31 | WIN | WT | 308.82 | COD | 2017-03-02 | 2016-05-09 | 2016-07-22 | 2017-03-02 | 2023-03-27 | No | 2018-09-20 | Yes | Not Required | Not Required | Not Required | 2020-02-07 | 2023-04-28 | 2023-05-01 |  |  | 2023-11-15 | 2023-12-01
18INR0031 | Maryneal Wind | SS Completed, FIS Completed, IA | Maryneal Windpower, LLC | 71050 Bitter Creek 345kV | Nolan | WEST | 2025-07-31 | WIN | WT | 182.4 |  | 2016-07-22 | 2016-05-26 | 2016-07-21 | 2016-07-22 | 2020-01-31 | No | 2020-01-31 | Yes | Not Required | Not Required | Not Required | 2020-01-31 | 2020-01-31 | 2020-01-31 |  |  | 2021-01-08 | 2021-04-23
18INR0064 | Silver Star repower | SS Completed, FIS Completed, IA | Silver Star I Power Partners, LLC | 1642 Flat Creek 138kV | Eastland | NORTH | 2025-11-12 | WIN | WT | -7.2 | COD | 2017-07-06 | 2017-04-05 | 2017-05-08 | 2017-07-06 | 2018-04-26 | No | 2018-10-16 | Yes | Not Required | Not Required | Not Required | 2019-10-23 | 2019-10-23 | 2019-10-28 |  |  |  | 2020-07-28
18INR0069 | Indian Mesa repower | SS Completed, FIS Completed, IA | Nextera | 76019 Indian NWP 138kV | Pecos | WEST | 2026-12-31 | WIN | WT | 9.3 |  | 2018-05-22 | 2018-05-22 | 2018-08-29 | 2018-05-22 | 2018-10-03 | No | 2018-12-04 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2018-11-02
18INR0073 | Sweetwater 1 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2024-11-30 | WIN | WT | 3 |  | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-12-27 | No | 2002-10-23 | No | Not Required | Not Required | Not Required
18INR0079 | Woodward I repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2026-12-31 | WIN | WT | 0 |  | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2019-01-09 | No | 2018-12-12 | Yes | Not Required | Not Required | Not Required | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2019-11-07 | 2019-11-13
18INR0080 | Woodward 2 repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2026-12-31 | WIN | WT | 0 |  | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-11-27 | No | 2018-12-18 | Yes | Not Required | Not Required | Not Required | 2018-11-29 | 2018-11-29 | 2020-10-30 |  |  |  | 2018-12-19
19INR0002 | Grandfalls Solar | SS Completed, FIS Started, No IA | Nextera | 842 King Mountain Station 345kV | Upton | WEST | 2027-07-01 | SOL | PV | 178 |  | 2016-05-24 | 2016-05-24 | 2016-06-06 | 2016-05-24 |  |  |  | No | Not Required | Not Required | Not Required
19INR0022 | Monte Alto I | SS Completed, FIS Started, IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2028-06-01 | WIN | WT | 141.5 |  |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  | No | 2020-02-13 | Yes | Not Required | Not Required | Not Required | 2025-02-12
19INR0023 | Monte Alto 2 Wind | SS Completed, FIS Started, IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2027-06-01 | WIN | WT | 199.5 |  |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  | No | 2022-03-22 | Yes | Not Required | Not Required | Not Required | 2025-02-12
19INR0026 | Holstein 2 Solar | SS Completed, FIS Started, No IA | 229HD 8me LLC | 11406 Central Bluff 345kV | Nolan | WEST | 2028-04-03 | SOL | PV | 100.7 |  | 2017-02-13 | 2016-12-21 | 2017-02-02 | 2017-02-13 |  |  |  | No | Not Required | Not Required | Not Required
19INR0035 | Norton Solar | SS Completed, FIS Completed, IA | TAI Norton Solar, LLC | 60451 Garnet 138kV | Runnels | WEST | 2025-11-24 | SOL | PV | 128.48 |  | 2017-11-08 | 2017-03-06 | 2017-04-20 | 2017-11-08 | 2024-10-29 | No | 2019-06-20 | Yes | Not Required | Not Required | Not Required | 2019-07-12 | 2023-05-30 | 2025-01-16 |  |  | 2025-07-24 | 2025-08-06
19INR0041 | Myrtle Solar | SS Completed, FIS Completed, IA | Myrtle Solar, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2025-10-31 | SOL | PV | 321.2 | COD |  | 2017-03-15 | 2017-04-28 | 2017-05-09 | 2022-01-25 |  | 2019-11-13 | Yes | Not Required | Not Required | Not Required | 2019-11-30 | 2020-05-06 | 2022-02-01 |  |  | 2022-12-07 | 2022-12-20
19INR0042 | Long Point Solar | SS Completed, FIS Completed, IA | Long Point Solar, LLC | 138 KV (CEHE Sub) Tap Burke (42410) - Eagle Nest (42430) ckt 02 | Brazoria | COASTAL | 2026-04-07 | SOL | PV | 120.7 | COD | 2017-11-02 | 2017-03-15 | 2017-04-20 | 2017-11-13 | 2025-03-14 | No | 2019-10-24 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2025-04-18 | 2025-04-28 | 2024-10-15 | 2025-10-30
19INR0054 | Monte Cristo 1 Wind | SS Completed, FIS Completed, IA | Terra-Gen | Tap 345kV #8574 Pomelo - #8383 North Edinburg Ckt 2 | Hidalgo | SOUTH | 2025-09-29 | WIN | WT | 234.5 |  | 2017-07-28 | 2017-04-11 | 2017-05-03 | 2017-07-28 | 2024-10-25 | No | 2023-05-09 | Yes | Not Required | Not Required | Not Required | 2024-10-25 | 2024-11-04 | 2024-11-04 |  |  | 2025-05-29 | 2025-07-24
19INR0055 | Monte Cristo II Wind | SS Completed, FIS Started, No IA | Monte Cristo Windpower II, LLC | tap 345kV #8574 Pomelo - #8383 North Edinburg ckt 2 | Hidalgo | SOUTH | 2028-04-15 | WIN | WT | 233.9 |  | 2017-07-28 | 2017-04-11 | 2017-05-03 | 2017-07-28 |  |  |  | No | Not Required | Not Required | Not Required
19INR0075 | Horseshoe Bend Solar | SS Completed, FIS Started, No IA | Clenera | 1444 Brown 345kV | Brown | NORTH | 2026-09-19 | SOL | PV | 301.1 |  | 2018-02-09 | 2017-06-23 | 2017-08-07 | 2018-02-09 |  | No |  | No | Not Required | Not Required | Not Required
19INR0080 | Whitehorse Wind | SS Completed, FIS Completed, IA | MESQUITE STAR SPECIAL LLC | 68001 Clayton 345kV | Fisher | WEST | 2024-10-31 | WIN | WT | 418.9 |  |  | 2017-06-23 | 2017-08-07 | 2018-02-16 | 2019-01-22 | No | 2018-12-05 | Yes | Not Required | Not Required | Not Required | 2019-03-12 | 2019-04-02 | 2019-05-01 |  |  | 2019-12-12 | 2019-12-27
19INR0085 | Blue Jay Solar | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2025-09-30 | SOL | PV | 141.05 |  | 2018-02-15 | 2017-05-30 | 2017-08-11 | 2018-02-15 | 2021-04-26 | No | 2020-10-26 | Yes | Not Required | Not Required | Not Required | 2020-12-02 | 2021-04-26 | 2021-04-29 |  |  | 2021-11-11 | 2022-06-28
19INR0100 | Prairie Hill Wind | SS Completed, FIS Completed, IA | Prairie Hill LLC | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | McLennan | NORTH | 2025-12-31 | WIN | WT | 300 |  | 2017-06-19 | 2017-06-19 | 2017-08-11 | 2017-06-19 | 2020-04-03 | No | 2018-09-17 | Yes | Not Required | Not Required | Not Required | 2018-11-27 | 2020-04-21 | 2020-04-21 |  |  | 2020-10-19 | 2020-11-12
19INR0103 | Rodeo Solar | SS Completed, FIS Started, IA | Core Solar SPV I, LLC | 138kV 11273 NELSON SWITCH | Andrews | WEST | 2026-11-30 | SOL | PV | 200 |  | 2018-02-19 | 2017-06-29 | 2017-08-04 | 2018-02-19 |  |  | 2019-08-20 | Yes | Not Required | Not Required | Not Required | 2021-03-10 | 2022-11-01
19INR0110 | Azalea Springs Solar | SS Completed, FIS Completed, IA | AZALEA SPRINGS SOLAR PARK LLC | tap 138kV Jim English – Lufkin Chipper Mill | Angelina | NORTH | 2025-10-31 | SOL | PV | 181 | COD | 2018-03-15 | 2017-07-26 | 2017-09-15 | 2018-03-15 | 2024-04-30 | No | 2023-09-14 | Yes | Not Required | Not Required | Not Required | 2024-05-01 | 2024-05-01 | 2024-05-01 |  |  | 2025-01-29 | 2025-02-11
19INR0120 | Sherbino II Wind repower | SS Completed, FIS Completed, IA | Sherbino II Wind Farm LLC | 38430 TN White Baker 138kV | Pecos | WEST | 2025-10-31 | WIN | WT | -18 | COD | 2017-09-21 | 2017-08-18 | 2017-09-28 | 2017-09-21 | 2018-12-04 | No | 2008-02-28 | Yes | Not Required | Not Required | Not Required | 2019-10-28 | 2019-10-28 | 2019-10-28 |  |  |  | 2020-06-09
19INR0134 | Cottonwood Bayou Solar | SS Completed, FIS Completed, IA | Cottonwood Bayou Solar, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2025-12-03 | SOL | PV | 351.4 |  |  | 2017-09-22 | 2017-11-17 | 2018-02-15 | 2023-04-27 | No | 2019-11-13 | Yes | Not Required | Not Required | Not Required | 2023-04-27 | 2023-04-27 | 2023-04-27 |  |  | 2024-05-01 | 2024-05-29
19INR0155 | Morrow Lake Solar | SS Completed, FIS Completed, IA | Morrow Lake Solar, LLC | Morrow Lake Switch 138kV (5896) | Frio | SOUTH | 2025-08-22 | SOL | PV | 201.1 |  | 2018-02-15 | 2017-12-05 | 2018-01-15 | 2018-02-15 | 2023-11-01 | No | 2019-08-29 | Yes | Not Required | Not Required | Not Required | 2019-11-18 | 2023-11-01 | 2023-11-01 |  |  | 2024-06-18 | 2024-07-16
19INR0174 | Elbow Creek repower | SS Completed, FIS Completed, IA | NRG | 1058 Longshore 345kV | Howard | WEST | 2025-09-01 | WIN | WT | 0 |  | 2018-07-19 | 2018-05-04 | 2018-05-18 | 2018-07-19 | 2018-09-17 | No | 2007-11-30 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-27
19INR0189 | SP TX-12B Phase III | SS Completed, FIS Started, No IA | ConEd Development | 76040 Castillo 138kV | Upton | WEST | 2025-12-02 | SOL | PV | 40 |  | 2019-01-29 | 2018-09-12 | 2018-10-03 |  |  | No |  | No | Not Required | Not Required | Not Required
20INR0012 | Lueders Solar | SS Completed, FIS Started, No IA | Innovative Solar 75 | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | WEST | 2027-12-31 | SOL | PV | 40 |  |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  | No |  | No | Not Required | Not Required | Not Required
20INR0019 | Trinity Hills Wind repower | SS Completed, FIS Completed, IA | Trinity Hills Wind Farm LLC | 17002 Garvey Rd 345kV | Young | WEST | 2025-10-24 | WIN | WT | -27 | COD | 2017-09-21 | 2017-07-20 | 2017-09-08 | 2017-09-21 | 2018-08-02 | No | 2018-10-17 | No | Not Required | Not Required | Not Required | 2019-10-29 | 2019-10-29 | 2019-10-29 |  |  |  | 2020-05-22
20INR0029 | Lutum Wind | SS Completed, FIS Started, No IA | RWE | tap 345kV 6101 Riley - 1730 W Krum | Clay | WEST | 2027-07-01 | WIN | WT | 241.5 |  |  | 2017-09-12 | 2017-11-07 | 2018-05-08 |  | No |  | No | Not Required | Not Required | Not Required
20INR0033 | WILDWIND | SS Completed, FIS Completed, IA | Wildcat Creek | tap 345kV 1730 KrumW - 2373 Anna | Cooke | NORTH | 2025-11-15 | WIN | WT | 180.08 |  | 2018-06-14 | 2017-10-18 | 2017-12-11 | 2018-06-14 | 2019-11-25 | No | 2020-02-21 | Yes | Not Required | Not Required | Not Required | 2020-03-23 | 2020-04-30 | 2020-04-30 |  |  | 2020-12-22 | 2021-02-10
20INR0047 | Siete | SS Completed, FIS Started, IA | Apex Clean Energy | 345kV 8718 Triada | Webb | SOUTH | 2026-10-31 | WIN | WT | 492.8 |  | 2019-06-13 | 2018-10-23 | 2018-12-11 | 2019-06-12 |  | No | 2022-06-30 | Yes | Not Required | Not Required | Not Required | 2022-07-19
20INR0050 | Castro Solar | SS Completed, FIS Started, IA | Castro Solar One, LLC | 23912 Ogallala 345kV | Castro | PANHANDLE | 2028-04-20 | SOL | PV | 222.95 |  | 2018-05-15 | 2018-02-08 | 2018-04-09 | 2018-05-15 |  | No | 2020-11-30 | No | Not Required | Not Required | Not Required
20INR0069 | Danish Fields Solar | SS Completed, FIS Completed, IA | Danish Fields Solar, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2025-10-31 | SOL | PV | 602.8 | COD | 2023-03-20 | 2018-04-12 | 2018-06-05 | 2018-08-21 | 2022-07-25 | No | 2020-02-24 | Yes | Not Required | Not Required | Not Required | 2022-07-28 | 2022-07-28 | 2022-07-28 |  |  | 2023-03-27 | 2023-05-04
20INR0083 | Baird North Wind | SS Completed, FIS Completed, IA | BMP Wind, LLC | 68008 Latimer 345kV | Callahan | WEST | 2025-12-31 | WIN | WT | 350 |  |  | 2018-05-04 | 2018-06-12 | 2018-08-20 | 2020-10-30 | No | 2019-05-31 | Yes | Not Required | Not Required | Not Required | 2019-07-19 | 2020-10-30 | 2020-11-01 |  |  | 2021-08-09 | 2021-08-20
20INR0086 | Arroyo Solar | SS Completed, FIS Started, IA | BT Cantwell Solar, LLC | 345 KV Tap #8318 Rio Hondo - #8317 La Palma | Cameron | COASTAL | 2028-02-22 | SOL | PV | 100 |  | 2018-10-10 | 2018-05-09 | 2018-07-09 | 2018-10-10 |  | No | 2021-09-28 | Yes | Not Required | Not Required | Not Required | 2025-08-05
20INR0091 | Fagus Solar Park 1 SLF | SS Completed, FIS Completed, IA | Excel Advantage Services, LLC dba Misae Solar Park II | 60501 Tesla 345kV | Childress | PANHANDLE | 2026-01-14 | SOL | PV | 166.42 |  | 2018-05-15 | 2018-05-15 | 2018-07-06 | 2018-05-15 | 2024-02-27 | No | 2019-02-21 | Yes | Not Required | Not Required | Not Required | 2021-01-15 | 2024-04-30 | 2024-04-30 |  |  | 2025-05-29 | 2025-08-04
20INR0097 | El Sauz Ranch | SS Completed, FIS Completed, IA | El Sauz Ranch Wind, LLC | 8663 EL SAUZ POI 345kV | Willacy | COASTAL | 2025-12-01 | WIN | WT | 301.5 |  | 2019-02-01 | 2018-06-19 | 2018-08-22 | 2019-01-31 | 2021-10-29 |  | 2021-01-27 | Yes | Not Required | Not Required | Not Required | 2021-10-14 | 2022-01-26 | 2022-01-26 |  |  | 2022-09-28 | 2023-02-28
20INR0106 | Wang Solar SLF | SS Completed, FIS Started, No IA | BT Yixin Solar, LLC | tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2026-03-31 | SOL | PV | 144.6 |  | 2018-08-29 | 2018-06-14 | 2018-08-13 | 2018-08-29 |  | No |  | No | Not Required | Not Required | Not Required
20INR0127 | Walleye Solar | SS Completed, FIS Started, No IA | Sandow Lakes Ranch Solar II, LLC | 138kV Walleye Creek Switch 3712 | Milam | SOUTH | 2027-10-01 | SOL | PV | 215.2 |  | 2019-08-13 | 2018-07-03 | 2018-09-18 |  |  |  |  | No | Not Required | Not Required | Not Required
20INR0129 | Foxtrot Wind | SS Completed, FIS Completed, IA | Lincoln Clean | AEP 88689 Tango 345kV station | Bee | SOUTH | 2025-10-31 | WIN | WT | 268.2 | COD |  | 2018-07-26 | 2018-09-14 | 2018-07-26 | 2021-07-30 | No | 2020-05-05 | Yes | Not Required | Not Required | Not Required | 2021-07-30 | 2021-07-30 | 2021-07-30 |  |  | 2022-02-23 | 2022-03-09
20INR0143 | Tri-X Solar 1 SLF | SS Completed, FIS Started, IA | Crane I Solar Electric, LLC | 138 kV Soda Lake (#76026) | Crane | WEST | 2027-12-01 | SOL | PV | 201.5 |  | 2020-09-08 | 2016-11-07 | 2016-11-08 | 2017-02-10 |  | No | 2022-02-28 | No | Not Required | Not Required | Not Required
20INR0155 | Peyton Creek Wind II | SS Completed, FIS Completed, IA | RWE Renewables Development, LLC | 42400 Refuge 345kV | Matagorda | COASTAL | 2025-10-01 | WIN | WT | 241.2 |  | 2019-01-30 | 2018-08-21 | 2018-11-02 | 2019-03-14 | 2024-06-25 | No | 2023-02-27 | Yes | Not Required | Not Required | Not Required | 2024-06-25 | 2024-07-24 | 2024-07-24 |  |  | 2024-12-30 | 2025-02-05
20INR0162 | Diamondback solar | SS Completed, FIS Started, IA | Diamondback Solar, LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2027-12-31 | SOL | PV | 203.8 |  |  | 2018-09-13 | 2018-12-06 | 2018-11-07 |  | No | 2024-06-14 | Yes | Not Required | Not Required | Not Required | 2025-02-12
20INR0203 | Pine Forest Solar | SS Completed, FIS Completed, IA | Pine Forest Solar I, LLC | Monticello Switch – Allen Switch 345 kV Line | Hopkins | NORTH | 2025-12-01 | SOL | PV | 301.51 |  | 2019-03-26 | 2018-10-04 | 2018-11-20 |  | 2024-12-18 | No | 2020-07-29 | Yes | Not Required | Not Required | Not Required | 2024-05-22 | 2025-01-28 | 2025-01-28 |  |  | 2025-06-03 | 2025-07-03
20INR0205 | Roseland Solar | SS Completed, FIS Completed, IA | Enel Green Power Roseland Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2025-11-29 | SOL | PV | 254 | COD | 2018-11-05 | 2018-11-30 | 2019-02-04 | 2019-02-04 | 2021-10-25 | No | 2020-12-10 | Yes | Not Required | Not Required | Not Required | 2021-08-18 | 2021-11-01 | 2021-10-25 |  |  | 2022-06-07 | 2022-09-26
20INR0213 | Brushy Creek Solar SLF | SS Completed, FIS Started, No IA | Brushy Creek Solar LLC | 6444 Red Creek 345kV | Tom Green | WEST | 2028-06-01 | SOL | PV | 177.09 |  | 2019-03-26 | 2019-01-07 | 2019-03-26 | 2019-03-05 |  | No |  | No | Not Required | Not Required | Not Required
20INR0216 | Starr Solar Ranch | SS Completed, FIS Completed, IA | Starr Solar Ranch 1 LLC | 8795 Roma 138kV | Starr | SOUTH | 2025-08-14 | SOL | PV | 136.73 |  | 2018-11-07 | 2018-11-07 | 2018-12-14 | 2018-11-07 | 2024-01-26 | No | 2020-10-01 | Yes | Not Required | Not Required | Not Required | 2024-01-24 | 2024-01-24 | 2024-01-31 |  |  | 2024-10-09 | 2024-10-30
20INR0217 | CAROL wind | SS Completed, FIS Completed, IA | Carol Renewable Energy, LLC | 23906 AJ Swope 345kV | Potter | PANHANDLE | 2026-04-15 | WIN | WT | 165.42 |  | 2019-06-10 | 2018-12-06 | 2019-01-18 | 2019-06-05 | 2023-10-30 | No | 2020-09-11 | Yes | Not Required | Not Required | Not Required | 2024-01-31 | 2024-01-31 | 2024-01-31
20INR0222 | Tyson Nick Solar | SS Completed, FIS Completed, IA | Tyson Nick Solar Project, LLC | 1700 Toco 138kV | Lamar | NORTH | 2025-10-03 | SOL | PV | 90.5 | COD | 2019-02-25 | 2018-12-12 | 2019-02-15 | 2019-01-14 | 2024-07-29 | No | 2020-08-28 | Yes | Not Required | Not Required | Not Required | 2024-04-19 | 2024-10-18 | 2024-10-18 |  |  | 2025-05-29 | 2025-06-20
20INR0233 | Impala Flats Wind | SS Completed, FIS Started, No IA | Antelope Flats Wind, LLC | 79641 Farmland 345kV | Lynn | WEST | 2026-06-03 | WIN | WT | 282 |  | 2019-01-15 | 2019-01-11 | 2019-04-03 | 2018-12-21 |  |  |  | No |  |  | Not Required
20INR0236 | New Hickory Solar | SS Completed, FIS Completed, IA | New Hickory Solar LLC | OLD_HCKRY_5 bus 5323 345 kV | Jackson | SOUTH | 2026-07-15 | SOL | PV | 209.15 |  | 2019-08-27 | 2019-01-25 | 2019-04-19 | 2019-08-12 | 2024-06-30 |  | 2020-06-30 | Yes | Not Required | Not Required | Not Required | 2021-04-12 | 2025-07-31 | 2025-07-31
20INR0238 | Voyager Storage | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2028-04-08 | OTH | BA | 50.14 |  | 2019-04-30 | 2019-01-14 | 2019-03-19 | 2019-04-26 |  |  |  | No | Not Required | Not Required
20INR0241 | Crowded Star Solar | SS Completed, FIS Completed, IA | Jones City Solar, LLC | tap 345kV 68001 Claytonville – 68004 Phantom Hill c2 (New Substation: Open Sky 68014) | Jones | WEST | 2026-06-20 | SOL | PV | 218.79 |  | 2019-05-23 | 2019-01-21 | 2019-04-19 | 2019-05-22 | 2024-11-05 | Yes | 2023-07-27 | Yes | Not Required | Not Required | Not Required | 2021-12-01 | 2025-07-24 | 2025-07-24
20INR0242 | Anson Solar 2 | SS Completed, FIS Completed, IA | Anson Solar Center 2, LLC | existing tap 345 kV 68004 Phantom Hill station | Jones | WEST | 2026-03-01 | SOL | PV | 200.9 |  | 2018-02-15 | 2017-06-23 | 2017-08-07 | 2018-02-15 | 2025-03-19 |  | 2024-08-15 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2025-05-22 | 2025-05-01
20INR0245 | Volunteer Storage | SS Completed, FIS Started, No IA | Blackjack Storage LLC | 7216 Lockhart 138kV | Caldwell | SOUTH | 2028-02-29 | OTH | BA | 50.6 |  | 2019-01-16 | 2019-01-15 | 2019-07-02 | 2019-03-15 |  |  |  | No | Not Required | Not Required
20INR0246 | Ryan Energy Storage | SS Completed, FIS Completed, IA | Ryan Storage LLC | 37580 TNPancake 69kV | Coryell | NORTH | 2026-12-12 | OTH | BA | 51.6 |  | 2019-02-08 | 2019-01-15 | 2019-04-05 | 2019-03-15 | 2025-09-16 | No | 2021-02-18 | Yes | Not Required | Not Required |  | 2022-08-03
20INR0247 | Water Valley Wind Energy | SS Completed, FIS Started, IA | Water Valley Wind Energy, LLC | 345 kV 76009 Twin Buttes to 76090 Divide Double Circuit | Tom Green | WEST | 2027-12-15 | WIN | WT | 180 |  | 2019-01-10 | 2019-01-15 | 2019-03-29 | 2019-01-10 |  |  | 2025-03-17 | Yes |  |  | Not Required
20INR0248 | DAMAZO (Second Division) SOLAR | SS Completed, FIS Completed, IA | TX Gulf Solar 1 LLC | Tap 138 kV SANBER_POI_8 (Bus# 43110) to WEST COLUMBIA (Bus# 43380) Ckt 60 Line | Brazoria | COASTAL | 2025-08-15 | SOL | PV | 100.2 |  | 2019-08-06 | 2019-03-28 | 2019-06-18 | 2019-07-29 | 2022-10-28 | No | 2020-10-14 | Yes | Not Required | Not Required | Not Required | 2023-10-31 | 2023-10-31 | 2023-10-31 |  |  | 2024-10-08 | 2024-10-17
20INR0255 | Renegade Project | SS Completed, FIS Started, IA | Renegade Renewable LLC | Tap 345kV 23910 Windmill - 23906 AJ Swope | Deaf Smith | PANHANDLE | 2027-04-17 | SOL | PV | 515.66 |  | 2019-04-01 | 2019-02-26 | 2019-05-17 | 2019-02-07 |  |  | 2021-01-04 | Yes | Not Required | Not Required | Not Required | 2024-04-30
20INR0266 | Tres Bahias Solar | SS Completed, FIS Completed, IA | Tres Bahias Solar Power LLC | 8140 Joslin 138kV | Calhoun | COASTAL | 2025-10-31 | SOL | PV | 195 | COD | 2019-06-03 | 2019-03-26 | 2019-06-11 | 2019-06-03 | 2022-01-21 |  | 2020-08-07 | Yes | Not Required | Not Required | Not Required | 2020-10-07 | 2022-12-20 | 2023-01-30 |  |  | 2023-06-26 | 2023-09-12
20INR0269 | Texas Solar Nova 2 | SS Completed, FIS Completed, IA | TEXAS SOLAR NOVA 2, LLC | 138kV 59909 WETT Nova Prime | Kent | WEST | 2025-06-30 | SOL | PV | 201.14 |  | 2016-07-06 | 2019-06-24 | 2015-12-30 | 2019-06-19 | 2022-05-19 |  | 2021-07-16 | Yes |  |  | Not Required | 2022-07-29 | 2022-07-29 | 2022-08-03 |  |  | 2023-08-22 | 2023-11-13
20INR0286 | Wise County Power Repower (CT1, CT2) | SS Completed, FIS Completed, IA | Wise County Power Company LLC | 1421 Willow Creek 345kV | Wise | NORTH | 2026-05-01 | GAS | CC | 21 | COD | 2019-07-15 | 2019-07-25 | 2019-10-23 | 2019-07-16 | 2019-10-23 | No | 2001-03-19 | Yes | 2020-01-21 | Not Required | 2019-12-05 | 2020-01-22 | 2020-01-27 | 2020-01-27
21INR0006 | Giddings Wind | SS Completed, FIS Started, No IA | Pioneer Natural Resources | 71212 Upton 138kV | Upton | WEST | 2027-09-09 | WIN | WT | 240 |  | 2019-04-02 | 2017-09-06 | 2019-08-19 | 2020-01-15 |  |  |  | No | Not Required | Not Required | Not Required
21INR0012 | Air Products GCA | SS Completed, FIS Completed, IA | Air Products | 39140 TNTxCityMain 69kV (Will be upgraded to 138kV) | Galveston | HOUSTON | 2025-09-30 | GAS | ST | 14 |  | 2019-03-26 | 2018-06-07 | 2018-08-01 |  | 2023-03-10 |  | 2020-08-07 | Yes | Not Required | Not Required | 2020-03-31 | 2023-03-13 | 2023-03-13 | 2023-03-13 |  |  | 2023-11-07 | 2024-07-10
21INR0022 | Red Holly Solar | SS Completed, FIS Started, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2027-06-01 | SOL | PV | 260 |  |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  | No | 2020-10-19 | No | Not Required | Not Required | Not Required
21INR0029 | Red Holly Storage 1 | SS Completed, FIS Started, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2028-05-30 | OTH | BA | 50 |  |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | 2020-10-19 | No | Not Required | Not Required
21INR0031 | Indigo Solar | SS Completed, FIS Started, IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2026-08-17 | SOL | PV | 150 |  | 2019-05-16 | 2018-09-27 | 2018-11-20 | 2019-05-15 |  | No | 2020-09-15 | Yes | Not Required | Not Required | Not Required | 2025-02-12
21INR0033 | Red Holly Storage | SS Completed, FIS Started, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2028-05-30 | OTH | BA | 50 |  |  | 2018-09-27 | 2018-12-18 | 2018-12-11 |  | No | 2020-10-19 | No | Not Required | Not Required
21INR0203 | Eastbell Milam Solar | SS Completed, FIS Completed, IA | EDP RENEWABLES NORTH AMERICA LLC | 345 kV Bell County East Switch (bus# 3687) - TNP One (bus# 39950) circuit 2 | Milam | SOUTH | 2025-10-31 | SOL | PV | 244.86 | COD | 2019-04-23 | 2018-10-10 | 2018-12-09 | 2019-04-23 | 2022-10-28 | No | 2022-09-02 | Yes | Not Required | Not Required | Not Required | 2022-11-03 | 2022-11-03 | 2022-11-12 |  |  | 2023-10-13 | 2023-11-01
21INR0207 | Quantum Solar | SS Completed, FIS Completed, IA | IP QUANTUM II, LLC | 60089 Kilby Station 345kV | Haskell | WEST | 2026-03-31 | SOL | PV | 321.66 |  | 2018-11-07 | 2018-09-27 | 2018-11-14 | 2018-11-07 | 2025-06-16 | No | 2023-10-26 | Yes | Not Required | Not Required | Not Required | 2025-08-04 | 2025-08-04 | 2025-08-04
21INR0210 | Adamstown Solar | SS Completed, FIS Started, IA | Adams Creek Solar Project, LLC | tap 345kV 1730 West Krum - 6111 Riley Ckt 2 | Wichita | WEST | 2027-08-31 | SOL | PV | 250.88 |  | 2019-05-22 | 2018-11-20 | 2019-02-04 | 2019-05-16 |  | No | 2022-08-08 | No |  |  | Not Required
21INR0220 | Maleza Solar | SS Completed, FIS Not Started, IA | Brush Solar LLC | tap Blue – Hillje 345 kv Ckt.#27 | Wharton | SOUTH | 2026-11-09 | SOL | PV | 254.94 | COD | 2019-03-07 | 2018-12-06 | 2019-01-18 |  |  | No | 2021-01-27 | Yes |  |  | Not Required | 2022-12-08
21INR0221 | Samson Solar 1 | SS Completed, FIS Completed, IA | Samson Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2026-06-30 | SOL | PV | 250 |  | 2019-05-13 | 2018-11-20 | 2019-01-04 | 2019-05-03 | 2020-06-09 | No | 2020-08-26 | Yes | Not Required | Not Required | Not Required | 2020-08-26 | 2020-10-15 | 2020-10-26 |  |  | 2021-06-30 | 2021-08-31
21INR0223 | Tulsita Solar | SS Completed, FIS Completed, IA | Ray Ranch Solar LLC | Tap 138kV 8590 Tuleta - 8595 Euler | Goliad | SOUTH | 2025-09-30 | SOL | PV | 256.2 |  | 2019-05-20 | 2018-12-05 | 2019-02-21 | 2019-05-17 | 2024-03-01 | No | 2022-09-19 | Yes | Not Required | Not Required | Not Required | 2022-10-03 | 2024-02-02 | 2024-04-30 |  |  | 2024-10-22 | 2024-10-30
21INR0240 | La Casa Wind | SS Completed, FIS Completed, IA | LA CASA WIND, LLC | New switching station: 138kV Graham Plant Switch - Breckenridge - Leon Switch | Stephens | NORTH | 2026-03-16 | WIN | WT | 148.4 | COD |  | 2018-12-28 | 2019-03-12 | 2018-12-29 | 2023-09-22 |  | 2023-09-07 | Yes | Not Required | Not Required | Not Required | 2024-01-04 | 2024-04-29 | 2024-04-29
21INR0247 | Anson Solar Center, Phase III | SS Completed, FIS Started, No IA | Anson Solar Center 3, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2027-06-01 | SOL | PV | 200 |  | 2018-02-15 | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  |  | No |  |  | Not Required
21INR0253 | Ulysses Solar | SS Completed, FIS Started, IA | BNB Tennyson Solar LLC | 60072 Odysseus Substation 345 kV | Coke | WEST | 2026-10-12 | SOL | PV | 151.2 |  | 2019-05-14 | 2019-01-25 | 2019-04-05 | 2019-05-10 |  |  | 2022-10-03 | Yes | Not Required | Not Required | Not Required | 2022-12-05
21INR0258 | Mercury Storage SLF | SS Completed, FIS Started, No IA | Mercury Storage, LLC | 68092 Liberty Station 345kV | Hill | NORTH | 2026-07-01 | OTH | BA | 0 |  | 2019-02-07 | 2019-02-14 | 2019-05-03 | 2019-02-07 |  |  |  | No | Not Required | Not Required
21INR0260 | Chariot Storage | SS Completed, FIS Started, No IA | Chariot Storage LLC | tap 69kV 99 Ben Hur - 107 Prairie Hill | Limestone | NORTH | 2028-02-29 | OTH | BA | 50 |  | 2019-02-19 | 2019-03-06 | 2019-05-24 | 2019-02-11 |  | No |  | No | Not Required | Not Required
21INR0262 | Grandfalls Storage SLF | SS Completed, FIS Started, No IA | King Mountain Storage LLC | tap 345kV 11028 Odessa - 76000 North McCamey | Upton | WEST | 2027-07-01 | OTH | BA | 0 |  | 2019-02-14 | 2019-03-25 | 2019-06-17 | 2019-02-14 |  |  |  | No |  |  | 2023-05-22
21INR0263 | Monarch Creek Wind | SS Completed, FIS Started, IA | MONARCH CREEK WIND, LLC | tap 345kV 11418 Tecumseh Creek Switch to 60515 Clear Crossing Switch | Throckmorton | WEST | 2027-09-17 | WIN | WT | 284.3 |  | 2019-10-28 | 2019-04-25 | 2019-07-19 | 2019-08-05 |  | No | 2020-08-24 | No | Not Required | Not Required | Not Required
21INR0265 | Sisters Solar | SS Completed, FIS Completed, IA | Oberon Solar LLC | tapping the 345 kV line connecting Moss Switch (Bus# 1018) to Wolf Switching Station (Bus# 11010) | Ector | WEST | 2027-05-31 | SOL | PV | 301.6 |  | 2019-02-28 | 2019-02-28 | 2019-03-29 | 2019-02-20 | 2025-06-20 | Yes | 2025-07-01 | Yes | Not Required | Not Required | Not Required | 2025-09-18
21INR0268 | Greyhound Solar | SS Completed, FIS Completed, IA | Rockhound Solar 2, LLC dba "Greyhound Solar" | Tap 345kV 11010 Wolf - 1018 Moss | Ector | WEST | 2026-03-31 | SOL | PV | 335.45 |  | 2019-03-14 | 2019-03-28 | 2019-06-05 | 2019-03-21 | 2024-10-31 | No | 2022-01-15 | Yes | Not Required | Not Required | Not Required | 2024-11-04 | 2024-11-04 | 2024-11-04
21INR0278 | Fighting Jays Solar | SS Completed, FIS Completed, IA | AP Solar Holdings, LLC | tap 345kV 44000 WA Parish - 44200 Hillje c64 | Fort Bend | HOUSTON | 2025-10-17 | SOL | PV | 351.29 | COD | 2019-04-30 | 2019-03-26 | 2019-06-17 | 2019-03-20 | 2021-06-30 | No | 2020-06-22 | Yes | Not Required | Not Required | Not Required | 2021-07-29 | 2021-07-29 | 2021-07-29 |  |  | 2022-03-18 | 2022-03-31
21INR0280 | Edgewater Storage | SS Completed, FIS Started, No IA | Edgewater Battery Storage LLC | 210 Reagor Springs 69kV | Ellis | NORTH | 2028-02-29 | OTH | BA | 50 |  | 2019-04-02 | 2019-04-08 | 2019-07-04 | 2019-03-24 |  | No |  | No | Not Required | Not Required
21INR0294 | Mountaineer Solar | SS Completed, FIS Started, No IA | Mustang Mountaineer Solar LLC | 1444 Brown 345 kV | Brown | NORTH | 2028-05-01 | SOL | PV | 332.1 |  | 2019-12-11 | 2019-04-16 | 2019-06-11 | 2019-12-08 |  | No |  | No | Not Required | Not Required | Not Required
21INR0320 | Ion Solar | SS Completed, FIS Completed, No IA | GSE Group LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2026-05-29 | SOL | PV | 384 |  | 2020-02-03 | 2019-05-17 | 2019-08-01 | 2020-01-28 | 2024-05-24 |  |  | No |  |  | Not Required
21INR0324 | Board Creek Wind | SS Completed, FIS Completed, IA | Limestone Wind Project, LLC | 345kV 3386 Outlaw Switch | Navarro | NORTH | 2025-10-31 | WIN | WT | 299.2 |  | 2019-11-08 | 2019-04-24 | 2019-07-22 | 2019-11-05 | 2022-04-26 | No | 2021-08-19 | Yes | Not Required | Not Required | Not Required | 2022-04-05 | 2022-04-21 | 2022-04-26 |  |  | 2022-09-19 | 2022-10-06
21INR0326 | Dove Run Solar | SS Completed, FIS Started, IA | Dove Run Solar Project, LLC | tap 138kV 8510 Falfurrias - 8695 Crestonio | Duval | SOUTH | 2027-10-15 | SOL | PV | 120.86 |  | 2019-05-07 | 2019-05-07 | 2019-07-23 | 2019-05-02 |  |  | 2023-10-31 | Yes | Not Required | Not Required | Not Required | 2025-02-12
21INR0334 | Nightfall Solar | SS Completed, FIS Started, IA | BDPU SOLAR NIGHTFALL, LLC | 138 kV Tap 8707 Dryfrio - 8234 Uvalde (new 138 kV Meil station) | Uvalde | SOUTH | 2026-06-30 | SOL | PV | 180.87 |  | 2020-09-24 | 2019-05-10 | 2019-07-31 | 2020-01-24 |  |  | 2023-10-26 | Yes | Not Required | Not Required | Not Required | 2025-05-14
21INR0341 | Space City Solar | SS Completed, FIS Started, IA | Apollo Solar Ranch, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2027-06-01 | SOL | PV | 366 |  | 2019-10-28 | 2019-11-01 | 2020-03-06 | 2019-10-15 |  |  | 2021-01-06 | Yes | Not Required | Not Required | Not Required | 2021-01-11
21INR0343 | Flag City Solar | SS Completed, FIS Started, No IA | Flag City Solar Project, LLC | tap 138kV 5588 Red Bluff - 5546 Danevang c1 | Jackson | SOUTH | 2027-12-31 | SOL | PV | 165.87 |  | 2019-05-07 | 2019-05-07 | 2019-07-29 | 2019-05-02 |  | No |  | No | Not Required | Not Required | Not Required
21INR0347 | Lunis Creek Storage SLF | SS Completed, FIS Started, No IA | Lunis Creek Solar Project, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2027-08-31 | OTH | BA | 0 |  | 2019-05-02 | 2019-05-02 | 2019-07-30 | 2019-05-02 |  |  |  | No
21INR0349 | Pearl Crescent Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | Rock Island (57640) 138kV | Colorado | SOUTH | 2026-12-08 | SOL | PV | 208.35 |  | 2019-06-04 | 2019-05-31 | 2019-08-26 | 2019-09-30 |  |  |  | No |  |  | Not Required
21INR0359 | Hickerson Solar | SS Completed, FIS Completed, IA | Hickerson Solar | tap 345kV 68091 Navarro - 68040 Kopperl | Bosque | NORTH | 2025-11-21 | SOL | PV | 311.1 |  | 2020-05-13 | 2019-05-29 | 2019-08-23 | 2020-02-19 | 2024-12-17 | Yes | 2023-12-18 | Yes |  |  | Not Required | 2025-01-30 | 2025-01-30 | 2025-01-30 |  |  | 2025-08-25 | 2025-08-28
21INR0362 | Oystercatcher Solar | SS Completed, FIS Started, IA | Oystercatcher Solar, LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2026-09-17 | SOL | PV | 222.2 |  | 2020-01-15 | 2019-05-30 | 2019-08-07 | 2019-12-20 |  | Yes | 2021-08-20 | No | Not Required | Not Required | Not Required
21INR0368 | Eliza Solar | SS Completed, FIS Completed, IA | Ables Springs Solar, LLC | tap 345kV 2478 Royse - 3103 Shamburger | Kaufman | NORTH | 2025-10-30 | SOL | PV | 151.7 | COD | 2020-05-04 | 2019-06-21 | 2019-08-30 | 2020-02-24 | 2023-10-30 | No | 2022-08-04 | Yes | Not Required | Not Required | Not Required | 2023-02-17 | 2023-09-18 | 2023-10-30 |  |  | 2024-08-13 | 2024-10-22
21INR0371 | Pecan Prairie South | SS Completed, FIS Started, No IA | ConnectGen Operating LLC | CTT Yellow Wolf, bus # 79007 | Leon | NORTH | 2027-05-01 | SOL | PV | 130.71 | COD | 2019-08-27 | 2019-08-16 | 2019-11-05 | 2019-08-22 |  |  |  | No |  |  | Not Required
21INR0380 | Charolais Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 44000 W A Parish - 5915 STP | Matagorda | COASTAL | 2026-12-15 | SOL | PV | 261.63 |  | 2020-05-11 | 2019-08-05 | 2019-10-31 | 2020-04-27 |  | Yes |  | No |  |  | Not Required
21INR0391 | Grandslam Solar | SS Completed, FIS Started, IA | Grandslam Solar, L.L.C. | 5700 Miracle Lake 138kV | Atascosa | SOUTH | 2026-11-28 | SOL | PV | 121.89 |  | 2019-09-03 | 2019-07-29 | 2019-10-30 | 2019-07-26 |  |  | 2021-01-29 | No | Not Required | Not Required | Not Required
21INR0406 | Buffalo Creek | SS Completed, FIS Completed, IA | Lincoln Clean Energy Development | tap 345kV 44000 WA Parish – 44040 BAILEY | Fort Bend | HOUSTON | 2025-11-01 | SOL | PV | 438.75 |  | 2019-08-06 | 2019-08-01 | 2019-10-30 | 2019-07-31 | 2021-04-23 | No | 2020-04-16 | Yes | Not Required | Not Required | Not Required | 2020-05-06 | 2021-04-15 | 2021-04-23 |  |  | 2021-12-08 | 2022-01-06
21INR0413 | Big Star Solar | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | Tap 345kV 9074 Lytton - 9073 Holman | Bastrop | SOUTH | 2025-08-08 | SOL | PV | 203.1 |  | 2020-01-02 | 2019-08-27 | 2019-11-08 | 2019-12-20 | 2021-07-19 |  | 2020-10-02 | Yes |  |  | Not Required | 2020-12-04 | 2021-07-19 | 2021-07-30 |  |  | 2022-12-06 | 2022-12-19
21INR0414 | Jayhawk Solar | SS Completed, FIS Started, No IA | Renewable Energy Ventures, LLC | tap 345kV 1030 Morgan - 76030 Gasconades | Mitchell | WEST | 2025-10-30 | SOL | PV | 101.5 |  | 2020-06-22 | 2019-08-05 | 2019-10-31 | 2020-01-17 |  |  |  | No |  |  | Not Required
21INR0421 | Armadillo Solar | SS Completed, FIS Started, IA | Armadillo Solar Center, LLC | 3387 Revolution 138kV | Navarro | NORTH | 2026-12-31 | SOL | PV | 200.03 |  | 2019-09-05 | 2019-08-28 | 2019-11-22 | 2019-08-28 |  | No | 2021-02-02 | Yes | Not Required | Not Required | Not Required | 2025-02-12
21INR0428 | Pecan Prairie North | SS Completed, FIS Started, IA | CG Leon County II LLC | CTT Yellow Wolf, bus # 79007 | Leon | NORTH | 2027-05-01 | SOL | PV | 321.27 |  | 2019-08-16 | 2019-09-23 | 2019-12-10 | 2019-09-11 |  | No | 2021-02-26 | Yes |  |  | Not Required | 2025-08-20
21INR0430 | Holstein 2 Energy Storage | SS Completed, FIS Started, No IA | 229HD 8me LLC | 11406 Central Bluff 345kV | Nolan | WEST | 2027-05-01 | OTH | BA | 102.42 |  | 2019-09-16 | 2019-08-26 | 2019-11-12 | 2019-08-16 |  |  |  | No
21INR0432 | Diversion Wind | SS Completed, FIS Started, No IA | Diversion Wind Development LLC | 6101 Riley 345kV | Baylor | WEST | 2026-12-31 | WIN | WT | 300 |  | 2020-07-15 | 2019-09-10 | 2019-12-04 | 2020-06-04 |  |  |  | No |  |  | Not Required
21INR0443 | Cottonwood Bayou Storage | SS Completed, FIS Completed, IA | Cottonwood Bayou Storage, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2025-11-19 | OTH | BA | 153.03 | COD | 2020-07-20 | 2019-10-31 | 2020-01-23 | 2020-07-17 | 2024-03-25 | No | 2022-03-18 | Yes | Not Required | Not Required |  | 2024-04-29 | 2024-04-29 | 2024-04-29 |  |  | 2025-05-19 | 2025-05-28
21INR0444 | Long Point Storage | SS Completed, FIS Started, IA | Long Point Storage, LLC | 138 KV (CEHE Sub) Tap Burke (42410) - Eagle Nest (42430) ckt 02 | Brazoria | COASTAL | 2026-12-30 | OTH | BA | 100.62 |  | 2020-09-17 | 2019-11-01 | 2020-02-05 | 2020-09-01 |  | No | 2023-08-28 | No | Not Required | Not Required
21INR0455 | Independence Trail Storage | SS Completed, FIS Started, No IA | KCE TX 16, LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2028-01-01 | OTH | BA | 100 |  | 2019-11-11 | 2019-12-03 | 2020-02-24 | 2019-10-22 |  |  |  | No | Not Required | Not Required
21INR0456 | Maleza Storage | SS Completed, FIS Started, No IA | Brush Storage, LLC | tap Blue – Hillje 345 kv Ckt.#27 | Wharton | SOUTH | 2026-11-09 | OTH | BA | 150.83 | COD | 2020-08-24 | 2019-10-31 | 2020-01-24 | 2020-08-18 |  |  |  | No
21INR0469 | Big Star Storage | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | Tap 345kV 9074 Lytton - 9073 Holman | Bastrop | SOUTH | 2025-08-08 | OTH | BA | 80 |  | 2020-10-23 | 2020-01-02 | 2020-03-26 | 2020-08-28 | 2021-07-19 |  | 2020-10-02 | Yes |  |  |  | 2021-08-18 | 2021-08-18 | 2021-07-30 |  |  | 2023-04-13 | 2023-11-06
21INR0470 | Pearl Crescent Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | Rock Island (57640) 138kV | Colorado | SOUTH | 2026-12-15 | OTH | BA | 50.26 |  | 2020-09-18 | 2019-12-20 | 2020-03-12 | 2020-04-10 |  |  |  | No
21INR0482 | Sisters Storage | SS Completed, FIS Completed, No IA | 174 Power Global Properties | tapping the 345 kV line connecting Moss Switch (Bus# 1018) to Wolf Switching Station (Bus# 11010) | Ector | WEST | 2027-05-31 | OTH | BA | 208.89 |  | 2020-03-30 | 2019-12-18 | 2020-03-11 | 2019-12-18 | 2025-06-20 |  |  | No
21INR0483 | Morrow Lake Storage | SS Completed, FIS Started, No IA | Morrow Lake Storage, LLC | Morrow Lake Switch 138kV (5896) | Frio | SOUTH | 2026-02-10 | OTH | BA | 201.13 |  | 2020-11-10 | 2020-02-07 | 2020-04-30 | 2020-10-26 |  |  |  | No
21INR0490 | Samson Solar 2 | SS Completed, FIS Completed, IA | Samson Solar Energy II LLC | 345 kV TTRSW 11688 | Lamar | NORTH | 2025-11-28 | SOL | PV | 203 |  | 2020-01-14 | 2020-01-13 | 2019-01-04 | 2020-01-13 | 2020-06-09 |  | 2020-08-27 | Yes | Not Required | Not Required | Not Required | 2021-04-12 | 2022-08-12 | 2022-08-12 |  |  | 2024-08-19 | 2024-10-14
21INR0491 | Samson Solar 3 | SS Completed, FIS Completed, IA | Samson Solar Energy III LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2026-06-30 | SOL | PV | 250 |  | 2020-01-14 | 2020-01-13 | 2019-01-04 | 2020-01-13 | 2020-06-09 |  | 2020-08-27 | Yes | Not Required | Not Required | Not Required | 2020-08-27 | 2020-10-15 | 2020-10-26 |  |  | 2021-06-30 | 2021-10-26
21INR0492 | Stockyard Grid Batt | SS Completed, FIS Completed, IA | Stockyard Grid, LLC | 2082 Hicks 138kV | Tarrant | NORTH | 2026-12-31 | OTH | BA | 150.6 |  | 2020-02-05 | 2020-01-13 | 2020-03-30 | 2020-01-13 | 2022-07-14 | No | 2022-10-26 | Yes | Not Required | Not Required |  | 2022-10-26 | 2022-10-26 | 2022-10-26
21INR0505 | Ramsey Storage | SS Completed, FIS Started, IA | Hecate Energy Ramsey Storage LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2027-12-31 | OTH | BA | 201.1 |  | 2021-01-20 | 2020-05-20 | 2020-07-30 | 2020-12-23 |  | No | 2022-08-11 | Yes |  |  |  | 2023-08-18 | 2024-01-02
21INR0509 | McClure Solar | SS Completed, FIS Started, No IA | McClure Solar LLC | tap 69kV 785 Oran - 343 Morris Sheppard | Palo Pinto | NORTH | 2025-12-31 | SOL | PV | 105.73 |  | 2021-03-18 | 2020-06-03 | 2020-08-18 | 2021-02-24 |  | No |  | No |  |  | Not Required
21INR0517 | Tidwell Prairie Storage 1 | SS Completed, FIS Completed, IA | Tidwell Prairie LLC | 39950 TNP ONE PLANT 345kV - 3400 TWIN OAK | Robertson | NORTH | 2025-10-07 | OTH | BA | 204 | COD | 2020-07-23 | 2020-07-24 | 2020-10-20 | 2020-07-16 | 2024-10-18 |  | 2022-11-03 | Yes |  |  |  | 2024-11-04 | 2024-11-04 | 2024-11-01 |  |  | 2025-07-23 | 2025-08-20
21INR0520 | Yellow Viking Solar | SS Completed, FIS Started, IA | Yellow Viking Development One, LLC | ap 345kV 1900 Comanche Peak - 11886 Timberview Switch | Somervell | NORTH | 2027-07-13 | SOL | PV | 170.86 |  | 2020-10-09 | 2020-10-23 | 2021-01-12 | 2020-08-20 |  |  | 2022-10-25 | No |  |  | Not Required
21INR0527 | Hays Energy Unit 3 Repower | SS Completed, FIS Started, No IA | HAYS ENERGY, LLC | 7043 Hays 345kV | Hays | SOUTH | 2026-12-03 | GAS | GT | 18 | COD | 2021-02-09 | 2020-10-07 | 2020-12-30 | 2021-02-05 |  |  |  | No | 2020-11-05
21INR0532 | Brazos Wind Repower | SS Completed, FIS Completed, No IA | BRAZOS WIND VENTURES, LLC | 1064 Sun 138kV | Scurry | WEST | 2025-08-29 | WIN | WT | 22.4 |  | 2020-12-18 | 2020-12-22 | 2021-03-10 | 2020-11-30 | 2022-04-01 |  |  | Yes | Not Required | Not Required | Not Required | 2022-08-03 | 2022-10-21 | 2023-02-03 |  |  | 2023-04-25 | 2023-07-01
21INR0534 | Midlothian Unit 2 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1939 Midlothian ELP 345kV | Ellis | NORTH | 2026-12-03 | GAS | GT | 18 | COD | 2021-04-28 | 2021-01-25 | 2021-04-30 | 2021-02-08 |  |  |  | No
21INR0538 | Blue Jay Solar II | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2025-10-31 | SOL | PV | 68.95 |  | 2018-02-15 | 2021-04-13 | 2021-04-14 |  | 2021-04-26 | No | 2020-10-26 | Yes |  |  | Not Required | 2020-12-02 | 2021-04-26 | 2021-04-29 |  |  | 2021-11-11 | 2021-11-19
21INR0546 | Anchor Wind III | SS Completed, FIS Completed, IA | RANCHLAND WIND PROJECT LLC | 345 kV Aspire Station (68011) | Eastland | NORTH | 2025-12-29 | WIN | WT | 16 | COD | 2019-06-26 | 2021-12-03 | 2022-03-01 |  | 2021-04-30 | No | 2020-11-30 | Yes | Not Required | Not Required | Not Required | 2020-12-02 | 2021-04-30 | 2021-04-30 |  |  | 2021-11-29 | 2022-12-13
22INR0202 | Delilah Solar 1 | SS Completed, FIS Completed, IA | Delilah Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2025-11-28 | SOL | PV | 300 |  | 2019-05-13 | 2018-11-20 | 2019-01-03 | 2019-05-03 | 2020-06-09 | No | 2020-12-22 | Yes | Not Required | Not Required | Not Required | 2021-03-23 | 2021-03-23 | 2021-04-27 |  |  | 2023-07-11 | 2024-03-21
22INR0203 | Delilah Solar 2 | SS Completed, FIS Completed, IA | Delilah Solar Energy II LLC | 345 kV TTRSW 11688 | Lamar | NORTH | 2025-11-10 | SOL | PV | 317.58 |  | 2019-05-13 | 2018-11-20 | 2019-01-03 | 2019-05-03 | 2020-06-09 | No | 2020-12-22 | Yes | Not Required | Not Required | Not Required | 2021-03-23 | 2022-08-12 | 2022-08-12 |  |  | 2024-10-29 | 2025-01-13
22INR0205 | Sbranch Solar | SS Completed, FIS Completed, IA | Bernard Creek Solar, LLC | Tap 138kV 44190 East Bernard - 44130 Caney | Wharton | SOUTH | 2025-08-22 | SOL | PV | 233.52 |  | 2019-04-01 | 2019-01-03 | 2019-03-13 | 2019-03-29 | 2021-07-29 | No | 2020-07-26 | Yes | Not Required | Not Required | Not Required | 2020-10-07 | 2021-07-06 | 2021-07-29 |  |  | 2022-09-12 | 2023-11-21
22INR0209 | Felix North Solar | SS Completed, FIS Started, IA | Crescent Solar, LLC | 6101 Riley 345kV | Wilbarger | WEST | 2027-07-31 | SOL | PV | 100.54 |  | 2019-09-23 | 2019-01-17 | 2019-04-02 | 2019-09-20 |  | No | 2025-02-21 | Yes | Not Required | Not Required | Not Required | 2025-04-03
22INR0215 | TEXAS SOLAR NOVA 3 | SS Completed, FIS Started, No IA | Texas Solar Nova 1, LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2026-01-31 | SOL | PV | 200.2 |  | 2019-05-28 | 2019-06-24 | 2015-12-30 | 2019-06-19 |  |  |  | No |  |  | Not Required
22INR0218 | Velociraptor Solar I | SS Completed, FIS Started, No IA | Greyhound Solar 2 | #10012 METEOR 5 Substation 345kV | Ector | WEST | 2028-11-17 | SOL | PV | 251.67 |  | 2019-05-23 | 2019-05-14 | 2019-08-05 | 2019-05-10 |  |  |  | No | Not Required | Not Required | Not Required
22INR0220 | Lamkin Solar | SS Completed, FIS Completed, IA | Commanche Solar, LLC | tap 69kV 258 Hamilton - 273 Gustine | Comanche | NORTH | 2027-08-08 | SOL | PV | 101.5 |  | 2020-05-11 | 2019-06-24 | 2019-09-18 | 2020-03-13 | 2022-07-11 |  | 2025-03-06 | Yes | Not Required | Not Required | Not Required | 2025-04-23
22INR0237 | Dragan Solar | SS Completed, FIS Started, No IA | Hecate Comanche Solar LLC | 1440 Comanche 345kV | Comanche | NORTH | 2027-09-15 | SOL | PV | 411 | COD | 2019-11-11 | 2019-11-11 | 2020-02-17 | 2019-08-23 |  | No |  | No |  |  | Not Required
22INR0239 | Rockefeller Storage | SS Completed, FIS Started, IA | Mittel Rockefeller Storage LLC | 76003 Big Hill 345kV | Schleicher | WEST | 2027-06-01 | OTH | BA | 206.8 |  | 2020-08-20 | 2019-10-31 | 2020-01-24 | 2020-07-21 |  | No | 2024-09-23 | Yes | Not Required | Not Required |  | 2025-02-12
22INR0244 | Razorbill Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP to 44200 Hillje 345kV Ckt 64 | Matagorda | COASTAL | 2027-12-15 | SOL | PV | 240 |  | 2020-10-23 | 2020-01-02 | 2020-03-26 | 2020-09-16 |  |  |  | No | Not Required | Not Required | Not Required
22INR0251 | Shaula I Solar | SS Completed, FIS Started, IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | DeWitt | SOUTH | 2026-03-31 | SOL | PV | 205.2 |  | 2019-11-27 | 2019-12-03 | 2020-03-08 | 2019-11-20 |  | No | 2022-02-16 | Yes |  |  | Not Required | 2023-03-27
22INR0257 | Corazon Solar Phase II | SS Completed, FIS Started, IA | BAYWA R.E. SOLAR PROJECTS | 80219 Lobo 345kV | Webb | SOUTH | 2028-06-01 | SOL | PV | 203.9 |  | 2019-12-16 | 2019-12-19 | 2020-03-12 | 2019-12-04 |  | No | 2020-08-04 | No | Not Required | Not Required | Not Required
22INR0261 | Dorado Solar | SS Completed, FIS Completed, IA | Enbridge Solar (Sequoia I), LLC | 68051 Reata 345kV | Callahan | WEST | 2025-12-31 | SOL | PV | 401.35 |  | 2020-09-02 | 2020-01-09 | 2020-03-30 | 2020-08-27 | 2025-03-14 | Yes | 2023-06-19 | Yes | Not Required | Not Required | Not Required | 2023-07-10 | 2025-04-17 | 2025-04-17
22INR0262 | Sequoia II Solar | SS Completed, FIS Started, IA | Deville Solar LLC | 68051 Reata 345kV | Callahan | WEST | 2026-11-21 | SOL | PV | 417.47 | COD | 2020-09-02 | 2020-01-22 | 2020-04-08 | 2020-08-27 |  |  | 2023-08-29 | Yes | Not Required | Not Required | Not Required | 2025-09-22
22INR0267 | Shaula II Solar | SS Completed, FIS Started, IA | Shaula Energy Project II, LLC | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | DeWitt | SOUTH | 2026-05-30 | SOL | PV | 205.2 |  | 2019-12-27 | 2019-12-18 | 2020-03-12 | 2019-12-18 |  | No | 2022-04-27 | Yes |  |  | Not Required | 2023-03-27
22INR0270 | Millers Branch Solar I | SS Completed, FIS Completed, IA | Miller's Branch Solar, LLC | Tap 345kV 60703 Gauss - 60514 Clear Crossing (60712 QUASAR) | Haskell | WEST | 2025-12-01 | SOL | PV | 200 |  | 2020-08-27 | 2019-12-17 | 2020-03-06 | 2020-06-19 | 2024-11-01 |  | 2021-06-14 | Yes |  |  | Not Required | 2021-06-25 | 2025-01-06 | 2025-01-29 | 2024-06-01 | 2025-12-01 | 2025-08-18 | 2025-08-25
22INR0274 | Crowded Star Solar II | SS Completed, FIS Completed, IA | Jones City Solar II, LLC | tap 345kV 68001 Claytonville – 68004 Phantom Hill c2 (New Substation: Open Sky 68014) | Jones | WEST | 2026-06-15 | SOL | PV | 189.5 | MW Size | 2019-05-23 | 2020-03-26 | 2020-06-05 | 2021-03-24 | 2024-11-05 | No | 2023-07-27 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2025-07-24 | 2025-07-24
22INR0279 | Clutch City Solar Phase I | SS Completed, FIS Started, IA | HZ Solar I, LLC | tap 138kV 42960 Mustang Bayou – 42100 Hudson CKT #04 | Brazoria | COASTAL | 2028-07-01 | SOL | PV | 200.75 |  | 2020-03-16 | 2020-01-22 | 2020-04-08 | 2020-02-11 |  | No | 2022-09-30 | No | Not Required | Not Required | Not Required
22INR0281 | Pink Solar | SS Completed, FIS Started, IA | Pink Solar, LLC | 971 Pruitt 138kV | Hunt | NORTH | 2027-04-30 | SOL | PV | 151.9 |  | 2020-10-21 | 2020-01-30 | 2020-04-20 | 2020-10-16 |  |  | 2022-08-30 | No | Not Required | Not Required | Not Required
22INR0301 | Fortuna Wind | SS Completed, FIS Completed, IA | RWE Renewables Development, LLC | Tap 345kV 1429 Jacksboro - 1730 WKrum | Jack | NORTH | 2026-07-01 | WIN | WT | 295.3 |  | 2021-01-18 | 2020-03-06 | 2020-05-27 | 2020-11-24 | 2024-05-09 |  | 2024-08-08 | No |  |  | Not Required
22INR0314 | Lan Solar SLF | SS Completed, FIS Started, No IA | BR Solar, LLC | Tap 345kV 1729 Valley South – 1692 Paris Switch | Lamar | NORTH | 2028-08-26 | SOL | PV | 182.2 |  | 2021-10-12 | 2020-05-01 | 2020-07-07 | 2021-01-04 |  | No |  | No | Not Required | Not Required | Not Required
22INR0328 | Inertia BESS | SS Completed, FIS Completed, IA | Inertia Energy Storage, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2025-09-30 | OTH | BA | 13 |  | 2020-08-24 | 2020-06-03 | 2021-02-02 | 2020-05-27 | 2022-07-25 | No | 2021-05-04 | Yes | Not Required | Not Required | 2022-09-30 | 2021-10-08 | 2022-10-03 | 2022-10-31 |  |  | 2024-04-10 | 2024-05-08
22INR0330 | Old Aqueduct Batt | SS Completed, FIS Started, No IA | Old Aqueduct LLC | 23920 Blackwater 345kV | Hale | PANHANDLE | 2028-06-01 | OTH | BA | 302.94 |  | 2020-07-24 | 2020-05-01 | 2020-07-13 | 2020-06-29 |  |  |  | No
22INR0332 | Brantley Branch Batt | SS Completed, FIS Started, No IA | Brantley Branch LLC | Mt. Enterprise (Bus # 3116) – Martin Lake 345kv Line (Bus # 3100 | Rusk | NORTH | 2026-09-14 | OTH | BA | 302.35 |  | 2020-12-07 | 2020-05-01 | 2020-07-15 | 2020-11-24 |  | No |  | No
22INR0337 | Skylab Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 5915 STP - 8249 Angstrom | Wharton | SOUTH | 2025-12-01 | SOL | PV | 609.74 |  | 2020-08-10 | 2020-06-03 | 2020-08-11 | 2020-05-27 |  | No |  | No |  |  | Not Required
22INR0342 | Matagorda Solar | SS Completed, FIS Completed, IA | Matagorda Solar Farm, LLC | 5555 Shropshire 69kV | Matagorda | COASTAL | 2027-08-25 | SOL | PV | 101 |  | 2020-12-08 | 2020-05-01 | 2020-07-15 | 2020-11-05 | 2021-09-14 |  | 2022-06-08 | Yes |  |  | Not Required | 2025-02-12
22INR0347 | Crater BESS | SS Completed, FIS Started, No IA | BRP Crater BESS LLC | Tap 345 kV Rockhound Switch (10062) – Prong Moss Switch (10057) ckt 1 | Howard | WEST | 2028-03-01 | OTH | BA | 301.5 |  | 2020-05-18 | 2020-05-20 | 2020-07-30 | 2020-04-30 |  |  |  | No
22INR0350 | Sandow Solar | SS Completed, FIS Completed, No IA | Sandow Lakes Ranch Solar I, LLC | tap one 345kV 7040 Austrop - 13429 Sandow line | Milam | SOUTH | 2027-04-02 | SOL | PV | 287.18 |  | 2020-08-24 | 2020-09-11 | 2021-02-08 | 2020-05-28 | 2024-07-18 |  |  | Yes |  |  | Not Required
22INR0357 | Loma Pinta Solar | SS Completed, FIS Started, No IA | Loma Pinta Wind Energy, LLC | 5705 Fowlerton 138kV | La Salle | SOUTH | 2027-05-31 | SOL | PV | 203.06 |  | 2020-09-08 | 2020-06-03 | 2020-08-18 | 2020-05-28 |  | No |  | No |  |  | Not Required
22INR0363 | Hayhurst Texas Solar | SS Completed, FIS Completed, IA | Hayhurst Texas Solar, LLC | tap 138 kV Three Mile Draw Switch – Horseshoe Springs Switch Line | Culberson | WEST | 2025-11-28 | SOL | PV | 24.76 | COD | 2020-10-23 | 2020-08-21 | 2020-11-04 | 2020-08-13 | 2023-04-26 |  | 2021-09-09 | Yes |  |  | Not Required | 2022-04-29 | 2022-04-29 | 2023-04-27 |  |  | 2023-11-10 | 2023-12-12
22INR0365 | Mensa BESS | SS Completed, FIS Started, No IA | BRP Mensa BESS LLC | 60718 Pecos Valley 138kV | Pecos | WEST | 2027-12-01 | OTH | BA | 307.43 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 | 2020-06-22 |  |  |  | No | Not Required | Not Required
22INR0374 | Inertia Solar | SS Completed, FIS Started, IA | Inertia Solar Project, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2029-03-31 | SOL | PV | 202.39 |  | 2020-10-26 | 2021-02-02 | 2021-02-02 | 2020-10-13 |  |  | 2021-05-04 | Yes | Not Required | Not Required | Not Required | 2021-10-08
22INR0382 | Razorbill Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP to 44200 Hillje 345kV Ckt 64 | Matagorda | COASTAL | 2027-12-15 | OTH | BA | 120 |  | 2021-06-25 | 2020-08-04 | 2020-10-28 | 2021-06-11 |  |  |  | No | Not Required | Not Required
22INR0383 | BRP Musca BESS | SS Completed, FIS Started, No IA | BRP Musca BESS LLC | 60361 Santa Rita 138kV | Reagan | WEST | 2027-12-01 | OTH | BA | 100.51 |  | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  | No |  | No
22INR0385 | BRP Pictor BESS | SS Completed, FIS Started, No IA | BRP Pictor BESS LLC | 60400 Lynx 138kV | Crane | WEST | 2025-11-01 | OTH | BA | 201.07 |  | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  | No |  | No
22INR0386 | BRP Octans BESS | SS Completed, FIS Started, No IA | BRP OCTANS BESS LLC | 6671 Tombstone 138kV | Pecos | WEST | 2029-12-01 | OTH | BA | 129.57 |  | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  | No |  | No
22INR0387 | Val Vista Grid BESS 1 | SS Completed, FIS Started, No IA | Val Vista Grid, LLC | Tap 345kV 8383 North Edinburg - 80137 Stewart Road | Hidalgo | SOUTH | 2028-06-01 | OTH | BA | 209.32 |  | 2020-08-04 | 2020-08-04 | 2020-10-16 | 2020-07-21 |  | Yes |  | No
22INR0390 | BRP Perseus BESS | SS Completed, FIS Started, No IA | BRP Perseus BESS LLC | tap 138 kV line from Lon Hill (#8452) to Bessel (#8060) | Nueces | COASTAL | 2027-12-01 | OTH | BA | 202.5 |  | 2020-08-19 | 2020-08-21 | 2020-11-10 | 2020-08-17 |  |  |  | No
22INR0392 | Kalina Solar | SS Completed, FIS Started, No IA | Aurora Solar LLC | 8606 Goddard 345kV | San Patricio | COASTAL | 2028-03-01 | SOL | PV | 120 |  | 2021-03-31 | 2020-08-04 | 2020-10-28 | 2021-03-29 |  | No |  | No | Not Required | Not Required | Not Required
22INR0400 | Dragan Storage | SS Completed, FIS Started, No IA | Hecate Grid Dragan Storage LLC | 1440 Comanche 345kV | Comanche | NORTH | 2026-02-28 | OTH | BA | 408.3 |  | 2020-10-02 | 2020-08-21 | 2020-11-04 | 2020-08-13 |  |  |  | No
22INR0401 | Eval Storage | SS Completed, FIS Started, IA | Hecate Grid East Valley Storage LLC | 80229 Cavazos 138kV | Cameron | COASTAL | 2028-12-31 | OTH | BA | 251.85 |  | 2020-12-29 | 2020-10-23 | 2021-01-12 | 2020-11-03 |  | No | 2022-02-03 | Yes | Not Required | Not Required |  | 2025-02-14
22INR0402 | Frye Storage | SS Completed, FIS Started, No IA | Hecate Energy Frye Storage LLC | new 345kV sub Kress connecting both 23912 Ogallala - 23914 Tule Canyon circuits | Swisher | PANHANDLE | 2026-12-15 | OTH | BA | 503.85 |  | 2020-08-26 | 2020-09-02 | 2020-11-19 | 2020-08-17 |  | No |  | No
22INR0408 | BRP Pular BESS | SS Completed, FIS Started, No IA | BRP Pular BESS LLC | 8963 Hidalgo Energy Center 138kV | Hidalgo | SOUTH | 2027-12-01 | OTH | BA | 233.1 |  | 2020-09-02 | 2020-09-11 | 2021-06-10 | 2020-08-25 |  |  |  | No
22INR0409 | Stampede Solar | SS Completed, FIS Completed, IA | Stampede Solar Project, LLC | tap 345kV 1685 Farmersville - 11688 Thorn Tree ckt 1 | Hopkins | NORTH | 2025-10-31 | SOL | PV | 256.34 |  | 2020-10-16 | 2020-11-05 | 2021-01-20 | 2020-10-21 | 2023-11-01 |  | 2021-12-15 | Yes |  |  | Not Required | 2022-04-11 | 2022-04-27 | 2023-11-01 |  |  | 2023-11-28 | 2023-12-22
22INR0422 | Ferdinand Grid BESS | SS Completed, FIS Completed, IA | Ferdinand Grid, LLC | 5260 Leon Creek 138kV | Bexar | SOUTH | 2026-05-01 | OTH | BA | 205.5 |  | 2021-01-28 | 2021-03-01 | 2021-05-12 | 2021-01-28 | 2025-06-16 | No | 2022-11-28 | Yes | Not Required | Not Required |  | 2023-08-18 | 2025-07-31 | 2025-07-31
22INR0423 | Quela BESS | SS Completed, FIS Started, No IA | BRP Quela BESS LLC | Tap 138kV 5110 J.T. Deely - 5294 Martinez | Bexar | SOUTH | 2027-12-01 | OTH | BA | 301.41 |  | 2020-09-25 | 2020-09-25 | 2020-12-16 | 2020-09-15 |  | No |  | No
22INR0424 | BRP Denali BESS | SS Completed, FIS Started, No IA | BRP Denali BESS LLC | Tap 138kV 5395 Sommers - 5030 Braunig East | Bexar | SOUTH | 2028-12-01 | OTH | BA | 258.41 |  | 2020-09-25 | 2020-09-25 | 2020-12-16 | 2020-09-17 |  |  |  | No | Not Required | Not Required
22INR0425 | MAKALU SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green X LLC | Tap 138kV 977 Pruitt - 971 Greenville | Hunt | NORTH | 2027-09-16 | SOL | PV | 50.16 |  | 2021-08-17 | 2021-01-21 | 2021-01-28 | 2021-08-10 |  | No |  | No |  |  | Not Required
22INR0426 | LUBIO SOLAR | SS Completed, FIS Completed, IA | BDPU Solar Lubio LLC | tap 138kV 2727 Crandall - 2724 Kaufman Northwest | Kaufman | NORTH | 2027-09-17 | SOL | PV | 54.47 |  | 2021-07-01 | 2020-10-07 | 2020-12-28 | 2021-06-28 | 2023-10-30 |  | 2024-11-08 | No |  |  | Not Required
22INR0427 | BRP Kabru BESS | SS Completed, FIS Started, No IA | BRP Kabru BESS LLC | 1159 Andrew North - 11284 Blackbird 138kV | Andrews | WEST | 2028-12-01 | OTH | BA | 202.45 |  | 2020-09-28 | 2020-10-07 | 2020-12-28 | 2020-09-22 |  | No |  | No
22INR0437 | TORMES SOLAR | SS Completed, FIS Started, IA | BDPU SOLAR TORMES LLC | tap 345kV 1906 Venus - 68091 Navarro | Navarro | NORTH | 2027-03-31 | SOL | PV | 356.6 |  | 2021-07-26 | 2020-10-23 | 2021-01-12 | 2021-07-19 |  |  | 2024-04-10 | Yes |  |  | Not Required | 2025-02-13
22INR0443 | Bowstring BESS | SS Completed, FIS Completed, IA | Longbow Energy Storage, LLC | 8961 White Point 138kV | San Patricio | COASTAL | 2028-09-18 | OTH | BA | 155 | SFS/NtP | 2021-04-01 | 2020-11-18 | 2021-02-09 | 2021-03-24 | 2023-05-30 |  | 2025-09-09 | Yes | Not Required |  | 2025-09-23
22INR0445 | SPC Bloom BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 2, LLC | 8911 Black Bayou 138kV | Victoria | SOUTH | 2027-04-07 | OTH | BA | 100 |  | 2021-02-04 | 2020-12-03 | 2021-02-19 | 2020-11-13 |  |  |  | No
22INR0454 | Delaware Ranch Solar | SS Completed, FIS Completed, IA | Delaware Ranch Solar, LLC | Delaware River SW (11112) | Culberson | WEST | 2026-09-16 | SOL | PV | 36 |  | 2020-11-04 | 2020-12-22 | 2021-03-10 | 2020-12-17 | 2025-06-16 | No | 2022-02-07 | Yes | Not Required | Not Required | Not Required | 2022-08-24
22INR0455 | Blue Sky Sol | SS Completed, FIS Started, IA | Blue Sky Solar LLC | 6562 Friends Ranch 138kV | Crockett | WEST | 2027-04-23 | SOL | PV | 101.2 |  | 2020-12-09 | 2020-12-03 | 2021-02-16 | 2020-11-10 |  | No | 2022-02-01 | Yes | Not Required | Not Required | Not Required | 2022-02-07 | 2023-07-31 | 2023-07-31
22INR0457 | Anson BAT | SS Completed, FIS Completed, IA | Anson II Storage LLC | tap 345 kV 68004 Phantom Hill station | Jones | WEST | 2026-09-01 | OTH | BA | 153.55 |  | 2022-03-03 | 2020-12-03 | 2021-02-19 | 2022-02-23 | 2025-03-19 |  | 2024-08-15 | Yes |  |  |  | 2025-02-12
22INR0462 | Old Aqueduct Solar | SS Completed, FIS Started, No IA | Old Aqueduct Solar | 23920 Blackwater 345kV | Hale | PANHANDLE | 2028-06-01 | SOL | PV | 511.63 |  | 2021-07-09 | 2020-12-03 | 2021-02-19 | 2021-06-29 |  |  |  | No |  |  | Not Required
22INR0466 | Pajarita BESS | SS Completed, FIS Started, IA | VESI 29 LLC | 8266 Marconi 138kV | Cameron | COASTAL | 2028-07-19 | OTH | BA | 205.5 |  | 2021-12-15 | 2021-01-25 | 2021-04-12 | 2021-12-01 |  | No | 2025-06-19 | Yes | Not Required | Not Required
22INR0467 | Bird Dog Energy Storage | SS Completed, FIS Completed, IA | VESI 37 LLC | 5669 Argenta 69kV | Live Oak | SOUTH | 2026-03-30 | OTH | BA | 60.4 | Proj Name | 2022-06-02 | 2021-02-04 | 2021-04-19 | 2022-05-19 | 2025-06-18 |  | 2024-02-16 | Yes | Not Required | Not Required |  | 2024-02-16 | 2025-08-07 | 2025-07-29
22INR0469 | Harper Energy Storage | SS Completed, FIS Started, No IA | VESI 31 LLC | Tap 138kV 8314 La Palma - 80229 Villa Cavazos | Cameron | COASTAL | 2028-09-15 | OTH | BA | 82.42 |  | 2022-02-10 | 2021-12-03 | 2022-03-01 | 2022-01-27 |  |  |  | No
22INR0473 | TAIN SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green VII LLC | tap 138kV 7216 Lockhart - 7224 Luling City | Caldwell | SOUTH | 2027-10-27 | SOL | PV | 37.54 |  | 2021-11-02 | 2020-12-03 | 2021-02-17 | 2021-10-20 |  |  |  | No |  |  | Not Required
22INR0480 | Pachanga Wind | SS Completed, FIS Started, No IA | Pachanga Wind LLC | tap 345kV 5966 Palmito - 80137 Stewart Rd | Cameron | COASTAL | 2027-04-01 | WIN | WT | 300 |  | 2021-06-28 | 2021-02-09 | 2021-05-06 | 2021-04-05 |  |  |  | No |  |  | Not Required
22INR0488 | Venture Hill Storage | SS Completed, FIS Started, No IA | KCE TX 24, LLC | 7336 Gilleland Creek 138kV | Travis | SOUTH | 2026-12-01 | OTH | BA | 70.44 |  | 2021-01-08 | 2021-02-09 | 2021-05-06 | 2020-12-29 |  |  |  | No
22INR0494 | Quail Run Storage System | SS Completed, FIS Started, No IA | Quail Run Energy Partners, LP | 11016 Quail Switch 345kV | Ector | WEST | 2026-02-01 | OTH | BA | 51.56 |  | 2022-01-21 | 2021-02-09 | 2021-05-06 | 2021-12-28 |  |  |  | No | Not Required | Not Required
22INR0497 | TEXPO | SS Completed, FIS Started, No IA | Oklaunion Power Station, LLC | 6100 Oklaunion 345kV | Wilbarger | WEST | 2027-10-31 | GAS | ST | 680 |  | 2021-11-30 | 2021-03-16 | 2021-05-28 | 2021-11-23 |  | No |  | No | Not Required | Not Required | 2022-05-02
22INR0499 | Aquilla Lake 3 Wind | SS Completed, FIS Completed, IA | Aquilla Lake 3 Wind | tap 345 kV 68040 Kopperl to 68091 Navarro | Hill | NORTH | 2027-03-01 | WIN | WT | 297.4 | MW Size | 2021-03-05 | 2021-03-08 | 2021-05-28 | 2021-02-18 | 2025-09-10 | Yes | 2024-01-24 | Yes | Not Required |  | Not Required | 2025-09-10 | 2025-09-10
22INR0503 | Tidwell Prairie II Batt | SS Completed, FIS Completed, IA | TIDWELL PRAIRIE II LLC | Tap 345kV 3400 Twin Oak - 39950 TNP One | Robertson | NORTH | 2026-03-01 | OTH | BA | 203.62 |  | 2021-03-02 | 2021-03-16 | 2021-05-28 | 2021-02-17 | 2025-06-16 | No | 2025-01-13 | Yes |  |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01
22INR0504 | Barton Branch IA | SS Completed, FIS Completed, IA | Barton Branch IA LLC | Tap 345kV 3400 Twin Oak - 39950 TNP One | Robertson | NORTH | 2026-03-01 | OTH | BA | 203.62 |  | 2021-03-02 | 2021-03-16 | 2021-05-28 | 2021-02-17 | 2025-06-16 | No | 2025-06-18 | Yes |  |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01
22INR0506 | Roseland Solar II | SS Completed, FIS Completed, IA | Enel Green Power Roseland Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2025-11-29 | SOL | PV | 254 | COD | 2018-11-05 | 2021-10-05 | 2019-02-04 |  | 2021-10-25 |  | 2020-12-10 | Yes | Not Required | Not Required | Not Required | 2021-10-26 | 2021-10-26 | 2021-10-26 |  |  | 2022-06-07 | 2022-09-26
22INR0514 | Wang Storage SLF | SS Completed, FIS Started, No IA | BT Yixin Solar, LLC | tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2026-03-31 | OTH | BA | 0 |  | 2021-06-09 | 2022-11-07 | 2023-02-03 | 2022-09-23 |  | No |  | No
22INR0517 | Lane City Wind | SS Completed, FIS Completed, IA | RWE Clean Energy, LLC | 44040 Bailey 345kV | Wharton | SOUTH | 2025-12-30 | WIN | WT | 199.5 | COD | 2021-05-05 | 2021-04-26 | 2021-07-28 | 2021-04-26 | 2024-07-18 | No | 2022-05-13 | Yes | Not Required | Not Required | Not Required | 2024-08-01 | 2024-08-01 | 2024-08-01 |  |  | 2025-06-12 | 2025-07-28
22INR0523 | Midlothian 4 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1940 Midlothian ANP 345kV | Ellis | NORTH | 2026-12-03 | GAS | GT | 18 | COD | 2021-04-28 | 2021-04-26 | 2021-07-28 | 2021-04-21 |  |  |  | No
22INR0526 | Pine Forest BESS | SS Completed, FIS Completed, IA | Pine Forest Hybrid I, LLC | tap 345kV 1696 Monticello SES - 2514 Allen Switch | Hopkins | NORTH | 2025-10-29 | OTH | BA | 200.74 |  | 2021-07-30 | 2021-05-04 | 2021-07-30 | 2021-07-19 | 2024-12-18 |  | 2024-04-10 | Yes |  |  |  | 2024-05-23 | 2025-01-28 | 2025-01-28 |  |  | 2025-06-03 | 2025-07-03
22INR0533 | Temple Generation I Repower | SS Completed, FIS Completed, IA | Panda Temple Power | 3413 Knob Creek 345kV | Bell | NORTH | 2024-09-01 | GAS | CC | 67 |  | 2021-04-26 | 2021-04-26 | 2021-05-13 | 2021-04-22 | 2021-09-30 |  | 2012-06-21 | Yes | Not Required | Not Required |  | 2021-10-26 | 2021-10-26 | 2021-10-26
22INR0540 | Walstrom BESS | SS Completed, FIS Completed, IA | Sealy Power LLC | 46220 Peters 138kV | Austin | SOUTH | 2025-09-15 | OTH | BA | 205.31 | COD | 2021-05-17 | 2021-07-08 | 2021-10-04 | 2021-06-03 | 2024-03-07 |  | 2023-06-30 | Yes | Not Required | Not Required |  | 2024-08-01 | 2024-08-01 | 2024-08-01 |  |  | 2025-05-14 | 2025-05-30
22INR0541 | ALWEST BESS | SS Completed, FIS Started, No IA | Castleman Power | 3114 Paltalco 138kV | Anderson | NORTH | 2028-04-19 | OTH | BA | 208.63 |  | 2021-05-17 | 2021-08-24 | 2021-11-15 | 2021-06-03 |  |  |  | No
22INR0543 | Midlothian Unit 3 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1940 Midlothian ELP 345kV | Ellis | NORTH | 2026-12-03 | GAS | GT | 18 | COD | 2021-05-21 | 2021-05-24 | 2021-08-06 | 2021-05-11 |  |  |  | No
22INR0546 | Enchanted Rock NEWPP | SS Completed, FIS Completed, IA | Generate ER-NG, LLC | 40475 Deusen 138kV | Harris | HOUSTON | 2026-02-28 | GAS | IC | 30 |  | 2022-12-01 | 2021-11-10 | 2022-01-17 | 2022-07-13 | 2024-04-19 | No | 2024-04-30 | Yes | 2024-04-25 | Not Required | 2024-04-30 | 2024-05-01 | 2024-05-01 | 2024-05-01
22INR0549 | Tanzanite Storage | SS Completed, FIS Completed, IA | Tanzanite Energy Storage LLC | 6867 NORTH ATHENS 138kV | Henderson | NORTH | 2025-09-30 | OTH | BA | 265.8 | COD | 2021-07-27 | 2021-09-01 | 2021-11-18 | 2021-08-16 | 2023-12-14 | No | 2022-07-15 | Yes | Not Required | Not Required |  | 2022-11-04 | 2024-04-22 | 2024-04-30 |  |  | 2025-03-14 | 2025-03-26
22INR0552 | Sowers Storage | SS Completed, FIS Completed, IA | Sowers Energy Storage LLC | 6894 Rose Hill_RC Sub 138 kV | Kaufman | NORTH | 2026-12-29 | OTH | BA | 203.9 |  | 2021-08-17 | 2021-08-18 | 2021-11-05 | 2021-08-18 | 2025-08-04 | No | 2022-04-22 | Yes | Not Required | Not Required |  | 2022-12-05
22INR0554 | Platinum Storage | SS Completed, FIS Completed, IA | Platinum Energy Storage LLC | 1729 Valley South 345kV | Fannin | NORTH | 2025-10-31 | OTH | BA | 309.53 |  | 2021-08-20 | 2021-09-02 | 2021-11-18 | 2021-08-31 | 2024-07-31 | No | 2022-11-17 | Yes | Not Required | Not Required |  | 2024-07-31 | 2024-08-01 | 2024-08-01 |  |  | 2025-05-21 | 2025-06-03
22INR0555 | TE Smith Storage | SS Completed, FIS Completed, IA | BT Smith Storage, LLC | 2483 Royse Switch 345kV | Rockwall | NORTH | 2025-12-01 | OTH | BA | 125.36 |  | 2021-08-24 | 2021-09-02 | 2021-11-18 | 2021-08-26 | 2024-05-16 | No | 2023-11-08 | Yes | Not Required | Not Required |  | 2023-11-13 | 2024-07-08 | 2024-10-31 |  |  | 2025-06-02
22INR0558 | Callisto II Energy Center | SS Completed, FIS Completed, IA | Callisto II Energy Center LLC | 47150 HO Clarke 138kV | Harris | HOUSTON | 2026-07-01 | OTH | BA | 203.2 |  | 2021-10-07 | 2021-10-07 | 2021-12-08 | 2021-09-29 | 2025-08-21 |  | 2023-12-11 | Yes |  |  |  | 2025-02-12 | 2025-09-11
22INR0559 | Honeycomb Solar SLF | SS Completed, FIS Completed, IA | Honeycomb Solar, LLC | 69 kV Tynan Substation (#8107) | Bee | SOUTH | 2026-06-30 | SOL | PV | 61.4 |  | 2021-10-26 | 2021-11-16 | 2022-01-17 | 2021-11-02 | 2025-03-28 | No | 2023-05-01 | Yes | Not Required | Not Required | Not Required | 2025-02-14 | 2025-07-25 | 2025-07-25
22INR0586 | Hays Energy Unit 2 Repower | SS Completed, FIS Started, No IA | HAYS ENERGY, LLC | 7043 Haysen 345kV | Hays | SOUTH | 2026-12-03 | GAS | GT | 18 | COD | 2022-12-01 | 2022-02-21 | 2022-05-21 | 2022-11-15 |  |  |  | No
22INR0605 | Camino Santiago Solar | SS Completed, FIS Completed, IA | Camino Solar Project, LLC | Tap 345kV 3687 Bell County East Switch – 39950 TNP One Plant Ckt 2 (North Circuit). | Milam | SOUTH | 2027-02-18 | SOL | PV | 196.3 |  | 2023-02-08 | 2022-09-02 | 2022-11-30 | 2023-01-05 | 2024-09-05 | No | 2024-12-06 | Yes | Not Required |  | Not Required | 2025-06-11
23INR0006 | Sierra Madre Solar | SS Completed, FIS Started, No IA | Sierra Madre Solar LLC | tap 345kV 80307 Del Sol - 80225 Cenizo | Zapata | SOUTH | 2027-12-01 | SOL | PV | 255.15 |  | 2020-10-07 | 2020-01-22 | 2020-04-08 | 2020-10-05 |  | No |  | No |  |  | Not Required
23INR0008 | Harley Hand Solar | SS Completed, FIS Started, No IA | HECTATE ENERGY HARLEY HAND SOLAR LLC | 11420 Sweetwater East 345kV | Nolan | WEST | 2028-05-01 | SOL | PV | 513.7 |  | 2019-12-12 | 2019-12-16 | 2020-03-11 | 2019-12-06 |  | No |  | No | Not Required | Not Required | Not Required
23INR0009 | Shaula III Solar | SS Completed, FIS Started, No IA | Shaula Energy Project III, LLC | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | DeWitt | SOUTH | 2025-12-24 | SOL | PV | 205.2 |  | 2020-01-13 | 2019-12-18 | 2020-03-11 | 2019-12-18 |  |  |  | No |  |  | Not Required
23INR0015 | Scarlet Solar | SS Completed, FIS Started, No IA | Innovative Solar 416, LLC | tap 345kV 23912 Ogallala - 23910 Windmill | Castro | PANHANDLE | 2025-08-26 | SOL | PV | 180 |  | 2020-09-16 | 2019-12-11 | 2020-03-06 | 2020-08-31 |  |  |  | No |  |  | Not Required
23INR0021 | Hornet Solar | SS Completed, FIS Completed, IA | Hornet Solar LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala | Swisher | PANHANDLE | 2025-08-31 | SOL | PV | 602.37 |  | 2020-05-15 | 2020-02-04 | 2020-04-29 | 2020-02-04 | 2021-10-06 | No | 2021-12-06 | Yes | Not Required | Not Required | Not Required | 2021-12-22 | 2023-09-28 | 2023-10-31 |  |  | 2024-06-17 | 2024-08-21
23INR0026 | Baker Branch Solar | SS Completed, FIS Completed, IA | Mockingbird Solar Center, LLC | tap 345kV 1692 Paris - 1690 Valley | Lamar | NORTH | 2026-05-31 | SOL | PV | 469.42 |  | 2020-04-09 | 2020-03-26 | 2020-06-04 | 2020-03-05 | 2023-10-30 |  | 2022-02-14 | Yes | Not Required | Not Required | Not Required | 2023-10-03 | 2023-10-30 | 2023-10-30 |  |  | 2024-04-01 | 2024-04-10
23INR0027 | Cachena Solar SLF | SS Completed, FIS Completed, IA | Clear Fork Creek Solar LLC | Tap 345KV 5133 Elm Creek - 5323 Old Hickory | Wilson | SOUTH | 2027-04-29 | SOL | PV | 600 |  | 2020-08-19 | 2020-05-01 | 2020-07-13 | 2020-08-17 | 2023-10-02 | No | 2021-11-23 | Yes | Not Required | Not Required | Not Required | 2021-11-29
23INR0029 | Cedar Bayou 5 (TEF - Due Diligence) | SS Completed, FIS Completed, IA | NRG Cedar Bayou 5 LLC | 40000 Cedar Bayou 345kV | Chambers | HOUSTON | 2027-12-15 | GAS | GT | 697 |  | 2020-03-31 | 2020-03-26 | 2020-06-04 | 2020-03-18 | 2025-05-30 | No | 2022-01-10 | Yes | 2021-03-17 | 2021-03-17 | 2024-06-07 | 2025-02-12
23INR0030 | Langer Solar | SS Completed, FIS Started, IA | Langer Solar LLC | tap 345kV 68040 Kopperl - 68091 Navarro | Bosque | NORTH | 2027-03-01 | SOL | PV | 249.8 |  | 2020-11-06 | 2020-06-03 | 2020-08-18 | 2020-10-30 |  | Yes | 2023-08-31 | Yes | Not Required | Not Required | Not Required | 2024-01-05
23INR0031 | Solace Solar | SS Completed, FIS Completed, IA | IP QUANTUM, LLC. | tap 345kV 1430 Graham - 1048 Tonkawas | Haskell | WEST | 2026-03-31 | SOL | PV | 321.64 |  | 2020-04-21 | 2020-04-22 | 2020-07-09 | 2020-04-03 | 2023-10-26 |  | 2024-01-30 | Yes | Not Required | Not Required | Not Required | 2024-06-07 | 2025-07-25 | 2025-07-24
23INR0035 | Starling Solar | SS Completed, FIS Started, IA | Starling Solar, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2028-01-28 | SOL | PV | 144 | COD | 2021-02-09 | 2020-06-26 | 2020-09-14 | 2021-01-22 |  |  | 2021-12-03 | Yes |  |  | Not Required | 2025-02-12
23INR0040 | Dori BQ Solar | SS Completed, FIS Started, IA | Sunnyside Energy, LLC | tap 138kV 47210 Holmes – 42680 Garden Villas | Harris | HOUSTON | 2027-08-30 | SOL | PV | 50.42 |  | 2021-02-10 | 2020-06-09 | 2020-08-18 | 2021-01-29 |  | No | 2022-12-01 | No | Not Required | Not Required | Not Required
23INR0044 | Parliament Solar | SS Completed, FIS Completed, IA | Parliament Solar LLC | Tap 345kV 44900 Zenith - 967 Gibbons Creek ckt 18 | Waller | HOUSTON | 2025-09-26 | SOL | PV | 484.56 |  | 2020-08-03 | 2020-06-19 | 2020-09-08 | 2020-06-08 | 2024-04-25 | No | 2022-05-26 | Yes | Not Required | Not Required | Not Required | 2024-01-24 | 2024-05-03 | 2024-05-03 |  |  | 2025-05-19 | 2025-06-02
23INR0045 | Caney Creek Solar | SS Completed, FIS Started, IA | HEP Aquamarine Holdings LLC | Tap 138kV 6829 Glen Pine - 6833 Explorer | Van Zandt | NORTH | 2027-06-21 | SOL | PV | 121.97 | Proj Name | 2016-02-23 | 2020-09-25 | 2020-12-16 | 2021-02-22 |  | No | 2021-12-29 | Yes | Not Required | Not Required | Not Required | 2021-12-13
23INR0047 | Charger Solar | SS Completed, FIS Completed, IA | AP Solar 4, LLC | tap 345kV 8249 Angstrom – 5915 STP | Refugio | COASTAL | 2026-08-31 | SOL | PV | 397.15 |  | 2020-07-29 | 2020-06-19 | 2020-09-08 | 2020-06-07 | 2025-09-22 | No | 2021-06-05 | Yes |  |  | Not Required | 2022-04-04
23INR0048 | Equinox Storage | SS Completed, FIS Started, No IA | Invenergy Storage Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2029-02-15 | OTH | BA | 103 |  | 2021-03-23 | 2020-06-26 | 2020-09-14 | 2021-03-12 |  |  |  | No
23INR0054 | Tanglewood Solar | SS Completed, FIS Completed, IA | Brazoria Solar, LLC | 345kV Seabreeze Substation | Brazoria | COASTAL | 2025-12-15 | SOL | PV | 250.96 | COD | 2021-01-15 | 2020-07-10 | 2020-09-28 | 2020-11-24 | 2024-06-03 | Yes | 2022-11-01 | Yes | Not Required | Not Required | Not Required | 2023-02-10 | 2024-11-07 | 2024-11-07 |  |  | 2025-08-05 | 2025-08-20
23INR0055 | Tabor Solar | SS Completed, FIS Started, No IA | Quanah Solar LLC | Tap 345kV 60504 Tesla - 61001 Jim Treece | Hardeman | WEST | 2027-04-16 | SOL | PV | 506.4 |  | 2020-08-31 | 2020-09-02 | 2020-11-19 | 2020-07-07 |  | No |  | No |  |  | Not Required
23INR0056 | Caliche Mound Solar | SS Completed, FIS Started, IA | Tierra Blanco Solar LLC | tap 345kV 23906 AJSwope - 23910 Windmill | Deaf Smith | PANHANDLE | 2026-10-10 | SOL | PV | 406.6 |  | 2020-08-27 | 2020-07-24 | 2020-09-08 | 2020-07-07 |  |  | 2023-10-12 | Yes |  |  | Not Required | 2025-02-12
23INR0057 | Duffy Solar | SS Completed, FIS Started, IA | VDA Solar Texas 1 LLC | Tap 345kV WAP to STP CKT39 (PTI# 5915-44000 CKT 39) | Matagorda | COASTAL | 2027-12-31 | SOL | PV | 502.46 |  | 2021-02-05 | 2020-09-11 | 2020-11-19 | 2021-02-04 |  | Yes | 2023-04-12 | Yes |  |  | Not Required | 2023-05-24
23INR0058 | Erin Solar | SS Completed, FIS Completed, IA | Erin Solar LLC | 44040 Bailey 345 kV | Wharton | SOUTH | 2027-11-30 | SOL | PV | 202.5 |  | 2021-02-15 | 2020-07-24 | 2020-10-08 | 2021-01-26 | 2022-05-24 | No | 2023-03-22 | No | Not Required | Not Required | Not Required
23INR0059 | Briggs Solar | SS Completed, FIS Started, IA | IP Quantum III, LLC | tap 345kV 60515 Clear Crossing - 60507 Pendulo | Haskell | WEST | 2027-09-15 | SOL | PV | 323.7 |  | 2021-03-15 | 2020-08-04 | 2020-10-28 | 2021-03-04 |  |  | 2025-03-15 | Yes | Not Required | Not Required | Not Required | 2025-03-24
23INR0061 | Noria Solar DCC | SS Completed, FIS Started, IA | Noria Hondo Solar, LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2027-10-01 | SOL | PV | 145 | COD | 2021-03-15 | 2020-08-04 | 2020-10-28 | 2021-03-10 |  |  | 2022-10-12 | Yes |  |  | Not Required | 2025-02-12
23INR0062 | Noria Storage | SS Completed, FIS Started, IA | Noria Hondo Solar, LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2027-10-01 | OTH | BA | 75 | COD | 2021-04-01 | 2020-08-04 | 2020-10-28 | 2021-03-30 |  |  | 2022-10-12 | Yes | Not Required | Not Required |  | 2023-04-12
23INR0066 | Accalia Point Solar | SS Completed, FIS Started, No IA | Accalia Point Solar LLC | Tap 345kV 8383 North Edingburg – 79501 Kingfisher | Cameron | COASTAL | 2029-05-31 | SOL | PV | 190.5 |  | 2021-02-10 | 2020-10-23 | 2021-01-12 | 2021-01-27 |  | No |  | No |  |  | Not Required
23INR0070 | Chillingham Solar | SS Completed, FIS Completed, IA | Chillingham Solar LLC | 3687 Bell County East 345kV | Bell | NORTH | 2025-10-31 | SOL | PV | 352.39 |  | 2020-09-02 | 2020-08-04 | 2020-10-28 | 2020-08-26 | 2024-01-26 | No | 2022-02-04 | Yes | Not Required | Not Required | Not Required | 2024-01-30 | 2024-01-30 | 2024-01-30 |  |  | 2024-08-19 | 2024-09-04
23INR0071 | BRP Volans BESS | SS Completed, FIS Started, No IA | BRP Volans BESS LLC | 11189 Quarry Field SW - 1074 Wink 138kV | Winkler | WEST | 2027-12-01 | OTH | BA | 206.88 |  | 2020-08-26 | 2020-08-04 | 2020-10-28 | 2020-08-24 |  | No |  | No
23INR0073 | BRP Galan BESS | SS Completed, FIS Started, No IA | BRP Galan BESS LLC | 5007 Alamo One 138kV | Bexar | SOUTH | 2027-12-01 | OTH | BA | 75.97 |  | 2020-08-20 | 2020-08-04 | 2020-10-28 | 2020-08-17 |  |  |  | No
23INR0074 | BRP Ampato BESS | SS Completed, FIS Started, No IA | BRP Ampato BESS LLC | 10002 NS Crane Switch 138kV | Crane | WEST | 2027-12-01 | OTH | BA | 121.56 |  | 2020-08-26 | 2020-08-04 | 2020-10-28 | 2020-08-24 |  |  |  | No
23INR0075 | BRP Rhine BESS | SS Completed, FIS Started, No IA | BRP Rhine BESS LLC | Tap 345kV 11188 QUARRYFLD - 11010 WOLF | Ward | WEST | 2028-12-01 | OTH | BA | 206.89 |  | 2020-09-22 | 2020-08-04 | 2020-11-02 | 2020-09-17 |  |  |  | No
23INR0077 | Cachena Storage SLF | SS Completed, FIS Started, No IA | Clear Fork Creek Solar LLC | Tap 345KV 5133 Elmcreek - 5323 Old Hickory | Wilson | SOUTH | 2027-04-29 | OTH | BA | 0 |  | 2020-08-21 | 2020-08-21 | 2020-10-16 | 2020-08-17 |  |  |  | No | Not Required | Not Required
23INR0078 | Shaw Solar | SS Completed, FIS Completed, IA | Rio Lago Solar, LLC | Tap 138kV 7146 Verde Creek - 7438 Bandera | Bandera | SOUTH | 2026-04-29 | SOL | PV | 124.65 |  | 2021-05-21 | 2020-10-23 | 2021-01-12 | 2021-05-11 | 2025-03-12 | No | 2023-02-17 | Yes | Not Required | Not Required | Not Required | 2025-03-26 | 2025-04-30 | 2025-04-30
23INR0080 | Soda Lake Solar 2 SLF | SS Completed, FIS Started, IA | Crane II Solar Electric, LLC | 138 kV Soda Lake (#76026) | Crane | WEST | 2027-12-01 | SOL | PV | 201.74 |  | 2020-09-08 | 2020-09-11 | 2020-11-30 | 2020-08-24 |  |  | 2022-03-23 | No |  |  | Not Required
23INR0082 | Bottom Grass Solar | SS Completed, FIS Started, IA | Bottom Grass Solar Project, LLC | tap 345 kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2028-03-01 | SOL | PV | 508.61 |  | 2020-10-19 | 2020-11-05 | 2021-02-02 | 2020-10-21 |  |  | 2023-06-29 | No |  |  | Not Required
23INR0083 | Bottom Grass BESS | SS Completed, FIS Started, IA | Bottom Grass Solar Project, LLC | tap 345 kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2028-03-01 | OTH | BA | 202.21 |  | 2020-10-19 | 2020-11-05 | 2021-02-02 | 2020-10-21 |  |  | 2023-06-29 | No | Not Required | Not Required
23INR0084 | Lavaca Bay Solar | SS Completed, FIS Completed, IA | Lavaca Bay Solar Project, LLC | tap 345 kV REFUGE 42400 - JONES CREEK 47532 ckt 27 | Matagorda | COASTAL | 2026-12-31 | SOL | PV | 243.46 |  | 2021-03-05 | 2020-09-11 | 2020-11-19 | 2021-03-05 | 2022-03-21 | Yes | 2022-06-15 | Yes | Not Required | Not Required | Not Required | 2025-02-17
23INR0086 | Hanson Solar | SS Completed, FIS Started, IA | Hanson Solar, LLC | tap 345kV 1444 Brown - 11406 Central Bluff | Coleman | WEST | 2027-04-17 | SOL | PV | 398.83 |  | 2021-03-30 | 2020-10-23 | 2021-02-02 | 2021-03-25 |  |  | 2023-09-20 | Yes |  |  | Not Required | 2025-02-12
23INR0087 | Kinenos Solar | SS Completed, FIS Started, No IA | Encino del Sol Energy, LLC | tap 345kV 8905 North Edinburg - 8455 Lon Hill | Brooks | SOUTH | 2026-12-31 | SOL | PV | 203.17 |  | 2020-08-28 | 2020-12-22 | 2021-03-10 | 2020-12-03 |  | No |  | No |  |  | Not Required
23INR0088 | Nockenut Springs Solar 1 | SS Completed, FIS Completed, IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Guadalupe | SOUTH | 2029-06-05 | SOL | PV | 203.17 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 | 2025-07-07 | Yes | 2023-11-17 | No |  |  | Not Required
23INR0089 | Donegal Solar | SS Completed, FIS Started, IA | Greenalia Solar Power Donegal, LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2028-03-01 | SOL | PV | 201.68 |  | 2020-10-08 | 2020-10-07 | 2020-12-28 | 2020-09-11 |  |  | 2022-07-25 | Yes | Not Required | Not Required | Not Required | 2025-05-14
23INR0090 | Iguala Solar | SS Completed, FIS Started, IA | Iguala Solar LLC | tap 345kV 5915 STP - 8249 Angstrom | Victoria | SOUTH | 2027-09-01 | SOL | PV | 250 | COD | 2021-06-11 | 2020-10-07 | 2020-12-28 | 2021-06-07 |  | Yes | 2025-07-29 | No |  |  | Not Required
23INR0091 | Cascade Solar | SS Completed, FIS Completed, IA | Cascade Solar Energy, LLC | 43180 SAVANAH 345 kV | Brazoria | COASTAL | 2026-09-01 | SOL | PV | 171 |  | 2021-05-05 | 2021-02-09 | 2021-05-06 | 2021-04-28 | 2025-09-02 | No | 2023-04-17 | Yes | Not Required | Not Required | Not Required | 2023-12-07
23INR0093 | Alila Solar | SS Completed, FIS Completed, IA | Electra Energy Project, LLC | 8249 Angstrom 345kV | San Patricio | COASTAL | 2027-05-08 | SOL | PV | 256.5 |  | 2020-10-19 | 2020-10-07 | 2020-12-30 | 2020-09-11 | 2023-03-16 | No | 2023-01-03 | Yes |  |  | Not Required | 2025-02-12
23INR0094 | BRP Pyxis BESS | SS Completed, FIS Started, No IA | BRP Pyxis BESS LLC | tap 138kV 1009 Yucca - 11197 Sand Tank Pod | Ward | WEST | 2028-12-01 | OTH | BA | 206.87 | COD | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No
23INR0101 | Atria Solar | SS Completed, FIS Completed, No IA | Atria Energy Project, LLC | 40770 Hacher 138kV | Chambers | HOUSTON | 2025-12-30 | SOL | PV | 112.4 |  | 2020-10-19 | 2020-10-23 | 2021-01-12 | 2020-09-28 | 2021-12-15 |  |  | No |  |  | Not Required
23INR0104 | BRP Kamet BESS | SS Completed, FIS Started, No IA | BRP Kamet BESS LLC | Andrews North – McKenzie Draw Switch 138 kV | Andrews | WEST | 2025-12-01 | OTH | BA | 202.46 |  | 2020-09-28 | 2020-10-07 | 2020-12-30 | 2020-09-23 |  | No |  | No
23INR0111 | PHOTON SOLAR 3 SLF | SS Completed, FIS Completed, IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2025-10-31 | SOL | PV | 109.99 |  | 2020-12-03 | 2020-10-23 | 2021-02-02 | 2020-11-24 | 2022-11-28 | No | 2021-10-01 | Yes | Not Required | Not Required | Not Required | 2021-11-05 | 2023-01-27 | 2023-01-27 |  |  | 2024-05-17 | 2024-10-02
23INR0115 | BRP Pobeda BESS | SS Completed, FIS Started, No IA | BRP Pobeda BESS LLC | 44645 Singleton 345kV | Grimes | NORTH | 2028-12-31 | OTH | BA | 301.41 |  | 2020-11-06 | 2020-11-18 | 2021-02-08 | 2020-10-27 |  |  |  | No
23INR0116 | Cantaloupe Solar | SS Completed, FIS Started, IA | Saragosa Del Sol Energy, LLC | 60716 Saragosa 138kV | Reeves | WEST | 2028-07-01 | SOL | PV | 307 |  | 2020-10-28 | 2020-12-22 | 2021-03-09 | 2020-12-01 |  |  | 2024-04-23 | Yes | Not Required | Not Required | Not Required | 2025-05-28
23INR0118 | Blevins Solar | SS Completed, FIS Completed, IA | Blevins Solar, LLC | Tap Bellfalls Switch (3404) – Lake Creek Switch (3409) | Falls | NORTH | 2025-10-30 | SOL | PV | 271.58 |  | 2021-02-18 | 2021-02-04 | 2021-04-19 | 2021-02-12 | 2024-06-24 |  | 2023-06-17 | Yes | Not Required | Not Required | Not Required | 2024-07-31 | 2024-08-12 | 2024-08-12 |  |  | 2025-03-11 | 2025-03-24
23INR0119 | Blevins Storage | SS Completed, FIS Completed, IA | Blevins Solar, LLC | Tap Bellfalls Switch (3404) – Lake Creek Switch (3409) | Falls | NORTH | 2025-10-29 | OTH | BA | 181.33 | COD | 2021-02-19 | 2021-02-04 | 2021-04-19 | 2021-02-12 | 2024-06-24 |  | 2023-06-17 | Yes | Not Required | Not Required |  | 2024-07-31 | 2024-08-12 | 2024-08-12 |  |  | 2025-03-12 | 2025-04-18
23INR0123 | Vaca Storage | SS Completed, FIS Started, No IA | Long Mount Storage, LLC | 138kV 8723 Cangrejo | Calhoun | COASTAL | 2029-07-01 | OTH | BA | 101 |  | 2022-06-01 | 2021-03-26 | 2021-06-14 | 2022-05-11 |  | No |  | No | Not Required | Not Required
23INR0126 | Sigma Storage | SS Completed, FIS Started, No IA | AES Distributed Energy, Inc | 40460 Deepwater 138kV | Harris | HOUSTON | 2029-10-01 | OTH | BA | 408.4 |  | 2022-02-17 | 2021-05-11 | 2021-07-30 | 2022-02-04 |  | No |  | No | [6 empty] | 2028-05-01 | 2029-05-01
23INR0127 | Beacon Storage | SS Completed, FIS Started, No IA | AES Distributed Energy, Inc | 40450 Deepwater 345kV | Harris | HOUSTON | 2029-10-01 | OTH | BA | 408.7 |  | 2022-03-23 | 2021-05-05 | 2021-07-27 | 2022-02-28 |  | No |  | No | [6 empty] | 2028-05-01 | 2029-05-01
23INR0132 | BRP Bonete BESS | SS Completed, FIS Started, No IA | BRP Bonete BESS LLC | 8951 Stewart Road 138kV | Hidalgo | SOUTH | 2027-12-01 | OTH | BA | 201.13 |  | 2020-11-17 | 2020-12-03 | 2021-02-16 | 2020-11-18 |  | No |  | No
23INR0135 | Elbus BESS | SS Completed, FIS Started, No IA | BRP Elbus BESS LLC | 9075 Lytton 138kV | Caldwell | SOUTH | 2027-12-01 | OTH | BA | 200.99 |  | 2020-11-30 | 2020-12-03 | 2021-02-18 | 2020-11-25 |  |  |  | No
23INR0137 | BRP Diran BESS | SS Completed, FIS Started, IA | BRP Diran BESS LLC | 43190 South Lane City 138kV | Wharton | SOUTH | 2028-01-31 | OTH | BA | 100.63 |  | 2020-11-30 | 2020-12-03 | 2021-02-18 | 2020-11-25 |  | No | 2025-01-07 | Yes | Not Required | Not Required |  | 2025-07-21
23INR0139 | BRP Passu BESS | SS Completed, FIS Started, No IA | BRP Passu BESS LLC | 6111 Riley 345kV | Wilbarger | WEST | 2028-12-31 | OTH | BA | 301.82 |  | 2020-11-30 | 2020-12-03 | 2021-02-19 | 2020-11-27 |  | No |  | No
23INR0140 | Seine BESS | SS Completed, FIS Started, IA | BRP Seine BESS LLC | 60500 Edith Clarke 345kV | Foard | WEST | 2027-12-01 | OTH | BA | 301.19 |  | 2020-11-30 | 2020-12-03 | 2021-02-19 | 2020-11-27 |  | No | 2024-12-01 | Yes | Not Required | Not Required
23INR0143 | Sepik BESS | SS Completed, FIS Started, No IA | BRP Sepik BESS LLC | tap 138kV 11342 Loraine South – 10050 Ranger Camp | Mitchell | WEST | 2028-03-01 | OTH | BA | 204.96 |  | 2020-12-08 | 2020-12-22 | 2021-03-15 | 2020-12-01 |  |  |  | No
23INR0150 | Cradle Solar | SS Completed, FIS Completed, IA | Cradle Solar LLC | tap 345kV 42500 Dow - 43035 Oasis ckt 18 | Brazoria | COASTAL | 2027-02-22 | SOL | PV | 200.85 | COD | 2021-03-26 | 2021-02-04 | 2021-04-21 | 2021-03-15 | 2025-03-14 | No | 2023-03-15 | Yes |  |  | Not Required | 2025-02-12 | 2025-04-30 | 2025-04-30
23INR0160 | Grimes County Solar | SS Completed, FIS Completed, IA | Grimes County Solar Project, LLC | 2 Keith Switch 138kV | Grimes | NORTH | 2025-10-31 | SOL | PV | 211.25 | COD | 2020-12-16 | 2021-01-26 | 2021-04-12 | 2020-12-16 | 2024-06-17 | No | 2022-06-22 | Yes | Not Required | Not Required | Not Required | 2022-09-21 | 2024-07-11 | 2024-08-01 |  |  | 2025-02-20 | 2025-03-20
23INR0162 | Redonda Solar | SS Completed, FIS Started, IA | J&R Power DevCo, LLC | tap 345kV 80307 Del Sol - 80225 Cenizo | Zapata | SOUTH | 2026-12-30 | SOL | PV | 253.21 |  | 2021-08-19 | 2021-01-25 | 2021-04-12 | 2021-08-11 |  |  | 2021-12-28 | Yes | Not Required | Not Required | Not Required | 2022-04-27
23INR0163 | Ringtail Ridge Storage | SS Completed, FIS Started, No IA | KCE TX 26, LLC | 7150 Kendall 138kV | Kendall | SOUTH | 2028-05-23 | OTH | BA | 100.57 |  | 2021-01-08 | 2021-01-25 | 2021-04-16 | 2020-12-29 |  |  |  | No
23INR0164 | Steppe Reserve Storage | SS Completed, FIS Started, No IA | KCE TX 25, LLC | 8283 Asherton 138 kV | Dimmit | SOUTH | 2028-01-01 | OTH | BA | 51.9 |  | 2021-01-08 | 2021-01-25 | 2021-04-16 | 2020-12-29 |  |  |  | No
23INR0168 | Charolais Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 44000 W A Parish - 5915 STP | Matagorda | COASTAL | 2026-12-15 | OTH | BA | 150 |  | 2021-06-25 | 2021-02-09 | 2021-05-06 | 2021-06-11 |  |  |  | No
23INR0171 | Goodalta Solar | SS Completed, FIS Started, No IA | GoodAlta Power Center LLC | tap 138kV 3127 Trinidad - 212 Winkler | Navarro | NORTH | 2027-09-20 | SOL | PV | 221.36 |  | 2021-08-03 | 2021-01-25 | 2021-04-12 | 2021-01-07 |  | No |  | No |  |  | Not Required
23INR0174 | Campsey Wind | SS Completed, FIS Completed, No IA | RWE | tap 345kV 1458 Cobb - 1429 Jacksboro | Jack | NORTH | 2027-12-15 | WIN | WT | 238.3 |  | 2021-09-28 | 2021-02-09 | 2021-05-06 | 2021-09-01 | 2025-05-21 | No |  | No |  |  | Not Required
23INR0180 | Jackalope Solar | SS Completed, FIS Completed, IA | Peacock Energy Project, LLC | 8173 Gibbs 138kV | San Patricio | COASTAL | 2025-11-30 | SOL | PV | 155.68 |  | 2021-01-29 | 2021-02-09 | 2021-05-06 | 2021-02-02 | 2021-11-18 |  | 2021-09-30 | Yes | Not Required | Not Required | Not Required | 2021-10-18 | 2022-10-24 | 2023-10-19 |  |  | 2024-07-30 | 2024-09-19
23INR0181 | Starling Storage | SS Completed, FIS Completed, IA | Starling Storage, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2027-05-15 | OTH | BA | 63.6 |  | 2021-10-20 | 2021-01-25 | 2021-04-16 | 2021-10-07 | 2023-07-31 | No | 2023-08-03 | Yes | Not Required | Not Required |  | 2025-02-12
23INR0183 | Pradera Storage | SS Completed, FIS Started, No IA | Pradera Storage, LLC | tap 345 kV Lobo 80219 - Fowlerton 5709 ckt #2 | Webb | SOUTH | 2027-03-31 | OTH | BA | 153.11 |  | 2021-10-18 | 2021-01-25 | 2021-04-16 | 2021-10-13 |  |  |  | No
23INR0187 | Leitrim 1 Solar | SS Completed, FIS Started, No IA | Leitsol LLC | tap 138kV 3522 Hillsboro - 3546 Whitney | Hill | NORTH | 2027-04-26 | SOL | PV | 98.44 |  | 2021-03-23 | 2021-01-26 | 2021-04-12 | 2021-03-18 |  | No |  | No |  |  | Not Required
23INR0194 | Pequin Energy Storage | SS Completed, FIS Started, No IA | Pequin Energy Storage, LLC | 39500 TN West Columbia 138kV | Brazoria | COASTAL | 2027-09-13 | OTH | BA | 103.4 |  | 2021-06-29 | 2021-01-25 | 2021-04-16 | 2021-06-14 |  |  |  | No
23INR0200 | Paradiso BESS | SS Completed, FIS Started, IA | VESI 13 | 8203 Pleasanton 138kV | Atascosa | SOUTH | 2028-03-15 | OTH | BA | 100.92 |  | 2021-09-03 | 2021-03-01 | 2021-05-13 | 2021-08-20 |  | No | 2025-04-18 | Yes | Not Required | Not Required
23INR0202 | Erath County Solar | SS Completed, FIS Started, IA | Erath County Solar, LLC | tap 345kV 68020 Romney1E - 68030 KopperlW | Erath | NORTH | 2028-09-01 | SOL | PV | 207.4 | COD | 2021-01-20 | 2021-03-08 | 2021-05-28 | 2021-03-06 |  | Yes | 2023-06-01 | Yes |  |  | Not Required | 2025-02-12
23INR0204 | GALVANIC BESS | SS Completed, FIS Started, No IA | CED Development Inc | 8252 Bracketville 138kV | Kinney | SOUTH | 2026-12-30 | OTH | BA | 100 |  | 2022-06-15 | 2021-02-09 | 2021-05-06 | 2022-05-13 |  |  |  | No
23INR0205 | SUNSETTER BESS | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2027-11-30 | OTH | BA | 100 |  | 2022-05-27 | 2021-02-09 | 2021-05-06 | 2022-05-13 |  |  |  | No
23INR0206 | PEREGRINE BESS | SS Completed, FIS Started, No IA | CED Development Inc. | tap 345kV 8624 Grissom - 8164 Coleto Creek | Goliad | SOUTH | 2027-07-01 | OTH | BA | 150 |  | 2022-06-15 | 2021-02-10 | 2021-05-06 | 2022-05-13 |  |  |  | No
23INR0207 | El Patrimonio Solar | SS Completed, FIS Completed, IA | Heritage Solar, LLC | tap 138kV 5429 Trumbo - 5260 Leon Creek | Bexar | SOUTH | 2027-04-29 | SOL | PV | 152.32 |  | 2022-03-02 | 2021-03-16 | 2021-05-28 | 2021-11-23 | 2024-10-17 | No | 2023-12-11 | No |  |  | Not Required
23INR0209 | Outpost Storage | SS Completed, FIS Started, No IA | Hecate Energy Outpost Storage LLC | Tap 345kV 80219 Lobo - 5709 Fowlerton | Webb | SOUTH | 2028-03-01 | OTH | BA | 508.1 |  | 2021-02-15 | 2021-03-01 | 2021-05-13 | 2021-02-15 |  |  |  | No
23INR0211 | Rosscommon Solar | SS Completed, FIS Started, No IA | Roscsol, LLC | tap 138kV 1691 Valley Switch - 1776 Paris Switch | Lamar | NORTH | 2027-04-19 | SOL | PV | 91 |  | 2021-01-30 | 2021-03-01 | 2021-05-13 | 2021-02-01 |  |  |  | No |  |  | Not Required
23INR0214 | Harley Hand Storage | SS Completed, FIS Started, No IA | Hecate Energy Harley Hand Solar LLC | 11420 Sweetwater East 345kV | Nolan | WEST | 2028-05-01 | OTH | BA | 509 |  | 2022-04-04 | 2021-03-01 | 2021-05-13 | 2022-03-22 |  |  |  | No | Not Required | Not Required
23INR0215 | Big River Solar | SS Completed, FIS Started, No IA | Rio Grande River Solar LLC | tap 138kV 8299 Zapata - 8957 Lopeno4A | Zapata | SOUTH | 2028-12-31 | SOL | PV | 104.35 |  | 2021-04-09 | 2021-05-04 | 2021-07-27 | 2021-04-15 |  |  |  | No |  |  | Not Required
23INR0222 | Sunbelt Solar | SS Completed, FIS Started, No IA | Rose Hill Solar LLC | tap 138kV 6902 Talty - 6801 Patton | Kaufman | NORTH | 2026-12-31 | SOL | PV | 81.5 |  | 2021-10-05 | 2021-03-16 | 2021-05-28 | 2021-09-30 |  |  |  | No |  |  | Not Required
23INR0224 | Morning Glory Solar | SS Completed, FIS Started, No IA | Armadillo Solar, LLC | tap 345kV 7077 Amos Creek - 76009 Twin Buttes | Tom Green | WEST | 2026-03-31 | SOL | PV | 122.4 |  | 2022-05-31 | 2021-06-16 | 2021-09-07 | 2022-05-17 |  |  |  | No |  |  | Not Required
23INR0225 | MRG GOODY SOLAR | SS Completed, FIS Completed, IA | MRG GOODY SOLAR PROJECT, LLC | Tap 138 kV Toco Switch (#1700) – Paris Switch (#1693) | Lamar | NORTH | 2026-05-02 | SOL | PV | 170.82 |  | 2022-04-04 | 2021-03-16 | 2021-06-11 | 2022-03-22 | 2025-06-17 | No | 2023-11-07 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2025-07-31 | 2025-07-31
23INR0227 | Maleza Solar II | SS Completed, FIS Started, No IA | Brush Solar, LLC | tap Blue – Hillje 345 kv Ckt.#27 | Wharton | SOUTH | 2026-11-09 | SOL | PV | 254.94 | COD | 2021-05-24 | 2021-04-06 | 2021-06-24 | 2021-05-19 |  |  |  | No |  |  | Not Required
23INR0228 | Hiru Solar | SS Completed, FIS Started, No IA | Hecate Energy Hazel LLC | Tap 345kV 6111 Riley - 1730 West Krum ckt 1 | Clay | WEST | 2029-04-01 | SOL | PV | 603.7 |  | 2021-09-08 | 2021-04-21 | 2021-07-14 | 2021-08-30 |  | No |  | No | Not Required | Not Required | Not Required
23INR0229 | CH Solterra LLC | SS Completed, FIS Started, No IA | CH Solterra LLC | Tap 138kV 11796 White Oak POI - 11797 Brinker POI | Hopkins | NORTH | 2026-09-30 | SOL | PV | 143 |  | 2021-03-17 | 2021-03-19 | 2021-06-11 | 2021-03-18 |  | No |  | No | Not Required | Not Required | Not Required
23INR0231 | Rocinante Solar | SS Completed, FIS Started, IA | Brush Country Solar Project, LLC | tap 138kV 7595 Deer Creek - 7621 Nixon | Gonzales | SOUTH | 2026-11-01 | SOL | PV | 95.29 |  | 2021-04-28 | 2021-04-22 | 2021-07-14 | 2021-04-22 |  | No | 2022-04-25 | Yes | Not Required | Not Required | Not Required | 2025-09-08
23INR0232 | Rocinante BESS | SS Completed, FIS Started, IA | Brush Country Solar Project, LLC | tap 138kV 7595 Deer Creek - 7621 Nixon | Gonzales | SOUTH | 2026-11-01 | OTH | BA | 33.17 |  | 2021-04-28 | 2021-04-22 | 2021-07-14 | 2021-04-22 |  | No | 2022-04-25 | Yes
23INR0233 | Earthwise Solar | SS Completed, FIS Started, No IA | Quanah Solar 2 | Tap 345kV 60504 Tesla - 61001 Jim Treece | Hardeman | WEST | 2026-12-31 | SOL | PV | 370.5 |  | 2022-02-23 | 2022-03-14 | 2022-06-09 | 2022-02-25 |  |  |  | No | Not Required | Not Required | Not Required
23INR0235 | Hoyte Solar | SS Completed, FIS Started, IA | Milano Solar LLC | (3707) Cannon Switch 138kV | Milam | SOUTH | 2027-04-15 | SOL | PV | 206.75 |  | 2021-04-02 | 2021-04-01 | 2021-07-02 | 2021-03-25 |  | No | 2022-10-14 | Yes | Not Required | Not Required | Not Required | 2025-02-13
23INR0237 | Big River BESS | SS Completed, FIS Started, No IA | Rio Grande River Solar LLC | tap 138kV 8299 Zapata - 8957 Lopeno4A | Zapata | SOUTH | 2028-12-31 | OTH | BA | 51.26 |  | 2021-04-09 | 2021-05-04 | 2021-07-27 | 2021-04-15 |  |  |  | No
23INR0244 | Tiger Solar | SS Completed, FIS Started, IA | Vaca Del Sol, LLC | 68004 PHANTOM HILL 345KV | Jones | WEST | 2027-06-30 | SOL | PV | 255 |  | 2021-04-21 | 2021-04-29 | 2021-07-22 | 2021-04-29 |  | Yes | 2024-10-30 | Yes | Not Required | Not Required | Not Required | 2025-02-12
23INR0248 | Limewood Storage | SS Completed, FIS Started, IA | Limewood Bell Renewables LLC | 3420 Temple Pecan Creek 138kV | Bell | NORTH | 2028-12-29 | OTH | BA | 50 |  | 2021-11-03 | 2021-04-30 | 2021-07-22 | 2021-10-06 |  | No | 2023-02-22 | Yes | Not Required | Not Required |  | 2025-05-22
23INR0249 | Limewood Solar | SS Completed, FIS Completed, IA | Limewood Bell Renewables LLC | 3420 Temple Pecan Creek 138kV | Bell | NORTH | 2026-03-02 | SOL | PV | 204.6 |  | 2021-11-03 | 2021-04-30 | 2021-07-22 | 2021-10-06 | 2025-03-14 | No | 2023-02-22 | Yes | Not Required | Not Required | Not Required | 2025-02-13 | 2025-05-01 | 2025-05-01
23INR0261 | Dodd Solar I | SS Completed, FIS Started, IA | Forest Grove Solar LLC | Tap 138kV 6951 Eustace Southeast Switch – 3131 Forest Grove Switch | Henderson | NORTH | 2028-06-05 | SOL | PV | 201.8 |  | 2022-04-12 | 2021-06-24 | 2021-09-20 | 2022-04-04 |  |  | 2025-02-08 | No |  |  | Not Required
23INR0266 | Langer Storage | SS Completed, FIS Started, IA | Langer Solar, LLC | tap 345kV 68040 Kopperl - 68091 Navarro | Bosque | NORTH | 2027-03-01 | OTH | BA | 61.53 |  | 2022-03-22 | 2021-05-10 | 2021-07-30 | 2022-02-25 |  | No | 2025-05-08 | Yes | Not Required | Not Required |  | 2025-07-15
23INR0272 | BRP Aras BESS | SS Completed, FIS Started, No IA | BRP Aras BESS LLC | 76595 North McCamey 138kV | Upton | WEST | 2028-12-01 | OTH | BA | 303.59 |  | 2021-05-27 | 2021-05-31 | 2021-08-19 | 2021-05-10 |  |  |  | No | Not Required | Not Required
23INR0273 | Poco Trail Solar | SS Completed, FIS Started, No IA | Eastern Trail Solar Center, LLC | Tap 345kV 6101 Riley - 1422 Bowman Byrd Road Switch | Wilbarger | WEST | 2027-05-01 | SOL | PV | 438.75 |  | 2021-06-02 | 2021-09-14 | 2021-11-30 | 2021-07-12 |  | No |  | No | Not Required | Not Required | Not Required
23INR0274 | BRP Parana BESS | SS Completed, FIS Started, No IA | BRP Parana BESS | 7178 Marion 138kV | Guadalupe | SOUTH | 2028-12-31 | OTH | BA | 303.67 |  | 2021-06-01 | 2021-05-31 | 2021-08-19 | 2021-05-10 |  |  |  | No | Not Required | Not Required
23INR0275 | BRP Nile BESS | SS Completed, FIS Started, No IA | BRP Nile BESS LLC | 80220 Cenizo 345kV | Webb | SOUTH | 2027-12-01 | OTH | BA | 202.34 |  | 2021-06-01 | 2021-05-31 | 2021-08-19 | 2021-05-10 |  |  |  | No
23INR0278 | Tucana BESS | SS Completed, FIS Completed, No IA | BRP Tucana BESS LLC | 1157 Andrews County South 138kV | Andrews | WEST | 2028-03-01 | OTH | BA | 201.3 |  | 2021-06-01 | 2021-06-03 | 2021-08-19 | 2021-05-10 | 2025-06-18 | No |  | No
23INR0279 | Trivor BESS | SS Completed, FIS Started, No IA | BRP Trivor BESS LLC | 1272 Fullerton 138kV | Andrews | WEST | 2028-03-01 | OTH | BA | 205.46 |  | 2021-06-01 | 2021-06-03 | 2022-03-15 | 2021-05-10 |  | No |  | No
23INR0283 | Kota Battery | SS Completed, FIS Started, No IA | Kota Storage, LLC | 23900 Alibates 345kV | Carson | PANHANDLE | 2028-10-31 | OTH | BA | 200.8 |  | 2021-06-02 | 2021-06-07 | 2021-08-27 | 2021-06-02 |  |  |  | No
23INR0284 | Las Moras Battery | SS Completed, FIS Started, No IA | Las Moras Storage, LLC | 8252 Brackett 138kV | Kinney | SOUTH | 2029-07-01 | OTH | BA | 101 |  | 2021-06-01 | 2021-06-07 | 2021-08-27 | 2021-06-02 |  | No |  | No
23INR0286 | Dry Creek Solar I | SS Completed, FIS Completed, IA | OAK HILL SOLAR LLC | tap 345kV 3100 Martin Lake - 3105 Elkton (Dorsett 345kV Switching Station) | Rusk | NORTH | 2026-01-01 | SOL | PV | 201.06 |  | 2022-04-04 | 2021-08-18 | 2021-11-05 | 2022-03-30 | 2024-06-12 | No | 2023-11-02 | Yes | Not Required | Not Required | Not Required | 2024-10-29 | 2024-10-29 | 2024-10-29 |  |  | 2025-05-08 | 2025-05-19
23INR0289 | Skull Creek Solar | SS Completed, FIS Started, IA | Skull Creek Solar, LLC | Tap 138kV 3281 Tennessee Colony - 3499 Blackfoot Massey Lake Switch in TSP’s Pin Oak Switch - Long Lake Substation | Anderson | NORTH | 2027-05-16 | SOL | PV | 137.26 |  | 2022-01-10 | 2021-05-28 | 2021-08-19 | 2021-12-16 |  | No | 2024-05-20 | No | Not Required | Not Required | Not Required
23INR0290 | Zeya BESS | SS Completed, FIS Started, IA | BRP Zeya BESS LLC | 38740 Heights 138kV | Galveston | HOUSTON | 2026-12-01 | OTH | BA | 255.33 |  | 2021-06-02 | 2021-05-31 | 2022-03-09 | 2021-05-20 |  | No | 2023-01-20 | Yes | Not Required | Not Required |  | 2025-02-12
23INR0296 | Trojan Solar SLF | SS Completed, FIS Completed, IA | Compadre Solar, LLC | 11735 Cedar Elm Switch 345kV | Cooke | NORTH | 2026-05-05 | SOL | PV | 150.59 |  | 2021-06-03 | 2021-07-01 | 2021-09-22 | 2021-06-30 | 2025-03-31 | No | 2022-10-10 | Yes | Not Required | Not Required | Not Required | 2023-07-28 | 2025-07-17 | 2025-07-17
23INR0300 | Greater Bryant G Solar | SS Completed, FIS Completed, IA | Greater Bryant G Solar, LLC | 11165 Sloan Switch 138kV | Midland | WEST | 2026-09-16 | SOL | PV | 17.7 |  | 2021-06-09 | 2021-06-17 | 2021-09-01 | 2021-06-16 | 2025-04-09 | No | 2022-07-18 | Yes | Not Required | Not Required | Not Required | 2025-06-18
23INR0308 | Fowler Ranch Storage | SS Completed, FIS Started, No IA | Crane BESS, LLC | 76025 Castle Mountain 138kV | Crane | WEST | 2027-01-01 | OTH | BA | 26.07 |  | 2022-06-03 | 2021-06-21 | 2021-09-07 | 2022-05-18 |  |  |  | No
23INR0310 | Dunkel BESS | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners | 59156 Yellow House Canyon 115kV | Lubbock | PANHANDLE | 2027-11-02 | OTH | BA | 226.3 |  | 2022-06-10 | 2022-06-27 | 2022-09-22 | 2022-06-20 |  |  |  | No
23INR0312 | Hofbrau BESS | SS Completed, FIS Started, No IA | Momentum Hofbrau LLC | 6442 Redcreek 138kV | Tom Green | WEST | 2028-07-01 | OTH | BA | 180.72 |  | 2021-09-22 | 2021-09-22 | 2021-12-09 | 2021-09-22 |  | No |  | No
23INR0318 | Marcelina Storage | SS Completed, FIS Completed, No IA | Marcelina Solar, LLC | Tap 345 kV 5133 Elm Creek - 5901 San Miguel | Wilson | SOUTH | 2026-12-18 | OTH | BA | 203.21 |  | 2022-05-03 | 2021-08-09 | 2021-10-29 | 2022-04-22 | 2024-01-23 |  |  | No
23INR0324 | Lumberjack Storage | SS Completed, FIS Started, IA | EDP Renewables North America LLC | 138 kV Tap 3110 Stryker Creek - 3147 Troup | Cherokee | NORTH | 2029-11-01 | OTH | BA | 51.3 | COD | 2022-04-20 | 2021-08-12 | 2021-10-29 | 2022-04-06 |  | No | 2024-03-20 | No | Not Required | Not Required
23INR0330 | BRP Snowdon BESS | SS Completed, FIS Started, No IA | BRP SNOWDON BESS LLC | 23914 Tule Canyon Substation 345kV | Briscoe | PANHANDLE | 2028-12-01 | OTH | BA | 410.94 |  | 2021-09-15 | 2021-09-15 | 2021-11-29 | 2021-09-08 |  |  |  | No
23INR0331 | Orange Grove BESS | SS Completed, FIS Completed, IA | Talitha Energy Project, LLC | 5660 Orange Grove Switching Station 138 kV | Jim Wells | SOUTH | 2027-04-30 | OTH | BA | 61.39 |  | 2021-07-20 | 2021-07-15 | 2021-09-28 | 2021-07-15 | 2022-05-03 | No | 2022-11-30 | Yes | Not Required | Not Required |  | 2023-04-04
23INR0332 | Backwater Solar | SS Completed, FIS Started, No IA | Backwater Solar LLC | Tap 138 kV line from Spring (#684) - Leo(#685) | Cooke | NORTH | 2027-05-06 | SOL | PV | 80 |  | 2021-09-17 | 2021-08-24 | 2021-11-15 | 2021-08-24 |  |  |  | No |  |  | Not Required
23INR0334 | Liberty Senate Energy Storage 1 | SS Completed, FIS Started, No IA | Senate Solar LLC | 1445 Burwick 345kV | Jack | NORTH | 2027-10-27 | OTH | BA | 207.4 |  | 2021-09-16 | 2021-10-05 | 2021-12-08 | 2021-10-03 |  | No |  | No | Not Required | Not Required
23INR0335 | BRP Bachman BESS | SS Completed, FIS Started, No IA | BRP Bachman BESS LLC | 44040 BAILEY 345kV | Wharton | SOUTH | 2027-12-01 | OTH | BA | 411.04 |  | 2021-10-05 | 2021-10-05 | 2021-12-08 | 2021-09-14 |  |  |  | No
23INR0336 | Bypass Battery Storage | SS Completed, FIS Completed, IA | Bypass BESS LLC | 44000 W_A_P__POI5A 345 kV | Fort Bend | HOUSTON | 2025-12-15 | OTH | BA | 207.89 |  | 2022-02-18 | 2021-08-18 | 2021-11-05 | 2022-02-03 | 2025-04-07 | No | 2023-12-04 | Yes | Not Required | Not Required |  | 2024-01-09 | 2025-04-23 | 2025-04-23
23INR0340 | Larkspur Energy Storage | SS Completed, FIS Started, IA | Larkspur Energy Storage LLC | 71213 Benedum 138kV | Upton | WEST | 2027-05-05 | OTH | BA | 307.46 |  | 2021-07-30 | 2021-08-02 | 2021-10-25 | 2021-07-27 |  |  | 2022-02-28 | No | Not Required | Not Required
23INR0342 | Brizo BESS | SS Completed, FIS Started, IA | BRP Brizo BESS LLC | 138 kV Loop 463 Substation (#5680) | Victoria | SOUTH | 2027-12-01 | OTH | BA | 140.76 |  | 2021-10-05 | 2021-10-05 | 2021-12-22 | 2021-09-24 |  |  | 2025-03-27 | No | Not Required | Not Required
23INR0343 | Corazon Storage | SS Completed, FIS Completed, IA | Guajillo Energy Storage LLC | 80219 Lobo Substation 345kV | Webb | SOUTH | 2025-09-16 | OTH | BA | 204.8 |  | 2021-08-02 | 2021-08-09 | 2021-11-01 | 2021-07-27 | 2024-10-31 | No | 2021-12-21 | Yes | Not Required | Not Required |  | 2022-06-27 | 2024-10-31 | 2024-10-31 |  |  | 2025-05-29 | 2025-06-09
23INR0344 | Hermes Solar | SS Completed, FIS Completed, IA | Bell 1 Solar, LLC | Tap 345kV 3687 Bell County East Switch - 39950 TNP One Plant Ckt 2 | Bell | NORTH | 2025-12-30 | SOL | PV | 100.36 |  | 2022-06-14 | 2021-09-21 | 2021-12-09 | 2022-06-01 | 2024-04-19 | No | 2023-11-08 | Yes |  |  | Not Required | 2025-01-31 | 2025-01-31 | 2025-01-31
23INR0345 | Elmax Power Station | SS Completed, FIS Started, IA | Elmax Generating, LLC | Tap 138 kV Lake Houston (#40820) - Atascocita (#40130) ckt 66 | Harris | HOUSTON | 2028-07-05 | GAS | GT | 518.83 |  | 2021-09-14 | 2021-09-14 | 2021-11-30 | 2021-09-14 |  | No | 2025-02-03 | No | 2023-10-06 | Not Required | 2023-10-06
23INR0348 | Aggie Energy storage | SS Completed, FIS Started, No IA | KINGFISHER ENERGY STORAGE LLC | TABOR RD (#32882) | Brazos | NORTH | 2026-06-15 | OTH | BA | 104.4 |  | 2021-08-13 | 2021-08-16 | 2021-11-05 | 2021-08-13 |  |  |  | No
23INR0349 | Tokio Solar | SS Completed, FIS Started, IA | Gransolar Texas Eight, LLC | Tap 138kV 3592 Waco Atco - 170 Cotton Belt | McLennan | NORTH | 2027-08-25 | SOL | PV | 170.45 |  | 2022-05-04 | 2021-08-12 | 2021-11-01 | 2022-04-14 |  |  | 2023-11-06 | Yes | Not Required | Not Required | Not Required | 2023-11-17
23INR0351 | Seven Flags BESS | SS Completed, FIS Completed, IA | Seven Flags BESS LLC | 8295 Wormser Substation 138kV | Webb | SOUTH | 2026-01-07 | OTH | BA | 102.7 |  | 2021-09-01 | 2021-09-01 | 2021-11-22 | 2021-08-19 | 2024-12-19 | No | 2023-05-19 | Yes | Not Required | Not Required |  | 2025-01-15 | 2025-01-15 | 2025-01-15 |  |  | 2025-09-22 | 2025-09-30
23INR0354 | Bordertown BESS | SS Completed, FIS Started, IA | Bordertown BESS LLC | 8796 Roma 138kV | Starr | SOUTH | 2027-06-15 | OTH | BA | 100 |  | 2021-08-17 | 2021-09-01 | 2021-11-22 | 2021-08-19 |  | No | 2022-10-12 | Yes | Not Required | Not Required | 2025-04-03 | 2025-02-13
23INR0358 | Castor BESS | SS Completed, FIS Completed, IA | BRP Castor BESS LLC | 138 kV West Columbia Local Substation (#39530) | Brazoria | COASTAL | 2025-12-31 | OTH | BA | 205.39 |  | 2021-10-01 | 2021-10-04 | 2021-12-22 | 2021-09-24 | 2024-07-31 | No | 2023-02-15 | Yes | Not Required | Not Required |  | 2024-10-22 | 2024-10-22 | 2024-10-22
23INR0359 | Crios BESS | SS Completed, FIS Started, No IA | BRP Crios BESS LLC | Tap 138 kV 1649 HASSE_P8 - 1684 SABANA_8 | Comanche | NORTH | 2028-03-01 | OTH | BA | 205.46 |  | 2021-10-18 | 2021-10-18 | 2022-01-07 | 2021-09-30 |  |  |  | No
23INR0360 | BRP Charon BESS | SS Completed, FIS Completed, No IA | BRP Charon BESS LLC | Tap Smithers (#44650) and Bellaire (#47000) 345kV | Fort Bend | HOUSTON | 2027-12-01 | OTH | BA | 410.81 |  | 2021-10-08 | 2021-10-08 | 2021-12-22 | 2021-09-24 | 2022-10-10 | No |  | No
23INR0361 | Third Coast BESS | SS Completed, FIS Completed, IA | Third Coast BESS LLC | 8125 Lolita substation 138kV | Jackson | SOUTH | 2026-11-24 | OTH | BA | 102.82 |  | 2021-09-16 | 2021-08-24 | 2021-11-16 | 2021-09-01 | 2024-12-02 | No | 2023-05-17 | Yes | Not Required | Not Required |  | 2025-01-29 | 2025-01-29 | 2025-01-29
23INR0364 | Tierra Seca BESS | SS Completed, FIS Completed, IA | Tierra Seca BESS LLC | 138kV 8255 HAMILTON4A (Hamilton Road Substation) | Val Verde | WEST | 2026-01-29 | OTH | BA | 102.7 |  | 2021-09-14 | 2021-08-24 | 2021-11-16 | 2021-09-01 | 2024-10-21 | No | 2023-05-18 | Yes | Not Required | Not Required |  | 2024-10-30 | 2024-10-30 | 2024-10-30
23INR0367 | Fewell Solar | SS Completed, FIS Completed, IA | Fewell Solar LLC | Tap 138kV 3597 Groesbeck - 3634 Groesbeck Main | Limestone | NORTH | 2027-03-15 | SOL | PV | 203.5 |  | 2022-02-28 | 2021-08-19 | 2021-11-05 | 2022-02-17 | 2023-04-17 | No | 2023-08-18 | Yes | Not Required | Not Required | Not Required | 2023-08-28
23INR0368 | Rocking X Solar | SS Completed, FIS Started, No IA | 7100 Tin Top LLC | Tap the 345 kV Parker Switch (bus#1436) – Comanche Peak SES (bus#1900) Double-Circuit line, Circuit 1. | Parker | NORTH | 2027-09-20 | SOL | PV | 602.2 |  | 2023-09-25 | 2023-10-04 | 2023-12-19 | 2023-09-06 |  | No |  | No | Not Required | Not Required | Not Required
23INR0375 | Backwater Storage | SS Completed, FIS Started, No IA | Backwater Solar LLC | Tap 138 kV 684 Spring - 685 Leo | Cooke | NORTH | 2027-09-15 | OTH | BA | 100 |  | 2021-09-02 | 2021-09-17 | 2021-12-06 | 2021-09-17 |  |  |  | No
23INR0376 | Cascade Storage | SS Completed, FIS Started, No IA | Oyster Creek LLC | 345kV Oasis (43035) – Seabreeze circuit 27 | Brazoria | COASTAL | 2026-01-16 | OTH | BA | 250 |  | 2021-09-09 | 2021-09-09 | 2021-11-29 | 2021-09-09 |  |  |  | No
23INR0381 | Bexar ESS | SS Completed, FIS Completed, IA | Bexar ESS LLC | 5007 Alamo One 138kV | Bexar | SOUTH | 2025-10-24 | OTH | BA | 102.6 | COD | 2022-01-05 | 2021-09-21 | 2021-12-06 | 2021-12-14 | 2024-07-08 |  | 2023-07-31 | Yes |  |  |  | 2023-08-25 | 2024-10-31 | 2024-10-31 |  |  | 2025-05-06 | 2025-06-03
23INR0382 | Outer Loop BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II | 40700 Greens Bayou 345kV | Harris | HOUSTON | 2027-12-06 | OTH | BA | 201.2 |  | 2022-05-02 | 2021-09-29 | 2021-12-06 | 2022-04-19 |  | No |  | No
23INR0385 | Camp Creek Solar SLF | SS Completed, FIS Completed, IA | White Rock Solar, LLC | TAP 345 KV 3400 TWIN OAK SWITCH - 46020 LIMESTONE PLANT CIRCUIT 1 | Robertson | NORTH | 2028-09-15 | SOL | PV | 110 |  | 2021-12-17 | 2021-12-24 | 2022-03-17 | 2021-12-09 | 2024-01-26 | Yes | 2023-07-15 | No |  |  | Not Required
23INR0391 | THUNDER ROAD ENERGY STORAGE | SS Completed, FIS Started, No IA | Hecate Grid Thunder Road Storage LLC | 12491 FISH CREEK 138KV | Dallas | NORTH | 2027-05-31 | OTH | BA | 153.4 |  | 2021-12-29 | 2021-10-22 | 2022-01-17 | 2021-12-17 |  |  |  | No
23INR0392 | Honeycomb Storage SLF | SS Completed, FIS Completed, IA | Honeycomb BESS, LLC | 69 kV Tynan Substation (#8107) | Bee | SOUTH | 2026-06-30 | OTH | BA | 0.07 |  | 2021-10-26 | 2021-11-16 | 2022-01-17 | 2021-11-02 | 2025-03-28 | No | 2023-05-01 | Yes | Not Required | Not Required |  | 2025-02-14 | 2025-07-25 | 2025-07-25
23INR0401 | Headcamp Energy Storage Plant | SS Completed, FIS Completed, IA | Momentum Headcamp LLC | tap 138kV 38331 TN Alamo St – 38455 TN Holiday | Pecos | WEST | 2025-11-26 | OTH | BA | 152.88 |  | 2022-02-11 | 2021-12-03 | 2022-02-28 | 2022-01-21 | 2024-09-18 | No | 2024-02-16 | Yes | Not Required | Not Required |  | 2024-04-11 | 2024-10-31 | 2024-10-31 |  |  | 2025-08-19 | 2025-09-16
23INR0409 | Sunbelt Storage | SS Completed, FIS Started, No IA | Rose Hill Solar LLC | Tap 138kV 6902 Talty - 6894 Rose Hill | Kaufman | NORTH | 2026-12-31 | OTH | BA | 52 |  | 2021-11-09 | 2021-11-12 | 2022-02-08 | 2021-11-09 |  |  |  | No
23INR0414 | Flag City Storage SLF | SS Completed, FIS Started, No IA | Flag City Solar Project, LLC | tap 138kV 5588 Red Bluff - 5546 Danevang | Jackson | SOUTH | 2027-12-31 | OTH | BA | 169.06 |  | 2021-11-16 | 2021-11-18 | 2022-02-08 | 2021-11-18 |  | No |  | No | Not Required | Not Required
23INR0419 | SAHARA BESS (SOHO BESS) | SS Completed, FIS Completed, IA | ESTX-PLD-HOUSTON2 | 43035 Oasis 345kV | Brazoria | COASTAL | 2026-06-01 | OTH | BA | 204.4 |  | 2021-12-13 | 2021-12-03 | 2022-02-28 | 2021-12-03 | 2025-05-02 | No | 2022-12-01 | Yes | Not Required | Not Required | 2025-04-29 | 2023-01-19 | 2025-07-22 | 2025-07-22
23INR0421 | Bee Branch IA | SS Completed, FIS Started, No IA | Tidwell Prairie LLC | Tap TNP ONE 39950 and Twin Oak 3400 | Robertson | NORTH | 2027-06-01 | OTH | BA | 202.88 |  | 2021-11-15 | 2021-11-15 | 2022-02-11 | 2021-11-09 |  |  |  | No
23INR0423 | Camp Creek Storage SLF | SS Completed, FIS Completed, IA | White Rock Solar | TAP 345 KV 3400 TWIN OAK SWITCH - 46020 LIMESTONE PLANT CIRCUIT 1 | Robertson | NORTH | 2028-09-15 | OTH | BA | 0 |  | 2021-12-24 | 2021-12-24 | 2022-03-17 | 2021-12-21 | 2024-01-26 | Yes | 2023-07-15 | No
23INR0425 | Coneflower Storage Project | SS Completed, FIS Started, IA | Coneflower Storage Project LLC | 40855 JORDON 138 kV | Chambers | HOUSTON | 2027-02-03 | OTH | BA | 170.85 |  | 2022-07-11 | 2021-12-20 | 2022-03-11 | 2022-07-06 |  | No | 2024-03-25 | Yes | Not Required | Not Required |  | 2024-04-11
23INR0431 | BRP Pollux BESS | SS Completed, FIS Started, No IA | BRP Pollux BESS LLC | 138 kV Olsen Switching Station (#37460) | Bosque | NORTH | 2026-12-01 | OTH | BA | 163.42 |  | 2021-12-20 | 2022-01-06 | 2022-03-16 | 2022-01-04 |  | No |  | No | Not Required | Not Required
23INR0439 | Smokey Willie Solar SLF | SS Completed, FIS Started, No IA | Neches Solar, LLC | Tap 138kV 3325 Blackburn Switch – 3272 Palestine | Anderson | NORTH | 2028-09-30 | SOL | PV | 201.04 |  | 2021-12-29 | 2022-01-06 | 2022-03-31 | 2021-12-29 |  | No |  | No |  |  | Not Required
23INR0441 | Bug Tussle Wind Project | SS Completed, FIS Started, IA | Bug Tussle Wind, LLC | Tap 1729 Valley South and 1692 Paris | Lamar | NORTH | 2027-08-23 | WIN | WT | 396.8 |  | 2022-08-30 | 2022-01-13 | 2022-04-11 | 2022-08-16 |  |  | 2024-07-10 | No |  |  | Not Required
23INR0455 | Bessie Storage | SS Completed, FIS Started, No IA | Bessie Energy Storage, LLC | Charly Egner Substation Tap 345kV 80355 Del Sol - 80368 LV4 Bridge | Starr | SOUTH | 2026-12-01 | OTH | BA | 210.8 |  | 2022-02-08 | 2022-02-21 | 2022-05-19 | 2022-02-07 |  | No |  | No | Not Required | Not Required
23INR0456 | Bronze Quinta Storage | SS Completed, FIS Started, No IA | KCE TX 28, LLC | S_MCALLN 8371 (S. McAllen 138kV Substation) | Hidalgo | SOUTH | 2028-01-01 | OTH | BA | 103.51 |  | 2022-01-12 | 2022-01-13 | 2022-04-11 | 2022-01-11 |  |  |  | No | Not Required | Not Required
23INR0462 | Palladium Storage | SS Completed, FIS Started, No IA | Palladium Energy Storage LLC | Tap 138 kV 8656 Luna - 8033 Pantera | Hidalgo | SOUTH | 2028-06-30 | OTH | BA | 152 |  |  | 2022-02-28 | 2022-05-27 | 2022-01-21 |  |  |  | No
23INR0464 | Sloan Storage | SS Completed, FIS Started, No IA | Sloan Energy Storage LLC | 3179 Pauline 138kV | Henderson | NORTH | 2026-03-27 | OTH | BA | 200.9 |  | 2022-07-13 | 2022-02-21 | 2022-05-21 | 2022-06-29 |  |  |  | No | Not Required | Not Required
23INR0466 | Shoshana Storage | SS Completed, FIS Started, No IA | Shoshana Storage Project LLC | Tap STP – Refuge ckt 27 | Matagorda | COASTAL | 2026-08-28 | OTH | BA | 221 |  | 2022-05-31 | 2022-03-30 | 2022-06-26 | 2022-05-16 |  | Yes |  | No
23INR0467 | Lavender Storage Project | SS Completed, FIS Started, IA | Lavender Storage Project LLC | Tap 138kV Deely (bus 5110) - Laredo (bus 5255) | Bexar | SOUTH | 2029-09-13 | OTH | BA | 231.9 |  | 2022-11-03 | 2022-02-28 | 2022-05-27 | 2022-10-21 |  | No | 2025-06-23 | No
23INR0468 | Petunia Storage Project | SS Completed, FIS Started, No IA | Petunia Storage Project LLC | 138kV Tap 3675 Rogers - 3485 Tin Roof Pod | Milam | SOUTH | 2027-01-22 | OTH | BA | 231.86 |  | 2022-04-14 | 2022-03-12 | 2022-06-02 | 2022-04-01 |  | No |  | No | Not Required | Not Required
23INR0469 | Big Elm Storage | SS Completed, FIS Completed, IA | Big Elm Storage, LLC | 3404 Belfalls 345kV | Bell | NORTH | 2027-11-10 | OTH | BA | 120 |  | 2022-10-25 | 2022-04-18 | 2022-07-08 | 2022-10-11 | 2024-02-19 | No | 2024-05-10 | Yes |  |  |  | 2024-05-15
23INR0471 | Ophelia Solar | SS Completed, FIS Started, No IA | Ophelia Solar | Tap 138 kV Raceway Switch #18663 - Shin Oak POD #11128 | Ector | WEST | 2028-09-18 | SOL | PV | 110.5 |  | 2022-08-15 | 2022-09-02 | 2022-11-29 | 2022-08-01 |  |  |  | No |  |  | Not Required
23INR0473 | Sepanta Solar | SS Completed, FIS Started, No IA | BREG - Belgian Renewable Energy Group | 1339 ESKOTA_9 138kV (PSS/E BUS #1339, Station Name: ESKOTA_8, kV: 138 kV) Property is adjacent (West) to the Oncor Sweetwater Eskota Switch #1339. POI would simply be on the other side of the fence of the switch. | Nolan | WEST | 2029-09-18 | SOL | PV | 217.26 | COD | 2022-11-17 | 2022-10-18 | 2023-01-13 | 2022-11-15 |  |  |  | No |  |  | Not Required
23INR0474 | AP Greenport | SS Completed, FIS Completed, No IA | AP Greenport | Austrop – Lost Pines 345 kV transmission line (Bus #7040 – 9041) | Travis | SOUTH | 2027-11-19 | OTH | BA | 100.45 |  | 2022-09-14 | 2022-06-10 | 2022-09-06 | 2022-06-24 | 2023-09-29 | No |  | No
23INR0478 | Rhoda Storage | SS Completed, FIS Started, No IA | Milam Energy, LLC | Tap 138kV 32 Robertson - 64 Milano | Milam | SOUTH | 2027-08-04 | OTH | BA | 141.23 |  | 2022-03-31 | 2022-04-18 | 2022-07-15 | 2022-03-18 |  |  |  | No | Not Required | Not Required
23INR0479 | Taormina Storage | SS Completed, FIS Started, IA | Taormina Storage Project LLC | Tap 138kV VH Braunig (5025) to Valley Road 138kV (5465) | Bexar | SOUTH | 2029-05-26 | OTH | BA | 231.86 |  | 2022-11-08 | 2022-04-18 | 2022-07-15 | 2022-10-26 |  | No | 2025-04-14 | Yes | Not Required | Not Required |  | 2025-06-20
23INR0480 | Camellia Storage | SS Completed, FIS Started, No IA | Camellia Storage Project LLC | Tap 138 kV 8358 NORTH MERCEDES - 8327 HARLINGEN 138 kV | Hidalgo | SOUTH | 2027-03-17 | OTH | BA | 90.76 |  | 2022-07-12 | 2022-07-05 | 2022-10-01 | 2022-07-06 |  |  |  | No | Not Required | Not Required
23INR0485 | Hacienda Storage | SS Completed, FIS Started, No IA | Galveston Energy Storage LLC | 38745 Attwater 138kV | Galveston | HOUSTON | 2026-12-18 | OTH | BA | 201.9 |  | 2022-04-20 | 2022-05-10 | 2022-08-06 | 2022-04-04 |  |  |  | No
23INR0486 | Lamar Unit 1 Repower | SS Completed, FIS Started, No IA | La Frontera Holdings, LLC | 1692 Paris Switch Station 345kV | Lamar | NORTH | 2027-12-18 | GAS | CC | 66 |  | 2023-06-26 | 2022-06-02 | 2022-08-30 | 2023-05-15 20:25 |  |  |  | No
23INR0487 | Brightside Solar Alt POI | SS Completed, FIS Not Started, IA | Brightside Solar, LLC | 8156 Charter Substation 138kV | Live Oak | SOUTH | 2026-08-14 | SOL | PV | 50 | COD |  | 2022-05-16 | 2022-08-05 |  |  |  | 2020-06-11 | Yes |  |  | Not Required
23INR0494 | Cartwheel BESS 1 | SS Completed, FIS Completed, IA | Cartwheel BESS, LLC | Tap 345kV 1697 Sulphur Springs Switch – 2464 Cash Switch | Hopkins | NORTH | 2025-09-30 | OTH | BA | 154.2 |  | 2022-05-20 | 2022-06-02 | 2022-08-30 | 2022-05-10 | 2024-04-12 |  | 2023-11-10 | Yes |  |  |  | 2024-11-04 | 2024-11-04 | 2024-10-30 |  |  | 2025-06-26 | 2025-09-10
23INR0495 | Cartwheel BESS 2 | SS Completed, FIS Started, No IA | RWE Renewables | Tap 345kV 1697 Sulphur Springs Switch – 2464 Cash Switch | Hopkins | NORTH | 2028-06-15 | OTH | BA | 156.91 | COD | 2022-05-20 | 2022-06-02 | 2022-08-30 | 2022-05-10 |  |  |  | No
23INR0496 | San Perlita BESS 1 | SS Completed, FIS Started, No IA | RWE Renewables | 8601 Cebolla 345kV | Willacy | COASTAL | 2025-12-15 | OTH | BA | 150 |  | 2022-05-20 | 2022-06-02 | 2022-08-29 | 2022-05-10 |  |  |  | No
23INR0497 | San Perlita BESS 2 | SS Completed, FIS Started, No IA | RWE Renewables | 8601 Cebolla 345kV | Willacy | COASTAL | 2025-12-15 | OTH | BA | 150 |  | 2022-05-20 | 2022-06-02 | 2022-08-29 | 2022-05-10 |  |  |  | No
23INR0501 | Soda Lake BESS 1 | SS Completed, FIS Completed, IA | Mendoza Trail BESS, LLC | 138kV Soda Lake Substation (#76026) | Crane | WEST | 2025-12-17 | OTH | BA | 203.87 |  | 2022-08-03 | 2022-09-02 | 2022-11-29 | 2022-08-09 | 2024-10-22 |  | 2018-08-20 | Yes | Not Required | Not Required |  | 2024-11-01 | 2024-11-01 | 2024-11-01 |  |  | 2025-09-02
23INR0502 | Adelite Storage | SS Completed, FIS Completed, IA | Adelite Storage Project LLC | Tap 138kV Thorndale North (bus #3659) – Rookie Switch (bus #3701) | Milam | SOUTH | 2026-07-31 | OTH | BA | 231.88 | COD | 2022-09-13 | 2022-06-27 | 2022-09-22 | 2022-09-09 | 2024-05-01 |  | 2024-08-27 | No
23INR0503 | Ardesia Storage | SS Completed, FIS Started, No IA | Ardesia Storage Project LLC | Tap 138kV 7325 Mendoza - 7216 Lockhart | Caldwell | SOUTH | 2026-08-28 | OTH | BA | 100 |  | 2022-08-29 | 2022-06-10 | 2022-09-06 | 2022-07-22 |  |  |  | No
23INR0524 | Temple II Repower | SS Completed, FIS Completed, IA | Panda Temple Power II | 3413 Knob Creek | Bell | NORTH | 2024-09-01 | GAS | CC | 0 |  | 2022-08-01 | 2022-08-05 | 2022-11-01 | 2022-07-22 | 2023-01-04 |  | 2012-06-21 | Yes | 2020-06-18 |  | 2023-01-26 | 2023-01-29 | 2023-01-29 | 2023-01-31
23INR0538 | Roadrunner Crossing BESS SLF | SS Completed, FIS Completed, IA | Roadrunner Crossing BESS | 68051 Reata 354kV | Eastland | NORTH | 2025-12-31 | OTH | BA | 0 |  | 2022-10-23 | 2022-11-15 | 2023-02-10 | 2022-10-28 | 2025-03-18 |  | 2025-02-18 | Yes | Not Required | Not Required | 2025-04-25 | 2025-04-28 | 2025-05-30 | 2025-04-28
23INR0561 | Cascabel Wind 2 | SS Completed, FIS Started, IA | Vaquero Wind Energy, LLC | 345 kV Rapido Substation (New ETT Substation) tapping the existing 345 kV Line from CENIZO7C (#80225) to DELSOL7C (#80307). | Zapata | SOUTH | 2027-12-01 | WIN | WT | 197.75 |  | 2023-03-08 | 2023-03-13 | 2023-06-09 | 2023-02-15 |  |  | 2025-05-23 | Yes | Not Required |  | Not Required | 2025-09-24
23INR0637 | Goodnight Wind II | SS Completed, FIS Started, IA | FGE Goodnight II, LLC | tap 345kV 23900 Alibates - 23914 Tule Canyon CKT2 | Armstrong | PANHANDLE | 2027-01-09 | WIN | WT | 259.2 |  | 2023-04-28 | 2023-04-19 | 2023-04-19 | 2023-05-01 |  | No | 2019-08-18 | Yes | Not Required | Not Required | Not Required | 2023-05-01 | 2023-05-01
23INR0794 | Invictus Energy Storage | SS Completed, FIS Started, No IA | GSA Land Holdings | 6390 FIREROCK4A 138kV | Coleman | WEST | 2028-05-31 | OTH | BA | 140.53 |  | 2024-06-21 | 2024-01-03 | 2024-03-28 | 2024-06-11 |  |  |  | No
24INR0003 | Stem Solar | SS Completed, FIS Started, No IA | Innovative Solar 134, LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala | Swisher | PANHANDLE | 2025-08-26 | SOL | PV | 200 |  | 2020-12-03 | 2020-02-04 | 2020-04-27 | 2020-10-22 |  |  |  | No |  |  | Not Required
24INR0007 | Nockenut Springs Solar 2 | SS Completed, FIS Started, IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Guadalupe | SOUTH | 2029-06-05 | SOL | PV | 203.26 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  | Yes | 2023-11-17 | No |  |  | Not Required
24INR0010 | Pinnington Solar | SS Completed, FIS Completed, IA | Hecate Energy Longhorn Solar LLC | 1506 Long Hollow Switch 345kV | Jack | NORTH | 2026-04-30 | SOL | PV | 653.7 |  | 2020-11-03 | 2020-12-03 | 2021-02-17 | 2020-11-10 | 2024-12-17 |  | 2023-11-02 | Yes |  |  | Not Required | 2023-11-15 | 2025-01-30 | 2025-01-30
24INR0011 | Pinnington Storage | SS Completed, FIS Started, No IA | Hecate Energy Longhorn Storage LLC | tap both 345kV 1430 Graham - 1436 Parker 345kV lines | Jack | NORTH | 2029-04-20 | OTH | BA | 502.67 | MW Size | 2020-11-10 | 2020-12-03 | 2021-02-17 | 2020-11-10 |  |  |  | No
24INR0020 | Percy Farm Solar | SS Completed, FIS Started, No IA | Percy Farm Solar 1, LLC | Tap 345kV 8123 Blessing - 5915 STP | Matagorda | COASTAL | 2029-05-31 | SOL | PV | 198.63 |  | 2021-08-05 | 2021-03-16 | 2021-06-11 | 2021-07-21 |  | No |  | No | Not Required | Not Required | Not Required
24INR0022 | Boxcar Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345kV 1907 Venus N - 68091 Navarro | Ellis | NORTH | 2027-04-01 | SOL | PV | 355.82 |  | 2021-03-25 | 2021-03-31 | 2021-06-17 | 2021-03-17 |  |  |  | No |  |  | Not Required
24INR0023 | Compadre Solar | SS Completed, FIS Completed, IA | Hill Solar I, LLC | tap 345kV 68090 Sam Switch - 1907 Venus | Hill | NORTH | 2025-11-15 | SOL | PV | 405.7 | COD | 2021-03-29 | 2021-03-16 | 2021-05-28 | 2021-03-08 | 2024-01-31 | No | 2022-11-12 | Yes | Not Required | Not Required | Not Required | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  | 2024-10-30 | 2024-11-13
24INR0031 | Stoneridge Solar | SS Completed, FIS Completed, IA | Stoneridge Solar, LLC | Tap 345 kV 13429 SANDOW SWITCH - 7040 AUSTROP Beulah Switch to tap above line | Milam | SOUTH | 2025-11-01 | SOL | PV | 201.6 |  | 2022-02-14 | 2021-10-08 | 2022-01-03 | 2022-01-31 | 2024-05-21 | No | 2023-05-15 | Yes | Not Required | Not Required | Not Required | 2024-07-18 | 2024-07-18 | 2024-07-18 |  |  | 2025-01-10 | 2025-04-01
24INR0038 | Jaguar Solar | SS Completed, FIS Started, IA | PP Jaguar Solar LLC | Tap 345kV 13405 Tradinghouse SES - 68090 Sam Switch | McLennan | NORTH | 2027-02-11 | SOL | PV | 300 |  | 2021-07-23 | 2021-03-18 | 2021-06-11 | 2021-07-15 |  |  | 2022-09-12 | Yes |  |  | Not Required | 2023-08-25 | 2024-01-23
24INR0040 | Rosebud Solar SLF | SS Completed, FIS Started, No IA | Rosebud Solar, LLC | Tap 69kV 67 BAGGINS - 69 BARCLAY | Falls | NORTH | 2028-01-15 | SOL | PV | 130 |  | 2022-01-12 | 2021-04-13 | 2021-07-06 | 2022-01-10 |  |  |  | No |  |  | Not Required
24INR0041 | Rock N' Roll Solar SLF | SS Completed, FIS Started, No IA | Rock N Roll Solar | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2027-08-30 | SOL | PV | 151.97 | COD | 2022-02-10 | 2021-05-10 | 2021-07-30 | 2022-01-20 |  | No |  | No | Not Required | Not Required | Not Required
24INR0042 | Yaupon Solar SLF | SS Completed, FIS Completed, IA | Yaupon Solar, LLC | Tap 345 kV Gibson Switch (3706) – TNP One (39950) | Milam | SOUTH | 2027-07-01 | SOL | PV | 200.78 |  | 2021-12-07 | 2021-03-30 | 2021-06-17 | 2021-11-23 | 2025-09-16 |  | 2023-09-28 | Yes |  |  | Not Required | 2025-09-08
24INR0044 | Millers Branch Solar II | SS Completed, FIS Completed, IA | Miller's Branch Solar, LLC | Tap 345kV 60703 Gauss - 60514 Clear Crossing (60712 QUASAR) | Haskell | WEST | 2026-04-01 | SOL | PV | 178 |  | 2021-11-02 | 2021-11-04 | 2020-03-06 | 2021-11-04 | 2024-12-09 |  | 2021-06-14 | Yes | Not Required | Not Required | Not Required | 2025-03-18 | 2025-04-30 | 2025-04-30
24INR0056 | Pradera Solar | SS Completed, FIS Started, No IA | Pradera Solar, LLC | tap 345 kV Lobo (80219) - Fowlerton (5709) | Webb | SOUTH | 2027-03-31 | SOL | PV | 118 |  | 2021-06-02 | 2021-07-08 | 2021-09-28 | 2021-06-23 |  |  |  | No |  |  | Not Required
24INR0058 | Briggs Storage | SS Completed, FIS Started, IA | IP Quantum III, LLC | tap 345kV 60515 Clear Crossing - 60507 Pendulo | Haskell | WEST | 2027-09-15 | OTH | BA | 336 |  | 2022-03-18 | 2021-05-31 | 2021-08-18 | 2022-03-04 |  |  | 2025-03-15 | Yes | Not Required | Not Required |  | 2025-03-24
24INR0059 | Cuchillas Solar | SS Completed, FIS Completed, IA | Gransolar Texas Two, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2027-09-01 | SOL | PV | 305.6 |  | 2022-02-24 | 2021-06-02 | 2021-08-18 | 2022-02-11 | 2025-05-27 | No | 2023-06-20 | Yes |  |  | Not Required | 2025-02-13
24INR0061 | Eighteenmile Solar SLF | SS Completed, FIS Started, No IA | Weser Solar, LLC | Tap 138kV 5730 Four Corners - 5728 Choate | Goliad | SOUTH | 2026-12-01 | SOL | PV | 153.06 |  | 2021-09-02 | 2021-08-18 | 2021-11-05 | 2021-08-24 |  |  |  | No |  |  | Not Required
24INR0062 | Eighteenmile Storage SLF | SS Completed, FIS Started, No IA | Weser Solar, LLC | Tap 5730 Four Corners to 5728 Choate 138 kV | Goliad | SOUTH | 2026-12-01 | OTH | BA | 0 |  | 2022-01-12 | 2021-12-29 | 2022-02-08 | 2022-01-07 |  |  |  | No
24INR0065 | Keys Hollow Solar Phase II SLF | SS Completed, FIS Started, IA | Keys Hollow Solar, LLC | 345kV Tap 8164 Coleto Creek - 8673 RAPTOR7A | Goliad | SOUTH | 2028-03-10 | SOL | PV | 204.08 |  | 2021-08-25 | 2021-06-17 | 2021-09-01 | 2021-07-29 |  | No | 2024-10-29 | No | Not Required | Not Required | Not Required
24INR0066 | Keys Hollow Storage Phase II SLF | SS Completed, FIS Started, IA | Keys Hollow Solar, LLC | 345kV Tap 8164 Coleto Creek - 8673 RAPTOR7A | Goliad | SOUTH | 2028-03-10 | OTH | BA | 0 |  | 2022-01-20 | 2021-06-17 | 2021-09-01 | 2022-01-10 |  | No | 2024-10-29 | No | Not Required | Not Required
24INR0067 | KEYS HOLLOW SOLAR SLF | SS Completed, FIS Started, IA | Keys Hollow Solar, LLC | TAP 345 KV LINE FROM COLETO 8164 - RAPTOR7A 8673 | Goliad | SOUTH | 2028-03-10 | SOL | PV | 204.08 |  | 2022-03-10 | 2021-06-17 | 2021-09-01 | 2022-03-04 |  | No | 2024-10-29 | No |  |  | Not Required
24INR0068 | KEYS HOLLOW STORAGE SLF | SS Completed, FIS Started, IA | Keys Hollow Solar, LLC | TAP 345 KV LINE FROM COLETO 8164 - RAPTOR7A 8673 | Goliad | SOUTH | 2028-03-10 | OTH | BA | 0 |  | 2022-03-10 | 2021-06-17 | 2021-09-01 | 2022-03-04 |  | No | 2024-10-29 | No
24INR0069 | Triple B Solar Alt#2 | SS Completed, FIS Started, No IA | Triple B Solar LLC | Tap 138kV 7066 Adamsville - 7064 Lampasas | Lampasas | NORTH | 2027-07-01 | SOL | PV | 150 |  | 2021-12-15 | 2021-06-10 | 2021-09-01 | 2021-11-15 |  |  |  | No |  |  | Not Required
24INR0070 | Sypert Branch Solar Project | SS Completed, FIS Completed, IA | Sypert Branch Solar LLC | Tap 345kV #3751 Scooter Switch - #3687 Bell County East Switch Ckt 2 | Milam | SOUTH | 2026-01-31 | SOL | PV | 261.15 |  | 2022-05-10 | 2021-09-21 | 2021-12-06 | 2022-04-28 | 2024-10-31 | No | 2023-10-12 | Yes | Not Required | Not Required | Not Required | 2023-10-18 | 2025-04-17 | 2025-04-17
24INR0073 | Hyacinth Storage | SS Completed, FIS Started, No IA | Hyacinth Storage, LLC | 46500 Tomball 345 kV | Harris | HOUSTON | 2030-12-25 | OTH | BA | 103.05 |  | 2022-04-02 | 2021-07-02 | 2021-09-22 | 2022-03-21 |  |  |  | No
24INR0077 | Quarter Ranch Solar | SS Completed, FIS Started, No IA | Gransolar Texas Three LLC | 80223 Cenizo Substation 345kV | Zapata | SOUTH | 2028-10-15 | SOL | PV | 154.12 |  | 2022-03-28 | 2021-07-13 | 2021-09-28 | 2022-03-23 |  | No |  | No |  |  | Not Required
24INR0078 | Apogee Wind II | SS Completed, FIS Started, No IA | King Creek Wind Farm 3, LLC | 60791 Perigee Substation 345kV | Throckmorton | WEST | 2027-03-31 | WIN | WT | 47.25 |  | 2021-12-29 | 2021-07-13 | 2021-09-20 | 2021-12-14 |  |  |  | No |  |  | Not Required
24INR0079 | Boxcar Solar 2 | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345 kV 1907 Venus N - 68091 Navarro | Ellis | NORTH | 2027-09-30 | SOL | PV | 251.3 |  | 2022-06-07 | 2021-07-13 | 2021-09-28 | 2022-05-23 |  | Yes |  | No |  |  | Not Required
24INR0081 | SANJAC BESS | SS Completed, FIS Started, No IA | Castleman Power | 40270 Riverside 138kV | Harris | HOUSTON | 2027-04-04 | OTH | BA | 202.37 |  | 2021-07-08 | 2021-07-08 | 2021-09-28 | 2021-07-08 |  |  |  | No
24INR0086 | Pisgah Ridge Solar 2 | SS Completed, FIS Started, No IA | Pisgah Ridge Solar 2, LLC | Tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2026-12-01 | SOL | PV | 101.89 |  | 2021-09-07 | 2021-07-14 | 2021-10-07 | 2021-08-25 |  | No |  | No | Not Required | Not Required | Not Required
24INR0087 | Pisgah Ridge Storage 3 | SS Completed, FIS Started, No IA | Pisgah Ridge 3, LLC | Tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2026-12-01 | OTH | BA | 101.36 |  | 2021-09-07 | 2021-07-14 | 2021-10-07 | 2021-08-25 |  | No |  | No | Not Required | Not Required
24INR0091 | BRP Springbok Solar | SS Completed, FIS Started, No IA | Antelope Solar LLC | 23920 Blackwater Draw Switching Station 345kV | Hale | PANHANDLE | 2027-12-01 | SOL | PV | 202.39 |  | 2021-08-25 | 2021-08-25 | 2021-11-17 | 2021-08-02 |  | No |  | No | Not Required | Not Required | Not Required
24INR0093 | Oriana Solar | SS Completed, FIS Completed, IA | Oriana Solar LLC | Tap 138kV 5502 Rayburn - 5584 Vanderbilt | Victoria | SOUTH | 2025-10-09 | SOL | PV | 181 |  | 2021-08-25 | 2021-08-25 | 2021-11-17 | 2021-08-13 | 2024-07-30 |  | 2023-02-27 | Yes | Not Required | Not Required | Not Required | 2024-07-25 | 2024-08-01 | 2024-08-01 |  |  | 2025-07-25 | 2025-08-06
24INR0094 | Dovetail Solar 1 | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Solar 1 LLC | Tap 345 KV 1421 Willow Creek - 60515 Clear Crossing Ckt 2 | Jack | NORTH | 2027-04-15 | SOL | PV | 666.1 |  | 2022-06-23 | 2021-09-21 | 2021-12-09 | 2022-06-06 |  |  |  | No | Not Required | Not Required | Not Required
24INR0095 | Dovetail Solar 2 | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Solar 2 LLC | Tap 345 KV 1421 Willow Creek - 60515 Clear Crossing | Jack | NORTH | 2028-03-31 | SOL | PV | 666.1 |  | 2022-07-29 | 2021-10-26 | 2022-01-21 | 2022-07-15 |  |  |  | No |  |  | Not Required
24INR0096 | BRP Volga BESS | SS Completed, FIS Started, No IA | BRP Volga BESS LLC | 138 kV Seagoville Switch Substation (#2434; ONCOR) | Dallas | NORTH | 2027-12-01 | OTH | BA | 174.63 |  | 2021-12-13 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  | No |  | No | Not Required | Not Required
24INR0097 | Dovetail Solar 3 | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Solar Holdings LLC | Tap 345kV 1421 Willow Creek – 11523 THOMPRIC | Jack | NORTH | 2028-12-29 | SOL | PV | 666.1 |  | 2022-08-29 | 2021-12-13 | 2022-02-08 | 2022-08-06 |  |  |  | No |  |  | Not Required
24INR0098 | Dovetail Storage | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Storage LLC | Tap 345 KV 1421 Willow Creek-60515 Clear Crossing CKT#2 | Jack | NORTH | 2027-04-15 | OTH | BA | 508.7 |  | 2022-06-20 | 2021-09-28 | 2021-12-03 | 2022-05-31 |  |  |  | No
24INR0099 | Two Rivers Solar | SS Completed, FIS Completed, No IA | Two Rivers Solar, LLC | Tap 138kV 64 Milano – 32 Robertson | Milam | SOUTH | 2029-06-07 | SOL | PV | 208.7 |  | 2021-07-27 | 2021-07-27 | 2021-10-21 | 2021-07-22 | 2024-08-15 | No |  | No | Not Required | Not Required | Not Required
24INR0101 | Lampe Solar | SS Completed, FIS Completed, No IA | Gransolar Texas Seven LLC | Tap 138 kV 7572 Gay Hill - 7573 Lyons | Washington | SOUTH | 2027-12-26 | SOL | PV | 60.24 |  | 2022-04-27 | 2021-08-03 | 2021-10-18 | 2022-04-14 | 2025-09-09 | No |  | No |  |  | Not Required
24INR0102 | Val Vista Grid BESS 2 | SS Completed, FIS Started, No IA | Val Vista Grid, LLC | Tap 345kV 8383 North Edinburg - 80137 Stewart Road | Hidalgo | SOUTH | 2028-06-01 | OTH | BA | 210.56 |  | 2021-09-30 | 2021-10-01 | 2021-12-09 | 2021-10-01 |  | Yes |  | No | Not Required | Not Required
24INR0103 | Opuntia Solar SLF | SS Completed, FIS Started, No IA | Opuntia Solar, LLC | tap 138kV 5607 Warburton - 8912 Medio Creek | Refugio | COASTAL | 2028-03-10 | SOL | PV | 102.04 |  | 2021-08-24 | 2021-08-24 | 2021-11-16 | 2021-08-09 |  | No |  | No | Not Required | Not Required | Not Required
24INR0104 | Braswell Solar | SS Completed, FIS Started, No IA | Gransolar Texas Nine, LLC | Tap 69kV 147 Lorena - 3580 Eddy Substation (Will be converted to 138kV line before 3/14/25 per TSP) | McLennan | NORTH | 2028-03-15 | SOL | PV | 42.6 |  | 2022-04-20 | 2021-08-30 | 2021-11-18 | 2022-04-08 |  | No |  | No | Not Required | Not Required | Not Required
24INR0106 | Payne Battlecreek | SS Completed, FIS Started, IA | Gransolar Texas Ten, LLC | tap 138kV 213 Haney - 3515 Hubbard | Hill | NORTH | 2027-08-25 | SOL | PV | 84.99 |  | 2022-03-23 | 2021-08-12 | 2021-10-29 | 2022-03-10 |  | No | 2024-02-23 | No | Not Required | Not Required | Not Required
24INR0108 | Louisa Energy Storage | SS Completed, FIS Started, IA | VESI 49 LLC | 138 kV Helotes (#5200) | Bexar | SOUTH | 2029-03-12 | OTH | BA | 102.77 |  | 2021-11-16 | 2021-11-16 | 2022-01-17 | 2021-11-08 |  | No | 2025-02-27 | Yes | Not Required | Not Required
24INR0109 | Oriana BESS | SS Completed, FIS Started, IA | Oriana Solar LLC | Tap 138kV 5502 Rayburn - 5584 Vanderbilt | Victoria | SOUTH | 2026-06-15 | OTH | BA | 60.3 |  | 2022-02-24 | 2021-08-25 | 2021-11-17 | 2022-02-14 |  |  | 2023-02-27 | Yes | Not Required | Not Required |  | 2023-08-25
24INR0110 | Kildare | SS Completed, FIS Completed, No IA | Galsol, LLC | 5524 Cordele 69 Sub 69 kV | Jackson | SOUTH | 2026-09-30 | SOL | PV | 70 |  | 2022-01-19 | 2022-01-28 | 2022-04-26 | 2022-01-18 | 2023-12-06 |  |  | No |  |  | Not Required
24INR0111 | BRP Triton BESS | SS Completed, FIS Started, No IA | BRP Triton BESS LLC | 138 kV Comanche Switch Substation (#1441) | Comanche | NORTH | 2026-12-01 | OTH | BA | 205.36 |  | 2021-10-18 | 2021-10-18 | 2022-01-12 | 2021-10-08 |  |  |  | No | Not Required | Not Required
24INR0115 | Aster Solar | SS Completed, FIS Started, No IA | Aster Solar | 7042 Zorn 345kV | Guadalupe | SOUTH | 2029-06-01 | SOL | PV | 203.52 | COD | 2022-06-16 | 2021-09-21 | 2021-12-09 | 2022-05-24 |  |  |  | No |  |  | Not Required
24INR0116 | Hart Wind | SS Completed, FIS Completed, IA | Hart Wind Project LLC | Tap 345kV 23912 OGALLALA - 23920 BLACKWATER DRAW SWITCH | Castro | PANHANDLE | 2025-10-31 | WIN | WT | 163.4 |  | 2022-05-20 | 2021-10-21 | 2022-01-17 | 2022-05-06 | 2023-11-13 |  | 2023-10-06 | Yes |  |  | Not Required | 2024-10-31 | 2024-12-12 | 2024-12-11 |  |  | 2025-06-25 | 2025-07-01
24INR0117 | Utley Solar | SS Completed, FIS Started, No IA | Palmera Solar Development LLC | Tap 345kV 3381 Big Brown Switch - 3391 Jewett | Freestone | NORTH | 2027-09-30 | SOL | PV | 221.78 |  | 2022-03-23 | 2021-09-07 | 2021-11-29 | 2022-03-09 |  |  |  | No |  |  | Not Required
24INR0118 | Possum Kingdom Solar | SS Completed, FIS Completed, No IA | PK Solar, LLC | Tap 345kV 1421 Willow Creek Switch – 11523 Thomas Price | Jack | NORTH | 2027-10-29 | SOL | PV | 262.22 |  | 2022-06-02 | 2021-09-13 | 2021-11-29 | 2022-05-23 | 2025-03-18 | No |  | No | Not Required | Not Required | Not Required |  |  |  | 2025-05-01 | 2026-05-08
24INR0120 | Eytcheson Ranches Solar | SS Completed, FIS Started, No IA | Gransolar Texas Fourteen, LLC | Tap 69kV 186 Navarro Mills – 107 Prairie Hill | Navarro | NORTH | 2028-01-01 | SOL | PV | 76.42 |  | 2022-05-31 | 2021-09-14 | 2021-11-29 | 2022-05-26 |  | No |  | No |  |  | Not Required
24INR0121 | PHOTO BESS 1 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2027-09-01 | OTH | BA | 75 |  | 2022-05-31 | 2021-10-29 | 2021-12-08 | 2022-05-13 |  |  |  | No
24INR0122 | PHOTO BESS 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2027-09-01 | OTH | BA | 150 |  | 2022-05-31 | 2021-10-29 | 2021-12-08 | 2022-05-13 |  |  |  | No
24INR0124 | High Noon Solar | SS Completed, FIS Started, IA | High Noon Solar Project, LLC | Tap 138kV 445 Yates - 444 Covington | Hill | NORTH | 2028-05-09 | SOL | PV | 182 |  | 2021-11-02 | 2021-11-03 | 2021-12-29 | 2021-11-02 |  |  | 2024-05-03 | Yes | Not Required | Not Required | Not Required | 2025-02-12
24INR0125 | Grasshopper Solar | SS Completed, FIS Started, No IA | Grasshopper Solar LLC | Smoky Hill 345kV Sub (Bus #6104) Locational coordinates : 33.34414; 99.624637 | Haskell | WEST | 2028-10-01 | SOL | PV | 407.68 |  | 2021-09-28 | 2021-09-28 | 2021-12-09 | 2021-09-22 |  |  |  | No |  |  | Not Required
24INR0126 | High Noon Storage | SS Completed, FIS Started, IA | High Noon Solar Project, LLC | Tap 138kV 445 Yates - 444 Covington | Hill | NORTH | 2028-05-09 | OTH | BA | 94 |  | 2021-11-02 | 2021-11-03 | 2021-12-29 | 2021-11-02 |  |  | 2024-05-08 | Yes | Not Required | Not Required |  | 2025-02-12
24INR0127 | Naduah Solar | SS Completed, FIS Started, No IA | Gransolar Texas Fifteen, LLC | Tap 69kV Ben Hur (99) - Prairie Hill (107) | Limestone | NORTH | 2027-10-15 | SOL | PV | 77.6 |  | 2022-06-17 | 2021-09-27 | 2021-12-09 | 2022-06-06 |  | No |  | No |  |  | Not Required
24INR0128 | Desna BESS | SS Completed, FIS Completed, IA | BRP Desna BESS LLC | 39703 TNP FM524 138kV | Brazoria | COASTAL | 2026-03-31 | OTH | BA | 205.46 |  | 2021-12-05 | 2021-12-15 | 2022-03-11 | 2021-11-29 | 2024-08-01 |  | 2023-09-15 | Yes | Not Required | Not Required |  | 2024-10-30 | 2024-10-30 | 2024-10-30
24INR0130 | BRP Artemis BESS | SS Completed, FIS Started, No IA | BRP Artemis BESS LLC | 40600 Roans Prairie Substation 345kV | Grimes | NORTH | 2028-12-01 | OTH | BA | 411.32 |  | 2021-12-15 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  | No |  | No
24INR0131 | Zelus BESS | SS Completed, FIS Started, No IA | BRP Zelus BESS LLC | the 138 kV Zapata Substation (#8299; AEP) | Zapata | SOUTH | 2027-12-01 | OTH | BA | 201.03 |  | 2021-12-15 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No
24INR0133 | BRP Hestia BESS | SS Completed, FIS Started, No IA | BRP Hestia BESS LLC | the 69 kV Rock Springs Substation (#78238, LCRA) | Edwards | SOUTH | 2028-12-01 | OTH | BA | 29.05 |  | 2021-12-28 | 2021-12-29 | 2022-03-25 | 2021-12-28 |  |  |  | No
24INR0134 | BRP Hemera BESS | SS Completed, FIS Started, No IA | BRP Hemera BESS LLC | 345 kV Deaf Smith Substation (#23908, Oncor) | Deaf Smith | PANHANDLE | 2029-12-01 | OTH | BA | 206.96 |  | 2021-12-20 | 2021-12-29 | 2022-03-25 | 2021-12-14 |  |  |  | No
24INR0135 | BRP Mekong BESS | SS Completed, FIS Started, No IA | BRP Mekong BESS LLC | Tap 345 kV line from Twin Oak Switch (#3400) to TPN One Plant Switchyard (#39950) | Robertson | NORTH | 2027-12-01 | OTH | BA | 409.88 |  | 2021-12-15 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No
24INR0136 | Eagle Springs Storage | SS Completed, FIS Completed, No IA | Eagle Springs Solar, LLC | Tap Lake Creek Substation (#6835) – Enloe Switching station (#6834) 138 kV Line | Delta | NORTH | 2026-12-31 | OTH | BA | 33.14 |  | 2022-06-20 | 2021-10-18 | 2022-01-12 | 2022-06-13 | 2025-09-17 | No |  | No
24INR0137 | Eagle Springs Solar | SS Completed, FIS Completed, No IA | Eagle Springs Solar, LLC | Tap Lake Creek Substation (#6835) – Enloe Switching station (#6834) 138 kV Line | Delta | NORTH | 2026-12-31 | SOL | PV | 77.21 |  | 2022-06-20 | 2021-10-18 | 2022-01-12 | 2022-06-13 | 2025-09-17 | No |  | No |  |  | Not Required
24INR0138 | Midpoint Storage | SS Completed, FIS Completed, IA | Midpoint Solar, LLC | 138 KV Tap #3518 BLUM to #237 Blanton | Hill | NORTH | 2025-12-31 | OTH | BA | 50.9 |  | 2022-05-24 | 2021-10-15 | 2022-01-04 | 2022-05-11 | 2024-10-31 | No | 2023-10-31 | Yes | Not Required | Not Required |  | 2023-11-13 | 2024-11-01 | 2024-11-01 |  |  | 2025-08-27
24INR0139 | Midpoint Solar | SS Completed, FIS Completed, IA | Midpoint Solar, LLC | 138 KV Tap #3518 BLUM to #237 Blanton | Hill | NORTH | 2025-12-31 | SOL | PV | 98.3 |  | 2022-05-18 | 2021-10-15 | 2022-01-04 | 2022-05-04 | 2024-10-31 | No | 2023-10-31 | Yes | Not Required | Not Required | Not Required | 2023-11-13 | 2024-11-01 | 2024-11-01 |  |  | 2025-08-25
24INR0140 | Gaia Storage | SS Completed, FIS Completed, IA | Gaia Solar, LLC | Tap 138kV 3127 Trinidad SES - 3454 Montfort Switch | Navarro | NORTH | 2026-05-01 | OTH | BA | 78.81 |  | 2022-05-23 | 2021-12-29 | 2022-03-23 | 2022-05-11 | 2025-05-16 | No | 2023-11-08 | Yes | Not Required | Not Required |  | 2023-11-15 | 2025-07-24 | 2025-07-28
24INR0141 | Gaia Solar | SS Completed, FIS Completed, IA | Gaia Solar, LLC | Tap 138kV 3127 Trinidad SES - 3454 Montfort Switch | Navarro | NORTH | 2026-05-01 | SOL | PV | 144.02 |  | 2022-05-23 | 2021-12-29 | 2022-03-23 | 2022-05-11 | 2025-05-16 | No | 2023-11-08 | Yes | Not Required | Not Required | Not Required | 2023-11-15 | 2025-07-24 | 2025-07-28
24INR0142 | De Los Santos | SS Completed, FIS Started, No IA | BRP De Los Santos BESS LLC | 78016 Sunglow Substation 138kV | Maverick | SOUTH | 2027-12-01 | OTH | BA | 200.97 |  | 2022-02-09 | 2022-05-10 | 2022-08-05 | 2022-04-18 |  |  |  | No | Not Required | Not Required
24INR0145 | Calpine Guadalupe Peakers | SS Completed, FIS Started, No IA | Guadalupe Peaking Energy Center, LLC | 7044 Marion 345kV | Guadalupe | SOUTH | 2027-05-23 | GAS | GT | 450 |  | 2021-10-26 | 2021-11-15 | 2022-02-11 | 2021-10-18 |  |  |  | No
24INR0150 | Lupinus Solar 1 | SS Completed, FIS Completed, IA | Lupinus Solar, LLC | Tap 345 kV 11699 Woodard Switch - 1695 Monticello SES | Franklin | NORTH | 2027-09-13 | SOL | PV | 164.86 |  | 2022-05-23 | 2021-12-08 | 2022-03-04 | 2022-05-11 | 2024-07-12 | No | 2025-06-26 | Yes |  |  | Not Required | 2025-08-05
24INR0153 | Lupinus Storage 1 | SS Completed, FIS Completed, No IA | Lupinus Solar, LLC | Tap 345 kV 11699 Woodard Switch - 1695 Monticello SES | Franklin | NORTH | 2027-09-13 | OTH | BA | 82.97 |  | 2022-05-23 | 2021-12-13 | 2022-03-10 | 2022-05-11 | 2024-07-12 | No |  | Yes |  |  |  | 2025-09-22
24INR0154 | Lupinus Solar 2 | SS Completed, FIS Completed, IA | Lupinus Solar 2, LLC | 1794 Monticello Tap Substation 138 kV | Franklin | NORTH | 2027-04-03 | SOL | PV | 244.24 |  | 2022-05-23 | 2021-12-13 | 2022-03-10 | 2022-05-11 | 2024-06-26 | No | 2025-03-04 | No | Not Required | Not Required | Not Required
24INR0155 | Lupinus Storage 2 | SS Completed, FIS Completed, IA | Lupinus Solar 2, LLC | 1794 Monticello Tap Substation 138 kV | Franklin | NORTH | 2027-04-03 | OTH | BA | 122.92 |  | 2022-06-03 | 2021-12-13 | 2022-03-10 | 2022-05-11 | 2024-06-26 | No | 2025-03-04 | No | Not Required | Not Required
24INR0156 | Moonstone Solar Project | SS Completed, FIS Completed, IA | Moon Stone Solar Farm, LLC | Tap 138kV Eagle Creek (5132) to Floresville (5155) | Wilson | SOUTH | 2030-03-24 | SOL | PV | 145.81 |  | 2022-06-20 | 2021-10-27 | 2022-01-24 | 2022-06-07 | 2024-01-18 |  | 2025-02-17 | No |  |  | Not Required
24INR0157 | Merope BESS | SS Completed, FIS Started, No IA | BRP Merope BESS LLC | 345 kV Corn Trail Switch Substation (#11441) | Comanche | NORTH | 2028-03-01 | OTH | BA | 402.44 |  | 2021-12-13 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No
24INR0160 | Huisache Solar | SS Completed, FIS Started, IA | Huisache Solar, LLC | Tapping the Elm Creek to Shaula circuit 1 | Wilson | SOUTH | 2029-06-30 | SOL | PV | 125.59 |  | 2022-07-11 | 2021-12-03 | 2022-03-01 | 2022-06-22 |  |  | 2025-08-12 | No | Not Required | Not Required | Not Required
24INR0161 | Miranda Solar Project | SS Completed, FIS Completed, IA | Miranda Solar Project, LLC | Tap 345kV 5709 Fowlerton - 5901 San Miguel Ckt 1 | McMullen | SOUTH | 2027-12-06 | SOL | PV | 261.42 |  | 2022-06-27 | 2021-11-03 | 2022-01-07 | 2022-06-22 | 2024-09-03 |  | 2024-07-16 | Yes | Not Required |  | Not Required
24INR0166 | Stillhouse Solar | SS Completed, FIS Completed, IA | Stillhouse Solar LLC | tap 345 kV Bell County East Switch (3687) – Little Pond Switch (3377) | Bell | NORTH | 2025-10-20 | SOL | PV | 210.8 | COD | 2021-11-17 | 2021-11-24 | 2022-02-19 | 2021-11-23 | 2024-10-31 | No | 2023-06-07 | Yes | Not Required | Not Required | Not Required | 2024-10-31 | 2024-10-31 | 2024-10-31 |  |  | 2025-05-20 | 2025-07-07
24INR0167 | OCI SunRoper | SS Completed, FIS Completed, No IA | OCI SunRoper LLC | tap138kV #43190 South Lane City to #42985 Dyann CKT#60 | Wharton | SOUTH | 2027-07-12 | SOL | PV | 265.1 |  | 2021-11-18 | 2021-11-24 | 2022-02-19 | 2021-11-23 | 2024-05-30 | No |  | No |  |  | Not Required
24INR0168 | Tejano Storage | SS Completed, FIS Started, No IA | Tejano Storage, LLC | Tap 138kV 8125 Lolita - 8172 Victoria | Victoria | SOUTH | 2029-07-01 | OTH | BA | 152.31 |  | 2022-05-06 | 2022-03-30 | 2022-06-26 | 2022-04-18 |  | No |  | No
24INR0172 | Smith Lake Solar DC | SS Completed, FIS Started, No IA | Smith Lake Solar | TAP 345 KV 44645 SINGLETON - 44900 ZENITH Ckt #99 | Grimes | NORTH | 2026-11-30 | SOL | PV | 402 |  | 2022-11-30 | 2022-02-07 | 2022-05-06 | 2022-11-02 |  | Yes |  | No |  |  | Not Required
24INR0174 | Solar Star North Herty Storage | SS Completed, FIS Started, No IA | Solar Star North Herty Storage, LLC | 3307 Redland Switch 138 kV | Angelina | NORTH | 2027-08-25 | OTH | BA | 125.4 |  | 2022-09-09 | 2022-02-21 | 2022-05-21 | 2022-08-15 |  |  |  | No
24INR0178 | Cumulus Grid BESS | SS Completed, FIS Completed, IA | Cumulus Grid, LLC | 1906 Venus Switch Substation 345kV | Ellis | NORTH | 2028-01-01 | OTH | BA | 210.74 | SFS/NtP | 2022-11-01 | 2022-03-14 | 2022-04-18 | 2022-10-18 | 2025-01-27 |  | 2025-06-03 | Yes
24INR0180 | Frio Farm | SS Completed, FIS Started, No IA | PREMIER ENGINEERING USA CORP. | 8221 BIG FOOT4A 138kV | Frio | SOUTH | 2026-06-25 | SOL | PV | 106.5 |  | 2022-10-03 | 2021-12-20 | 2022-03-10 | 2022-09-13 |  |  |  | No |  |  | Not Required
24INR0181 | Bynum Solar Project | SS Completed, FIS Completed, IA | Bynum Solar Project, LLC | Tap 69kV 37470 Olsen - 37520 Sycamore | Coryell | NORTH | 2026-01-21 | SOL | PV | 56 | COD | 2022-06-02 | 2021-12-18 | 2022-03-11 | 2022-05-23 | 2025-02-24 | No | 2023-11-22 | Yes | Not Required |  | Not Required | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-01-04
24INR0182 | DeSpain Solar Project | SS Completed, FIS Started, No IA | Gransolar Texas Thirteen LLC | 7425 Odlaw Switch 138kV | Kinney | SOUTH | 2027-12-15 | SOL | PV | 236.17 |  | 2022-06-22 | 2021-12-05 | 2022-03-02 | 2022-06-16 |  |  |  | No |  |  | Not Required
24INR0184 | Slate Solar Project | SS Completed, FIS Started, No IA | Ignis TX Solar Three LLC | Tap 138kV 8646 Rio Bravo - 8985 San Ygancio | Zapata | SOUTH | 2027-10-30 | SOL | PV | 104.89 |  | 2022-08-03 | 2021-12-20 | 2022-03-10 | 2022-07-13 |  | No |  | No |  |  | Not Required
24INR0186 | Rowdy Creek Solar | SS Completed, FIS Started, IA | Rowdy Creek Solar LLC | Tap 345kV 1692 Paris Switch – 1690 Valley SES | Lamar | NORTH | 2027-04-01 | SOL | PV | 351.78 |  | 2021-12-13 | 2022-01-28 | 2022-04-27 | 2022-01-25 |  |  | 2025-05-02 | Yes |  |  | Not Required | 2025-07-29
24INR0187 | Rowdy Creek BESS | SS Completed, FIS Started, IA | Rowdy Creek Solar LLC | Tap 345kV 1692 Paris Switch – 1690 Valley SES | Lamar | NORTH | 2027-04-01 | OTH | BA | 175.89 |  | 2021-12-13 | 2022-01-28 | 2022-04-27 | 2022-01-25 |  |  | 2025-05-02 | Yes | Not Required | Not Required |  | 2025-07-29
24INR0188 | Tehuacana Creek Solar | SS Completed, FIS Started, IA | Tehuacana Creek Solar LLC | Tap 345kV 3381 Big Brown – 68091 Navarro circuit | Navarro | NORTH | 2027-03-10 | SOL | PV | 505.43 |  | 2021-12-15 | 2021-12-20 | 2022-03-10 | 2021-12-09 |  |  | 2024-11-25 | Yes | Not Required | Not Required | Not Required | 2025-02-12
24INR0189 | Tehuacana Creek BESS SLF | SS Completed, FIS Completed, IA | Tehuacana Creek Solar LLC | Tap 345kV 3381 Big Brown – 68091 Navarro circuit #01 | Navarro | NORTH | 2027-03-10 | OTH | BA | 0 |  | 2021-12-15 | 2021-12-20 | 2022-03-10 | 2021-12-09 | 2024-04-09 |  | 2024-11-25 | Yes | Not Required | Not Required |  | 2025-02-12
24INR0196 | Dori BQ BESS | SS Completed, FIS Started, IA | Sunnyside Energy LLC | 138kV line Holmes (#47210) - Garden Villas (#42680); CNP | Harris | HOUSTON | 2027-08-30 | OTH | BA | 154 |  | 2022-01-05 | 2022-02-07 | 2022-05-06 | 2022-01-19 |  | No | 2023-05-31 | No | Not Required | Not Required
24INR0197 | Opuntia Storage SLF | SS Completed, FIS Started, No IA | Opuntia Solar, LLC | tap 138 kV 5607 Warburton - 8912 Medio Creek | Refugio | COASTAL | 2028-03-10 | OTH | BA | 0 |  | 2022-02-01 | 2022-02-07 | 2022-05-07 | 2022-01-20 |  | No |  | No | Not Required | Not Required
24INR0198 | Two Forks BESS | SS Completed, FIS Started, IA | Two Forks LLC | 684 SPRING 138kV | Cooke | NORTH | 2027-06-30 | OTH | BA | 309.8 |  | 2022-10-23 | 2022-01-28 | 2022-04-26 | 2022-10-13 |  | No | 2024-05-03 | Yes | Not Required |  |  | 2024-05-06
24INR0200 | White Tail Solar | SS Completed, FIS Started, No IA | Mule Deer Solar LLC | Tap 345kV Windmill (23910) – AJ Swope (23906) | Deaf Smith | PANHANDLE | 2027-09-21 | SOL | PV | 226.8 |  | 2022-11-09 | 2022-02-07 | 2022-05-07 | 2022-10-21 |  |  |  | No |  |  | Not Required
24INR0201 | Short Creek Solar | SS Completed, FIS Started, IA | Wichita Solar I, LLC | Tap 345kV 6101 Riley - 1425 Fisher Road Switch Ckt 1 | Wichita | WEST | 2027-12-17 | SOL | PV | 628.33 |  | 2022-10-17 | 2022-01-20 | 2022-04-18 | 2022-10-12 |  | No | 2024-10-02 | Yes | Not Required |  | Not Required | 2025-02-12
24INR0204 | Trigo Solar Project | SS Completed, FIS Started, No IA | Ignis TX Solar Two LLC | 5705 Fowlerton 138kV | La Salle | SOUTH | 2025-12-15 | SOL | PV | 145.62 |  | 2022-08-15 | 2022-01-07 | 2022-04-01 | 2022-07-27 |  |  |  | No |  |  | Not Required
24INR0205 | Wensowitch Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Wensowitch LLC | Tapping 138 kV line Telico (192) to Montfort Switch (3454) | Navarro | NORTH | 2028-03-28 | SOL | PV | 146.08 |  | 2022-08-15 | 2022-01-07 | 2022-04-01 | 2022-07-25 |  |  |  | No | Not Required | Not Required | Not Required
24INR0206 | Glasgow Solar | SS Completed, FIS Completed, IA | Glasgow Solar LLC | Tap 345kV #2466 Big Onion - #68091 Navarro | Navarro | NORTH | 2027-03-16 | SOL | PV | 203.5 |  | 2022-02-03 | 2022-02-07 | 2022-05-07 | 2022-01-12 | 2023-09-10 | No | 2023-11-08 | Yes | Not Required | Not Required | Not Required | 2025-02-12
24INR0207 | Glasgow Storage | SS Completed, FIS Completed, IA | Glasgow Solar LLC | Tap 345kV #2466 Big Onion - #68091 Navarro | Navarro | NORTH | 2027-03-16 | OTH | BA | 101 |  |  | 2022-02-21 | 2022-05-07 | 2022-02-02 | 2023-09-10 |  | 2023-11-08 | Yes | Not Required | Not Required |  | 2025-02-12
24INR0208 | Eastbell Milam Solar II | SS Completed, FIS Completed, IA | Cattlemen Solar Park II LLC | 345 kV Bell County East Switch (bus# 3687) - TNP One (bus# 39950) circuit 2 | Milam | SOUTH | 2025-10-31 | SOL | PV | 150.6 | COD | 2022-02-07 | 2022-03-07 | 2022-06-02 | 2022-02-03 | 2024-02-01 |  | 2023-10-25 | Yes |  |  | Not Required | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  | 2024-09-13 | 2024-11-20
24INR0210 | Raven Storage | SS Completed, FIS Completed, No IA | Raven Storage, LLC | Tap 138kV 44740 Wallis - 44190 East Bernard CKT#65 | Wharton | SOUTH | 2026-07-31 | OTH | BA | 101.4 |  | 2022-11-01 | 2022-01-28 | 2022-04-26 | 2022-10-18 | 2025-09-16 | No |  | No
24INR0213 | Owens Solar | SS Completed, FIS Started, No IA | Owens Solar LLC | Tap 138kV line between 177 BOSQUE and 181 Cayote | Bosque | NORTH | 2025-12-31 | SOL | PV | 203.5 |  | 2022-02-01 | 2022-02-07 | 2022-05-06 | 2022-01-12 |  |  |  | No |  |  | Not Required
24INR0233 | St. Gall Solar | SS Completed, FIS Started, No IA | St. Gall Solar LLC | 38355 Leon Creek 138kV | Pecos | WEST | 2026-06-01 | SOL | PV | 207 |  | 2022-02-07 | 2022-02-28 | 2022-05-27 | 2022-02-24 |  | No |  | No |  |  | Not Required
24INR0234 | Rock N' Roll Storage SLF | SS Completed, FIS Started, No IA | Rock N’ Roll Solar, LLC | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2027-05-02 | OTH | BA | 0 |  | 2022-02-10 | 2022-02-28 | 2022-05-27 | 2022-02-11 |  | No |  | No | Not Required | Not Required
24INR0235 | Rock N' Roll Storage Two | SS Completed, FIS Started, No IA | Rock N' Roll Solar, LLC | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2027-08-30 | OTH | BA | 206 | COD | 2022-02-24 | 2022-02-28 | 2022-05-27 | 2022-02-11 |  | No |  | No | Not Required | Not Required
24INR0238 | Appaloosa Run BESS | SS Completed, FIS Started, No IA | APPALOOSA RUN STORAGE, LLC | New Palouse 138kV (#60278) | Upton | WEST | 2026-08-30 | OTH | BA | 103 |  | 2022-02-11 | 2022-03-07 | 2022-06-02 | 2022-03-01 |  |  |  | No |  |  | 2024-02-09
24INR0239 | Trojan BESS SLF | SS Completed, FIS Started, No IA | Trojan BESS | 11735 Cedar Elm Switch 345kV | Cooke | NORTH | 2027-07-01 | OTH | BA | 0 |  | 2022-05-17 | 2022-06-02 | 2022-08-30 | 2022-04-19 |  |  |  | No
24INR0247 | Lacy Creek Energy Storage SLF | SS Completed, FIS Started, No IA | Edmondson Ranch Wind Holdings, LLC | 59907 Bernoulli 345kV | Glasscock | WEST | 2027-07-01 | OTH | BA | 0 |  | 2022-04-02 | 2024-04-09 | 2024-07-05 | 2024-02-20 |  |  |  | Yes
24INR0249 | Hickerson BESS | SS Completed, FIS Started, No IA | Hickerson BESS | tap 345kV 68091 Navarro - 68040 Kopperl | Bosque | NORTH | 2027-07-01 | OTH | BA | 0 |  | 2022-02-24 | 2022-03-07 | 2022-06-02 | 2022-02-24 |  |  |  | No
24INR0252 | Kruth Storage | SS Completed, FIS Started, No IA | Martinez Energy Storage LLC | 3319 Redland 138kV | Angelina | NORTH | 2026-03-31 | OTH | BA | 203 |  | 2022-08-05 | 2022-02-28 | 2022-05-27 | 2022-07-22 |  |  |  | No | Not Required | Not Required
24INR0256 | Kennedy Solar | SS Completed, FIS Started, No IA | Kennedy Bypass Solar LLC | Tap 345kV 68040 Kopprl Capacitor Yard - 68091 Navarro | Navarro | NORTH | 2028-12-31 | SOL | PV | 101.5 |  | 2022-07-11 | 2022-03-07 | 2022-06-02 | 2022-06-29 |  |  |  | No |  |  | Not Required
24INR0258 | Zeissel Solar | SS Completed, FIS Started, IA | ZSS Power, LLC | #60094 Joule 345kV | Knox | WEST | 2028-06-30 | SOL | PV | 457.5 |  | 2022-05-19 | 2022-02-28 | 2022-05-27 | 2022-04-25 |  |  | 2024-02-24 | Yes | Not Required | Not Required | Not Required | 2025-02-12
24INR0260 | Lager Storage | SS Completed, FIS Started, No IA | Momentum Lager LLC | 8031 Gillrina 69kV | Nueces | COASTAL | 2028-06-30 | OTH | BA | 31.1 |  | 2022-02-21 | 2022-02-28 | 2022-05-27 | 2022-02-23 |  | No |  | No
24INR0262 | Lan Battery SLF | SS Completed, FIS Started, No IA | BR Solar, LLC | Tap 345kV 1729 Valley South – 1692 Paris Switch | Lamar | NORTH | 2028-08-26 | OTH | BA | 0 |  | 2022-04-04 | 2022-06-10 | 2022-09-06 | 2022-04-27 |  | No |  | No
24INR0269 | Bar Candela Solar SLF | SS Completed, FIS Completed, IA | Bar Candela Solar Project LLC | Long Lake Sub (Bus 3280) – Long Lake Tap Switch (Bus 3279) | Freestone | NORTH | 2027-12-31 | SOL | PV | 200.3 |  | 2022-12-16 | 2022-03-21 | 2022-06-13 | 2022-12-06 | 2024-02-09 |  | 2025-05-06 | No |  |  | Not Required
24INR0271 | Bar Candela Storage SLF | SS Completed, FIS Completed, IA | Bar Candela Storage Project LLC | Long Lake Sub (Bus 3280) – Long Lake Tap Switch (Bus 3279) | Freestone | NORTH | 2027-12-31 | OTH | BA | 0 |  | 2022-12-16 | 2022-03-21 | 2022-06-13 | 2022-12-05 | 2024-02-09 |  | 2025-05-06 | No | Not Required | Not Required
24INR0272 | Brushy Creek Storage SLF | SS Completed, FIS Started, No IA | Brushy Creek Solar | the 345 kV San Angelo Red Creek Substation (#6444); AEP | Tom Green | WEST | 2028-06-01 | OTH | BA | 0 |  | 2022-03-03 | 2022-03-30 | 2022-06-26 | 2022-03-08 |  | No |  | No
24INR0274 | Bufflehead BESS | SS Completed, FIS Completed, IA | Boxcar Energy Storage, LLC | 2475 Lavon Switch 138kV | Collin | NORTH | 2027-02-15 | OTH | BA | 153.3 |  | 2022-02-25 | 2022-03-07 | 2022-06-02 | 2022-02-28 | 2023-05-04 |  | 2024-04-10 | No | Not Required | Not Required
24INR0275 | Picadillo BESS | SS Completed, FIS Completed, IA | Black Mountain Energy Storage II | 23837 Buffalo 138kV | Martin | WEST | 2026-12-15 | OTH | BA | 100.83 |  | 2022-02-25 | 2022-03-07 | 2022-06-02 | 2022-02-28 | 2023-06-13 |  | 2024-01-23 | No
24INR0280 | Port Bay ESC | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | 8434 Rockport Substation (ROCKPORT4A) 138kV | Aransas | COASTAL | 2027-06-28 | OTH | BA | 200 |  | 2022-03-18 | 2022-03-21 | 2022-06-16 | 2022-03-07 |  | No |  | No
24INR0281 | Red Egret BESS | SS Completed, FIS Completed, IA | Red Egret LLC | 38820 FREEWAY PARK 138KV | Galveston | HOUSTON | 2026-08-31 | OTH | BA | 310.58 |  | 2022-10-23 | 2022-03-14 | 2022-06-09 | 2022-10-13 | 2025-08-21 | No | 2023-06-07 | Yes | Not Required | Not Required |  | 2023-08-08 | 2024-08-13
24INR0282 | Royal River BESS | SS Completed, FIS Started, No IA | Royal River LLC | Tap 138kV 42110 Angleton - 43381 West Columbia | Brazoria | COASTAL | 2027-01-11 | OTH | BA | 310.7 |  | 2023-02-08 | 2022-03-30 | 2022-06-27 | 2022-12-19 |  | No |  | No
24INR0285 | APV Plumwood Storage | SS Completed, FIS Completed, IA | APV Lonestar Energy LLC | Tap 138kV 40171 Baytown - 40015Cedar Bayou Plant | Chambers | HOUSTON | 2027-05-01 | OTH | BA | 200.82 |  | 2022-03-18 | 2022-03-30 | 2022-06-26 | 2022-03-22 | 2024-04-24 | No | 2024-09-03 | No | Not Required | Not Required
24INR0287 | Rockridge Solar Project | SS Completed, FIS Started, IA | Magnolia Solar Development LLC | 7225 Hickory Forest 138kV | Guadalupe | SOUTH | 2027-04-03 | SOL | PV | 211.2 |  | 2022-08-10 | 2022-04-18 | 2022-07-12 | 2022-08-03 |  |  | 2025-03-14 | No | Not Required | Not Required | Not Required
24INR0289 | Ratcliff Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Ratcliff | Tap 138kV 3279 Long Lake Tap Switch - 3280 Long Lake | Freestone | NORTH | 2027-09-07 | SOL | PV | 85.74 |  | 2022-08-22 | 2022-06-27 | 2022-09-23 | 2022-08-17 |  |  |  | No |  |  | Not Required
24INR0291 | Rubicon Alpha Wind | SS Completed, FIS Started, IA | Throckmorton Wind, LLC | Tap 345kV 60791 Perigee – 6235 Abilene Mulberry Creek | Haskell | WEST | 2027-07-31 | WIN | WT | 225.6 |  | 2022-03-28 | 2022-05-10 | 2022-08-06 | 2022-04-15 |  |  | 2024-05-08 | Yes | Not Required | Not Required | Not Required | 2025-02-13
24INR0294 | Citrus Flatts BESS | SS Completed, FIS Completed, IA | Citrus Flatts Energy Center, LLC | 80022 Oleander 138kV | Cameron | COASTAL | 2026-05-16 | OTH | BA | 101.2 |  | 2022-03-21 | 2022-03-30 | 2022-06-26 | 2022-03-24 | 2025-02-20 | No | 2023-09-08 | Yes | Not Required | Not Required |  | 2025-02-13 | 2025-04-18 | 2025-04-29 | 2024-10-24 | 2025-08-28
24INR0295 | Lucky Bluff BESS SLF | SS Completed, FIS Completed, IA | Lucky Bluff BESS LLC | 1652 Fullhouse 138kV tapped in 138kV 1641 Stephenville - 1636 Dublin | Erath | NORTH | 2025-10-15 | OTH | BA | 100.8 |  | 2022-03-23 | 2022-03-30 | 2022-06-26 | 2022-03-24 | 2024-10-23 | No | 2023-11-08 | Yes | Not Required | Not Required |  | 2023-11-20 | 2024-10-31 | 2024-10-31 |  |  | 2025-08-19 | 2025-09-17
24INR0298 | Leighton Solar SLF | SS Completed, FIS Started, IA | Lavender Solar LLC | 99 BENHUR 69kV | Limestone | NORTH | 2027-04-30 | SOL | PV | 183 |  | 2022-04-27 | 2022-05-11 | 2022-08-05 | 2022-03-16 |  | No | 2024-05-28 | Yes | Not Required | Not Required | Not Required | 2025-02-13
24INR0302 | Pintail Pass BESS | SS Completed, FIS Completed, IA | Pintail Pass BESS, LLC | 8249 ANGSTROM 345KV | San Patricio | COASTAL | 2025-09-30 | OTH | BA | 207.25 |  | 2022-04-02 | 2022-04-18 | 2022-06-16 | 2022-04-07 | 2024-10-15 | No | 2023-05-16 | Yes |  |  |  | 2024-11-01 | 2024-11-01 | 2024-11-01
24INR0303 | Erika Solar | SS Completed, FIS Completed, IA | Erika Solar, LLC | Tap 345kV ELKTON 5 (#3105 ) to Tricrn1 5 (#2432) | Kaufman | NORTH | 2027-06-30 | SOL | PV | 200.5 | MW Size SFS/NtP | 2022-05-02 | 2022-07-25 | 2022-10-18 | 2022-07-06 | 2025-09-15 | No | 2023-10-12 | Yes | Not Required | Not Required | Not Required | 2025-09-15
24INR0304 | Jack Barton BESS | SS Completed, FIS Completed, IA | Jack Barton BESS | 1599 Barton Chapel Wind Farm station 138kV | Jack | NORTH | 2027-04-13 | OTH | BA | 47.34 |  | 2022-04-04 | 2022-08-05 | 2022-11-01 | 2022-04-20 | 2023-09-11 |  | 2024-03-17 | No | Not Required | Not Required
24INR0305 | MRG Goody Storage | SS Completed, FIS Completed, IA | MRG Goody Solar Project LLC | Tap 138 kV Toco Switch (#1700) – Paris Switch (#1693) | Lamar | NORTH | 2026-05-02 | OTH | BA | 52.29 |  | 2022-04-07 | 2022-05-10 | 2022-08-05 | 2022-04-11 | 2025-06-17 | No | 2023-11-07 | Yes | Not Required | Not Required |  | 2025-02-12 | 2025-07-31 | 2025-07-31
24INR0306 | Arroyo Storage | SS Completed, FIS Completed, IA | BT Cantwell Solar, LLC | Tap 345kV 8318 Rio Hondo - 8317 La Palma (New Gulch Substation ) | Cameron | COASTAL | 2026-04-01 | OTH | BA | 183.76 | COD | 2022-05-03 | 2022-05-10 | 2022-08-05 | 2022-04-26 | 2024-04-30 |  | 2022-08-10 | Yes |  |  |  | 2024-06-24 | 2024-06-24 | 2024-10-29
24INR0308 | Forts Trail Solar | SS Completed, FIS Started, No IA | JC Central Bluff, LLC | 11406 Central Bluff Switch 345kV | Taylor | WEST | 2028-03-03 | SOL | PV | 200.81 |  | 2022-06-07 | 2022-06-02 | 2022-08-30 | 2022-06-03 |  | No |  | No | Not Required | Not Required | Not Required
24INR0313 | Backbone Creek BESS | SS Completed, FIS Completed, IA | Backbone Creek BESS LLC | 7351 STARCKE 138kV | Burnet | SOUTH | 2026-08-10 | OTH | BA | 124.1 |  | 2022-05-09 | 2022-04-18 | 2022-07-08 | 2022-04-27 | 2025-09-08 |  | 2023-12-22 | Yes |  |  |  | 2023-12-22
24INR0315 | Black Springs BESS | SS Completed, FIS Completed, IA | Black Springs BESS LLC | 1571 ORAN 138KV | Palo Pinto | NORTH | 2025-10-15 | OTH | BA | 120.68 |  | 2022-06-02 | 2022-04-18 | 2022-07-12 | 2022-05-05 | 2023-08-17 |  | 2023-10-18 | Yes |  |  |  | 2024-04-19 | 2024-10-04 | 2024-10-31 |  |  | 2025-08-20 | 2025-09-16
24INR0319 | Burro Loco Energy Storage | SS Completed, FIS Started, No IA | VESI | 8626 Resaca 69kV | Cameron | COASTAL | 2026-12-01 | OTH | BA | 25.14 |  | 2022-07-14 | 2022-07-18 | 2022-10-14 | 2022-07-08 |  |  |  | No | Not Required | Not Required
24INR0326 | Blarney Solar | SS Completed, FIS Completed, IA | Blarney Solar Project LLC | tap 138kV 1815 Cumby Tap - 1819 Commerce South Sub | Hopkins | NORTH | 2027-07-01 | SOL | PV | 81 |  | 2022-04-20 | 2022-07-05 | 2022-10-01 | 2022-04-21 | 2023-10-18 |  | 2024-04-22 | No |  |  | Not Required
24INR0329 | XE Murat [Adlong] Storage | SS Completed, FIS Completed, IA | Liberty 1 Solar LLC | tap the 138 kV CROSBY C66(#40391) -ATASCOCITA (#40130) Line; CNP | Harris | HOUSTON | 2025-09-24 | OTH | BA | 60.14 |  | 2022-05-16 | 2022-06-02 | 2022-08-30 | 2022-04-28 | 2023-05-02 | No | 2023-11-01 | Yes | Not Required | Not Required |  | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  | 2025-03-10 | 2025-04-01
24INR0330 | TRAVIS KIMBRO BESS | SS Completed, FIS Started, IA | Travis Kimbro BESS LLC | 7337 Kimbro 138kV | Travis | SOUTH | 2028-09-18 | OTH | BA | 36.84 |  | 2022-04-20 | 2022-09-02 | 2022-11-29 | 2022-04-25 |  |  | 2024-10-31 | No
24INR0331 | Chisme Storage | SS Completed, FIS Completed, No IA | Blue Heron Solar, LLC | Tap 345 kV 1444 BROWN SWITCH - 3424 BUCKHORN SWITCH | Brown | NORTH | 2027-04-13 | OTH | BA | 146 |  | 2023-01-11 | 2023-01-17 | 2023-04-14 | 2023-01-11 | 2024-07-23 | No |  | Yes | Not Required | Not Required | 2025-09-15 | 2025-09-15
24INR0333 | Chisme Solar | SS Completed, FIS Completed, No IA | Blue Heron Solar, LLC | Tap 345 kV 1444 BROWN SWITCH - 3424 BUCKHORN SWITCH | Brown | NORTH | 2027-04-13 | SOL | PV | 147 |  | 2023-01-11 | 2023-01-17 | 2023-04-14 | 2023-01-11 | 2024-07-23 |  |  | Yes | Not Required | Not Required | Not Required | 2025-09-16
24INR0337 | Eldora Solar | SS Completed, FIS Completed, IA | Eldora Energy LLC | Tap 345 kV 5915 South Texas Project – 44200 Hillje Ckt 1 | Matagorda | COASTAL | 2026-06-30 | SOL | PV | 200.94 |  | 2022-05-31 | 2022-06-10 | 2022-09-06 | 2022-06-01 | 2023-12-18 |  | 2023-11-15 | Yes | Not Required | Not Required | Not Required | 2023-12-18
24INR0338 | Eldora BESS | SS Completed, FIS Completed, IA | Eldora Energy LLC | 345 kV South Texas Project (Bus# 5915) – Hillje (Bus# 44200) Transmission Line Ckt 1 | Matagorda | COASTAL | 2026-06-30 | OTH | BA | 201.31 |  | 2022-06-03 | 2022-06-10 | 2022-09-06 | 2022-06-01 | 2023-12-18 |  | 2023-11-15 | Yes | Not Required | Not Required |  | 2023-12-18
24INR0339 | Mystic Springs Renewable Energy Solar SLF | SS Completed, FIS Completed, No IA | Mystic Spring Renewable Energy LLC | Tap 345 kV Royse Switch (2478) – Poetry Switch (2485) | Kaufman | NORTH | 2027-08-31 | SOL | PV | 258.83 |  | 2022-12-14 | 2022-05-10 | 2022-08-06 | 2022-11-28 | 2025-04-17 | No |  | No |  |  | Not Required
24INR0340 | Mystic Springs Renewable Energy Storage SLF | SS Completed, FIS Completed, No IA | Mystic Spring Renewable Energy LLC | Tap 345 kV Royse Switch (2478) – Poetry Switch (2485) | Kaufman | NORTH | 2027-08-31 | OTH | BA | 0 |  | 2022-12-14 | 2022-05-10 | 2022-08-06 | 2022-11-28 | 2025-04-17 | No |  | No
24INR0341 | Forts Trail BESS | SS Completed, FIS Started, No IA | JC Central Bluff, LLC | 11406 Central Bluff Switch 345kV | Taylor | WEST | 2028-03-03 | OTH | BA | 200.81 |  | 2022-06-06 | 2022-06-02 | 2022-08-30 | 2022-06-03 |  | No |  | No | Not Required | Not Required
24INR0352 | Guinness BESS | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners,LLC | Tap 138kV 7520 BERTRA - 7522 ANDICE | Williamson | SOUTH | 2027-04-15 | OTH | BA | 100.51 |  | 2022-11-02 | 2022-07-25 | 2022-10-20 | 2022-09-27 |  |  |  | No
24INR0355 | Anatole Renewable Energy Storage | SS Completed, FIS Completed, IA | Eustace Storage LLC | (Bus# 6951) Eustace Southeast 138kV Substation (owned by Rayburn Electric Cooperative) | Henderson | NORTH | 2027-03-31 | OTH | BA | 207.82 |  | 2022-12-14 | 2022-06-02 | 2022-08-30 | 2022-12-02 | 2024-01-22 |  | 2024-05-10 | Yes | Not Required |  |  | 2025-02-12
24INR0356 | Cibeles Solar | SS Completed, FIS Started, IA | Elawan Cibeles Solar, LLC | Tap 345kV 68090 Sam Switch – 13405 Tradinghouse SES | McLennan | NORTH | 2027-06-30 | SOL | PV | 251 |  | 2023-01-31 | 2022-05-16 | 2022-08-13 | 2023-01-13 |  |  | 2025-02-25 | Yes |  |  | Not Required
24INR0358 | Blanket Ranch South Solar SLF | SS Completed, FIS Started, No IA | Blanket Ranch South Solar, LLC | Tap 345kV 11441 CORN TRAIL SWITCH - 1444 BROWN SWITCH | Brown | NORTH | 2028-06-15 | SOL | PV | 134.7 |  | 2022-11-30 | 2022-06-10 | 2022-09-06 | 2022-11-17 |  | No |  | No |  |  | Not Required
24INR0360 | Blanket Ranch North Solar SLF | SS Completed, FIS Started, No IA | Blanket Ranch North Solar, LLC | Tap 345kV 11441 CORN TRAIL SWITCH - 1444 BROWN SWITCH | Brown | NORTH | 2028-06-15 | SOL | PV | 230.5 |  | 2022-12-08 | 2022-06-10 | 2022-09-06 | 2022-11-29 |  | No |  | No |  |  | Not Required
24INR0361 | Blanket Ranch South Storage SLF | SS Completed, FIS Started, No IA | Blanket Ranch South Solar, LLC | Tap 345kV 11441 CORN TRAIL SWITCH - 1444 BROWN SWITCH | Brown | NORTH | 2028-06-15 | OTH | BA | 33.8 |  | 2022-11-30 | 2022-06-10 | 2022-09-06 | 2022-11-17 |  | No |  | No
24INR0362 | Blanket Ranch North Storage SLF | SS Completed, FIS Started, No IA | Blanket Ranch North Solar, LLC | Tap 345kV 11441 CORN TRAIL SWITCH - 1444 BROWN SWITCH | Brown | NORTH | 2028-06-15 | OTH | BA | 50.1 |  | 2022-12-08 | 2022-06-10 | 2022-09-06 | 2022-11-29 |  | No |  | No
24INR0364 | Pitts Dudik II | SS Completed, FIS Completed, IA | Pitts Dudik II | 138 kV Ash Creek Switch (#3473) | Hill | NORTH | 2026-02-04 | SOL | PV | 30.23 |  | 2022-08-28 | 2022-07-18 | 2022-10-14 | 2022-08-04 | 2024-01-17 |  | 2024-06-13 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2025-07-30 | 2025-07-30
24INR0365 | Hermes Storage | SS Completed, FIS Completed, IA | Bell 1 Storage LLC | Tap 345kV 3687 Bell County East Switch - 39950 TNP One Plant Ckt 2 | Bell | NORTH | 2025-12-30 | OTH | BA | 100.42 |  | 2022-07-14 | 2022-07-18 | 2022-10-12 | 2022-06-30 | 2024-04-19 | No | 2023-11-08 | Yes |  |  |  | 2025-01-31 | 2025-01-31 | 2025-01-31
24INR0368 | Glory Bee Solar | SS Completed, FIS Completed, No IA | Riley Solar LLC | Tap 345kV 1440 Comanche Switch - 1900 Comanche Peak | Erath | NORTH | 2026-04-14 | SOL | PV | 305 |  | 2022-06-06 | 2022-06-10 | 2022-09-06 | 2022-06-06 | 2023-04-18 |  |  | No |  |  | Not Required
24INR0369 | Glory Bee Storage | SS Completed, FIS Completed, No IA | Riley Solar LLC | Tap 345kV 1440 Comanche Switch - 1900 Comanche Peak | Erath | NORTH | 2026-04-14 | OTH | BA | 101 |  | 2022-06-06 | 2022-06-10 | 2022-09-06 | 2022-06-06 | 2023-04-18 |  |  | No | Not Required | Not Required
24INR0372 | GIGA AUSTIN SOLAR | SS Completed, FIS Started, No IA | GIGA TEXAS ENERGY LLC | 7047 HORNSBY Substation 138kV | Travis | SOUTH | 2025-03-14 | SOL | PV | -53.3 |  | 2022-08-09 | 2022-07-18 | 2022-10-14 | 2022-07-26 |  |  |  | No |  |  | Not Required
24INR0375 | Possum Kingdom BESS | SS Completed, FIS Completed, No IA | PK Solar, LLC | Tap 345kV 1421 Willow Creek – 11523 Thomas Price | Jack | NORTH | 2027-10-29 | OTH | BA | 200.86 |  | 2023-05-31 | 2022-09-02 | 2022-11-29 | 2023-05-25 | 2025-03-18 | No |  | No | Not Required | Not Required |  |  |  |  | 2025-05-01 | 2026-05-08
24INR0376 | Huisache BESS | SS Completed, FIS Started, IA | Huisache Solar, LLC | Tapping the Elm Creek to Shaula circuit 1 | Wilson | SOUTH | 2029-06-30 | OTH | BA | 100.67 |  | 2023-01-11 | 2022-08-05 | 2022-11-01 | 2022-11-07 |  |  | 2025-08-12 | No
24INR0378 | Solara BESS 1 | SS Completed, FIS Started, No IA | CED Development Inc. | 60387 Hendrick 138kV | Jones | WEST | 2027-11-30 | OTH | BA | 150 |  | 2022-08-08 | 2022-07-05 | 2022-10-01 | 2022-07-26 |  |  |  | No
24INR0379 | Solara BESS 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 60387 Hendrick 138kV | Jones | WEST | 2027-11-30 | OTH | BA | 150 |  | 2022-08-08 | 2022-07-05 | 2022-10-01 | 2022-07-26 |  |  |  | No
24INR0380 | Photo BESS 3 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie Substation 138kV | Uvalde | SOUTH | 2027-09-01 | OTH | BA | 100 |  | 2022-07-28 | 2022-07-25 | 2022-10-21 | 2022-07-26 |  |  |  | No
24INR0381 | Alexandrite Storage | SS Completed, FIS Started, No IA | Johnson Energy Storage, LLC | 8359 Santa Rosa (S_SNROSA4A) 138kV | Cameron | COASTAL | 2026-12-10 | OTH | BA | 203 |  | 2022-06-20 | 2022-06-27 | 2022-09-22 | 2022-06-15 |  |  |  | No
24INR0382 | Remy Jade III Power Station | SS Completed, FIS Completed, IA | Remy Jade III Generating, LLC | Tap 138kV 40390 Crosby - 40811 Highlands | Harris | HOUSTON | 2028-05-01 | GAS | GT | 102 |  | 2022-07-14 | 2022-07-18 | 2022-10-12 | 2022-07-07 | 2025-07-10 |  | 2022-08-01 | No | 2022-03-16 | Not Required | 2023-03-14
24INR0383 | Soda Lake BESS 2 SLF | SS Completed, FIS Started, No IA | Crane II Solar Electric, LLC | 138 kV Soda Lake (#76026) | Crane | WEST | 2027-12-01 | OTH | BA | 205.56 |  | 2022-08-03 | 2022-09-02 | 2022-11-29 | 2022-08-09 |  |  |  | No
24INR0386 | Black & Gold Energy Storage | SS Completed, FIS Started, IA | Black & Gold Energy Storage, LLC | 6364 Yellow Jacket Sub 138kV | Menard | WEST | 2027-06-30 | OTH | BA | 254.58 |  | 2022-09-13 | 2022-07-18 | 2022-10-14 | 2022-08-30 |  | No | 2024-08-14 | Yes | Not Required | Not Required |  | 2025-02-13
24INR0387 | PaleAle BESS | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners,LLC | Tap 138 kV Bus 7506 L_CEDAVA8_1Y - Bus 7507 L_FRIEND8_1Y | Hays | SOUTH | 2027-04-15 | OTH | BA | 75.38 |  | 2022-12-13 | 2022-07-18 | 2022-10-14 | 2022-12-06 |  |  |  | No
24INR0391 | Kennedy Storage | SS Completed, FIS Started, No IA | Kennedy Bypass Solar LLC | Tap 345kV 68040 Kopprl Capacitor Yard - 68091 Navarro | Navarro | NORTH | 2028-12-31 | OTH | BA | 25.3 |  | 2022-07-06 | 2022-07-18 | 2022-10-12 | 2022-07-06 |  |  |  | No
24INR0392 | Riverwalk BESS | SS Completed, FIS Started, No IA | RWE Solar Developement, LLC | 5294 Martinez Substation 138kV | Bexar | SOUTH | 2027-10-01 | OTH | BA | 120 |  | 2022-07-14 | 2022-07-18 | 2022-10-14 | 2022-07-11 |  |  |  | No | Not Required | Not Required
24INR0393 | ELECTRODE BESS | SS Completed, FIS Started, No IA | CED Development Inc. | 76040 Castillo 138kV | Upton | WEST | 2026-12-31 | OTH | BA | 150 |  | 2022-07-18 | 2022-07-25 | 2022-10-21 | 2022-07-12 |  |  |  | No | Not Required | Not Required
24INR0394 | CATHODE BESS | SS Completed, FIS Started, No IA | CED Development Inc. | 76635 King Mountain 138kV | Upton | WEST | 2026-12-31 | OTH | BA | 150 |  | 2022-07-25 | 2022-08-05 | 2022-11-01 | 2022-07-12 |  |  |  | No
24INR0397 | Rhapsody Storage | SS Completed, FIS Completed, IA | Destiny Storage, LLC | Tap 138kV 40390 Crosby - 40680 Placid Ckt 86 | Harris | HOUSTON | 2026-06-30 | OTH | BA | 205.57 | COD | 2022-08-12 | 2022-08-16 | 2022-11-11 | 2022-07-28 | 2025-03-14 | No | 2023-09-20 | Yes |  |  |  | 2023-09-21 | 2025-04-18 | 2025-04-29
24INR0399 | Buzios Solar | SS Completed, FIS Completed, IA | Roaring Springs Solar, LLC | Tap between Cottonwood (#59904) and White River (#23922) | Motley | PANHANDLE | 2026-01-30 | SOL | PV | 252 |  | 2022-08-03 | 2022-09-15 | 2022-12-13 | 2022-08-04 | 2025-03-10 | No | 2023-11-06 | Yes | Not Required | Not Required | Not Required | 2025-02-11 | 2025-04-30 | 2025-04-30 |  |  | 2025-08-27
24INR0404 | Tres Rios Ranch Solar | SS Completed, FIS Started, No IA | LectricWind LLC | 76008 Twelvemile 345kV | Upton | WEST | 2027-12-31 | SOL | PV | 508 |  | 2023-05-04 | 2022-08-05 | 2022-11-01 | 2023-04-26 19:05 |  |  |  | No |  |  | Not Required
24INR0405 | Crowned Heron BESS | SS Completed, FIS Completed, IA | RWE Renewables | WA Parish 345 kV Bus #44000 | Fort Bend | HOUSTON | 2025-09-30 | OTH | BA | 154.2 |  | 2022-07-14 | 2022-07-18 | 2022-10-14 | 2022-07-12 | 2023-05-17 |  | 2023-06-26 | Yes | Not Required | Not Required |  | 2024-05-01 | 2024-05-01 | 2024-05-01
24INR0407 | Mercury Solar III | SS Completed, FIS Started, No IA | Mercury Solar | 68092 Liberty Station 345kV | Hill | NORTH | 2029-07-01 | SOL | PV | 203.5 | COD | 2022-08-02 | 2022-08-16 | 2022-11-11 | 2022-08-03 |  | Yes |  | No |  |  | Not Required
24INR0410 | NRG Greens Bayou 6 (TEF-Due Diligence) | SS Completed, FIS Completed, IA | NRG Texas Power | Position 1/0 PSSE 40710, Greens Bayou Substation, 138 kV | Harris | HOUSTON | 2028-05-01 | GAS | GT | 445 |  | 2022-07-21 | 2022-08-16 | 2022-11-11 | 2022-07-21 | 2025-08-14 |  | 2025-02-07 | No | 2023-09-15 | 2023-09-15 | 2024-06-26
24INR0412 | Camino Ranch Solar SLF | SS Completed, FIS Started, No IA | Camino Ranch Solar Project LLC | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | Houston | NORTH | 2027-10-30 | SOL | PV | 296.42 |  | 2023-07-01 | 2022-10-06 | 2023-01-03 | 2023-06-22 18:26 |  |  |  | No |  |  | Not Required
24INR0413 | Furay Battery Energy Storage System | SS Completed, FIS Started, No IA | Blue Topaz 1, LLC | Tap 138kV 45660 Jonte substation – 46332 Scenic Woods Tapping both radial lines. | Harris | HOUSTON | 2027-03-19 | OTH | BA | 304 |  | 2022-08-31 | 2022-09-02 | 2022-11-29 | 2022-09-01 |  | No |  | No | Not Required | Not Required
24INR0416 | Trelas | SS Completed, FIS Started, No IA | Trelasol, LLC | 76006 Bow Wood 345kV Bus | McCulloch | SOUTH | 2028-05-01 | OTH | BA | 200.83 |  | 2022-08-15 | 2022-09-02 | 2022-11-29 | 2022-08-15 |  |  |  | No
24INR0417 | Sierra Diablo Energy Storage | SS Completed, FIS Started, No IA | SIERRA DIABLO ENERGY STORAGE LLC | Tap 138kv 1698 Sulphur Springs Switch – 3174 Canton Switch | Van Zandt | NORTH | 2026-04-20 | OTH | BA | 203.81 |  | 2022-07-28 | 2022-08-05 | 2022-11-01 | 2022-07-26 |  |  |  | No
24INR0418 | Middlebrook Solar Limited Liability Company | SS Completed, FIS Started, IA | Middlebrook Solar LLC | Tap 345kV 3109 Stryker - 3117 Lufkin | Nacogdoches | NORTH | 2027-08-13 | SOL | PV | 316.19 |  | 2022-09-21 | 2022-10-18 | 2023-01-13 | 2022-10-06 |  |  | 2025-07-21 | Yes | Not Required | Not Required | Not Required | 2025-09-08
24INR0419 | High Plains Storage | SS Completed, FIS Started, No IA | ROBP Holdings, LLC | 45880 Hockley 138kV | Harris | HOUSTON | 2027-10-30 | OTH | BA | 157.7 |  | 2022-08-18 | 2022-09-02 | 2022-11-29 | 2022-08-18 |  |  |  | No | Not Required | Not Required
24INR0420 | Camino Ranch Storage SLF | SS Completed, FIS Started, No IA | Camino Solar Ranch, LLC | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | Houston | NORTH | 2027-10-30 | OTH | BA | 298.06 |  | 2023-07-04 | 2022-10-18 | 2023-01-03 | 2023-06-22 18:28 |  |  |  | No
24INR0422 | Hollow Branch Creek Solar | SS Completed, FIS Completed, IA | Hollow Branch Creek Solar LLC | Tap 345kV 3390 Jewett - 44645 Singleton | Leon | NORTH | 2027-12-31 | SOL | PV | 460 |  | 2022-09-06 | 2022-09-02 | 2022-11-29 | 2022-08-15 | 2024-10-03 | Yes | 2024-10-22 | Yes | Not Required | Not Required | Not Required | 2025-09-22
24INR0423 | Hollow Branch Creek Storage | SS Completed, FIS Completed, No IA | Hollow Branch Creek Solar LLC | Jewett – Singleton 345 kV [PTI Bus # 3390 – 44645] | Leon | NORTH | 2027-12-31 | OTH | BA | 460 |  | 2022-09-20 | 2022-09-02 | 2022-11-29 | 2022-09-16 | 2024-10-03 | Yes |  | No
24INR0424 | Cascabel Wind 1 | SS Completed, FIS Started, IA | Vaquero Wind Energy, LLC | 345 kV Rapido Substation (New ETT Substation) tapping the existing 345 kV Line from CENIZO7C (#80225) to DELSOL7C (#80307) | Zapata | SOUTH | 2027-12-01 | WIN | WT | 197.75 |  | 2023-03-08 | 2023-03-13 | 2023-06-09 | 2023-02-15 |  |  | 2025-05-23 | Yes | Not Required |  | Not Required | 2025-09-24
24INR0425 | Two Brothers ESS | SS Completed, FIS Started, IA | BRP Blue Topaz 2, LLC | 8911 BLKBYU4A 138kV | Victoria | SOUTH | 2027-04-07 | OTH | BA | 152 |  | 2022-09-13 | 2022-09-15 | 2022-12-13 | 2022-09-14 |  | No | 2024-04-22 | Yes | Not Required | Not Required |  | 2025-02-13
24INR0427 | CPS AvR CT1 Rotor Replacement | SS Completed, FIS Completed, No IA | CPS Energy | 5475 Braunig 345kV | Bexar | SOUTH | 2025-06-30 | GAS | CC | 11.3 |  | 2022-08-30 | 2022-10-24 | 2023-01-20 | 2022-09-20 | 2023-04-18 |  |  | No | 2018-06-01 |  | 2023-04-21 | 2023-04-18 | 2023-04-18 | 2023-05-01 |  |  |  | 2023-12-04
24INR0436 | Carambola BESS | SS Completed, FIS Completed, IA | SMT McAllen II LLC | North Mcallen 138 kV Substation (N_MCALLN, Bus#8632) | Hidalgo | SOUTH | 2026-04-20 | OTH | BA | 100.9 |  | 2022-10-04 | 2022-10-18 | 2023-01-13 | 2022-10-05 | 2025-06-23 | No | 2023-07-31 | Yes | Not Required | Not Required |  | 2023-08-08 | 2025-07-22 | 2025-07-22
24INR0440 | Starling Solar Phase II | SS Completed, FIS Started, No IA | Starling Solar, LLC | tap 138kV 7224 Luling - 7245 Gonzales. Starling Solar Phase II is a an addition of 42.24MW to the 23INR0035 (solar) filed in 2020. 23INR0181 (storage) was filed in 2021. | Gonzales | SOUTH | 2028-01-28 | SOL | PV | 43.56 | COD | 2023-06-21 | 2022-10-06 | 2022-12-28 | 2023-06-16 19:02 |  |  |  | No |  |  | Not Required
24INR0442 | Midnight Sun Energy Storage | SS Completed, FIS Started, IA | Midnight Sun Energy Storage, LLC | 6601 Rio Pecos 138kV | Crockett | WEST | 2028-06-29 | OTH | BA | 510 |  | 2022-12-05 | 2022-12-07 | 2023-03-04 | 2022-11-18 |  | No | 2025-07-14 | Yes |  |  |  | 2025-07-29
24INR0444 | Hiru Storage | SS Completed, FIS Started, No IA | Hecate Energy Hazel LLC | Tap 345kV 6111 Riley - 1730 West Krum ckt 1 | Clay | WEST | 2029-04-01 | OTH | BA | 503.6 |  | 2023-12-22 | 2022-11-15 | 2023-02-10 | 2023-08-19 00:08 |  |  |  | No
24INR0445 | PSE Flores TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | TAP 138KV 8793 RIO GRANDE CITY - 8798 LAGRULLA | Starr | SOUTH | 2027-04-30 | OTH | BA | 200 |  | 2023-10-01 | 2022-12-15 | 2023-03-13 | 2023-09-19 |  |  |  | No | Not Required | Not Required
24INR0446 | PSE Gongora Hill TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | Tap 138kV 8796 Roma – 7870 Escobares | Starr | SOUTH | 2027-04-30 | OTH | BA | 200 |  | 2023-11-02 | 2023-02-27 | 2023-03-13 | 2022-11-22 |  |  |  | No | Not Required | Not Required
24INR0447 | PSE Chihuahua TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | Tap 138kV 8392 Bates – 8394 Liston | Hidalgo | SOUTH | 2027-04-30 | OTH | BA | 200 |  | 2023-09-25 | 2022-12-07 | 2023-03-06 | 2023-09-15 |  | No |  | No | Not Required | Not Required
24INR0448 | PSE Minnesota TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | Tap 138kV 8372 North Pharr – 8906 North Alamo | Hidalgo | SOUTH | 2027-04-30 | OTH | BA | 94 |  | 2023-08-21 | 2022-11-15 | 2023-02-09 | 2023-08-09 |  |  |  | No | Not Required | Not Required
24INR0449 | PSE Richardson TX Storage | SS Completed, FIS Completed, No IA | PureSky Development Inc. | TAP 138KV 8374 SOUTH EAST EDINBURG - 8029 CLOSNER | Hidalgo | SOUTH | 2027-04-30 | OTH | BA | 100 |  | 2023-09-28 | 2022-12-07 | 2023-03-06 | 2023-09-15 19:29 | 2025-09-15 |  |  | No | Not Required | Not Required
24INR0450 | Smokey Willie BESS SLF | SS Completed, FIS Started, No IA | Neches Solar, LLC | Tap 138kV 3325 Blackburn Switch – 3272 Palestine | Anderson | NORTH | 2028-09-30 | OTH | BA | 0 |  | 2022-11-11 | 2022-11-15 | 2023-02-09 | 2022-10-28 |  | No |  | No
24INR0452 | Longfellow Solar I | SS Completed, FIS Started, IA | CENTURY GAS PROCESSING, LLC | 38431 TNCENTRY1_1 138 KV | Pecos | WEST | 2027-06-30 | SOL | PV | 178.2 | COD | 2023-04-26 | 2022-11-07 | 2023-02-03 | 2023-04-17 |  | No | 2025-04-15 | No |  |  | Not Required
24INR0453 | Longfellow BESS I | SS Completed, FIS Started, IA | CENTURY GAS PROCESSING, LLC | 38431 TNCENTRY1_1 138 KV | Pecos | WEST | 2026-08-31 | OTH | BA | 54.99 | COD | 2023-04-25 | 2022-11-07 | 2023-02-03 | 2023-04-12 |  |  | 2025-04-15 | Yes | Not Required | Not Required |  | 2025-04-29
24INR0454 | Longfellow Solar II | SS Completed, FIS Started, IA | CENTURY GAS PROCESSING, LLC | 38432 TNCENTRY2_1 138 KV | Pecos | WEST | 2027-06-30 | SOL | PV | 207.36 | COD | 2023-04-25 | 2022-11-07 | 2023-02-03 | 2023-04-13 |  | No | 2025-04-15 | No |  |  | Not Required
24INR0455 | Longfellow BESS II | SS Completed, FIS Started, IA | CENTURY GAS PROCESSING, LLC | 38432 TNCENTRY2_1 138 KV | Pecos | WEST | 2026-08-31 | OTH | BA | 105.75 | COD | 2023-04-26 | 2022-11-07 | 2023-02-03 | 2023-04-12 |  |  | 2025-04-15 | Yes | Not Required | Not Required |  | 2025-04-29
24INR0456 | FRIENDSWOOD ENERGY GENCO | SS Completed, FIS Completed, IA | Tejas Power Generation LLC | 47170 H O CLARKE 138KV | Harris | HOUSTON | 2025-12-05 | GAS | GT | 143.7 |  | 2023-05-04 | 2022-12-07 | 2023-03-06 | 2023-04-26 | 2024-03-21 | No | 2024-04-23 | Yes | 2032-11-04 | Not Required | 2024-10-09 | 2024-10-28 | 2024-10-28 | 2024-10-28 | 2025-03-26
24INR0459 | Exodus BESS | SS Completed, FIS Started, No IA | Exodus Solar LLC | Tap 345kV 7040 Austrop – 7042 Zorn | Caldwell | SOUTH | 2027-12-01 | OTH | BA | 201.36 | COD | 2023-06-30 | 2023-07-10 | 2023-10-05 | 2023-06-30 |  |  |  | No
24INR0461 | Augie BESS | SS Completed, FIS Completed, No IA | BRP Blue Topaz 5, LLC | 46560 Waller 138kV | Waller | HOUSTON | 2027-12-17 | OTH | BA | 200.81 |  | 2022-12-01 | 2023-01-23 | 2023-04-22 | 2023-01-18 | 2024-01-24 | No |  | No
24INR0471 | McGee Storage | SS Completed, FIS Completed, IA | BT McGee Storage, LLC | Bus #6843 at Rayburn Barton Chapel Substation | Henderson | NORTH | 2026-05-29 | OTH | BA | 151.39 |  | 2022-11-10 | 2022-11-15 | 2023-02-09 | 2022-11-09 | 2024-05-30 | No | 2024-12-20 | No | Not Required
24INR0472 | Amador Storage | SS Completed, FIS Completed, IA | BT Amador Storage, LLC | 6833 Explorer Switching Station 138kV | Van Zandt | NORTH | 2025-12-31 | OTH | BA | 102.41 |  | 2022-11-15 | 2022-11-23 | 2023-02-17 | 2022-11-18 | 2024-12-18 | No | 2023-11-02 | Yes |  |  |  | 2025-02-03 | 2025-02-03 | 2025-02-03
24INR0473 | Hooper Solar | SS Completed, FIS Started, No IA | BT Brown Solar, LLC | Tap 138kV line between Lexington (Bus #7571) and Lyle Wolz (Bus #7567) | Lee | SOUTH | 2027-12-15 | SOL | PV | 50.48 |  | 2022-12-01 | 2022-12-07 | 2023-03-06 | 2022-11-03 |  | No |  | No |  |  | Not Required
24INR0474 | Hooper Storage | SS Completed, FIS Started, No IA | BT Brown Solar, LLC | Tap 138kV line between Lexington (Bus #7571) and Lyle Wolz (Bus #7567) | Lee | SOUTH | 2027-12-15 | OTH | BA | 30.68 |  | 2022-11-23 | 2022-12-07 | 2023-03-06 | 2022-11-23 |  | No |  | No
24INR0476 | DOS RIOS ENERGY STORAGE SLF | SS Completed, FIS Completed, IA | DOS RIOS SOLAR, LLC | TAP 69 KV 61 BRANCHVILLE -- 65 SILVER CITY | Milam | SOUTH | 2027-03-15 | OTH | BA | 164.5 |  | 2023-03-29 | 2022-11-15 | 2023-02-11 | 2023-03-27 | 2024-10-24 |  | 2025-05-13 | Yes | Not Required | Not Required |  | 2025-09-12
24INR0477 | Barrett Solar | SS Completed, FIS Completed, IA | Barrett Solar Project, LLC | 138kV Lone Oak Substation (#6797) | Rains | NORTH | 2026-03-13 | SOL | PV | 125.81 | COD | 2022-11-30 | 2023-02-27 | 2023-05-26 | 2023-02-22 | 2025-05-02 | No | 2023-10-05 | Yes | Not Required | Not Required | Not Required | 2025-04-10 | 2025-07-18 | 2025-07-28 | 2024-11-15
24INR0479 | NRG THW GT 138 | SS Completed, FIS Started, No IA | NRG THW GT LLC | 138 kV Bus Number: 45515, Bus Name: T_H_W__POI_8 | Harris | HOUSTON | 2026-06-05 | GAS | GT | 458 |  | 2022-11-17 | 2022-11-22 | 2023-02-17 | 2022-11-17 |  | No |  | No | 2022-12-05
24INR0482 | NRG THW GT 345 (TEF) | SS Completed, FIS Completed, IA | NRG THW GT LLC | 345 kV Bus Number: 45500, Bus Name: T_H_W__POI_5 | Harris | HOUSTON | 2026-05-01 | GAS | GT | 456 |  | 2022-11-16 | 2022-11-17 | 2023-02-09 | 2022-11-17 | 2024-02-05 | No | 2024-08-22 | Yes | 2022-12-05 | Not Required | 2024-06-17 | 2025-02-12 | 2025-07-30 | 2025-07-30
24INR0484 | Lupinus Solar 3 | SS Completed, FIS Completed, IA | Lupinus Solar 2, LLC | 1794 Monticello Tap 138 kV | Franklin | NORTH | 2026-09-21 | SOL | PV | 100.8 |  | 2023-09-13 | 2023-09-23 | 2023-12-20 | 2023-09-13 | 2024-06-26 | No | 2025-03-04 | No |  |  | Not Required
24INR0485 | Rutile BESS | SS Completed, FIS Started, IA | Rutile BESS, LLC | Tap 138kV 6340 BALLINGER - 60399 WEISS | Runnels | WEST | 2026-06-30 | OTH | BA | 100.65 |  | 2023-05-10 | 2023-01-23 | 2023-04-22 | 2023-04-19 |  | No | 2025-07-17 | Yes |  |  |  | 2025-08-05
24INR0488 | Forts Trail BESS 2 | SS Completed, FIS Started, No IA | JC Central Bluff, LLC | 11406 Central Bluff Switch 345 kV | Taylor | WEST | 2028-03-03 | OTH | BA | 201.54 |  | 2023-02-15 | 2023-02-20 | 2023-05-20 | 2023-02-01 |  | No |  | No | Not Required | Not Required
24INR0490 | Lupinus Storage 3 | SS Completed, FIS Completed, IA | Lupinus Solar 2, LLC | 1794 Monticello Tap Substation 138 kV | Franklin | NORTH | 2026-09-21 | OTH | BA | 50.9 |  | 2023-01-23 | 2023-09-23 | 2023-12-20 | 2023-09-13 | 2024-06-26 | No | 2025-03-04 | Yes | Not Required | Not Required |  | 2025-08-05
24INR0491 | Gunnar BESS | SS Completed, FIS Completed, IA | Gunnar Reliability Project LLC | 8029 CLOSNER4A 138kV | Hidalgo | SOUTH | 2026-08-31 | OTH | BA | 154.75 | MW Size | 2023-02-01 | 2023-02-09 | 2023-05-05 | 2023-01-30 | 2025-09-11 |  | 2023-09-22 | Yes | Not Required | Not Required |  | 2024-05-06
24INR0493 | Crowned Heron BESS 2 | SS Completed, FIS Completed, IA | RWE Renewables | WA Parish 345 kV Bus #44000 | Fort Bend | HOUSTON | 2026-03-31 | OTH | BA | 154.2 |  | 2022-11-22 | 2022-11-23 | 2023-02-17 | 2022-11-15 | 2024-01-28 | No | 2024-08-20 | Yes |  |  |  | 2024-10-10 | 2024-11-04 | 2024-11-04
24INR0494 | Hana Springs BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II LLC | 7064 LAMPASAS 138KV | Lampasas | NORTH | 2027-12-15 | OTH | BA | 100.8 |  | 2022-11-22 | 2022-11-23 | 2023-02-17 | 2022-11-18 |  |  |  | No
24INR0496 | Indigo Storage | SS Completed, FIS Started, No IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2026-08-17 | OTH | BA | 60 |  | 2023-10-16 | 2022-12-15 | 2023-03-13 | 2023-08-28 13:47 |  |  |  | No
24INR0500 | Claire BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 3, LLC | 40011 Cedar Bayou 138kV | Harris | HOUSTON | 2027-12-17 | OTH | BA | 406.01 |  | 2023-01-30 | 2023-02-09 | 2023-05-08 | 2023-01-30 |  |  |  | No
24INR0505 | Corralitos Wind 1 | SS Completed, FIS Started, IA | Vaquero Wind Energy, LLC | Tap 345kV 80225 CENIZO7C - 80307 DELSOL7C (New ETT Tiempo Substation) | Zapata | SOUTH | 2027-12-01 | WIN | WT | 196.1 |  | 2023-01-24 | 2023-01-30 | 2023-04-28 | 2023-01-19 |  |  | 2025-06-19 | Yes |  |  | Not Required
24INR0506 | Corralitos Wind 2 | SS Completed, FIS Started, IA | Vaquero Wind Energy, LLC | Tap 345kV 80225 CENIZO7C - 80307 DELSOL7C (New ETT Tiempo Substation) | Zapata | SOUTH | 2027-12-31 | WIN | WT | 195.4 |  | 2023-01-24 | 2023-01-30 | 2023-04-28 | 2023-01-19 |  |  | 2025-06-19 | Yes |  |  | Not Required
24INR0508 | White Oak King Wind | SS Completed, FIS Started, No IA | White Oak Energy, LLC | 345 kV Gauss ( Bus # 60701) | King | WEST | 2027-03-31 | WIN | WT | 606.5 |  | 2023-01-06 | 2023-03-09 | 2023-06-05 | 2023-02-07 |  | No |  | No |  |  | Not Required
24INR0514 | Rogers Draw BESS | SS Completed, FIS Completed, IA | ROGERS DRAW ENERGY STORAGE, LLC | 7751 Headwaters substation 138kV | Gillespie | SOUTH | 2026-06-30 | OTH | BA | 148.61 | COD | 2023-01-10 | 2023-01-03 | 2023-03-30 | 2023-01-09 | 2025-09-10 | No | 2024-02-28 | No
24INR0516 | French Riviera Storage | SS Completed, FIS Started, No IA | Arana Creek Battery Storage LLC | 5646 Riviera Substation 69kV | Kleberg | COASTAL | 2028-05-01 | OTH | BA | 75 |  | 2023-01-24 | 2023-02-09 | 2023-05-05 | 2023-01-21 |  |  |  | No
24INR0519 | Roost Energy Storage | SS Completed, FIS Started, No IA | Bluff Creek Energy Storage LLC | KNDRSACRC Bus #11130 to Knapp Substation Bus #1310 | Scurry | WEST | 2027-09-13 | OTH | BA | 102.36 |  | 2023-01-24 | 2023-01-30 | 2023-04-28 | 2023-01-21 |  | No |  | No
24INR0528 | Blanquilla BESS | SS Completed, FIS Completed, IA | Blanquilla BESS LLC | Tap 138kV 8452 LON_HILL4A - 8441 NUECES_B4A | Nueces | COASTAL | 2026-12-31 | OTH | BA | 200.78 | COD | 2023-03-14 | 2023-02-09 | 2023-05-08 | 2023-03-07 | 2025-03-13 |  | 2024-09-05 | Yes |  |  |  | 2025-02-13 | 2025-07-31 | 2025-07-16
24INR0530 | Southside Energy | SS Completed, FIS Started, No IA | Southside Energy, LLC | Tap 138kV 42960 Mustang Bayou - 42100 HUDSON ckt 4 | Brazoria | COASTAL | 2028-12-31 | OTH | BA | 101.2 |  | 2023-11-01 | 2023-02-27 | 2023-05-26 | 2023-10-24 |  |  |  | No
24INR0532 | Timber Cove Solar SLF | SS Completed, FIS Started, No IA | Freestone Solar, LLC | Tap 138 kV 212 Winkler - 3510 Pin Oak | Freestone | NORTH | 2027-04-01 | SOL | PV | 100.5 |  | 2023-05-02 | 2023-05-22 | 2023-08-17 | 2023-05-17 |  |  |  | No |  |  | Not Required
24INR0533 | Padua Grid BESS Unit 2 | SS Completed, FIS Completed, IA | Padua Grid 2, LLC | 5395 Sommers 138kV | Bexar | SOUTH | 2026-03-15 | OTH | BA | 150.94 |  | 2023-05-30 | 2023-06-07 | 2023-09-01 | 2023-06-01 | 2025-02-06 | No | 2025-01-10 | Yes | Not Required | Not Required |  | 2025-04-24 | 2025-04-24 | 2025-04-24
24INR0534 | Lyford Energy | SS Completed, FIS Started, No IA | Lyford Energy, LLC | 5745 E Raymondville 138kV | Willacy | COASTAL | 2027-09-02 | OTH | BA | 101.2 |  | 2023-11-07 | 2023-03-08 | 2023-06-05 | 2023-10-24 |  |  |  | No
24INR0538 | FLIFER Solar I | SS Completed, FIS Started, No IA | FLIFER LLC | Tap 138 kV Yucca Drive Switch (bus# 1009) – Sand Tank (bus# 11197) | Ward | WEST | 2027-04-15 | SOL | PV | 84 |  | 2023-05-08 | 2023-03-08 | 2023-06-01 | 2023-04-26 |  |  |  | No |  |  | Not Required
24INR0541 | Kinney County Energy | SS Completed, FIS Started, No IA | Kinney County Energy, LLC | Tap 138kV 8252 Brackett4A - 78255 L_PINTCR8_1Y | Kinney | SOUTH | 2027-05-15 | OTH | BA | 101.2 |  | 2023-11-10 | 2023-03-27 | 2023-06-19 | 2023-10-24 15:45 |  |  |  | No
24INR0543 | Thomas Cameron BESS | SS Completed, FIS Completed, IA | Thomas Cameron BESS LLC | Tap 345kV 3424 BUCKHORN SWITCH - 3422 KILLEEN SWITCH | Lampasas | NORTH | 2027-05-03 | OTH | BA | 201.52 |  | 2023-06-01 | 2023-06-07 | 2023-09-01 | 2023-06-02 | 2024-07-23 | No | 2024-10-30 | Yes | Not Required | Not Required |  | 2025-09-12
24INR0544 | Wetzel BESS | SS Completed, FIS Started, No IA | Brown ESS, LLC | Tap 138kV 1654 Zephyr – 1655 Brownwood Switch | Brown | NORTH | 2026-09-15 | OTH | BA | 185.57 |  | 2023-03-14 | 2023-03-27 | 2023-06-20 | 2023-03-15 |  |  |  | No
24INR0555 | Shaula I BESS | SS Completed, FIS Started, No IA | Shaula Energy Project LLC | 5380 Shaula 345kV | DeWitt | SOUTH | 2025-12-31 | OTH | BA | 86.88 |  | 2023-05-19 | 2023-07-10 | 2023-10-05 | 2023-07-03 |  |  |  | No
24INR0558 | Parthenon Energy | SS Completed, FIS Started, No IA | Parthenon Energy, LLC | Tap 138kV 88380 RGTAP4A - 8896 RACHAL4A | Hidalgo | SOUTH | 2028-12-31 | OTH | BA | 101.2 |  | 2023-10-31 | 2023-04-19 | 2023-07-14 | 2023-10-24 |  | No |  | No | Not Required | Not Required
24INR0559 | Nerva Energy Storage | SS Completed, FIS Started, No IA | Nerva Energy Storage, LLC | Tap 138kV 402410 BURKE_POI_8 - 42430 EGLNST_POI_8 CKT#02 | Brazoria | COASTAL | 2028-12-31 | OTH | BA | 101.2 |  | 2023-10-30 | 2023-04-19 | 2023-07-14 | 2023-10-24 |  | No |  | No | Not Required | Not Required
24INR0567 | Wolf Hollow III | SS Completed, FIS Completed, No IA | Wolf Hollow II Power LLC | 1877 Mitchell Bend 345KV | Hood | NORTH | 2026-05-31 | GAS | GT | 306.32 |  | 2023-05-18 | 2023-06-07 | 2023-09-01 | 2023-05-30 | 2024-06-03 |  |  | No
24INR0569 | Hadrian Energy Storage | SS Completed, FIS Completed, No IA | Hadrian Energy Storage, LLC | Line Tap 138kV #43012 NEWGLF60T3_8 - #43190 S_LANE_B138 | Wharton | SOUTH | 2028-12-31 | OTH | BA | 101.2 |  | 2023-11-07 | 2023-05-15 | 2023-08-11 | 2023-10-24 | 2025-02-12 |  |  | No
24INR0570 | Marcus Energy Storage | SS Completed, FIS Completed, No IA | Marcus Energy Storage, LLC | Tap 138kV 39500 West Columbia Main - 110505 Sweeny Co-Gen LP Ckt 1 | Brazoria | COASTAL | 2027-09-01 | OTH | BA | 201.04 | COD | 2023-10-31 | 2023-06-07 | 2023-09-01 | 2023-10-24 | 2024-09-30 |  |  | No
24INR0572 | Megacharge BESS | SS Completed, FIS Started, No IA | SMT Harlingen III LLC | 8320 WEST HARLINGEN 69kV | Cameron | COASTAL | 2027-07-01 | OTH | BA | 110 |  | 2023-06-27 | 2023-06-28 | 2023-09-20 | 2023-06-26 |  |  |  | No
24INR0576 | Boling Generation (TEF-Due Diligience) | SS Completed, FIS Completed, No IA | Boling Generation | 43340 Gulftie 138kV | Wharton | SOUTH | 2027-10-29 | GAS | GT | 400 |  | 2023-10-11 | 2023-12-04 | 2024-03-01 | 2023-11-02 | 2025-08-20 | No |  | No
24INR0578 | Panther Creek 1 Repower | SS Completed, FIS Completed, No IA | Panther Creek Wind Farm I&II, LLC | 1058 Longshore 345kV | Glasscock | WEST | 2025-09-01 | WIN | WT | 11 |  | 2023-06-27 | 2023-06-28 | 2023-09-21 | 2023-06-21 | 2024-05-03 |  |  | Yes | Not Required | Not Required | Not Required | 2024-06-21 | 2024-06-21 | 2024-05-06 |  |  |  | 2024-10-02
24INR0582 | Panther Creek 2 Repower | SS Completed, FIS Completed, No IA | Panther Creek Wind Farm I&II, LLC | Longshore 345kV [Bus# 1058] | Glasscock | WEST | 2025-09-01 | WIN | WT | 8 |  | 2023-06-27 | 2023-06-28 | 2023-09-21 | 2023-06-27 | 2024-05-03 |  |  | Yes | Not Required | Not Required | Not Required | 2024-06-21 | 2024-06-21 | 2024-05-06 |  |  |  | 2024-10-02
24INR0584 | Houston IV BESS | SS Completed, FIS Completed, IA | SMT Houston IV LLC | 44140 CLODINE 138kV | Harris | HOUSTON | 2026-06-03 | OTH | BA | 164.6 |  | 2023-06-30 | 2023-07-10 | 2023-10-05 | 2023-06-27 | 2025-07-01 | No | 2024-11-07 | Yes | Not Required |  | 2025-09-18 | 2025-02-12
24INR0589 | Antoninus Energy Storage | SS Completed, FIS Started, No IA | Antoninus Energy Storage, LLC | Tap 138kV #43190 S_LANE_B138 - #42985 DYANN_POI_8 Transmission Line. | Wharton | SOUTH | 2028-12-31 | OTH | BA | 101.2 |  | 2023-11-02 | 2023-06-28 | 2023-09-24 | 2023-10-30 |  |  |  | No | Not Required | Not Required
24INR0616 | GridGuardian BESS | SS Completed, FIS Started, No IA | SMT Temple BESS LLC | 3412 TEMPLE PECAN CREEK 345kV | Bell | NORTH | 2027-04-19 | OTH | BA | 227.99 |  | 2023-09-08 | 2023-09-22 | 2023-12-14 | 2023-09-11 |  |  |  | No | Not Required | Not Required
24INR0617 | Serrano Storage | SS Completed, FIS Started, No IA | Maverick ESS, LLC | 8267 GANSO Substation 138kV | Maverick | SOUTH | 2026-12-01 | OTH | BA | 185.59 |  | 2023-09-11 | 2023-09-23 | 2023-12-20 | 2023-08-31 |  |  |  | No | Not Required | Not Required
24INR0627 | Champion Wind Repower | SS Completed, FIS Completed, IA | Champion Wind Farm, LLC | Bus# 1048 - Tonkawa | Nolan | WEST | 2025-05-09 | WIN | WT | 0.31 |  | 2023-09-13 | 2023-09-25 | 2023-12-21 | 2023-09-13 | 2024-04-26 |  | 2007-01-19 | Yes | Not Required | Not Required | Not Required | 2024-07-29 | 2024-07-30 | 2024-07-30 |  |  |  | 2025-01-13
24INR0630 | Andromeda Storage SLF | SS Completed, FIS Completed, IA | IP Lumina II BESS, LLC | 60011 Nebulast 345kV | Scurry | WEST | 2025-09-30 | OTH | BA | 0 | COD | 2023-10-22 | 2023-10-25 | 2024-01-22 | 2023-10-17 | 2024-07-30 | No | 2024-04-18 | Yes | Not Required | Not Required |  | 2024-04-29 | 2024-04-29 | 2024-07-31 |  |  | 2025-04-01 | 2025-04-10
24INR0631 | Radian Storage SLF | SS Completed, FIS Completed, IA | IP Radian BESS, LLC | 345 kV Brown Switch (Bus# 1444) | Brown | NORTH | 2025-11-07 | OTH | BA | 0 | COD | 2023-10-23 | 2023-10-25 | 2024-01-22 | 2023-10-17 | 2025-07-23 | No | 2024-06-20 | Yes | Not Required | Not Required |  | 2024-07-24 | 2024-07-24 | 2024-08-01 |  |  | 2025-03-24 | 2025-04-07
24INR0632 | Cedro Hill Wind Repower | SS Completed, FIS Completed, IA | CEDRO HILL WIND LLC | 80439 LA QUINTA 138kV | Webb | SOUTH | 2025-12-31 | WIN | WT | 9.93 | COD | 2023-09-29 | 2023-09-28 | 2023-12-20 | 2023-09-28 | 2023-11-22 |  | 2009-09-09 | Yes |  |  | Not Required | 2024-01-30 | 2024-01-30 | 2024-01-30 |  |  |  | 2024-09-11
24INR0763 | Team Ranch Storage | SS Completed, FIS Started, No IA | BAF Storage, LLC | 1869 Benbrook Switch 345kV | Tarrant | NORTH | 2026-12-01 | OTH | BA | 307.2 | COD | 2024-06-05 | 2024-06-13 | 2024-08-07 | 2024-06-05 |  |  |  | No
25INR0002 | Barcelona TxHSR TPSS HN-4 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 45885 HocklyC - 46220 Peters | Harris | HOUSTON | 2028-07-15 | OTH | OT | 50 |  | 2019-10-11 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  | No |  | No | Not Required | Not Required
25INR0005 | Tokyo TxHSR TPSS EW-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2241 Ennis W - 2321 Waxahachie | Ellis | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-09-13 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  |  |  | No | Not Required | Not Required
25INR0006 | Atlanta TxHSR TPSS DS-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2429 Watermill E - 3083 Wilmer | Dallas | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-10-11 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  |  |  | No | Not Required | Not Required
25INR0008 | BasRanch (TEF - Due Diligence) | SS Completed, FIS Completed, IA | CPV Basin Ranch, LLC | tap 345kV Riverton Switch - Sand Lake Switch | Ward | WEST | 2028-12-01 | GAS | CC | 1350 |  | 2021-11-24 | 2020-08-04 | 2020-11-02 | 2021-10-28 | 2025-05-05 | Yes | 2025-07-16 | Yes | 2024-11-25 | 2024-11-25 | 2025-09-05 | 2025-09-08
25INR0010 | Nockenut Springs Solar 3 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Gonzales | SOUTH | 2029-06-05 | SOL | PV | 203.39 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No |  |  | Not Required
25INR0018 | Yellow Cat Wind | SS Completed, FIS Started, IA | Yellow Cat Wind LLC | Tap 345kV 1906 Venus - 68091 Navarro | Navarro | NORTH | 2027-04-01 | WIN | WT | 262 |  | 2022-03-18 | 2021-08-17 | 2021-11-05 | 2022-03-07 |  | No | 2024-07-09 | Yes | Not Required | Not Required | Not Required | 2025-02-12
25INR0021 | Findley Solar | SS Completed, FIS Started, No IA | Gransolar Texas Sixteen, LLC | 107 Prairie Hill 69 kV | Limestone | NORTH | 2028-01-01 | SOL | PV | 50.34 |  | 2022-07-05 | 2021-10-05 | 2021-12-10 | 2022-05-24 |  | No |  | No |  |  | Not Required
25INR0029 | Whistle Solar | SS Completed, FIS Started, No IA | Gransolar Texas Nineteen, LLC | Tap 138kV 213 Haney – 3478 Navarro | Navarro | NORTH | 2028-05-15 | SOL | PV | 56.3 |  | 2022-08-10 | 2021-11-23 | 2022-02-18 | 2022-08-05 |  |  |  | No |  |  | Not Required
25INR0039 | Borderland ESC | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | tap 138kV 8380 NEDIN4A – 8632 NMCALLEN4C | Hidalgo | SOUTH | 2026-06-30 | OTH | BA | 200 |  | 2022-02-08 | 2022-02-21 | 2022-05-22 | 2022-02-08 |  |  |  | No
25INR0040 | McMEXICO STORAGE | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | 8644 Trade Zone 138kV | Hidalgo | SOUTH | 2026-12-01 | OTH | BA | 201.9 |  | 2022-01-28 | 2022-02-28 | 2022-05-27 | 2022-02-15 |  | No |  | No | Not Required | Not Required
25INR0045 | Smith Lake Storage DC | SS Completed, FIS Started, No IA | Smith Lake Solar | Tap 345kV 44645 Singleton - 44900 Zenith Ckt #99 | Grimes | NORTH | 2026-11-30 | OTH | BA | 65 |  | 2022-11-30 | 2022-03-07 | 2022-05-06 | 2022-11-02 |  | Yes |  | No
25INR0046 | Blue Skies BESS | SS Completed, FIS Started, IA | ACTX BESS Project LLC | 68090 SAM SW 345kV | Hill | NORTH | 2027-12-31 | OTH | BA | 306.26 |  | 2022-04-02 | 2022-05-10 | 2022-08-06 | 2022-04-15 |  |  | 2024-06-20 | Yes |  |  |  | 2025-02-12
25INR0052 | SanPat Solar II | SS Completed, FIS Started, IA | CGRP 04, LLC | Tap 345kV 8249 Angstrom – 8659 Naismith | San Patricio | COASTAL | 2027-11-30 | SOL | PV | 256.23 | COD | 2022-07-29 | 2022-02-28 | 2022-05-27 | 2022-07-15 |  | Yes | 2023-10-18 | Yes |  |  | Not Required | 2025-02-13
25INR0055 | Three W Solar | SS Completed, FIS Completed, IA | Three W Solar LLC | tap 138kV 3522 Hillboro1_8 - 237 Blanton CKT 1 | Hill | NORTH | 2026-06-01 | SOL | PV | 110.89 |  | 2022-02-25 | 2022-03-07 | 2022-06-02 | 2022-02-28 | 2025-06-18 | No | 2023-03-28 | Yes | Not Required | Not Required | Not Required | 2025-07-31 | 2025-07-31 | 2025-07-31
25INR0057 | Sombrero Solar | SS Completed, FIS Started, No IA | Aurora Solar LLC | Tap 345kV 76003 Big Hill - 60708 Orsted | Schleicher | WEST | 2028-05-31 | SOL | PV | 351.85 |  | 2023-01-23 | 2022-03-30 | 2022-06-26 | 2023-01-03 |  | Yes |  | No | Not Required | Not Required | Not Required
25INR0060 | Argenta Solar | SS Completed, FIS Started, IA | Charter Oak Solar, LLC | Tap 345kV 8689 Tango - 8606 Goddard | Bee | SOUTH | 2027-07-01 | SOL | PV | 310 |  | 2022-07-27 | 2022-06-27 | 2022-09-21 | 2022-07-14 |  |  | 2024-04-05 | Yes | Not Required | Not Required | Not Required | 2025-02-12
25INR0061 | Argenta Storage | SS Completed, FIS Started, IA | Charter Oak Storage, LLC | Tap 345kV 8689 Tango - 8606 Goddard | Bee | SOUTH | 2027-07-01 | OTH | BA | 192 |  | 2022-07-21 | 2022-06-27 | 2022-09-21 | 2022-07-13 |  |  | 2024-04-05 | Yes | Not Required | Not Required |  | 2025-02-12
25INR0068 | High Chap Solar | SS Completed, FIS Started, IA | HIGH CHAPARRAL SOLAR PROJECT LLC | 43035 Oasis 345kV - 42500 Dow Chemical 345 kV Ckt 18 | Brazoria | COASTAL | 2028-06-26 | SOL | PV | 152.25 |  | 2022-07-05 | 2022-07-05 | 2022-10-01 | 2022-06-17 |  | Yes | 2023-11-21 | Yes | Not Required | Not Required | Not Required | 2025-05-28
25INR0071 | Albatross BESS | SS Completed, FIS Started, No IA | Albatross Solar, LLC | From Bus #165 Windsor Switch To Bus #161 McGregor | McLennan | NORTH | 2028-02-22 | OTH | BA | 50.4 |  | 2023-01-27 | 2022-05-16 | 2022-08-13 | 2022-10-25 |  | No |  | No
25INR0072 | High Chap Storage | SS Completed, FIS Started, No IA | HIGH CHAPARRAL SOLAR PROJECT LLC | 43035 Oasis 345kV - 42500 Dow Chemical 345 kV Ckt 18 | Brazoria | COASTAL | 2028-06-26 | OTH | BA | 71.78 |  | 2022-07-21 | 2022-07-25 | 2022-10-21 | 2022-07-07 |  | Yes |  | No
25INR0076 | Violet Storage | SS Completed, FIS Started, No IA | VIOLET STORAGE | McKenzie Road (8858) 138 kV Substation | Nueces | COASTAL | 2029-07-01 | OTH | BA | 151 |  | 2022-04-13 | 2022-05-10 | 2022-08-06 | 2022-04-14 |  | No |  | No
25INR0078 | Peregrine BESS 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 8673 RAPTOR7A 345kV | Goliad | SOUTH | 2027-07-01 | OTH | BA | 150 |  | 2022-08-15 | 2022-08-05 | 2022-11-01 | 2022-08-02 |  |  |  | No
25INR0080 | Meitner Solar | SS Completed, FIS Started, IA | IP Meitner, LLC | 345 kV Gray (Bus# 79000) | Gray | PANHANDLE | 2027-12-20 | SOL | PV | 702.64 |  | 2022-07-26 | 2022-08-05 | 2022-11-01 | 2022-07-27 |  | Yes | 2024-01-31 | No |  |  | Not Required
25INR0081 | SanPat Solar I | SS Completed, FIS Started, IA | Padre Solar LLC | Tap 345kV 8249 Angstrom – 8659 Naismith | San Patricio | COASTAL | 2027-10-01 | SOL | PV | 308.88 | COD | 2022-07-29 | 2022-07-18 | 2022-10-12 | 2022-07-15 |  | Yes | 2023-10-18 | Yes |  |  | Not Required | 2025-02-13
25INR0082 | Reis Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Reis LLC | Tapping into 138 kV line (5689) Choke Canyon AEP to (5902) San Miguel Gen | Atascosa | SOUTH | 2027-08-03 | SOL | PV | 105.48 |  | 2022-09-19 | 2022-06-02 | 2022-08-29 | 2022-09-09 |  |  |  | No |  |  | Not Required
25INR0097 | Soleil Solar | SS Completed, FIS Started, IA | Soleil Solar, LLC | Tap 345 kV 1730 Krum West Switch - 6111 Riley ckt 2 | Clay | WEST | 2028-02-01 | SOL | PV | 728.72 |  | 2022-08-31 | 2022-09-02 | 2022-11-29 | 2022-08-26 |  | No | 2025-05-08 | No |  |  | Not Required
25INR0100 | Goldeneye BESS | SS Completed, FIS Completed, IA | Black Mountain Energy Storage II | 3423 KILLEEN Switch 138 KV | Bell | NORTH | 2027-06-01 | OTH | BA | 201.6 |  | 2022-08-03 | 2022-06-10 | 2022-09-06 | 2022-07-13 | 2023-08-18 | No | 2024-02-26 | No | Not Required | Not Required
25INR0101 | Mallard BESS | SS Completed, FIS Completed, IA | Mallard Energy Storage LLC | #833 Wylie Switch 138kV | Collin | NORTH | 2026-04-02 | OTH | BA | 257.3 |  | 2022-06-22 | 2022-06-02 | 2022-08-29 | 2022-06-17 | 2025-06-18 | No | 2025-05-06 | Yes | Not Required | Not Required |  | 2025-07-16 | 2025-07-17 | 2025-07-17
25INR0102 | Austin Bayou Solar | SS Completed, FIS Completed, IA | Austin Bayou Solar, LLC | Tap 345 kV Savana 43180 to Seabreeze 43020 - Ckt 27 | Brazoria | COASTAL | 2027-06-01 | SOL | PV | 502.48 |  | 2022-08-15 | 2022-06-27 | 2022-09-21 | 2022-07-26 | 2023-03-29 | No | 2023-11-15 | Yes |  |  | Not Required | 2025-02-12
25INR0103 | Elio BESS | SS Completed, FIS Completed, IA | Elio Energy LLC | Tap 138kV 42980 Nash - 44010 Wa Parish circuit 02 | Brazoria | COASTAL | 2027-08-05 | OTH | BA | 317.2 |  | 2023-05-19 | 2022-07-05 | 2022-10-01 | 2023-05-15 17:16 | 2024-10-31 |  | 2024-09-15 | Yes | Not Required | Not Required |  | 2025-02-12
25INR0105 | Diver Solar | SS Completed, FIS Completed, IA | Diver Solar | Tap 345kV 3384 St Johns - 3390 Jewett | Limestone | NORTH | 2025-11-21 | SOL | PV | 225.59 |  | 2022-06-23 | 2022-09-02 | 2022-11-29 | 2022-06-28 | 2024-11-09 | No | 2023-10-27 | Yes | Not Required | Not Required | Not Required | 2023-11-13 | 2025-01-10 | 2025-01-30 |  |  | 2025-07-24 | 2025-08-01
25INR0106 | Luthor Solar | SS Completed, FIS Started, No IA | TREX US Luthor LLC | Tap 138kV 23831 Luther Station – 10032 Little Luther | Howard | WEST | 2027-09-25 | SOL | PV | 101 | COD | 2023-05-10 | 2022-06-27 | 2022-09-21 | 2023-04-28 |  |  |  | No |  |  | Not Required
25INR0109 | Sun Cactus Solar | SS Completed, FIS Started, IA | Sun Cactus Solar Project, LLC | tap 138kV 8510 Falfurrias - 8695 Crestonio | Duval | SOUTH | 2027-10-15 | SOL | PV | 120.63 |  | 2022-06-17 | 2022-07-05 | 2022-10-01 | 2022-06-20 |  |  | 2023-11-06 | Yes |  |  | Not Required | 2025-02-12
25INR0112 | August Draw Energy | SS Completed, FIS Started, IA | August Draw Solar Holdings, LLC | Tap 138kV 60207 Verhalen – 60808 Hoefs Road | Reeves | WEST | 2028-06-27 | SOL | PV | 250 | SFS/NtP | 2023-06-22 | 2022-09-15 | 2022-12-13 | 2023-06-09 |  | No | 2025-09-12 | Yes | Not Required | Not Required | Not Required | 2025-09-25
25INR0122 | Vial BESS | SS Completed, FIS Completed, IA | Gransolar Texas Eleven LLC | Chatt(234) - Pecan Street (3352) 138kV | Hill | NORTH | 2027-09-15 | OTH | BA | 135.18 |  | 2023-04-03 | 2022-07-05 | 2022-10-01 | 2023-03-29 | 2025-05-30 | No | 2025-08-04 | Yes | Not Required | Not Required | 2025-08-18 | 2025-08-28
25INR0129 | Demeter Solar | SS Completed, FIS Started, No IA | Demeter Solar, LLC | Tap 138kV 7224 LULING - 7216 LOCKHART | Caldwell | SOUTH | 2029-06-01 | SOL | PV | 88 |  | 2023-03-17 | 2022-08-05 | 2022-11-01 | 2023-03-10 |  |  |  | No |  |  | Not Required
25INR0130 | Demeter Storage | SS Completed, FIS Started, No IA | Demeter Solar, LLC | Tap 138kV 7224 LULING - 7216 Lockhart | Caldwell | SOUTH | 2029-06-01 | OTH | BA | 65 |  | 2023-03-17 | 2022-08-05 | 2022-11-01 | 2023-03-10 |  |  |  | No
25INR0131 | SOSA Storage | SS Completed, FIS Started, IA | SOSA Energy Center LLC | Tap 138kV 25 North Zulch - 47 Hilltop Lakes | Madison | NORTH | 2027-07-01 | OTH | BA | 155.3 |  | 2022-07-21 | 2022-07-25 | 2022-10-20 | 2022-07-21 |  | No | 2023-12-05 | Yes | Not Required | Not Required |  | 2025-02-13
25INR0133 | Rose Quartz BESS | SS Completed, FIS Completed, No IA | Rose Quartz BESS, LLC | Tap 138kV 8283 Asherton - 8613 Bigwells | Dimmit | SOUTH | 2026-12-01 | OTH | BA | 101.41 |  | 2022-10-27 | 2022-09-02 | 2022-11-30 | 2022-10-14 | 2025-04-23 |  |  | No | Not Required | Not Required
25INR0134 | Hoskins Solar | SS Completed, FIS Started, No IA | SGT HOSKINS SOLAR PROJECT, LLC | TAP 138 kV 1687 BLOSSOM_T8 - 1771 LAMARBM1_8 | Lamar | NORTH | 2026-08-31 | SOL | PV | 204.12 |  | 2023-08-10 | 2022-10-24 | 2023-01-20 | 2023-07-28 20:26 |  |  |  | No |  |  | Not Required
25INR0135 | Hayrick BESS | SS Completed, FIS Started, No IA | Gransolar Texas Five LLC | 6351 Nicole 138kV | Coke | WEST | 2028-03-15 | OTH | BA | 113.9 |  | 2023-05-31 | 2022-08-16 | 2022-11-11 | 2023-05-18 |  | No |  | No
25INR0138 | Champaign BESS | SS Completed, FIS Completed, IA | Champaign BESS, LLC | Tap 138kV Shaw POD (18664) – Desert Wind Sub (11222) new station Potterson Lake Switch | Glasscock | WEST | 2027-06-28 | OTH | BA | 201.13 |  | 2022-12-30 | 2022-09-21 | 2022-12-19 | 2022-12-29 | 2024-08-13 | No | 2025-07-31 | No
25INR0139 | Dolce BESS | SS Completed, FIS Completed, No IA | Dolce BESS, LLC | Tap 138kV 1189 BARBER_LK1_8 - 19520 CHINAGRVX2_8 | Mitchell | WEST | 2028-01-31 | OTH | BA | 100.65 |  | 2023-03-30 | 2022-09-27 | 2022-12-21 | 2023-03-28 | 2024-06-26 | No |  | No
25INR0140 | Seragio BESS | SS Completed, FIS Started, No IA | Seragio BESS, LLC | 11140 ECTRCNTYN_8 138kV | Ector | WEST | 2027-06-28 | OTH | BA | 201.13 |  | 2022-12-27 | 2022-09-15 | 2022-12-13 | 2022-12-29 |  | No |  | No
25INR0141 | Fairgreen BESS | SS Completed, FIS Started, No IA | Fairgreen BESS, LLC | Tap 138kV 1322 BIGSPRIG_8 - 11351 HILLCREST_8 | Howard | WEST | 2026-09-14 | OTH | BA | 201.13 |  | 2023-02-01 | 2022-09-15 | 2022-12-13 | 2022-12-29 20:48 |  |  |  | No
25INR0142 | Sagewood BESS | SS Completed, FIS Started, No IA | Sagewood BESS, LLC | tap McDonald Road Switch (1333) – Pastores Switch (10121) ckt 1 | Glasscock | WEST | 2028-03-31 | OTH | BA | 100.57 | COD | 2022-12-30 | 2022-09-21 | 2022-12-19 | 2022-12-29 |  | No |  | No
25INR0143 | Ariji BESS | SS Completed, FIS Started, IA | Ariji BESS, LLC | Tap 138kV 1394 GTTYVTAP_8 - 1322 BIGSPRIG_8 | Howard | WEST | 2027-06-28 | OTH | BA | 100.32 |  | 2023-06-19 | 2022-09-15 | 2022-12-13 | 2023-06-09 00:21 |  |  | 2025-08-01 | No
25INR0144 | Jasper BESS | SS Completed, FIS Started, No IA | Jasper BESS, LLC | Tap 138kV 71230 Pleasant Farms - 1236 Pegasus South | Midland | WEST | 2028-03-31 | OTH | BA | 201.13 | COD | 2023-04-03 | 2022-09-21 | 2022-12-19 | 2023-03-28 |  |  |  | No
25INR0146 | Blue Heron BESS | SS Completed, FIS Started, No IA | Blue Heron BESS, LLC | Tap 138kV MANSON (1094) - Riverton (11083) | Reeves | WEST | 2028-03-31 | OTH | BA | 201.13 | MW Size COD | 2023-04-26 | 2022-10-24 | 2023-01-20 | 2023-04-10 |  | No |  | No
25INR0152 | Bottom Grass Solar II | SS Completed, FIS Completed, No IA | Flint Rock Solar Project, LLC | Tap 345kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2028-03-01 | SOL | PV | 401.6 |  | 2022-11-01 | 2022-11-07 | 2023-02-04 | 2022-11-02 | 2025-08-04 |  |  | No |  |  | Not Required
25INR0153 | Bottom Grass BESS II | SS Completed, FIS Completed, No IA | Flint Rock Solar Project, LLC | Tap 345kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2028-03-01 | OTH | BA | 150.6 |  | 2022-11-01 | 2022-11-07 | 2023-02-03 | 2022-11-02 | 2025-08-04 |  |  | No
25INR0154 | Nymphaea Solar | SS Completed, FIS Started, No IA | Nymphaea Solar, LLC | Tap 345kV 1730 Krum West Swtich - 6111 Riley7B | Wichita | WEST | 2028-07-01 | SOL | PV | 120.9 |  | 2023-01-06 | 2022-09-21 | 2022-12-19 | 2022-12-23 |  | No |  | No |  |  | Not Required
25INR0155 | Nymphaea Storage | SS Completed, FIS Started, No IA | Nymphaea Solar, LLC | Tap 345kV 1730 Krum West Swtich - 6111 Riley7B | Wichita | WEST | 2028-07-01 | OTH | BA | 61 |  | 2023-01-13 | 2022-09-21 | 2022-12-19 | 2022-12-23 |  | No |  | No
25INR0162 | SAHARA II BESS (SOHO II BESS) | SS Completed, FIS Completed, IA | ESTX-PLD-HOUSTON2 | 43035 Oasis 345kV | Brazoria | COASTAL | 2026-06-01 | OTH | BA | 204.3 |  | 2022-08-10 | 2022-08-16 | 2022-11-11 | 2022-08-10 | 2025-05-01 | No | 2023-04-15 | Yes | Not Required | Not Required | 2025-04-29 | 2023-08-24 | 2025-07-22 | 2025-07-22
25INR0164 | Star Dairy Solar | SS Completed, FIS Completed, IA | Star Dairy Solar LLC | Tap 345kV 1692 PARIS_SW1_5 -- 11699 WOODARD_5 | Lamar | NORTH | 2027-04-03 | SOL | PV | 125.61 |  | 2022-11-18 | 2022-11-23 | 2023-02-17 | 2022-11-09 | 2025-02-17 | No | 2024-12-09 | No | Not Required | Not Required | Not Required
25INR0165 | Timberlakes Solar | SS Completed, FIS Started, No IA | Donegalsol | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2026-10-31 | SOL | PV | 203.5 |  | 2022-08-26 | 2022-11-07 | 2023-02-03 | 2022-09-02 |  |  |  | No |  |  | Not Required
25INR0166 | Padrino Solar | SS Completed, FIS Completed, IA | Hill Solar II, LLC | Tap 345kV 68090 Sam Switch – 3389 Fort Smith | Hill | NORTH | 2026-07-30 | SOL | PV | 201.4 | COD | 2023-03-17 | 2022-09-15 | 2022-12-13 | 2023-03-07 | 2025-06-16 |  | 2024-12-24 | Yes |  |  | Not Required | 2025-03-04
25INR0168 | Piedra Solar | SS Completed, FIS Completed, IA | Piedra Solar, LLC | Tap 345-kV line Navarro (68091) – Limestone (46020)) | Freestone | NORTH | 2026-12-22 | SOL | PV | 281.7 |  | 2023-03-09 | 2022-09-02 | 2022-11-30 | 2023-03-07 | 2025-09-17 |  | 2024-07-02 | Yes | Not Required |  | Not Required | 2025-09-17
25INR0169 | Piedra BESS | SS Completed, FIS Completed, IA | Piedra Solar, LLC | Tap 345-kV line Navarro (68091) – Limestone (46020) | Freestone | NORTH | 2026-12-22 | OTH | BA | 103.65 |  | 2023-03-08 | 2022-09-02 | 2022-11-30 | 2023-03-07 | 2025-09-18 |  | 2024-07-02 | Yes | Not Required |  | 2025-09-19 | 2025-09-18
25INR0170 | Pinewood Solar | SS Completed, FIS Completed, IA | Brazoria Solar II, LLC | 43020 Seabreeze 345kV | Brazoria | COASTAL | 2027-01-09 | SOL | PV | 150.68 |  | 2023-07-03 | 2022-09-02 | 2022-11-30 | 2023-06-20 | 2024-07-01 |  | 2025-05-08 | No |  |  | Not Required
25INR0172 | Wolf Spring Solar | SS Completed, FIS Started, IA | Wolf Spring Solar, LLC | Tap 345kV 59904 Cotton Wood - 23922 White River Ckt 1 | Dickens | PANHANDLE | 2028-04-19 | SOL | PV | 195.8 |  | 2022-12-05 | 2022-12-07 | 2023-03-06 | 2022-11-30 |  | No | 2024-08-14 | No | Not Required | Not Required | Not Required
25INR0173 | Wolf Spring Storage | SS Completed, FIS Started, IA | Wolf Spring Solar, LLC | Tap 345kV 59904 Cotton Wood - 23922 White River Ckt 1 | Dickens | PANHANDLE | 2028-04-19 | OTH | BA | 202.7 |  | 2022-12-05 | 2022-12-15 | 2023-03-13 | 2022-12-07 |  | No | 2024-08-14 | No | Not Required | Not Required | 2025-09-15
25INR0174 | Concho Pearl Solar | SS Completed, FIS Started, IA | Concho Pearl Solar, LLC | Tap 345kV 76009 Twin Buttes - 7077 Amos Creek | Concho | WEST | 2027-10-14 | SOL | PV | 171.9 |  | 2022-12-05 | 2022-12-07 | 2023-03-06 | 2022-11-30 |  |  | 2024-07-22 | No | Not Required | Not Required | Not Required
25INR0175 | Concho Pearl Storage | SS Completed, FIS Started, IA | Concho Pearl Solar, LLC | Tap 345kV 76009 Twin Buttes - 7077 Amos Creek | Concho | WEST | 2027-10-14 | OTH | BA | 162.4 |  | 2022-12-08 | 2022-12-15 | 2023-03-13 | 2022-12-07 |  |  | 2024-07-22 | No | Not Required | Not Required | 2025-09-15
25INR0176 | Masava Storage | SS Completed, FIS Started, No IA | Savannah Oaks Solar Project, LLC | tap 345 kV 46020 Limestone Plant - 967 Gibbons Creek ckt 18 | Madison | NORTH | 2028-09-30 | OTH | BA | 261.51 |  | 2022-08-23 | 2022-09-02 | 2022-11-30 | 2022-08-17 |  |  |  | No
25INR0177 | Triangle Ranch Alpha | SS Completed, FIS Started, No IA | Triangle Ranch Wind | Edith Clark 345 kV (#60500) | Cottle | WEST | 2029-07-01 | WIN | WT | 301.74 |  | 2022-10-04 | 2022-10-06 | 2022-12-29 | 2022-09-15 |  |  |  | No |  |  | Not Required
25INR0178 | Triangle Ranch Bravo | SS Completed, FIS Started, No IA | Triangle Ranch Wind | Edith Clark 345 kV (#60500) | Cottle | WEST | 2028-07-01 | WIN | WT | 200.22 |  | 2022-10-04 | 2022-10-06 | 2022-12-29 | 2022-09-15 |  |  |  | No |  |  | Not Required
25INR0184 | Legato BESS | SS Completed, FIS Completed, No IA | Legato Storage, LLC | 138kV #608 Crafton Substation - #620 Bowie Substation | Wise | NORTH | 2028-04-24 | OTH | BA | 202.65 |  | 2023-01-20 | 2022-09-27 | 2022-12-21 | 2023-02-09 01:23 | 2024-09-12 | No |  | No
25INR0186 | Moonlight Sonata BESS | SS Completed, FIS Started, No IA | Samsung Solar Energy 2, LLC | Altair (78118) – Nada (78103) 138KV | Colorado | SOUTH | 2028-07-01 | OTH | BA | 201.08 |  | 2023-07-01 | 2022-09-27 | 2022-12-22 | 2023-06-20 |  |  |  | No
25INR0189 | Staccato BESS | SS Completed, FIS Started, No IA | Staccato Storage, LLC | 138kV WARDA #7312. | Fayette | SOUTH | 2026-12-31 | OTH | BA | 202.65 |  | 2023-01-05 | 2022-11-07 | 2023-02-03 | 2022-12-15 04:41 |  |  |  | No
25INR0190 | Fortissimo BESS | SS Completed, FIS Completed, No IA | Fortissimo BESS, LCC | 741 Dyemound 138kV | Montague | NORTH | 2028-04-24 | OTH | BA | 202.65 |  | 2023-02-28 | 2022-10-18 | 2023-01-13 | 2023-02-09 01:31 | 2024-09-12 | No |  | No
25INR0192 | Palmvalley Storage | SS Completed, FIS Started, No IA | Palmvalley Energy Storage LLC | Frontera (#8980) | Hidalgo | SOUTH | 2027-05-01 | OTH | BA | 100 |  | 2022-08-26 | 2022-09-27 | 2022-12-21 | 2022-09-16 |  |  |  | No
25INR0193 | Nockenut Springs Solar 4 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | The 345 kV Elm Creek - South Texas Project Line (Bus #5133 - #5915) | Gonzales | SOUTH | 2029-06-05 | SOL | PV | 201.15 |  | 2022-09-13 | 2022-09-15 | 2022-12-13 | 2022-08-31 |  |  |  | No |  |  | Not Required
25INR0194 | Photo Solar 1 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2027-05-31 | SOL | PV | 150 |  | 2022-10-04 | 2022-09-15 | 2022-12-13 | 2022-09-15 |  |  |  | No |  |  | Not Required
25INR0195 | Photo Solar 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2027-05-31 | SOL | PV | 300 |  | 2022-10-04 | 2022-09-15 | 2022-12-13 | 2022-09-15 |  |  |  | No |  |  | Not Required
25INR0196 | Inadale Solar | SS Completed, FIS Started, No IA | Inadale Solar, LLC | Tap 345 kV TONKAWAW_5 (11048) – SCURCNTYS_5 (11318) Circuit #2 | Scurry | WEST | 2028-03-03 | SOL | PV | 281.03 |  | 2023-02-17 | 2023-02-20 | 2023-05-19 | 2023-02-08 |  | No |  | No |  |  | Not Required
25INR0197 | Inadale BESS | SS Completed, FIS Started, No IA | Inadale BESS, LLC | Tap 345 kV TONKAWAW_5 (11048) – SCURCNTYS_5 (11318) Circuit #2 | Scurry | WEST | 2028-03-03 | OTH | BA | 287.16 |  | 2023-02-17 | 2023-02-20 | 2023-05-19 | 2023-02-16 |  | No |  | No
25INR0199 | Bonham Solar SLF | SS Completed, FIS Completed, IA | J&J Solar Ranch LLC | TAP 138 kV MEXIA_2_1_8 3632 - GROES_SE1_8 3634 | Limestone | NORTH | 2026-08-31 | SOL | PV | 138.4 | Proj Name | 2022-11-09 | 2022-11-15 | 2023-02-09 | 2022-10-31 | 2024-02-15 | No | 2024-08-07 | Yes | Not Required | Not Required | Not Required | 2025-05-09
25INR0200 | Sunbeam Solar | SS Completed, FIS Started, No IA | Buckeye Midway Solar | 80258 Mayo 138kV | San Patricio | COASTAL | 2028-06-30 | SOL | PV | 73.43 |  | 2024-10-21 | 2024-10-29 | 2024-12-09 | 2024-10-21 |  |  |  | No |  |  | Not Required
25INR0202 | East West BESS | SS Completed, FIS Started, IA | East West Energy Storage, LLC | 7750 LCRA MOUNTAIN HOME SUB | Kerr | SOUTH | 2027-04-29 | OTH | BA | 122.6 | COD | 2022-09-28 | 2022-10-06 | 2022-12-29 | 2022-09-27 |  |  | 2024-07-12 | No | Not Required | Not Required
25INR0204 | Claxton Solar | SS Completed, FIS Started, IA | BT Claxton Solar, LLC | Tap 345kV line between Allen Switch (#2514) and Monticello (#1696) | Hopkins | NORTH | 2027-09-17 | SOL | PV | 150.64 |  | 2023-03-06 | 2022-09-21 | 2022-12-19 | 2022-11-03 |  |  | 2025-07-02 | No |  |  | Not Required
25INR0205 | Claxton Storage | SS Completed, FIS Started, IA | BT Claxton Solar, LLC | Tap 345kV line between Allen Switch (#2514) and Monticello (#1696) | Hopkins | NORTH | 2027-09-17 | OTH | BA | 75.7 |  | 2022-11-18 | 2022-09-21 | 2022-12-19 | 2022-11-03 |  |  | 2025-07-02 | No
25INR0207 | Shadow Ranch Solar | SS Completed, FIS Started, No IA | LectricWind LLC | 842 King Mountain 345kV | Upton | WEST | 2026-06-01 | SOL | PV | 807.61 |  | 2023-07-24 | 2022-09-27 | 2023-01-12 | 2023-07-11 19:49 |  |  |  | No |  |  | Not Required
25INR0208 | Iron Belt Energy Storage | SS Completed, FIS Started, IA | Iron Belt Energy Storage Project, LLC | Long Draw (# 59900) - Volta (#59910) 345kV | Borden | WEST | 2027-07-31 | OTH | BA | 401.9 | COD | 2022-12-27 | 2023-01-03 | 2023-03-30 | 2022-12-19 |  |  | 2023-01-16 | Yes | Not Required | Not Required |  | 2025-02-13
25INR0214 | Burgos Solar | SS Completed, FIS Started, No IA | Twin Oaks Solar, LLC | 3701 Rookie Switch 138 kV | Milam | SOUTH | 2027-11-22 | SOL | PV | 105.52 |  | 2023-03-17 | 2022-10-18 | 2023-01-13 | 2023-03-03 |  |  |  | No |  |  | Not Required
25INR0215 | Middlebrook BESS | SS Completed, FIS Started, IA | Middlebrook Solar LLC | Tap 345kV 3109 Stryker - 3117 Lufkin | Nacogdoches | NORTH | 2027-06-30 | OTH | BA | 158.63 |  | 2022-09-21 | 2022-10-24 | 2023-01-20 | 2022-10-11 |  |  | 2025-07-21 | Yes | Not Required | Not Required |  | 2025-09-08
25INR0216 | Blue Sky Storage SLF | SS Completed, FIS Started, No IA | UKA North America, LLC | 138 kV Friend Ranch (Bus# 6562) | Crockett | WEST | 2025-11-15 | OTH | BA | 0 |  | 2022-10-17 | 2022-10-24 | 2023-01-22 | 2022-10-14 |  |  |  | No
25INR0220 | Hector Solar | SS Completed, FIS Started, No IA | Hector Solar, LLC | Haney (213) - Hubbard_8 (3515) 138kV Line | Navarro | NORTH | 2027-12-31 | SOL | PV | 81.59 |  | 2023-01-06 | 2022-10-24 | 2023-01-20 |  |  | No |  | No |  |  | Not Required
25INR0221 | Hector Storage | SS Completed, FIS Started, No IA | Hector Solar, LLC | Haney (213) - Hubbard_8 (3515) 138kV Line | Navarro | NORTH | 2027-12-31 | OTH | BA | 42.69 |  | 2023-01-06 | 2022-10-24 | 2023-01-20 | 2023-01-02 12:49 |  | No |  | No
25INR0222 | Olympic BESS | SS Completed, FIS Completed, No IA | SMT Olympic BESS LLC | AIRLINE 138 kV Substation (Bus# 8490) | Nueces | COASTAL | 2027-07-01 | OTH | BA | 222.81 |  | 2022-09-27 | 2022-10-18 | 2023-01-13 | 2022-09-29 | 2024-04-19 | No |  | No
25INR0225 | Lucy Solar | SS Completed, FIS Started, IA | Concho County Solar 1 LLC | Tap 345kV 7077 Amos Creek - 6444 San Angelo Red Creek and 7077 Amos Creek - 76009 Twin Buttes | Concho | WEST | 2027-06-30 | SOL | PV | 352.21 |  | 2023-06-15 | 2023-06-28 | 2023-09-20 | 2023-06-08 |  |  | 2024-05-29 | No |  |  | Not Required
25INR0227 | SERENGETI SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green XIV LLC | Tap 138kV Enloe Tap (bus# 11806) – Delta sub (bus# 1802) | Delta | NORTH | 2028-04-20 | SOL | PV | 76.18 |  | 2022-11-08 | 2022-12-07 | 2023-03-06 | 2022-11-18 |  |  |  | No |  |  | Not Required
25INR0229 | OCI Cobb Creek Solar | SS Completed, FIS Completed, IA | Hillsboro Solar Project LLC | tap 345kV 1907 Venus - 68090 Sam Sw | Hill | NORTH | 2026-12-01 | SOL | PV | 203.1 |  | 2022-11-11 | 2022-11-15 | 2023-02-09 | 2022-11-09 | 2024-05-06 | No | 2024-07-24 | Yes | Not Required | Not Required | Not Required | 2025-06-11
25INR0230 | Great Rock BESS | SS Completed, FIS Started, IA | Black Mountain Energy Storage II | Tap 345kV 46020 Limestone - 967 Gibbon Creek Ckt 18 | Leon | NORTH | 2026-12-20 | OTH | BA | 300.9 |  | 2022-10-19 | 2022-11-07 | 2023-02-04 | 2022-10-19 |  | No | 2024-08-23 | No
25INR0231 | Apache Hill BESS | SS Completed, FIS Started, IA | APACHE HILL ENERGY CENTER | 363 Hood 138kV | Hood | NORTH | 2026-07-31 | OTH | BA | 201.15 |  | 2022-10-25 | 2022-11-07 | 2023-02-03 | 2022-10-25 |  | No | 2024-06-26 | Yes | Not Required | Not Required |  | 2024-07-17
25INR0232 | Isaac Solar | SS Completed, FIS Started, IA | Industrial Bravo Project LLC | 8114 Conoco 138kV | Matagorda | COASTAL | 2026-06-30 | SOL | PV | 50.73 | MW Size COD | 2022-10-24 | 2022-11-07 | 2023-02-03 | 2022-10-27 |  | No | 2023-10-18 | Yes | Not Required | Not Required | Not Required | 2023-10-31
25INR0233 | OCI Cobb Creek ESS | SS Completed, FIS Completed, IA | Hillsboro Solar Project LLC | tap 345kV 1907 Venus - 68090 Sam Sw | Hill | NORTH | 2026-12-01 | OTH | BA | 201.6 |  | 2022-11-17 | 2022-12-07 | 2023-03-04 | 2022-11-23 | 2024-05-06 | No | 2024-07-24 | Yes | Not Required |  |  | 2025-06-11
25INR0235 | Austin Bayou Storage I | SS Completed, FIS Started, IA | Austin Bayou Solar, LLC | Tap 345 kV Savana 43180 to Seabreeze 43020 - Ckt 27 | Brazoria | COASTAL | 2027-06-01 | OTH | BA | 150.68 |  | 2023-03-02 | 2023-03-08 | 2023-06-05 | 2023-02-23 |  |  | 2025-02-14 | No | Not Required | Not Required
25INR0236 | Austin Bayou Storage II | SS Completed, FIS Started, IA | Austin Bayou Solar, LLC | Tap to CKT#27 from Savana (Bus# 43180) to Oasis (Bus# 43035) – 345 kV Line | Brazoria | COASTAL | 2027-06-01 | OTH | BA | 156.6 |  | 2023-03-02 | 2023-03-08 | 2023-06-05 | 2023-02-23 |  |  | 2025-02-14 | No | Not Required | Not Required
25INR0237 | Austin Bayou Storage III | SS Completed, FIS Started, IA | Austin Bayou Solar, LLC | Tap 345 kV Savana 43180 to Seabreeze 43020 - Ckt 27 | Brazoria | COASTAL | 2027-06-01 | OTH | BA | 156.6 |  | 2023-03-02 | 2023-03-08 | 2023-06-05 | 2023-02-23 |  |  | 2025-02-14 | No | Not Required | Not Required
25INR0238 | Little Ridge Storage | SS Completed, FIS Started, No IA | TX BESS B LLC | Tap 138kV Swindell (812) - Olinger (818) | Collin | NORTH | 2025-12-11 | OTH | BA | 252 |  | 2023-05-04 | 2023-05-15 | 2023-08-11 | 2023-04-25 |  |  |  | No
25INR0239 | Big Five Storage | SS Completed, FIS Started, No IA | TX BESS 3 LLC | Tap 138kV (5784) Redgtss - (8380) Nedina | Hidalgo | SOUTH | 2026-06-30 | OTH | BA | 102.18 |  | 2023-05-24 | 2023-05-26 | 2023-08-17 | 2023-05-22 |  |  |  | No
25INR0241 | Halcon Storage | SS Completed, FIS Started, No IA | TX BESS A LLC | Tap 138kV 8957 Central Lopeno - 80106 Falcon Dam | Starr | SOUTH | 2028-05-15 | OTH | BA | 132.65 |  | 2023-05-15 | 2023-05-22 | 2023-08-17 | 2023-04-24 |  |  |  | No
25INR0242 | Pato Blanco Storage | SS Completed, FIS Completed, No IA | TX BESS 4, LLC | Tap 138 kV 44010 W A Parish - 42980 NASH___S02_8 | Fort Bend | HOUSTON | 2026-03-01 | OTH | BA | 71.34 |  | 2023-04-25 | 2023-05-15 | 2023-08-11 | 2023-04-24 | 2025-09-12 |  |  | No
25INR0246 | VALDIVIAN SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green III LLC | 138kV 1816 Commerce Switch - 1809 Wolf City | Hunt | NORTH | 2028-03-28 | SOL | PV | 74.9 |  | 2022-11-17 | 2023-02-27 | 2023-05-26 | 2023-02-22 |  |  |  | No |  |  | Not Required
25INR0247 | Bluebonnet Prairie Wind | SS Completed, FIS Started, IA | Bluebonnet Prairie Wind, LLC | Tap 138kV 200 CHATFIELD - 3454 MONTFTSS__8 | Navarro | NORTH | 2027-07-15 | WIN | WT | 173 |  | 2022-12-06 | 2022-12-07 | 2023-03-06 | 2022-11-23 |  | No | 2025-07-03 | Yes |  |  | Not Required
25INR0248 | Strawberry Acres Storage | SS Completed, FIS Started, No IA | Strawberry Acres Energy Center, LLC | 5132 Eagle Creek Substation 138kV | Wilson | SOUTH | 2028-09-30 | OTH | BA | 156.73 |  | 2022-11-11 | 2022-11-23 | 2023-02-17 | 2022-11-15 |  | No |  | No
25INR0253 | Whiskey BESS | SS Completed, FIS Completed, IA | Whiskey BESS LLC | 6828 Canton Tap 138 kV | Van Zandt | NORTH | 2027-01-30 | OTH | BA | 153.72 |  | 2023-05-04 | 2022-12-07 | 2023-03-06 | 2023-05-02 00:13 | 2024-06-03 |  | 2025-03-28 | No | Not Required | Not Required
25INR0262 | Shepard Energy Storage | SS Completed, FIS Completed, IA | Shepard Energy Storage LLC | Hidden Lakes 138kV substation (Bus# 38900) | Galveston | HOUSTON | 2027-07-01 | OTH | BA | 256.37 |  | 2022-12-02 | 2022-12-15 | 2023-03-11 | 2022-12-09 | 2025-08-21 | No | 2024-01-17 | Yes | Not Required | Not Required |  | 2025-02-12
25INR0266 | East Blackland Battery Storage SLF | SS Completed, FIS Started, No IA | DERIVA ENERGY STORAGE, LLC | 7337 Kimbro 138kV | Travis | SOUTH | 2027-05-31 | OTH | BA | 75 | COD | 2022-11-17 | 2022-11-23 | 2023-02-17 | 2022-11-22 |  |  |  | No
25INR0270 | Harryoung Solar | SS Completed, FIS Started, No IA | Gransolar Texas Four LLC | Tap 8319 Rio Hondo - SOUTH SANTA ROSA: 8359, 138kV | Cameron | COASTAL | 2028-05-15 | SOL | PV | 190.01 |  | 2023-11-02 | 2022-11-23 | 2023-02-17 | 2023-08-14 |  |  |  | No | Not Required | Not Required | Not Required
25INR0271 | City Breeze BESS | SS Completed, FIS Started, IA | City Breeze BESS LLC | 8111 MAGILL4A 138KV | Matagorda | COASTAL | 2027-01-04 | OTH | BA | 143.1 |  | 2022-12-14 | 2022-12-15 | 2023-03-11 | 2022-12-06 |  |  | 2024-05-15 | Yes |  |  |  | 2024-05-25
25INR0280 | Nockenut Springs Solar 5 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | Tap 345 kV 5133 Elm Creek - 5915 South Texas Project | Gonzales | SOUTH | 2029-06-05 | SOL | PV | 201.15 |  | 2023-01-24 | 2023-02-09 | 2023-05-08 | 2023-01-27 |  |  |  | No |  |  | Not Required
25INR0281 | Cosper Solar | SS Completed, FIS Completed, IA | Gransolar Texas Twenty LLC | Tap 138kV 115 Ding Dong - 3630 Copperas Cove Tu | Bell | NORTH | 2027-11-12 | SOL | PV | 148.16 |  | 2023-06-13 | 2023-01-03 | 2023-03-30 | 2023-05-26 17:16 | 2024-11-01 |  | 2025-07-31 | Yes | Not Required | Not Required | Not Required | 2025-08-18
25INR0282 | Hornet Solar II SLF | SS Completed, FIS Completed, IA | Hornet Solar II LLC | Ozark Trail Switch 345kV substation (Bus #23901) | Swisher | PANHANDLE | 2028-03-31 | SOL | PV | 208.95 |  | 2022-12-20 | 2023-01-03 | 2023-03-29 | 2022-12-20 | 2024-07-02 | No | 2024-08-21 | Yes |  |  | Not Required | 2025-02-12
25INR0283 | Hornet Storage II SLF | SS Completed, FIS Completed, IA | Hornet Storage II LLC | Ozark Trail Switch 345kV substation (Bus # 23901) | Swisher | PANHANDLE | 2028-03-31 | OTH | BA | 0 |  | 2022-12-28 | 2023-01-03 | 2023-03-29 | 2022-12-20 | 2024-07-02 | No | 2024-08-21 | Yes |  |  |  | 2025-02-12
25INR0284 | Railway BESS | SS Completed, FIS Started, No IA | Grand Reserve Energy, LLC | Martin Lake Switch (3100) – Elkton (3105) 345 kV Line | Rusk | NORTH | 2028-06-01 | OTH | BA | 254.8 |  | 2023-01-27 | 2023-01-30 | 2023-04-28 | 2023-01-23 |  | No |  | No
25INR0286 | Savannah Oaks Solar | SS Completed, FIS Started, No IA | Savannah Oaks Solar Project LLC | Tap 345kV 46020 Limestone Plant - 967 Gibbons Creek | Madison | NORTH | 2028-09-30 | SOL | PV | 200.97 |  | 2022-12-19 | 2023-01-03 | 2023-03-30 | 2022-12-02 |  |  |  | No |  |  | Not Required
25INR0287 | Hide Town Energy Storage | SS Completed, FIS Started, No IA | Hide Town Energy Storage LLC | 1311 SACROC 138kV | Scurry | WEST | 2028-10-11 | OTH | BA | 100.75 |  | 2025-04-24 | 2023-01-17 | 2023-04-14 | 2024-08-28 |  |  |  | No
25INR0288 | Buffalo Prairie Storage | SS Completed, FIS Started, No IA | Buffalo Meadow Energy Center, LLC | Tap 345kV 975 Jack Creek - 3400 Twin Oak | Robertson | NORTH | 2028-09-30 | OTH | BA | 313.51 |  | 2022-12-30 | 2023-01-03 | 2023-03-29 | 2022-12-02 |  |  |  | No
25INR0293 | TOCE BESS 1 | SS Completed, FIS Completed, IA | TOCE BESS 1, LLC | 138 kV Danevang Switching Station (Bus# 5546) | Wharton | SOUTH | 2027-06-01 | OTH | BA | 205.2 |  | 2023-10-02 | 2023-10-13 | 2024-01-10 | 2023-09-22 | 2024-11-07 |  | 2024-12-30 | No | Not Required | Not Required
25INR0297 | RIVERBEND SOLAR SLF | SS Completed, FIS Started, No IA | Riverbend Renewables, LLC | TAP 345 KV LINE FROM TRADINGHOUSE (#3405) TO TEMPLE PECAN CREEK (#3412) SUBSTATIONS | Falls | NORTH | 2027-12-31 | SOL | PV | 301.6 |  | 2023-02-13 | 2023-03-08 | 2023-06-05 | 2023-03-03 |  |  |  | No |  |  | Not Required
25INR0300 | Wizard BESS | SS Completed, FIS Completed, IA | Wizard Energy Storage, LLC | To the 138 kV League City Substation (#38920) | Galveston | HOUSTON | 2025-12-16 | OTH | BA | 150.82 | COD | 2023-03-14 | 2023-03-27 | 2023-06-19 | 2023-03-15 | 2024-01-24 |  | 2023-08-21 | Yes | Not Required | Not Required |  | 2024-07-30 | 2024-07-30 | 2024-07-30 |  |  | 2025-08-25
25INR0301 | Van Zandt Energy Storage | SS Completed, FIS Completed, No IA | Rocky Mountain Energy Holdings, LLC | 1027 Odessa EHV Switch 138 kV | Ector | WEST | 2027-04-13 | OTH | BA | 256.58 |  | 2023-03-21 | 2023-06-07 | 2023-09-01 | 2023-04-05 | 2024-11-18 | No |  | No
25INR0304 | Flying Kite Solar | SS Completed, FIS Started, IA | FLYING KITE SOLAR LLC | Tap the 138 kV La Pryor (#8008) - Poblano (#8009) | Zavala | SOUTH | 2027-05-21 | SOL | PV | 80.38 |  | 2023-03-31 | 2023-04-07 | 2023-07-05 | 2023-03-17 |  |  | 2024-10-02 | No |  |  | Not Required
25INR0306 | Red Top Solar I | SS Completed, FIS Started, No IA | Cat Red Top Solar, LLC | Tap 138kV 1431 Graham SES - Short Grass 11525 | Young | WEST | 2028-04-13 | SOL | PV | 200.59 |  | 2023-10-24 | 2023-01-17 | 2023-04-14 | 2023-10-12 |  |  |  | No | Not Required | Not Required | Not Required
25INR0310 | IEP Blackhawk | SS Completed, FIS Started, No IA | IEP Texas Verde II, llc | 38740 Heights Substation 138kV | Galveston | HOUSTON | 2026-12-01 | OTH | BA | 100 |  | 2023-04-04 | 2023-04-07 | 2023-07-05 | 2023-03-08 |  |  |  | No
25INR0311 | RIVERBEND STORAGE SLF | SS Completed, FIS Completed, No IA | Riverbend Renewables, LLC | TAP 345 KV LINE FROM TRADINGHOUSE (#3405) TO TEMPLE PECAN CREEK (#3412) SUBSTATIONS | Falls | NORTH | 2027-12-31 | OTH | BA | 0 |  | 2023-02-13 | 2023-03-08 | 2023-06-05 | 2023-03-03 | 2024-07-23 |  |  | No
25INR0319 | Northington Solar | SS Completed, FIS Started, IA | Northington Solar, LLC | The 138 kV El Campo (#8102) - Pulsar (#8192) Line; AEP. | Wharton | SOUTH | 2027-07-15 | SOL | PV | 129.81 |  | 2023-02-17 | 2023-02-20 | 2023-05-19 | 2023-02-02 |  |  | 2024-10-02 | Yes | Not Required |  | Not Required | 2025-02-12
25INR0321 | El Molino Solar SLF | SS Completed, FIS Started, No IA | El Molino Solar, LLC | Tap 138kV 80439 LaQuinta - 8297 Bruni 8297 | Webb | SOUTH | 2027-09-01 | SOL | PV | 201.32 |  | 2023-01-16 | 2023-01-17 | 2023-04-14 | 2023-03-31 |  | No |  | No |  |  | Not Required
25INR0322 | El Molino Storage SLF | SS Completed, FIS Started, No IA | El Molino Solar, LLC | Tap 138kV 80439 LaQuinta - 8297 Bruni 8297 | Webb | SOUTH | 2027-09-01 | OTH | BA | 0 |  | 2023-01-16 | 2023-01-17 | 2023-04-14 | 2023-01-13 |  | No |  | No
25INR0329 | Project Lynx BESS | SS Completed, FIS Completed, IA | Corpus Battery Storage, LLC | 138KV Tap 8921 Terra Verde - 8518 Kingsville | Nueces | COASTAL | 2026-05-01 | OTH | BA | 125.3 | MW Size | 2023-03-02 | 2023-03-08 | 2023-06-01 | 2023-03-01 | 2025-08-22 | No | 2024-04-09 | Yes | Not Required | Not Required |  | 2025-02-12
25INR0330 | Clutch City Solar Phase II | SS Completed, FIS Started, IA | HZ SOLAR I, LLC | tap 138kV 42960 Mustang Bayou – 42100 Hudson CKT#04 | Brazoria | COASTAL | 2028-07-01 | SOL | PV | 251.27 |  | 2023-02-17 | 2023-02-20 | 2023-05-20 | 2023-02-10 |  |  | 2025-02-11 | No |  |  | Not Required
25INR0331 | Buffalo Meadow Solar | SS Completed, FIS Started, No IA | Buffalo Meadow Energy Center, LLC | Tap Jack Creek (975) - Twin Oak (3400) 345kV line | Robertson | NORTH | 2028-09-30 | SOL | PV | 251.27 |  | 2023-02-15 | 2023-02-27 | 2023-05-26 | 2023-01-27 |  |  |  | No |  |  | Not Required
25INR0334 | Star Dairy Storage | SS Completed, FIS Completed, IA | Star Dairy Storage | Tap 345kV 1692 PARIS_SW1_5 -- 11699 WOODARD_5 | Lamar | NORTH | 2027-04-03 | OTH | BA | 204.93 |  | 2023-04-17 | 2023-04-19 | 2023-07-14 | 2023-04-11 | 2025-02-17 | No | 2024-12-09 | No | Not Required | Not Required
25INR0337 | Butcherbird Solar | SS Completed, FIS Started, No IA | Butcherbird Solar, LLC | Tap 138 kV - Bell County #133 to Bartlett Switch #114 | Bell | NORTH | 2027-02-01 | SOL | PV | 116 |  | 2023-11-28 | 2023-12-18 | 2024-03-15 | 2023-12-06 |  |  |  | No | Not Required | Not Required | Not Required
25INR0338 | Les Energy Storage | SS Completed, FIS Completed, No IA | Rocky Mountain Energy Development, LLC | Tap 138 kV 1326 Stanton East – 11324 Leatherwood Pod | Howard | WEST | 2028-04-30 | OTH | BA | 205.13 |  | 2023-02-23 | 2023-02-09 | 2023-05-05 | 2023-02-17 | 2025-06-09 |  |  | No
25INR0339 | Fort Concho Energy storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Development, LLC | Tap 138 kV #76320 Schkade - #76011 Twin Buttes Line; LCRA | Tom Green | WEST | 2028-12-31 | OTH | BA | 251.15 |  | 2023-02-23 | 2023-01-30 | 2023-04-28 | 2023-02-17 |  |  |  | No
25INR0341 | Rosebud Storage SLF | SS Completed, FIS Started, No IA | Rosebud Storage, LLC | Tap 69 kV 67 BAGGINS - 69 BARCLAY | Falls | NORTH | 2028-01-15 | OTH | BA | 0 |  | 2024-01-05 | 2023-03-09 | 2023-06-05 | 2023-12-04 20:34 |  |  |  | No
25INR0342 | Nickel Spruce Solar | SS Completed, FIS Started, No IA | Nickel Spruce Solar LLC | Tap 138kV 6735 Pleasant Springs Switching Station - 6736 Middl | Leon | NORTH | 2027-12-15 | SOL | PV | 150 |  | 2023-11-10 | 2023-01-30 | 2023-04-28 | 2023-10-31 17:43 |  |  |  | No |  |  | Not Required
25INR0346 | Cado Storage | SS Completed, FIS Started, No IA | Cado Storage, LLC | Tap 138 kV Line from Braunig East (#5030) to Highland Hills (#5205) Ckt. 1 | Bexar | SOUTH | 2029-04-06 | OTH | BA | 205.51 |  | 2023-03-10 | 2023-03-13 | 2023-06-09 | 2023-03-07 |  |  |  | No
25INR0347 | Cadet Storage | SS Completed, FIS Started, No IA | TX BESS 5, LLC | Tap 69kV 32864 BRYN_ATK69 to 32873 BRYN SHADY | Brazos | NORTH | 2026-04-01 | OTH | BA | 104.42 |  |  | 2023-05-22 | 2023-08-18 | 2023-04-24 |  |  |  | No
25INR0353 | Marshall Spring Solar | SS Completed, FIS Started, No IA | Marshall Springs Solar, LLC | New POI station between 7132 L_GILLES8_1Y - 7126 L_FERGUS8_1Y 138kV line and 7132 L_GILLES8_1Y - 7128 L_HORSBA8_1Y 138kV line, then loop in both lines into the new POI station. | Gillespie | SOUTH | 2026-07-01 | SOL | PV | 150 |  | 2023-10-04 | 2023-02-20 | 2023-05-18 | 2023-09-27 22:57 |  |  |  | No |  |  | Not Required
25INR0354 | Marshall Spring Storage | SS Completed, FIS Started, No IA | Marshall Springs Storage, LLC | New POI station between 7132 L_GILLES8_1Y - 7126 L_FERGUS8_1Y 138kV line and 7132 L_GILLES8_1Y - 7128 L_HORSBA8_1Y 138kV line, then loop in both lines into the new POI station. | Gillespie | SOUTH | 2026-07-01 | OTH | BA | 150 |  | 2023-10-04 | 2023-02-20 | 2023-05-18 | 2023-09-27 23:01 |  |  |  | No
25INR0368 | Echols Creek Solar | SS Completed, FIS Started, IA | BT Ferguson Solar, LLC | Tap 138kV Hawk Hollow Switch (#11768) and Lamar Blossom Switch (#11770) | Lamar | NORTH | 2027-04-03 | SOL | PV | 201.15 |  | 2023-03-17 | 2023-04-07 | 2023-07-05 | 2023-03-22 |  |  | 2024-07-06 | Yes | Not Required | Not Required | Not Required | 2025-07-08
25INR0369 | Echols Creek Storage | SS Completed, FIS Started, IA | BT Ferguson Solar, LLC | Tap 138kV Hawk Hollow Switch (#11768) and Lamar Blossom Switch (#11770) | Lamar | NORTH | 2027-10-13 | OTH | BA | 100.57 |  | 2023-03-17 | 2023-04-07 | 2023-07-05 | 2023-03-22 |  |  | 2024-12-06 | Yes | Not Required | Not Required |  | 2025-07-08
25INR0370 | Willis Storage | SS Completed, FIS Completed, IA | BT Majewski Storage LLC | tap 138kV Emory North 3171 to Liberty POD 1723 | Rains | NORTH | 2027-08-13 | OTH | BA | 176.13 |  | 2023-03-03 | 2023-03-27 | 2023-06-24 | 2023-03-13 | 2024-11-08 |  | 2025-04-07 | Yes |  |  |  | 2025-07-07
25INR0371 | McMurtre Storage | SS Completed, FIS Completed, No IA | BT McMurtre Storage, LLC | tap 138kV 1819 Commerce South - 1815 Cumby Tap | Hunt | NORTH | 2027-06-01 | OTH | BA | 176.13 |  | 2023-03-10 | 2023-03-13 | 2023-06-09 | 2023-03-06 | 2024-07-08 |  |  | No
25INR0372 | Elan BESS | SS Completed, FIS Completed, No IA | Elan BESS, LLC | 42380 Needville 138kV | Fort Bend | HOUSTON | 2026-12-31 | OTH | BA | 202.65 |  | 2023-03-01 | 2023-03-08 | 2023-06-05 | 2023-02-15 | 2024-03-21 |  |  | No
25INR0374 | Meridian BESS | SS Completed, FIS Completed, No IA | Navitas Energy- Meredian BESS | 319 Meridian 69 KV | Bosque | NORTH | 2027-10-01 | OTH | BA | 31.23 |  | 2023-03-10 | 2023-03-13 | 2023-06-09 | 2023-03-10 | 2024-06-14 | No |  | No | Not Required
25INR0375 | NavBoot BESS | SS Completed, FIS Started, No IA | Navboot BESS LLC | 8858 MCKENZIE4A 138kV | Nueces | COASTAL | 2026-12-01 | OTH | BA | 303.7 |  | 2023-03-10 | 2023-03-13 | 2023-06-09 | 2023-03-10 |  |  |  | No
25INR0376 | Hawkins BESS | SS Completed, FIS Started, No IA | BRP BLUE TOPAZ 7, LLC | 85005 ELGATO4A 138 kV | Hidalgo | SOUTH | 2028-01-16 | OTH | BA | 150.43 |  | 2023-04-19 | 2023-05-03 | 2023-07-28 | 2023-04-19 |  |  |  | No
25INR0377 | Proteus Vernon Solar SLF | SS Completed, FIS Started, No IA | Vernon Solar and Storage LLC (a Delaware LLC) | 6060 Vernon 138kV | Wilbarger | WEST | 2028-05-31 | SOL | PV | 75 |  | 2023-07-17 | 2023-03-27 | 2023-06-19 | 2023-07-03 |  |  |  | No |  |  | Not Required
25INR0378 | Second Division Storage | SS Completed, FIS Started, No IA | Mound Creek Storage, LLC | Tap 138 kV SANBER_POI_8 (Bus# 43110) to WEST COLUMBIA (Bus# 43380) Ckt 60 Line | Brazoria | COASTAL | 2025-12-31 | OTH | BA | 0 |  | 2023-04-03 | 2023-04-19 | 2023-07-13 | 2023-03-15 |  |  |  | No
25INR0379 | Starr Storage | SS Completed, FIS Started, No IA | Falcon Lake Storage, LLC | 8795 Roma 138kV | Starr | SOUTH | 2028-03-29 | OTH | BA | 0 |  | 2023-04-03 | 2023-06-28 | 2023-09-22 | 2023-03-08 |  |  |  | No
25INR0380 | Fike BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 9, LLC | 5754 Aderhold 138kV | Hidalgo | SOUTH | 2027-06-18 | OTH | BA | 200.8 |  | 2023-04-17 | 2023-05-15 | 2023-08-11 | 2023-04-19 |  |  |  | No
25INR0382 | HappyDogSolar | SS Completed, FIS Completed, IA | Rosula Solar LLC | Tap 345kV 3704 Hog Creek Switch – 3687 Bell County East Switch | Milam | SOUTH | 2027-04-13 | SOL | PV | 85.54 |  | 2023-05-30 | 2023-06-07 | 2023-09-01 | 2023-05-25 | 2025-01-07 | No | 2024-12-16 | No |  |  | Not Required
25INR0384 | Zorro BESS | SS Completed, FIS Completed, IA | ZORRO BESS LLC | 138 kV Ben Wheeler (Bus# 6852) | Van Zandt | NORTH | 2027-05-01 | OTH | BA | 153.69 |  | 2023-06-13 | 2023-03-27 | 2023-06-19 | 2023-06-02 23:26 | 2024-05-21 | No | 2025-03-28 | No | Not Required | Not Required
25INR0385 | Bobcat Cameron BESS | SS Completed, FIS Started, No IA | Bobcat BESS, LLC | 5764 East Rio Hondo Substation 138kV | Cameron | COASTAL | 2027-12-31 | OTH | BA | 200.78 |  | 2023-04-06 | 2023-04-19 | 2023-07-14 | 2023-04-11 |  |  |  | No
25INR0386 | Diaz BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 10, LLC | 8950 Olmito 138kV | Cameron | COASTAL | 2027-11-18 | OTH | BA | 241.48 |  | 2023-05-19 | 2023-05-22 | 2023-08-17 | 2023-05-17 |  | No |  | No
25INR0389 | Stoneridge BESS | SS Completed, FIS Completed, IA | Stoneridge Solar, LLC | Tap 345 kV 13429 SANDOW SWITCH - 7040 AUSTROP CKT 2 | Milam | SOUTH | 2025-12-30 | OTH | BA | 101.9 | COD | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-03-09 | 2024-09-06 | No | 2024-04-19 | Yes | Not Required | Not Required |  | 2025-01-28 | 2025-01-28 | 2025-01-28 |  |  | 2025-06-26 | 2025-07-10
25INR0390 | Macho Creek BESS | SS Completed, FIS Started, No IA | Macho Creek BESS, LLC | Tap 138kV 8793 RIO GRANDE CITY - 8806 LAS LOMAS | Starr | SOUTH | 2027-05-31 | OTH | BA | 150.56 |  | 2023-06-19 | 2023-06-28 | 2023-09-22 | 2023-06-06 |  |  |  | No
25INR0391 | Purple Sage BESS 1 | SS Completed, FIS Completed, IA | Purple Sage, LLC | Anna 345 kV Bus# 2373. | Collin | NORTH | 2027-05-30 | OTH | BA | 156 |  | 2023-03-07 | 2023-03-08 | 2023-06-05 | 2023-03-07 | 2024-03-20 | No | 2024-10-11 | Yes | Not Required | Not Required |  | 2025-02-13
25INR0392 | Purple Sage BESS 2 | SS Completed, FIS Completed, IA | Purple Sage, LLC | Anna 345 kV Bus# 2373 | Collin | NORTH | 2027-05-30 | OTH | BA | 156 |  | 2023-03-07 | 2023-03-08 | 2023-06-05 | 2023-03-07 | 2024-03-20 | No | 2024-10-11 | Yes | Not Required | Not Required |  | 2025-02-13
25INR0394 | Orchard Ray BESS | SS Completed, FIS Started, No IA | Pettus BESS | 8593 PETTUS2A 69kV | Bee | SOUTH | 2027-05-01 | OTH | BA | 51.85 |  | 2023-05-22 | 2023-06-07 | 2023-09-01 | 2023-05-31 |  |  |  | No
25INR0395 | Hinkell BESS | SS Completed, FIS Started, No IA | Reveille BESS | 8612 Reveille 138kV | La Salle | SOUTH | 2027-07-01 | OTH | BA | 78.05 |  | 2023-08-15 | 2023-08-21 | 2023-11-17 | 2023-08-14 |  | No |  | No
25INR0396 | Stewart Grady BESS | SS Completed, FIS Completed, No IA | Grady BESS | Tap 138kV 11368 Expanse Switch – 23841 Sale Ranch | Martin | WEST | 2028-04-19 | OTH | BA | 150.5 |  | 2023-05-22 | 2023-05-26 | 2023-08-22 | 2023-05-01 | 2024-08-23 | No |  | No
25INR0397 | Beeman BESS | SS Completed, FIS Started, No IA | Beeman BESS LLC | 69kV Waelder Substation (7232) | Gonzales | SOUTH | 2027-05-15 | OTH | BA | 50.18 |  | 2023-04-07 | 2023-04-19 | 2023-07-13 | 2023-03-22 |  |  |  | No
25INR0399 | Blossomheath BESS | SS Completed, FIS Started, No IA | Taurbeng LLC | tap VENUS SWITCH (#1907) – SAM SWITCH (#68090) 345 kV line | Ellis | NORTH | 2026-11-28 | OTH | BA | 300.78 |  | 2023-05-02 | 2023-05-26 | 2023-08-17 | 2023-05-23 |  |  |  | No
25INR0400 | Maldives Solar | SS Completed, FIS Started, IA | Maldives Solar LLC | Tap 345kV 59900 Long Draw - 11318 Scurry County South and 345kV 59905 Faraday - 11318 Scurry County South | Scurry | WEST | 2028-07-01 | SOL | PV | 184 |  | 2023-07-08 | 2023-07-18 | 2023-10-15 | 2023-07-05 |  |  | 2023-12-01 | Yes |  |  | Not Required | 2024-07-17
25INR0401 | WOE Gyp King Wind | SS Completed, FIS Started, No IA | White Oak Energy, LLC | Tap 138kV 33798 GYP_18 – 6088 BENJ4A | King | WEST | 2027-03-31 | WIN | WT | 315 |  | 2023-04-18 | 2023-04-19 | 2023-07-12 | 2023-04-17 |  |  |  | No |  |  | Not Required
25INR0402 | Driet BESS | SS Completed, FIS Started, No IA | Weimar BESS | 7254 WEIMAR8 138kV | Colorado | SOUTH | 2027-10-15 | OTH | BA | 150.52 |  | 2023-05-22 | 2023-06-07 | 2023-09-01 | 2023-05-31 |  |  |  | No
25INR0405 | Pledgor BESS | SS Completed, FIS Completed, No IA | Pledgor BESS | Tap Gulftie (43340) – Pledger (43120) circuit 60 | Matagorda | COASTAL | 2028-04-06 | OTH | BA | 100.33 |  | 2023-04-26 | 2023-05-03 | 2023-07-31 | 2023-04-25 | 2024-08-27 | No |  | No
25INR0414 | Rogers Creek BESS | SS Completed, FIS Completed, No IA | Dialville BESS | Tap 138 KV DailVille (3160) - Neches Pump (3296) | Cherokee | NORTH | 2028-04-19 | OTH | BA | 100.33 |  | 2023-05-03 | 2023-05-15 | 2023-08-11 | 2023-05-03 | 2025-09-23 | No |  | No
25INR0416 | Proteus Vernon Storage SLF | SS Completed, FIS Started, No IA | Vernon Solar and Storage LLC (a Delaware LLC) | 6060 Vernon 138kV | Wilbarger | WEST | 2026-12-31 | OTH | BA | 0 |  | 2023-07-13 | 2023-03-27 | 2023-06-19 | 2023-07-03 18:26 |  |  |  | No
25INR0417 | Mesa View Storage | SS Completed, FIS Started, No IA | Mesa View Storage, LLC | Tap 345 kV KINGMTSW (#842) to NORTMC (#76000) | Upton | WEST | 2027-01-29 | OTH | BA | 251.3 |  | 2023-04-11 | 2023-04-19 | 2023-07-12 | 2023-04-12 |  |  |  | No
25INR0419 | Marengo BESS | SS Completed, FIS Started, No IA | BRP BLUE TOPAZ 8, LLC | 8640 Kelvin Station 138kV (AEP) | Cameron | COASTAL | 2028-05-15 | OTH | BA | 120.72 |  | 2023-04-25 | 2023-05-15 | 2023-08-11 | 2023-05-08 |  | No |  | No
25INR0420 | Houston BESS | SS Completed, FIS Completed, No IA | SMT Houston | Tap 138 kV LAUDER (#46002) - RITTENHOUSE (#46282) ckt 95 | Harris | HOUSTON | 2026-12-15 | OTH | BA | 227.9 | COD | 2023-03-31 | 2023-04-07 | 2023-07-03 | 2023-03-28 | 2024-04-04 |  |  | No
25INR0421 | Aldrin 138 BESS | SS Completed, FIS Completed, IA | Aldrin Energy Storage LLC | (Bus: 39015) North Alvin TNMP 138kV | Brazoria | COASTAL | 2027-07-01 | OTH | BA | 207 |  | 2023-05-02 | 2023-05-15 | 2023-08-11 | 2023-05-04 | 2025-08-22 | No | 2024-04-18 | Yes | Not Required | Not Required |  | 2024-05-06
25INR0422 | Waterloo Solar 1 | SS Completed, FIS Started, IA | Waterloo Solar, LLC | AUSTROP TO GARFIELD 345kV LINE [Bus # 7040 - 7048] | Bastrop | SOUTH | 2027-12-01 | SOL | PV | 200.64 |  | 2023-04-18 | 2023-04-19 | 2023-07-12 | 2023-03-30 |  |  | 2024-09-04 | No |  |  | Not Required
25INR0423 | Brackens Solar | SS Completed, FIS Started, No IA | Brackens Solar | 3558 Ranchland 138 kV | Freestone | NORTH | 2027-07-01 | SOL | PV | 177.24 |  | 2023-05-04 | 2023-05-15 | 2023-08-11 | 2023-05-01 |  |  |  | No |  |  | Not Required
25INR0424 | Brackens BESS | SS Completed, FIS Started, No IA | Brackens BESS | 3558 Ranchland 138 kV | Freestone | NORTH | 2027-07-01 | OTH | BA | 103.58 |  | 2023-04-19 | 2023-05-03 | 2023-07-28 | 2023-04-19 |  |  |  | No
25INR0425 | Aldrin 345 BESS | SS Completed, FIS Completed, IA | Aldrin Energy Storage LLC | (Bus: 43030) Meadow 345kV substation | Brazoria | COASTAL | 2027-12-01 | OTH | BA | 362 |  | 2023-05-10 | 2023-05-15 | 2023-08-11 | 2023-05-05 | 2025-04-21 | No | 2024-06-15 | Yes | Not Required | Not Required |  | 2025-02-12
25INR0430 | Hackberry Creek Solar | SS Completed, FIS Started, No IA | Hackberry Creek Solar LLC | tap 345kV 10053 Cattleman Switch - 1058 Longshore Switch | Mitchell | WEST | 2028-07-01 | SOL | PV | 176.13 |  | 2023-07-19 | 2023-07-31 | 2023-10-27 | 2023-07-19 |  |  |  | No |  |  | Not Required
25INR0432 | Brotherton Storage | SS Completed, FIS Started, IA | BT Brotherton Storage, LLC | 6937 Tucker Sub 138kV | Anderson | NORTH | 2026-12-31 | OTH | BA | 176.13 |  | 2023-04-12 | 2023-04-19 | 2023-07-13 | 2023-04-12 |  | No | 2024-08-06 | Yes |  |  |  | 2025-09-15
25INR0434 | Bluegill BESS | SS Completed, FIS Started, No IA | Bluegill BESS, LLC | Tap 138 kV 40130 Atascocita - 40690 East Gate | Harris | HOUSTON | 2027-10-31 | OTH | BA | 251 | COD | 2023-06-07 | 2023-06-28 | 2023-09-21 | 2023-05-18 |  | No |  | No
25INR0436 | Hess King Solar Farm | SS Completed, FIS Started, No IA | Facility Innovations Group | 8212 DILLEYSW4A 138kV | Frio | SOUTH | 2025-12-31 | SOL | PV | 130 |  | 2023-08-25 | 2023-04-19 | 2023-07-13 | 2023-08-14 20:25 |  |  |  | No | Not Required | Not Required | Not Required |  |  |  | 2023-09-01 | 2025-09-01
25INR0439 | Stephens Ranch Wind Repower | SS Completed, FIS Started, No IA | Stephens Ranch Wind Energy, LLC | 59900 Long Draw 345 kV | Borden | WEST | 2026-10-01 | WIN | WT | 12.4 |  | 2023-06-07 | 2023-06-28 | 2023-09-20 | 2023-05-15 |  |  |  | Yes |  |  | Not Required
25INR0440 | Bronc Rodeo Solar Project | SS Completed, FIS Completed, No IA | Energiekontor US Texas SP 16 LLC | Tap 138 kV Line from Temple Pecan Creek (#3420) to the Cow Bayou Switch (#3385) | Falls | NORTH | 2028-03-27 | SOL | PV | 121.63 |  | 2023-09-19 | 2023-05-03 | 2023-07-28 | 2023-09-12 | 2025-03-25 |  |  | No | Not Required | Not Required | Not Required
25INR0441 | Dios BESS | SS Completed, FIS Started, IA | Dios BESS, LLC | 8117 GANADO138kV | Jackson | SOUTH | 2027-12-31 | OTH | BA | 201.08 |  | 2023-04-26 | 2023-05-15 | 2023-08-11 | 2023-05-08 |  |  | 2025-04-03 | Yes | Not Required | Not Required |  | 2025-09-08
25INR0442 | Happy Dog Storage | SS Completed, FIS Started, IA | Rosula Solar LLC | Tap 345kV 3704 Hog Creek Switch – 3687 Bell County East Switch | Milam | SOUTH | 2027-04-13 | OTH | BA | 104.47 |  | 2023-05-23 | 2023-06-07 | 2023-09-01 | 2023-06-02 |  | No | 2024-12-16 | No
25INR0446 | Guitar BESS | SS Completed, FIS Started, No IA | Guitar BESS LLC | Tap 138kV 6275 ABEAST4A - 6670 PUTN4C | Callahan | WEST | 2027-12-31 | OTH | BA | 204.79 |  | 2024-04-15 | 2023-05-15 | 2023-08-11 | 2024-04-03 |  |  |  | No
25INR0447 | Waterloo BESS 1 | SS Completed, FIS Started, IA | Waterloo Solar, LLC | Tap 345kV 7040 AUSTROP - 7048 GARFIELD | Bastrop | SOUTH | 2027-12-01 | OTH | BA | 105.64 |  | 2023-05-03 | 2023-05-15 | 2023-08-11 | 2023-05-03 |  |  | 2024-09-04 | No | Not Required | Not Required
25INR0451 | Tres Rios Ranch BESS | SS Completed, FIS Started, No IA | LectricWind LLC | 76008 Twelvemile 345kV | Upton | WEST | 2027-12-31 | OTH | BA | 290 |  | 2023-05-22 | 2023-05-26 | 2023-08-22 | 2023-05-23 |  |  |  | No
25INR0452 | Spaniel Farm Solar Project | SS Completed, FIS Started, No IA | Energiekontor US Texas SP 18 LLC | Tap 138 kV 2241 Ennis West Switch - 12320 Templeton | Ellis | NORTH | 2027-04-12 | SOL | PV | 100.52 |  | 2023-09-26 | 2023-05-03 | 2023-07-28 | 2023-09-12 22:39 |  |  |  | No |  |  | Not Required
25INR0455 | John Bull BESS | SS Completed, FIS Started, No IA | BRP BLUE TOPAZ 13, LLC | 8482 WEIL TRC4A 138kV | Nueces | COASTAL | 2028-04-16 | OTH | BA | 147.42 |  | 2023-07-17 | 2023-07-31 | 2023-10-27 | 2023-07-27 |  |  |  | No
25INR0458 | Surfside Energy Storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Holdings, LLC | Tap 138kV 42110 Angleton – 43150 Riwood ckt 82 | Brazoria | COASTAL | 2028-12-31 | OTH | BA | 50.34 |  | 2024-03-12 | 2023-07-19 | 2023-10-10 | 2024-02-28 |  |  |  | No | Not Required | Not Required
25INR0459 | Old Sorrell Energy Storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Holdings, LLC | Tap 69kV 6372 Eden - 6376 Colorado River Municipal Water #1 | Concho | WEST | 2028-01-10 | OTH | BA | 43.1 |  | 2024-04-23 | 2023-06-28 | 2023-09-21 | 2024-04-23 18:42 |  |  |  | No
25INR0460 | Acker BESS | SS Completed, FIS Completed, IA | Ogallala BESS LLC | 23912 Ogallala 345 kV | Castro | PANHANDLE | 2028-04-17 | OTH | BA | 301.04 | COD | 2023-05-26 | 2023-06-07 | 2023-09-01 | 2023-05-09 | 2025-02-04 |  | 2025-04-21 | No | Not Required | Not Required
25INR0466 | Yooperlite Storage | SS Completed, FIS Completed, No IA | BT Yooperlite Storage, LLC | Tap 138 kV 580 Westbrook Switch - 588 Willow | Wise | NORTH | 2028-05-31 | OTH | BA | 175.65 |  | 2023-06-13 | 2023-06-28 | 2023-09-20 | 2023-06-06 | 2025-05-19 | No |  | No
25INR0473 | Crowded Star I BESS | SS Completed, FIS Started, No IA | Jones City Solar II, LLC | 68014 Open Sky | Jones | WEST | 2026-12-31 | OTH | BA | 202.69 |  | 2023-07-25 | 2023-08-21 | 2023-11-02 | 2023-08-09 |  |  |  | No
25INR0474 | Solheim Solar | SS Completed, FIS Started, No IA | Solheim Solar, LLC | Meridian (Bus# 315) - Glen Rose (Bus #319) 69 kV | Bosque | NORTH | 2027-11-01 | SOL | PV | 108.68 |  | 2024-04-04 | 2023-08-14 | 2023-11-10 | 2024-03-21 14:26 |  |  |  | No |  |  | Not Required
25INR0475 | Castle Corral BESS | SS Completed, FIS Completed, No IA | Castle Corral BESS, LLC | 345 kV Russell Gap Switching Station Bus #3348 | Mills | NORTH | 2028-03-27 | OTH | BA | 200.9 |  | 2023-07-26 | 2023-07-31 | 2023-10-27 | 2023-07-26 | 2025-06-18 |  |  | No
25INR0480 | Bell Creek BESS | SS Completed, FIS Completed, IA | BELL CREEK BESS, LLC | Tap 138kV 39500 West Colombia - 39703 FM524 | Brazoria | COASTAL | 2027-10-30 | OTH | BA | 200.9 |  | 2023-11-29 | 2023-06-28 | 2023-09-21 | 2023-11-17 | 2024-05-16 |  | 2024-11-14 | No
25INR0482 | Vault Solar | SS Completed, FIS Completed, No IA | PPM THR Solar | Tap #331 Rwmiller - #320 Jaybird 138kV | Palo Pinto | NORTH | 2026-12-31 | SOL | PV | 108.5 |  | 2023-06-20 | 2023-06-28 | 2023-09-20 | 2023-06-16 | 2024-12-02 | No |  | No |  |  | Not Required
25INR0487 | Marick Rose BESS | SS Completed, FIS Completed, No IA | Marick BESS | Tap 138kV 44521 Marick - 44615 Rosenberg Ckt 60 | Fort Bend | HOUSTON | 2026-05-01 | OTH | BA | 50.18 |  | 2023-07-01 | 2023-07-10 | 2023-10-05 | 2023-06-23 | 2024-04-19 |  |  | No
25INR0489 | Ranchero BESS | SS Completed, FIS Started, No IA | Ranchero Battery Facility, LLC | 7053 Noelke 345 kV | Crockett | WEST | 2026-10-30 | OTH | BA | 150 |  | 2024-04-25 | 2023-06-28 | 2023-09-22 | 2024-04-03 |  |  |  | No
25INR0491 | Tarim BESS | SS Completed, FIS Started, No IA | BRP Tarim BESS LLC | 5727 Pawnee Switching Substation 138kV | Karnes | SOUTH | 2027-12-01 | OTH | BA | 201 |  | 2024-10-07 | 2024-11-19 | 2025-02-14 | 2024-10-10 |  |  |  | No
25INR0492 | Blue Summit Energy Storage | SS Completed, FIS Completed, IA | NextEra Energy Interconnection Holdings, LLC | 61001 JIM TREECE 345kV | Wilbarger | WEST | 2026-07-01 | OTH | BA | 100 |  | 2023-08-28 | 2023-10-20 | 2024-01-16 | 2023-10-18 | 2025-05-08 | No | 2012-02-22 | Yes | Not Required | Not Required | 2023-10-26 | 2025-02-13 | 2025-07-28 | 2025-07-28
25INR0493 | PHOTON SOLAR 1 2 SLF | SS Completed, FIS Completed, IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2025-10-31 | SOL | PV | 235.66 |  | 2024-08-28 | 2024-09-02 | 2021-02-02 | 2024-08-28 | 2022-11-28 |  | 2021-10-01 | Yes |  |  | Not Required | 2021-11-05 | 2021-11-05 | 2023-01-27 |  |  | 2024-10-15 | 2024-10-31
25INR0494 | Willow Beach Wind | SS Completed, FIS Completed, IA | ACE DevCo NC LLC | Tap 138 kV Bus# 42100 HUD_8 – Bus# 42960 MUSTNG_S04_8 138kV CKT# 4 | Brazoria | COASTAL | 2027-10-01 | WIN | WT | 202.33 |  | 2023-08-28 | 2023-10-13 | 2024-01-10 | 2023-09-20 | 2024-11-18 |  | 2025-06-16 | No |  |  | Not Required
25INR0495 | Dolomite Storage | SS Completed, FIS Started, No IA | BT Wilson Storage, LLC | 218 Rockett 69kV | Ellis | NORTH | 2026-12-01 | OTH | BA | 125.7 |  | 2023-08-15 | 2023-09-08 | 2023-12-04 | 2023-08-22 |  | No |  | No | Not Required | Not Required
25INR0497 | Stegall Solar | SS Completed, FIS Completed, No IA | BT Martin Solar, LLC | Elliott (Bus #53) to Franklin (Bus #57) 69kV Transmission Line | Robertson | NORTH | 2026-12-31 | SOL | PV | 81.57 |  | 2023-08-15 | 2023-08-21 | 2023-11-06 | 2023-08-02 | 2025-08-06 | No |  | No |  |  | Not Required
25INR0498 | Stegall Storage | SS Completed, FIS Completed, No IA | BT Martin Solar, LLC | Tap connection to a new switching station on the Elliott (Bus #53) - Franklin (Bus #57) 69 kV Transmission Line | Robertson | NORTH | 2026-12-31 | OTH | BA | 50.47 |  | 2023-08-07 | 2023-08-21 | 2023-11-06 | 2023-08-15 | 2025-08-06 | No |  | No
25INR0501 | Longday Solar SLF | SS Completed, FIS Started, No IA | Longday Solar | Tap138 kV 8252 Brackettville - 8260 Escondido | Kinney | SOUTH | 2027-12-15 | SOL | PV | 200.8 |  | 2023-07-22 | 2023-07-31 | 2023-10-27 | 2023-07-20 |  | No |  | No | Not Required | Not Required | Not Required
25INR0502 | Longday BESS SLF | SS Completed, FIS Started, No IA | Longday Solar | Tap 138 kV 8252 Brackettville - 8260 Escondido | Kinney | SOUTH | 2027-12-15 | OTH | BA | 0 |  | 2023-07-22 | 2023-07-31 | 2023-10-27 | 2023-07-20 |  | No |  | No
25INR0503 | Timmerman Power Plant Phase 2 | SS Completed, FIS Completed, IA | Lower Colorado River Authority | 7041 John Dumas 345kV | Caldwell | SOUTH | 2026-04-07 | GAS | IC | 188.4 |  | 2023-10-04 | 2023-09-22 | 2023-12-14 | 2023-09-29 | 2025-06-04 | No | 2023-12-28 | Yes | 2024-03-12 | Not Required | 2024-01-04 | 2025-05-22 | 2025-07-29 | 2025-07-29
25INR0504 | Lazy Frog Solar SLF | SS Completed, FIS Started, No IA | Lazy Frog Solar, LLC | 11688 Thorn Tree Switch 345kV | Franklin | NORTH | 2028-04-17 | SOL | PV | 100.4 |  | 2024-05-15 | 2023-09-22 | 2023-12-14 | 2024-05-10 |  |  |  | No |  |  | Not Required
25INR0505 | Mud Cat Solar SLF | SS Completed, FIS Started, No IA | Mud Cat Solar, LLC | Tap 138KV 11768 Hawk Hollow – 1768 Deport | Lamar | NORTH | 2027-09-13 | SOL | PV | 100.5 |  | 2024-05-13 | 2023-10-20 | 2024-01-16 | 2024-05-14 |  |  |  | No |  |  | Not Required
25INR0506 | Lazy Frog Storage SLF | SS Completed, FIS Started, No IA | Lazy Frog Solar, LLC | 11688 Thorn Tree Switch 345kV | Franklin | NORTH | 2028-04-17 | OTH | BA | 0 |  | 2024-05-15 | 2023-09-22 | 2023-12-14 | 2024-05-10 |  |  |  | No
25INR0507 | Mud Cat Storage SLF | SS Completed, FIS Started, No IA | Mud Cat Solar, LLC | 11768 Hawk Hollow – 1768 Deport 138kV | Lamar | NORTH | 2027-09-13 | OTH | BA | 0 |  | 2024-05-13 | 2023-10-20 | 2024-01-16 | 2024-05-14 |  |  |  | No
25INR0511 | Pearl Moon | SS Completed, FIS Started, No IA | Pearl Moon Solar, LLC | Tap 345kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2028-03-31 | SOL | PV | 208 |  | 2023-07-31 | 2023-09-07 | 2023-12-06 | 2023-08-23 |  |  |  | No | Not Required | Not Required | Not Required
25INR0512 | Monument Hill Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | Tap 345kV 7055 Fayette - 9074 Lytton Springs | Fayette | SOUTH | 2027-06-01 | SOL | PV | 200 |  | 2023-07-31 | 2023-10-13 | 2024-01-10 | 2023-08-23 |  |  |  | No |  |  | Not Required
25INR0513 | Kahla Storage | SS Completed, FIS Started, No IA | BT Kahla Storage, LLC | Tap 345kV 46020 Limestone 967 Gibbons Creek Circuit 50 | Leon | NORTH | 2028-12-29 | OTH | BA | 200.9 |  | 2023-08-16 | 2023-08-21 | 2023-11-17 | 2023-08-15 |  | No |  | No
25INR0515 | Fagus Storage SLF | SS Completed, FIS Started, No IA | Greenalia Energy Storage MISAE II LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2026-09-01 | OTH | BA | 0 |  | 2023-10-19 | 2023-10-25 | 2024-01-22 | 2023-09-22 |  |  |  | No
25INR0528 | Indigo Storage 2 | SS Completed, FIS Started, No IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2026-08-17 | OTH | BA | 60 |  | 2024-06-12 | 2023-09-22 | 2023-12-20 | 2024-06-06 15:40 |  |  |  | No
25INR0529 | Indigo Storage 3 | SS Completed, FIS Started, No IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2026-08-17 | OTH | BA | 60 |  | 2024-08-23 | 2023-11-14 | 2024-02-09 | 2024-06-06 10:43 |  |  |  | No
25INR0530 | Indigo Storage 4 | SS Completed, FIS Started, No IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2026-08-17 | OTH | BA | 60 |  | 2024-06-26 | 2023-10-25 | 2024-01-22 | 2024-06-06 15:45 |  |  |  | No
25INR0531 | CPS Energy AvR1CT2 Rotor Replacement | SS Completed, FIS Completed, No IA | CPS Energy | 5475 Braunig 345kV | Bexar | SOUTH | 2025-06-30 | GAS | CC | 23.2 |  | 2024-02-09 | 2023-10-13 | 2024-01-10 | 2024-01-26 17:03 | 2024-04-25 |  |  | No | 2028-03-20 |  | 2024-04-01 | 2024-04-01 | 2024-04-25 | 2024-05-01 |  |  |  | 2024-11-22
25INR0541 | Port City Energy Storage | SS Completed, FIS Started, No IA | Port City Energy Storage, LLC | Tap 138kV 80258 Mayo4A - 80260 Gila4A | San Patricio | COASTAL | 2028-12-31 | OTH | BA | 101.2 |  | 2023-10-17 | 2023-10-25 | 2024-01-22 | 2023-10-17 |  | No |  | No | Not Required | Not Required
25INR0542 | Hynes Bay Energy Storage | SS Completed, FIS Started, No IA | Hynes Bay Energy Storage, LLC | Tap 138kV 5546 DANEVANG SW - 8121 BLESSING | Wharton | SOUTH | 2027-12-31 | OTH | BA | 101.2 |  | 2023-10-16 | 2023-10-25 | 2024-01-22 | 2023-10-16 |  |  |  | No | Not Required | Not Required
25INR0544 | Palacios Bay Energy Storage | SS Completed, FIS Started, No IA | Palacios Bay Energy Storage, LLC | Tap 138kV #8115 WADSWORT4A - #8139 CELNEBC4B | Matagorda | COASTAL | 2028-12-31 | OTH | BA | 101.2 |  | 2023-10-10 | 2023-10-19 | 2024-01-16 | 2023-10-10 |  |  |  | No | Not Required | Not Required
25INR0545 | Blue Creek Energy Storage | SS Completed, FIS Started, No IA | Blue Creek Energy Storage, LLC | Tap 138kV 42985 DYANN_POI8 - 43190 S_LANE_B138 Ckt 60 | Wharton | SOUTH | 2028-12-31 | OTH | BA | 101.2 |  | 2023-10-11 | 2023-10-13 | 2024-01-10 | 2023-10-11 |  | No |  | No | Not Required | Not Required
25INR0546 | VISOL 1 SOLAR | SS Completed, FIS Started, No IA | VISOL 1 SOLAR, LLC | Tap 138kV 8683 Comstock - 60389 Corral | Val Verde | WEST | 2028-06-30 | SOL | PV | 94.78 |  | 2024-02-04 | 2023-10-25 | 2024-01-22 | 2024-01-24 |  |  |  | No | Not Required | Not Required | Not Required
25INR0547 | Indigo solar 2 | SS Completed, FIS Started, No IA | Indigo Solar 2 | Tap 345KV 68001 Clayton 345KV -68000 WShack Ckt 2 | Fisher | WEST | 2027-07-15 | SOL | PV | 180 |  | 2024-08-23 | 2023-10-04 | 2023-12-22 | 2024-08-13 |  |  |  | No |  |  | Not Required
25INR0550 | Carolina Storage Friendswood | SS Completed, FIS Started, No IA | CSE Storage, LLC | TAP 138kV 39010 HASTINGS - 38980 FRIENDSWOOD | Brazoria | COASTAL | 2026-12-14 | OTH | BA | 105.08 |  | 2024-01-04 | 2024-02-02 | 2024-04-29 | 2024-01-17 |  |  |  | No
25INR0552 | HarryoungBESS | SS Completed, FIS Started, No IA | Gransolar Texas Four LLC | 8319 Rio Hondo sub 138kV | Cameron | COASTAL | 2028-05-15 | OTH | BA | 190.01 |  | 2023-09-26 | 2023-10-04 | 2023-12-19 | 2023-09-19 |  |  |  | No | Not Required | Not Required
25INR0554 | Dan Kearney BESS | SS Completed, FIS Completed, IA | Dan Kearney BESS LLC | 39703 TNFM524 138kV | Brazoria | COASTAL | 2027-10-01 | OTH | BA | 200.78 |  | 2023-10-19 | 2024-01-11 | 2024-04-08 | 2024-01-03 | 2024-10-02 |  | 2024-10-18 | No
25INR0555 | Stargazer Solar | SS Completed, FIS Started, No IA | Stargazer Solar LLC | 44010 WA Parish - 42980 Nash 138 kV Ckt 02 | Brazoria | COASTAL | 2027-02-01 | SOL | PV | 157.7 |  | 2023-10-11 | 2023-10-30 | 2024-01-26 | 2023-10-23 |  |  |  | No | Not Required | Not Required | Not Required
25INR0556 | Stargazer BESS | SS Completed, FIS Started, No IA | Stargazer Solar LLC | 44010 WA Parish - 42980 Nash 138 kV | Brazoria | COASTAL | 2027-02-01 | OTH | BA | 104.5 |  | 2023-10-20 | 2023-10-30 | 2024-01-26 | 2023-10-23 |  |  |  | No | Not Required | Not Required
25INR0557 | McCamey's Castle Battery | SS Completed, FIS Started, IA | Castle Storage, LLC | 76597 Robbins Switch 138 kV | Upton | WEST | 2025-12-15 | OTH | BA | 409.6 |  | 2023-09-29 | 2023-10-13 | 2024-01-10 | 2023-10-09 |  |  | 2025-03-20 | Yes | Not Required | Not Required |  | 2025-03-20
25INR0558 | Ayass BESS | SS Completed, FIS Started, No IA | Harvick BESS, LLC | 6206 Bush Knob 69kV | Throckmorton | WEST | 2028-12-30 | OTH | BA | 51.28 |  | 2023-11-27 | 2023-12-04 | 2024-03-01 | 2023-11-15 |  |  |  | No
25INR0566 | Copano Bay Energy Storage | SS Completed, FIS Started, No IA | Copano Bay Energy Storage, LLC | Tap 138kV 42980 Nash - 44010 WA Parish Ckt 2 | Brazoria | COASTAL | 2027-12-31 | OTH | BA | 201.04 |  | 2023-10-22 | 2023-10-25 | 2024-01-22 | 2023-10-17 |  |  |  | No | Not Required | Not Required
25INR0578 | Forest Creek Wind Repower | SS Completed, FIS Completed, IA | Forest Creek Wind Farm, LLC | Mcdonald 138 kV (Bus #: 1333) | Glasscock | WEST | 2025-12-15 | WIN | WT | 125.1 |  | 2023-11-15 | 2024-01-11 | 2024-04-05 | 2023-12-08 | 2024-12-10 |  | 2005-11-17 | Yes |  |  | Not Required | 2025-01-24 | 2025-01-24 | 2025-01-24 |  |  | 2025-07-28 | 2025-08-27
25INR0579 | Albatross BESS 2 | SS Completed, FIS Started, No IA | Albatross Solar, LLC | Tap 138kV 165 Windsor Switch - 161 McGregor | McLennan | NORTH | 2028-02-22 | OTH | BA | 159.6 |  | 2024-02-01 | 2024-02-27 | 2024-05-22 | 2024-01-03 |  | No |  | No
25INR0582 | Maleza Storage II | SS Completed, FIS Started, No IA | Brush Storage, LLC | 44220 Julia 345kV | Wharton | SOUTH | 2026-11-09 | OTH | BA | 256.1 | COD | 2024-02-10 | 2024-02-27 | 2024-05-24 | 2024-02-20 |  | No |  | No
25INR0583 | Shannon Wind Repower | SS Completed, FIS Started, No IA | Shannon Wind, LLC | 1458 Cobb Switching Station 345 kV | Archer | WEST | 2027-09-15 | WIN | WT | 18.52 | MW Size | 2024-02-26 | 2024-02-27 | 2024-05-31 | 2024-01-29 |  |  |  | No |  |  | Not Required
25INR0586 | Zeus Armstrong Solar | SS Completed, FIS Started, No IA | Armstrong Solar, LLC | Tap 345KV 23900 AlLIBATES -23914 TULECNYN | Armstrong | PANHANDLE | 2028-04-17 | SOL | PV | 503.56 |  | 2024-08-01 | 2024-05-20 | 2024-06-19 | 2024-07-22 |  |  |  | No |  |  | Not Required |  |  |  | 2026-01-01 | 2027-03-01
25INR0587 | Zeus Armstrong BESS | SS Completed, FIS Started, No IA | Armstrong BESS, LLC | Tap 345KV 23900 ALIBATES - 23914 TULECNYN | Armstrong | PANHANDLE | 2028-04-17 | OTH | BA | 1043.08 |  | 2024-08-12 | 2024-03-22 | 2024-06-19 | 2024-08-08 |  |  |  | No | [6 empty] | 2026-01-01 | 2027-03-01
25INR0588 | Zeus Mitchell Solar | SS Completed, FIS Started, No IA | Mitchell Solar, LLC | Tap 345KV Ranger Camp (10049) – Prong Moss (10057) CKT#01 | Mitchell | WEST | 2026-08-01 | SOL | PV | 804.71 |  | 2024-05-14 | 2024-03-22 | 2024-06-19 | 2025-03-28 |  |  |  | No |  |  | Not Required |  |  |  | 2025-02-18 | 2026-03-15
25INR0589 | Zeus Mitchell BESS | SS Completed, FIS Started, No IA | Mitchell BESS | Tap 345KV Ranger Camp (10049) – Prong Moss (10057) CKT#01 | Mitchell | WEST | 2027-05-01 | OTH | BA | 1042.94 |  | 2025-06-02 | 2024-05-20 | 2024-06-19 | 2025-03-28 |  |  |  | No | [6 empty] | 2025-02-18 | 2026-03-15
25INR0590 | Zeus Rusk Solar | SS Completed, FIS Started, No IA | Rusk Solar, LLC | Tap 345kV 3109 Stryker to 3100 Martin Lake | Rusk | NORTH | 2027-03-01 | SOL | PV | 26.8 | MW Size | 2025-09-05 | 2024-03-22 | 2024-06-19 | 2024-12-16 |  |  |  | No |  |  | Not Required |  |  |  | 2025-10-01 | 2026-10-15
25INR0591 | Zeus Rusk BESS | SS Completed, FIS Started, No IA | Rusk BESS, LLC | Tap 345kV 3109 Stryker to 3100 Martin Lake | Rusk | NORTH | 2027-03-01 | OTH | BA | 208.8 |  | 2024-12-30 | 2024-04-09 | 2024-06-19 | 2024-12-16 |  |  |  | No | [6 empty] | 2025-10-01 | 2026-10-15
25INR0606 | Proteus Thornton Ranch Solar SLF | SS Completed, FIS Started, No IA | Thornton Ranch Solar, LLC | 37990 TNSTAGHORN1 138kV | Ward | WEST | 2027-09-30 | SOL | PV | 180 |  | 2024-02-12 | 2024-02-26 | 2024-05-20 | 2024-02-12 |  | No |  | No | Not Required | Not Required | Not Required
25INR0607 | Proteus Thornton Ranch Storage SLF | SS Completed, FIS Started, No IA | Thornton Ranch Solar, LLC | 37990 TNSTAGHORN1 138kV | Ward | WEST | 2027-09-30 | OTH | BA | 0 |  | 2024-01-08 | 2024-03-22 | 2024-06-19 | 2024-03-11 |  | No |  | No
25INR0608 | Proteus London-Leigh Solar SLF | SS Completed, FIS Started, No IA | London Leigh Solar, LLC | 345kV Bernoulli (bus # 59907) | Glasscock | WEST | 2028-09-30 | SOL | PV | 600 |  | 2024-01-08 | 2024-03-22 | 2024-06-19 | 2024-02-19 |  |  |  | No |  |  | Not Required
25INR0609 | Proteus London-Leigh Storage SLF | SS Completed, FIS Started, No IA | London Leigh Solar, LLC | Bernoulli (bus # 59907) | Glasscock | WEST | 2028-09-30 | OTH | BA | 0 |  | 2024-01-08 | 2024-02-27 | 2024-04-19 | 2023-12-22 |  |  |  | No
25INR0610 | Adam Bryant BESS | SS Completed, FIS Started, No IA | Adam Bryant BESS LLC | Tap 138kV 5225 HONDO – 5819 HONDO CREEK | Medina | SOUTH | 2027-12-01 | OTH | BA | 99.52 |  | 2024-04-15 | 2024-02-26 | 2024-05-24 | 2024-04-12 |  |  |  | No
25INR0611 | Carolina Storage Odessa | SS Completed, FIS Started, No IA | CSE Storage, LLC | 1058 LONGSHORE 345kV | Howard | WEST | 2029-05-01 | OTH | BA | 202.8 | COD | 2024-01-03 | 2024-02-02 | 2024-04-29 | 2024-01-17 |  |  |  | No | Not Required | Not Required
25INR0616 | Bobcat Bluff Storage SLF | SS Completed, FIS Started, No IA | Cub Storage LLC | 1475 Windthorst 138 kV | Archer | WEST | 2027-04-15 | OTH | BA | 0 |  | 2024-06-18 | 2024-02-27 | 2024-05-25 | 2024-06-12 |  |  |  | No
25INR0621 | Anagram Solar | SS Completed, FIS Started, No IA | Anagram Solar | 8156 Charter 138 kV | Live Oak | SOUTH | 2026-12-01 | SOL | PV | 130.56 |  | 2025-01-07 | 2024-04-09 | 2024-07-05 | 2025-01-02 |  |  |  | No |  |  | Not Required
25INR0622 | Turkey Creek Solar | SS Completed, FIS Started, No IA | Greenray Solar Corporation | 7425 ODLASW 138kV | Kinney | SOUTH | 2026-12-22 | SOL | PV | 180.9 | MW Size | 2024-10-04 | 2024-02-26 | 2024-05-24 | 2024-08-23 |  |  |  | No |  |  | Not Required |  |  |  | 2025-09-23 | 2026-10-13
25INR0623 | Turkey Creek Battery Energy Storage System | SS Completed, FIS Started, No IA | Greenray Solar Corporation | 7425 ODLASW 138 kV | Kinney | SOUTH | 2026-12-22 | OTH | BA | 0 | MW Size | 2024-09-26 | 2024-03-29 | 2024-05-24 | 2024-09-13 |  |  |  | No
25INR0628 | Carolina Storage Wichita Falls | SS Completed, FIS Started, No IA | CSE Storage, LLC | Tap 345kV 1422 Bowman - 1458 Cobb Switch | Archer | WEST | 2028-08-01 | OTH | BA | 202 |  | 2024-01-30 | 2024-02-26 | 2024-05-25 | 2024-02-14 |  |  |  | No | Not Required | Not Required
25INR0629 | Carolina Storage Midland | SS Completed, FIS Started, No IA | CSE Storage, LLC | Tap 345kV 10057 Prong Moss Switch - 10062 Rockhound Switch CKT 1 | Howard | WEST | 2028-10-03 | OTH | BA | 204.7 |  | 2024-06-17 | 2024-07-01 | 2024-09-26 | 2024-03-26 |  |  |  | No
25INR0632 | Jenna Eco-Electric Solar | SS Completed, FIS Started, No IA | Clean Energy Holdings, LLC | Tap 345 kV 1048 Tonkawa Switch - 1430 Graham SES | Fisher | WEST | 2027-06-05 | SOL | PV | 576.3 |  | 2024-05-17 | 2024-05-20 | 2024-08-13 | 2024-05-17 |  |  |  | No |  |  | Not Required
25INR0653 | Southfork Energy Storage | SS Completed, FIS Started, No IA | Southfork Energy Storage, LLC | tap 345kV 60709 Oersted - 60616 Edison CKT 1 | Kimble | SOUTH | 2028-11-30 | OTH | BA | 306.4 |  | 2024-06-19 | 2024-07-22 | 2024-10-08 | 2024-06-13 |  | Yes |  | No
25INR0656 | Gilleys Energy Storage | SS Completed, FIS Started, No IA | Gilleys Energy Storage, LLC | Tap 345 kV 1730 West Krum - 6111 Riley CKT 2 | Wise | NORTH | 2028-04-21 | OTH | BA | 306.4 |  | 2024-05-03 | 2024-06-03 | 2024-08-27 | 2024-05-06 |  |  |  | No
25INR0657 | O'Bannion Energy Storage | SS Completed, FIS Completed, No IA | O'Bannion Energy Storage, LLC | 1506 Long Hollow Switch 345 kV | Jack | NORTH | 2027-09-25 | OTH | BA | 306.4 |  | 2024-05-06 | 2024-05-09 | 2024-08-05 | 2024-05-01 | 2025-05-02 |  |  | No
25INR0660 | Wooderson Energy Storage | SS Completed, FIS Started, No IA | Wooderson Energy Storage, LLC | Tap 345 kV 11418 TECUMSEH- 1421 Willow Creek | Jack | NORTH | 2028-09-30 | OTH | BA | 306.4 |  | 2024-04-15 | 2024-05-09 | 2024-08-05 | 2024-04-18 |  |  |  | No | [7 empty] | 2027-09-21
25INR0661 | McCrae Energy Storage | SS Completed, FIS Started, No IA | McCrae Energy Storage, LLC | Tap 345 kV 1900 COMCHPKW_5 - 1440 COMCHESS1_5 | Erath | NORTH | 2028-04-21 | OTH | BA | 306.35 |  | 2024-04-29 | 2024-05-20 | 2024-08-13 | 2024-05-01 |  |  |  | No
25INR0666 | GIBSON BRANCH BESS | SS Completed, FIS Started, No IA | Gibson Branch BESS LLC | 7064 Lampasas Substation 138kV | Lampasas | NORTH | 2028-01-15 | OTH | BA | 142.9 |  | 2024-05-09 | 2024-05-20 | 2024-08-14 | 2024-04-24 |  |  |  | No
25INR0672 | Fagus Solar Park 2 SLF | SS Completed, FIS Completed, IA | Excel Advantage Services, LLC dba Misae Solar Park II | 60501 Tesla 345 kV | Childress | PANHANDLE | 2025-10-03 | SOL | PV | 166.57 |  | 2024-05-15 | 2024-06-03 | 2018-07-06 | 2024-05-30 | 2024-02-27 | No | 2019-02-21 | Yes |  |  | Not Required | 2024-12-19 | 2024-12-19 | 2024-04-30 |  |  | 2025-05-29 | 2025-07-07
25INR0673 | PHOTON SOLAR 4 SLF | SS Completed, FIS Completed, No IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2025-10-31 | SOL | PV | 105.98 |  | 2024-08-28 | 2024-09-04 | 2021-02-02 | 2024-08-21 | 2022-11-28 |  |  | Yes | Not Required | Not Required | Not Required | 2021-11-05 | 2023-01-27 | 2023-01-27 |  |  | 2024-06-25 | 2024-11-04
25INR0688 | Giga Texas Data Center | SS Completed, FIS Completed, IA | Giga Texas Energy, LLC | HORNSBY Substation POIB# 7047 Site will be connected behind the meter at Medium Voltage 24.9 kV with non export controls GSU TRANSFORMER 80/106/133MVA 345kV DELTA PRIMARY 24.9kV WYE-G SECONDARY Z=XX%, 65DEG C RISE | Travis | SOUTH | 2025-12-15 | OTH | BA | 133 |  | 2024-08-15 | 2024-08-27 | 2024-11-25 | 2024-07-30 | 2025-03-17 |  | 2025-04-30 | No | Not Required | Not Required |  |  |  | 2025-05-01
25INR0693 | Leon BESS | SS Completed, FIS Started, No IA | Leon BESS | Tab 138kv 3355 Grapeland_Magnolia - 3357 Pleasant_Springs. | Houston | NORTH | 2028-02-16 | OTH | BA | 153.7 | COD | 2024-11-13 | 2024-11-26 | 2025-02-18 | 2024-11-18 |  |  |  | No
25INR0706 | Bocanova Power II | SS Completed, FIS Completed, IA | Bocanova Power II LLC | 39030 TNMP Alvin 138kV | Brazoria | COASTAL | 2026-05-01 | OTH | BA | 150.46 | SFS/NtP | 2024-10-14 | 2024-10-10 | 2025-01-07 | 2024-10-01 | 2025-03-07 |  | 2025-08-19 | Yes |  |  |  | 2025-09-15
25INR0777 | V4 Palo Alto DGR | SS Completed, FIS Completed, IA | Life Cycle Power | XFMR. #1 | Bexar | SOUTH | 2025-09-11 | OIL | OT | 33 |  |  | 2025-06-06 | 2025-06-19 | 2025-06-06 | 2025-08-01 |  | 2025-08-08 | No | [8 empty] | 2025-08-27 | 2025-08-29
25INR0809 | Jaguar BESS_1 | SS Started, FIS Started, No IA | PP Jaguar BESS LLC | Tap 345kV 13405 Tradinghouse SES - 68090 Sam Switch | McLennan | NORTH | 2025-10-03 | OTH | BA | 157.1 | COD |  |  |  | 2025-06-05 |  |  |  | No | [8 empty] | 2025-05-09 | 2025-07-18
26INR0001 | Turin TxHSR TPSS HN-6 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | 8 Crutchfield 138kV | Grimes | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-10-22 | 2019-09-27 | 2021-04-28 | 2019-09-27 |  |  |  | No
26INR0004 | GRIMES SOLAR | SS Completed, FIS Started, No IA | CG Grimes County LLC | 40600 Roans Prairie 345kV | Grimes | NORTH | 2026-02-15 | SOL | PV | 153.45 |  | 2022-03-09 | 2022-03-14 | 2022-06-03 | 2022-03-07 |  |  |  | No |  |  | Not Required
26INR0008 | Puerto Del Sol 1 | SS Completed, FIS Started, No IA | PUERTO DEL SOL, LLC | Tap 345kV 79500 Palmito - 79501 King Fisher Ckt 1 | Cameron | COASTAL | 2026-12-31 | SOL | PV | 213.8 |  | 2023-01-20 | 2022-05-16 | 2022-08-13 | 2023-01-13 16:05 |  |  |  | No | Not Required | Not Required | Not Required
26INR0019 | HyFuels Green Lake Solar | SS Completed, FIS Started, No IA | HyFuels Green Lake Solar LLC | 8189 Tungsten 138kV | Victoria | SOUTH | 2027-12-01 | SOL | PV | 346 |  | 2023-06-09 | 2022-09-27 | 2022-12-22 | 2023-06-13 21:34 |  |  |  | No |  |  | Not Required
26INR0021 | Crossroads Wind | SS Completed, FIS Started, IA | HyFuels Green Lake Wind LLC | Tap 138 KV 8723 Cangrejo - 8721 BEECHER | Victoria | SOUTH | 2027-06-30 | WIN | WT | 276.7 | MW Size | 2023-07-01 | 2022-09-27 | 2022-12-22 | 2023-06-16 |  |  | 2024-07-24 | Yes | Not Required | Not Required | Not Required | 2025-09-10
26INR0023 | Leon Solar Park | SS Completed, FIS Completed, IA | Misae Solar IV LLC | Tap 138kV Grapeland Magnolia Tap (bus #3355) to Pleasant Springs POI (bus# 3357) section of the Jewett -Crockett 138kV Line | Leon | NORTH | 2026-07-01 | SOL | PV | 210.11 |  | 2022-08-11 | 2022-09-15 | 2022-12-13 | 2022-08-27 | 2025-09-09 | Yes | 2024-05-21 | Yes |  |  | Not Required | 2025-02-12
26INR0024 | Becerra Creek Storage 1 | SS Completed, FIS Started, No IA | Bordas Renewable Energy, LLC | 345 kV Cenizo Substation (#80220) | Webb | SOUTH | 2027-12-01 | OTH | BA | 125.62 |  | 2022-09-19 | 2022-09-21 | 2022-12-19 | 2022-09-07 |  |  |  | No
26INR0028 | HyFuels Calhoun Solar | SS Completed, FIS Started, No IA | HyFuels Green Lake Solar LLC | Tap 345kV 8715 RADIANT7A - 8728 COBRA7A | Victoria | SOUTH | 2027-10-01 | SOL | PV | 301.82 | COD | 2023-07-17 | 2022-10-18 | 2023-01-15 | 2023-07-07 |  | Yes |  | No |  |  | Not Required
26INR0030 | Perry Creek Solar SLF | SS Completed, FIS Started, No IA | Perry Creek Solar, LLC | 345kV Navarro (#68091) to Limestone (# 46020) | Freestone | NORTH | 2027-03-24 | SOL | PV | 102.04 |  | 2022-11-08 | 2022-12-07 | 2023-03-04 | 2022-11-08 |  |  |  | No | Not Required | Not Required | Not Required
26INR0031 | Perry Creek Storage SLF | SS Completed, FIS Started, No IA | Perry Creek Solar, LLC | 345kV Navarro (#68091) to Limestone (# 46020) | Freestone | NORTH | 2027-03-24 | OTH | BA | 0 |  | 2022-11-08 | 2022-12-07 | 2023-03-04 | 2022-11-08 |  |  |  | No
26INR0033 | Fairway Storage | SS Completed, FIS Started, No IA | Fairway Storage LLC | Tap 138kV 3503 FAIRWPOD_8 - 196 FAIRFIELD | Freestone | NORTH | 2027-09-24 | OTH | BA | 120.3 |  | 2023-02-17 | 2022-11-07 | 2023-02-04 | 2023-02-15 |  | No |  | No
26INR0034 | Bracero Pecan Storage | SS Completed, FIS Started, IA | Bracero Pecan Storage LLC | 60716 SARAGOSA 138kV | Reeves | WEST | 2027-07-01 | OTH | BA | 232 |  | 2023-07-13 | 2022-11-07 | 2023-02-04 | 2023-07-10 |  |  | 2024-06-27 | Yes |  |  |  | 2025-02-12
26INR0045 | LUND STORAGE CENTER 1 | SS Completed, FIS Started, No IA | Lund Storage Center 1, LLC | TAP 138 KV LINE AND CREATE NEW BUS BETWEEN KIMBRO (7337) AND ELGIN SWITCH (3650) | Bastrop | SOUTH | 2026-12-31 | OTH | BA | 407.55 |  | 2023-05-26 | 2023-01-17 | 2023-04-14 | 2023-05-16 22:50 |  |  |  | No
26INR0049 | Pin Peaking Energy Center 1 (TEF- Due Diligence) | SS Completed, FIS Completed, IA | PIN OAK CREEK ENERGY CENTER, LLC | 3134 RICHLAND CHAMBERS 345kV (PSS/E Bus Name: RICHLND1_5) | Freestone | NORTH | 2026-05-01 | GAS | GT | 228 |  | 2023-04-12 | 2023-04-19 | 2023-07-13 | 2023-04-11 | 2024-04-23 |  | 2024-05-30 | Yes | 2024-06-12 | 2024-06-12 | 2024-11-27 | 2025-02-12 | 2025-06-27 | 2025-07-29
26INR0068 | Charro Creek Solar 1 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-07-01 | SOL | PV | 203 |  | 2023-01-23 | 2023-01-30 | 2023-04-28 | 2023-02-10 |  |  |  | No |  |  | Not Required
26INR0069 | Charro Creek Storage 1 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-07-01 | OTH | BA | 0 |  | 2023-02-27 | 2023-03-08 | 2023-04-28 | 2023-02-15 |  |  |  | No
26INR0070 | Charro Creek Solar 2 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-07-01 | SOL | PV | 203 |  | 2023-02-27 | 2023-03-08 | 2023-06-01 | 2023-02-15 |  |  |  | No |  |  | Not Required
26INR0071 | Charro Creek Storage 2 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-07-01 | OTH | BA | 0 |  | 2023-02-27 | 2023-03-08 | 2023-06-01 | 2023-02-15 |  |  |  | No
26INR0072 | Charro Creek Solar 3 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap on PAWNEESW5 (#5725) - COLETO7A (#8164) Line | Karnes | SOUTH | 2026-07-01 | SOL | PV | 203 |  | 2023-02-27 | 2023-03-08 | 2023-06-01 | 2023-02-15 |  |  |  | No |  |  | Not Required
26INR0073 | Charro Creek Storage 3 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-07-01 | OTH | BA | 0 |  | 2023-01-23 | 2023-01-30 | 2023-04-28 | 2023-02-10 |  |  |  | No
26INR0074 | Anila Solar | SS Completed, FIS Completed, IA | Alina Energy LLC | Tap 345kV 5133 Elm Creek - 5901 San Miguel Gen Ckt 1 | Wilson | SOUTH | 2028-06-30 | SOL | PV | 200.8 |  | 2023-01-23 | 2023-01-30 | 2023-04-28 | 2023-01-20 | 2024-07-10 |  | 2025-03-06 | No |  |  | Not Required
26INR0077 | Anila BESS | SS Completed, FIS Completed, IA | Alina Energy LLC | Tap of 345 kV Elm Creek (Bus# 5133) - San Miguel Gen (Bus# 5901) Transmission Line Ckt 1 | Wilson | SOUTH | 2028-06-30 | OTH | BA | 209 |  | 2023-06-01 | 2023-02-20 | 2023-05-20 | 2023-05-25 17:00 | 2024-07-10 |  | 2025-03-06 | No | Not Required | Not Required
26INR0082 | Amerada Solar | SS Completed, FIS Started, No IA | Amerada Solar, LLC | Tap 345kV 3133 RICHLND2_5 - 3381 BIGBRNW_5 | Freestone | NORTH | 2028-07-21 | SOL | PV | 301.57 |  | 2023-05-12 | 2023-05-15 | 2023-08-11 | 2023-04-28 |  |  |  | No |  |  | Not Required
26INR0083 | Zeppelin Energy Storage | SS Completed, FIS Started, No IA | ZEPPELIN ENERGY STORAGE LLC | 6464 San Angelo North | Tom Green | WEST | 2028-05-31 | OTH | BA | 163.93 |  | 2023-03-08 | 2023-01-30 | 2023-04-28 | 2023-02-17 19:02 |  |  |  | No
26INR0084 | Amerada Storage | SS Completed, FIS Started, No IA | Amerada Solar, LLC | Tap 345kV 3133 RICHLND2_5 - 3381 BIGBRNW_5 | Freestone | NORTH | 2028-07-21 | OTH | BA | 150.78 |  | 2023-05-10 | 2023-05-15 | 2023-08-11 | 2023-04-28 |  |  |  | No
26INR0086 | Solarville Solar | SS Completed, FIS Started, No IA | Ville Solar, LLC | 2432 Tri-Corner 345kV | Dallas | NORTH | 2028-09-19 | SOL | PV | 400 |  | 2025-02-12 | 2024-05-20 | 2024-08-15 | 2025-02-05 |  |  |  | No |  |  | Not Required
26INR0088 | La Salle Solar | SS Completed, FIS Started, No IA | OCI La Salle Solar LLC | Tap 345kV LOBO7A (#80219) - FOWLERTONSW5 (#5709) | La Salle | SOUTH | 2027-07-01 | SOL | PV | 512.6 |  | 2023-03-31 | 2023-04-19 | 2023-07-14 | 2023-04-03 |  | No |  | No |  |  | Not Required
26INR0089 | Crescent C BESS | SS Completed, FIS Started, No IA | OCI La Salle ESS LLC | Tap 345kV LOBO7A (#80219) - FOWLERTONSW5 (#5709) CKT#2 | La Salle | SOUTH | 2028-02-12 | OTH | BA | 508.34 |  | 2023-03-15 | 2023-04-07 | 2023-07-03 | 2023-03-15 |  | Yes |  | No
26INR0098 | Douie Solar | SS Completed, FIS Completed, No IA | Buffalo Spring Solar LLC | Tap 138 kV 3501 Sea way Teague - 3394 Jewett | Freestone | NORTH | 2027-09-30 | SOL | PV | 221.2 |  | 2023-05-09 | 2023-05-15 | 2023-08-11 | 2023-05-12 | 2025-07-07 |  |  | No |  |  | Not Required
26INR0107 | Freedom Falcon BESS | SS Completed, FIS Started, No IA | Falcon BESS, LLC | Tap 345kV #80224 Tiempo - #80227 Rapido | Zapata | SOUTH | 2028-08-11 | OTH | BA | 501.9 |  | 2023-04-26 | 2023-06-28 | 2023-09-22 | 2023-06-14 |  | Yes |  | No
26INR0109 | Pin Peaking Energy Center 2 (TEF- Due Diligence) | SS Completed, FIS Completed, IA | PIN OAK CREEK ENERGY CENTER, LLC | 3134 RICHLAND CHAMBERS (PSS/E Bus Name: RICHLND1_5) | Freestone | NORTH | 2026-05-01 | GAS | GT | 228 |  | 2023-04-12 | 2023-04-19 | 2023-07-13 | 2023-04-11 | 2024-04-23 | No | 2024-05-30 | Yes | 2024-06-12 | 2024-06-12 | 2024-11-27 | 2025-02-12 | 2025-06-27 | 2025-07-29
26INR0110 | Western Flats Solar | SS Completed, FIS Started, No IA | Hecate Energy Point Mountain Solar Facility 1 LLC | Tap 138 kV 76615 Crane -76635 King Mountain; POI is 7.85 miles from Crane. | Crane | WEST | 2028-11-01 | SOL | PV | 410.2 |  | 2023-11-17 | 2023-04-07 | 2023-07-05 | 2023-09-11 |  |  |  | No |  |  | Not Required
26INR0111 | Graphic Packaging Gas | SS Completed, FIS Started, No IA | Graphic Packaging International | Tap 138kV 3446 Peppervine Switch - 3544 Castleman Substation | McLennan | NORTH | 2026-04-07 | GAS | GT | 43.36 |  | 2024-01-05 | 2024-01-11 | 2024-03-19 | 2024-01-05 |  |  |  | No
26INR0112 | Lemma Solar | SS Completed, FIS Started, No IA | Greening USA Corp. | 6088 Benjamin AEP 138kV | Knox | WEST | 2028-07-01 | SOL | PV | 100.61 |  | 2023-05-23 | 2023-04-07 | 2023-07-05 | 2023-05-17 |  |  |  | No |  |  | Not Required
26INR0113 | Meitner Wind | SS Completed, FIS Started, IA | IP Meitner, LLC | 79000 Gray Substation 345kV | Gray | PANHANDLE | 2027-12-20 | WIN | WT | 709 |  | 2023-07-13 | 2023-07-18 | 2023-10-15 | 2023-06-29 |  |  | 2024-04-19 | No |  |  | Not Required
26INR0114 | Ochoa Energy Storage | SS Completed, FIS Completed, No IA | Ochoa Energy Storage LLC | Tap 138kV Katy (44420) - Franz (44260) Ckt 09 | Waller | HOUSTON | 2027-06-03 | OTH | BA | 260.8 |  | 2023-04-18 | 2023-04-19 | 2023-07-14 | 2023-04-11 | 2025-06-24 | No |  | No
26INR0116 | Falcon Zapata Storage 138 | SS Completed, FIS Started, No IA | Falcon BESS, LLC | Tap 138kV 8299 Zapata - 8957 Lopeno | Zapata | SOUTH | 2028-03-11 | OTH | BA | 200.79 |  | 2023-04-28 | 2023-05-15 | 2023-08-11 | 2023-05-08 |  | No |  | No
26INR0117 | Oyster Creek Solar I SLF | SS Completed, FIS Started, No IA | Oyster Creek Solar 1, LLC | Tap 138kV 42110 Angleton - 42050 Clute | Brazoria | COASTAL | 2027-09-30 | SOL | PV | 0 |  | 2023-05-15 | 2023-06-28 | 2023-09-22 | 2023-06-15 |  | No |  | No |  |  | Not Required
26INR0118 | Oyster Creek Storage I SLF | SS Completed, FIS Started, No IA | Oyster Creek Solar 1, LLC | Tap 138kV 42110 Angleton - 42050 Clute | Brazoria | COASTAL | 2027-09-30 | OTH | BA | 0 |  | 2023-06-02 | 2023-06-28 | 2023-09-22 | 2023-06-20 |  | No |  | No
26INR0120 | Bramble Energy Center | SS Completed, FIS Started, No IA | Bramble Energy Center, LLC | 8236 Batesville 138kV | Zavala | SOUTH | 2026-10-03 | OTH | BA | 225.1 |  | 2023-08-23 | 2023-09-08 | 2023-12-04 | 2023-08-15 |  |  |  | No | Not Required | Not Required
26INR0121 | Pioneer Hutt Solar (Alternative POI) | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings LLC | TAP 345kV 11028 Odessa Ehv - 59901 Grelton (West C) | Midland | WEST | 2028-07-01 | SOL | PV | 116 |  | 2023-06-26 | 2023-06-28 | 2023-09-22 | 2023-06-12 |  |  |  | No |  |  | Not Required
26INR0128 | SunWave Solar | SS Completed, FIS Started, No IA | Buckeye Nueces Bay Solar LLC | 8459 Bunsen 138kV | Nueces | COASTAL | 2028-06-30 | SOL | PV | 154.4 |  | 2024-02-09 | 2023-05-26 | 2023-08-22 | 2024-02-01 |  |  |  | No |  |  | Not Required
26INR0130 | Elm Flats Solar SLF | SS Completed, FIS Started, No IA | Orca Falls Solar, LLC | Tap 138kV 3472 BRIAR_CRK_8 – 3467 POWELL1_8 | Navarro | NORTH | 2027-09-30 | SOL | PV | 125.58 |  | 2023-05-12 | 2024-07-30 | 2023-09-01 | 2023-06-13 |  |  |  | No |  |  | Not Required
26INR0131 | Elm Flats Storage SLF | SS Completed, FIS Started, No IA | Orca Falls Solar, LLC | Tap 138kV 3472 BRIAR_CRK_8 – 3467 POWELL1_8 | Navarro | NORTH | 2027-09-30 | OTH | BA | 0 |  | 2023-05-17 | 2023-06-07 | 2023-09-01 | 2023-05-22 |  |  |  | No
26INR0134 | Myers Solar | SS Completed, FIS Started, No IA | BT Myers Solar, LLC | 8629 Baez 69 kV | Bee | SOUTH | 2028-05-22 | SOL | PV | 101.59 |  | 2023-06-13 | 2023-06-28 | 2023-09-20 | 2023-06-01 |  |  |  | No |  |  | Not Required
26INR0135 | Myers Storage | SS Completed, FIS Started, No IA | BT Myers Solar, LLC | 8629 Baez 69 kV | Bee | SOUTH | 2028-05-22 | OTH | BA | 75.96 |  | 2023-06-07 | 2023-06-28 | 2023-09-20 | 2023-06-01 |  |  |  | No
26INR0143 | Santa Garcias Solar | SS Completed, FIS Started, No IA | Oxy Renewable Energy LLC | Tap 138kV 8515 Alazan - 8458 Barney Davis | Kleberg | COASTAL | 2028-05-30 | SOL | PV | 265 |  | 2023-06-06 | 2023-06-28 | 2023-09-22 | 2023-06-07 |  | No |  | No |  |  | Not Required
26INR0144 | Wittig Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Wittig LLC | 138 kV Gulftie (#43340) – San Bernard (#43110) | Wharton | SOUTH | 2027-09-30 | SOL | PV | 106.9 |  | 2024-02-05 | 2024-02-27 | 2024-05-24 | 2024-01-18 |  | No |  | No | Not Required | Not Required | Not Required
26INR0146 | DMF Sagerton Solar SLF | SS Completed, FIS Completed, No IA | Double Mountain Fork LLC | Tap 138kV 6158 Aspermont – 6161 Paint Creek | Haskell | WEST | 2026-12-31 | SOL | PV | 125.5 |  | 2023-07-23 | 2023-07-31 | 2023-10-27 | 2023-07-24 | 2025-09-19 |  |  | No |  |  | Not Required
26INR0147 | Seven Springs Solar | SS Completed, FIS Started, IA | Hancock Springs, LLC | Tap 7061 COPPERAS COVE 7260 Kempner 138kV | Lampasas | NORTH | 2028-05-16 | SOL | PV | 145 | SFS/NtP | 2023-08-18 | 2023-09-22 | 2023-12-14 | 2023-09-05 |  |  | 2025-08-28 | Yes | Not Required | Not Required | Not Required
26INR0148 | DMF Sagerton Storage SLF | SS Completed, FIS Completed, No IA | Double Mountain Fork LLC | Tap 138kV 6158 Aspermont – 6161 Paint Creek | Haskell | WEST | 2026-12-31 | OTH | BA | 0 |  | 2023-07-23 | 2023-07-31 | 2023-10-27 | 2023-07-20 | 2025-09-19 |  |  | No
26INR0150 | Proving Ground Solar | SS Completed, FIS Started, No IA | Lantana Solar LLC | Tap 138 kV Live Oak (6500) - Santiago (6490) | Schleicher | WEST | 2028-06-30 | SOL | PV | 82.1 |  | 2024-01-30 | 2023-07-10 | 2023-10-05 | 2024-01-26 16:36 |  |  |  | No | Not Required | Not Required | Not Required
26INR0155 | Ross Solar | SS Completed, FIS Started, IA | S&S Renewables, LLC | tap 345kV 8249 Angstrom – 8676 Static | Refugio | COASTAL | 2027-07-31 | SOL | PV | 1025.57 |  | 2023-07-17 | 2023-07-31 | 2023-10-27 | 2023-07-18 |  | Yes | 2024-06-27 | No |  |  | Not Required
26INR0156 | Ross Storage | SS Completed, FIS Started, IA | S&S Renewables, LLC | tap the 345 kV Angstrom (#8249) – Static (#8676) line; AEP | Refugio | COASTAL | 2027-07-31 | OTH | BA | 510.99 |  | 2023-07-21 | 2023-08-14 | 2023-11-03 | 2023-07-27 |  | Yes | 2024-06-27 | No
26INR0159 | Proving Ground BESS | SS Completed, FIS Started, No IA | Lantana Solar LLC | Tap 138kV 6500 Live Oak - 6490 Santiago | Schleicher | WEST | 2028-06-30 | OTH | BA | 51.4 |  | 2024-03-06 | 2023-07-10 | 2023-10-05 | 2024-01-26 16:41 |  |  |  | No
26INR0161 | Timberline Solar | SS Completed, FIS Started, No IA | Timberline Renewables, LLC | Tap 345 kV 3119 Nacogdoches SE - 3116 Mt Enterprise | Nacogdoches | NORTH | 2026-09-22 | SOL | PV | 201 |  | 2023-07-24 | 2023-08-14 | 2023-11-10 | 2023-08-02 |  |  |  | No | Not Required | Not Required | Not Required
26INR0162 | Timberline Storage | SS Completed, FIS Started, No IA | Timberline Renewables, LLC | Tap 345 kV 3119 Nacogdoches SE - 3116 Mt Enterprise | Nacogdoches | NORTH | 2026-09-22 | OTH | BA | 100.5 |  | 2023-08-15 | 2023-08-14 | 2023-11-10 | 2023-08-04 |  |  |  | No
26INR0171 | Lazy U Solar 1 | SS Completed, FIS Started, No IA | Lazy U Solar 1 | Tap 345kV 60505 EDITHCLA7B - 60501 TESLA7A ckt2 | Hardeman | WEST | 2029-06-30 | SOL | PV | 252 |  | 2023-08-07 | 2023-08-21 | 2023-11-02 | 2023-08-09 |  | Yes |  | No |  |  | Not Required
26INR0172 | Lazy U Solar 2 | SS Completed, FIS Started, No IA | Lazy U Solar 2 | Tap 345kV 60505 EDITHCLA7B - 60501 TESLA7A CKT2 | Hardeman | WEST | 2029-06-30 | SOL | PV | 252 |  | 2023-08-14 | 2023-08-21 | 2023-11-02 | 2023-08-15 |  | Yes |  | No |  |  | Not Required
26INR0173 | Juniper Ridge BESS 1 | SS Completed, FIS Started, No IA | Lazy U ESS 1 | Tap EDITHCLA7B [60505] -- TESLA7A [60501] 345kV ckt2 | Hardeman | WEST | 2029-06-30 | OTH | BA | 251.5 |  | 2023-08-03 | 2023-09-08 | 2023-12-04 | 2023-08-16 |  | Yes |  | No
26INR0174 | Juniper Ridge BESS 2 | SS Completed, FIS Started, No IA | Lazy U ESS 2 | Tap EDITHCLA7B [60505] -- TESLA7A [60501] ckt2 | Hardeman | WEST | 2029-06-30 | OTH | BA | 251.5 |  | 2023-08-16 | 2023-08-21 | 2023-11-02 | 2023-08-16 |  | Yes |  | No
26INR0176 | Dionysus Solar | SS Completed, FIS Started, No IA | Dionysus Solar, LLC | Tap 138kV 6733 Mustang Prairie - 6732 Latexo | Houston | NORTH | 2027-03-11 | SOL | PV | 153.26 |  | 2023-06-14 | 2023-06-28 | 2023-09-22 | 2023-06-05 |  |  |  | No |  |  | Not Required
26INR0177 | Dionysus Storage | SS Completed, FIS Started, No IA | Dionysus Solar, LLC | Tap 138kV 6733 Mustang Prairie - 6732 Latexo | Houston | NORTH | 2027-03-11 | OTH | BA | 77.28 |  | 2023-06-14 | 2023-06-28 | 2023-09-22 | 2023-06-05 |  |  |  | No
26INR0179 | SunShiner ESS | SS Completed, FIS Started, No IA | SunShiner ESS LLC | 8672 LaPryor2A 138 kV | Zavala | SOUTH | 2027-07-01 | OTH | BA | 200 |  | 2023-09-20 | 2023-09-25 | 2023-12-21 | 2023-09-20 |  | No |  | No
26INR0180 | Cape Rich BESS | SS Completed, FIS Completed, IA | Cape Rich BESS | 3387 Revolution Switch 138kV | Navarro | NORTH | 2027-09-23 | OTH | BA | 150.52 |  | 2023-07-03 | 2023-07-10 | 2023-10-06 | 2023-07-03 | 2024-06-26 | No | 2025-02-03 | No | Not Required | Not Required
26INR0181 | Solar Star Frontier BESS | SS Completed, FIS Started, No IA | Solar Star Frontier BESS, LLC | 8656 Luna 138kV | Cameron | COASTAL | 2029-02-27 | OTH | BA | 100.26 | COD | 2023-12-23 | 2023-06-28 | 2023-09-22 | 2023-12-18 |  | No |  | No | Not Required | Not Required
26INR0183 | TRIFECTA Gas | SS Completed, FIS Completed, No IA | NET Power | Tap 345 kV 1185 Midland County Northwest Switch (bus #1185) – Midland East (bus #1021) 345 kV Line Ckt 01 | Midland | WEST | 2030-02-11 | GAS | GT | 453 |  | 2024-03-15 | 2023-06-28 | 2023-09-20 | 2024-03-14 | 2025-03-24 |  |  | No
26INR0184 | Arc Energy Storage | SS Completed, FIS Completed, No IA | Paris Energy Storage, LLC | Tap 138kV 1693 Paris Switch - 11806 ENLOE T8 | Lamar | NORTH | 2027-09-21 | OTH | BA | 204.5 |  | 2023-06-19 | 2023-07-31 | 2023-10-27 | 2023-07-25 | 2025-05-02 |  |  | No
26INR0185 | Beitel Energy Storage | SS Completed, FIS Started, No IA | Brazos Energy Storage, LLC | 579 Jack County 138kV | Jack | NORTH | 2027-12-31 | OTH | BA | 200.6 |  | 2023-06-26 | 2023-08-14 | 2023-11-10 | 2023-08-02 |  |  |  | No | Not Required | Not Required
26INR0188 | Western Flats Storage | SS Completed, FIS Started, No IA | Hecate Energy Point Mountain Solar Facility 1 LLC | Tap 138 kV 76615 Crane -76635 King Mountain | Crane | WEST | 2028-11-01 | OTH | BA | 410.7 |  | 2025-01-17 | 2024-04-09 | 2024-07-05 | 2025-01-07 |  |  |  | No
26INR0189 | Skipjack Energy Storage | SS Completed, FIS Started, IA | Skipper Energy Storage LLC | Tap 138 42980 Nash - 44010 W A Parish ckt #2 | Brazoria | COASTAL | 2028-02-28 | OTH | BA | 150.6 |  | 2023-07-17 | 2023-07-31 | 2023-10-27 | 2023-07-29 |  |  | 2024-08-13 | Yes |  |  |  | 2025-02-24
26INR0194 | Motif BESS II | SS Completed, FIS Started, No IA | Motif Storage, LLC | 7440 Tarpley 138kV | Bandera | SOUTH | 2029-02-19 | OTH | BA | 201.13 |  | 2024-11-04 | 2024-11-19 | 2025-02-18 | 2024-10-29 |  |  |  | No
26INR0195 | Realitos Storage SLF | SS Completed, FIS Started, No IA | Mesquite Creek LLC | Bruni (#8297) – Crestonio (#8695) 138 kV line; AEP | Duval | SOUTH | 2026-12-31 | OTH | BA | 0 |  | 2023-07-31 | 2023-09-07 | 2023-12-05 | 2023-08-02 |  | No |  | No | Not Required | Not Required
26INR0196 | Realitos Solar SLF | SS Completed, FIS Started, No IA | Mesquite Creek LLC | Bruni (#8297) – Crestonio (#8695) 138 kV line; AEP | Duval | SOUTH | 2026-12-31 | SOL | PV | 150.49 |  | 2023-08-22 | 2023-09-07 | 2023-12-05 | 2023-07-20 |  | No |  | No | Not Required | Not Required | Not Required
26INR0200 | Vaughn Energy Storage | SS Completed, FIS Started, No IA | Vaughn Battery Storage, LLC | 13 Keith 138kV | Grimes | NORTH | 2027-12-31 | OTH | BA | 200.6 |  | 2023-08-21 | 2023-08-21 | 2023-11-17 | 2023-08-20 |  |  |  | No
26INR0201 | Rock Rose Energy BESS | SS Completed, FIS Completed, IA | Rock Rose Energy Storage LLC | 44070 Whaley 345 kV | Fort Bend | HOUSTON | 2026-12-15 | OTH | BA | 211.5 |  | 2023-03-21 | 2023-09-22 | 2023-12-14 | 2023-09-08 | 2024-05-07 |  | 2024-06-15 | Yes | Not Required | Not Required
26INR0211 | Titus Low Carbon Ventures Solar 1 | SS Completed, FIS Started, No IA | Vaquero Solar, LLC | Tap 345kV 8249 Angstrom - 8624 Grissom | San Patricio | COASTAL | 2028-10-16 | SOL | PV | 338.04 |  | 2023-08-21 | 2023-10-13 | 2024-01-10 | 2023-09-21 |  | Yes |  | No |  |  | Not Required
26INR0215 | JackGard BESS | SS Completed, FIS Completed, No IA | Jackgard BESS | 1429 Jacksboro 345kV | Jack | NORTH | 2028-04-17 | OTH | BA | 200.59 | COD | 2023-08-12 | 2023-08-14 | 2023-11-02 | 2023-07-31 | 2024-11-15 | No |  | No
26INR0218 | Fort Chadbourne Cattle BESS | SS Completed, FIS Started, No IA | Fort Chadbourne BESS | AEP Fort Chadbourne 138 kv substation (#6324) | Coke | WEST | 2027-06-29 | OTH | BA | 50.23 |  | 2023-08-14 | 2023-08-21 | 2023-11-06 | 2023-07-31 |  |  |  | No
26INR0219 | Mountain Springs BESS | SS Completed, FIS Completed, No IA | Mountain Springs BESS | 704 Mountain Springs 138 kV | Cooke | NORTH | 2027-04-01 | OTH | BA | 150.52 |  | 2023-09-25 | 2023-10-04 | 2023-12-30 | 2023-09-21 | 2025-06-05 | No |  | No
26INR0222 | GOTHAM BESS | SS Completed, FIS Started, No IA | AEU BATTERY PROJECT IV LLC | 5640 DRISCOLLSUB9 69kV | Nueces | COASTAL | 2027-03-17 | OTH | BA | 151.2 |  | 2024-07-01 | 2023-07-31 | 2023-10-27 | 2024-06-17 09:02 |  |  |  | No
26INR0226 | First Capitol BESS | SS Completed, FIS Started, IA | First Capitol BESS, LLC | Tap 138kV West Columbia Main (39500) - Sweeny Cogen (110505) | Brazoria | COASTAL | 2027-05-01 | OTH | BA | 257.48 |  | 2023-09-25 | 2023-10-04 | 2023-12-14 | 2023-09-22 |  | No | 2025-05-15 | Yes | Not Required | Not Required |  | 2025-02-12
26INR0228 | Santa Monica Solar | SS Completed, FIS Started, No IA | Karol Solar IV | Tap 345 KV 68091 NAVARRO - 3381 BIGBRNW_5 Ckt 2 | Navarro | NORTH | 2028-09-20 | SOL | PV | 105.85 |  | 2024-10-03 | 2023-09-07 | 2023-12-04 | 2024-09-24 |  |  |  | No |  |  | Not Required
26INR0229 | Pamplona Solar | SS Completed, FIS Completed, No IA | Karol Solar III | Tap 138 kV 44740 WALLIS_S65_8 - 44700 GEBHRT_X65B8 Ckt#65 | Austin | SOUTH | 2028-10-17 | SOL | PV | 42.38 |  | 2024-10-08 | 2023-08-14 | 2023-11-03 | 2024-06-18 | 2025-07-25 |  |  | No |  |  | Not Required
26INR0230 | Titus Sienta Solar | SS Completed, FIS Started, No IA | Sol Sienta Solar, LLC | Tap 138kV 1239 Coyanosa - 11238 Blair Lake Sub | Pecos | WEST | 2028-06-01 | SOL | PV | 501.93 |  | 2023-08-21 | 2023-10-13 | 2024-01-09 | 2023-10-09 |  |  |  | No |  |  | Not Required |  |  |  | 2025-10-01 | 2026-04-01
26INR0231 | Energy City BESS | SS Completed, FIS Completed, No IA | Energy City BESS LLC | Tap 138kV 1179 Texaco Mabee Tap - 1200 Mariensfield | Midland | WEST | 2027-06-30 | OTH | BA | 204.9 |  | 2023-09-13 | 2023-10-04 | 2023-12-30 | 2023-09-25 | 2025-03-20 |  |  | No
26INR0235 | Noor Solar | SS Completed, FIS Completed, No IA | Industrial Kilo Project LLC | Tap 138kV 40390 Crosby - 40680 Placid Ckt 86 | Liberty | HOUSTON | 2028-03-01 | SOL | PV | 188.2 |  | 2023-10-04 | 2023-10-13 | 2024-01-09 | 2023-10-04 | 2024-05-20 | Yes |  | No |  |  | Not Required
26INR0238 | Clapton Solar | SS Completed, FIS Started, No IA | Clapton Solar | Tap 345 kV 3424 Buckhorn Switch - 1444 Brown Switch | Mills | NORTH | 2028-03-08 | SOL | PV | 200.99 |  | 2024-02-05 | 2024-03-22 | 2024-06-19 | 2024-02-13 |  |  |  | No |  |  | Not Required
26INR0241 | Sol Marina Energy Center | SS Completed, FIS Completed, IA | Adapture Solar Development, LLC | Tap 345kV 2427 Watermill - 2466 Big Onion | Ellis | NORTH | 2027-10-29 | SOL | PV | 175.3 |  | 2023-10-17 | 2023-10-25 | 2024-01-22 | 2023-09-07 | 2025-03-03 | No | 2025-04-25 | Yes | Not Required | Not Required | Not Required | 2025-07-29
26INR0242 | Sol Marina Energy Center BESS | SS Completed, FIS Completed, IA | Adapture Solar Development, LLC | Tap 345kV 2427 Watermill - 2466 Big Onion | Ellis | NORTH | 2027-10-29 | OTH | BA | 57.15 |  | 2023-10-17 | 2023-10-25 | 2024-01-22 | 2023-09-07 | 2025-03-03 |  | 2025-04-25 | Yes | Not Required | Not Required |  | 2025-07-29
26INR0243 | Caladium BESS | SS Completed, FIS Started, No IA | Caladium Storage, LLC | 57664 Sunnyside 69kV | Waller | HOUSTON | 2027-11-30 | OTH | BA | 201.28 |  | 2024-09-09 | 2024-11-19 | 2025-02-18 | 2024-10-29 |  |  |  | No
26INR0245 | Cairos Storage | SS Completed, FIS Started, No IA | Cairos Solar, LLC | 7425 ODLAW SWITCH 138kV | Kinney | SOUTH | 2026-12-31 | OTH | BA | 77.28 |  | 2023-10-03 | 2023-10-25 | 2023-12-30 | 2023-10-03 |  |  |  | No
26INR0246 | Cairos Solar | SS Completed, FIS Started, No IA | Cairos Solar, LLC | ODLAW SWITCH (#7425) | Kinney | SOUTH | 2026-12-31 | SOL | PV | 153.26 |  | 2023-09-26 | 2023-10-04 | 2023-12-30 | 2023-09-22 |  |  |  | No |  |  | Not Required
26INR0247 | Jane Storage Energy Center | SS Completed, FIS Started, No IA | NMRE Holdings, LLC | 59901 Grelton 345 kV | Martin | WEST | 2027-03-01 | OTH | BA | 240.6 |  | 2023-08-13 | 2023-09-08 | 2023-12-01 | 2023-08-28 |  |  |  | Yes | Not Required | Not Required
26INR0248 | Sengun BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 12, LLC | WEST_OSO4A (8484) 138 KV | Nueces | COASTAL | 2028-03-17 | OTH | BA | 200.89 |  | 2023-12-20 | 2024-01-03 | 2024-03-29 | 2023-12-18 |  | No |  | No | Not Required | Not Required
26INR0250 | Duffy BESS | SS Completed, FIS Completed, IA | Duffy Energy Storage LLC | Tap 345kV WAP to STP CKT39 (PTI# 5915-44000 CKT 39) | Matagorda | COASTAL | 2026-12-31 | OTH | BA | 235.9 | COD | 2023-08-14 | 2023-08-21 | 2023-11-17 | 2023-08-08 | 2025-05-03 | No | 2025-07-28 | No |  |  |  | 2025-08-04
26INR0252 | Neutron Storage | SS Completed, FIS Started, No IA | Elawan Neutron Storage, LLC | Tap 345kV 13405 Trading House - 68090 Sam Switch | McLennan | NORTH | 2027-08-18 | OTH | BA | 104.5 |  | 2023-08-21 | 2023-09-08 | 2023-12-01 | 2023-08-21 |  |  |  | No | Not Required | Not Required
26INR0253 | Goldfinch Solar | SS Completed, FIS Started, No IA | BT DJ4M Solar, LLC | Tap Connection Bus 2485 Poetry Switch – 3223 Shamburger Switch | Van Zandt | NORTH | 2028-03-18 | SOL | PV | 150.77 | MW Size | 2023-09-15 | 2023-09-22 | 2023-12-14 | 2023-09-15 |  |  |  | No | Not Required | Not Required | Not Required
26INR0254 | Goldfinch Storage | SS Completed, FIS Started, No IA | BT DJ4M Solar, LLC | Tap Connection Bus 2485 Poetry Switch – 3223 Shamburger Switch | Van Zandt | NORTH | 2028-03-18 | OTH | BA | 100.44 |  | 2023-09-26 | 2023-10-04 | 2023-12-14 | 2023-09-20 |  |  |  | No | Not Required | Not Required
26INR0255 | Operation Sunshine | SS Completed, FIS Started, IA | Duck Creek Solar, LLC | 7077 Amos Creek 345kV | Concho | WEST | 2028-03-12 | SOL | PV | 603.2 | SFS/NtP | 2023-09-29 | 2023-11-14 | 2024-02-09 | 2023-09-27 |  |  | 2025-08-27 | Yes |  |  | Not Required | 2025-09-11
26INR0256 | Camino Ranch Solar 2 SLF | SS Completed, FIS Started, No IA | Camino Ranch Solar Project LLC | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | Houston | NORTH | 2027-10-30 | SOL | PV | 237.21 |  | 2023-09-05 | 2024-02-27 | 2024-05-24 | 2024-01-10 |  |  |  | No |  |  | Not Required
26INR0257 | Camino Ranch Storage 2 SLF | SS Completed, FIS Started, No IA | Camino Ranch Solar LLC | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | Houston | NORTH | 2027-10-30 | OTH | BA | 238.45 |  | 2023-08-23 | 2024-02-02 | 2024-04-29 | 2023-10-12 |  |  |  | No
26INR0258 | Running Iron Solar | SS Completed, FIS Started, No IA | Running Iron Solar, LLC | Tap 138kV Conoco 8138 - Black Cat 80124 | Matagorda | COASTAL | 2028-10-16 | SOL | PV | 204.74 |  | 2023-10-04 | 2023-10-25 | 2024-01-22 | 2023-10-19 |  | No |  | No |  |  | Not Required
26INR0259 | Cottontail Energy Center | SS Completed, FIS Started, No IA | Cottontail Energy Center, LLC | 7258 Glidden Substation 138kV | Colorado | SOUTH | 2027-10-19 | OTH | BA | 200.85 |  | 2023-10-05 | 2023-10-25 | 2024-01-22 | 2023-10-17 |  |  |  | No
26INR0260 | Evans Creek Energy Storage | SS Completed, FIS Started, No IA | Evans Creek Energy Storage LLC | Comstock 138kV Substation (PSSE Bus #8683) | Val Verde | WEST | 2028-04-01 | OTH | BA | 102.96 |  | 2023-09-13 | 2023-10-25 | 2024-01-22 | 2023-10-19 |  |  |  | No
26INR0261 | Bastrop Peaking Generators (TEF-Due Diligence) | SS Completed, FIS Started, No IA | MPH Bastrop Peakers, LLC | 7048 L_GARFIE5_1Y 345kV | Bastrop | SOUTH | 2026-05-31 | GAS | GT | 1104 |  | 2024-04-09 | 2024-02-02 | 2024-05-01 | 2024-03-15 |  |  |  | No
26INR0269 | Moccasin Solar | SS Completed, FIS Started, IA | Swenson Solar LLC | Tapping the 345 kV Line from Kirchhoff (Bus# 60707) to Clear Crossing (Bus# 60515) | Stonewall | WEST | 2027-07-06 | SOL | PV | 603.59 |  | 2023-08-30 | 2023-09-07 | 2023-12-06 | 2023-09-01 |  | Yes | 2024-09-04 | Yes | Not Required | Not Required | Not Required | 2025-02-12
26INR0272 | Momentum Stout BESS | SS Completed, FIS Started, No IA | Momentum STOUT, LLC | 70111 Flat Rock 138kV | Burnet | SOUTH | 2027-10-01 | OTH | BA | 125.5 |  | 2024-08-13 | 2023-11-14 | 2024-02-09 | 2024-08-08 14:43 |  |  |  | No
26INR0273 | Momentum Hazy Jane BESS | SS Completed, FIS Started, No IA | MOMENTUM HAZY JANE, LLC | Tap 138kV 1102 Judkins - 1110 Edward | Ector | WEST | 2028-02-26 | OTH | BA | 125.5 | COD | 2024-08-21 | 2023-11-14 | 2024-02-09 | 2024-08-08 |  |  |  | No
26INR0277 | Salt-Lick Solar | SS Completed, FIS Started, No IA | Salt-Lick Solar, LLC | Elcor_8 bus # 11198 | Culberson | WEST | 2028-06-01 | SOL | PV | 453 |  | 2023-10-04 | 2023-10-13 | 2024-01-10 | 2023-10-02 |  |  |  | No |  |  | Not Required |  |  |  | 2025-10-01 | 2027-04-01
26INR0279 | Firebird Solar | SS Completed, FIS Started, No IA | TX Firebird SB 6, LLC | 138 kV 1099 SOUTHWESTERN PORTLAND TAP - 11281 OLSIN SWITCH | Ector | WEST | 2028-09-30 | SOL | PV | 100.42 |  | 2023-10-31 | 2023-11-14 | 2024-02-09 | 2023-10-31 |  |  |  | No |  |  | Not Required
26INR0280 | Pethrus BESS | SS Completed, FIS Completed, No IA | Pethrus BESS, LLC | Tap Wichita Falls Switch (#1464) – North Star (#1467) 138 kV Line | Wichita | WEST | 2028-02-01 | OTH | BA | 174.08 |  | 2023-09-15 | 2023-09-23 | 2023-12-20 | 2023-08-30 | 2025-03-18 | No |  | No | Not Required | Not Required
26INR0283 | Bonaparte BESS | SS Completed, FIS Started, No IA | Bonaparte BESS, LLC | 7568 Lincoln 138 kV | Lee | SOUTH | 2027-12-29 | OTH | BA | 153.67 |  | 2023-11-07 | 2023-11-14 | 2024-02-09 | 2023-09-06 |  |  |  | No
26INR0285 | Hill Valley BESS | SS Completed, FIS Completed, No IA | Hill Valley BESS, LLC | 345 kV Singleton (#44645) | Grimes | NORTH | 2028-07-15 | OTH | BA | 245.8 |  | 2023-11-09 | 2023-12-04 | 2024-03-01 | 2023-11-10 | 2024-12-03 |  |  | No
26INR0287 | Firebird BESS | SS Completed, FIS Started, No IA | TX BESS 6, LLC | Tap 138kV #1099 Southwestern Portland Tap - #1052 Rexall | Ector | WEST | 2028-08-28 | OTH | BA | 102.65 |  | 2023-10-31 | 2023-11-14 | 2024-02-09 | 2023-10-31 |  |  |  | No | Not Required | Not Required
26INR0290 | Cold Creek Solar 2 | SS Completed, FIS Started, IA | Cold Creek Solar LLC | Tap 345kV line Big Hill (#76003) - Twin Buttes (#76009) | Schleicher | WEST | 2028-05-28 | SOL | PV | 445.41 | COD | 2023-11-07 | 2023-12-18 | 2024-03-01 | 2023-11-07 |  |  | 2025-04-23 | No |  |  | Not Required
26INR0291 | Cold Creek Storage 2 | SS Completed, FIS Started, IA | Cold Creek Solar LLC | Tap 345kV line Big Hill (#76003) - Twin Buttes (#76009) | Schleicher | WEST | 2026-12-31 | OTH | BA | 174.24 |  | 2023-11-02 | 2023-12-04 | 2024-03-01 | 2023-11-02 |  |  | 2025-04-23 | No | Not Required | Not Required
26INR0294 | Longleaf Power Station | SS Completed, FIS Completed, No IA | WattBridge Texas Holding, LLC | Redland Substation (# 3321) | Angelina | NORTH | 2028-06-01 | GAS | GT | 600 |  | 2023-10-04 | 2023-10-13 | 2024-01-09 | 2023-10-04 | 2024-10-22 | No |  | No | Not Required | Not Required
26INR0295 | Trinity Hills BESS SLF | SS Completed, FIS Started, No IA | Phoenix Battery Storage, LLC | To the 345 kV Garvey Road Switch (#17002) | Archer | WEST | 2027-04-12 | OTH | BA | 94 |  | 2023-11-13 | 2023-11-30 | 2024-02-26 | 2023-11-03 |  |  |  | No
26INR0296 | Sherbino II BESS SLF | SS Completed, FIS Completed, IA | Phoenix Battery Storage, LLC | 38430 TNMP White baker Switching Station 138kV | Pecos | WEST | 2026-02-08 | OTH | BA | 77.37 |  | 2023-11-19 | 2023-11-30 | 2024-02-27 | 2023-11-16 | 2025-04-23 |  | 2024-08-01 | Yes |  |  |  | 2025-02-12 | 2025-05-14 | 2025-05-01
26INR0297 | Buzzi Maryneal Wind Project | SS Completed, FIS Started, No IA | Buzzi Unicem USA | 1413 SWEETCRK-9 | Nolan | WEST | 2026-01-02 | WIN | WT | 18 |  | 2023-10-02 | 2023-10-25 | 2024-01-22 | 2023-10-16 |  |  |  | No | Not Required | Not Required | Not Required
26INR0300 | Whitewright Solar 2 | SS Completed, FIS Started, No IA | SunWR, LLC | Tap 345kV 1729 Valley South – Anna Switch 2373 | Grayson | NORTH | 2028-05-02 | SOL | PV | 301.69 |  | 2023-11-07 | 2023-12-18 | 2024-03-15 | 2023-11-07 |  |  |  | No |  |  | Not Required
26INR0301 | Bhalu Storage | SS Completed, FIS Started, No IA | Bhalu Storage, LLC | Tap 138kV Bulldog (#23833) – Elbow (#23834) | Howard | WEST | 2028-04-21 | OTH | BA | 205.5 | COD | 2023-10-23 | 2023-10-30 | 2024-01-26 | 2023-10-23 |  |  |  | No | Not Required | Not Required
26INR0302 | Carolina Storage Young County | SS Completed, FIS Started, No IA | CSE Storage, LLC | TAP 138 KV BUS AND CREAT NEW BUS BETWEEN MURRAY (792) AND GRAHAM SES (1431) COUNTY : YOUNG | Young | WEST | 2028-08-01 | OTH | BA | 104.5 |  | 2024-01-02 | 2024-02-27 | 2024-05-20 | 2024-02-12 |  |  |  | No | Not Required | Not Required
26INR0304 | JUNIPERUSSS | SS Completed, FIS Started, No IA | BLUE STONE RENEWABLE XXI LLC | TAP CASHSW_T5 (2464) -SULSP_SS1_5 (1697) | Hopkins | NORTH | 2029-07-09 | SOL | PV | 80.33 |  | 2024-01-05 | 2024-01-11 | 2024-04-08 | 2024-01-04 |  |  |  | No | Not Required | Not Required | Not Required
26INR0306 | Nautilus Heavy Storage | SS Completed, FIS Started, No IA | Nautilus Heavy Storage, LLC | 8422 Dupont 138kV | San Patricio | COASTAL | 2028-06-10 | OTH | BA | 256.24 |  | 2023-12-11 | 2023-12-20 | 2024-03-15 | 2023-12-01 |  |  |  | No
26INR0309 | Solace Storage | SS Completed, FIS Completed, IA | IP Quantum BESS, LLC | tap 345kV 1430 Graham - 1048 Tonkawas | Haskell | WEST | 2026-03-31 | OTH | BA | 321.79 |  | 2024-02-27 | 2024-03-22 | 2024-06-19 | 2024-02-22 | 2025-06-09 | No | 2025-03-21 | Yes | Not Required | Not Required |  | 2025-07-24 | 2025-07-24 | 2025-07-24
26INR0310 | Quantum Storage | SS Completed, FIS Completed, IA | IP Quantum II BESS, LLC | 60089 Kilby Switching Station 345kV | Haskell | WEST | 2026-06-30 | OTH | BA | 321.75 |  | 2024-02-28 | 2024-03-22 | 2024-06-19 | 2024-02-22 | 2025-06-16 | No | 2023-10-26 | Yes | Not Required | Not Required |  | 2025-08-04 | 2025-08-04 | 2025-08-04
26INR0311 | Senator Aggreko Solar | SS Completed, FIS Started, No IA | Senator Aggreko Solar LLC | 138 kV Sunglow Substation (#78016) | Maverick | SOUTH | 2026-10-31 | SOL | PV | 251 |  | 2024-01-30 | 2024-02-02 | 2024-04-29 | 2023-10-18 |  |  |  | No |  |  | Not Required
26INR0312 | Senator Aggreko Storage | SS Completed, FIS Started, No IA | Senator Aggreko Storage LLC | 138 kV Sunglow Substation (#78016) | Maverick | SOUTH | 2026-10-31 | OTH | BA | 153.1 |  | 2023-11-09 | 2023-11-14 | 2024-01-08 | 2023-10-25 |  |  |  | No
26INR0313 | Edens Solar | SS Completed, FIS Started, No IA | Hill PV, LLC | Tap 69kV 3532 Itasca - 3523 Hillsboro | Hill | NORTH | 2027-08-15 | SOL | PV | 70.37 |  | 2023-10-18 | 2023-10-25 | 2024-01-22 | 2023-10-20 |  |  |  | No |  |  | Not Required
26INR0314 | Brazos River BESS | SS Completed, FIS Completed, IA | Brazos River BESS LLC | Tap 138kV 39530 West Colombia LOCAL TNP - 39560 ANGLETON TNP | Brazoria | COASTAL | 2027-10-30 | OTH | BA | 180.36 |  | 2024-05-31 | 2023-10-04 | 2024-01-01 | 2024-05-24 | 2024-11-04 |  | 2025-05-24 | No | Not Required | Not Required
26INR0317 | Pinnacle Point Energy Storage | SS Completed, FIS Started, No IA | GCI Pinnacle Point, LLC | Tap Highlands (Bus # 40812) - HANEY ( BUS # 40790) 138 kV | Harris | HOUSTON | 2027-06-01 | OTH | BA | 101.3 |  | 2023-11-07 | 2023-11-14 | 2024-01-08 | 2023-11-08 |  | Yes |  | No | Not Required | Not Required
26INR0318 | Sandford Solar | SS Completed, FIS Started, No IA | BT Sandford Solar, LLC | Tap 345kV Bird Dog (Bus #11736) - Jacksboro (Bus #1429) | Wise | NORTH | 2028-08-15 | SOL | PV | 126.18 |  | 2023-12-20 | 2024-01-03 | 2024-03-29 | 2023-12-12 |  |  |  | No | Not Required | Not Required | Not Required
26INR0319 | Sandford Storage | SS Completed, FIS Started, No IA | BT Sandford Solar, LLC | Tap 345kV Bird Dog (Bus #11736) - Jacksboro (Bus #1429) | Wise | NORTH | 2028-08-15 | OTH | BA | 100.93 |  | 2023-12-18 | 2024-01-03 | 2024-03-29 | 2023-12-12 |  |  |  | No | Not Required | Not Required
26INR0321 | Windmill Ridge Storage | SS Completed, FIS Completed, No IA | BT WMR Storage, LLC | Angleton (Bus #42110) - West Columbia Local (Bus #43381) 138 kV Substation | Brazoria | COASTAL | 2026-12-31 | OTH | BA | 151.4 |  | 2023-11-07 | 2023-11-14 | 2024-01-08 | 2023-11-03 | 2024-07-29 |  |  | No
26INR0324 | Misty Hollow BESS | SS Completed, FIS Completed, No IA | Clear Fork BESS, LLC | 345 kV Singleton (#44645) | Grimes | NORTH | 2028-07-15 | OTH | BA | 245.8 |  | 2023-12-06 | 2023-12-20 | 2024-03-15 | 2023-12-06 | 2025-03-04 |  |  | No | Not Required | Not Required
26INR0326 | Leaning Tree BESS | SS Completed, FIS Started, No IA | RamZ BESS, LLC | To Tap 345 kV Thomas Price Switch (Bus# 11523) to Clear Crossing (Bus# 60515) Line | Throckmorton | WEST | 2027-02-13 | OTH | BA | 256.1 |  | 2023-11-20 | 2023-11-30 | 2024-02-27 | 2023-11-15 |  |  |  | No | Not Required | Not Required
26INR0327 | Sleepy Hollow BESS | SS Completed, FIS Completed, No IA | Sleepy Hollow BESS, LLC | Tap 138 kV 792 Murray - 6169 Paint Creek | Throckmorton | WEST | 2028-02-22 | OTH | BA | 123.1 |  | 2023-11-30 | 2023-11-30 | 2024-02-27 | 2023-11-15 | 2025-07-21 |  |  | No | Not Required | Not Required
26INR0328 | Yorktown BESS | SS Completed, FIS Started, No IA | Navitas Energy LLC | (#78575) LCRA Yorktown 138 kV | DeWitt | SOUTH | 2026-12-16 | OTH | BA | 150.49 |  | 2023-10-18 | 2023-10-25 | 2024-01-22 | 2023-10-10 |  |  |  | No
26INR0329 | Pianissimo BESS II | SS Completed, FIS Started, No IA | Pianissimo Storage, LLC | Tap 138kV 685 LEO - 587 GREENWOOD | Wise | NORTH | 2027-12-31 | OTH | BA | 202 |  | 2024-10-07 | 2024-11-19 | 2025-02-18 | 2024-10-29 |  |  |  | No
26INR0330 | Alamo City BESS | SS Completed, FIS Completed, IA | ALAMO CITY ESS LLC | Tap 138kV 5294 Martinez - 5110 JT Deely | Bexar | SOUTH | 2027-09-21 | OTH | BA | 128.3 |  | 2024-02-21 | 2024-02-27 | 2024-05-24 | 2024-02-13 | 2025-07-24 | No | 2025-05-22 | No
26INR0331 | RUSH ESS | SS Completed, FIS Started, No IA | OCI Solar Power LLC | Tap 345 kV 5231 HOWARD_5 – 5400 SPRUCE | Bexar | SOUTH | 2027-07-01 | OTH | BA | 201.27 |  | 2024-02-20 | 2023-11-30 | 2024-01-16 | 2024-02-12 |  |  |  | No
26INR0333 | VERTUS ENERGY STORAGE | SS Completed, FIS Completed, IA | VERTUS ENERGY STORAGE LLC | Bus Name: TnMainland1, Bus Number: 38830, | Galveston | HOUSTON | 2026-02-01 | OTH | BA | 207.3 |  | 2023-10-10 | 2023-10-13 | 2024-01-10 | 2023-10-10 | 2024-09-09 |  | 2025-01-08 | Yes |  |  |  | 2025-02-14 | 2025-04-16 | 2025-07-16
26INR0334 | TOCE TX BESS 2 | SS Completed, FIS Completed, No IA | TOCE TX BESS 2, LLC | Tap 44200 Hillje - 44000 WA Parrish 345 kV | Wharton | SOUTH | 2027-08-01 | OTH | BA | 523.38 |  | 2024-01-22 | 2024-02-02 | 2024-04-29 | 2024-01-23 | 2025-06-05 |  |  | No | Not Required | Not Required
26INR0340 | SOUTHERN SELECT ENERGY STORAGE | SS Completed, FIS Completed, IA | SOUTHERN SELECT ENERGY STORAGE LLC | Bus Name: TNHEIGHTS_1 Bus Number: 38740 | Galveston | HOUSTON | 2027-03-31 | OTH | BA | 404.3 | COD | 2023-10-16 | 2023-10-25 | 2024-01-22 | 2023-10-12 | 2024-10-22 |  | 2025-05-09 | No | Not Required | Not Required
26INR0341 | Megamouth Energy Storage | SS Completed, FIS Completed, No IA | GCI Megamouth, LLC | 42750 Mykawa 138 kV | Harris | HOUSTON | 2026-09-01 | OTH | BA | 101.3 |  | 2024-03-11 | 2024-03-22 | 2024-06-19 | 2024-03-11 | 2024-09-17 |  |  | No
26INR0343 | Stinger Energy Storage | SS Completed, FIS Started, No IA | Stinger Energy Storage LLC | Tap Atascocita 138kV Substation (Bus # 40130) - Lake Houston (Bus #40820) | Harris | HOUSTON | 2028-03-01 | OTH | BA | 200.8 |  | 2023-11-02 | 2023-11-14 | 2024-01-08 | 2023-11-02 |  |  |  | No
26INR0345 | NET Power Demonstration plant | SS Completed, FIS Completed, No IA | NET Power LLC | 42360 Mirage POI 8 138kV | Harris | HOUSTON | 2027-07-05 | GAS | GT | 25.5 |  | 2024-09-03 | 2023-12-20 | 2024-03-08 | 2024-09-03 | 2025-07-10 |  |  | No
26INR0347 | Midfield PV Project SLF | SS Completed, FIS Started, No IA | HQC Solar Holdings 1, LLC | Tap 138kV 8121 Blessing - 8125 Lolita | Matagorda | COASTAL | 2028-07-01 | SOL | PV | 150 |  | 2023-11-13 | 2023-12-04 | 2024-02-27 | 2023-11-28 |  |  |  | No |  |  | Not Required
26INR0349 | ARTIO ENERGY STORAGE | SS Completed, FIS Completed, No IA | Artio Energy Storage LLC | Farmersville 345kV Substation (PSSE BUS # 1685) | Collin | NORTH | 2028-10-01 | OTH | BA | 205.94 |  | 2023-10-30 | 2023-11-14 | 2024-02-08 | 2023-10-30 | 2025-03-05 |  |  | No | Not Required | Not Required
26INR0350 | Jack County III – 138 kV | SS Completed, FIS Started, No IA | Jack County Power Development, LLC | 579 JACK COUNTY 138kV | Jack | NORTH | 2026-05-01 | GAS | GT | 660 |  | 2023-12-23 | 2023-11-14 | 2024-02-08 | 2023-12-19 14:52 |  |  |  | No
26INR0351 | Jack County III – 345 kV | SS Completed, FIS Started, No IA | Jack County Power Development, LLC | Substation Name: JACK COUNTY 2 PLANT STATION CODE: JCKCNTY2 BUS NUMBER: 575 | Jack | NORTH | 2027-07-01 | GAS | GT | 660 |  | 2024-01-03 | 2023-11-14 | 2024-02-08 | 2023-12-19 |  |  |  | No
26INR0355 | Pleiades Storage | SS Completed, FIS Completed, No IA | Pleiades Storage, LLC | Tap 138kV Einstein 23852 - 10043 St. Lawrence | Glasscock | WEST | 2027-09-29 | OTH | BA | 205.5 |  | 2024-03-06 | 2024-03-22 | 2024-06-19 | 2024-02-23 | 2025-01-17 | No |  | No
26INR0356 | Saluga Ranch Storage | SS Completed, FIS Started, No IA | Saluga Ranch Energy, LLC | Asherton 8283 - Big wells 8613 -138 kV | Dimmit | SOUTH | 2027-08-25 | OTH | BA | 125.4 |  | 2024-01-08 | 2024-02-02 | 2024-04-29 | 2024-01-08 |  |  |  | No
26INR0357 | Operation Sunshine Storage | SS Completed, FIS Started, IA | Duck Creek Storage, LLC | 7077 Amos Creek 345kV | Concho | WEST | 2028-03-12 | OTH | BA | 409.8 | SFS/NtP | 2024-01-17 | 2024-02-02 | 2024-02-09 | 2024-01-18 |  |  | 2025-08-27 | Yes |  |  |  | 2025-09-11
26INR0359 | Uva Creek Solar | SS Completed, FIS Started, IA | Grape Creek Solar, LLC | Tap 345 kV 59905 Faraday - 59900 Long Draw | Borden | WEST | 2028-08-25 | SOL | PV | 302.16 |  | 2023-12-18 | 2024-02-27 | 2024-05-20 | 2024-02-06 |  |  | 2024-10-30 | Yes | Not Required | Not Required | Not Required
26INR0362 | Midfield BESS Project SLF | SS Completed, FIS Started, No IA | HQC Solar Holdings 1, LLC | Tap 138kV 8121 Blessing - 8125 Lolita | Matagorda | COASTAL | 2028-07-01 | OTH | BA | 0 |  | 2024-04-09 | 2024-05-20 | 2024-07-22 | 2024-05-07 |  |  |  | No
26INR0363 | Saint Charles Energy Storage | SS Completed, FIS Started, No IA | RSN STORAGE 001, LLC | TAP 138kV 3345 FLATBRA_8 - 3351 JIM_ENG_8 | Houston | NORTH | 2027-06-01 | OTH | BA | 253.9 |  | 2024-12-09 | 2024-02-27 | 2024-05-24 | 2024-11-20 |  |  |  | No
26INR0364 | Pollo Pinto Solar | SS Completed, FIS Started, No IA | TX Palo Pinto SB 6, LLC | Tap 138kV 331 RWMILLER - 320 JAYBIRD | Palo Pinto | NORTH | 2027-08-15 | SOL | PV | 150.8 |  | 2023-12-11 | 2024-02-27 | 2024-05-20 | 2024-02-26 |  |  |  | No |  |  | Not Required
26INR0365 | BLACK BEAR SOLAR | SS Completed, FIS Started, No IA | ESCONDIDO DRAW RESOURCES, LLC | #6564 ILLN4A 138 KV | Crockett | WEST | 2028-06-01 | SOL | PV | 102.9 |  | 2024-06-19 | 2023-12-04 | 2024-03-04 | 2024-05-17 |  | No |  | No |  |  | Not Required
26INR0366 | BLACK BEAR BESS | SS Completed, FIS Started, No IA | ESCONDIDO DRAW RESOURCES, LLC | #6564 ILLN4A 138kV | Crockett | WEST | 2028-06-01 | OTH | BA | 51.2 |  | 2024-06-19 | 2023-12-04 | 2024-03-04 | 2024-05-17 19:23 |  | No |  | No
26INR0370 | Central Power Station | SS Completed, FIS Not Started, No IA | Hydra-Gen Energy Unlimited | 967 Gibbons Creek 345kV | Grimes | NORTH | 2027-05-01 | GAS | GT | 750 |  |  | 2024-03-22 | 2024-06-19 | 2025-01-14 22:43 |  |  |  | No
26INR0372 | Centennial Solar | SS Completed, FIS Started, No IA | Centennial AD 8 LLC | Tap 138kV 6364 YELLOW JACKET - 76390 FORT MASON | Menard | WEST | 2029-04-30 | SOL | PV | 61.36 |  | 2023-12-09 | 2024-01-03 | 2024-03-22 | 2023-12-22 |  |  |  | No |  |  | Not Required
26INR0374 | Cobra Clean Energy Center | SS Completed, FIS Started, No IA | Cobra Clean Energy Center LLC | looped on circuit 04 between Mustang Bayou (#42960) and Hudson (#42100) | Brazoria | COASTAL | 2027-10-08 | OTH | BA | 100.4 |  | 2024-07-09 | 2024-02-02 | 2024-05-01 | 2024-07-02 |  | No |  | No
26INR0375 | Avalon BESS | SS Completed, FIS Completed, IA | Avalon BESS, LLC | Tapping the 345 kV Line from Smithers (Bus# 44650) to Bellaire (Bus# 47000). | Fort Bend | HOUSTON | 2026-12-01 | OTH | BA | 522.12 |  | 2023-12-06 | 2023-12-20 | 2024-03-08 | 2023-11-30 | 2024-05-20 | Yes | 2024-12-17 | No | Not Required | Not Required
26INR0376 | Blackcat Storage | SS Completed, FIS Started, No IA | Matagorda ESS, LLC | 138kV Blackcat Substation (#80124) | Matagorda | COASTAL | 2027-12-31 | OTH | BA | 200.59 |  | 2024-01-02 | 2024-01-11 | 2024-04-08 | 2023-11-30 |  |  |  | No | Not Required | Not Required
26INR0377 | Ridley Solar SLF | SS Completed, FIS Started, No IA | Ridley Solar Project, LLC | Tap 138kV 8912 Medio Creek - 8920 HAISLEY | Refugio | COASTAL | 2029-03-23 | SOL | PV | 200.81 |  | 2024-06-12 | 2024-07-01 | 2024-09-27 | 2024-06-12 |  |  |  | No |  |  | Not Required
26INR0380 | Pepper Solar Farm | SS Completed, FIS Completed, IA | Pepper Solar Farm LLC | Tap 345kV 3405 THOUSE__5 - 3406 ELM_MOTT_5 | McLennan | NORTH | 2027-09-20 | SOL | PV | 120.69 |  | 2024-02-21 | 2024-02-27 | 2024-05-20 | 2024-02-22 | 2025-06-24 | No | 2025-06-23 | Yes |  |  | Not Required | 2025-08-11
26INR0385 | Nanulak BESS | SS Completed, FIS Started, No IA | Hunt Energy Network, LLC | 38113 TNCOYOTSPG1 138kV | Reeves | WEST | 2027-03-16 | OTH | BA | 180 |  | 2025-03-26 | 2024-03-22 | 2024-06-19 | 2025-03-06 |  |  |  | No
26INR0386 | Zeus Spade Wind | SS Completed, FIS Started, No IA | Spade Wind, LLC | Tap 345 kV 1030 Morgan Creek to 76030 Gasconades Creek | Mitchell | WEST | 2027-03-20 | WIN | WT | 987.3 |  |  | 2024-03-29 | 2024-06-25 | 2025-01-07 15:35 |  |  |  | No |  |  | Not Required |  |  |  | 2025-08-01 | 2026-10-20
26INR0387 | Zeus Spade BESS | SS Completed, FIS Started, No IA | Spade BESS | Tap 345 kV 1030 Morgan Creek to 76030 Gasconades Creek | Mitchell | WEST | 2027-03-20 | OTH | BA | 446.3 |  | 2025-02-04 | 2024-03-29 | 2024-06-25 | 2025-01-24 23:11 |  |  |  | No | [6 empty] | 2025-08-01 | 2026-10-20
26INR0388 | Aggie Solar Project SLF | SS Completed, FIS Completed, No IA | reNRG TX 8 LLC | POI: COYOTE SPRINGS SUBSTATION - 138KV BUS NUMBER : 38113 COUNTY : REEVES POI LOCATION: 31.396675, -103.6252777 | Reeves | WEST | 2026-12-31 | SOL | PV | 103.7 |  | 2024-01-17 | 2024-02-02 | 2024-04-29 | 2023-12-08 | 2025-07-03 |  |  | No | Not Required | Not Required | Not Required
26INR0389 | AGGIE STORAGE PROJECT SLF | SS Completed, FIS Completed, No IA | reNRG TX 8 LLC | POI: COYOTE SPRINGS SUBSTATION - 138KV BUS NUMBER: 38113 POI LOCATION: 31.396675, -103.6252777 COUNTY: REEVES | Reeves | WEST | 2026-12-31 | OTH | BA | 0 |  | 2024-01-17 | 2024-02-02 | 2024-04-29 | 2023-12-08 | 2025-07-03 |  |  | No | Not Required | Not Required
26INR0391 | Jumping Cactus Storage | SS Completed, FIS Started, No IA | Dove Run Solar Project, LLC | 138 kV Zenaida Bus# 80043 | Duval | SOUTH | 2028-10-15 | OTH | BA | 125.37 |  | 2024-01-03 | 2024-01-11 | 2024-03-19 | 2023-12-19 |  |  |  | No
26INR0393 | Dove Wing Storage | SS Completed, FIS Started, No IA | Dove Run Solar Project, LLC | Tap 138kV 8510 Falfurriass - 8695 Crestonio | Duval | SOUTH | 2028-10-15 | OTH | BA | 122.41 |  | 2024-01-13 | 2024-02-07 | 2024-04-29 | 2024-01-05 |  |  |  | No
26INR0394 | Timber Cove Storage SLF | SS Completed, FIS Started, No IA | Freestone Solar, LLC | Tap 138 kV 212 Winkler - 3510 Pin Oak | Freestone | NORTH | 2027-04-01 | OTH | BA | 0 |  | 2024-01-04 | 2024-01-11 | 2024-04-08 | 2023-12-18 |  |  |  | No
26INR0396 | Kodiak AGR1 | SS Completed, FIS Started, No IA | Hunt Energy Network, LLC | 38113 TNCOYOTSPG1 | Reeves | WEST | 2027-06-15 | OIL | OT | 132 |  | 2024-10-03 | 2024-02-27 | 2024-05-28 | 2024-09-10 |  |  |  | No
26INR0402 | HILLBORO BESS | SS Completed, FIS Started, No IA | Abei Energy Green XI LLC | TAP 138 kV 3522 HILLBORO1_8 - 234 CHATT | Hill | NORTH | 2028-09-21 | OTH | BA | 127.29 |  | 2025-05-28 | 2024-02-27 | 2024-05-24 | 2024-11-14 |  |  |  | No
26INR0405 | Buffalo Creek BESS | SS Completed, FIS Completed, IA | Old 300 Storage Center, LLC | 44090 Cedar Creek 345kV | Fort Bend | HOUSTON | 2026-06-01 | OTH | BA | 251.4 |  | 2024-03-12 | 2024-03-22 | 2024-06-19 | 2024-03-07 | 2025-03-18 | No | 2024-10-02 | Yes | Not Required | Not Required | 2025-04-30 | 2025-05-01 | 2025-05-01 | 2025-05-01
26INR0407 | Rock Creek BESS | SS Completed, FIS Started, IA | Flat Rock Energy Center, LLC | 7150 Kendall 138kV | Kendall | SOUTH | 2028-03-29 | OTH | BA | 251.05 |  | 2024-02-22 | 2024-02-27 | 2024-05-24 | 2024-02-27 |  |  | 2025-07-22 | Yes |  |  |  | 2025-08-04
26INR0408 | Liatris Flexible Gas | SS Completed, FIS Completed, No IA | Stone Creek Peaker LLC | Tap 138 kV (42980) Nash - (44010) WA Parish CKT02 | Brazoria | COASTAL | 2026-12-31 | GAS | GT | 204.71 |  | 2024-02-06 | 2024-03-22 | 2024-06-19 | 2024-03-06 | 2025-05-01 |  |  | No
26INR0409 | Lucky 7 Solar | SS Completed, FIS Completed, IA | Lucky 7 Solar Farm LLC | Tap 345kV 1697 SULPHUR SPRINGS SWITCH - 2464 CASH SWITCH | Hopkins | NORTH | 2027-09-20 | SOL | PV | 100.8 | Status Change INA-to-PLN | 2024-03-06 | 2024-03-22 | 2024-06-19 | 2024-02-29 | 2025-08-08 | No | 2025-08-13 | No |  |  | Not Required
26INR0410 | Prost ESS | SS Completed, FIS Started, No IA | Prost ESS LLC | Tap 138kV L_PISEK_8_1Y (#7296) - L_WELCOM8_1Y(#7577) | Austin | SOUTH | 2028-09-08 | OTH | BA | 202.7 |  | 2024-02-12 | 2024-02-27 | 2024-05-20 | 2024-02-12 |  |  |  | No
26INR0411 | Tex-Bar ESS | SS Completed, FIS Completed, No IA | Tex-Bar ESS LLC | Tap 345kV JEWETT_S5 (#3390) -- SINGLETON (#44645) | Madison | NORTH | 2027-07-01 | OTH | BA | 201.5 |  | 2024-02-14 | 2024-03-22 | 2024-06-19 | 2024-02-26 | 2024-09-26 | Yes |  | No
26INR0412 | BumbleBee Solar | SS Completed, FIS Started, No IA | BumbleBee Solar Farm LLC | Tap 345kV 5725 PawneeSW5 - 8689 Tango | Bee | SOUTH | 2027-07-01 | SOL | PV | 211.6 |  | 2024-02-22 | 2024-02-27 | 2024-05-24 | 2024-02-26 |  |  |  | No |  |  | Not Required
26INR0417 | GAMAY ENERGY STORAGE | SS Completed, FIS Completed, IA | GAMAY ENERGY STORAGE LLC | Tap 138 kV Line from TNFM524 (39703) to West Columbia Main (39500), in Brazoria County. | Brazoria | COASTAL | 2027-03-01 | OTH | BA | 418.6 |  | 2024-01-30 | 2024-02-07 | 2024-04-30 | 2024-01-26 | 2024-10-17 |  | 2025-05-27 | No | Not Required | Not Required
26INR0418 | TE Smith Storage 2 | SS Completed, FIS Started, No IA | Smith II Battery Storage, LLC | 2478 Royse 345kV | Rockwall | NORTH | 2027-08-16 | OTH | BA | 125.32 |  | 2024-12-09 | 2024-04-15 | 2024-07-12 | 2024-11-21 |  |  |  | No
26INR0420 | Whitetail BESS | SS Completed, FIS Started, No IA | Hunt Energy Network, LLC | #23846 SALTMN_SU8 138kV | Mitchell | WEST | 2027-03-16 | OTH | BA | 180 |  | 2025-08-26 | 2024-02-27 | 2024-05-24 | 2025-03-06 |  |  |  | No
26INR0422 | PowerVault BESS | SS Completed, FIS Started, No IA | SMT Elm Mott BESS | Tap 345kV 3406 Elm Mott - 3405 Tradinghouse Ses | McLennan | NORTH | 2027-07-01 | OTH | BA | 254.8 |  | 2024-04-07 | 2024-03-22 | 2024-06-19 | 2024-04-02 15:58 |  |  |  | No
26INR0425 | Twinwood Solar 1 | SS Completed, FIS Started, No IA | Twinwood PV1, LLC | Tap 138kV 44750 FULSHR_S25_8 - 44860 TWINWD_S25_8 | Waller | HOUSTON | 2027-10-27 | SOL | PV | 358.06 |  | 2024-08-06 | 2024-03-22 | 2024-06-19 | 2024-07-20 |  |  |  | No |  |  | Not Required
26INR0426 | Maderagemela BESS1 | SS Completed, FIS Started, No IA | Twinwood ES1, LLC | Tap 138kV 44750 FULSHR_S25_8 to 44860 TWINWD_S25_8 | Waller | HOUSTON | 2027-10-27 | OTH | BA | 153.96 |  | 2024-07-31 | 2024-02-27 | 2024-05-24 | 2024-07-20 |  |  |  | No
26INR0427 | BremRaek BESS | SS Completed, FIS Started, No IA | BremRaek BESS | 7271 LCRA New Bremen 138 kV | Austin | SOUTH | 2027-11-14 | OTH | BA | 200.6 |  | 2024-02-29 | 2024-03-22 | 2024-06-19 | 2024-02-28 |  |  |  | No
26INR0428 | Diamond Cowboy Storage | SS Completed, FIS Started, No IA | Diamond B Storage, LLC | Tap 345kV 8249 Angstrom - 8624 Grissom | San Patricio | COASTAL | 2028-10-16 | OTH | BA | 103.5 |  | 2024-04-03 | 2024-04-15 | 2024-07-12 | 2024-04-16 |  | Yes |  | No
26INR0429 | Post Trail Energy | SS Completed, FIS Started, No IA | Post Trail Energy, LLC | Tap 138kV Conoco 8138 - Black Cat 80124 | Matagorda | COASTAL | 2028-10-16 | OTH | BA | 103.5 |  | 2024-08-26 | 2024-09-10 | 2024-12-08 | 2024-08-26 |  | No |  | No
26INR0430 | Clapton Storage | SS Completed, FIS Started, No IA | Clapton BESS | Tap 345 kV 3424 Buckhorn Switch - 1444 Brown Switch | Mills | NORTH | 2028-03-08 | OTH | BA | 208.91 |  | 2024-02-05 | 2024-03-22 | 2024-06-19 | 2024-02-13 |  |  |  | No
26INR0431 | Big Rooter West Solar | SS Completed, FIS Started, IA | Big Rooter West, LLC | 39950# TNTNP_ONE_3 345 KV | Robertson | NORTH | 2028-05-31 | SOL | PV | 403.42 | Proj Name COD | 2024-02-26 | 2024-03-22 | 2024-06-19 | 2024-03-22 |  |  | 2025-02-18 | No | Not Required | Not Required | Not Required
26INR0432 | Big Rooter West Storage SLF | SS Completed, FIS Started, No IA | Big Rooter West, LLC | 39950# TNTNP_ONE_3 345 KV | Robertson | NORTH | 2028-12-01 | OTH | BA | 0 | COD | 2024-03-05 | 2024-03-22 | 2024-06-19 | 2024-03-22 |  |  |  | No | Not Required | Not Required
26INR0440 | Hamby Solar | SS Completed, FIS Started, No IA | Abilene GCE LLC | 6245 ABILENE ROBERTSON PRISON 69 KV | Jones | WEST | 2028-06-27 | SOL | PV | 205.8 |  | 2024-03-26 | 2024-03-22 | 2024-06-19 | 2024-03-20 |  |  |  | No |  |  | Not Required
26INR0442 | Donna BESS | SS Completed, FIS Started, No IA | Donna Solar LLC | Tap 345 kV 80137 Stewart Road - 8383 North Edinburg | Hidalgo | SOUTH | 2029-02-22 | OTH | BA | 53.91 |  | 2024-11-20 | 2024-03-22 | 2024-06-19 | 2024-11-06 |  | Yes |  | No | Not Required | Not Required
26INR0443 | Sullivan Solar | SS Completed, FIS Started, No IA | Sullivan Solar LLC | Tap 138kV 8798 La Grulla - 8355 Goodwin | Hidalgo | SOUTH | 2029-02-25 | SOL | PV | 170.68 |  | 2024-11-12 | 2024-03-22 | 2024-06-19 | 2024-11-06 |  |  |  | No |  |  | Not Required
26INR0444 | Sullivan BESS | SS Completed, FIS Started, No IA | Sullivan Solar LLC | Tap 138kV 8798 La Grulla - 8355 Goodwin | Hidalgo | SOUTH | 2029-02-25 | OTH | BA | 72.19 |  | 2024-11-12 | 2024-03-22 | 2024-06-19 | 2024-11-06 20:53 |  |  |  | No
26INR0445 | Sword Solar | SS Completed, FIS Started, No IA | Hidalgo Solar LLC | Tap 138 kV 8394 Liston - 8392 Bates | Starr | SOUTH | 2029-02-22 | SOL | PV | 137.18 |  | 2024-11-20 | 2024-03-22 | 2024-06-19 | 2024-11-12 |  |  |  | No |  |  | Not Required
26INR0446 | Sword BESS | SS Completed, FIS Started, No IA | Hidalgo Solar LLC | Tap 138 kV 8394 Liston - 8392 Bates | Starr | SOUTH | 2029-02-22 | OTH | BA | 44.4 |  | 2024-11-20 | 2024-03-22 | 2024-06-19 | 2024-11-12 |  |  |  | No
26INR0447 | Honey Mesquite Wind Farm | SS Completed, FIS Completed, IA | Honey Mesquite Wind Farm , LLC | 59902 Sand Bluff 345kV | Glasscock | WEST | 2026-12-15 | WIN | WT | 173.95 |  | 2024-03-06 | 2024-03-22 | 2024-06-19 | 2024-03-11 | 2025-09-11 |  | 2024-09-10 | Yes | Not Required | Not Required | Not Required | 2025-02-12
26INR0448 | Cairos Storage 2 | SS Completed, FIS Started, No IA | Cairos Solar, LLC | 7425 ODLAW SWITCH 138kV | Kinney | SOUTH | 2026-12-31 | OTH | BA | 184 |  | 2024-06-26 | 2024-07-01 | 2024-09-27 | 2024-06-20 |  |  |  | No
26INR0452 | Cannibal Draw Solar | SS Completed, FIS Started, IA | Cannibal Draw Solar, LLC | Sand_Bluff 345 kV (59902) | Glasscock | WEST | 2028-04-10 | SOL | PV | 149.5 |  | 2024-06-26 | 2024-07-01 | 2024-09-27 | 2024-06-10 |  |  | 2025-01-17 | Yes | Not Required | Not Required | Not Required | 2025-02-12
26INR0453 | Cannibal Draw Storage | SS Completed, FIS Started, IA | Cannibal Draw Solar, LLC | Sand_Bluff 345 kV (59902) | Glasscock | WEST | 2028-04-10 | OTH | BA | 98.6 |  | 2024-06-26 | 2024-07-01 | 2024-09-27 | 2024-06-10 |  |  | 2025-01-17 | Yes | Not Required | Not Required | 2025-09-15 | 2025-02-12
26INR0454 | Dove Creek Solar | SS Completed, FIS Started, No IA | Dove Creek Solar, LLC | Tap at Big Hill - Twin Buttes 345 kV line (76003 / 76009) | Tom Green | WEST | 2028-07-01 | SOL | PV | 163.6 |  | 2024-07-10 | 2024-07-22 | 2024-10-08 | 2024-06-25 |  |  |  | No | Not Required | Not Required | Not Required
26INR0455 | Dove Creek Storage | SS Completed, FIS Started, No IA | Dove Creek Solar, LLC | Tap at Big Hill - Twin Buttes 345 kV line (76003 / 76009) | Tom Green | WEST | 2028-07-01 | OTH | BA | 162.5 |  | 2024-07-10 | 2024-07-22 | 2024-10-08 | 2024-06-25 |  |  |  | No | Not Required |  | 2025-09-15
26INR0456 | Ridley Storage SLF | SS Completed, FIS Started, No IA | Ridley Solar Project, LLC | Medio Creek (Bus# 8912) to HAISLEY (Bus# 8920) | Refugio | COASTAL | 2029-03-23 | OTH | BA | 0 |  | 2024-06-17 | 2024-07-01 | 2024-09-27 | 2024-06-12 |  |  |  | No
26INR0460 | Lightning Ridge Energy Storage | SS Completed, FIS Started, No IA | Lightning Ridge Storage LLC | Tap #1429 Jacksboro Substation 345kV | Jack | NORTH | 2028-03-21 | OTH | BA | 204.7 | COD | 2024-03-18 | 2024-03-29 | 2024-06-25 | 2024-03-27 |  |  |  | No
26INR0461 | Rio Hondo BESS | SS Completed, FIS Started, No IA | SBESS TX25 LLC | Tap 138kV #80309 Las Pulgas - #8319 Rio Hondo | Cameron | COASTAL | 2028-06-30 | OTH | BA | 200.78 |  | 2024-04-18 | 2024-05-09 | 2024-08-05 | 2024-04-18 |  | No |  | No
26INR0464 | Ceres BESS | SS Completed, FIS Started, No IA | Ceres BESS, LLC | Tap 138 kV 6883 QUINLAN NORTH SS - 6860 UNION VALLEY SS | Hunt | NORTH | 2027-11-30 | OTH | BA | 202.7 |  | 2024-10-24 | 2024-10-29 | 2025-01-14 | 2024-10-24 |  |  |  | No
26INR0465 | Lavita BESS | SS Completed, FIS Started, No IA | Lavita BESS, LLC | Tap 345kV Temple Pecan Creek (3412) - Temple Switch (3414) 345kV ckt 2 | Bell | NORTH | 2028-07-01 | OTH | BA | 606 |  | 2024-06-03 | 2024-12-19 | 2025-02-20 | 2024-12-16 |  |  |  | No
26INR0466 | Symphony BESS | SS Completed, FIS Started, No IA | Symphony BESS, LLC | 46220 PETERS | Austin | SOUTH | 2028-07-01 | OTH | BA | 612 |  | 2025-01-28 | 2025-02-14 | 2025-04-22 | 2025-01-28 |  |  |  | No
26INR0467 | Basketflower Storage | SS Completed, FIS Started, No IA | Basketflower Solar, LLC | Tap 138kV Risingstar (285) - Nimrod (289) | Eastland | NORTH | 2027-12-31 | OTH | BA | 92 |  | 2024-10-24 | 2024-10-29 | 2025-01-14 | 2024-10-25 |  |  |  | No
26INR0468 | Basketflower Solar | SS Completed, FIS Started, No IA | Basketflower Solar, LLC | Tap 138kV Risingstar (285) - Nimrod (289) | Eastland | NORTH | 2027-12-31 | SOL | PV | 183 |  | 2024-10-24 | 2024-10-29 | 2025-01-14 | 2024-10-24 |  |  |  | No |  |  | Not Required
26INR0469 | Roxton Storage | SS Completed, FIS Started, No IA | Roxton Solar, LLC | Tap 138 KV Bois Pump (1835) - Brookston (1833) | Lamar | NORTH | 2028-02-18 | OTH | BA | 102 |  | 2024-05-22 | 2024-11-26 | 2025-02-03 | 2024-11-05 |  |  |  | No
26INR0470 | Roxton Solar | SS Completed, FIS Started, No IA | Roxton Solar, LLC | Tap 138 KV Bois Pump (1835) - Brookston (1833) | Lamar | NORTH | 2028-02-18 | SOL | PV | 116.8 |  | 2024-11-20 | 2024-11-26 | 2025-02-03 | 2024-11-05 |  |  |  | No |  |  | Not Required
26INR0472 | Bologna BESS | SS Completed, FIS Completed, No IA | MALONEY BESS LLC | Tap 138kV #1450 Pleasant Valley Switch - #1492 Wichita Falls Riverbend | Wichita | WEST | 2028-04-19 | OTH | BA | 202.56 | COD | 2024-03-26 | 2024-03-29 | 2024-06-25 | 2024-03-20 | 2025-03-25 | No |  | No
26INR0474 | Sorghum BESS | SS Completed, FIS Completed, IA | Blue Creek BESS, LLC | #44060 Blue Substation 345kV | Wharton | SOUTH | 2026-12-01 | OTH | BA | 208.9 |  | 2024-04-18 | 2024-04-15 | 2024-07-05 | 2024-04-18 | 2024-11-13 | No | 2025-01-08 | No | Not Required | Not Required
26INR0485 | Prospector Energy Storage | SS Completed, FIS Started, No IA | Prospector Storage LLC | Natural Dam 138kV Substation (23836) | Howard | WEST | 2026-09-30 | OTH | BA | 204.6 |  | 2024-06-28 | 2024-08-16 | 2024-11-01 | 2024-06-27 |  |  |  | No
26INR0487 | Anglin BESS | SS Completed, FIS Started, No IA | Fort Worth BESS LLC | 1883 EVRSW 138kV | Tarrant | NORTH | 2028-09-30 | OTH | BA | 206 |  | 2024-11-11 | 2024-05-09 | 2024-08-06 | 2024-11-11 |  |  |  | No
26INR0489 | Seven Springs Storage | SS Completed, FIS Started, No IA | Hancock Reservoir, LLC | Tap 7061 Copperas Cove to 7260 Kempner 138 kV | Lampasas | NORTH | 2028-05-16 | OTH | BA | 170.51 |  | 2024-04-04 | 2024-04-09 | 2024-07-03 | 2024-04-08 |  |  |  | No
26INR0496 | Hardeman BESS | SS Completed, FIS Started, No IA | Quanah BESS LLC | 6050 PAUL 138kV | Hardeman | WEST | 2028-06-30 | OTH | BA | 104 |  | 2024-12-06 | 2024-05-09 | 2024-08-05 | 2024-11-11 |  |  |  | No
26INR0497 | Rosharon BESS | SS Completed, FIS Started, No IA | Rosharon BESS LLC | 138 kV 42570 Archer (ACH) | Brazoria | COASTAL | 2028-06-30 | OTH | BA | 120 |  | 2025-01-07 | 2024-04-09 | 2024-07-05 | 2024-12-27 |  |  |  | No
26INR0498 | Buckaroo BESS | SS Completed, FIS Started, No IA | Weatherford BESS LLC | Tap 138kV BROCK(487) – STHBROCKSW(489) | Parker | NORTH | 2027-12-08 | OTH | BA | 120 |  | 2024-11-25 | 2024-05-09 | 2024-08-05 | 2024-11-11 |  |  |  | No
26INR0499 | Mineral Springs BESS | SS Completed, FIS Started, No IA | Burnet County LLC | 7065 DOBVI 138kV | Burnet | SOUTH | 2026-10-31 | OTH | BA | 104 |  | 2024-12-16 | 2024-06-03 | 2024-08-30 | 2024-10-21 |  |  |  | No
26INR0500 | Shackleford BESS | SS Completed, FIS Started, No IA | Shackelford County BESS LLC | 1442 CFRSW 345kV | Shackelford | WEST | 2028-09-23 | OTH | BA | 206.5 |  | 2025-02-03 | 2024-12-19 | 2025-03-17 | 2025-01-31 |  |  |  | No
26INR0501 | Rolling Plains BESS | SS Completed, FIS Started, No IA | Haskell County BESS LLC | 6104 SMOKY HILL 345kV | Haskell | WEST | 2028-06-30 | OTH | BA | 120 |  | 2024-11-15 | 2024-08-16 | 2024-09-13 | 2024-10-21 |  |  |  | No
26INR0502 | Fudge Ranch BESS | SS Completed, FIS Started, No IA | Crandall BESS LLC | 6902<6902><TALTY_RC><138kV> | Kaufman | NORTH | 2027-06-30 | OTH | BA | 104 |  | 2024-12-02 | 2024-04-15 | 2024-07-11 | 2024-11-11 |  |  |  | No
26INR0503 | Rex Storage | SS Completed, FIS Started, No IA | Rex BESS, LLC | Tap 138 kV 48096 El Dorado - 43610 Scarsdale CKT 92 | Harris | HOUSTON | 2027-09-15 | OTH | BA | 256.4 |  | 2024-06-05 | 2024-06-13 | 2024-08-07 | 2024-06-04 |  |  |  | No
26INR0505 | Goldhill Energy Storage | SS Completed, FIS Started, No IA | Goldhill Energy Storage LLC | Tap 138kV 8154 VISTRON4B – 8189 TUNGSTEN4A | Victoria | SOUTH | 2026-09-30 | OTH | BA | 200.58 |  | 2024-04-12 | 2024-04-15 | 2024-07-05 | 2024-04-15 |  |  |  | No
26INR0506 | Momentum Bock | SS Completed, FIS Started, No IA | Momentum Bock, LLC | 1771 LAMAR BLOSSOM 138kV | Lamar | NORTH | 2028-04-20 | OTH | BA | 125.38 |  | 2024-08-20 | 2024-09-04 | 2024-12-03 | 2024-08-04 |  |  |  | No
26INR0507 | Los Vientos IB Repower | SS Completed, FIS Started, No IA | Los Vientos Windpower IB, LLC | #8319 RIOHONDO 138 kV | Willacy | COASTAL | 2027-03-01 | WIN | WT | 184.8 |  | 2024-07-17 | 2024-07-22 | 2024-10-07 | 2024-07-12 |  |  |  | No |  |  | Not Required
26INR0511 | Little Star Solar | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | #9043 CISTERN 345kV | Bastrop | SOUTH | 2026-12-31 | SOL | PV | 61.6 |  | 2024-06-20 | 2024-07-01 | 2024-09-23 | 2024-06-12 |  |  |  | No |  |  | Not Required
26INR0514 | Techne BESS | SS Completed, FIS Started, No IA | Techne BESS, LLC | 7560 RED ROCK 138kV | Bastrop | SOUTH | 2026-12-31 | OTH | BA | 202.7 |  | 2024-09-05 | 2024-09-10 | 2024-12-08 | 2024-09-05 |  |  |  | No
26INR0515 | Rio Grand Valley Element Fuels Power | SS Completed, FIS Started, No IA | Element H2Gen, LLC | Tap 138kV 59450 Waterport Substation - 5789 Southmost Sub | Cameron | COASTAL | 2027-07-01 | HYD | OT | 230 |  | 2025-04-14 | 2024-06-13 | 2024-09-10 | 2025-03-03 |  |  |  | No
26INR0516 | Jade Flash Storage | SS Completed, FIS Started, No IA | IP Lumina BESS, LLC | 59911 MHOS 345kV | Scurry | WEST | 2027-06-15 | OTH | BA | 320 |  | 2024-07-05 | 2024-07-22 | 2024-10-08 | 2024-07-17 |  |  |  | No
26INR0517 | Andromeda Storage II | SS Completed, FIS Started, No IA | IP Lumina II BESS, LLC | 60011 Nebulast 345kV | Scurry | WEST | 2027-06-15 | OTH | BA | 320 |  | 2024-07-02 | 2024-08-16 | 2024-11-12 | 2024-07-15 |  |  |  | No
26INR0518 | Radian Storage II | SS Completed, FIS Completed, No IA | IP Radian BESS, LLC | Tap 1444 Brown Switch 345KV | Brown | NORTH | 2027-06-15 | OTH | BA | 320 |  | 2024-07-03 | 2024-07-30 | 2024-10-25 | 2024-07-15 | 2025-08-20 | No |  | No
26INR0519 | Sky Global West Houston | SS Completed, FIS Completed, IA | Sky Global Power Two, LLC | tap 138kV 44700 Gebhardt - 44740 Wallis circuit 65 | Austin | SOUTH | 2027-06-01 | GAS | IC | 324.58 |  | 2024-05-29 | 2024-07-01 | 2024-10-04 | 2024-06-04 | 2025-03-12 | Yes | 2025-03-25 | No
26INR0521 | Millers Branch Solar III | SS Completed, FIS Completed, IA | Miller's Branch Solar LLC | Tap 345kV 60703 Gauss - 60514 Clear Crossing (60712 QUASAR) | Haskell | WEST | 2026-07-01 | SOL | PV | 133 | COD | 2025-01-30 | 2024-08-16 | 2024-11-04 | 2025-01-30 | 2024-12-09 |  | 2021-06-14 | Yes | Not Required | Not Required | Not Required | 2025-05-14
26INR0523 | Demeter Storage 2 | SS Completed, FIS Started, No IA | Demeter Solar, LLC | Tap 138kV 7224 LULING - 7216 Lockhart | Caldwell | SOUTH | 2029-06-01 | OTH | BA | 138 |  | 2024-09-17 | 2024-10-01 | 2024-12-30 | 2024-09-19 |  |  |  | No
26INR0524 | Fagus Solar Park 3 SLF | SS Completed, FIS Started, IA | Greenalia Solar Power Misae III, LLC | 60501 Tesla 345 kV | Childress | PANHANDLE | 2026-09-30 | SOL | PV | 186.36 |  |  | 2024-06-03 | 2018-07-06 | 2024-05-30 |  | No | 2019-02-21 | Yes |  |  | Not Required | 2024-12-19
26INR0525 | Bypass BESS II | SS Completed, FIS Started, No IA | Bypass BESS II LLC | 44000 Wa Parish 345 kV | Fort Bend | HOUSTON | 2027-04-30 | OTH | BA | 415.97 |  | 2024-11-04 | 2024-11-19 | 2025-02-18 | 2024-10-23 |  | Yes |  | No
26INR0527 | Mandolin Solar SLF | SS Completed, FIS Started, No IA | Mandolin Solar Project, LLC | Del Sol (SERIES CAP LINE SIDE) BUS#80307 to Cenizo (CAP LINE SIDE) BUS#80225 Transmission Line | Starr | SOUTH | 2028-11-15 | SOL | PV | 300 |  | 2024-07-09 | 2024-07-22 | 2024-10-17 | 2024-06-24 |  |  |  | No |  |  | Not Required
26INR0528 | Mandolin Storage SLF | SS Completed, FIS Started, No IA | Mandolin Solar Project, LLC | Del Sol (SERIES CAP LINE SIDE) BUS#80307 to Cenizo (CAP LINE SIDE) BUS#80225 Transmission Line | Starr | SOUTH | 2028-11-15 | OTH | BA | 0 |  | 2024-07-09 | 2024-07-22 | 2024-10-17 | 2024-06-24 |  |  |  | No
26INR0529 | Electric E - West Texas Generation | SS Completed, FIS Started, No IA | Electric E Power Marketing | #11166 ENPOD 138kV | Loving | WEST | 2028-04-09 | GAS | GT | 43.8 | MW Size | 2024-08-19 | 2024-10-18 | 2025-01-10 | 2024-10-10 |  |  |  | No
26INR0530 | Longview Wind | SS Started, FIS Started, No IA | Longview Wind, LLC | To tap 345 kV Long Draw (Bus# 59900) to Venturi (Bus# 59923) Transmission line | Dawson | WEST | 2027-10-07 | WIN | WT | 352.6 | FIS Request | 2025-09-17 | 2025-09-22 |  | 2025-09-05 |  |  |  | No |  |  | Not Required
26INR0531 | West Munday Wind | SS Completed, FIS Started, IA | West Munday Wind, LLC | Tap 345kV 60703 Gauss7D – 60712 Quasar | Knox | WEST | 2028-06-30 | WIN | WT | 351.91 |  | 2024-11-05 | 2024-11-19 | 2025-02-20 | 2024-11-05 |  |  | 2025-07-21 | No |  |  | Not Required
26INR0537 | Comanche Creek generating station | SS Completed, FIS Started, No IA | Longfellow Power LLC | TNCENTRY1_1 [138 kV] ( 38431) | Pecos | WEST | 2027-12-31 | GAS | IC | 107 | COD | 2024-06-10 | 2024-07-01 | 2024-09-23 | 2024-06-18 |  |  |  | No
26INR0543 | Three Canes Solar SLF | SS Completed, FIS Completed, IA | Three Canes Solar LLC | Tap 345kV 3381 Big Brown – 68091 Navarro circuit | Navarro | NORTH | 2027-07-31 | SOL | PV | 333 | COD | 2024-07-10 | 2024-07-22 | 2024-10-17 | 2024-07-10 | 2025-02-18 |  | 2024-11-27 | Yes | Not Required | Not Required | Not Required | 2025-02-12
26INR0544 | Signal Hill BESS I | SS Completed, FIS Started, No IA | Signal Hill Generating LLC | 1498 WFCOGEN_8 138 - Wichita Falls Cogen 138 kV Substation | Wichita | WEST | 2027-08-18 | OTH | BA | 122.78 |  | 2024-08-06 | 2024-09-04 | 2024-12-03 | 2024-08-06 |  |  |  | No
26INR0545 | Knight Airport BESS I | SS Completed, FIS Started, No IA | Airport Storage I LLC | Tap 138kV 48126 Gulfgate - 48199 Knight 06 and 42680 Garden Villas - 42770 Ashville 06 | Harris | HOUSTON | 2027-10-15 | OTH | BA | 522.46 |  | 2024-08-07 | 2024-08-16 | 2024-11-13 | 2024-08-08 |  |  |  | No
26INR0546 | Hobby BESS I | SS Completed, FIS Started, No IA | Airport Storage II LLC | Double Tap 138kV 42680 Garden Villas – 48250 Hall & 42680 Garden Villas – 48013 Chocolate Bayou | Harris | HOUSTON | 2027-10-15 | OTH | BA | 602.56 |  | 2024-08-06 | 2024-09-04 | 2024-12-03 | 2024-08-15 |  |  |  | No
26INR0548 | Burnet Bay Storage | SS Completed, FIS Started, No IA | TOCE TX BESS 4, LLC | tap 138kV 40390 Crosby - 40790 Haney | Harris | HOUSTON | 2027-06-01 | OTH | BA | 207.83 |  | 2024-08-27 | 2024-09-10 | 2024-12-08 | 2024-08-29 |  |  |  | No
26INR0550 | Grand Mesa BESS | SS Completed, FIS Started, No IA | PERRY GREEN POWER LLC | 76582 MESA VIEW SWITCH 138kV | Pecos | WEST | 2026-09-30 | OTH | BA | 253.28 |  | 2024-08-02 | 2024-08-16 | 2024-11-13 | 2024-08-01 |  |  |  | No
26INR0551 | Hastings Park BESS | SS Completed, FIS Completed, IA | Brazos Roots BESS, LLC | 39010 138kV HASTINGS | Brazoria | COASTAL | 2027-09-15 | OTH | BA | 256.34 | COD | 2024-08-02 | 2024-08-16 | 2024-11-01 | 2024-08-09 | 2025-03-21 |  | 2025-08-13 | No
26INR0552 | Coastal Bayou Storage | SS Completed, FIS Completed, No IA | TOCE TX BESS 5, LLC | Tap 138kV #40015 Cedar Bayou Plant - #40050 Sjolander Ckt 86 | Harris | HOUSTON | 2027-06-01 | OTH | BA | 174.59 |  | 2024-08-30 | 2024-09-04 | 2024-12-03 | 2024-08-30 | 2025-07-15 | Yes |  | No
26INR0555 | Desert Palm BESS | SS Completed, FIS Started, No IA | Desert Palm BESS LLC | 78280 Bevo Substation 138 kV | Dimmit | SOUTH | 2027-07-01 | OTH | BA | 201.3 |  | 2024-08-07 | 2024-08-16 | 2024-11-13 | 2024-08-08 |  |  |  | No
26INR0556 | Wintergarden BESS | SS Completed, FIS Started, No IA | Wintergarden BESS LLC | 8970 Catarina 138 kV | Dimmit | SOUTH | 2028-06-30 | OTH | BA | 201.2 |  | 2024-08-13 | 2024-08-16 | 2024-10-08 | 2024-08-07 |  | No |  | No
26INR0559 | Georgia-Lynn BESS | SS Completed, FIS Started, No IA | Georgia Lynn BESS LLC | 80064 CHOCBAYU4A 138 kV | Victoria | SOUTH | 2028-02-20 | OTH | BA | 108.7 |  | 2024-07-25 | 2024-07-30 | 2024-10-28 | 2024-07-25 |  |  |  | No
26INR0560 | Fort Worth Power Core Bastrop Gas Plant | SS Completed, FIS Started, No IA | Fort Worth Power Core LLC | Tap 345kV 7042 ZORN - 7040 AUSTROP | Bastrop | SOUTH | 2029-09-28 | GAS | CC | 506.38 |  | 2025-05-05 | 2025-05-27 | 2025-08-22 | 2025-04-30 |  |  |  | No
26INR0568 | Texas Cotton Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | Tap 345kV 975 Jack_Creek - 967 Gibbons Creek | Brazos | NORTH | 2028-12-31 | SOL | PV | 201.6 |  | 2024-09-03 | 2024-10-01 | 2024-12-30 | 2024-09-19 |  |  |  | No |  |  | Not Required
26INR0573 | Cummins BESS | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 1333 MCDONALD 138kV | Glasscock | WEST | 2028-06-30 | OTH | BA | 200.89 |  | 2024-09-10 | 2024-10-01 | 2024-11-12 | 2024-09-16 |  |  |  | No
26INR0589 | Goat Mountain BESS | SS Completed, FIS Started, No IA | Goat Wind LLC | 76030-Gasconades Creek 345 kV | Sterling | WEST | 2027-06-01 | OTH | BA | 201.1 |  | 2025-01-21 | 2025-01-28 | 2025-04-08 | 2025-01-17 |  |  |  | No
26INR0590 | Callisto ID Energy Center | SS Completed, FIS Started, No IA | Tempus Power management LLC | 47150 (H_O_C__B138) 138kV | Harris | HOUSTON | 2026-12-01 | OTH | BA | 100 | COD | 2024-09-10 | 2024-10-01 | 2024-11-13 | 2024-09-10 |  |  |  | No
26INR0597 | Electric E - West Texas Generation 2 | SS Completed, FIS Started, No IA | Electric E Power Marketing | #18664 SHAWPD 138kV | Midland | WEST | 2028-09-19 | GAS | GT | 0 |  | 2024-12-17 | 2024-12-19 | 2025-02-20 | 2024-11-06 |  |  |  | No
26INR0598 | Tennuto BESS | SS Completed, FIS Started, No IA | Tennuto BESS, LLC | Wolfridge (#730) | Cooke | NORTH | 2027-12-31 | OTH | BA | 202 |  | 2025-01-10 | 2025-01-28 | 2025-04-08 | 2025-01-14 |  |  |  | No
26INR0599 | Coda BESS | SS Completed, FIS Started, No IA | Coda BESS, LLC | (#80258) Mayo 138kV | San Patricio | COASTAL | 2028-07-31 | OTH | BA | 202 |  | 2025-01-16 | 2025-01-28 | 2025-04-08 | 2025-01-17 |  |  |  | No
26INR0600 | Crocus Solar | SS Completed, FIS Started, No IA | Crocus Solar, LLC | Tap 138kV 1613 BRECKENRIDGE TAP - 1614 BRECKENRIDGE | Stephens | NORTH | 2028-07-01 | SOL | PV | 102 |  | 2025-01-27 | 2025-01-28 | 2025-04-08 | 2025-01-27 |  |  |  | No |  |  | Not Required
26INR0601 | Crocus Storage | SS Completed, FIS Started, No IA | Crocus Solar, LLC | Tap 138kV 1613 BRECKENRIDGE TAP - 1614 BRECKENRIDGE | Stephens | NORTH | 2028-07-01 | OTH | BA | 51 |  | 2025-01-27 | 2025-01-28 | 2025-04-08 | 2025-01-27 |  |  |  | No
26INR0602 | Damia Storage | SS Completed, FIS Started, No IA | Damia Solar, LLC | Tap 138kV 6317 Cisco - 3545 MTNBRANCH_8 | Eastland | NORTH | 2028-07-01 | OTH | BA | 153 |  | 2025-03-30 | 2025-04-01 | 2025-06-25 | 2025-03-18 |  |  |  | No
26INR0603 | Damia Solar | SS Completed, FIS Started, No IA | Damia Solar, LLC | Tap 138kV 6317 Cisco - 3545 MTNBRANCH_8 | Eastland | NORTH | 2028-07-01 | SOL | PV | 306 |  | 2025-03-30 | 2025-04-01 | 2025-06-25 | 2025-03-18 |  |  |  | No |  |  | Not Required
26INR0605 | White Bright BESS | SS Completed, FIS Started, No IA | VLN, LLC | Tap 345 kV 1729 Valley South - 1685 Farmersville | Grayson | NORTH | 2027-04-15 | OTH | BA | 300 |  | 2025-03-12 | 2025-03-21 | 2025-06-17 | 2024-11-13 |  |  |  | No
26INR0609 | Scorpius Solar | SS Completed, FIS Started, No IA | Ben Milam Solar 4 | 3377 LTPSW 345KV | Milam | SOUTH | 2028-11-16 | SOL | PV | 500 |  | 2024-11-19 | 2024-12-16 | 2025-03-03 | 2024-11-20 |  |  |  | No |  |  | Not Required
26INR0611 | Goat Mountain BESS 2 | SS Completed, FIS Started, No IA | Goat Wind LLC | 76030-Gasconades Creek 345 kV | Sterling | WEST | 2027-06-01 | OTH | BA | 100.7 |  | 2025-01-21 | 2025-01-28 | 2025-04-08 | 2025-01-17 |  |  |  | No
26INR0612 | Clay County Yang Storage | SS Completed, FIS Started, No IA | DM-CCY, LLC | 1458 Cobb Switching Station 345 kV | Clay | WEST | 2028-10-01 | OTH | BA | 307.51 |  | 2024-12-20 | 2024-12-26 | 2025-03-19 | 2024-12-20 |  |  |  | No
26INR0613 | Wichita County Mawson Storage | SS Completed, FIS Started, No IA | DM-WCM, LLC | Tap 345kV Fisher Road Switch (#1425) – Riley (#6101) Line | Wichita | WEST | 2028-10-01 | OTH | BA | 153.7 |  | 2024-12-13 | 2024-12-19 | 2025-02-20 | 2024-12-13 |  |  |  | No
26INR0614 | Bell County Leifester Storage | SS Completed, FIS Started, No IA | DM-BCRCML, LLC | Tap 138kV 3428 Killeen South – 13628 Founders Trail Sub | Bell | NORTH | 2028-10-01 | OTH | BA | 205 |  | 2024-11-14 | 2024-11-19 | 2025-02-18 | 2024-11-14 |  |  |  | No
26INR0615 | Bell County Morgan Storage | SS Completed, FIS Started, No IA | DM-BCTRM, LLC | To Tap 138 kV Trimmier Substation (Bus# 136) | Bell | NORTH | 2028-04-01 | OTH | BA | 256.4 |  | 2024-11-14 | 2024-11-19 | 2025-02-18 | 2024-11-14 |  |  |  | No
26INR0616 | Blanco County Behrends Storage | SS Completed, FIS Started, No IA | DM-BCB, LLC | #70482 Blanco Substation 138 kV - currently being upgraded | Blanco | SOUTH | 2028-12-15 | OTH | BA | 153.8 |  | 2024-12-13 | 2024-12-19 | 2025-03-17 | 2024-12-13 |  |  |  | No
26INR0617 | Knox County Moore Storage | SS Completed, FIS Started, No IA | DM-KCM, LLC | 6110 Munday East Substation 138kV | Knox | WEST | 2028-06-30 | OTH | BA | 77 |  | 2024-12-17 | 2024-12-19 | 2025-02-20 | 2024-12-13 |  | No |  | No
26INR0618 | Taylor County Paul Storage | SS Completed, FIS Started, No IA | DM-TCP, LLC | 6260 Abilene South Substation 138kV | Taylor | WEST | 2028-06-30 | OTH | BA | 205 |  | 2024-12-05 | 2024-12-19 | 2025-02-20 | 2024-12-05 |  | No |  | No
26INR0619 | Bonham Storage SLF | SS Completed, FIS Started, No IA | J&J Solar Ranch LLC | Tap 138kV 3632 Mexia_Main - 3634 Groesbeck_Main | Limestone | NORTH | 2027-04-05 | OTH | BA | 104.92 |  | 2025-01-16 | 2025-01-28 | 2025-04-15 | 2025-01-16 |  |  |  | Yes
26INR0621 | Juno 3 Solar | SS Completed, FIS Started, IA | Juno Solar 3 | #59916 Buck Canyon 345kV | Borden | WEST | 2027-11-30 | SOL | PV | 500 |  | 2025-03-18 | 2025-03-24 | 2025-06-09 | 2025-03-18 |  |  | 2025-07-01 | No |  |  | Not Required
26INR0622 | Buffalo Gap 1 Wind Repower | SS Completed, FIS Started, No IA | Buffalo Gap Wind Farm, LLC | 6216 Bluff Creek Substation 138kV | Nolan | WEST | 2026-12-01 | WIN | WT | 120.26 |  | 2025-01-16 | 2025-01-28 | 2025-04-15 | 2025-01-10 |  |  |  | No |  |  | Not Required
26INR0625 | Buffalo Gap 2 Wind Repower | SS Completed, FIS Started, No IA | Buffalo Gap Wind Farm 2, LLC | 6216 Bluff Creek 138 kV | Nolan | WEST | 2026-12-01 | WIN | WT | 231.37 |  | 2024-12-03 | 2024-12-19 | 2025-02-20 | 2024-11-26 |  |  |  | No |  |  | Not Required
26INR0626 | Buffalo Gap 3 Wind Repower | SS Completed, FIS Started, No IA | Buffalo Gap Wind Farm 3, LLC | 6216 Bluff_Creek 138kV | Taylor | WEST | 2026-12-01 | WIN | WT | 168.39 |  | 2024-11-26 | 2024-12-03 | 2025-02-18 | 2024-11-20 |  |  |  | No |  |  | Not Required
26INR0630 | Betel Storage I | SS Completed, FIS Started, No IA | BETEL STORAGE I | 3377 Little Pond Switch ( LTPSW) 345 | Milam | SOUTH | 2026-08-12 | OTH | BA | 500 |  | 2024-12-06 | 2025-01-28 | 2025-04-15 | 2025-01-22 |  |  |  | No
26INR0632 | Dempsey Solar SLF | SS Completed, FIS Started, No IA | Dempsey Solar LLC | Tap 138 KV Ridge (#37)-Robertson (#32) line; BEPC | Leon | NORTH | 2028-09-08 | SOL | PV | 245.34 |  | 2025-02-06 | 2025-02-25 | 2025-05-20 | 2025-03-20 |  |  |  | No |  |  | Not Required
26INR0633 | Betel Storage II | SS Completed, FIS Started, No IA | BETEL STORAGE II | 3377 Little Pond 345 | Milam | SOUTH | 2026-12-17 | OTH | BA | 500 |  | 2024-12-06 | 2025-01-28 | 2025-04-15 | 2025-01-22 |  |  |  | No
26INR0636 | Lyra Storage | SS Completed, FIS Started, IA | JUNO BESS I | Tap Long Draw (59900) – Faraday (59905) CKT 1 and LONGDRAW (59900) - GALVANI(59912) CKT 2 | Borden | WEST | 2026-11-12 | OTH | BA | 500 |  |  | 2025-05-27 | 2025-08-23 | 2025-05-12 |  |  | 2025-08-13 | No
26INR0640 | Amberjack2 BESS | SS Completed, FIS Started, No IA | Hunt Energy Network, LLC | 79501 KINGFISHER 345KV | Cameron | COASTAL | 2027-03-08 | OTH | BA | 180 |  | 2024-12-26 | 2025-01-28 | 2025-05-03 | 2025-01-06 |  |  |  | No
26INR0647 | Wake Wind Energy | SS Completed, FIS Started, No IA | WAKE WIND ENERGY | 59904 Cottonwood 345 | Crosby | PANHANDLE | 2027-05-01 | WIN | WT | 251.3 |  | 2025-04-04 | 2025-04-21 | 2025-07-15 | 2025-04-17 |  |  |  | No |  |  | Not Required
26INR0654 | Great Hambino BESS | SS Started, FIS Started, No IA | Atascosa BESS, LLC | #5700 Miracle Lake Substation 138kV | Atascosa | SOUTH | 2027-02-01 | OTH | BA | 122.98 | FIS Request | 2025-09-10 | 2025-09-11 |  | 2025-09-10 |  |  |  | No
26INR0664 | Coleto Creek - Fuel Change Only | SS Completed, FIS Started, No IA | COLETO CREEK POWER LLC | 8162 Coleto Creek 138kV | Goliad | SOUTH | 2026-12-15 | GAS | ST | 655 |  | 2025-06-02 | 2025-04-21 | 2025-07-19 | 2025-05-21 |  |  |  | No
26INR0669 | Greyhound Solar - Phase E | SS Completed, FIS Completed, IA | ROCKHOUND SOLAR 2 LLC DBA GREYHOUND SOLAR | Tap 345kV 11010 Wolf - 1018 Moss | Ector | WEST | 2025-10-30 | SOL | PV | 150.71 | COD | 2019-03-14 | 2025-04-17 | 2019-06-05 | 2025-04-17 | 2024-10-31 | No | 2022-01-15 | Yes | Not Required | Not Required | Not Required | 2024-11-04 | 2024-11-04 | 2024-11-04 |  |  | 2025-08-14 | 2025-09-10
26INR0670 | Greyhound Solar - Phase F | SS Completed, FIS Completed, IA | ROCKHOUND SOLAR 2 LLC DBA GREYHOUND SOLAR | Tap 345kV 11010 Wolf - 1018 Moss | Ector | WEST | 2025-11-13 | SOL | PV | 101.6 |  | 2019-03-14 | 2025-04-17 | 2019-06-05 | 2025-04-17 | 2024-10-31 | No | 2022-01-15 | Yes | Not Required | Not Required | Not Required | 2024-11-04 | 2024-11-04 | 2024-11-04 |  |  | 2025-08-14 | 2025-09-10
26INR0675 | A4 Pearsall DGR | SS Completed, FIS Completed, IA | Life Cycle Power | XFMR. #1 and XFMR. #4 | Bexar | SOUTH | 2025-09-10 | OIL | OT | 58 |  |  | 2025-06-06 | 2025-06-19 | 2025-06-06 | 2025-08-01 |  | 2025-08-08 | No | [8 empty] | 2025-08-13 | 2025-08-15
26INR0676 | Q1 Valley Road DGR | SS Completed, FIS Completed, IA | Life Cycle Power | XFMR. #2 | Bexar | SOUTH | 2025-10-02 | OIL | OT | 29 |  |  | 2025-06-06 | 2025-06-19 | 2025-06-06 | 2025-08-01 |  | 2025-08-08 | No | [8 empty] | 2025-09-03 | 2025-09-08
26INR0681 | K2 Nacogdoches DGR | SS Completed, FIS Completed, IA | Life Cycle Power | TRANF. No.1 and TRANF. No.3 | Bexar | SOUTH | 2025-09-17 | OIL | OT | 58 |  |  | 2025-06-06 | 2025-06-19 | 2025-06-06 | 2025-08-01 |  | 2025-08-08 | No | [8 empty] | 2025-09-30
26INR0683 | Z0 BECK ROAD DGR | SS Completed, FIS Completed, IA | Life Cycle Power | XFMR #1 and XFMR #3 | Bexar | SOUTH | 2025-09-09 | OIL | OT | 60 |  |  | 2025-06-06 | 2025-06-19 | 2025-06-06 | 2025-08-01 |  | 2025-08-08 | No | [8 empty] | 2025-09-17
26INR0686 | Zeus Mitchell BESS II | SS Completed, FIS Started, No IA | Zeus Mitchell BESS II, LLC | Tap 345 kV 10049 Ranger Camp - 10057 Prong Moss CKT #01 | Mitchell | WEST | 2027-05-01 | OTH | BA | 1042.94 |  | 2025-05-20 | 2025-06-19 | 2025-09-16 | 2025-05-20 |  |  |  | No
26INR0694 | V2 Brooks Field DGR | SS Completed, FIS Completed, IA | Life Cycle Power | XFMR. #1, XFMR. #2 and XFMR. #3 | Bexar | SOUTH | 2025-09-10 | OIL | OT | 76.5 |  |  | 2025-06-06 | 2025-06-19 | 2025-06-06 | 2025-08-01 |  | 2025-08-08 | No
27INR0002 | Puerto Del Sol 2 | SS Completed, FIS Started, No IA | PUERTO DEL SOL, LLC | Tap 345kV 79500 Palmito - 79501 King Fisher Ckt 1 | Cameron | COASTAL | 2027-12-31 | SOL | PV | 213.8 |  | 2023-03-28 | 2022-05-16 | 2022-08-13 | 2023-01-30 17:14 |  |  |  | No |  |  | Not Required
27INR0003 | Becerra Creek Storage 2 | SS Completed, FIS Started, No IA | Bordas Renewable Energy, LLC | 345 kV Cenizo Substation (#80220) | Webb | SOUTH | 2027-12-01 | OTH | BA | 125.62 |  | 2022-09-19 | 2022-09-21 | 2022-12-19 | 2022-09-07 |  |  |  | No
27INR0004 | Dundee North Wind | SS Completed, FIS Started, IA | Felix 2, LLC | 345 kV Riley Substation (#6101); AEP | Wilbarger | WEST | 2027-07-31 | WIN | WT | 307.72 |  | 2022-12-28 | 2023-01-03 | 2023-03-30 | 2022-12-28 |  | No | 2025-02-21 | Yes | Not Required |  | Not Required | 2025-04-03
27INR0005 | Dundee South A Wind | SS Completed, FIS Started, IA | Felix 2, LLC | 345 kV Riley Substation (#6101); AEP | Baylor | WEST | 2027-07-31 | WIN | WT | 307.23 |  | 2022-12-28 | 2023-01-03 | 2023-03-30 | 2022-12-22 |  | No | 2025-02-21 | Yes | Not Required |  | Not Required | 2025-04-03
27INR0007 | Felix East Solar | SS Completed, FIS Started, IA | Felix 1, LLC | The 345 kV Riley Substation (#6101); AEP | Wilbarger | WEST | 2027-07-31 | SOL | PV | 301.44 |  | 2022-12-28 | 2023-01-03 | 2023-03-30 | 2022-12-22 |  | No | 2025-02-21 | Yes | Not Required |  | Not Required | 2025-04-03
27INR0009 | Felix Storage | SS Completed, FIS Started, No IA | Felix 1, LLC | The 345 kV Riley Substation (#6101); AEP | Wilbarger | WEST | 2027-07-31 | OTH | BA | 100.54 |  | 2022-12-28 | 2023-01-03 | 2023-03-30 | 2022-12-22 |  | No |  | No
27INR0011 | Dundee South B Wind | SS Completed, FIS Started, IA | Felix 2, LLC | 345 kV Riley Substation (#6101); AEP | Baylor | WEST | 2027-07-31 | WIN | WT | 300.27 |  | 2023-01-06 | 2023-01-17 | 2023-04-14 | 2023-01-03 |  | No | 2025-02-21 | Yes | Not Required |  | Not Required | 2025-04-03
27INR0012 | Felix West Solar | SS Completed, FIS Started, IA | Felix 1, LLC | 6101 Riley 345 kV | Wilbarger | WEST | 2027-07-31 | SOL | PV | 200.95 |  | 2023-01-06 | 2023-01-17 | 2023-04-14 | 2023-01-03 |  | No | 2025-02-21 | Yes | Not Required |  | Not Required | 2025-04-03
27INR0014 | Kit Fox Storage | SS Completed, FIS Started, No IA | Kit Fox Storage, LLC | Walton Switch (6899) 138KV | Henderson | NORTH | 2027-07-01 | OTH | BA | 153.6 |  | 2023-03-08 | 2023-03-13 | 2023-06-09 | 2023-03-10 |  | No |  | No
27INR0015 | Cumbia Energy Center | SS Completed, FIS Started, No IA | Cumbia Energy Center, LLC | 8485 Westside Bulk 138kV | Nueces | COASTAL | 2027-09-07 | OTH | BA | 200 |  | 2023-03-20 | 2023-03-27 | 2023-06-19 | 2023-03-21 |  |  |  | No
27INR0020 | SCOTT CROSSING SOLAR SLF | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | Tap 345kV 60514 Clear Crossing - 60507 | Haskell | WEST | 2027-09-01 | SOL | PV | 364.14 |  | 2023-03-14 | 2023-03-27 | 2023-06-19 | 2023-03-13 |  |  |  | No |  |  | Not Required
27INR0022 | Panhandle Flagship Solar 1 | SS Completed, FIS Completed, No IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005) | Carson | PANHANDLE | 2027-12-01 | SOL | PV | 439.4 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-02-23 | 2025-07-11 | Yes |  | No |  |  | Not Required
27INR0023 | Panhandle Flagship Solar 2 | SS Completed, FIS Completed, No IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005). Station 2 (27INR0023) connects to Station 1 (27INR0022 & 27INR0025) via a 4.9 mile internal tie line. Station 1 (27INR0022 & 27INR0025) connects to POIB via 22.5 mile tie-line | Hutchinson | PANHANDLE | 2027-12-01 | SOL | PV | 304.4 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-02-23 | 2025-07-11 | Yes |  | No |  |  | Not Required
27INR0024 | Panhandle Flagship Solar 3 | SS Completed, FIS Completed, No IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005).Station 3 (27INR0024) connects to Station 2 (27INR0023) via a 4.4 mile internal tie line. Station 2 connects to Station 1 (27INR0022 & 27INR0025) via a 4.9 mile internal tie line. Station 1 connects to POI | Hutchinson | PANHANDLE | 2027-12-01 | SOL | PV | 260.3 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-02-23 | 2025-07-11 | Yes |  | No |  |  | Not Required
27INR0025 | Panhandle Flagship Storage | SS Completed, FIS Completed, No IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005) | Carson | PANHANDLE | 2027-12-01 | OTH | BA | 371.7 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-02-23 | 2025-07-11 | Yes |  | No
27INR0029 | Short Creek BESS | SS Completed, FIS Started, No IA | Wichita Solar I, LLC | Tap 345kV 6101 Riley - 1425 Fisher Road Switch Ckt 1 | Wichita | WEST | 2027-12-17 | OTH | BA | 155.66 |  | 2023-04-12 | 2023-04-19 | 2023-07-14 | 2023-04-12 |  | No |  | No
27INR0038 | SCOTT CROSSING STORAGE SLF | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | Tap 345kV 60514 Clear Crossing - 60507 Pendulo | Haskell | WEST | 2027-09-01 | OTH | BA | 0 |  | 2023-04-06 | 2023-04-19 | 2023-07-13 | 2023-04-07 |  |  |  | No
27INR0040 | Solar Star Rhome Storage | SS Completed, FIS Completed, No IA | Solar Star Rhome Storage | 576 RHOME 138kV | Wise | NORTH | 2027-03-31 | OTH | BA | 220.7 |  | 2023-08-17 | 2023-04-19 | 2023-07-12 | 2023-08-04 | 2025-07-21 |  |  | No
27INR0047 | Sunscape Renewable Energy Solar SLF | SS Completed, FIS Started, IA | Sunscape Renewable Energy LLC | Bus# 8455 Lon C Hill to Bus# 80078 Reforzar 345 kV Line | Nueces | COASTAL | 2029-01-26 | SOL | PV | 522.75 | COD | 2023-06-14 | 2023-06-28 | 2023-09-20 | 2023-05-30 |  | Yes | 2024-07-18 | Yes |  |  | Not Required | 2025-08-10
27INR0048 | Sunscape Renewable Energy Storage SLF | SS Completed, FIS Started, IA | Sunscape Renewable Energy LLC | Tap 345kV 8455 Lon C Hill -- 80078 Reforzar | Nueces | COASTAL | 2029-01-26 | OTH | BA | 0 | COD | 2023-06-06 | 2023-06-28 | 2023-09-20 | 2023-06-06 |  | Yes | 2024-07-18 | Yes |  |  |  | 2025-08-10
27INR0049 | Darkwood Solar | SS Completed, FIS Completed, No IA | Mustang Creek Solar, LLC | Tap 345KV 1900 Comanche Peak to 1440 Comanche SS | Comanche | NORTH | 2027-09-20 | SOL | PV | 150.76 |  | 2023-11-09 | 2023-06-28 | 2023-09-01 | 2023-11-09 | 2025-07-29 |  |  | No |  |  | Not Required
27INR0050 | Darkwood BESS | SS Completed, FIS Completed, No IA | Mustang Creek Solar, LLC | Tap 345KV 1900 Comanche Peak - 1440 Comanche Switch | Comanche | NORTH | 2027-09-20 | OTH | BA | 150.5 |  | 2023-11-09 | 2023-06-07 | 2023-09-01 | 2023-10-31 | 2025-07-29 |  |  | No
27INR0056 | Laurel Wind Energy Center | SS Completed, FIS Started, IA | Laurel Energy Center, LLC | Solstice to Bakersfield (Bus# 60404 -76002) 345kV Ckt 2 line tap | Pecos | WEST | 2027-03-28 | WIN | WT | 306.6 | MW Size | 2023-06-15 | 2023-06-28 | 2023-09-22 | 2023-06-08 |  |  | 2024-10-25 | Yes | Not Required | Not Required | Not Required | 2025-09-15
27INR0061 | Hecate Energy Orem Wind | SS Completed, FIS Started, No IA | Hecate Energy LLC | 42530 Jones Creek 345kV | Brazoria | COASTAL | 2030-06-01 | WIN | WT | 1542 |  | 2024-06-27 | 2023-06-28 | 2023-09-22 | 2024-06-14 21:31 |  |  |  | No |  |  | Not Required
27INR0063 | Supra Wind | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap #6101 Riley 7A to #60505 Edithcla 7B 345kV | Hardeman | WEST | 2027-12-23 | WIN | WT | 205.86 |  | 2023-07-05 | 2023-07-10 | 2023-10-05 | 2023-06-29 |  |  |  | No |  |  | Not Required
27INR0071 | Sandow Lakes Energy Station | SS Completed, FIS Started, No IA | SL Energy Power Plant I, LLC | #3431 Sandow SES 138kV | Milam | SOUTH | 2028-04-01 | GAS | GT | 1291.6 |  | 2024-12-20 | 2024-03-22 | 2024-06-19 | 2024-11-22 |  |  |  | No
27INR0076 | Bob Creek Wind | SS Completed, FIS Started, IA | NextEra Energy Interconnection Holdings, LLC | 59902 Sand Bluff 345kV | Sterling | WEST | 2028-07-01 | WIN | WT | 240 |  | 2024-01-08 | 2024-01-11 | 2024-04-08 | 2024-01-09 |  |  | 2025-06-06 | Yes | Not Required | Not Required | Not Required | 2025-09-08
27INR0077 | Cuchillas BESS | SS Completed, FIS Started, No IA | Gransolar Texas Two | 80219 Lobo 345kV | Webb | SOUTH | 2026-12-27 | OTH | BA | 306.94 |  | 2023-08-17 | 2023-09-26 | 2023-12-20 | 2023-08-17 |  |  |  | No
27INR0080 | Laurel Storage Energy Center | SS Completed, FIS Started, IA | Laurel Energy Center, LLC | Tap 345kV 60404 Solstice - 76002 Bakersfield Ckt 2 | Pecos | WEST | 2027-03-28 | OTH | BA | 200.8 |  | 2023-08-18 | 2023-09-07 | 2023-12-01 | 2023-08-21 |  |  | 2024-10-25 | Yes | Not Required | Not Required |  | 2025-09-08
27INR0082 | Orbit Energy Storage | SS Completed, FIS Started, No IA | GCI Orbit Energy Storage, LLC | Tap 345 kV Calaveras Power Station (BUS #5400) to HOWARD_5 (BUS #5231). | Bexar | SOUTH | 2027-06-01 | OTH | BA | 501.94 |  | 2023-11-28 | 2023-11-30 | 2024-02-29 | 2023-09-27 |  |  |  | No
27INR0083 | Spinner Energy Storage | SS Completed, FIS Started, No IA | GCI Wolf Energy Storage, LLC | 8196 Poesta Substation 138kV | Bee | SOUTH | 2027-06-01 | OTH | BA | 125.63 |  | 2023-10-05 | 2023-10-13 | 2024-01-09 | 2023-09-27 |  |  |  | No
27INR0084 | Aegle Power | SS Completed, FIS Started, No IA | Aegle Power LLC | (#79501) Kingfisher 345 kV | Cameron | COASTAL | 2027-07-30 | GAS | CC | 1536.4 |  | 2024-07-03 | 2024-07-22 | 2024-10-17 | 2024-07-03 |  |  |  | No
27INR0085 | Eagle Claw Energy Center | SS Completed, FIS Completed, No IA | Eagle Claw Energy Center, LLC | 30.615932, -95.962023 - Singleton (Bus #44645) - Zenith (Bus #44900) Circuit #98 345 kV Line | Grimes | NORTH | 2027-03-15 | OTH | BA | 200.84 |  | 2023-09-28 | 2023-10-13 | 2024-01-10 | 2023-10-06 | 2024-10-30 | Yes |  | No | Not Required | Not Required
27INR0086 | Tumbleweed Solar | SS Completed, FIS Started, No IA | Hecate Energy Tumbleweed Solar LLC | 59905 Faraday 345 kV | Borden | WEST | 2027-12-01 | SOL | PV | 613.89 |  | 2024-04-10 | 2023-09-22 | 2023-12-20 | 2024-04-08 17:47 |  |  |  | No | Not Required | Not Required | Not Required
27INR0087 | Tumbleweed Storage | SS Completed, FIS Started, No IA | Hecate Energy Tumbleweed Storage LLC | 59905 Faraday 345 kV | Borden | WEST | 2027-12-01 | OTH | BA | 507.2 |  | 2024-05-22 | 2023-10-04 | 2023-12-20 | 2024-05-09 16:45 |  |  |  | No
27INR0090 | Antonio Road BESS | SS Completed, FIS Started, No IA | Tempus Power management LLC | Paige 138kV, bus 7308, connecting to the existing substation via adding a breaker | Bastrop | SOUTH | 2027-06-01 | OTH | BA | 155.52 |  | 2024-09-19 | 2023-10-13 | 2024-01-09 | 2024-09-09 |  |  |  | No
27INR0091 | Oak Tree Energy Storage | SS Completed, FIS Started, No IA | Live Oak Energy Storage, LLC | Tap Shaula (#5380) – South Texas (#5915) | Lavaca | SOUTH | 2029-08-01 | OTH | BA | 310.2 |  | 2023-11-14 | 2023-12-04 | 2024-02-21 | 2023-11-21 |  |  |  | No
27INR0092 | Pecan BESS | SS Completed, FIS Started, No IA | Gransolar Texas Three LLC | (PSSE BUS# 47) HILTOPLKS8 138kV | Leon | NORTH | 2027-07-15 | OTH | BA | 157.12 |  | 2023-10-11 | 2023-10-25 | 2024-01-22 | 2023-10-12 |  |  |  | No
27INR0093 | Guadalupe Battery Storage Project | SS Completed, FIS Started, No IA | Guadalupe Power Partners, LP | # 7044 Marion 345kV | Guadalupe | SOUTH | 2027-05-01 | OTH | BA | 210.5 |  | 2024-12-02 | 2023-11-14 | 2024-02-08 | 2024-10-22 19:50 |  |  |  | No
27INR0095 | Bulldog Power (TEF - Due Diligence) | SS Completed, FIS Started, No IA | Bulldog Power LLC | 39703 TNMP FM524 Substation 138kV | Brazoria | COASTAL | 2027-12-18 | GAS | GT | 311 |  | 2023-11-13 | 2023-11-14 | 2024-02-08 | 2023-11-08 |  | No |  | No
27INR0096 | Rubicon Power BESS | SS Completed, FIS Completed, No IA | Rubicon Power LLC | 39703 TNMP FM524 138kV | Brazoria | COASTAL | 2026-12-31 | OTH | BA | 301.38 |  | 2023-11-13 | 2023-11-14 | 2024-02-08 | 2023-11-08 | 2024-08-23 | No |  | No
27INR0097 | JUNIPERUS BESS | SS Completed, FIS Started, No IA | BLUE STONE RENEWABLE XXI LLC | TAP CASHSW_T5 (2464) -SULSP_SS1_5 (1697) | Hopkins | NORTH | 2029-07-09 | OTH | BA | 169.6 |  | 2024-08-05 | 2023-10-30 | 2024-01-26 | 2024-07-24 |  |  |  | No
27INR0099 | Silver Spur Energy Center | SS Completed, FIS Started, No IA | Silver Spur Energy Center, LLC | TAP BRYN_WBRN (BUS #32895) - MILL_SW138 (BUS #32856) 138 KV LINE | Brazos | NORTH | 2027-02-01 | OTH | BA | 200.83 |  | 2023-12-04 | 2023-12-04 | 2024-03-01 | 2023-10-16 |  |  |  | No | Not Required | Not Required
27INR0102 | Cottonseed Energy Storage | SS Completed, FIS Completed, No IA | Cottonseed Energy Storage LLC | South Lane City and PSEE # is 43190 | Wharton | SOUTH | 2027-04-20 | OTH | BA | 207.6 |  | 2023-11-01 | 2023-11-14 | 2024-01-08 | 2023-11-02 | 2024-08-23 |  |  | No
27INR0105 | Starlight Solar | SS Completed, FIS Started, No IA | Mills Tx Solar LLC | tap the 138 kV Goldthwaite (#7070) – San Saba Switch (#77074) | Mills | NORTH | 2027-03-15 | SOL | PV | 130.72 |  | 2023-10-06 | 2024-02-27 | 2024-05-22 | 2024-02-08 |  |  |  | No | Not Required | Not Required | Not Required
27INR0107 | Starlight Storage | SS Completed, FIS Started, No IA | Mills Tx Solar LLC | Tap 138kV 7070 Goldthwaite – 77074 San Saba Switch | Mills | NORTH | 2027-03-15 | OTH | BA | 104.66 |  | 2024-02-16 | 2024-02-27 | 2024-05-22 | 2024-02-08 |  |  |  | No | Not Required | Not Required
27INR0108 | Paint Rock Wind | SS Completed, FIS Started, No IA | Orsted Onshore Development North America, LLC | Tap 345-kV Double Circuit Amos Creek (7077) – Brown (1444)/Amos Creek (7077) – Bow Wood (76006) | Concho | WEST | 2028-10-01 | WIN | WT | 405.4 | COD | 2023-12-06 | 2024-01-03 | 2024-03-29 | 2023-12-11 |  |  |  | No | Not Required | Not Required | Not Required
27INR0109 | Two Barbaras BESS | SS Completed, FIS Started, No IA | Two Barbaras BESS | Tap 138 kV Pinehurst (#46240) – Mill Creek (#44850) Line | Montgomery | HOUSTON | 2028-12-06 | OTH | BA | 217.16 |  | 2024-03-15 | 2024-03-22 | 2024-06-19 | 2024-03-14 |  |  |  | No
27INR0111 | Malachite Solar | SS Completed, FIS Started, No IA | Malachite Solar LLC | The 345 kV Hillje (#44200) – Holman (#9073) Line; AEN. | Wharton | SOUTH | 2028-07-31 | SOL | PV | 184.55 |  | 2024-01-31 | 2024-02-27 | 2024-05-22 | 2024-01-25 |  |  |  | No |  |  | Not Required
27INR0112 | Malachite BESS | SS Completed, FIS Started, No IA | Malachite Storage LLC | Tap 345 kV 44200 Hillje – 9073 Holman | Wharton | SOUTH | 2028-07-31 | OTH | BA | 191.12 |  | 2024-05-15 | 2024-05-20 | 2024-07-22 | 2024-05-15 |  |  |  | No
27INR0115 | Diamante BESS | SS Completed, FIS Started, No IA | Flexen USA LLC | 40600 ROANS__POI_5 345kV | Grimes | NORTH | 2028-11-01 | OTH | BA | 513.68 |  | 2025-01-17 | 2024-02-27 | 2024-05-24 | 2024-11-21 |  | No |  | No
27INR0117 | Roble BESS | SS Completed, FIS Started, No IA | Flexen USA LLC | 7180 L_ZORN__8_1Y 138kV | Guadalupe | SOUTH | 2028-12-01 | OTH | BA | 154.3 |  | 2025-06-17 | 2024-08-16 | 2024-11-14 | 2025-06-02 |  |  |  | No
27INR0118 | Grapefruit Solar | SS Completed, FIS Started, IA | Grapefruit Solar LLC | North Edinburg (Bus #8905) - Reforzar (Bus # 80078) 345kV | Hidalgo | SOUTH | 2028-12-31 | SOL | PV | 291.4 | MW Size | 2024-02-05 | 2024-02-27 | 2024-05-22 | 2024-01-26 |  | No | 2025-04-10 | No | Not Required | Not Required | Not Required | 2025-08-04
27INR0120 | Solar Star Bay City Storage | SS Completed, FIS Started, No IA | Solar Star Bay City Storage | Tap 138kV Bay City (#8113) – Black Cat (#80124) | Matagorda | COASTAL | 2027-03-31 | OTH | BA | 201.6 |  | 2024-12-06 | 2023-12-20 | 2024-03-11 | 2024-11-25 |  |  |  | No
27INR0124 | RedSun Solar | SS Completed, FIS Started, No IA | Gransolar Texas Twenty Two | Tap 138kV 7100 Burnet - 7529 Bertram | Burnet | SOUTH | 2027-06-15 | SOL | PV | 82.55 |  | 2023-11-28 | 2023-12-04 | 2024-03-01 | 2023-11-28 |  |  |  | No |  |  | Not Required
27INR0125 | RedSun BESS | SS Completed, FIS Started, No IA | Gransolar Texas Twenty Two | Existing Line from Substation Name: Burnet (PSSE#7100) to Substation Name: Bertram (PSSE#7520) | Burnet | SOUTH | 2027-06-15 | OTH | BA | 84.04 |  | 2023-11-27 | 2023-12-04 | 2024-03-01 | 2023-11-21 |  |  |  | No
27INR0126 | Corvus Solar | SS Completed, FIS Started, IA | Corvus Solar, LLC | Tap 345kV Cenzio (#80219) - Lobo (#80220) | Webb | SOUTH | 2028-11-12 | SOL | PV | 201.5 | MW Size | 2024-01-16 | 2024-02-07 | 2024-04-30 | 2024-01-16 |  | No | 2025-07-31 | No | Not Required | Not Required | Not Required | 2025-08-04
27INR0127 | Bigway Solar I | SS Completed, FIS Started, IA | NextEra Energy Interconnection Holdings, LLC | Tap 345kV 59904 Cottonwood - 60500 Edith Clarke Ckt #2 | King | WEST | 2028-12-31 | SOL | PV | 203 |  | 2024-03-12 | 2024-01-11 | 2024-03-15 | 2024-02-28 21:55 |  |  | 2025-02-15 | Yes | Not Required | Not Required | Not Required | 2025-03-19
27INR0128 | Bigway Solar II | SS Completed, FIS Started, IA | NextEra Energy Interconnection Holdings, LLC | Tap 345KV #59904 Cottonwood - #60500 Edith Clarke Ckt #2 | King | WEST | 2028-12-31 | SOL | PV | 203 |  | 2024-03-04 | 2023-12-20 | 2024-03-15 | 2024-02-28 21:56 |  | No | 2025-02-15 | Yes | Not Required | Not Required | Not Required | 2025-03-19
27INR0132 | Palo Verde Wind | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | Tap 345kV 8624 Grissom – 8455 Lon C Hill | San Patricio | COASTAL | 2027-09-02 | WIN | WT | 301.5 |  | 2024-04-01 | 2024-04-09 | 2024-07-05 | 2024-04-01 |  | Yes |  | No |  |  | Not Required
27INR0137 | Moonlit Bayou Storage | SS Completed, FIS Started, No IA | Moonlit Bayou Energy Center, LLC | Tap 138kV 7252 Schulenburg - 7254 Weimar | Fayette | SOUTH | 2028-07-31 | OTH | BA | 209.23 |  | 2023-12-23 | 2024-02-26 | 2024-05-24 | 2024-02-08 |  |  |  | No
27INR0139 | Gatsby Energy Storage | SS Completed, FIS Started, No IA | Gatsby Energy Storage LLC | Fort Lancaster 138 kV Substation (PSSE Bus #76579) | Pecos | WEST | 2027-03-31 | OTH | BA | 103.36 |  | 2023-12-07 | 2024-02-07 | 2024-04-29 | 2023-12-07 |  |  |  | No
27INR0140 | Kingsmill Wind SLF | SS Completed, FIS Started, No IA | Kingsmill Wind, LLC | 79005 Railhead 345kV | Carson | PANHANDLE | 2028-09-15 | WIN | WT | 403.53 |  | 2025-03-18 | 2024-01-11 | 2024-04-08 | 2024-10-08 |  |  |  | No |  |  | Not Required
27INR0141 | Bluefox Solar 1 | SS Completed, FIS Started, No IA | Industrial November Project LLC | #8754 Zoisite 345kV | Matagorda | COASTAL | 2029-05-31 | SOL | PV | 402.6 |  | 2024-03-12 | 2024-03-22 | 2024-06-19 | 2024-02-21 |  |  |  | No |  |  | Not Required
27INR0142 | UNICORN BESS | SS Completed, FIS Started, No IA | Unicorn Energies | Tap 138 kV Wa Parish (#44015) - Crabb River Road Line (#44170) Line; CNP | Fort Bend | HOUSTON | 2027-09-01 | OTH | BA | 278.98 |  | 2024-01-05 | 2024-01-11 | 2024-04-05 | 2024-01-05 |  |  |  | No
27INR0143 | Ogalalla Storage | SS Completed, FIS Started, No IA | Hecate Energy Ogalalla Solar LLC | 23912 OGALLALA_5 345kV | Castro | PANHANDLE | 2028-04-15 | OTH | BA | 251.6 |  | 2024-04-24 | 2024-01-03 | 2024-03-25 | 2024-04-19 |  |  |  | No
27INR0144 | Angel City Solar | SS Completed, FIS Started, No IA | Angel City Energy Center, LLC | Coleto Creek (# 8164) AEP – Pawnee (#5725) STEC, 25.9 miles from Coleto Creek, 28.2 miles from Pawnee Sub. POI co-ordinates: 28.755, -97.583 | Goliad | SOUTH | 2029-09-30 | SOL | PV | 221.02 |  | 2024-01-22 | 2024-02-07 | 2024-04-30 | 2024-01-23 |  |  |  | No |  |  | Not Required
27INR0145 | Steelhead Energy Storage | SS Completed, FIS Started, No IA | GRS BESS TEXAS SEVEN, LLC | Tap 1593 BONHAM_P8 to Allens Creek 1835 138kV | Fannin | NORTH | 2027-09-30 | OTH | BA | 192.1 |  | 2023-12-17 | 2024-02-07 | 2024-04-29 | 2024-01-04 |  |  |  | No | Not Required | Not Required
27INR0146 | Larrea Solar | SS Completed, FIS Started, No IA | Greasewood IV LLC | Tap 345kV 76002 Bakerfield - 60404 Solstice CKT#1 | Pecos | WEST | 2027-09-18 | SOL | PV | 231.6 |  | 2024-06-10 | 2024-01-03 | 2024-03-29 | 2024-06-05 13:05 |  |  |  | No |  |  | Not Required
27INR0147 | Paloma Energy Center | SS Completed, FIS Started, No IA | Harrison Street Development, LLC | Tap 138 kV 57640 Rock Island - 57639 Sheridan | Colorado | SOUTH | 2027-06-01 | SOL | PV | 193.8 |  | 2024-01-08 | 2024-02-07 | 2024-05-01 | 2024-01-09 |  |  |  | No | Not Required | Not Required | Not Required
27INR0148 | Paloma Energy Center BESS | SS Completed, FIS Started, No IA | Harrison Street Development, LLC | Tap 138kV 57640 Rock Island - 57639 Sheridan | Colorado | SOUTH | 2027-06-01 | OTH | BA | 53.6 |  | 2024-01-22 | 2024-02-07 | 2024-05-01 | 2024-01-22 |  |  |  | No
27INR0149 | Diablo Campo Storage | SS Completed, FIS Started, No IA | Diablo Campo Energy Center, LLC | The Coleto Greek (#8164) to Pawnee Switching Station (#5725) ; LCRA | Goliad | SOUTH | 2029-09-30 | OTH | BA | 313.54 |  | 2024-01-23 | 2024-02-07 | 2024-04-29 | 2024-01-23 |  |  |  | No
27INR0150 | Cielo Vista Solar | SS Completed, FIS Started, No IA | Cielo Vista Solar, LLC | Tap 345kV Bus #5901 Miguel5 - Bus #80079 Cruce7A Ckt 1 | Duval | SOUTH | 2028-06-30 | SOL | PV | 503.34 |  | 2025-03-26 | 2025-04-21 | 2025-07-18 | 2025-04-14 |  |  |  | No |  |  | Not Required
27INR0151 | Coyote Den Storage | SS Completed, FIS Started, No IA | Coyote Den Energy Center, LLC | The Kenedy Switching Station #2 (#8186) to Rosata POD (#8153) Line ; AEP | Karnes | SOUTH | 2029-09-30 | OTH | BA | 156.61 |  | 2024-01-31 | 2024-02-07 | 2024-04-29 | 2024-01-09 |  |  |  | No
27INR0152 | New Shepherd Solar | SS Completed, FIS Started, No IA | New Shepherd Energy Center, LLC | the Kenedy Switching Station #2 (#8186) – Rosata POD (#8153) line, AEP. | Karnes | SOUTH | 2029-09-30 | SOL | PV | 150.81 |  | 2024-01-03 | 2024-01-11 | 2024-04-05 | 2023-12-19 |  |  |  | No |  |  | Not Required
27INR0154 | Jim Wells BESS | SS Completed, FIS Started, No IA | Jim Wells ESS | 69kV PREMONT (#8894) | Jim Wells | SOUTH | 2028-06-30 | OTH | BA | 100.32 |  | 2024-01-18 | 2024-02-07 | 2024-05-01 | 2024-01-15 |  |  |  | No
27INR0169 | Marcos Solar SLF | SS Completed, FIS Started, No IA | GRS BESS Texas Eight | To the 138 kV line from EDNA (#8118) to VICTORIA4A (#8172) | Victoria | SOUTH | 2028-08-15 | SOL | PV | 216.11 |  | 2024-01-06 | 2024-01-11 | 2024-04-08 | 2023-12-28 |  |  |  | No |  |  | Not Required
27INR0170 | Marcos BESS | SS Completed, FIS Started, No IA | GRS BESS Texas Eight LLC | To the 138 kV line from EDNA (#8118) to VICTORIA4A (#8172) | Victoria | SOUTH | 2027-08-15 | OTH | BA | 115.88 |  | 2024-01-17 | 2024-02-07 | 2024-04-30 | 2024-01-16 |  |  |  | No
27INR0173 | Trenno BESS | SS Completed, FIS Started, IA | JSB1, LLC | Tap 138kV 2281 Godley - 2888 Carmichael | Johnson | NORTH | 2027-09-13 | OTH | BA | 202.56 |  | 2024-03-25 | 2024-02-07 | 2024-04-30 | 2024-03-19 21:43 |  | No | 2025-08-18 | No
27INR0180 | Otter BESS | SS Completed, FIS Started, No IA | GRS BESS TEXAS TEN, LLC | 5378 SHEPHERD RD 138kV | Bexar | SOUTH | 2027-04-15 | OTH | BA | 157.12 |  | 2024-02-01 | 2024-02-27 | 2024-05-20 | 2024-02-05 |  |  |  | No
27INR0181 | Elk Unit 4 | SS Completed, FIS Completed, No IA | Golden Spread Electric Cooperative, Inc. | 141607 AEEC_5 | Hale | PANHANDLE | 2027-02-28 | GAS | GT | 210 |  | 2024-03-04 | 2024-04-09 | 2024-07-05 | 2024-03-19 | 2025-07-16 |  |  | No
27INR0186 | Silver Dollar Solar | SS Completed, FIS Started, No IA | Silver Dollar Solar Project, LLC | Tap 345 kV Big Brown 3380 to Navarro 68091 ckt#2 | Freestone | NORTH | 2028-04-28 | SOL | PV | 301.9 |  | 2024-05-21 | 2024-06-03 | 2024-08-29 | 2024-05-13 |  |  |  | No |  |  | Not Required
27INR0187 | Silver Dollar Storage | SS Completed, FIS Started, No IA | Silver Dollar Solar Project, LLC | Tap 345 kV Big Brown 3380 to Navarro 68091 ckt#2 | Freestone | NORTH | 2028-04-28 | OTH | BA | 153.1 |  | 2024-05-21 | 2024-06-03 | 2024-08-29 | 2024-05-13 |  |  |  | No
27INR0190 | Millsing BESS | SS Completed, FIS Completed, No IA | Millsing BESS | 44645 CNP Singleton 345kV | Grimes | NORTH | 2028-10-15 | OTH | BA | 501.6 |  | 2024-02-02 | 2024-02-27 | 2024-05-24 | 2024-02-05 | 2024-10-08 |  |  | No
27INR0192 | Cedar Draw Solar | SS Completed, FIS Started, No IA | Cedar Draw Solar LLC | 60011 Nebula7A 345kV | Scurry | WEST | 2027-12-31 | SOL | PV | 451.4 |  |  | 2024-03-22 | 2024-06-19 | 2024-03-01 |  |  |  | No |  |  | Not Required
27INR0193 | Cedar Draw BESS | SS Completed, FIS Started, No IA | Cedar Draw Solar LLC | 60011 Nebula7A 345kV | Scurry | WEST | 2027-12-31 | OTH | BA | 225.7 |  | 2024-03-04 | 2024-03-22 | 2024-06-19 | 2024-02-20 |  |  |  | No
27INR0195 | CORRUSCANT BESS | SS Completed, FIS Started, No IA | AEU Battery Project III LLC | Tap 345kV 59904 COTTONWOOD - 60500 EDITHCLA7A | Dickens | PANHANDLE | 2027-04-18 | OTH | BA | 401.45 | MW Size | 2024-02-12 | 2024-02-27 | 2024-05-20 | 2024-02-06 |  |  |  | No
27INR0196 | Houston County BESS | SS Completed, FIS Started, No IA | Houston ESS, LLC | Tap ETEC 138kV #6733 Mustang Prairie to #6732 Latexo Sub | Houston | NORTH | 2027-04-12 | OTH | BA | 125.4 |  | 2024-02-02 | 2024-02-27 | 2024-05-20 | 2024-01-31 |  |  |  | No | Not Required | Not Required
27INR0198 | Musgravite Solar | SS Completed, FIS Started, No IA | BT Thompson Solar, LLC | Tap 138 kV (6855) Coffee - (6849) New York. | Henderson | NORTH | 2027-05-28 | SOL | PV | 100.6 |  | 2024-03-01 | 2024-03-22 | 2024-06-19 | 2024-03-06 |  | No |  | No |  |  | Not Required
27INR0202 | Shallow Valley Storage | SS Completed, FIS Started, No IA | Shallow Valley Storage, LLC | Tap 138kV 1239 Coyanosa - 11238 Blair Lake Sub | Ward | WEST | 2028-06-01 | OTH | BA | 103.39 |  | 2024-07-19 | 2024-07-22 | 2024-10-17 | 2024-07-19 |  |  |  | No
27INR0203 | Dunlay Solar | SS Completed, FIS Started, No IA | Medina PV, LLC | Tap 138kV 5813 PearsonSW - 5225 Hondo | Medina | SOUTH | 2028-06-01 | SOL | PV | 150.5 |  | 2024-03-12 | 2024-03-22 | 2024-06-19 | 2024-03-12 |  |  |  | No |  |  | Not Required
27INR0205 | Donna Solar | SS Completed, FIS Started, No IA | Donna Solar LLC | Tap 345 kV (80137) Stewart Road - (8383) North Edinburg CKT ID#01 | Hidalgo | SOUTH | 2029-02-22 | SOL | PV | 168.13 |  | 2024-11-26 | 2024-03-22 | 2024-06-19 | 2024-11-06 |  | Yes |  | No |  |  | Not Required
27INR0206 | Chacon Creek | SS Completed, FIS Started, No IA | Cattlemen BESS LLC | (#8962) LYTLE4A 138KV | Medina | SOUTH | 2027-10-31 | OTH | BA | 188.95 |  | 2024-03-07 | 2024-03-22 | 2024-06-19 | 2024-03-14 |  | No |  | No
27INR0207 | Wander Waters BESS | SS Completed, FIS Started, No IA | Wander Waters BESS LLC | 61001 JIMTREEC7A 345kV | Wilbarger | WEST | 2027-10-31 | OTH | BA | 303.5 |  | 2024-03-11 | 2024-03-22 | 2024-06-19 | 2024-03-12 |  |  |  | No
27INR0208 | Sugarloaf BESS | SS Completed, FIS Started, No IA | Sugarloaf Clean Energy LLC | (#80481) PILONCIL4 138KV | Dimmit | SOUTH | 2028-01-31 | OTH | BA | 100.6 |  | 2024-03-04 | 2024-03-22 | 2024-06-19 | 2024-03-11 |  | No |  | No
27INR0209 | Goby Energy Center | SS Completed, FIS Completed, No IA | Goby Energy Center | Tap 138kV line 44390 Karsten - 44721 Thompsons | Brazoria | COASTAL | 2027-06-30 | OTH | BA | 200.65 |  | 2024-05-01 | 2024-05-20 | 2024-08-15 | 2024-05-07 | 2025-04-07 |  |  | No
27INR0216 | Champs Elysees BESS | SS Completed, FIS Started, No IA | Champs Elysees Renewables, LLC | Tap 345 kV 3377 Little Pond Switch - 3704 Hog Creek Switch | Milam | SOUTH | 2027-12-15 | OTH | BA | 256.1 |  | 2024-07-25 | 2024-08-16 | 2024-10-08 | 2024-07-26 |  |  |  | No
27INR0217 | Journey Solar | SS Completed, FIS Started, No IA | Journey Solar, LLC | Tap 138kV Paint Creek 6161 - Aspermont 6158 | Haskell | WEST | 2027-09-14 | SOL | PV | 124.7 |  | 2024-03-13 | 2024-03-29 | 2024-06-19 | 2024-03-14 |  |  |  | No |  |  | Not Required
27INR0218 | Themisto Solar | SS Completed, FIS Completed, No IA | Themisto Solar, LLC | Tap 345kV Champion Creek #1414 – Sweetwater East #11420 | Nolan | WEST | 2028-06-30 | SOL | PV | 301.2 |  | 2023-08-23 | 2024-02-26 | 2024-05-24 | 2024-02-13 | 2025-04-14 | No |  | No |  |  | Not Required
27INR0219 | Galaxy Solar | SS Completed, FIS Started, No IA | Galaxy Solar, LLC | Tap 345kV 2427 Watermill - 3159 Elrod | Ellis | NORTH | 2028-10-30 | SOL | PV | 147.39 |  | 2024-08-22 | 2024-03-22 | 2024-06-19 | 2024-08-16 |  |  |  | No |  |  | Not Required
27INR0220 | Galaxy Storage | SS Completed, FIS Started, No IA | Galaxy Solar, LLC | Tap 345kV 2427 Watermill - 3159 Elrod | Ellis | NORTH | 2028-10-30 | OTH | BA | 154.54 |  | 2024-08-22 | 2024-03-22 | 2024-06-19 | 2024-08-16 |  |  |  | No
27INR0221 | Fierce River Solar | SS Completed, FIS Started, No IA | Rio Grande Solar LLC | Tap 345 kV 80355 Del Sol - 80119 Frontera Ckt 1 | Starr | SOUTH | 2029-02-22 | SOL | PV | 895.67 |  | 2024-11-21 | 2024-03-22 | 2024-06-19 | 2024-11-12 |  |  |  | No |  |  | Not Required
27INR0222 | Fierce River BESS | SS Completed, FIS Started, No IA | Rio Grande Solar LLC | Tapping the 345 kV Line from Del Sol (Bus# 80355) to Frontera (Bus# 80119) ckt 1 | Starr | SOUTH | 2029-02-22 | OTH | BA | 284.49 |  | 2024-11-21 | 2024-03-22 | 2024-06-19 | 2024-11-12 |  |  |  | No
27INR0223 | Benitoite Storage | SS Completed, FIS Started, No IA | BT Van Storage, LLC | Tap 138kV 3183 VAN_8 - 3197 TYLERSW_8 | Van Zandt | NORTH | 2027-08-25 | OTH | BA | 125.65 |  | 2024-03-11 | 2024-03-22 | 2024-06-19 | 2024-03-10 |  |  |  | No
27INR0224 | Leopard BESS | SS Completed, FIS Started, IA | Bobcat Energy Center, LLC | 8721 Beecher 138 kV | Victoria | SOUTH | 2028-07-09 | OTH | BA | 264.24 |  | 2024-04-22 | 2024-05-09 | 2024-08-05 | 2024-04-05 |  |  | 2025-06-09 | Yes | Not Required | Not Required | 2025-08-08 | 2025-08-08
27INR0226 | Sunlit Pines Solar SLF | SS Completed, FIS Started, No IA | Sunlit Pines Energy Center LLC | Tap 138 kV 3342 Bayou Loco - 3341 Central Angelina County | Nacogdoches | NORTH | 2027-10-03 | SOL | PV | 206.71 |  | 2024-03-29 | 2024-03-29 | 2024-06-24 | 2024-03-29 |  |  |  | No |  |  | Not Required
27INR0227 | PALO VERDE BESS | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | Tap 345kV 8624 Grissom – 8455 Lon C Hill | San Patricio | COASTAL | 2027-09-02 | OTH | BA | 150 |  | 2024-04-01 | 2024-04-15 | 2024-07-05 | 2024-04-01 |  | Yes |  | No
27INR0228 | Sunlit Pines BESS SLF | SS Completed, FIS Started, No IA | Sunlit Pines BESS LLC | Tap 138 kV 3342 Bayou Loco - 3341 Central Angelina County | Nacogdoches | NORTH | 2027-10-03 | OTH | BA | 208.12 |  | 2024-03-29 | 2024-04-09 | 2024-06-24 | 2024-03-29 |  |  |  | No
27INR0231 | Easy Battery Energy Storage Center | SS Completed, FIS Started, No IA | Easy Wind Energy Center, LLC | Tap 345 kV 76003 Big Hill to 76005 Schneeman Draw | Schleicher | WEST | 2027-12-01 | OTH | BA | 200 |  | 2024-03-18 | 2024-03-29 | 2024-06-19 | 2024-03-20 |  |  |  | No
27INR0232 | Anawa La Solar | SS Completed, FIS Started, No IA | EIA Properties, Ltd. | TAP 138 KV 8394 LISTON - 8392 BATES | Hidalgo | SOUTH | 2027-08-31 | SOL | PV | 93.3 |  | 2024-04-29 | 2024-03-29 | 2024-06-19 | 2024-04-15 22:37 |  | No |  | No |  |  | Not Required
27INR0233 | Anawa La BESS | SS Completed, FIS Started, No IA | EIA Properties, Ltd. | Tap 138KV 8394 Liston- 8392 Bates | Hidalgo | SOUTH | 2027-08-31 | OTH | BA | 103.7 |  | 2024-04-29 | 2024-03-22 | 2024-06-19 | 2024-04-15 22:34 |  | No |  | No
27INR0234 | Maddox Solar | SS Completed, FIS Completed, No IA | Industrial Lima Project LLC | Tap 138 kV Haggerty Switch (12677) to Van Al (1754) 138kV | Grayson | NORTH | 2027-09-17 | SOL | PV | 101.3 |  | 2024-04-16 | 2024-05-09 | 2024-08-05 | 2024-04-17 | 2025-04-08 |  |  | No |  |  | Not Required
27INR0235 | Ochoa Energy Storage II | SS Completed, FIS Completed, No IA | Ochoa Energy Storage II LLC | Tap 138kV 44420 Katy - 44230 Flewellen | Waller | HOUSTON | 2027-06-03 | OTH | BA | 516.56 |  | 2024-04-08 | 2024-04-15 | 2024-07-12 | 2024-04-11 | 2025-08-19 | No |  | No
27INR0236 | Atticus Energy Storage | SS Completed, FIS Started, No IA | Atticus Energy Storage | Tap 69 KV 6570 Bond Road - 6513 Sonora | Sutton | WEST | 2027-03-01 | OTH | BA | 102.98 |  | 2024-03-26 | 2024-03-29 | 2024-06-25 | 2024-03-29 |  |  |  | No
27INR0241 | Callan Solar | SS Completed, FIS Started, No IA | Menard PV, LLC | Tap 69kV 60386 Heartland to 6363 Yellow Jacket | Menard | WEST | 2028-09-01 | SOL | PV | 90.97 |  | 2024-05-22 | 2024-06-13 | 2024-08-07 | 2024-06-04 |  | No |  | No |  |  | Not Required
27INR0242 | Stonewall Solar | SS Completed, FIS Started, No IA | Stonewall PV, LLC | #755 BEPC ASPERMONT 69KV | Stonewall | WEST | 2029-01-15 | SOL | PV | 60.2 |  | 2024-05-06 | 2024-05-09 | 2024-08-05 | 2024-05-01 |  |  |  | No |  |  | Not Required
27INR0243 | Brookview Road BESS | SS Completed, FIS Completed, IA | Brookview Reliability Project LLC | Channelview 1 ( 40280) 138kV Substation | Harris | HOUSTON | 2028-05-02 | OTH | BA | 203.2 |  | 2024-04-01 | 2024-04-09 | 2024-07-05 | 2024-04-02 | 2025-06-12 |  | 2025-02-01 | Yes | Not Required | Not Required |  | 2025-09-18
27INR0245 | Pez Rojo BESS | SS Completed, FIS Started, No IA | Pez Rojo BESS, LLC | Tap 138 kV #40260 Chamon - #40912 King | Harris | HOUSTON | 2028-03-01 | OTH | BA | 217.23 |  | 2024-06-26 | 2024-07-01 | 2024-09-23 | 2024-06-14 |  | No |  | No
27INR0246 | Easy Wind Energy Center | SS Completed, FIS Started, No IA | Easy Wind Energy Center, LLC | Tap 345kV #76003 Big Hill - #76005 Schneeman Draw circuit #1 | Schleicher | WEST | 2027-12-01 | WIN | WT | 241.13 |  | 2024-05-01 | 2024-05-20 | 2024-08-16 | 2024-05-02 |  |  |  | No |  |  | Not Required
27INR0247 | Sun Angel ESS | SS Completed, FIS Started, No IA | Sun Angel ESS LLC | Tap 138kV LUFKINE East (#3326) - HERTY TAP (#3318) | Angelina | NORTH | 2028-07-01 | OTH | BA | 201.54 |  | 2024-06-03 | 2024-06-13 | 2024-08-07 | 2024-06-11 |  |  |  | No
27INR0248 | Double A Solar SLF | SS Completed, FIS Started, No IA | Double A Solar, LLC | Tap 69kV 5678 Schroeder - 5675 Big Oak | Goliad | SOUTH | 2027-05-31 | SOL | PV | 132.6 |  | 2024-05-14 | 2024-06-13 | 2024-08-07 | 2024-05-30 |  |  |  | No |  |  | Not Required
27INR0249 | Raghorn Solar SLF | SS Completed, FIS Started, No IA | Raghorn Solar LLC | Tap 69kV #5654 San Diego - #5658 Orange Grove | Jim Wells | SOUTH | 2027-05-31 | SOL | PV | 91.9 |  | 2024-05-14 | 2024-05-20 | 2024-08-16 | 2024-05-16 |  |  |  | No |  |  | Not Required
27INR0251 | Sayle Solar SLF | SS Completed, FIS Started, No IA | Sayle Solar LLC | Tap 69kV #5522 Edna - #5518 El Toro SW | Jackson | SOUTH | 2027-05-31 | SOL | PV | 122.4 |  | 2024-05-09 | 2024-06-03 | 2024-08-30 | 2024-05-22 |  |  |  | No |  |  | Not Required
27INR0252 | Parula Energy Center | SS Completed, FIS Started, No IA | Parula Energy Center | 7287 Bellville North 138kV | Austin | SOUTH | 2027-06-30 | OTH | BA | 250.95 |  | 2024-05-10 | 2024-05-20 | 2024-08-15 | 2024-05-09 |  |  |  | No
27INR0253 | Old Victory Energy Center | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | 8692 MAVERICK4A 138kV | Maverick | SOUTH | 2027-05-01 | OTH | BA | 202.5 |  | 2024-04-17 | 2024-05-09 | 2024-08-05 | 2024-04-25 |  |  |  | No
27INR0254 | REVOLUTION BESS | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | 8619 Encinal Substation 138KV | La Salle | SOUTH | 2027-05-01 | OTH | BA | 208.8 |  | 2024-04-17 | 2024-05-09 | 2024-08-05 | 2024-04-22 |  |  |  | No
27INR0255 | New Minglewood Energy Center | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | #11098 Sand Lake Switch Station (SANDLAKE_5) 345kV | Ward | WEST | 2027-09-30 | OTH | BA | 208.3 |  | 2024-04-24 | 2024-05-09 | 2024-08-05 | 2024-04-29 |  | No |  | No
27INR0257 | Double A Storage SLF | SS Completed, FIS Started, No IA | Double A Storage, LLC | Tap 69kV 5678 Schroeder - 5675 Big Oak | Goliad | SOUTH | 2027-05-31 | OTH | BA | 0 |  | 2024-06-10 | 2024-06-13 | 2024-08-07 | 2024-05-30 |  |  |  | No
27INR0259 | Raghorn Storage SLF | SS Completed, FIS Started, No IA | Raghorn Storage LLC | Tap 69kV #5654 San Diego - #5658 Orange Grove | Jim Wells | SOUTH | 2027-05-31 | OTH | BA | 0 |  | 2024-05-16 | 2024-05-20 | 2024-08-16 | 2024-05-16 |  |  |  | No
27INR0260 | Sayle Storage SLF | SS Completed, FIS Started, No IA | Sayle Storage LLC | Tap 69kV #5522 Edna - #5518 El Toro SW | Jackson | SOUTH | 2027-05-31 | OTH | BA | 122.3 |  | 2024-05-09 | 2024-06-03 | 2024-08-30 | 2024-05-22 |  |  |  | No
27INR0261 | Tipperary Solar | SS Completed, FIS Started, No IA | Tippsol | 6498 Live Oak AEP 69kV | Schleicher | WEST | 2028-03-15 | SOL | PV | 60.16 |  | 2024-05-10 | 2024-06-13 | 2024-09-10 | 2024-05-17 |  |  |  | No |  |  | Not Required
27INR0272 | EMPower Odessa (TEF - Due Diligence) | SS Completed, FIS Completed, No IA | EMPOWER USA, LLC | Tap 138 kV 1110 EDWARDS TAP - 1102 JUDKINS | Ector | WEST | 2027-07-07 | GAS | IC | 123.4 |  | 2024-07-02 | 2024-07-22 | 2024-10-17 | 2024-07-03 | 2025-08-05 |  |  | No
27INR0274 | Flying Kite Bess | SS Completed, FIS Started, No IA | Flying Kite BESS, LLC | Tap the 138 kV La Pryor (#8008) - Poblano (#8009) | Zavala | SOUTH | 2027-05-21 | OTH | BA | 104.8 |  | 2024-07-10 | 2024-07-30 | 2024-10-28 | 2024-07-22 |  |  |  | No
27INR0279 | Red Hollow Renewable Energy BESS SLF | SS Completed, FIS Started, No IA | Red Hollow Renewable Energy LLC | Tap 345kV 1422 Bowman - 17002 Garvey Road | Archer | WEST | 2028-04-10 | OTH | BA | 308.6 |  | 2024-06-04 | 2024-06-13 | 2025-08-04 | 2024-06-04 |  |  |  | No
27INR0285 | Rain Lily Storage 1 | SS Completed, FIS Started, No IA | Rain Lily Solar 1 | Tap 138kV #350 ABBYBEND - #363 HOOD | Hood | NORTH | 2028-10-15 | OTH | BA | 105.6 |  | 2024-06-04 | 2025-02-25 | 2025-05-13 | 2025-01-10 |  |  |  | No
27INR0288 | Rain Lily Solar 1 | SS Completed, FIS Started, No IA | Rain Lily Solar 1 LLC | Tap 138kV #350 ABBYBEND - #363 HOOD | Hood | NORTH | 2028-10-15 | SOL | PV | 147.76 |  | 2024-06-04 | 2025-02-25 | 2025-05-13 | 2025-01-10 |  |  |  | No |  |  | Not Required
27INR0290 | Drill Baby Drill BESS | SS Completed, FIS Started, No IA | SBESS TX8 LLC | 23859 SALTFLAT 138KV | Midland | WEST | 2028-10-11 | OTH | BA | 204.31 |  | 2025-05-12 | 2024-09-04 | 2024-11-20 | 2025-05-07 |  |  |  | No
27INR0291 | Nouveau BESS | SS Completed, FIS Started, No IA | RamZ BESS, LLC | 1444 Brown Switch - 3348 Russell Gap 345 kV Line | Brown | NORTH | 2027-12-15 | OTH | BA | 256.1 |  | 2024-07-31 | 2024-08-16 | 2024-01-08 | 2024-07-31 |  |  |  | No
27INR0292 | Donelson Solar SLF | SS Completed, FIS Started, No IA | Donelson Solar | Tap the 69 kV Bagwell (#1785) - Clarksville (#11784) line, ONCOR | Red River | NORTH | 2028-10-17 | SOL | PV | 75.44 |  | 2025-03-13 | 2025-03-24 | 2025-06-09 | 2025-03-04 |  |  |  | No |  |  | Not Required
27INR0293 | Donelson Storage SLF | SS Completed, FIS Started, No IA | Donelson Storage | Tap the 69 kV Bagwell (#1785) - Clarksville (#11784) line, ONCOR | Red River | NORTH | 2028-10-17 | OTH | BA | 0 |  | 2025-03-13 | 2025-03-24 | 2025-06-09 | 2025-03-04 |  |  |  | No
27INR0294 | Bernice Energy Storage | SS Completed, FIS Started, No IA | Bernice Energy Storage LLC | 5135 ELMENDORF 138kV | Bexar | SOUTH | 2027-02-15 | OTH | BA | 402.8 |  | 2024-08-09 | 2024-09-04 | 2024-12-02 | 2024-08-12 |  |  |  | No
27INR0297 | Tolivar Power Plant (TEF- Due Diligence) | SS Completed, FIS Completed, IA | Pecos Power Plant, LLC | Tap 138 KV 38045 IH20-38043 COWPEN | Reeves | WEST | 2027-05-06 | GAS | IC | 224.5 |  | 2024-06-10 | 2024-07-01 | 2024-09-25 | 2024-06-14 | 2025-06-23 |  | 2025-07-01 | No | 2024-12-12 | Not Required | 2025-03-25 | 2025-08-04
27INR0298 | Symank Solar | SS Completed, FIS Started, No IA | BT Symank Solar, LLC | Tap 69 kV 37470 TNOLSEN - 37520 TNSYCAMORE | Bosque | NORTH | 2027-12-15 | SOL | PV | 66.55 |  | 2024-10-29 | 2024-11-19 | 2025-02-14 | 2024-11-11 |  | No |  | No |  |  | Not Required
27INR0301 | Hondo Arroyo Solar | SS Completed, FIS Started, No IA | Hondo Creek Solar, LLC | Tap 138 kV 5225 Hondo - 5813 Pearson | Medina | SOUTH | 2028-07-01 | SOL | PV | 60.4 |  | 2024-06-11 | 2024-06-13 | 2024-09-10 | 2024-06-06 |  |  |  | No | Not Required | Not Required | Not Required
27INR0303 | Rocky Point BESS | SS Completed, FIS Started, No IA | Nicole BESS | 6351 Nicole Substation 138kV | Coke | WEST | 2027-11-01 | OTH | BA | 150.96 |  | 2024-07-09 | 2024-07-30 | 2024-10-25 | 2024-07-18 |  |  |  | No
27INR0305 | Kurtz Solar SLF | SS Completed, FIS Started, No IA | Kurtz Solar, LLC | Tap 69kV #8206 Charlotte - #8607 Jourdanton | Atascosa | SOUTH | 2029-10-01 | SOL | PV | 101.9 |  | 2024-08-29 | 2024-09-04 | 2024-12-02 | 2024-08-05 |  |  |  | No |  |  | Not Required
27INR0306 | Kurtz Storage SLF | SS Completed, FIS Started, No IA | Kurtz Storage, LLC | Tap 69kV #8206 Charlotte - #8607 Jourdanton | Atascosa | SOUTH | 2029-10-01 | OTH | BA | 0 |  | 2024-08-29 | 2024-09-04 | 2024-12-02 | 2024-08-26 |  |  |  | No
27INR0307 | Beaverhead Solar SLF | SS Completed, FIS Started, No IA | Beaverhead Solar, LLC | Direct to Sub 69kv #5653 Ben Bolt. | Jim Wells | SOUTH | 2027-07-31 | SOL | PV | 61.5 |  | 2024-08-06 | 2024-08-16 | 2024-10-07 | 2024-08-05 |  |  |  | No |  |  | Not Required
27INR0308 | Beaverhead Storage SLF | SS Completed, FIS Started, No IA | Beaverhead Solar, LLC | Direct to Sub 69kv #5653 Ben Bolt. | Jim Wells | SOUTH | 2027-07-31 | OTH | BA | 61.5 |  | 2024-08-06 | 2024-08-16 | 2024-10-07 | 2024-08-05 |  |  |  | No
27INR0309 | Tall Saddle Solar | SS Completed, FIS Started, No IA | Tall Saddle Solar, LLC | 80076 AJO SUBSTATION 345kV | Kenedy | COASTAL | 2029-10-15 | SOL | PV | 252.3 |  | 2025-04-01 | 2024-07-01 | 2024-09-26 | 2025-03-25 16:48 |  |  |  | No |  |  | Not Required
27INR0310 | Tall Saddle Wind | SS Completed, FIS Started, No IA | Tall Saddle Wind, LLC | 80076 AJO SUBSTATION 345kV | Kenedy | COASTAL | 2029-10-15 | WIN | WT | 522.8 |  | 2025-04-02 | 2024-07-01 | 2024-09-26 | 2025-03-25 15:06 |  |  |  | No |  |  | Not Required
27INR0312 | HILLBORO WIND | SS Completed, FIS Started, No IA | Abei Energy Green XI LLC | Tap 138 kV 3522 HILLBORO1_8 - 234 CHATT | Hill | NORTH | 2028-09-21 | WIN | WT | 27.77 |  | 2025-04-04 | 2024-07-01 | 2024-09-24 | 2024-11-19 |  |  |  | No |  |  | Not Required
27INR0313 | Spindletop Solar | SS Completed, FIS Started, No IA | Banita Creek Solar LLC | Tap Stryker [3109] - Lufkin [3117] 345 kV line | Nacogdoches | NORTH | 2027-06-30 | SOL | PV | 286.04 |  | 2024-07-16 | 2024-07-30 | 2024-10-25 | 2024-07-26 |  |  |  | No |  |  | Not Required
27INR0314 | Spindletop Storage | SS Completed, FIS Started, No IA | Banita Creek Solar LLC | Tap 345kV 3109 Stryker - 3117 Lufkin | Nacogdoches | NORTH | 2027-06-30 | OTH | BA | 142.57 |  | 2024-07-24 | 2024-07-30 | 2024-10-25 | 2024-07-26 |  |  |  | No
27INR0315 | Old Roman Energy Center | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | 23868 STILES 138 KV | Reagan | WEST | 2027-08-31 | OTH | BA | 207.34 |  | 2024-09-11 | 2024-10-01 | 2024-11-13 | 2024-08-30 |  |  |  | No
27INR0316 | Avant Prairie BESS | SS Completed, FIS Started, No IA | Avant Prairie ESS LLC | Tap 345kV BIGBRNE (#3380) - JEWETT (#3390) CKT 1 | Freestone | NORTH | 2027-07-01 | OTH | BA | 201.72 |  | 2024-09-03 | 2024-09-04 | 2024-12-02 | 2024-09-02 |  |  |  | No
27INR0317 | Edgewood BESS 1 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap Edgewood 138kV bus(3181) to CANTNSW_8 (3174) | Van Zandt | NORTH | 2028-03-01 | OTH | BA | 102.1 |  | 2024-10-16 | 2024-11-21 | 2025-02-18 | 2024-11-05 |  |  |  | No
27INR0320 | Perseus Gas | SS Completed, FIS Started, No IA | Engie Flexible Generation NA LLC | Tap 345kV 84550 BLULACY 7A – 8455 Lon Hill 7A Ckt 2 | Nueces | COASTAL | 2028-12-31 | GAS | GT | 1056.8 |  | 2024-12-18 | 2024-08-16 | 2024-11-13 | 2024-12-13 |  |  |  | No
27INR0321 | Rock Island Generating (TEF -Due Diligence) | SS Completed, FIS Completed, IA | Kerrville Public Utility Board Public Facility Corporation | 57640 Rock Island 138 kV | Colorado | SOUTH | 2027-06-01 | GAS | IC | 121.8 |  | 2024-07-15 | 2024-07-22 | 2024-10-08 | 2024-07-11 | 2025-03-21 |  | 2025-03-17 | Yes | 2024-08-01 | Not Required | 2025-05-05 | 2025-08-04
27INR0323 | Prairie Blossom Storage | SS Completed, FIS Started, No IA | Prairie Blossom Storage, LLC | 1322 Big Spring 138kV | Howard | WEST | 2028-09-21 | OTH | BA | 122.5 |  | 2024-12-05 | 2024-12-19 | 2025-02-03 | 2024-10-07 |  |  |  | No | Not Required | Not Required | 2025-09-15
27INR0324 | LONE STAR INDUSTRIAL PARK GAS POWER PROJECT | SS Completed, FIS Started, No IA | LONE STAR INDUSTRIAL PARK, LLC | 1795 Monticello SES 138kV | Morris | NORTH | 2028-05-11 | GAS | IC | 166 |  | 2024-08-29 | 2024-09-04 | 2024-12-02 | 2024-08-28 |  |  |  | No
27INR0326 | Thunderbird Valley Storage | SS Completed, FIS Started, No IA | Thunderbird Valley Storage | (787) Olney Substation 138 kV | Young | WEST | 2028-07-01 | OTH | BA | 150.39 |  | 2024-11-04 | 2024-11-19 | 2025-02-14 | 2024-10-22 |  |  |  | No | Not Required | Not Required | 2025-09-15
27INR0327 | Sunflower Valley Storage | SS Completed, FIS Started, No IA | Sunflower Valley Storage, LLC | 1414 Champion Creek Substation 345 kV | Mitchell | WEST | 2029-04-17 | OTH | BA | 205.7 | MW Size | 2025-04-07 | 2025-04-25 | 2025-07-22 | 2025-04-08 |  |  |  | No | Not Required | Not Required | 2025-09-15
27INR0330 | Wild Horse Desert Solar | SS Completed, FIS Started, No IA | Wild Horse Desert Solar, LLC | Tap 138kV 8613 Big Well - 8212 Dilley Switch | Dimmit | SOUTH | 2028-07-01 | SOL | PV | 120 |  | 2024-12-10 | 2024-12-19 | 2025-02-20 | 2024-12-06 |  | No |  | No | Not Required | Not Required | Not Required
27INR0331 | Wild Horse Desert Storage | SS Completed, FIS Started, No IA | Wild Horse Desert Solar, LLC | Tap 138kV 8613 Big Well - 8212 Dilley Switch | Dimmit | SOUTH | 2028-07-01 | OTH | BA | 90.3 |  | 2024-12-05 | 2024-12-19 | 2025-02-20 | 2024-12-06 |  | No |  | No | Not Required | Not Required | 2025-09-15
27INR0332 | White Wing Solar | SS Started, FIS Started, No IA | White Wing Solar, LLC | Tap 345 kV (#60504) Tesla - (#6111) Riley | Wilbarger | WEST | 2027-07-01 | SOL | PV | 127.4 |  | 2025-07-24 | 2025-08-13 |  | 2025-08-01 |  |  |  | No |  |  | Not Required
27INR0333 | White Wing Storage | SS Started, FIS Started, No IA | White Wing Solar, LLC | Tap 345 kV (#60504) Tesla - (#6111) Riley | Wilbarger | WEST | 2027-07-01 | OTH | BA | 130.4 |  | 2025-07-24 | 2025-08-13 |  | 2025-08-01 |  |  |  | No
27INR0337 | Jalisco Cogen | SS Completed, FIS Started, No IA | HEP Power Generation, LLC | 8475 JAVELINA4A 138 KV | Nueces | COASTAL | 2029-05-31 | GAS | CC | 167.8 |  | 2025-05-06 | 2024-08-16 | 2024-11-05 | 2025-05-01 |  |  |  | No
27INR0338 | Billie Storage | SS Completed, FIS Started, No IA | Weslaco Storage LLC | Tap 138kV 8357 North Weslaco – 8358 North Mercedes | Hidalgo | SOUTH | 2029-09-02 | OTH | BA | 83.75 |  | 2025-05-02 | 2024-07-30 | 2024-10-27 |  |  |  |  | No
27INR0341 | Tomahawk Road BESS | SS Completed, FIS Started, No IA | Horizon Energy Storage Greenfield Project Holdings LLC | Tap 138 kV 1019 Moss - 1113 Odessa Southwest | Ector | WEST | 2028-03-01 | OTH | BA | 257.25 |  | 2024-08-06 | 2024-08-16 | 2024-11-12 | 2024-08-09 |  |  |  | No
27INR0342 | Dorsey Road BESS | SS Completed, FIS Started, No IA | Horizon Energy Storage Greenfield Project Holdings LLC | Tap 138 kV Chavanea (5085) - Palo Alto (5330). | Bexar | SOUTH | 2029-08-31 | OTH | BA | 257.4 |  | 2025-02-04 | 2025-03-06 | 2025-06-03 | 2025-02-05 |  |  |  | No
27INR0343 | Plant Road BESS | SS Completed, FIS Started, No IA | Horizon Energy Storage Greenfield Project Holdings LLC | 1027 ODEHV 138kV | Ector | WEST | 2028-03-01 | OTH | BA | 251.32 |  | 2024-09-18 | 2024-10-10 | 2025-01-07 | 2024-10-02 |  |  |  | No
27INR0348 | Johnson Grass Solar | SS Completed, FIS Started, No IA | Johnson Grass Solar ,LLC | Tap 138kV (#11395) Navigation - (#10054) Cattlemen | Mitchell | WEST | 2028-04-19 | SOL | PV | 195.8 |  | 2024-09-30 | 2024-10-01 | 2024-12-09 | 2024-09-30 |  |  |  | No | Not Required | Not Required | Not Required
27INR0350 | Saddle Horn Station BESS SLF | SS Completed, FIS Started, No IA | Saddle Horn Station BESS LLC | tap 138kV 1650 COMANCHE_T8 - 290SHILOHC | Comanche | NORTH | 2028-09-11 | OTH | BA | 177.41 |  | 2024-08-27 | 2024-09-04 | 2024-11-13 | 2024-08-28 |  |  |  | No
27INR0351 | Saddle Horn Station Solar SLF | SS Completed, FIS Started, No IA | Saddle Horn Station LLC | 1650 COMANCHE_T8 - 290 SHILOHC 138 kV Line | Comanche | NORTH | 2028-09-11 | SOL | PV | 174.64 |  | 2024-09-03 | 2024-09-04 | 2024-11-13 | 2024-09-03 |  |  |  | No |  |  | Not Required
27INR0354 | Cebocell BESS | SS Completed, FIS Started, No IA | Cebocell, LLC | 3137 BlackFork 138 KV | Smith | NORTH | 2028-10-31 | OTH | BA | 200.87 | COD | 2024-08-20 | 2024-09-04 | 2024-11-13 | 2024-08-13 |  |  |  | No
27INR0355 | Gardner Draw Solar | SS Completed, FIS Started, IA | RWE Clean Energy Development, LLC | 59902 Sand Bluff 345kV | Glasscock | WEST | 2027-12-31 | SOL | PV | 200 |  | 2024-09-26 | 2024-10-01 | 2024-12-30 | 2024-09-25 |  |  | 2025-08-07 | No |  |  | Not Required
27INR0362 | Hamlet Solar SLF | SS Completed, FIS Started, No IA | Hamlet Solar, LLC | Tap 138kV #5895 PEARSALL - #5827 MOORE | Frio | SOUTH | 2029-09-04 | SOL | PV | 204 |  | 2024-11-04 | 2024-11-19 | 2025-02-14 | 2024-11-04 |  |  |  | No |  |  | Not Required
27INR0363 | Hamlet Storage SLF | SS Completed, FIS Started, No IA | Hamlet Solar, LLC | Tap 138kV #5895 PEARSALL -#5827 MOORE | Frio | SOUTH | 2029-09-04 | OTH | BA | 204 |  | 2024-11-04 | 2024-11-19 | 2025-02-14 | 2024-11-04 |  |  |  | No
27INR0364 | Cashel BESS | SS Completed, FIS Started, No IA | TIPPSOL LLC | 6500 Live Oak AEP 138kV | Schleicher | WEST | 2028-03-15 | OTH | BA | 150.44 |  | 2024-10-22 | 2024-10-29 | 2025-01-26 | 2024-10-22 |  |  |  | No
27INR0365 | Comanche BESS | SS Completed, FIS Started, No IA | ENERGOS BESS | #1440 Comanche Switching Station 345kV | Comanche | NORTH | 2028-10-11 | OTH | BA | 614.4 |  | 2024-12-06 | 2024-12-06 | 2025-02-18 | 2024-11-05 |  |  |  | No
27INR0366 | Gold Coin Storage | SS Completed, FIS Started, No IA | Grenergy USA | Tap 138kV 1470 Newport - 616 Carter | Montague | NORTH | 2027-07-01 | OTH | BA | 72.95 |  | 2024-10-15 | 2024-11-19 | 2025-02-18 | 2024-10-25 |  |  |  | No
27INR0367 | Goat Mountain Wind-Repower | SS Completed, FIS Started, No IA | Goat Wind LLC | 76030 Gasconades Creek 345kV | Sterling | WEST | 2027-06-01 | WIN | WT | 303.2 |  | 2025-01-10 | 2025-01-13 | 2025-04-07 | 2024-12-13 |  |  |  | No |  |  | Not Required
27INR0371 | Feather Dalea BESS | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | 59902 Sand_Bluff 345kV | Glasscock | WEST | 2027-07-02 | OTH | BA | 200 |  | 2024-09-16 | 2024-10-01 | 2024-12-09 | 2024-09-24 |  |  |  | No
27INR0372 | Abeja Solar Farm | SS Completed, FIS Started, No IA | Abeja Solar | Tap 345kV 8012 PALADIO7A - 8689 TANGO7A | Bee | SOUTH | 2027-12-12 | SOL | PV | 200.84 |  | 2024-12-09 | 2024-12-19 | 2025-02-20 | 2024-12-09 |  | Yes |  | No |  |  | Not Required
27INR0373 | Velado Solar SLF | SS Completed, FIS Started, No IA | Velado Solar, LLC | Tap 138kV 78281 Dimmit - 8274 Conoco Chittam | Dimmit | SOUTH | 2028-09-14 | SOL | PV | 115.2 |  | 2024-11-07 | 2024-11-19 | 2025-02-14 | 2024-11-07 |  |  |  | No |  |  | Not Required
27INR0374 | Velado Storage SLF | SS Completed, FIS Started, No IA | Velado Solar, LLC | Tap 138kv 78281 Dimmit - 8274 Conoco Chittam. | Dimmit | SOUTH | 2028-09-14 | OTH | BA | 115.2 |  | 2024-11-05 | 2024-11-19 | 2025-02-14 | 2024-11-05 |  |  |  | No
27INR0375 | Buck Ranch Solar SLF | SS Completed, FIS Started, No IA | Buck Ranch Solar, LLC | 5690 WEST GEORGE WEST SUB 69kV | Live Oak | SOUTH | 2028-08-02 | SOL | PV | 40.8 |  | 2024-11-13 | 2024-12-19 | 2025-02-03 | 2024-12-16 |  |  |  | No |  |  | Not Required
27INR0376 | Buck Ranch Storage SLF | SS Completed, FIS Started, No IA | Buck Ranch Solar, LLC | 5690 WEST GEORGE WEST SUB 69kV | Live Oak | SOUTH | 2028-08-09 | OTH | BA | 40.8 |  | 2024-11-13 | 2025-01-28 | 2025-04-15 | 2024-12-16 |  |  |  | No
27INR0378 | Vista Bluff Wind 2 | SS Completed, FIS Started, No IA | Vista Bluff Windpower, LLC | Double Tap 345kV Bearkat 59903 - 76000 McCamey Ckt 1 & 2 | Upton | WEST | 2028-12-31 | WIN | WT | 290.4 |  | 2024-12-09 | 2024-09-04 | 2024-11-13 | 2024-11-19 |  | Yes |  | No |  |  | Not Required
27INR0379 | Scrap Iron Solar | SS Completed, FIS Started, No IA | Energiekontor US Texas SP 15 LLC | Tap 138kV (#9) Bedias - (#15) Cross | Grimes | NORTH | 2028-09-01 | SOL | PV | 110.77 |  | 2025-05-02 | 2024-09-10 | 2024-12-06 | 2025-04-23 |  |  |  | No |  |  | Not Required
27INR0380 | La Mancha Solar SLF | SS Completed, FIS Started, No IA | La Mancha Solar, LLC | Tap 69kV 5836 NBatesville - 5822 Leona | Zavala | SOUTH | 2028-10-10 | SOL | PV | 40.9 |  | 2024-11-07 | 2024-11-19 | 2025-02-14 | 2024-11-07 |  |  |  | No |  |  | Not Required
27INR0381 | La Mancha Storage SLF | SS Completed, FIS Started, No IA | La Mancha Storage, LLC | Tap 69kV 5836 NBatesville - 5822 Leona | Zavala | SOUTH | 2028-10-10 | OTH | BA | 40.9 |  | 2024-11-07 | 2024-11-19 | 2025-02-14 | 2024-11-07 |  |  |  | No
27INR0382 | Calico BESS | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | Tap 138 kV 8723 CANGREJO4A - 8721 BEECHER4A | Victoria | SOUTH | 2028-06-01 | OTH | BA | 204.9 |  | 2024-10-28 | 2025-04-29 | 2025-07-26 | 2025-03-14 |  |  |  | No
27INR0383 | Windjammer Windpower | SS Completed, FIS Completed, No IA | Windjammer Windpower, LLC | tap 345kV 59902 Sand Bluff Wind Farm - 59907 Bernoulli | Glasscock | WEST | 2028-06-01 | WIN | WT | 292.58 |  | 2024-12-20 | 2024-09-10 | 2024-12-06 | 2024-12-12 | 2025-09-30 | Yes |  | No |  |  | Not Required
27INR0384 | Straight Spur Wind | SS Completed, FIS Started, No IA | ENGIE IR Holdings LLC | Tap 345 kV 23876 Clear Fork -11157 Gardenale Switch | Andrews | WEST | 2027-12-01 | WIN | WT | 247.4 |  | 2024-12-06 | 2024-12-19 | 2025-02-03 | 2024-12-06 |  |  |  | No |  |  | Not Required
27INR0385 | Straight Spur Solar | SS Completed, FIS Started, No IA | ENGIE IR Holdings LLC | Tap 345 kV ClearFork (Bus #23876) to Gardenale Switch (Bus #11157) | Andrews | WEST | 2027-12-01 | SOL | PV | 251.8 |  | 2024-10-17 | 2024-11-21 | 2025-02-18 | 2024-11-08 |  |  |  | No |  |  | Not Required
27INR0386 | Straight Spur Storage | SS Completed, FIS Started, No IA | ENGIE IR Holdings LLC | Tap 345kV ClearFork( Bus # 23876) to Gardenale Switch (Bus # 11157) | Andrews | WEST | 2027-12-01 | OTH | BA | 306.2 |  | 2024-11-14 | 2024-11-19 | 2025-02-18 | 2024-11-08 |  |  |  | No
27INR0389 | Sugaree Solar | SS Completed, FIS Started, IA | Sugaree Solar LLC | 138kV Escondido (8260) to Brackettville (8252) | Maverick | SOUTH | 2028-09-21 | SOL | PV | 251.4 |  | 2024-10-08 | 2024-10-10 | 2024-12-09 | 2024-10-08 |  | No | 2025-09-29 | No |  |  | Not Required
27INR0390 | Diamond Sage Solar 1 | SS Completed, FIS Started, No IA | DGC Renewables, LLC | tap 345kV 80219 LOBO7A - 5709 FOWLER TONSW5 CKT2 | Webb | SOUTH | 2028-10-01 | SOL | PV | 213.96 |  | 2024-01-28 | 2025-01-28 | 2025-04-15 | 2025-01-27 |  | Yes |  | No |  |  | Not Required
27INR0392 | Cernan BESS | SS Completed, FIS Started, No IA | Scarlet BESS LLC | Hillje 345kV (#44200) | Wharton | SOUTH | 2027-06-01 | OTH | BA | 301.15 | COD | 2024-12-23 | 2025-02-14 | 2025-04-22 | 2025-01-30 |  |  |  | No
27INR0393 | Ferdinand Grid BESS II | SS Completed, FIS Started, No IA | Coval Infrastructure DevCo LLC | 5260 Leon Creek 138kV | Bexar | SOUTH | 2027-06-08 | OTH | BA | 208.12 |  | 2024-10-14 | 2024-12-19 | 2025-03-04 | 2024-12-03 |  |  |  | No
27INR0395 | Diamond Sage Solar 2 | SS Completed, FIS Started, No IA | DGC Renewables, LLC | Tap 345kV LOBO7A (80219) - FOWLERTONSW5 (5709) | Webb | SOUTH | 2028-10-01 | SOL | PV | 213.96 |  | 2025-01-24 | 2025-01-28 | 2025-04-21 | 2025-01-27 |  | Yes |  | No |  |  | Not Required
27INR0396 | Bluewind BESS | SS Completed, FIS Started, No IA | Bluewind Energy Center, LLC | 5713 Oaks Substation 138kV | Atascosa | SOUTH | 2029-07-02 | OTH | BA | 246.5 |  | 2025-04-22 | 2025-04-25 | 2025-07-22 | 2025-05-15 |  |  |  | No
27INR0397 | Zodiac Storage | SS Completed, FIS Started, No IA | Grenergy USA | Tap 138 kV 8680 RGEC Rough Canyon (ROUGHCAN4A) - 8683 Comstock (COMSTOCK4A) Line | Val Verde | WEST | 2028-08-29 | OTH | BA | 125.58 |  | 2024-11-14 | 2024-11-19 | 2025-02-18 | 2024-11-13 |  | No |  | No
27INR0398 | Bravo BESS | SS Completed, FIS Started, No IA | Bravo BESS LLC | Tap 345kV 80220 CENIZO7A - 80224 TIEMPO7A | Webb | SOUTH | 2027-12-12 | OTH | BA | 207.38 |  | 2024-11-20 | 2024-11-26 | 2025-02-18 | 2024-11-21 |  |  |  | No
27INR0399 | Resaca Oasis Storage | SS Completed, FIS Started, IA | Resaca Oasis Storage, LLC | # 79601 Stillman Substation 138 kV | Cameron | COASTAL | 2027-09-20 | OTH | BA | 200.7 |  | 2024-12-03 | 2024-12-12 | 2025-03-03 | 2024-11-22 |  | No | 2025-05-22 | Yes | Not Required | Not Required | 2025-09-15 | 2025-06-03
27INR0400 | Reforzar BESS 1 | SS Completed, FIS Started, No IA | Tempus Power management LLC | POIB is AEP's new Reforzar 345kV switching station, PSSE bus number 80078 | Brooks | SOUTH | 2028-04-13 | OTH | BA | 207.6 |  | 2024-09-30 | 2024-12-19 | 2025-03-17 | 2024-11-05 |  |  |  | No
27INR0401 | Reforzar Bess 2 | SS Completed, FIS Started, No IA | Tempus Power management LLC | 345 kV 80078 Reforzar | Brooks | SOUTH | 2028-04-13 | OTH | BA | 207.6 |  | 2024-11-14 | 2024-12-19 | 2025-03-17 | 2024-10-10 |  |  |  | No
27INR0409 | Baker Branch BESS | SS Completed, FIS Started, No IA | Mockingbird Storage Center, LLC | Pacific Switch (PACSW) 345 kV Bus 11683 | Lamar | NORTH | 2027-04-01 | OTH | BA | 287.22 |  | 2025-06-13 | 2025-06-19 | 2025-09-11 | 2025-06-10 |  |  |  | No
27INR0412 | Spinosa BESS | SS Completed, FIS Started, No IA | Spinosa Energy Center, LLC | Tap 138 kV 1450 Pleasant Valley Switch - 1499 Parkway | Wichita | WEST | 2028-10-10 | OTH | BA | 201.2 |  | 2025-04-28 | 2025-04-29 | 2025-07-23 | 2025-04-29 |  |  |  | No
27INR0413 | Edgewood BESS 2 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap Edgewood 138kV bus(3181) to 3174 | Van Zandt | NORTH | 2028-03-01 | OTH | BA | 102.1 |  | 2024-10-24 | 2025-01-28 | 2025-04-21 | 2025-01-14 |  |  |  | No
27INR0414 | Diamond Sage BESS 1 | SS Completed, FIS Started, No IA | DGC Renewables, LLC | tap 345kV 80219 LOBO7A - 5709 FOWLERTONSW5 CKT2 | Webb | SOUTH | 2028-10-01 | OTH | BA | 100.14 |  | 2024-01-28 | 2025-01-28 | 2025-04-15 | 2025-01-27 |  | Yes |  | No
27INR0416 | Kresge Land Battery Storage | SS Completed, FIS Started, No IA | Kresge Land Battery Storage LLC | 138 kV Nighthawk Substation (Bus #38985) | Galveston | HOUSTON | 2027-06-01 | OTH | BA | 200 |  | 2025-02-03 | 2025-03-24 | 2025-06-09 | 2025-03-11 |  |  |  | No
27INR0417 | Bluebonnet Trail Solar | SS Completed, FIS Started, No IA | Bluebonnet trail solar LLC | Tap 345 kV (#2427) WATMLL_W5 - (#2466) BIGONION_5 | Ellis | NORTH | 2028-09-19 | SOL | PV | 150.9 |  | 2024-12-18 | 2024-12-19 | 2025-03-17 | 2024-12-13 |  |  |  | No |  |  | Not Required
27INR0418 | Pioneer Path Energy Storage 1 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0421 | M-Bar Solar I | SS Completed, FIS Started, No IA | M-Bar Energy I, LLC | 1141 Holt Switch Substation 138kV | Ector | WEST | 2028-09-18 | SOL | PV | 30.21 |  | 2024-12-13 | 2024-12-19 | 2025-03-17 | 2024-12-13 |  |  |  | No |  |  | Not Required
27INR0422 | M-Bar BESS I | SS Completed, FIS Started, No IA | M-Bar Energy I, LLC | 1141 Holt Switch Substation 138 kV | Ector | WEST | 2028-09-18 | OTH | BA | 82.1 |  | 2024-12-13 | 2024-12-19 | 2025-03-17 | 2024-12-13 |  |  |  | No
27INR0423 | Pioneer Path Energy Storage 2 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0424 | Pioneer Path Energy Storage 3 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0425 | Pioneer Path Energy Storage 4 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0426 | Prairie Horizon Energy Storage 1 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0427 | Prairie Horizon Energy Storage 2 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0428 | Prairie Horizon Energy Storage 3 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0429 | Prairie Horizon Energy Storage 4 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0432 | Coyote Ridge BESS | SS Completed, FIS Started, No IA | Grenergy USA | 292 Holder 138 kV | Brown | NORTH | 2027-10-06 | OTH | BA | 111.06 |  | 2025-01-16 | 2025-01-28 | 2025-04-17 | 2025-01-15 |  |  |  | No
27INR0434 | Lyra Solar | SS Completed, FIS Started, IA | Juno Solar 4 | Tap Long Draw (59900) – Faraday (59905) CKT 1 and LONGDRAW (59900) - GALVANI(59912) CKT 2 | Borden | WEST | 2027-09-15 | SOL | PV | 500 |  | 2025-03-20 | 2025-03-24 | 2025-06-09 | 2025-03-20 |  |  | 2025-07-01 | No |  |  | Not Required
27INR0435 | Clairemont Solar 1 | SS Completed, FIS Started, No IA | Clairemont Solar LLC | 59908 Novaprime 345kV | Kent | WEST | 2028-12-01 | SOL | PV | 251.75 |  | 2025-01-21 | 2025-01-28 | 2025-04-17 | 2025-01-21 |  |  |  | No |  |  | Not Required
27INR0436 | Coati Energy Storage | SS Completed, FIS Started, No IA | PowerPulse LLC | Bus # 40830, Humble, 138 kV | Harris | HOUSTON | 2029-06-15 | OTH | BA | 202.8 |  | 2025-05-28 | 2024-12-19 | 2025-03-17 | 2025-05-21 |  |  |  | No
27INR0437 | Hondo Arroyo Storage | SS Completed, FIS Started, No IA | Hondo Creek Solar, LLC | Tap 138 kV 5225 Hondo - 5813 Pearson | Medina | SOUTH | 2028-07-01 | OTH | BA | 100.7 |  | 2024-11-27 | 2024-12-19 | 2025-03-17 | 2024-12-06 |  |  |  | No | Not Required | Not Required | 2025-09-15
27INR0438 | Wisdom Solar SLF | SS Completed, FIS Started, No IA | Wisdom Green Energy LLC | Tap 138 kV #38455 HOLIDAY SUB TNP - #38450 SOAPTREE TNP | Pecos | WEST | 2027-10-06 | SOL | PV | 299.37 |  | 2025-01-17 | 2025-02-12 | 2025-04-18 | 2025-02-05 |  | No |  | No |  |  | Not Required
27INR0440 | Wisdom BESS SLF | SS Completed, FIS Started, No IA | Wisdom Green Energy LLC | Tap 138 kV #38455 HOLIDAY SUB TNP - 138 kV #38450 SOAPTREE TNP | Pecos | WEST | 2027-10-06 | OTH | BA | 102.88 |  | 2025-01-27 | 2025-02-12 | 2025-04-18 | 2025-02-21 |  | No |  | No
27INR0441 | Pavo Creek Storage | SS Completed, FIS Started, No IA | Pavo Creek Storage, LLC | Tap #3659 Thorndale North - #3701 Rookie Switch 138 kV | Milam | SOUTH | 2028-09-21 | OTH | BA | 154.2 |  | 2025-02-20 | 2025-02-25 | 2025-05-13 | 2025-02-20 |  |  |  | No | Not Required | Not Required | 2025-09-15
27INR0443 | Serenity Wind | SS Completed, FIS Started, No IA | Serenity Wind, LLC | 23931 MIDPOINT SWITCH 345 kV | Armstrong | PANHANDLE | 2028-09-18 | WIN | WT | 473 |  | 2025-03-06 | 2025-03-24 | 2025-06-09 | 2025-03-07 |  |  |  | No |  |  | Not Required
27INR0444 | Diamond Sage BESS 2 | SS Completed, FIS Started, No IA | DGC Renewables, LLC | Tap 345kV LOBO7A (80219) - FOWLERTONSW5 (5709) | Webb | SOUTH | 2028-10-01 | OTH | BA | 100.14 |  | 2025-01-24 | 2025-01-28 | 2025-04-21 | 2025-01-27 |  | Yes |  | No
27INR0445 | Moon Chapel Wind | SS Completed, FIS Started, No IA | Orsted Onshore Development North America, LLC | Tap 345kV 76090 Divide - 76009 Twin Buttes Ckt 1 and 2 | Tom Green | WEST | 2028-12-30 | WIN | WT | 506.8 |  | 2025-02-07 | 2025-02-14 | 2025-05-12 | 2025-02-07 |  |  |  | No |  |  | Not Required
27INR0447 | Clairemont BESS | SS Completed, FIS Started, No IA | Clairemont BESS LLC | 59908 Novaprime 345kV | Kent | WEST | 2028-12-01 | OTH | BA | 259.36 |  | 2025-01-21 | 2025-01-28 | 2025-04-17 | 2025-01-21 |  |  |  | No
27INR0449 | Gulf Prairie Solar | SS Completed, FIS Started, No IA | Gulf Prairie Energy LLC | #43150 Riwood [Substation Expansion] 138kV | Brazoria | COASTAL | 2028-12-01 | SOL | PV | 202.17 |  | 2025-05-29 | 2025-06-19 | 2025-09-16 | 2025-01-22 |  |  |  | No |  |  | Not Required
27INR0451 | Dairyland Storage | SS Completed, FIS Started, No IA | ENGIE IR Holdings LLC | To 345 kV Birthright Station (#11684) | Hopkins | NORTH | 2029-04-30 | OTH | BA | 301.8 |  | 2025-04-07 | 2025-04-21 | 2025-07-18 | 2025-02-04 |  |  |  | No
27INR0452 | Moccasin Storage | SS Completed, FIS Started, No IA | ENGIE IR Holdings LLC | Tap 345kV #60707 Kirchhoff - #60515 Clear Crossing CKT-2 | Jones | WEST | 2028-07-01 | OTH | BA | 603.08 | COD | 2025-01-14 | 2025-01-28 | 2025-04-17 | 2025-01-15 |  |  |  | No
27INR0453 | Roboman Solar | SS Completed, FIS Started, No IA | Roboman Solar, LLC | Tap 345 kV (#76009) Twin Buttes – (#76090) Divide Ckt 1 | Coke | WEST | 2029-07-01 | SOL | PV | 272.6 | COD | 2025-06-26 | 2025-07-07 | 2025-09-30 | 2025-06-26 |  |  |  | No | Not Required | Not Required | Not Required
27INR0455 | Yellow Leaf Solar | SS Completed, FIS Started, No IA | Lightsource Renewable Energy Development LLC | Tap 138kV #2727 Crandall - #12715 Forney S | Kaufman | NORTH | 2027-05-10 | SOL | PV | 104.5 |  | 2025-04-24 | 2025-04-25 | 2025-07-22 | 2025-03-14 |  |  |  | No |  |  | Not Required
27INR0456 | Yellow Leaf BESS | SS Completed, FIS Started, No IA | Lightsource Renewable Energy Development LLC | Tap 138kV #2727 Crandall - #12715 Forney S | Kaufman | NORTH | 2027-05-10 | OTH | BA | 103.8 |  | 2025-04-24 | 2025-04-25 | 2025-07-22 | 2025-03-14 |  |  |  | No
27INR0457 | watermelon 1 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2024-12-13 | 2025-01-13 | 2025-04-08 | 2025-01-06 |  |  |  | No | Not Required | Not Required
27INR0458 | watermelon 2 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2024-12-16 | 2025-01-13 | 2025-04-08 | 2025-01-06 |  |  |  | No | Not Required | Not Required
27INR0459 | watermelon 3 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. 1.6 miles from 2427 WATMLL_W5 | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2024-12-16 | 2025-01-13 | 2025-04-08 | 2025-01-06 |  |  |  | No | Not Required | Not Required
27INR0460 | watermelon 4 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2024-12-16 | 2025-01-13 | 2025-04-08 | 2025-01-06 |  |  |  | No | Not Required | Not Required
27INR0461 | Fermata BESS | SS Completed, FIS Started, No IA | Fermata BESS, LLC | Tap 345kV 2464# CASHSW_T5 – 2461# ROYSE_N5 | Hunt | NORTH | 2028-07-01 | OTH | BA | 204 |  | 2025-02-20 | 2025-02-25 | 2025-05-20 | 2025-02-21 |  |  |  | No
27INR0465 | Althea Storage | SS Completed, FIS Started, IA | Sugaree Solar LLC | Tap Escondido (8260) - Brackettville (8252) | Maverick | SOUTH | 2028-09-21 | OTH | BA | 251.3 |  | 2025-01-13 | 2025-02-12 | 2025-04-22 | 2024-12-30 |  |  | 2025-09-29 | No
27INR0466 | Wolfram Storage | SS Completed, FIS Started, No IA | Nova Clean Energy, LLC | 8189 Tungsten 138 kV | Calhoun | COASTAL | 2027-12-01 | OTH | BA | 205.4 |  | 2025-04-04 | 2025-05-19 | 2025-08-15 | 2025-05-02 |  |  |  | No
27INR0469 | Kickstart Energy Storage I | SS Completed, FIS Started, No IA | Kickstart Infrastructure LLC | Tap 345 kV 1907 Venus Switch - 3383 BYNUM_5 | Ellis | NORTH | 2029-09-30 | OTH | BA | 1.44 | COD | 2025-03-06 | 2025-03-24 | 2025-06-09 | 2025-03-12 |  |  |  | No
27INR0470 | Kickstart Energy Storage II | SS Completed, FIS Started, No IA | Kickstart Infrastructure LLC | Tap 345 kV 1907 Venus Switch - 3383 BYNUM_5 | Ellis | NORTH | 2029-09-30 | OTH | BA | 1.44 | COD | 2025-03-06 | 2025-03-24 | 2025-06-09 | 2025-03-12 |  |  |  | No
27INR0471 | Kickstart Energy Storage III | SS Completed, FIS Started, No IA | Kickstart Infrastructure LLC | Tap 345 kV #1906 VENUS_S5 to #68091 NAVARRO | Ellis | NORTH | 2029-09-30 | OTH | BA | 1.44 | COD | 2025-03-06 | 2025-03-24 | 2025-06-09 | 2025-03-10 |  |  |  | No
27INR0472 | Kickstart Energy Storage IV | SS Completed, FIS Started, No IA | Kickstart Infrastructure LLC | Tap 345 kV #1906 VENUS_S5 to #68091 NAVARRO | Ellis | NORTH | 2029-09-30 | OTH | BA | 1.44 | COD | 2025-03-06 | 2025-03-24 | 2025-06-09 | 2025-03-10 |  |  |  | No
27INR0474 | Fivemile Wind | SS Completed, FIS Started, No IA | Longview Wind, LLC | To 138 kV Hardy Morgan substation (Bus # 11363) | Dawson | WEST | 2028-11-01 | WIN | WT | 282.3 |  | 2025-04-25 | 2025-04-25 | 2025-07-22 | 2025-04-25 |  |  |  | No |  |  | Not Required
27INR0478 | Metro BESS | SS Completed, FIS Started, No IA | Metro BESS LLC | #9074 LYTTON5 345kv | Caldwell | SOUTH | 2030-12-07 | OTH | BA | 207.17 |  | 2025-02-22 | 2025-02-25 | 2025-05-20 | 2025-02-24 |  |  |  | No
27INR0480 | Borden Dino Solar | SS Completed, FIS Started, No IA | Borden Dino Solar, LLC | 59905 FARADAY 345KV | Borden | WEST | 2028-07-01 | SOL | PV | 120.47 |  | 2025-03-06 | 2025-04-01 | 2025-06-09 | 2025-03-06 |  |  |  | No |  |  | Not Required
27INR0481 | Borden Dino BESS | SS Completed, FIS Started, No IA | Borden Dino Solar, LLC | 59905 FARADAY 345KV | Borden | WEST | 2028-07-01 | OTH | BA | 60.26 |  | 2025-03-06 | 2025-04-01 | 2025-06-09 | 2025-03-06 |  |  |  | No
27INR0485 | Blackland Prairie 1 Energy Storage | SS Completed, FIS Started, No IA | Tempus power management LLC | 9328 Austrop 138kV | Travis | SOUTH | 2027-12-01 | OTH | BA | 102.1 |  | 2025-02-24 | 2025-03-24 | 2025-06-09 | 2025-02-24 |  |  |  | No
27INR0486 | Blackland Prairie 2 Energy Storage | SS Completed, FIS Started, No IA | Tempus power management LLC | 9328 Austrop 138kV | Travis | SOUTH | 2027-12-01 | OTH | BA | 102.1 |  | 2025-02-24 | 2025-03-24 | 2025-06-09 | 2025-02-24 |  |  |  | No
27INR0487 | Blackland Prairie 3 Energy Storage | SS Completed, FIS Started, No IA | Tempus power management LLC | 9328 Austrop 138kV | Travis | SOUTH | 2027-12-01 | OTH | BA | 102.1 |  | 2025-02-24 | 2025-03-24 | 2025-06-09 | 2025-02-24 |  |  |  | No
27INR0488 | Dry Creek Solar II | SS Completed, FIS Started, No IA | Oak Hill Solar II LLC | Dorsett 345 kV Switching Station(tap 345 kV 3100 Martin Lake - 3105 Elkton) | Rusk | NORTH | 2028-06-30 | SOL | PV | 302.64 |  | 2025-06-02 | 2025-06-19 | 2025-09-16 | 2025-06-02 |  |  |  | No |  |  | Not Required
27INR0489 | Power Lane II Gas | SS Completed, FIS Started, No IA | GEUS | Tap 138kV Caddo Mills Explorer (11832) – Scatter Branch Sub (1818) Line via (future) GEUS_STM Substation | Hunt | NORTH | 2027-06-01 | GAS | IC | 104.39 |  | 2025-05-07 | 2025-06-03 | 2025-08-29 | 2025-05-28 |  |  |  | No
27INR0492 | Gulf Gateway Solar One | SS Completed, FIS Started, No IA | Gulf Gateway Solar, LLC | 88249 SDI7A 345kV | San Patricio | COASTAL | 2027-06-24 | SOL | PV | 301.4 |  | 2025-04-03 | 2025-04-21 | 2025-07-19 | 2025-04-03 |  |  |  | No |  |  | Not Required
27INR0493 | Velociraptor BESS I | SS Completed, FIS Started, No IA | Greyhound BESS 2 LLC | 10012 METEOR_5 Substation 345kV | Ector | WEST | 2028-11-17 | OTH | BA | 261.12 |  | 2025-05-15 | 2025-05-27 | 2025-08-23 | 2025-05-07 |  |  |  | No
27INR0494 | Obbligato BESS | SS Completed, FIS Started, No IA | Obbligato BESS, LLC | Tap 138kV 120# TALBRTRIDG – 3683# MINERVA1_8 | Milam | SOUTH | 2029-02-28 | OTH | BA | 200.71 |  | 2025-06-06 | 2025-06-19 | 2025-09-10 | 2025-06-09 |  |  |  | No
27INR0497 | Black Mountain Somervell Gas Combined | SS Completed, FIS Started, No IA | Fort Worth Power Core LLC | Tap Comanche Peak SES Substation (#1900) to Johnson Switch (#1902) 345kV Line | Somervell | NORTH | 2029-09-28 | GAS | CC | 495.3 |  | 2025-04-11 | 2025-04-21 | 2025-07-19 | 2025-04-16 |  |  |  | No
27INR0499 | Draco Solar | SS Completed, FIS Started, No IA | Draco Solar LLC | Tap Long Draw (59900) – Faraday (59905) CKT 1 and LONGDRAW (59900) - GALVANI(59912) CKT 2 | Borden | WEST | 2027-08-19 | SOL | PV | 500 |  | 2025-03-31 | 2025-04-21 | 2025-07-19 | 2025-04-01 |  |  |  | No |  |  | Not Required
27INR0500 | Antila Solar | SS Completed, FIS Started, IA | Antila Solar LLC | #59916 Buck Canyon 345kV | Borden | WEST | 2027-11-30 | SOL | PV | 500 |  | 2025-04-01 | 2025-04-21 | 2025-07-19 | 2025-04-02 |  |  | 2025-08-13 | No |  |  | Not Required
27INR0501 | Mesquite Creek Windpower Repower | SS Completed, FIS Started, No IA | Mesquite Creek Wind LLC | <59900><Long Draw><345> | Dawson | WEST | 2027-12-31 | WIN | WT | 212.91 |  | 2025-04-28 | 2025-04-29 | 2025-07-26 | 2025-04-28 |  |  |  | No |  |  | Not Required
27INR0503 | Dog Star Solar I | SS Completed, FIS Started, No IA | Dog Star Solar LLC | 6235 ABILENE MULBERRY CREEK 345 kV | Taylor | WEST | 2027-03-01 | SOL | PV | 502.6 |  | 2025-06-25 | 2025-07-07 | 2025-09-16 | 2025-06-20 |  |  |  | No |  |  | Not Required
27INR0504 | Dog Star Solar II | SS Completed, FIS Started, No IA | Dog Star Solar LLC | 6235 ABILENE MULBERRY CREEK 345 kV | Taylor | WEST | 2027-12-31 | SOL | PV | 502.6 |  | 2025-06-25 | 2025-07-02 | 2025-09-19 | 2025-06-20 |  |  |  | No |  |  | Not Required
27INR0510 | Pecos Wind | SS Completed, FIS Started, No IA | Midnight Energy Center, LLC | Tap 345 kV 60404 Solstice (SOLSTICE7A) – 76002 Bakersfield (L_BAKERS5_1Y) CKT 2 | Pecos | WEST | 2027-03-28 | WIN | WT | 191 | MW Size | 2025-07-23 | 2025-07-07 | 2025-09-30 |  |  |  |  | No |  |  | Not Required
27INR0512 | Silver Hills Windpower | SS Completed, FIS Started, No IA | Silver Hills Windpower, LLC | 10066 Prong Moss Switch 138kV | Howard | WEST | 2029-06-01 | WIN | WT | 54.05 |  | 2025-07-07 | 2025-04-21 | 2025-07-19 |  |  |  |  | No |  |  | Not Required
27INR0515 | Paolo Sole Gustine Solar | SS Completed, FIS Started, No IA | Viridian Power Development, LLC | #273 Gustine 69 kV | Comanche | NORTH | 2028-07-11 | SOL | PV | 40.34 |  | 2025-05-12 | 2025-05-27 | 2025-08-23 | 2025-05-22 |  |  |  | No |  |  | Not Required
27INR0516 | Paolo Sole Hamilton Solar | SS Completed, FIS Started, No IA | Viridian Power Development, LLC | #258 Hamilton 69 kV | Hamilton | NORTH | 2028-07-11 | SOL | PV | 40.63 |  | 2025-05-12 | 2025-05-27 | 2025-08-23 | 2025-05-22 |  |  |  | No |  |  | Not Required
27INR0519 | Wagyu BESS SLF | SS Completed, FIS Started, No IA | Wagyu BESS, LLC | 42410 Burke_POI_8 138kV | Brazoria | COASTAL | 2026-12-31 | OTH | BA | 120.55 |  | 2025-06-18 | 2025-06-19 | 2025-09-17 | 2025-06-18 |  |  |  | No
27INR0524 | Portland Storage SLF | SS Started, FIS Started, No IA | Convergent Energy Solutions LLC | 8566 HOT IRON 4A 138 kV 8569 HOT IRON 4B 138 kV (2) POIs will be used for this project because there are (2) 138 kV lines supplying the ArcelorMittal plant. Project physical connection will be 13.8 kV bus at ArcelorMittal. | San Patricio | COASTAL | 2028-01-03 | OTH | BA | 0 |  | 2025-06-30 | 2025-07-29 |  | 2025-07-18 |  |  |  | No
27INR0529 | Zeus Scurry Solar | SS Completed, FIS Started, No IA | Scurry Solar, LLC | MHOS 345 kV Substation (#59911) | Scurry | WEST | 2028-10-01 | SOL | PV | 503.54 |  | 2025-05-28 | 2025-06-03 | 2025-08-29 | 2025-05-29 |  |  |  | No |  |  | Not Required
27INR0531 | Erika BESS | SS Completed, FIS Started, No IA | Erika Solar, LLC | Tap 345kV ELKTON 5 (#3105 ) to Tricrn1 5 (#2432) | Kaufman | NORTH | 2029-07-01 | OTH | BA | 100 |  | 2025-06-11 | 2025-06-19 | 2025-09-17 | 2025-06-06 |  |  |  | No
27INR0535 | Zeus Scurry BESS | SS Completed, FIS Started, No IA | Zeus Scurry BESS | MHOS 345 kV Substation (#59911) | Scurry | WEST | 2028-10-01 | OTH | BA | 1043.07 |  | 2025-06-02 | 2025-06-05 | 2025-08-29 | 2025-06-04 |  |  |  | No
27INR0536 | Siete Wind | SS Completed, FIS Started, No IA | Siete Wind, LLC | 345kV 8718 Triada | Webb | SOUTH | 2028-01-03 | WIN | WT | 492.8 | COD | 2025-06-12 | 2025-07-07 | 2025-09-25 | 2025-06-24 |  |  |  | No |  |  | Not Required
27INR0554 | Texas Sun Solar | SS Started, FIS Started, No IA | Pigg Grounds LLC | Cordele Substation ; Bus no. 5524 | Jackson | SOUTH | 2027-12-18 | SOL | PV | 71.7 | FIS Request | 2025-08-26 | 2025-09-22 |  | 2025-09-01 |  |  |  | No |  |  | Not Required
27INR0555 | Montezuma Storage | SS Started, FIS Started, No IA | Montezuma Storage LLC | L_GLIDDE8_1Y; Bus number - 7258 138KV | Colorado | SOUTH | 2027-09-30 | MWH | SO | 185.1 | FIS Request | 2025-09-15 | 2025-09-22 |  | 2025-09-04 |  |  |  | No
27INR0556 | Gulf Gateway Storage One | SS Started, FIS Started, No IA | Gulf Gateway Storage, LLC | 88249 SDI7A 345kV | San Patricio | COASTAL | 2027-06-24 | OTH | BA | 301.4 |  | 2025-08-25 | 2025-08-26 |  | 2025-08-21 |  |  |  | No
27INR0562 | Frizzle BESS | SS Started, FIS Started, No IA | Frizzle BESS, L.L.C. | #38143, TNSLVRLEAF1, 138kV | Reeves | WEST | 2027-10-18 | OTH | BA | 180 | FIS Request | 2025-09-10 | 2025-09-11 |  | 2025-09-10 |  |  |  | No
27INR0569 | Gardner Draw 2 Solar | SS Started, FIS Started, No IA | RWE Solar Development, LLC | 59902 Sand Bluff 345 kV | Glasscock | WEST | 2027-12-31 | SOL | PV | 100 | FIS Request | 2025-09-15 | 2025-09-22 |  | 2025-09-05 |  |  |  | No |  |  | Not Required
28INR0005 | Tetris Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings LLC | TAP 345kV 80307 Del Sol 7C - 80225 Cenizo 7C | Zapata | SOUTH | 2029-07-01 | SOL | PV | 359 |  | 2023-06-15 | 2023-07-28 | 2023-10-23 | 2023-07-21 |  |  |  | No |  |  | Not Required
28INR0008 | Oriole Solar | SS Completed, FIS Started, No IA | Rolling Plains Solar | Tap 345kV 6076 Foxtail - 60791 Perigee | Knox | WEST | 2028-12-29 | SOL | PV | 503.91 |  | 2023-05-03 | 2023-05-15 | 2023-08-11 | 2023-05-09 |  |  |  | No |  |  | Not Required
28INR0009 | Oriole BES | SS Completed, FIS Started, No IA | Rolling Plains Solar | Tap 345kV 6076 Foxtail - 60791 Perigee | Knox | WEST | 2028-12-29 | OTH | BA | 150.39 |  | 2023-04-28 | 2023-05-15 | 2023-08-11 | 2023-05-09 |  |  |  | No
28INR0013 | Varadero Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | #68092 Liberty Station 345kV | Limestone | NORTH | 2029-04-01 | SOL | PV | 304.74 |  | 2023-06-26 | 2023-07-10 | 2023-10-03 | 2023-07-05 |  |  |  | No |  |  | Not Required
28INR0017 | Sitges Wind | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap 345kV 59904 Cottonwood to 23922 White River Ckt 2 | Motley | PANHANDLE | 2029-01-30 | WIN | WT | 600 |  | 2024-02-29 | 2024-03-22 | 2024-06-19 | 2024-02-29 |  |  |  | No |  |  | Not Required
28INR0020 | Caracara Energy Storage Center | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | Tap 138kV 5055 Cagnon - 5346 Potranco | Bexar | SOUTH | 2028-08-01 | OTH | BA | 203 |  | 2024-08-19 | 2024-05-09 | 2024-08-05 | 2024-08-05 17:56 |  |  |  | No
28INR0023 | Silverton Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap 345kV 23914 Tule Canyon - 79001 Cross_W1 | Briscoe | PANHANDLE | 2029-07-01 | SOL | PV | 410 |  | 2024-04-01 | 2023-12-04 | 2024-03-01 | 2024-03-18 21:54 |  |  |  | No |  |  | Not Required
28INR0024 | Padua Grid BESS Unit 3 | SS Completed, FIS Completed, IA | Padua Grid 3, LLC | Tap #5395 O.W Sommer 138kV | Bexar | SOUTH | 2026-05-15 | OTH | BA | 201.35 |  | 2024-03-14 | 2024-03-22 | 2024-06-19 | 2024-03-01 | 2025-06-20 | No | 2025-03-07 | Yes | Not Required | Not Required |  | 2025-06-20 | 2025-07-17 | 2025-07-17
28INR0029 | Old Fiddler Energy Storage | SS Completed, FIS Started, No IA | Old Fiddler Energy Storage LLC | A direct connection to the 138 kV Bus (Bus #3238) in the Oncor owned - Athens 138/XX kV Substation | Henderson | NORTH | 2029-04-16 | OTH | BA | 224.08 |  | 2025-06-19 | 2024-01-11 | 2024-04-08 |  |  |  |  | No
28INR0030 | Brela BESS LLC | SS Completed, FIS Started, No IA | Brela BESS LLC | 44040 Bailey SW 345 kV | Wharton | SOUTH | 2028-05-29 | OTH | BA | 251.3 |  | 2024-06-26 | 2024-01-11 | 2024-04-08 | 2024-06-13 08:58 |  |  |  | No
28INR0037 | Bullring Wind 1 | SS Completed, FIS Started, No IA | ACE DevCo NC LLC | Tap 345 kV 80355 DelSol7A - 80079 Cruce Ckt 1 | Starr | SOUTH | 2028-06-30 | WIN | WT | 303.5 |  | 2024-03-21 | 2024-05-09 | 2024-08-05 | 2024-04-30 |  | Yes |  | No |  |  | Not Required
28INR0038 | Bullring Wind 2 | SS Completed, FIS Started, No IA | ACE DevCo NC LLC | Tap 345 kV 80355 DelSol7A - 80079 Cruce Ckt 1 | Starr | SOUTH | 2028-06-30 | WIN | WT | 303.8 |  | 2025-02-19 | 2024-05-09 | 2024-08-05 | 2024-04-30 |  | Yes |  | No |  |  | Not Required
28INR0039 | Bullring Wind 3 | SS Completed, FIS Started, No IA | ACE DevCo NC LLC | Tap 345 kV 80355 DelSol7A - 80079 Cruce Ckt 1 | Starr | SOUTH | 2028-06-30 | WIN | WT | 190.4 |  | 2025-02-19 | 2024-05-09 | 2024-08-05 | 2024-04-29 |  | Yes |  | No |  |  | Not Required
28INR0040 | Black Hawk Solar | SS Completed, FIS Started, No IA | ACE DevCo NC, LLC | San Miguel (5901) - Cruce (80079) double circuit transmission line. Requesting interconnection to both lines on the double circuit. This is a planned double circuit with ISD of 2027. | Duval | SOUTH | 2028-12-31 | SOL | PV | 251.34 |  | 2024-11-26 | 2024-02-27 | 2024-05-24 | 2024-11-21 |  |  |  | No |  |  | Not Required
28INR0043 | Muy Grande Solar | SS Completed, FIS Started, No IA | ACE DevCo NC, LLC | Tap 345kV 80079 Cruce - 80355 Del Sol | Starr | SOUTH | 2028-05-15 | SOL | PV | 502.69 |  | 2025-07-22 | 2024-01-11 | 2024-04-09 |  |  |  |  | No |  |  | Not Required
28INR0048 | Findley BESS | SS Completed, FIS Started, No IA | Gransolar Texas Sixteen, LLC | #107 Prairie Hill 69 kV | Limestone | NORTH | 2028-01-01 | OTH | BA | 51.74 |  | 2023-12-23 | 2024-02-07 | 2024-04-30 | 2024-01-16 |  |  |  | No | Not Required | Not Required
28INR0055 | Freestone Battery Storage Project | SS Completed, FIS Started, No IA | Freestone Power Generation, LLC | 3134 RICHLAND CHAMBERS 345kV (PSS/E Bus Name: RICHLND1_5) | Freestone | NORTH | 2028-12-16 | OTH | BA | 210.5 |  | 2025-01-24 | 2024-02-07 | 2024-04-30 | 2025-01-17 22:00 |  |  |  | No
28INR0057 | Windecker | SS Completed, FIS Started, No IA | Windecker Energy LLC | 10058 Catclaw Switch 138kV | Upton | WEST | 2028-04-17 | WIN | WT | 419.7 |  | 2024-03-13 | 2024-03-29 | 2024-06-19 | 2024-03-14 |  |  |  | No |  |  | Not Required
28INR0059 | Verily Solar (FKA Cuello De Cuero Solar) | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | 80078 Reforzar Switch Station 345kV | Brooks | SOUTH | 2029-07-01 | SOL | PV | 261 |  | 2024-02-29 | 2024-03-22 | 2024-06-19 | 2024-03-06 |  |  |  | No |  |  | Not Required
28INR0061 | Sunrose Renewable Energy Solar SLF | SS Completed, FIS Completed, No IA | Sunrose Renewable Energy LLC | Tap 138kV #44740 WALLIS - #44700 GEBHRT | Austin | SOUTH | 2027-12-31 | SOL | PV | 300.88 |  | 2024-04-05 | 2024-04-09 | 2024-07-05 | 2024-03-29 | 2025-09-11 | No |  | No |  |  | Not Required
28INR0063 | Bluefox Solar 2 | SS Completed, FIS Started, No IA | Industrial November Project LLC | #8754 Zoisite 345kV | Matagorda | COASTAL | 2030-01-17 | SOL | PV | 401.8 |  | 2024-03-12 | 2024-03-22 | 2024-06-19 | 2024-02-21 |  |  |  | No |  |  | Not Required
28INR0064 | Bluefox Solar 3 | SS Completed, FIS Started, No IA | Industrial November Project LLC | #8754 Zoisite 345kV | Matagorda | COASTAL | 2030-04-18 | SOL | PV | 201.8 |  | 2024-03-12 | 2024-03-22 | 2024-06-19 | 2024-02-21 |  |  |  | No |  |  | Not Required
28INR0066 | Sunrose Renewable Energy Storage SLF | SS Completed, FIS Completed, No IA | Sunrose Renewable Energy LLC | Tap 138kV 44740 WALLIS - 44700 GEBHRT | Austin | SOUTH | 2027-12-31 | OTH | BA | 0 |  | 2024-03-19 | 2024-04-15 | 2024-07-05 | 2024-04-12 | 2025-09-11 | No |  | No
28INR0067 | Indigo Solar 3 | SS Completed, FIS Started, No IA | Indigo solar 3 | Tap Line Segment Tankawa (Bus #1048) to Graham (Bus #1430) | Fisher | WEST | 2028-11-01 | SOL | PV | 800 |  |  | 2024-10-29 | 2025-01-25 | 2025-07-15 |  |  |  | No |  |  | Not Required
28INR0068 | Alpujarra Solar | SS Completed, FIS Started, No IA | Greening USA Corp. | 5521 GALOW 138 KV | Wharton | SOUTH | 2028-05-01 | SOL | PV | 112.5 |  | 2024-08-23 | 2024-09-04 | 2024-11-27 | 2024-08-12 |  |  |  | No |  |  | Not Required
28INR0072 | Mirando Valley Wind | SS Completed, FIS Started, No IA | ACE DevCo NC LLC | Tap 345kV 80220 Cenizo - 80079 Cruce Ckt-1 | Jim Hogg | SOUTH | 2028-07-06 | WIN | WT | 478.74 |  | 2024-06-12 | 2024-08-16 | 2024-11-12 | 2024-06-05 |  |  |  | No |  |  | Not Required
28INR0073 | Daystar Solar | SS Completed, FIS Started, No IA | Choate Solar, LLC | 5728 Choate 138kV | Karnes | SOUTH | 2028-03-15 | SOL | PV | 150 |  | 2024-04-09 | 2024-04-15 | 2024-07-05 | 2024-04-09 |  |  |  | No |  |  | Not Required
28INR0074 | Massey Storage | SS Completed, FIS Started, No IA | Massey Storage, LLC | Tap 138kV Chevron_NewSub(#99300) and Cedar Bayou Tap(#48065) circuit 84 | Harris | HOUSTON | 2028-01-03 | OTH | BA | 102.86 |  | 2024-07-23 | 2024-07-30 | 2024-10-25 | 2024-07-23 |  |  |  | No
28INR0075 | Wild Paw Storage | SS Completed, FIS Started, No IA | Wild Paw Energy Center, LLC | Tap 345kV 3124 Trinidad - 3130 Forest Grove | Henderson | NORTH | 2028-09-30 | OTH | BA | 313.2 |  | 2024-05-07 | 2024-05-09 | 2024-08-05 | 2024-05-07 |  |  |  | No
28INR0080 | Turtle Rock Storage | SS Completed, FIS Started, No IA | Turtle Rock Energy Center, LLC | Tap 138 kV 13501 Clayhill to 13681 Reed | Freestone | NORTH | 2028-07-02 | OTH | BA | 135.59 |  | 2024-05-07 | 2024-05-09 | 2024-08-05 | 2024-05-08 |  |  |  | No
28INR0086 | West Royal Natural Gas (TEF-Due Diligence) | SS Completed, FIS Started, No IA | Invenergy Energy Transition Development LLC | 76000 L_NORTMC5_1Y 345kV | Upton | WEST | 2030-06-01 | GAS | GT | 888 |  | 2025-01-13 | 2024-06-13 | 2024-09-10 | 2024-12-17 |  |  |  | No
28INR0087 | North Royal Thermal (TEF- Due Diligence) | SS Completed, FIS Started, No IA | Invenergy Energy Transition Development LLC | Tap 345kV 1695 MOSES_5 - 11699 WOODARD_5 | Lamar | NORTH | 2030-08-01 | GAS | GT | 479 |  | 2025-02-05 | 2024-06-13 | 2024-09-10 | 2024-12-17 |  |  |  | No
28INR0088 | Red Hollow Renewable Energy Solar SLF | SS Completed, FIS Started, No IA | Red Hollow Renewable Energy LLC | Tap 345kV (Bus# 1422) Bowman - (Bus# 17002) Garvey Road | Archer | WEST | 2028-04-10 | SOL | PV | 308.6 |  | 2024-06-04 | 2024-07-01 | 2024-10-04 | 2024-06-04 |  |  |  | No |  |  | Not Required
28INR0089 | EmberYork | SS Completed, FIS Completed, No IA | EmberYork Energy Center | TAP 138kV WALLIS 44740 - GERBHRT 44700 | Austin | SOUTH | 2028-01-01 | GAS | GT | 900 |  | 2024-12-30 | 2024-08-29 | 2024-08-29 | 2024-12-11 | 2025-07-14 | Yes |  | No
28INR0090 | EmberGreen | SS Completed, FIS Started, No IA | EmberGreen Energy Center | Tap 138kV 48050 Caney - 44150 Hungerford | Wharton | SOUTH | 2028-01-01 | GAS | GT | 1036 |  | 2024-06-28 | 2024-06-13 | 2024-09-10 | 2024-12-18 |  |  |  | No
28INR0094 | Pham BESS | SS Completed, FIS Started, No IA | ASB1, LLC | Tap 138kV 3281 TENNCLNY_8 - 3284 BETO_8 | Anderson | NORTH | 2028-04-17 | OTH | BA | 132.98 |  | 2024-08-30 | 2024-06-13 | 2024-09-10 |  |  |  |  | No
28INR0095 | Starlit Pasture Storage | SS Completed, FIS Started, No IA | Starlit Pasture Energy Center, LLC | 7574 Chappell Hill 138 KV | Washington | SOUTH | 2029-09-30 | OTH | BA | 208.8 |  | 2024-06-23 | 2024-08-16 | 2024-11-12 | 2024-06-24 |  |  |  | No
28INR0097 | Catamount Storage | SS Completed, FIS Started, No IA | TOCE TX BESS 3, LLC | Tap 345kV 46100 North Belt - 40850 Jordan CKT 99 | Harris | HOUSTON | 2028-06-01 | OTH | BA | 515.44 |  | 2024-08-26 | 2024-09-04 | 2024-11-27 | 2024-08-21 |  | Yes |  | No
28INR0101 | Vazlon Solar SLF | SS Completed, FIS Started, No IA | Vazlon Energy LLC | 8619 Encinal - 8627 Lemay Box Bay 138kV line | La Salle | SOUTH | 2028-06-30 | SOL | PV | 211.41 |  | 2024-08-07 | 2024-10-01 | 2024-12-16 | 2024-09-06 |  | No |  | No |  |  | Not Required
28INR0104 | Vazlon BESS SLF | SS Completed, FIS Started, No IA | Vazlon Energy LLC | 8619 Encinal - 8627 Lemay Box Bay 138kV line | La Salle | SOUTH | 2028-06-30 | OTH | BA | 0 |  | 2024-08-07 | 2024-10-01 | 2024-12-16 | 2024-09-06 |  | No |  | No
28INR0105 | Vast Sands Power I (TEF -Due Diligence) | SS Completed, FIS Started, No IA | Permian Power I LLC | Tap 345kV 11010 Wolf Switch - 11188 Quarry Field Switch Ckt 2 | Ward | WEST | 2027-12-01 | GAS | GT | 440 |  | 2024-07-05 | 2024-07-22 | 2024-10-08 | 2024-07-05 |  |  |  | No
28INR0108 | RAYBURN ENERGY STATION II Gas (TEF-Due Diligence) | SS Completed, FIS Started, No IA | Rayburn Energy Station LLC | Double Tap 138 kV Haggerty (12677) - Progress Park (#12678) & Haggerty - Winding Oaks Switch | Grayson | NORTH | 2028-02-26 | GAS | GT | 570 |  | 2025-01-02 | 2025-01-13 | 2025-04-08 | 2025-01-02 |  |  |  | No
28INR0109 | Vast Sands Power II (TEF-Due Diligence) | SS Completed, FIS Started, No IA | Permian Power I LLC | Tap 345kV 11010 Wolf Switch - 11188 Quarry Field Switch Ckt 2 | Ward | WEST | 2028-02-01 | GAS | GT | 440 |  | 2024-07-05 | 2024-07-22 | 2024-10-08 | 2024-07-03 |  |  |  | No
28INR0110 | Biggs BESS | SS Completed, FIS Started, No IA | Biggs Battery Facility, LLC | 76006 Bow Wood 345 kV | McCulloch | SOUTH | 2028-11-15 | OTH | BA | 200 |  | 2025-04-28 | 2024-07-22 | 2024-10-18 | 2025-04-21 |  |  |  | No
28INR0111 | Biggs Solar | SS Completed, FIS Started, No IA | Biggs Solar Farm, LLC | #76006 Bow Wood 345 kV | McCulloch | SOUTH | 2028-11-15 | SOL | PV | 400 |  | 2025-04-28 | 2024-07-22 | 2024-10-18 | 2025-04-21 |  |  |  | No |  |  | Not Required
28INR0113 | Axis Ridge Wind | SS Completed, FIS Started, No IA | Axis Ridge Wind, LLC | Tap 345kV 60709 Oersted - 60616 Edison | Sutton | WEST | 2029-07-01 | WIN | WT | 750.05 |  | 2024-11-12 | 2024-11-19 | 2025-02-03 | 2024-11-07 |  |  |  | No |  |  | Not Required
28INR0114 | Elk Ridge Solar | SS Started, FIS Started, No IA | Boulevard Associates, LLC | AEP Solstice Substation #60384 | Pecos | WEST | 2030-07-01 | SOL | PV | 500 | FIS Request | 2025-09-26 |  |  | 2025-09-26 |  |  |  | No |  |  | Not Required
28INR0116 | Salazar BESS | SS Completed, FIS Started, No IA | Salazar Energy Storage LLC | 2068 Rosen Heights 138kV | Tarrant | NORTH | 2028-07-11 | OTH | BA | 127.82 |  | 2024-09-10 | 2024-10-01 | 2024-12-09 | 2024-08-27 |  |  |  | No
28INR0118 | Copperleaf Energy Storage | SS Completed, FIS Started, No IA | Copperleaf Energy Storage, LLC | Tap 345kV Fisher Road Switch (#1425) – Riley (#6101) | Wichita | WEST | 2029-04-18 | OTH | BA | 306.53 |  | 2024-11-04 | 2024-11-19 | 2025-02-18 | 2024-10-16 |  |  |  | No
28INR0119 | Rabbit Hollow Energy Storage | SS Completed, FIS Started, No IA | Rabbit Hollow Energy Storage, LLC | 1190 Barber Lake Switch 138kV | Mitchell | WEST | 2028-09-30 | OTH | BA | 341.8 |  | 2024-11-26 | 2024-12-19 | 2025-03-18 | 2024-12-01 |  |  |  | No
28INR0121 | Jalisco Peaker | SS Completed, FIS Started, No IA | HEP Power Generation, LLC | 8475 JAVELINA4A 138kV | Nueces | COASTAL | 2029-05-31 | GAS | GT | 183.6 |  | 2025-05-06 | 2024-08-16 | 2024-11-04 | 2025-05-01 |  |  |  | No
28INR0124 | Silverbell Storage | SS Completed, FIS Started, No IA | Silverbell Energy Center, LLC | Tap 138kV Rivercrest SES 1780 - Deport REA 1768 | Red River | NORTH | 2028-09-30 | OTH | BA | 129.18 | MW Size | 2024-08-07 | 2024-08-16 | 2024-10-07 | 2024-07-31 |  |  |  | No
28INR0125 | Silverbell Solar | SS Completed, FIS Started, No IA | Silverbell Energy Center, LLC | Tap 138kV Rivercrest SES 1780 - Deport REA 1768 | Red River | NORTH | 2028-09-30 | SOL | PV | 125.59 | MW Size | 2024-08-07 | 2024-08-16 | 2024-10-07 | 2024-07-31 |  |  |  | No |  |  | Not Required
28INR0127 | Half Moon Solar | SS Completed, FIS Started, IA | NextEra Energy Interconnection Holdings, LLC | #80231 Pronto 345kV | Starr | SOUTH | 2029-07-01 | SOL | PV | 512.5 | SFS/NtP | 2024-12-26 | 2025-01-13 | 2025-04-08 | 2024-12-23 |  |  | 2025-09-08 | Yes | Not Required | Not Required | Not Required | 2025-09-15
28INR0132 | River Boat Solar | SS Completed, FIS Started, No IA | Champion Creek Solar, LLC | Tap 345kV 10053 Cattlemen 5 - 76030 Gasconades Creek | Mitchell | WEST | 2028-09-25 | SOL | PV | 502.2 |  | 2024-08-14 | 2024-09-04 | 2024-12-02 | 2024-08-22 |  |  |  | No |  |  | Not Required
28INR0133 | River Boat Storage | SS Completed, FIS Started, No IA | Champion Creek Storage, LLC | Tap 345kV 10053 Cattlemen 5 - 76030 Gasconades Creek | Mitchell | WEST | 2028-09-25 | OTH | BA | 207.02 |  | 2024-09-11 | 2024-10-01 | 2024-12-02 | 2024-09-24 |  |  |  | No
28INR0134 | Salt-Lick Storage | SS Completed, FIS Started, No IA | Salt-Lick Storage, LLC | 11198 Elcor_8 138 KV | Culberson | WEST | 2028-06-01 | OTH | BA | 155.3 |  | 2024-10-07 | 2024-10-10 | 2024-12-09 | 2024-10-07 |  |  |  | No
28INR0147 | Fallstone Solar SLF | SS Completed, FIS Started, No IA | Fallstone Solar, LLC | Tap 69kV 3588 Groesbeck - 3637 Otto Junction | Falls | NORTH | 2028-09-21 | SOL | PV | 60.55 |  | 2024-11-08 | 2024-12-19 | 2025-03-18 | 2024-12-04 |  |  |  | No |  |  | Not Required
28INR0148 | Sonora High Noon BESS | SS Completed, FIS Started, No IA | Sonora High Noon, LLC | 60412 CARVER 138kV | Sutton | WEST | 2028-07-01 | OTH | BA | 204.08 |  | 2024-08-28 | 2024-09-04 | 2024-11-27 | 2024-09-03 |  |  |  | No
28INR0149 | Fallstone Storage SLF | SS Completed, FIS Started, No IA | Fallstone Solar, LLC | Tap 69kV 3588 Groesbeck - 3637 Otto Junction | Falls | NORTH | 2028-09-21 | OTH | BA | 0 |  | 2024-11-08 | 2024-12-19 | 2025-03-18 | 2024-12-04 |  |  |  | No
28INR0154 | Pamela Heights I | SS Completed, FIS Completed, No IA | Pamela heights I Energy Center LLC | #47150 HOC 138kV | Harris | HOUSTON | 2026-06-01 | OTH | BA | 101.65 |  | 2024-09-03 | 2024-09-10 | 2024-12-03 | 2024-09-09 | 2025-08-15 |  |  | No
28INR0155 | Coke BESS | SS Completed, FIS Started, No IA | Coke ESS, LLC | 76090 Divide Switchyard 345kV | Coke | WEST | 2028-04-10 | OTH | BA | 220.3 |  | 2024-09-24 | 2024-10-01 | 2024-12-09 | 2024-09-27 |  |  |  | No
28INR0156 | Chimney Rock BESS | SS Completed, FIS Started, No IA | Taylor ESS, LLC | Tap 138kV 76317 MOORE - 76318 BUTMAN | Taylor | WEST | 2028-04-10 | OTH | BA | 156 |  | 2024-12-11 | 2025-02-14 | 2025-05-12 | 2024-12-17 |  |  |  | No
28INR0157 | Axtell BESS | SS Completed, FIS Started, No IA | Axtell BESS LLC | #13401 Tiger Creek Switch 345kV | McLennan | NORTH | 2028-01-01 | OTH | BA | 306.94 |  | 2025-04-30 | 2024-10-01 | 2024-12-09 | 2025-03-31 |  |  |  | No
28INR0160 | Neal Solar | SS Completed, FIS Started, No IA | CH Neal Solar LLC | tap of 138kV 8750 CHARMERP4A - 8127 South Lane City | Wharton | SOUTH | 2029-04-03 | SOL | PV | 146.6 | MW Size COD | 2025-05-14 | 2025-05-27 | 2025-08-23 | 2025-05-14 |  |  |  | No |  |  | Not Required
28INR0166 | Brookesmith Storage | SS Completed, FIS Started, No IA | Brookesmith Storage LLC | Tap Brown Switch #1444 – Russell Gap Switch #3348 | Brown | NORTH | 2029-05-07 | OTH | BA | 351 |  | 2025-03-12 | 2025-04-01 | 2025-06-25 | 2025-05-21 |  |  |  | No
28INR0168 | Guajillo Wind | SS Completed, FIS Started, No IA | Guajillo Wind LLC | Tap 345 kV 80079 Cruce - 5901 San Miguel CKT 01 | Duval | SOUTH | 2028-09-01 | WIN | WT | 202.4 |  | 2024-12-11 | 2024-12-19 | 2025-03-18 | 2024-12-10 |  |  |  | No |  |  | Not Required
28INR0169 | Sanders Hollow Energy Center | SS Completed, FIS Started, No IA | Sanders Hollow Energy Center, LLC | Tap 345 kV 59904 Cottonwood (W_CW_345) - 60500 Edith Clarke (EDITHCLA7A) CKT 01 | Dickens | PANHANDLE | 2028-09-30 | WIN | WT | 292.6 | MW Size COD | 2025-07-09 | 2024-10-29 | 2025-01-27 |  |  |  |  | No |  |  | Not Required
28INR0175 | Mobee Springs BESS | SS Completed, FIS Started, No IA | Mobee Springs, LLC | #8805 BONIVIEW2A 69kV | Refugio | COASTAL | 2028-03-31 | OTH | BA | 100.61 |  | 2025-04-29 | 2025-06-05 | 2025-09-02 | 2025-05-09 |  |  |  | No
28INR0176 | Gail Mountain Solar | SS Completed, FIS Started, No IA | Gail Mountain Solar, LLC | Tap 345kV 59905 Faraday - 59900 Long Draw | Borden | WEST | 2028-08-25 | SOL | PV | 244.4 |  | 2024-10-22 | 2024-10-29 | 2025-01-14 | 2024-10-11 |  |  |  | No | Not Required | Not Required | Not Required
28INR0177 | Sisters Solar II | SS Completed, FIS Started, No IA | Oberon Solar III, LLC | tap 345kV 11010 Wolf Switching Station - 10012 Meteor | Ector | WEST | 2028-12-15 | SOL | PV | 205.54 |  | 2024-10-18 | 2024-10-21 | 2025-01-10 | 2024-10-18 |  |  |  | No |  |  | Not Required
28INR0179 | Sunburst Solar | SS Completed, FIS Started, No IA | Indigo Solar, LLC | Tap LONHILL (Bus#8455) to KATOEN (Bus#8579). | San Patricio | COASTAL | 2029-03-16 | SOL | PV | 301.6 |  | 2024-10-09 | 2024-10-10 | 2025-01-07 | 2024-10-23 |  |  |  | No |  |  | Not Required
28INR0180 | Green Ocelot Solar | SS Completed, FIS Started, No IA | Ocelot Solar LLC | Tap 345kV 80076 Ajo - 8601 Cebolla | Kenedy | COASTAL | 2028-11-17 | SOL | PV | 357 |  | 2025-01-14 | 2025-01-28 | 2025-04-18 | 2025-01-28 |  | Yes |  | No |  |  | Not Required
28INR0181 | Sunburst BESS | SS Completed, FIS Started, No IA | Indigo Solar, LLC | Tap 345kV 8455 LONHILL - 8579 KATOEN | San Patricio | COASTAL | 2029-03-16 | OTH | BA | 256.3 |  | 2024-10-09 | 2024-10-10 | 2025-01-07 | 2024-10-23 |  |  |  | No
28INR0182 | Ponferrada Solar | SS Completed, FIS Started, No IA | Karol Solar VI | Tap 138 KV 3456 CORSWEST1_8 - 3457 CORS_MOBT_8 | Navarro | NORTH | 2029-04-06 | SOL | PV | 148.87 |  | 2025-04-02 | 2024-10-01 | 2024-12-18 | 2025-04-15 |  |  |  | No |  |  | Not Required
28INR0185 | San Gabriel Solar | SS Completed, FIS Started, No IA | San Gabriel Solar LLC | Tap 138 kV 3750 Vosslake - 3749 Buckholts | Milam | SOUTH | 2028-07-01 | SOL | PV | 255 |  | 2025-01-07 | 2025-01-28 | 2025-04-17 | 2025-01-08 |  |  |  | No |  |  | Not Required
28INR0186 | Saddlehorn Energy Storage | SS Completed, FIS Started, No IA | Saddlehorn, LLC | Tap 138kV 7287 Bellville North - 7291 Highway 36 | Austin | SOUTH | 2028-11-01 | OTH | BA | 256.8 |  | 2024-11-25 | 2024-11-26 | 2025-02-18 | 2024-12-03 |  |  |  | No
28INR0188 | Ashra Solar SLF | SS Completed, FIS Started, No IA | Ashra Solar, LLC | Tap 69kV bus#5823 UVALDE Switch (UVALDESW9) to bus#5820 UVALDE SUB (UVALDESUB9) | Uvalde | SOUTH | 2028-06-14 | SOL | PV | 40.25 |  | 2025-03-30 | 2025-04-25 | 2025-07-22 | 2025-03-31 |  |  |  | No |  |  | Not Required
28INR0189 | Green Ocelot Storage | SS Completed, FIS Started, No IA | Ocelot Solar LLC | Tap 345kV 80076 Ajo 80076 - 8601 Cebolla | Kenedy | COASTAL | 2028-11-17 | OTH | BA | 178.5 |  | 2025-01-14 | 2025-01-28 | 2025-04-18 | 2025-01-28 |  | Yes |  | No
28INR0190 | Ashra Storage SLF | SS Completed, FIS Started, No IA | Ashra Solar, LLC | Tap 69kV 5823 UVALDE Switch - 5820 UVALDE SUB | Uvalde | SOUTH | 2028-06-14 | OTH | BA | 1.62 |  | 2025-03-30 | 2025-04-25 | 2025-07-22 | 2025-03-31 |  |  |  | No
28INR0191 | San Gabriel Storage | SS Completed, FIS Started, No IA | San Gabriel Solar LLC | Tap 138 kV 3750 Vosslake - 3749 Buckholts | Milam | SOUTH | 2028-07-01 | OTH | BA | 127.5 |  | 2025-01-07 | 2025-01-28 | 2025-04-17 | 2025-01-08 |  |  |  | No
28INR0194 | Tapaderos Solar | SS Completed, FIS Started, No IA | Tapaderos Solar, LLC | TAP 345kV #1435 Long Creek - #1430 Graham SES | Young | WEST | 2028-09-19 | SOL | PV | 301.6 |  | 2024-11-04 | 2024-11-19 | 2025-02-15 | 2024-10-16 |  |  |  | No |  |  | Not Required
28INR0195 | Star Grass Renewable Energy Solar SLF | SS Completed, FIS Started, No IA | Star Grass Renewable Energy LLC | Tap 138kV 6310 Putnam - 3378 Carbon_8 | Eastland | NORTH | 2029-09-14 | SOL | PV | 150 |  | 2025-01-13 | 2025-02-14 | 2025-05-12 | 2024-12-30 |  |  |  | No |  |  | Not Required
28INR0196 | Tapaderos Storage | SS Completed, FIS Started, No IA | Tapaderos Storage, LLC | TAP 345kV #1430 GRAHAM SES - #1435 LONG CREEK | Young | WEST | 2028-09-19 | OTH | BA | 207 |  | 2024-11-04 | 2024-11-19 | 2025-02-15 | 2024-10-16 |  |  |  | No
28INR0197 | Star Grass Renewable Energy Storage SLF | SS Completed, FIS Started, No IA | Star Grass Renewable Energy LLC | Tap 138kV 6310 Putnam - 3378 Carbon_8 | Eastland | NORTH | 2029-09-14 | OTH | BA | 0 |  | 2025-01-13 | 2025-02-14 | 2025-05-12 | 2024-12-30 |  |  |  | No
28INR0198 | Winters Glow Solar | SS Completed, FIS Started, No IA | Winters Glow Solar, LLC | tap 345kV 1444 BROWN SWITCH - 11406 CENTRAL BLUFF | Runnels | WEST | 2028-09-19 | SOL | PV | 301.6 |  | 2024-10-21 | 2024-10-29 | 2024-01-06 | 2024-10-16 |  |  |  | No |  |  | Not Required
28INR0199 | Winters Glow Storage | SS Completed, FIS Started, No IA | Winters Glow Storage, LLC | tap 345kV 1444 BROWN SWITCH - 11406 CENTRAL BLUFF | Runnels | WEST | 2028-09-19 | OTH | BA | 155.2 |  | 2024-10-21 | 2024-10-29 | 2024-01-06 | 2024-10-21 |  |  |  | No
28INR0202 | Fluvanna Max BESS SLF | SS Completed, FIS Started, No IA | Fluvanna Max Solar LLC | 11305 DERMOTT 345 kV | Scurry | WEST | 2029-09-14 | OTH | BA | 51.8 |  | 2024-11-04 | 2024-12-19 | 2025-03-10 | 2024-11-11 |  |  |  | No
28INR0205 | Gypsum Plains Solar | SS Completed, FIS Started, No IA | Gypsum Plains Solar, LLC | Tap 345kv line Wolf BUS# 11010 - Reiter BUS#18544 | Ector | WEST | 2029-06-21 | SOL | PV | 503.12 |  | 2025-05-28 | 2025-06-05 | 2025-09-02 | 2025-05-29 |  |  |  | No |  |  | Not Required
28INR0206 | Wagon Timber Solar | SS Completed, FIS Started, No IA | Wagon Timber Solar, LLC | 6110 Munday East 138kV | Knox | WEST | 2028-10-16 | SOL | PV | 172.1 |  | 2024-12-05 | 2024-12-19 | 2025-03-10 | 2024-11-15 |  | No |  | No |  |  | Not Required
28INR0207 | Wagon Timber Storage | SS Completed, FIS Started, No IA | Wagon Timber Storage, LLC | 6110 Munday East 138kV | Knox | WEST | 2028-10-16 | OTH | BA | 53.49 |  | 2024-12-05 | 2025-01-13 | 2025-04-08 | 2024-12-05 |  | No |  | No
28INR0208 | Strawberry Dunes Solar SLF | SS Completed, FIS Started, No IA | Strawberry Dunes LLC | Tap 138kV ROSSVILLESB8 (5718) to OAKSSW8 (5713) | Atascosa | SOUTH | 2028-06-30 | SOL | PV | 101.1 |  | 2024-12-23 | 2025-02-14 | 2025-05-12 | 2025-02-11 |  |  |  | No |  |  | Not Required
28INR0209 | Strawberry Dunes BESS SLF | SS Completed, FIS Started, No IA | Strawberry Dunes LLC | Tap 138kV ROSSVILLESB8 (5718) to OAKSSW8 (5713) | Atascosa | SOUTH | 2028-06-30 | OTH | BA | 0 |  | 2024-12-23 | 2025-02-14 | 2025-05-12 | 2025-02-11 |  |  |  | No
28INR0212 | Badger Solar | SS Completed, FIS Started, No IA | 174 Power Global Properties, LLC | 345 kV North McCamey Substation (Bus# 76000) | Upton | WEST | 2029-05-25 | SOL | PV | 301.83 |  | 2025-02-05 | 2025-02-12 | 2025-04-22 | 2024-11-27 |  |  |  | No |  |  | Not Required
28INR0213 | Badger BESS | SS Completed, FIS Started, No IA | 174 Power Global Properties, LLC | 345 kV North McCamey (Bus# 76000) | Upton | WEST | 2029-05-25 | OTH | BA | 154.12 |  | 2025-02-05 | 2025-02-12 | 2025-04-22 | 2024-11-27 |  |  |  | No
28INR0215 | Complex Serenity Wind | SS Completed, FIS Started, No IA | Serenity Wind, LLC | Double tap 345 kV Alibates (bus# 23900) to Tule Canyon (bus# 23914) and the Alibates (bus# 23900) to Midpoint Switch (bus# 23931) | Armstrong | PANHANDLE | 2029-04-16 | WIN | WT | 971 |  | 2025-04-22 | 2025-06-05 | 2025-09-02 | 2025-04-30 |  |  |  | No |  |  | Not Required
28INR0217 | Gypsum Plains Storage | SS Completed, FIS Started, No IA | Gypsum Plains Solar, LLC | Tap 345kv 11010 Wolf - 18544 Reiter | Ector | WEST | 2029-06-21 | OTH | BA | 211.14 |  | 2024-12-30 | 2025-01-31 | 2025-04-18 | 2025-01-24 |  |  |  | No
28INR0221 | Rio Star Energy Storage | SS Completed, FIS Started, No IA | Rio Star Energy Storage, LLC | Tap 1464 Wichita Falls South Switch – 1474 Scotland 138 kV | Wichita | WEST | 2028-09-28 | OTH | BA | 143.6 | MW Size COD | 2025-02-03 | 2025-02-14 | 2025-05-12 | 2025-02-04 |  |  |  | No
28INR0223 | Bayou Creek Solar | SS Completed, FIS Started, No IA | Ferrovial Energy US 1 | 88607 Goddard 345kV | San Patricio | COASTAL | 2028-09-25 | SOL | PV | 255.47 | FIS Request | 2025-07-22 | 2024-12-19 | 2025-03-24 | 2025-09-17 |  |  |  | No |  |  | Not Required
28INR0226 | Pamplona Storage | SS Completed, FIS Completed, No IA | Karol Solar V | Tap 138 kV 44740 WALLIS_S65_8 - 44700 GEBHRT_X65B8 Ckt#65 | Austin | SOUTH | 2028-10-17 | OTH | BA | 153.88 |  | 2025-07-07 | 2024-12-19 | 2025-03-18 | 2025-06-25 | 2025-08-26 |  |  | No
28INR0227 | GPlains Solar | SS Completed, FIS Started, No IA | Gypsum Plains Solar, LLC | Tap 138kV #1013 WOLFSS_8 - #1103 SANDHLTA_8 | Ector | WEST | 2029-06-21 | SOL | PV | 151.29 | MW Size | 2025-03-27 | 2025-04-21 | 2025-07-19 | 2025-04-08 |  |  |  | No |  |  | Not Required
28INR0228 | GPlains Storage | SS Completed, FIS Started, No IA | Gypsum Plains Solar, LLC | Tap 138kV WOLFSS_8 (1013) - SANDHLTA_8 (1103) | Ector | WEST | 2029-06-21 | OTH | BA | 51.27 |  | 2025-03-27 | 2025-04-21 | 2025-07-19 | 2025-04-11 |  |  |  | No
28INR0229 | Allthorn Solar | SS Completed, FIS Started, No IA | ALLTHORN SOLAR, LLC | Tap 138 kV BRUNI4A (#8297) - CRESTONI4A (#8695) | Duval | SOUTH | 2029-01-15 | SOL | PV | 231.5 | COD | 2024-12-17 | 2025-02-14 | 2025-05-13 | 2025-02-03 |  |  |  | No |  |  | Not Required
28INR0230 | Allthorn BESS | SS Completed, FIS Started, No IA | ALLTHORN SOLAR, LLC | Tap 138 kV BRUNI44A (#8297) - CRESTONI4A (#8695) | Duval | SOUTH | 2029-01-15 | OTH | BA | 205.2 | COD | 2024-12-17 | 2025-02-14 | 2025-05-13 | 2025-02-03 |  |  |  | No
28INR0238 | Dempsey Storage SLF | SS Completed, FIS Started, No IA | Dempsey Storage LLC | Tap the 138 KV Ridge (#37)-Robertson (#32) line; BEPC | Leon | NORTH | 2028-09-08 | OTH | BA | 0 |  | 2025-02-06 | 2025-02-25 | 2025-05-20 | 2025-03-20 |  |  |  | No
28INR0240 | Dahlia Solar | SS Completed, FIS Started, No IA | Dahlia Energy LLC | Tap 138kV 5723 Los Angeles - 5705 Fowlerton | La Salle | SOUTH | 2028-07-02 | SOL | PV | 200.98 |  | 2025-02-13 | 2025-02-14 | 2025-05-12 | 2025-02-06 |  |  |  | No |  |  | Not Required
28INR0245 | Hittson Creek Solar | SS Completed, FIS Started, No IA | 174 Power Global Properties | Tapping the two 345 kV Lines: Sam Line Reactor (Bus# 68005) - Reata (Bus# 68051) and Latimer (Bus# 68008) - Reata (Bus# 68051). | Callahan | WEST | 2028-12-15 | SOL | PV | 402.93 |  | 2024-12-17 | 2024-12-19 | 2025-03-18 | 2024-12-18 |  |  |  | No |  |  | Not Required
28INR0246 | Hittson Creek BESS | SS Completed, FIS Started, No IA | 174 Power Global Properties | Tapping the two 345 kV Lines: Sam Line Reactor (Bus# 68005) - Reata (Bus# 68051) and Latimer (Bus# 68008) - Reata (Bus# 68051). | Callahan | WEST | 2028-12-15 | OTH | BA | 205.38 |  | 2024-12-17 | 2024-12-19 | 2025-03-18 | 2024-12-18 |  |  |  | No
28INR0247 | Eligius BESS | SS Completed, FIS Started, No IA | Eligius Storage LLC | tap 138kV Liston (#8394) – JL Bates (#8392) line, AEP | Hidalgo | SOUTH | 2028-11-28 | OTH | BA | 174.66 |  | 2025-02-17 | 2025-02-25 | 2025-05-20 | 2025-02-18 |  |  |  | No
28INR0250 | Mojo Solar | SS Completed, FIS Started, No IA | Power Synergy | Tap 345 kV 5133 Elm Creek - 5901 San Miguel CKT 1 & 2 | Wilson | SOUTH | 2028-06-30 | SOL | PV | 527.94 |  | 2025-02-26 | 2025-03-03 | 2025-05-19 | 2025-02-12 |  |  |  | No |  |  | Not Required
28INR0253 | Stonewall BESS | SS Completed, FIS Started, No IA | Stonewall ESS, LLC | tap 138kV 6150 SPUR4A - 6158 ASPM4A | Stonewall | WEST | 2028-12-29 | OTH | BA | 135 |  | 2025-02-17 | 2025-02-25 | 2025-05-20 | 2025-02-06 |  |  |  | No
28INR0254 | Summerhill BESS | SS Completed, FIS Started, No IA | Taylor ESS, LLC | Tap 138kv 6228 ABNTHWST4A - 6288 MULBERRY4D | Taylor | WEST | 2028-12-15 | OTH | BA | 143 |  | 2025-02-14 | 2025-02-14 | 2025-05-13 | 2025-02-06 |  |  |  | No
28INR0255 | watermelon 5 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2025-02-06 | 2025-02-14 | 2025-05-12 | 2025-02-06 |  |  |  | No | Not Required | Not Required
28INR0256 | watermelon 6 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2025-02-06 | 2025-02-14 | 2025-05-12 | 2025-02-06 |  |  |  | No | Not Required | Not Required
28INR0257 | watermelon 7 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2025-02-06 | 2025-02-14 | 2025-05-12 | 2025-02-06 |  |  |  | No | Not Required | Not Required
28INR0258 | watermelon 8 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2025-02-06 | 2025-02-14 | 2025-05-12 | 2025-02-06 |  |  |  | No | Not Required | Not Required
28INR0260 | Rio Vista Solar | SS Completed, FIS Started, No IA | Rio Vista Solar, LLC | Tap 138kV #60393 PigCreek4A – #60385 Solstice4A | Pecos | WEST | 2028-10-16 | SOL | PV | 553.66 |  | 2025-01-13 | 2025-06-19 | 2025-09-17 | 2025-01-21 |  |  |  | No |  |  | Not Required
28INR0261 | Rio Vista Storage | SS Completed, FIS Started, No IA | Rio Vista Storage, LLC | Tap 138kV #60393 Pigcreek4A – #60385 Solstice4A | Pecos | WEST | 2028-10-16 | OTH | BA | 103.37 |  | 2025-01-14 | 2025-06-19 | 2025-09-17 | 2025-01-21 |  |  |  | No
28INR0262 | Pasture Rose Wind | SS Completed, FIS Started, No IA | Pasture Rose, LLC | TAP 345KV BUS 3721 STRINGER SW - 3711 BALE_S5 | Falls | NORTH | 2029-06-07 | WIN | WT | 198.7 |  | 2025-02-05 | 2025-03-24 | 2025-06-09 | 2025-04-01 |  |  |  | No |  |  | Not Required
28INR0265 | Agricola BESS | SS Completed, FIS Started, No IA | Agricola BESS LLC | Tap 138kV GEBHARDT (#44700) - Wallis (#44740) | Austin | SOUTH | 2029-05-31 | OTH | BA | 0 |  | 2025-01-24 | 2025-03-24 | 2025-06-09 | 2025-02-12 |  |  |  | No
28INR0266 | Cycle Storage | SS Completed, FIS Started, No IA | Grenergy USA | #1480 Rathgeber 138kv | Wichita | WEST | 2028-09-19 | OTH | BA | 104.53 |  | 2025-03-27 | 2025-04-01 | 2025-06-25 | 2025-03-27 |  |  |  | No
28INR0267 | Soluce Cotton Solar | SS Completed, FIS Started, No IA | CTPB1, LLC | Tap 345kV 59904 COTTONWOOD - 60500 EDITH CLARKE | Cottle | WEST | 2028-07-29 | SOL | PV | 202.91 |  | 2025-07-16 | 2025-02-14 | 2025-05-12 |  |  |  |  | No |  |  | Not Required
28INR0268 | Soluce Cotton Storage | SS Completed, FIS Started, No IA | CTPB1,LLC | Tap 345kV 59904 COTTONWOOD - 60500 EDITH CLARKE | Cottle | WEST | 2028-07-29 | OTH | BA | 201.54 |  | 2025-07-16 | 2025-02-14 | 2025-05-12 |  |  |  |  | No
28INR0271 | Three Ranches Solar | SS Completed, FIS Started, No IA | Three Ranches Energy LLC | TAP 138kV #6680 Alamitto Creek - #60444 Hayter Ranch | Brewster | WEST | 2027-01-30 | SOL | PV | 125.53 |  | 2025-02-10 | 2025-02-14 | 2025-05-12 | 2025-01-22 |  |  |  | No |  |  | Not Required
28INR0272 | Miracle Ranch Solar SLF | SS Completed, FIS Started, No IA | Miracle Ranch LLC | 138kV North Laredo (8909_NLARSW4A) to Barrera (8717_BARRERA4A) - AEP | Webb | SOUTH | 2028-06-30 | SOL | PV | 221.6 |  | 2025-02-04 | 2025-02-25 | 2025-05-20 | 2025-02-07 |  |  |  | No |  |  | Not Required
28INR0273 | Miracle Ranch BESS SLF | SS Completed, FIS Started, No IA | Miracle Ranch LLC | 138kV North Laredo (8909_NLARSW4A) to Barrera (8717_BARRERA4A) - AEP | Webb | SOUTH | 2028-06-30 | OTH | BA | 0 |  | 2025-02-05 | 2025-03-19 | 2025-06-09 | 2025-02-07 |  |  |  | No
28INR0274 | Wood Fern Wind | SS Completed, FIS Started, No IA | Wood Fern Wind LLC | Tap 345kV #2432 Tri-Corner to #3102 Tyler Grande | Van Zandt | NORTH | 2029-06-07 | WIN | WT | 197.3 |  | 2024-12-26 | 2025-01-31 | 2025-04-18 | 2025-01-06 |  |  |  | No |  |  | Not Required
28INR0277 | Aurora Energy Storage | SS Completed, FIS Started, No IA | Aurora Energy Storage, LLC | Tap 345kV --- KILL_SS_5 (3422) --- BUCK_H_5 (3424) | Lampasas | NORTH | 2028-09-26 | OTH | BA | 306.2 |  | 2025-02-03 | 2025-02-14 | 2025-05-13 | 2025-02-05 |  |  |  | No
28INR0278 | Spur Energy Storage | SS Completed, FIS Started, No IA | Spur Energy Storage, LLC | Tap 345kV (1429) JACKSBRO_5 - (11736) BIRDDOG_5 | Wise | NORTH | 2028-09-26 | OTH | BA | 306.31 |  | 2025-01-28 | 2025-02-25 | 2025-05-20 | 2025-01-30 |  |  |  | No
28INR0280 | Live Oak Wind II | SS Completed, FIS Started, No IA | ENGIE IR Holdings LLC | #76003 Big Hill 345kV | Schleicher | WEST | 2028-09-29 | WIN | WT | 302.63 |  | 2025-03-21 | 2025-03-24 | 2025-06-09 | 2025-03-19 |  |  |  | No |  |  | Not Required
28INR0281 | Jukebox Solar | SS Completed, FIS Started, No IA | ACE DevCo NC, LLC | 8221 BIG FOOT4A 138kV | Frio | SOUTH | 2027-07-01 | SOL | PV | 281 |  | 2025-01-03 | 2025-06-19 | 2025-09-17 | 2025-05-16 |  |  |  | No |  |  | Not Required
28INR0285 | Wilson BESS | SS Completed, FIS Started, No IA | Dunamis BESS | Tap 345 kV 5133 Elm Creek - 5901 San Miguel CKT 1 & 2 | Wilson | SOUTH | 2028-06-30 | OTH | BA | 409.74 |  | 2025-04-15 | 2025-04-21 | 2025-07-19 | 2025-04-15 |  |  |  | No
28INR0288 | Outrider BESS | SS Completed, FIS Started, No IA | Sanders Hollow Energy Center, LLC | Tap 345 kV 59904 Cottonwood (W_CW_345) - 60500 Edith Clarke (EDITHCLA7A) CKT. Approximately distance from the POI to Cottonwood Substation is 11.13 miles and to Edith Clarke Substation 77.6 miles. | Dickens | PANHANDLE | 2028-09-30 | OTH | BA | 302 | FIS Request | 2025-09-10 | 2025-06-05 | 2025-08-29 | 2025-09-03 |  |  |  | No
28INR0290 | Field Marshal Storage | SS Completed, FIS Started, No IA | Field Marshal Storage LLC | Dublin (1636) - Fullhouse (1652) 138kV | Erath | NORTH | 2029-05-07 | OTH | BA | 150.8 |  | 2025-03-11 | 2025-03-24 | 2025-06-09 | 2025-03-20 |  |  |  | No
28INR0292 | Wildflower Storage | SS Completed, FIS Started, No IA | Wildflower Storage LLC | Drane Switch 345 kV substation on Venus Switch (1906) - Navarro (68091) 345 kV line | Navarro | NORTH | 2028-09-30 | OTH | BA | 359.1 |  | 2025-05-08 | 2025-06-05 | 2025-09-02 | 2025-05-15 |  |  |  | No
28INR0293 | Dart Energy Storage A1 | SS Completed, FIS Started, No IA | Dart Energy Storage LLC | TAP138KV #6290 ABILENE MAPLE STREET - #6275 ABILENE EAST | Taylor | WEST | 2028-11-30 | OTH | BA | 50 |  | 2025-04-25 | 2025-02-25 | 2025-05-20 | 2025-04-17 |  |  |  | No
28INR0295 | Margay Energy Storage | SS Completed, FIS Started, No IA | PowerPulse LLC | Tap 138kV 42750 Mykawa - 48353 Telephone Ckt 06 | Brazoria | COASTAL | 2028-10-15 | OTH | BA | 101.3 |  | 2025-01-29 | 2025-02-25 | 2025-05-20 | 2025-02-24 |  |  |  | No
28INR0297 | Magnet Solar | SS Completed, FIS Started, No IA | HyFuels Big Spring Solar LLC | Faraday Substation 345kV - Bus #59905 | Borden | WEST | 2028-10-06 | SOL | PV | 503.09 |  | 2025-05-05 | 2025-04-21 | 2025-07-19 | 2025-04-24 |  |  |  | No |  |  | Not Required
28INR0298 | Magnet Storage | SS Started, FIS Started, No IA | HyFuels Big Spring LLC | Faraday 345 kV Substation (#59905) | Borden | WEST | 2028-10-06 | OTH | BA | 426.7 |  |  | 2025-07-29 |  | 2025-08-22 10:31 |  |  |  | No
28INR0300 | Champion Road BESS | SS Completed, FIS Started, No IA | Horizon Energy Storage Greenfield Project Holdings LLC | 138 kV Tap 3328 Lufkin South - 3324 Lufkin Switch Tap East | Angelina | NORTH | 2028-09-30 | OTH | BA | 200 | MW Size | 2025-02-07 | 2025-02-14 | 2025-05-13 | 2025-02-07 |  |  |  | No
28INR0301 | Carpet Tech Solar One | SS Started, FIS Started, No IA | CT Solar One | #59911 MHOS 345 kV | Kent | WEST | 2028-10-01 | SOL | PV | 110.76 |  | 2025-06-19 | 2025-07-07 |  | 2025-06-26 |  |  |  | No |  |  | Not Required
28INR0303 | Goliad County Solar 1 SLF | SS Completed, FIS Started, No IA | Goliad County Solar 1, LLC | Tap Coleto Creek (Bus # 8162) - Victoria (Bus# 8172) 138 kV CKT 1 | Goliad | SOUTH | 2028-09-21 | SOL | PV | 234.87 |  | 2025-02-18 | 2025-04-21 | 2025-06-18 | 2025-03-03 |  |  |  | No |  |  | Not Required
28INR0304 | Goliad County Storage 1 SLF | SS Completed, FIS Started, No IA | Goliad County Solar 1, LLC | Tap - Coleto Creek (Bus # 8162) - Victoria (Bus# 8172) 138 kV CKT 1 | Goliad | SOUTH | 2028-09-21 | OTH | BA | 151.46 |  | 2025-02-18 | 2025-03-24 | 2025-06-18 | 2025-03-03 |  |  |  | No
28INR0305 | Iron Cowboy Solar | SS Completed, FIS Started, No IA | Vaquero II Solar, LLC | Bus #8920 Haisley 4A 138 kV | San Patricio | COASTAL | 2028-12-29 | SOL | PV | 120.69 |  | 2025-04-25 | 2025-06-05 | 2025-09-02 | 2025-05-16 |  |  |  | No |  |  | Not Required
28INR0306 | Iron Cowboy Storage | SS Completed, FIS Started, No IA | Vaquero II Storage, LLC | Bus #8920 Haisley 4A 138 kV | San Patricio | COASTAL | 2028-12-29 | OTH | BA | 63.27 |  | 2025-04-25 | 2025-06-05 | 2025-09-02 | 2025-05-16 |  |  |  | No
28INR0307 | Prairie Power Wind | SS Completed, FIS Started, No IA | Prairie Power Wind, LLC | TAP 345KV BUS #1058 LONGSHORE_5 - BUS #10053 CATTLEMEN_5 | Mitchell | WEST | 2029-04-17 | WIN | WT | 303.3 | MW Size COD | 2025-05-27 | 2025-06-05 | 2025-09-02 | 2025-05-27 |  |  |  | No |  |  | Not Required
28INR0321 | Altair Energy Storage | SS Completed, FIS Started, No IA | Altair Energy Storage | Tap on 138 kV ALTAIR (bus# 78118) to STAFFORD HILL (bus# 78520) | Colorado | SOUTH | 2030-03-31 | OTH | BA | 201.76 |  | 2025-04-14 | 2025-04-21 | 2025-07-19 | 2025-03-31 |  |  |  | No
28INR0322 | Velociraptor Solar II | SS Completed, FIS Started, No IA | Greyhound Solar 3 LLC | Tap south bus Odessa EHV SW (11028) - Wolf Switch (11010) 345KV section at (31.740371, -102.502076) | Ector | WEST | 2028-11-17 | SOL | PV | 251.73 |  | 2025-05-20 | 2025-05-27 | 2025-08-23 | 2025-05-12 |  |  |  | No |  |  | Not Required
28INR0323 | Velociraptor BESS II | SS Completed, FIS Started, No IA | Greyhound BESS 3 LLC | #11028 Odessa EHV SW - #11010 Wolf Switch 345K | Ector | WEST | 2028-11-17 | OTH | BA | 261.29 |  | 2025-05-15 | 2025-05-27 | 2025-08-23 | 2025-05-07 |  |  |  | No
28INR0324 | Barkley Creek Solar | SS Completed, FIS Started, No IA | 174 Power Global Properties, LLC | Tapping the two 345 kV Lines: Russel Gap Switch (Bus# 3348) - Killeen (Bus# 3422) and Buckhorn Switch (Bus# 3424) - Killeen (Bus# 3422). | Lampasas | NORTH | 2029-10-15 | SOL | PV | 312.34 |  | 2025-08-12 | 2025-08-26 | 2025-09-30 | 2025-08-19 |  |  |  | No |  |  | Not Required
28INR0325 | Cielo Vista Power Gas Plant | SS Started, FIS Started, No IA | Cielo Vista Power, LLC | Tap 345kV Bus #5901 Miguel5 - Bus #80079 Cruce7A Ckt 1 | Duval | SOUTH | 2028-06-30 | GAS | IC | 334.7 |  | 2025-07-29 | 2025-08-18 |  | 2025-08-13 |  |  |  | No
28INR0327 | 18-BRAVO BESS | SS Completed, FIS Started, No IA | Scout Energy Management, LLC | 138 kV Commerce Switch Substation. Bus no. #1816 | Hunt | NORTH | 2028-02-01 | OTH | BA | 407 |  | 2025-03-28 | 2025-04-01 | 2025-06-25 | 2025-03-26 |  |  |  | No
28INR0328 | 18-ALPHA BESS | SS Completed, FIS Started, No IA | SCOUT ENERGY MANAGEMENT, LLC | To the 138 kV Valley View Substation, ( Bus No.691) | Cooke | NORTH | 2028-02-01 | OTH | BA | 307.4 |  | 2025-04-04 | 2025-04-21 | 2025-07-19 | 2025-04-04 |  |  |  | No
28INR0335 | Oak Valley Solar | SS Completed, FIS Started, No IA | Oak Valley Solar LLC | 68091 (Navarro) (345) | Navarro | NORTH | 2028-01-20 | SOL | PV | 251.3 |  | 2025-03-25 | 2025-04-01 | 2025-06-25 | 2025-03-19 |  |  |  | No |  |  | Not Required
28INR0337 | Barrosos Creek Wind 3 | SS Started, FIS Started, No IA | Cascabel Wind Energy, LLC | #80227 Rapido 345 kV | Zapata | SOUTH | 2028-05-31 | WIN | WT | 197.75 |  | 2025-07-30 | 2025-08-18 |  | 2025-07-30 |  |  |  | No |  |  | Not Required
28INR0338 | Barrosos Creek Wind 4 | SS Started, FIS Started, No IA | Cascabel Wind Energy, LLC | #80227 Rapido 345 kV | Zapata | SOUTH | 2028-05-31 | WIN | WT | 197.75 |  | 2025-07-30 | 2025-08-18 |  | 2025-07-30 |  |  |  | No |  |  | Not Required
28INR0339 | Corralitos Wind 3 | SS Completed, FIS Started, No IA | Las Crestas Wind Energy, LLC | ETT 345 kV Tiempo #80224 Substation (Tap on 345kV 80225 CENIZO7C - 80307 DELSOL7C) | Zapata | SOUTH | 2028-05-31 | WIN | WT | 196.1 |  | 2025-06-11 | 2025-06-13 | 2025-09-11 | 2025-06-24 |  |  |  | No |  |  | Not Required
28INR0340 | Corralitos Wind 4 | SS Completed, FIS Started, No IA | Las Crestas Wind Energy, LLC | ETT 345 kV Tiempo #80224 Substation (Tap on 345kV 80225 CENIZO7C - 80307 DELSOL7C) | Zapata | SOUTH | 2028-05-31 | WIN | WT | 195.4 |  | 2025-06-11 | 2025-06-13 | 2025-09-11 | 2025-06-24 |  |  |  | No |  |  | Not Required
28INR0341 | Bastion BESS | SS Started, FIS Started, No IA | BESS BASTION LLC | Blessing Substation 138 kV (ID 8121) | Matagorda | COASTAL | 2028-11-01 | OTH | BA | 154.3 |  | 2025-06-26 | 2025-07-07 |  | 2025-06-19 |  |  |  | No
28INR0343 | Amphion Solar Phase 2 | SS Completed, FIS Started, No IA | Amphion Solar, LLC | TAP 345KV (#5709) Fowlerton - (#5901) SAN MIGUEL LINE Ckt-2 | Atascosa | SOUTH | 2029-05-15 | SOL | PV | 205.9 |  | 2025-03-28 | 2025-04-21 | 2025-07-19 | 2025-04-09 |  |  |  | No |  |  | Not Required
28INR0344 | Amphion Solar Phase 3 | SS Completed, FIS Started, No IA | Amphion Solar, LLC | TAP 345KV (#5709) Fowlerton - (#5901) SAN MIGUEL LINE Ckt-2 | Atascosa | SOUTH | 2029-11-15 | SOL | PV | 115.4 |  | 2025-03-28 | 2025-04-21 | 2025-07-19 | 2025-04-09 |  |  |  | No |  |  | Not Required
28INR0346 | Maximino Road BESS | SS Completed, FIS Started, No IA | Horizon Energy Storage Greenfield Project Holdings LLC | 7170 BERGHEIM 138kV | Comal | SOUTH | 2028-05-31 | OTH | BA | 257.6 |  | 2025-03-21 | 2025-03-24 | 2025-06-19 | 2025-03-14 |  |  |  | No
28INR0348 | Ringtail Energy Storage | SS Completed, FIS Started, No IA | PowerPulse LLC | Bus # 1446, Lake Wichita, 138 kV | Archer | WEST | 2028-12-15 | OTH | BA | 200.8 |  | 2025-04-15 | 2025-04-25 | 2025-07-22 | 2025-04-23 |  |  |  | No
28INR0349 | Jaguarundi Energy Storage | SS Completed, FIS Started, No IA | PowerPulse LLC | Bus # 1339, Eskota 138kV | Nolan | WEST | 2029-11-10 | OTH | BA | 152.02 | MW Size COD | 2025-05-29 | 2025-06-05 | 2025-09-02 | 2025-06-02 |  |  |  | No
28INR0350 | Mojo BESS | SS Completed, FIS Started, No IA | Power Synergy | Tap 345 kV 5133 Elm Creek 5901 - San Miguel CKT 1 & 2 | Wilson | SOUTH | 2028-06-30 | OTH | BA | 245.71 |  | 2025-04-23 | 2025-04-25 | 2025-07-23 | 2025-05-20 |  |  |  | No
28INR0351 | River Boat Power Gas Plant | SS Started, FIS Started, No IA | Champion Creek Power, LLC | Tap 345kV 10053 Cattlemen 5 - 76030 Gasconades Creek | Mitchell | WEST | 2028-06-30 | GAS | IC | 334.36 |  | 2025-08-12 | 2025-08-18 |  | 2025-08-11 |  |  |  | No
28INR0353 | Cowboy Power Gas Plant | SS Started, FIS Started, No IA | Vaquero Power, LLC | Tap 345kV 8249 Angstrom - 8624 Grissom | San Patricio | COASTAL | 2028-10-16 | GAS | IC | 251.53 |  | 2025-07-29 | 2025-08-18 |  | 2025-08-07 |  |  |  | No
28INR0355 | Galaxy I Solar | SS Completed, FIS Started, No IA | Galaxy Solar, LLC | Tap 345kV 2427 Watermill - 3159 Elrod | Ellis | NORTH | 2028-10-30 | SOL | PV | 82.85 |  | 2025-07-22 | 2025-04-21 | 2025-07-19 | 2025-07-16 |  |  |  | No |  |  | Not Required
28INR0356 | Arpeggio BESS | SS Completed, FIS Started, No IA | Arpeggio BESS, LLC | #80064 Chocolate Bayou 138kV | Victoria | SOUTH | 2029-01-01 | OTH | BA | 200.71 |  | 2025-06-17 | 2025-06-19 | 2025-09-17 | 2025-06-18 |  |  |  | No
28INR0358 | Cherry Sage Solar 1 SLF | SS Completed, FIS Started, No IA | Cherry Sage Solar 1 LLC | (#60423) TREADWELL 138kV. | Concho | WEST | 2029-02-23 | SOL | PV | 142.51 |  | 2025-04-15 | 2025-04-25 | 2025-07-23 | 2025-04-22 |  |  |  | No |  |  | Not Required
28INR0359 | Cherry Sage Storage 1 SLF | SS Completed, FIS Started, No IA | Cherry Sage Storage 1 LLC | (#60423) TREADWELL 138kV. | Concho | WEST | 2029-02-23 | OTH | BA | 150.28 |  | 2025-04-15 | 2025-04-25 | 2025-07-23 | 2025-04-22 |  |  |  | No
28INR0363 | Graves Storage | SS Completed, FIS Started, No IA | Snowshoe Falls, LLC | 165 WINDSORSW 138kV | McLennan | NORTH | 2028-09-30 | OTH | BA | 201.3 |  | 2025-05-08 | 2025-06-05 | 2025-09-02 | 2025-04-28 |  |  |  | No
28INR0373 | Berryman Road Storage | SS Completed, FIS Started, No IA | Horizon Energy Storage Greenfield Project Holdings LLC | Tap 138kV 1424# Bowman Substation - 11525# Short grass Substation | Archer | WEST | 2028-05-31 | OTH | BA | 254.49 |  | 2025-05-20 | 2025-06-05 | 2025-09-02 | 2025-05-21 |  |  |  | No
28INR0375 | Barranca Wind 1 | SS Started, FIS Started, No IA | Barranca Wind Energy, LLC | Tap the 345 kV CENIZO (#80225) - DELSOL (#80307) line | Jim Hogg | SOUTH | 2028-06-01 | WIN | WT | 300.9 |  | 2025-07-07 | 2025-07-29 |  | 2025-07-09 |  |  |  | No |  |  | Not Required
28INR0376 | Barranca Wind 2 | SS Started, FIS Started, No IA | Barranca Wind Energy, LLC | Tap the 345 kV CENIZO7C (#80225) - DELSOL7C (#80307) line. | Jim Hogg | SOUTH | 2028-06-01 | WIN | WT | 298.6 |  | 2025-07-07 | 2025-07-29 |  | 2025-07-09 |  |  |  | No |  |  | Not Required
28INR0385 | Galaxy Solar 2 | SS Completed, FIS Started, No IA | Galaxy Solar 2, LLC | Tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2028-12-31 | SOL | PV | 301.08 | FIS Request | 2025-06-12 | 2025-06-19 | 2025-09-17 | 2025-09-03 |  |  |  | No |  |  | Not Required
28INR0386 | Sagebrush Wind | SS Started, FIS Started, No IA | ACE DevCo NC, LLC | TAP 345KV 11420 SWEETWATER EAST - 11406 CENTRAL BLUFF | Nolan | WEST | 2029-12-01 | WIN | WT | 200.3 |  | 2025-05-28 | 2025-07-29 |  | 2025-07-28 |  |  |  | No |  |  | Not Required
28INR0387 | Galaxy Storage 2 | SS Completed, FIS Started, No IA | Galaxy Solar 2, LLC | Tap Venus [#1906] to Navarro [#68091] | Ellis | NORTH | 2028-12-31 | OTH | BA | 201.47 | FIS Request | 2025-09-10 | 2025-06-19 | 2025-09-17 | 2025-09-03 |  |  |  | No
28INR0389 | Tri-X BESS 1 SLF | SS Started, FIS Started, No IA | Crane I Solar Electric, LLC | 138 kV Soda Lake (#76026) | Crane | WEST | 2027-12-01 | OTH | BA | 205.51 |  | 2025-08-05 | 2025-08-18 |  | 2025-08-06 |  |  |  | No
28INR0391 | Ruedrich BESS | SS Completed, FIS Started, No IA | Ruedrich BESS | LINE TAP OF CIBOLO (7608) AND McQUEENEY (7606) | Guadalupe | SOUTH | 2028-11-09 | OTH | BA | 200.58 |  | 2025-06-11 | 2025-06-19 | 2025-09-17 | 2025-06-12 |  |  |  | No
28INR0392 | Devine Mary BESS | SS Started, FIS Started, No IA | Devine Mary BESS | 5813 PEARSONSW8 138 kV | Medina | SOUTH | 2028-11-21 | OTH | BA | 200.58 |  | 2025-06-12 | 2025-07-07 |  | 2025-06-19 |  |  |  | No
28INR0394 | Treehouse Solar | SS Started, FIS Started, No IA | Treehouse Solar, LLC | Tap the 345 kV Jewett (#3390) - Singleton (#44645) line | Grimes | NORTH | 2028-11-13 | SOL | PV | 281.77 | FIS Request | 2025-07-11 | 2025-07-29 |  | 2025-09-03 |  |  |  | No |  |  | Not Required
28INR0395 | Treehouse Storage | SS Started, FIS Started, No IA | Treehouse Solar, LLC | Tap the 345 kV Jewett (#3390) - Singleton (#44645) line, ONCOR | Grimes | NORTH | 2028-11-13 | OTH | BA | 209.21 | FIS Request | 2025-07-07 | 2025-07-29 |  | 2025-09-03 |  |  |  | No
28INR0408 | Max 4 Wind | SS Started, FIS Started, No IA | Max 4 Wind LLC | Tap 345 kV Gauss7D (Bus# 60703) to Quasar7A (Bus# 60712) Transmission Line | Haskell | WEST | 2028-06-15 | WIN | WT | 352.6 |  | 2025-07-16 | 2025-07-29 |  | 2025-07-16 |  |  |  | No |  |  | Not Required
28INR0412 | Yellow Leaf II BESS | SS Started, FIS Started, No IA | Yellow Leaf 2 BESS LLC | Tap 138kV 2727 CRANDALL1_8 - 2724 KAUFMN_8 | Kaufman | NORTH | 2028-12-31 | OTH | BA | 205.74 |  | 2025-07-22 | 2025-07-22 |  | 2025-07-18 |  |  |  | No
28INR0413 | Tolivar Power Plant Phase 2 | SS Started, FIS Started, No IA | Pecos Power Plant, LLC | Tap 138 KV 38045 IH20-38043 COWPEN | Reeves | WEST | 2027-07-30 | GAS | IC | 224.5 |  | 2025-07-03 | 2025-07-29 |  | 2025-07-07 |  |  |  | No
28INR0415 | Alkali Creek Wind | SS Started, FIS Started, No IA | Alkali Creek Wind, LLC | Tap 345 kV BUS #1048 Tonkawa - BUS #11050 Dusty Road | Fisher | WEST | 2028-12-01 | WIN | WT | 474.4 |  | 2025-07-31 | 2025-08-18 |  | 2025-07-31 |  |  |  | No |  |  | Not Required
28INR0419 | PRI Solar | SS Started, FIS Started, No IA | BHER Power Resources, Inc. | The 345 kV Falcon Seaboard (#1025) substation; Oncor | Howard | WEST | 2027-01-31 | SOL | PV | 63.4 |  |  | 2025-07-29 |  | 2025-07-29 |  |  |  | No |  |  | Not Required
28INR0422 | Prairie Branch Solar | SS Started, FIS Started, No IA | Prairie Branch Solar | Tap 345kV #1730 Krum West - #6111 Riley Ckt 1 | Montague | NORTH | 2028-06-24 | SOL | PV | 301.14 |  | 2025-09-05 | 2025-09-09 |  | 2025-08-28 |  |  |  | No |  |  | Not Required
28INR0423 | Prairie Branch BESS | SS Started, FIS Started, No IA | Prairie Branch Energy, LLC | Tap 345kV #1730 Krum West - #6111 Riley Ckt 1 | Montague | NORTH | 2028-06-24 | OTH | BA | 310.16 |  | 2025-08-27 | 2025-09-09 |  | 2025-08-18 |  |  |  | No
28INR0433 | Blue Spring Solar | SS Started, FIS Started, No IA | Flat Creek Solar, LLC | 345 KV Clear Crossing Substation | Haskell | WEST | 2028-10-28 | SOL | PV | 301 | FIS Request | 2025-08-28 |  |  | 2025-09-22 |  |  |  | No |  |  | Not Required
28INR0434 | Viento Bravo Wind | SS Started, FIS Started, No IA | Webb Wind, LLC | Tap 345kV 80220 Cenizo - 80079 Cruce Ckt-1 | Jim Hogg | SOUTH | 2028-07-06 | WIN | WT | 366.51 | FIS Request | 2025-08-29 |  |  | 2025-09-23 |  |  |  | No |  |  | Not Required
28INR0436 | Englehardt BESS | SS Started, FIS Started, No IA | Comal BESS LLC | River Oaks (7173) | Comal | SOUTH | 2029-01-22 | OTH | BA | 200.51 | FIS Request | 2025-08-26 | 2025-09-22 |  | 2025-09-19 |  |  |  | No
28INR0442 | Zunkerville BESS | SS Started, FIS Started, No IA | Zunkerville Energy, LLC | 345kV BUS #5725 PAWNEE SWITCHING STATION | Karnes | SOUTH | 2028-06-01 | OTH | BA | 206.74 | FIS Request | 2025-09-15 | 2025-09-22 |  | 2025-09-05 |  |  |  | No
28INR0446 | Vista Bluff Wind I "Alternate POI" | SS Started, FIS Started, No IA | Vista Bluff Windpower | tap 345 kV (76000) North McCamey - (59903) Bearkat (Benedum 345 kV station that LCRA will build part of 24RPG024). | Upton | WEST | 2028-06-01 | WIN | WT | 290.4 | FIS Request | 2025-09-16 | 2025-09-22 |  | 2025-09-22 |  |  |  | No |  |  | Not Required
28INR0447 | Vista Bluff Wind II "Alternate POI" | SS Started, FIS Started, No IA | Vista Bluff Windpower | tap 345 kV (76000) North McCamey - (59903) Bearkat (Benedum 345 kV station that LCRA will build part of 24RPG024). | Upton | WEST | 2028-12-31 | WIN | WT | 290.4 | FIS Request | 2025-09-16 | 2025-09-22 |  | 2025-09-22 |  |  |  | No |  |  | Not Required
28INR0448 | Gulf Prairie BESS | SS Started, FIS Started, No IA | Gulf Prairie Energy LLC | 138kV BUS #43150 RIWOOD SUBSTATION | Brazoria | COASTAL | 2028-12-01 | OTH | BA | 207.78 | FIS Request | 2025-09-16 | 2025-09-22 |  | 2025-09-03 |  |  |  | No
29INR0003 | Aurelius Solar | SS Completed, FIS Started, No IA | IP Roman, LLC | 23908 Deaf Smith station 345 kV | Deaf Smith | PANHANDLE | 2028-06-30 | SOL | PV | 1124.24 |  | 2023-07-13 | 2023-07-18 | 2023-10-15 | 2023-07-13 |  |  |  | No |  |  | Not Required
29INR0004 | Aurelius Wind | SS Completed, FIS Started, No IA | IP Roman Wind, LLC | 23908 Deaf Smith station 345 kV | Deaf Smith | PANHANDLE | 2028-06-30 | WIN | WT | 621.6 |  | 2023-07-13 | 2023-08-14 | 2023-11-06 | 2023-08-07 |  |  |  | No |  |  | Not Required
29INR0009 | Aurelius 2 Solar | SS Completed, FIS Started, No IA | IP Roman, LLC | 23908 Deaf Smith station 345 kV. This INR has a 600 MW PUN load at the medium voltage side of the MPTs for a total of 1800 MW PUN load (refer to the substation SLD). | Deaf Smith | PANHANDLE | 2028-09-30 | SOL | PV | 445.4 |  | 2023-11-28 | 2023-12-04 | 2024-03-01 | 2023-11-30 |  |  |  | No |  |  | Not Required
29INR0010 | Aurelius 2 Wind | SS Completed, FIS Started, No IA | IP Roman Wind II, LLC | 23908 Deaf Smith station 345kV | Deaf Smith | PANHANDLE | 2028-09-30 | WIN | WT | 621.6 |  | 2023-11-28 | 2023-12-04 | 2024-03-01 | 2023-11-30 |  |  |  | No |  |  | Not Required
29INR0011 | Aurelius 3 Solar | SS Completed, FIS Started, No IA | IP Roman III, LLC | 23908 Deaf Smith station 345 kV. This INR has a 600 MW PUN load at the medium voltage side of the MPTs for a total of 1800 MW PUN load (refer to the substation SLD). | Deaf Smith | PANHANDLE | 2029-03-31 | SOL | PV | 445.4 |  | 2023-11-20 | 2023-12-04 | 2024-03-01 | 2023-11-30 |  |  |  | No |  |  | Not Required
29INR0012 | Aurelius 3 Wind | SS Completed, FIS Started, No IA | IP Roman III, LLC | 23908 Deaf Smith station 345kV | Deaf Smith | PANHANDLE | 2029-03-31 | WIN | WT | 623 |  | 2023-11-28 | 2023-12-04 | 2024-03-01 | 2023-11-30 |  |  |  | No |  |  | Not Required
29INR0013 | Cattle Drive Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | 76000 North McCamey 345kV | Crane | WEST | 2029-07-01 | SOL | PV | 307 |  | 2024-06-13 | 2024-06-13 | 2024-09-10 | 2024-06-13 |  |  |  | No |  |  | Not Required
29INR0015 | Funston Solar | SS Completed, FIS Started, IA | Funston Solar LLC | tap 345 kV 68000 West Shackelford – 68004 Phantom Hill Circuit 2 | Jones | WEST | 2027-07-01 | SOL | PV | 351.4 |  | 2024-04-03 | 2024-02-27 | 2024-05-26 | 2024-03-19 |  | Yes | 2024-10-23 | Yes | Not Required | Not Required | Not Required | 2025-09-15
29INR0017 | Big Rooter East Solar | SS Completed, FIS Started, IA | Big Rooter East, LLC | 39950 TNP One Plant 345 kV | Robertson | NORTH | 2029-05-31 | SOL | PV | 554.94 | Proj Name COD | 2024-03-04 | 2024-03-22 | 2024-06-19 | 2024-03-22 |  |  | 2025-06-01 | No |  |  | Not Required
29INR0018 | Big Rooter East Storage SLF | SS Completed, FIS Started, IA | Big Rooter East, LLC | 39950 TNP One Plant 345 kV | Robertson | NORTH | 2029-12-31 | OTH | BA | 0 | COD | 2024-03-04 | 2024-03-22 | 2024-06-19 | 2024-03-22 |  |  | 2025-06-01 | No | Not Required | Not Required
29INR0019 | Infinium Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | #1058 Longshore_5 345kV | Howard | WEST | 2029-07-01 | SOL | PV | 401.6 |  | 2024-06-03 | 2024-08-16 | 2024-10-07 | 2024-07-18 |  |  |  | No |  |  | Not Required
29INR0021 | Buzios BESS SLF | SS Completed, FIS Started, No IA | Buzios Energy Storage, LLC | Tap 345kV 59904 Cottonwood - 23922 White River Ckt 2 | Motley | PANHANDLE | 2029-07-01 | OTH | BA | 0 |  | 2025-04-03 | 2025-04-08 | 2025-07-01 | 2025-01-23 |  |  |  | No
29INR0025 | Skyrider Wind | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | 138kV #38365 TNPINION | Pecos | WEST | 2028-07-01 | WIN | WT | 370 |  | 2024-11-04 | 2024-11-19 | 2025-02-18 | 2024-10-29 |  | No |  | No |  |  | Not Required
29INR0026 | Skeeter Solar | SS Completed, FIS Started, No IA | Mesquite Solar, LLC | 345 kV SWEETWATER EAST (11420) - LONG CREEK (1435) | Jones | WEST | 2028-12-02 | SOL | PV | 251 |  |  | 2024-06-03 | 2024-08-29 | 2024-05-30 |  |  |  | No |  |  | Not Required
29INR0030 | Commodus Solar | SS Completed, FIS Started, No IA | IP Blackwell, LLC | Tap 345kV 23914 Tule Canyon - 23900 Alibates | Briscoe | PANHANDLE | 2029-07-30 | SOL | PV | 502.1 |  | 2024-07-17 | 2024-07-22 | 2024-10-17 | 2024-07-11 |  |  |  | No |  |  | Not Required
29INR0031 | Commodus Wind | SS Completed, FIS Started, No IA | IP Blackwell, LLC | tap 345kV 23914 Tule Canyon - 23900 Alibates | Briscoe | PANHANDLE | 2029-07-30 | WIN | WT | 641.4 |  | 2024-07-17 | 2024-07-22 | 2024-10-17 | 2024-07-11 |  |  |  | No |  |  | Not Required
29INR0032 | Commodus 2 Solar | SS Completed, FIS Started, No IA | IP Blackwell II, LLC | Tapping the 345 kV Double-Circuit Line from Tule Canyon (Bus# 23914) to Alibates (Bus# 23900) | Swisher | PANHANDLE | 2029-07-30 | SOL | PV | 502.1 |  | 2025-02-25 | 2025-03-03 | 2025-06-03 | 2025-02-18 |  |  |  | No |  |  | Not Required
29INR0033 | Commodus 2 Wind | SS Completed, FIS Started, No IA | IP Blackwell II, LLC | Tapping the 345 kV Double-Circuit Line from Tule Canyon (Bus# 23914) to Alibates (Bus# 23900) | Swisher | PANHANDLE | 2029-07-30 | WIN | WT | 641.48 |  | 2025-02-24 | 2025-03-03 | 2025-06-03 | 2025-02-18 |  |  |  | No |  |  | Not Required
29INR0034 | Cavell Solar | SS Completed, FIS Started, No IA | IP Cavell, LLC | Tap 345kV 23910 Windmill - 23912 Ogallala Ckt 1 | Castro | PANHANDLE | 2029-07-30 | SOL | PV | 502.1 |  | 2024-07-03 | 2024-07-22 | 2024-10-17 | 2024-06-28 |  |  |  | No |  |  | Not Required
29INR0035 | Cavell Wind | SS Completed, FIS Started, No IA | IP Cavell, LLC | tap 345kV 23910 Windmill - 23912 Ogallala Ckt 1 | Castro | PANHANDLE | 2029-07-30 | WIN | WT | 641.2 |  | 2024-07-03 | 2024-07-22 | 2024-10-17 | 2024-07-03 |  |  |  | No |  |  | Not Required
29INR0040 | Gusty Windpower | SS Completed, FIS Completed, No IA | Ballenger Windpower, LLC | Tap 345kV 59903 Bearkat - 1058 Longshore_5; Anemone 345 kV Station | Glasscock | WEST | 2028-06-01 | WIN | WT | 208.5 |  | 2024-09-12 | 2024-07-30 | 2024-10-27 | 2024-08-20 | 2025-09-25 | No |  | No |  |  | Not Required
29INR0041 | Homestead Power (TEF-Due Diligence) | SS Completed, FIS Started, No IA | Homestead Power LLC | 138 kV New Bremen #7271 | Austin | SOUTH | 2029-12-15 | GAS | GT | 260.3 |  | 2024-07-29 | 2024-07-30 | 2024-10-27 | 2024-07-29 |  |  |  | No
29INR0042 | Slager Lake Wind | SS Started, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | tap 138kV 10058 CATCLAW_8 - 1210 MIDKIFF_8 | Pecos | WEST | 2030-01-01 | WIN | WT | 310.2 | FIS Request | 2025-09-05 | 2025-09-09 |  | 2025-09-03 |  |  |  | No |  |  | Not Required
29INR0048 | Rippling Curve Peaking Power | SS Completed, FIS Started, No IA | OxyVinyls LP | 41580 TIDAL__X06B8 138kV | Harris | HOUSTON | 2029-01-01 | GAS | GT | 208 |  | 2024-07-31 | 2024-09-04 | 2024-11-27 | 2024-08-20 |  |  |  | No
29INR0050 | Amphion Solar Phase 1 | SS Completed, FIS Started, No IA | Amphion Solar, LLC | TAP 345KV (#5709) Fowlerton - (#5901) SAN MIGUEL LINE Ckt FOWRTN_SMIGL2 | Atascosa | SOUTH | 2028-09-01 | SOL | PV | 180.6 |  | 2024-10-10 | 2024-10-10 | 2025-01-07 | 2024-10-10 |  |  |  | No |  |  | Not Required
29INR0056 | Palomino Solar | SS Completed, FIS Started, No IA | Palomino Renewables | Tap 345kV 1695 Monticello - 1697 Sulphur Springs | Hopkins | NORTH | 2028-12-31 | SOL | PV | 301.2 |  | 2025-04-28 | 2024-10-18 | 2025-01-13 | 2025-04-09 |  |  |  | No |  |  | Not Required
29INR0057 | Palomino Storage | SS Completed, FIS Started, No IA | Palomino Renewables | Tap 345kV 1695 Monticello - 1697 Sulphur Springs | Hopkins | NORTH | 2028-12-31 | OTH | BA | 152.5 |  | 2025-04-28 | 2024-11-19 | 2025-01-13 | 2025-04-09 |  |  |  | No
29INR0058 | Brahman Renewables Solar | SS Completed, FIS Started, No IA | Brahman Renewables | Tap Voss Lake switch #3751 – Badger Switch #3761 345 kV | Milam | SOUTH | 2029-05-01 | SOL | PV | 100.6 |  | 2025-04-28 | 2024-10-29 | 2025-01-25 | 2025-04-09 |  |  |  | No |  |  | Not Required
29INR0059 | Brahman Renewables Storage | SS Completed, FIS Started, No IA | Brahman Renewables | Tap Voss Lake switch #3751 – Badger Switch #3761 345 kV | Milam | SOUTH | 2029-05-01 | OTH | BA | 203.1 |  | 2025-04-21 | 2024-10-29 | 2025-01-25 | 2025-04-09 |  |  |  | No
29INR0063 | Columbine Wind | SS Completed, FIS Started, No IA | Wilson Wind LLC | TAP 345KV BUS #5380 SHAULA- BUS #5133 ELM CREEK | Gonzales | SOUTH | 2029-09-01 | WIN | WT | 297.6 |  | 2025-02-18 | 2025-02-25 | 2025-05-20 | 2025-02-18 |  |  |  | No |  |  | Not Required
29INR0065 | Cash Mills Storage Center | SS Completed, FIS Started, No IA | Mills Storage Center | Tap Line between Evant (bus#7068) and Goldthwaite (Bus# 7070) | Mills | NORTH | 2029-06-01 | OTH | BA | 200.66 |  | 2025-03-28 | 2024-11-26 | 2025-02-18 | 2025-03-19 |  |  |  | No
29INR0068 | Gregory Power Development SLF | SS Completed, FIS Started, No IA | Gregory Power Partners LLC | 8580 Resnick 138kV | San Patricio | COASTAL | 2028-12-19 | GAS | CC | 469.9 | Proj Name | 2025-04-15 | 2024-11-19 | 2025-02-20 | 2025-03-26 |  |  |  | No
29INR0077 | Fluvanna Max Solar SLF | SS Completed, FIS Started, No IA | Fluvanna Max Solar LLC | 11305 DERMOTT 345 kV | Scurry | WEST | 2029-09-14 | SOL | PV | 152.7 |  | 2024-11-04 | 2024-12-19 | 2025-03-18 | 2024-11-11 |  |  |  | No |  |  | Not Required
29INR0083 | Denver City - Mustang - Gas | SS Completed, FIS Started, No IA | Golden Spread Electric Cooperative, Inc. | 23876 CLEARFRK_5 345kV | Yoakum | WEST | 2029-10-27 | GAS | GT | 472.1 |  | 2024-12-17 | 2024-12-19 | 2025-03-18 | 2024-12-17 |  |  |  | No
29INR0084 | Jolly Rock Storage Center | SS Completed, FIS Started, No IA | Jolly Rock Storage Center LLC | Tap 138kV 1431 GRAHAM Plant Switch - 11525 Short Grass Circuit 1. | Young | WEST | 2029-05-16 | OTH | BA | 208.57 |  | 2025-04-29 | 2024-12-19 | 2025-03-18 | 2025-04-23 |  |  |  | No
29INR0085 | Firefly Fields Solar | SS Completed, FIS Started, No IA | Firefly Fields Energy Center LLC | Tap 138 kV <57640> <Rock Island> - <7258> <Glidden> | Colorado | SOUTH | 2028-09-30 | SOL | PV | 100.52 |  | 2025-01-06 | 2025-01-13 | 2025-04-08 | 2024-12-09 |  |  |  | No |  |  | Not Required
29INR0088 | Cricket Storage | SS Completed, FIS Started, No IA | Cricket Storage, LLC | Tap 138kV #3179 Pauline - #3177 Eustace | Henderson | NORTH | 2028-10-05 | OTH | BA | 232.18 |  | 2025-02-10 | 2025-04-04 | 2025-06-30 | 2025-02-14 |  |  |  | No
29INR0089 | Arnold Hills Storage | SS Completed, FIS Started, No IA | Arnold Hills Storage, LLC | #6926 Seven Points 138kV | Henderson | NORTH | 2029-02-09 | OTH | BA | 122.5 |  | 2025-03-11 | 2025-03-24 | 2025-06-19 | 2025-03-07 |  |  |  | No
29INR0090 | Bandana Solar SLF | SS Completed, FIS Started, No IA | Bandana Solar, LLC | Tap 69kV Bus# 8508 Falfurrias - Bus# 8894 Premont | Jim Wells | SOUTH | 2029-02-09 | SOL | PV | 86.9 |  | 2025-03-17 | 2025-04-21 | 2025-06-19 | 2025-03-17 |  |  |  | No |  |  | Not Required
29INR0091 | Bandana Storage SLF | SS Completed, FIS Started, No IA | Bandana Solar, LLC | Tap 69kV Bus# 8508 Falfurrias - Bus# 8894 Premont | Jim Wells | SOUTH | 2029-02-09 | OTH | BA | 0 |  | 2025-03-17 | 2025-03-24 | 2025-06-19 | 2025-03-14 |  |  |  | No
29INR0103 | Meitner 2 Wind | SS Completed, FIS Started, No IA | IP Meitner, LLC | 79000 Gray Substation 345kV | Gray | PANHANDLE | 2028-06-30 | WIN | WT | 709.1 |  | 2025-05-02 | 2025-06-05 | 2025-09-02 | 2025-04-18 |  |  |  | No |  |  | Not Required
29INR0107 | 7L Solar SLF | SS Started, FIS Started, No IA | 7L Solar, LLC | Tap 69kV 5870 Brundage - 5868 Big Wells | Dimmit | SOUTH | 2029-11-13 | SOL | PV | 71.6 | FIS Request | 2025-09-15 | 2025-09-22 |  | 2025-09-12 |  |  |  | No |  |  | Not Required
29INR0108 | 7L Storage SLF | SS Started, FIS Started, No IA | 7L Solar, LLC | Tap 69kV 5870 Brundage - 5868 Big Wells | Dimmit | SOUTH | 2029-11-13 | OTH | BA | 0 | FIS Request | 2025-09-16 | 2025-09-22 |  | 2025-09-12 |  |  |  | No
29INR0109 | Rockpile Storage | SS Completed, FIS Started, No IA | Rockpile Storage, LLC | Direct to substation at 69kV Derby BUS ID #5842 | Frio | SOUTH | 2029-06-12 | OTH | BA | 104 |  | 2025-04-11 | 2025-04-21 | 2025-07-19 | 2025-03-31 |  |  |  | No
29INR0115 | Cielo Vista Storage | SS Completed, FIS Started, No IA | Cielo Vista Storage, LLC | Tap 345kV Bus #5901 Miguel5 - Bus #80079 Cruce7A Ckt 1 | Duval | SOUTH | 2028-06-30 | OTH | BA | 310.8 |  | 2025-03-18 | 2025-04-21 | 2025-07-18 | 2025-03-25 |  |  |  | No
29INR0117 | Bendito Wind | SS Started, FIS Started, No IA | Bendito Wind Farm, LLC | Tap 345 kV80220 Cenizo - 80079 Cruce Ckt 2 | Webb | SOUTH | 2029-07-13 | WIN | WT | 300 |  | 2025-07-15 | 2025-07-29 |  | 2025-07-14 |  |  |  | No |  |  | Not Required
29INR0119 | Simsboro Storage | SS Completed, FIS Started, No IA | Simsboro Storage LLC | Tap Outlaw (3386) – Limestone (46020) | Freestone | NORTH | 2029-03-31 | OTH | BA | 301.6 |  | 2025-05-09 | 2025-06-11 | 2025-09-04 | 2025-05-21 |  |  |  | No
29INR0122 | Sundance Solar | SS Completed, FIS Started, No IA | Sundance Solar, LLC | (#6076) Foxtail - (#60791) Perigee 345kV Line | Knox | WEST | 2029-07-18 | SOL | PV | 301 |  | 2025-03-28 | 2025-04-21 | 2025-07-19 | 2025-04-14 |  |  |  | No |  |  | Not Required
29INR0123 | Firefly Fields Storage | SS Completed, FIS Started, No IA | Firefly Fields Energy Center LLC | Tap 138 kV 57640 Rock Island to 7258 Glidden | Colorado | SOUTH | 2028-09-30 | OTH | BA | 156.52 |  | 2025-03-17 | 2025-03-24 | 2025-06-19 | 2025-03-19 |  |  |  | No
29INR0124 | Apricot Sun Solar | SS Completed, FIS Started, No IA | Apricot Sun Energy Center, LLC | Tap 80079 (Cruce) - 5901 (San Miguel) 345 kV Ckt 1 | Duval | SOUTH | 2029-09-30 | SOL | PV | 245.69 |  | 2025-03-26 | 2025-04-01 | 2025-06-25 | 2025-03-30 |  |  |  | No |  |  | Not Required
29INR0125 | Apricot Sun Storage | SS Completed, FIS Started, No IA | Apricot Sun Energy Center, LLC | Tap 80079 (Cruce) - 5901 (San Miguel) 345 kV Ckt 1 | Duval | SOUTH | 2029-09-30 | OTH | BA | 301.02 |  | 2025-03-26 | 2025-04-01 | 2025-06-25 | 2025-03-30 |  |  |  | No
29INR0131 | Caesar Solar | SS Started, FIS Started, No IA | Caesar Solar, LLC | 59916 Buck Canyon 345 kV | Borden | WEST | 2029-11-26 | SOL | PV | 181.6 |  | 2025-07-16 | 2025-07-29 |  | 2025-07-07 |  |  |  | No |  |  | Not Required
29INR0132 | Caesar Storage | SS Started, FIS Started, No IA | Caesar Solar, LLC | 59916 Buck Canyon 345 kV | Borden | WEST | 2029-11-26 | OTH | BA | 205.5 |  | 2025-07-16 | 2025-07-29 |  | 2025-07-07 |  |  |  | No
29INR0146 | Estrella Dorada Wind | SS Completed, FIS Started, No IA | Estrella Dorada Wind Farm, LLC | Tap 345 kV 80079 Cruce - 5901 San Miguel Ckt 2 | Duval | SOUTH | 2029-07-13 | WIN | WT | 306 | MW Size | 2025-07-16 | 2025-07-21 | 2025-09-30 | 2025-07-17 |  |  |  | No |  |  | Not Required
29INR0147 | Selenite Springs Solar | SS Completed, FIS Started, No IA | Selenite Springs Solar, LLC | Tap 138kV 38355 Leon Creek Switching Station - 38308 Woodhouse Switching Station | Pecos | WEST | 2028-07-31 | SOL | PV | 300 |  | 2025-04-16 | 2025-04-21 | 2025-07-19 | 2025-04-18 |  |  |  | No |  |  | Not Required
29INR0148 | Big Field Solar | SS Completed, FIS Started, No IA | Big Field Solar Energy LLC | 6101 RILEY7A 345kV | Wilbarger | WEST | 2029-12-31 | SOL | PV | 506.17 | FIS Request | 2025-09-16 | 2025-06-11 | 2025-09-04 |  |  |  |  | No |  |  | Not Required
29INR0151 | Juanita Creek BESS | SS Completed, FIS Started, No IA | Juanita Creek Energy Center, LLC | Tap 345 kV 5915 South Texas Project - 44200 Hillje | Matagorda | COASTAL | 2031-10-01 | OTH | BA | 303.6 |  | 2025-06-12 | 2025-06-19 | 2025-09-17 | 2025-06-13 |  |  |  | No
29INR0152 | Ranger BESS | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | SSWG Bus name: CSTROVILESB8 , Bus# : 5804 Planning Bus long name: CSTROVILESB8, 138 kV | Medina | SOUTH | 2028-04-29 | OTH | BA | 155.2 |  | 2025-05-20 | 2025-06-12 | 2025-09-04 | 2025-05-15 |  |  |  | No
29INR0160 | Cazadores Solar | SS Started, FIS Started, No IA | OCI Energy LLC | (80079) CRUCE7A – (5901) MIGUEL5 | Duval | SOUTH | 2029-04-10 | SOL | PV | 301.62 |  | 2025-06-16 | 2025-07-07 |  | 2025-06-20 |  |  |  | No |  |  | Not Required
29INR0162 | Wolf Bone North Energy Center | SS Started, FIS Started, No IA | NRG Wolf Bone Energy Center LLC | Tap 345 kV 60404 SOLTICE7A - 18669 TOYAHCRK_5 Ckt 1 Tap 345 kV 60404 SOLTICE7A - 18669 TOYAHCRK_5 Ckt 2 | Reeves | WEST | 2029-11-01 | GAS | CC | 1204 | FIS Request | 2025-09-30 |  |  | 2025-09-19 |  |  |  | No
29INR0163 | Brazos Bend Solar SLF | SS Started, FIS Started, No IA | Grenergy USA | 345 kV Line (3765) GRISTMILL_5 to (39950) TNTNP_ONE_3 | Milam | SOUTH | 2029-08-09 | SOL | PV | 244.94 | FIS Request | 2025-08-20 | 2025-09-11 |  | 2025-09-10 |  |  |  | No |  |  | Not Required
29INR0164 | Brazos Bend Storage SLF | SS Started, FIS Started, No IA | Grenergy USA | 345 kV Line (3765) GRISTMILL_5 to (39950) TNTNP_ONE_3 | Milam | SOUTH | 2029-08-09 | OTH | BA | 247.2 | FIS Request | 2025-08-20 | 2025-09-11 |  | 2025-09-10 |  |  |  | No
29INR0166 | LOST PINES GAS RECIP | SS Completed, FIS Started, No IA | LCRA | (#170174) LOST PINES 345 kV | Bastrop | SOUTH | 2029-08-02 | GAS | IC | 113.02 |  | 2025-06-27 | 2025-07-07 | 2025-09-30 | 2025-07-02 |  |  |  | No
29INR0167 | Big Watt Power Austin-1 | SS Started, FIS Started, No IA | Big Watt Power Austin-1 LLC | Tapping the 345 kV Double circuit Line: Zorn (Bus# 7042) - Lytton Springs (Bus# 9074) and Zorn (Bus# 7042) - Austrop (Bus# 7040). | Caldwell | SOUTH | 2029-11-01 | GAS | CC | 448.98 | FIS Request | 2025-09-26 |  |  | 2025-09-26 |  |  |  | No
29INR0169 | Falcon BESS | SS Started, FIS Started, No IA | Falcon Energy Project, LLC | Tap 345kV #80225 CENIZO to #80307 DEL SOL | Zapata | SOUTH | 2028-06-24 | OTH | BA | 516.72 |  | 2025-08-25 | 2025-09-09 |  | 2025-08-28 |  |  |  | No
29INR0170 | Three Ranches BESS | SS Started, FIS Started, No IA | Three Ranches Energy LLC | TAP 138kV #6680 Alamitto Creek - #60444 Hayter Ranch | Brewster | WEST | 2027-01-30 | OTH | BA | 103.37 |  | 2025-08-22 | 2025-08-21 |  | 2025-08-29 |  |  |  | No
29INR0171 | Sweetheart Solar | SS Started, FIS Started, No IA | Sweetheart Energy, LLC | Tap 345kV #1430 GRAHAM SES - # 17002 GARVEY ROAD SWITCH | Young | WEST | 2029-02-14 | SOL | PV | 301.14 |  | 2025-08-25 | 2025-08-26 |  | 2025-08-11 |  |  |  | No |  |  | Not Required
29INR0172 | Sweetheart BESS | SS Started, FIS Started, No IA | Sweetheart Energy, LLC | Tap 345kV #1430 GRAHAM SES - # 17002 GARVEY ROAD SWITCH | Young | WEST | 2029-02-14 | OTH | BA | 310.16 |  | 2025-08-25 | 2025-08-26 |  | 2025-08-11 |  |  |  | No
29INR0173 | Howard Road BESS | SS Started, FIS Started, No IA | Project Fast Flow LLC | BUS#5231 HOWARD RD 345 kV SUBSTATION | Bexar | SOUTH | 2028-04-01 | OTH | BA | 617.63 |  | 2025-07-03 | 2025-07-29 |  | 2025-07-16 |  |  |  | No
29INR0174 | Palisade BESS | SS Started, FIS Started, No IA | Flexen USA LLC | Hoffman (42810) - Lake Jackson (42880) 138 kV line | Brazoria | COASTAL | 2029-10-01 | OTH | BA | 153.5 | FIS Request | 2025-09-23 | 2025-09-23 |  | 2025-09-23 |  |  |  | No
29INR0176 | SCHNEIDER GAS RICE | SS Started, FIS Started, No IA | LCRA | Double Tap 345kV #7042 Zorn - #7040 Austrop and #7042 Zorn - #9074 Lytton Springs | Caldwell | SOUTH | 2029-08-02 | GAS | IC | 113.02 |  | 2025-07-22 | 2025-07-29 |  | 2025-07-25 |  |  |  | No
29INR0177 | Rattlesnake Gap Wind SLF | SS Started, FIS Started, No IA | ET Fuels US Inc. | 10119 Tributary Switch 138 kV | Howard | WEST | 2029-06-01 | WIN | WT | 200 | FIS Request | 2025-09-15 | 2025-09-22 |  | 2025-09-12 |  |  |  | No |  |  | Not Required
29INR0178 | Rattlesnake Gap Solar SLF | SS Started, FIS Started, No IA | ET Fuels US Inc. | 10119 Tributary Switch 138 kV | Howard | WEST | 2029-06-01 | SOL | PV | 93 | FIS Request | 2025-09-15 | 2025-09-22 |  | 2025-09-15 |  |  |  | No |  |  | Not Required
29INR0179 | Rattlesnake Gap Storage SLF | SS Started, FIS Started, No IA | ET Fuels US Inc. | 10119 Tributary Switch 138 kV | Howard | WEST | 2029-06-01 | OTH | BA | 0 | FIS Request | 2025-09-15 | 2025-09-22 |  | 2025-09-15 |  |  |  | No
29INR0180 | Tolar Energy Center | SS Started, FIS Started, No IA | NRG Tolar Power LLC | Tap 345 KV circuit 1 from 1440 Comanche Switch to 1900 Comanche Peak SES. | Hood | NORTH | 2029-11-01 | GAS | CC | 1252 | FIS Request | 2025-08-27 | 2025-09-22 |  | 2025-09-11 |  |  |  | No
29INR0181 | Glass Mountain Solar Solstice | SS Started, FIS Started, No IA | Glass Mountain Solar, LLC | 60404 SOLSTICE 345 kV | Pecos | WEST | 2029-03-31 | SOL | PV | 304 | FIS Request | 2025-08-22 | 2025-09-22 |  | 2025-09-05 |  |  |  | No |  |  | Not Required
29INR0182 | Glass Mountain Solar 2 | SS Started, FIS Started, No IA | Glass Mountain Solar, LLC | Tap 345 kV 60404 SOLSTICE - 18669 TOYAHCRK_5 | Pecos | WEST | 2029-03-31 | SOL | PV | 304.3 | FIS Request | 2025-08-25 | 2025-09-22 |  | 2025-09-05 |  |  |  | No |  |  | Not Required
29INR0183 | Glass Mountain Solar 1 | SS Started, FIS Started, No IA | Glass Mountain Solar, LLC | Tap 345 60404 SOLSTICE - 18669 TOYAHCRK_5 | Pecos | WEST | 2029-03-31 | SOL | PV | 304.3 | FIS Request | 2025-08-25 | 2025-09-22 |  | 2025-09-05 |  |  |  | No |  |  | Not Required
29INR0184 | Gridline Solar | SS Started, FIS Started, No IA | Big Lake Ranch LLC | 76005 Schneeman Draw LCRA | Crockett | WEST | 2029-07-01 | SOL | PV | 400 |  | 2025-07-31 | 2025-08-18 |  | 2025-07-31 |  |  |  | No |  |  | Not Required
29INR0188 | Star Of Texas Solar | SS Started, FIS Started, No IA | BOULEVARD ASSOCIATES, LLC | AEP Solstice (60404) to Bakersfield (76002) | Pecos | WEST | 2029-07-01 | SOL | PV | 415 |  | 2025-08-05 | 2025-08-18 |  | 2025-08-12 |  |  |  | No |  |  | Not Required
30INR0002 | Southeast Oklahoma Pumped Storage | SS Completed, FIS Started, No IA | Apex Energy Solutions, LLC | 1692 Paris Switch 345kV | Lamar | NORTH | 2030-01-01 | WAT | OT | 1232 |  | 2023-03-28 | 2022-08-05 | 2022-11-01 | 2023-03-10 |  |  |  | No
30INR0003 | Hecate Energy Jamaica Wind | SS Completed, FIS Not Started, No IA | Hecate Energy LLC | 42000 P. H. Robinson 345kV | Galveston | HOUSTON | 2030-06-01 | WIN | WT | 1029.39 |  |  | 2023-06-28 | 2023-09-25 | 2024-06-14 18:19 |  |  |  | No |  |  | Not Required
30INR0004 | Hecate Energy Arkansas Wind | SS Completed, FIS Started, No IA | Hecate Energy Gulf Wind LLC | 8659 Naismith 345kV | San Patricio | COASTAL | 2030-06-01 | WIN | WT | 1029.39 |  | 2024-05-15 | 2023-06-28 | 2023-09-22 | 2024-04-03 15:06 |  |  |  | No |  |  | Not Required
30INR0005 | Woodland Energy Storage | SS Completed, FIS Started, No IA | Woodland Energy Storage, LLC | 68040 Kopperl Substation 345kV | Bosque | NORTH | 2030-10-01 | OTH | BA | 207.6 |  | 2023-10-28 | 2023-12-18 | 2024-03-15 | 2023-10-23 |  |  |  | No
30INR0018 | Big Canyon Wind | SS Completed, FIS Started, No IA | Longfellow Wind, LLC | 38441 Bottlebrush 345kV | Pecos | WEST | 2031-07-01 | WIN | WT | 1500 |  | 2025-01-07 | 2025-01-13 | 2025-04-08 | 2025-01-08 |  |  |  | No |  |  | Not Required
30INR0041 | Bell Song Solar | SS Completed, FIS Started, No IA | Bell Song Solar, LLC | Tap 345 kV #80079 CRUCE7A - #80355 DELSOL7A ckt 1 | Jim Hogg | SOUTH | 2029-09-15 | SOL | PV | 167.6 |  | 2025-05-15 | 2025-06-12 | 2025-09-04 | 2025-05-22 |  |  |  | No |  |  | Not Required
30INR0047 | Mandolin Load | SS Started, FIS Started, No IA | Mandolin Solar Project, LLC | Del Sol (Series CAP LINE SIDE) BUS #80307 to Cenizo (CAP LINE SIDE) BUS #80225 Transmission Line | Starr | SOUTH | 2028-11-15 | SOL | PV | 0 |  | 2025-07-09 | 2025-07-29 |  | 2025-07-18 |  |  |  | No |  |  | Not Required
30INR0049 | Bell Song Solar 2 | SS Completed, FIS Started, No IA | Bell Song Solar, LLC 2 | Tap 345kV (#80079) CRUCE7A - (#80355) DELSOL7A ckt 1 | Jim Hogg | SOUTH | 2030-03-16 | SOL | PV | 167.6 |  | 2025-06-04 | 2025-06-12 | 2025-09-05 | 2025-06-06 |  |  |  | No |  |  | Not Required
30INR0051 | Sim Gideon Combined Cycle | SS Completed, FIS Started, No IA | LCRA | (#7310) SIM GIDEON 138 kV | Bastrop | SOUTH | 2030-12-15 | GAS | CC | 880 |  | 2025-06-12 | 2025-06-19 | 2025-09-17 | 2025-06-13 |  |  |  | No
30INR0052 | Lost Pines Power Park | SS Completed, FIS Started, No IA | LCRA | (#170174) LOST PINES 345 kV | Bastrop | SOUTH | 2030-12-15 | GAS | CC | 880 |  | 2025-06-06 | 2025-06-19 | 2025-09-17 | 2025-06-11 |  |  |  | No
30INR0053 | MRR Solar | SS Started, FIS Started, No IA | BOULEVARD ASSOCIATES, LLC | Solstice Substation #60384 -AEP | Pecos | WEST | 2030-07-01 | SOL | PV | 500 |  | 2025-07-15 | 2025-07-29 |  | 2025-07-18 |  |  |  | No |  |  | Not Required
30INR0054 | SCHNEIDER COMBINED CYCLE | SS Started, FIS Started, No IA | LCRA | Double Tap 345kV #7042 Zorn - #7040 Austrop and #7042 Zorn - #9074 Lytton Springs | Caldwell | SOUTH | 2030-12-15 | GAS | CC | 880 |  | 2025-07-22 | 2025-07-29 |  | 2025-07-25 |  |  |  | No
30INR0058 | Springfield Solar | SS Started, FIS Started, No IA | BOULEVARD ASSOCIATES, LLC | Tap Leon Creek (#38355) to Woodhouse Station (#38308) 138kV line | Pecos | WEST | 2030-07-01 | SOL | PV | 400 | FIS Request | 2025-08-12 | 2025-09-09 |  | 2025-09-08 |  |  |  | No |  |  | Not Required
31INR0009 | Bell Song Solar 3 | SS Completed, FIS Started, No IA | Bell Song Solar, LLC_3 | Tap 345 kV #80079 CRUCE7A - #80355 DELSOL7A ckt 1 | Jim Hogg | SOUTH | 2030-08-31 | SOL | PV | 167.6 |  | 2025-06-12 | 2025-06-19 | 2025-09-17 | 2025-06-13 |  |  |  | No |  |  | Not Required
31INR0010 | LOST PINES GAS RECIP PHASE 2 | SS Completed, FIS Started, No IA | LCRA | (#170174) LOST PINES 345 kV | Bastrop | SOUTH | 2031-05-10 | GAS | IC | 113.02 |  | 2025-06-27 | 2025-07-07 | 2025-09-30 | 2025-07-02 |  |  |  | No
31INR0011 | SIM GIDEON GAS RICE | SS Started, FIS Started, No IA | LCRA | (#7310) SIM GIDEON 138 kV | Bastrop | SOUTH | 2031-05-10 | GAS | IC | 226.03 |  | 2025-07-03 | 2025-07-29 |  | 2025-07-08 |  |  |  | No
31INR0013 | SCHNEIDER GAS RICE PHASE 2 | SS Started, FIS Started, No IA | LCRA | Double Tap 345kV #7042 Zorn - #7040 Austrop and #7042 Zorn - #9074 Lytton Springs | Caldwell | SOUTH | 2031-05-10 | GAS | IC | 113.02 |  | 2025-07-22 | 2025-07-29 |  | 2025-07-25 |  |  |  | No

## Project Details - Small Gen
GIM Project Details - Small Generators
NOTES:
Due to Protocol confidentiality provisions, only those Small Generator projects are included for which ERCOT has (1) received written Notice from Interconnecting Entities (IE) that authorize the project
information to be made public, or (2) approved the IE's completed Resource Registration form as indicated by assignment of a “Model Ready Date".
Excludes projects that have a status of Inactive (status = INA).
INR | Project Name | Model Ready Date | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) | Change indicators: Proj Name, MW | IA Signed | Financial Security | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Size, COD, SFS. |  | Required to fund
[11 empty] | Status Change INA-to-PLN |  | Dist. Upgrades
12INR0059b | HOVEY (Barilla Solar 1B) | 2015-09-02 | First Solar | 60385 Solstice 138kV | Pecos | WEST | 2025-11-30 | SOL | PV | 7.4 |  | 2013-12-26 | Yes | 2015-09-02 | 2015-09-14
22INR0596 | Grizzly Ridge BESS SLF | 2022-09-01 | Grizzly Ridge Solar LLC | Pottsville Switching Substation (Bus# 178) | Hamilton | NORTH | 2026-07-01 | OTH | BA | 0 |  | 2021-10-18 | Yes | 2023-02-10
22INR0608 | Wharton BESS | 2025-05-01 | I-eye Storage LLC | Property: 29.3134928 N, 96.1081571 W. Site is adjacent to Centerpoint substation. Station Name (TDSP Station Code): WR (Wharton) Load/Load Transformer Name:TR4 PTI BUS number #43570 Voltage in kV (Transmission): 138 kV transmission voltage | Wharton | SOUTH | 2025-11-18 | OTH | BA | 9.96 |  | 2024-03-18 | Yes
23INR0483 | Rio Nogales CT1 Rotor Replacement | 2023-04-12 | CPS Energy | Rio Nogales Substation 5362 RIONOG 345kV | Guadalupe | SOUTH | 2023-06-08 | GAS | CC | 3.1 |  | 2023-01-20 | Yes |  | 2023-04-27
23INR0499 | Laureles BESS | 2024-09-05 | Regis Laureles LLC | Station Name (TDSP Station Code) LAURELES; Load/Load Transformer Name LD01; PTI BUS number 5756; Voltage in kV (Transmission Level) 138kV | Cameron | COASTAL | 2025-11-12 | OTH | BA | 9.9 |  | 2023-02-16 | Yes | 2025-05-23 | 2025-07-15
23INR0529 | Torrecillas BESS | 2024-09-05 | Torrecillas Interconnect, LLC | 161257 Torrecillas 345kV Station code: TORR | Webb | SOUTH | 2025-12-31 | OTH | BA | 9.9 | COD | 2015-01-30 | Yes | 2025-06-25 | 2025-07-01
23INR0552 | Milton BESS | 2025-01-15 | Regis Milton LLC | Station Name (TSP Station Code): MILTON; Load/Load Transformer Name: LD_1; PTI Bus Number: 78583; Voltage in kV (Transmission Level): 138 kV | Karnes | SOUTH | 2025-08-12 | OTH | BA | 9.9 |  | 2023-09-07 | Yes | 2025-04-01 | 2025-04-11
23INR0556 | IEP Orchard BESS | 2024-01-04 | IEP Tejas Verde LLC | Station Name (TDSP Station Code): OR Load/Load Transformer Name :TR1 PTI BUS number: 44541 Voltage in kV (Transmission Level): 138 kV Project Size: 9.99 MW battery energy storage (BESS) system; 50 MWh connecting on CNP 34.5kV Distribution System. | Fort Bend | HOUSTON | 2025-10-16 | OTH | BA | 9.99 |  | 2023-08-09 | Yes | 2024-11-12 | 2024-12-06
23INR0603 | Damon BESS 2 | 2024-07-03 | PR DAMON, LLC | 9.99 MW 50 MWh battery energy storage project connecting at 12.47kV Damon (DA) substation. Station Name (TDSP Station Code): DA Load/Load Transformer Name: TR2 PTI BUS number: 42370 Voltage in kV (Transmission Level): 138 kV | Brazoria | COASTAL | 2026-08-21 | OTH | BA | 9.99 |  | 2023-10-06 | Yes
23INR0617 | Hidden Lakes BESS | 2024-08-01 | SBESS TX 6 LLC | Station Name: HDNLAKES PTI Bus#: 38900 Load XFMR Name: HDLAKE_2 Transmission Level Voltage: 138 kV | Galveston | HOUSTON | 2026-02-16 | OTH | BA | 9.9 |  | 2024-02-07 | Yes
23INR0790 | DAMON BESS3 | 2025-09-04 | BarBar Storage LLC | Station Name: DAMON TSP Station Code: DA Load/Load Transformer Name: TR2 PTI BUS number: 42370 Voltage in kV (Transmission Level): 138 kV Node (associated w/ load/load XFRM in NMMS): TR2 | Brazoria | COASTAL | 2025-12-01 | OTH | BA | 9.96 | COD | 2024-01-30 | Yes | 2025-09-29
24INR0499 | Medina Lake BESS | 2024-09-05 | Regis Medina Lake LLC | Station Name (TDSP Station Code) MEDILA; Load/Load Transformer Name T2; PTI BUS number 7432; Voltage in kV (Transmission Level) 138kV | Bandera | SOUTH | 2025-12-20 | OTH | BA | 9.8 | COD | 2023-01-18 | Yes | 2025-02-04 | 2025-04-01
24INR0501 | Utopia BESS | 2026-01-07 | Regis Utopia, LLC | Station Name (TDSP Station Code): UTOPIA; Load/Load Transformer Name: UTOPIAT1; PTI BUS number: 7428; Voltage in kV (Transmission Level): 69kV Transformers: 3x 4000kVA 800VAC Δ - 12.47kVA Υ 12,000 MVA connected, Running load limited to 9.99 MW | Bandera | SOUTH | 2026-05-04 | OTH | BA | 9.8 | COD | 2023-01-18 | Yes
24INR0594 | Hidden Valley BESS | 2025-02-05 | Regis Hidden Valley, LLC | Station Name (TSP Station Code): Hidden Valley (HV) Load/Load Transformer Name: TR4 PTI Bus Number: 45862 Voltage in kV (Transmission Level): 138 kV | Harris | HOUSTON | 2025-10-24 | OTH | BA | 9.9 |  | 2023-09-11 | Yes
24INR0595 | Gears BESS | 2024-11-01 | Regis Gears-Harris LLC | Station Name (TSP Station Code): Gears (GZ) Load/Load Transformer Name: TR1 PTI Bus Number: 45781 Voltage in kV (Transmission Level): 138 kV | Harris | HOUSTON | 2025-10-21 | OTH | BA | 9.9 |  | 2023-09-20 | Yes | 2025-07-21 | 2025-07-28
24INR0602 | CPS Rio Nogales CT301 Rotor Replacement | 2024-04-24 | CPS Energy | 5362 RIONOG 345kV | Guadalupe | SOUTH | 2025-09-30 | GAS | CC | 3.1 |  | 2023-11-10 | Yes |  | 2024-04-03
24INR0628 | Palmview BESS | 2025-03-05 | SBESS TX14 LLC | Palmview XFMR 2 CKT 6790 Substation transmission - 138kv ERCOT station code - PALMVIEW PTI Bus # 8387 ERCOT Load Name - LD02 | Hidalgo | SOUTH | 2025-11-30 | OTH | BA | 9.9 |  | 2024-04-15 | Yes
24INR0638 | Cotulla BESS 1 | 2025-03-05 | SBESS TX19 LLC | Cotulla Substation XFMR 2 #460 CKT Sub max transmission - 138kv Substation name - COTULLA Bus # 8610 Load - LOAD02 | La Salle | SOUTH | 2025-11-27 | OTH | BA | 9.9 | COD | 2024-04-15 | Yes | 2025-07-02 | 2025-08-19
24INR0642 | SE Edinburg BESS | 2025-03-05 | SBESS TX16 LLC | Southeast Edinburg, XFMR 2, #6580 CKT, SOUTHEAST EDINBURG, SE_EDINB, Ercot Bus # 8374, Ercot Load name - 138_12_2 | Hidalgo | SOUTH | 2025-11-17 | OTH | BA | 9.9 |  | 2024-04-26 | Yes
24INR0645 | COYOTE SPRINGS AGR1 | 2024-06-05 | HEN INFRASTRUCTURE, LLC 1 | Station Name: COYOTSPR Load Name: COYOTE_1 Bus#: 38113 Voltage: 138 kV DAC: COYOTSPR_LD8 COYOTSPR/COYOTE_1/38113/COYOTSPR_LD8 | Reeves | WEST | 2025-11-26 | OIL | OT | 9.95 |  | 2023-10-16 | Yes
24INR0646 | SADDLEBACK AGR1 | 2024-06-05 | HEN INFRASTRUCTURE, LLC 1 | SADLBACK/SADLBK_1/38058/SADLBACK_LD8 | Reeves | WEST | 2025-11-26 | OIL | OT | 9.95 |  | 2023-10-16 | Yes
24INR0647 | OLNEY AGR1 | 2024-06-05 | HEN INFRASTRUCTURE, LLC 1 | OLNEYTN/OLNEY_2/37830/OLNEYTN_LD2 | Young | WEST | 2025-12-12 | OIL | OT | 9.95 | COD | 2023-10-16 | Yes | 2025-04-08 | 2025-05-01
24INR0659 | Empire Central BESS | 2024-10-02 | SMT Dallas III LLC | Station name: EMPCT, Load name: LDLXFMR2, XFMR Number: 2, Bus Number:2799, Voltage: 138kV | Dallas | NORTH | 2025-09-22 | OTH | BA | 9.95 |  | 2024-05-20 | Yes | 2025-07-28 | 2025-08-19
25INR0592 | Carrizo Springs BESS | 2025-04-02 | Regis Carrizo Springs LLC | Station Name: CARRIZO SPRINGS Station Code: CARIZZO Load/Load XFMR Name: LOAD1 PTI Bus Number: #8244 Voltage in kV (Transmission): 69 kV Distribution Voltage: 12.47 kV | Dimmit | SOUTH | 2025-12-06 | OTH | BA | 9.99 | COD | 2023-11-29 | Yes | 2025-05-16 | 2025-07-16
25INR0593 | Escondido BESS | 2025-04-02 | Regis Escondido LLC | Station Name: ESCONDIDO TSP Station Code: ESCONDID Load Transformer Name: LOAD2 Bus #: 8260 Voltage in kV (Transmission Level): 138 kV | Maverick | SOUTH | 2026-03-05 | OTH | BA | 9.99 | COD | 2023-11-29 | Yes
25INR0594 | Goodwin BESS | 2025-04-02 | Regis Goodwin LLC | Station Name: GOODWIN TSP Station Code: GOODWIN Load Transformer Name: 138_12_1 Bus #: 8355 Voltage in kV (Transmission Level): 138 kV | Hidalgo | SOUTH | 2025-11-22 | OTH | BA | 9.99 | COD | 2023-11-29 | Yes | 2025-05-30 | 2025-07-11
25INR0597 | Lyssy BESS | 2025-05-01 | Regis Lyssy LLC | TSP Station Name: LYSSY TSP Station Code: LYSSY Load Name/ Load Transformer Name: Lyssy1 Bus # - PTI Bus Number: #8193 Voltage in kV (Transmission Level): 138 kV Node (associated w/ load/load XFMR in NMMS): 0001 | Wilson | SOUTH | 2025-12-22 | OTH | BA | 9.9 |  | 2023-11-07 | Yes | 2025-06-12 | 2025-08-21
25INR0647 | Lantana BESS | 2025-05-01 | Aggreko MSR Grid PC2 | Station Name: LANTANA Load Name or Load Transformer name: LOAD1 Bus#: 8965 Voltage: 69kV | Nueces | COASTAL | 2026-01-03 | OTH | BA | 9.99 |  | 2024-03-17 | Yes | 2025-09-12
25INR0648 | East Harrison BESS | 2025-05-01 | Aggreko MSR Grid PC5 | Station Name: E_HARRIS Load Name or Load Transformer name: 69_12_1 Bus#: 8323 Voltage: 69kV | Cameron | COASTAL | 2026-01-03 | OTH | BA | 9.99 |  | 2024-03-17 | Yes | 2025-09-03
25INR0649 | Olmito BESS | 2025-05-01 | Aggreko MSR Grid PC7 | Station Name: OLMITO Load Name or Load Transformer name: LD1 Bus#: 8950 Voltage: 138kV | Cameron | COASTAL | 2025-12-05 | OTH | BA | 9.99 |  | 2024-03-17 | Yes | 2025-07-24 | 2025-07-31
25INR0650 | Buda BESS | 2025-08-06 | Buda Infra LLC | Transmisson kV - 138 Interconnection kV - 24.9 EROCT Bus # - 70498 ERCOT Load Name - BUDA_T1 Station Code - BUDA | Hays | SOUTH | 2026-04-08 | OTH | BA | 9.9 |  | 2025-02-26 | Yes
25INR0655 | Elm Street BESS | 2025-07-02 | Elm St Infra LLC | Station Code: ELM_ST Load Name: ELMST_2 Bus # 38049 138kv | Reeves | WEST | 2026-02-13 | OTH | BA | 9.9 |  | 2025-01-02 | Yes
25INR0665 | CPS Rio Nogales CT201 Rotor Replacement | 2025-04-02 | CPS Energy | 5362 RIONOG 345kV | Guadalupe | SOUTH | 2025-09-30 | GAS | CC | 3.1 |  | 2025-02-07 | Yes |  | 2025-04-02
25INR0696 | BESS Stadium | 2025-07-02 | Grenergy USA | Substation: Stadium, XFMR # Substation transmission kV: 69kV ERCOT Station Long Name (ERCOT model): STADIUM ERCOT Station site code (short name): STADIUM ERCOT BUS# 8889 ERCOT Load Name: 2_69_12 | Jim Wells | SOUTH | 2025-12-23 | OTH | BA | 9.9 | COD | 2024-02-26 | Yes
25INR0697 | MESQUITE BESS | 2025-07-02 | Grenergy USA | Substation: Mesquite, XFMR 1 Substation transmission kV: 138 ERCOT Station Long Name: MESQUITE ERCOT Station site code: MESQUITE ERCOT Bus#: 8554 ERCOT Load Name: Load1 | Cameron | COASTAL | 2026-01-28 | OTH | BA | 9.9 | COD | 2024-02-26 | Yes
25INR0701 | Abilene Elmcreek BESS | 2025-01-08 | DGSP2 LLC | Station Name: Abilene Elm Creek TSP Station Code: ELMCRK Load Transformer name: LOAD1 Bus#: 6255 Voltage in kV (Transmission Level): 138kV | Taylor | WEST | 2025-11-26 | OTH | BA | 9.9 |  | 2024-08-15 | Yes
25INR0702 | Abilene Industrial Park BESS | 2025-01-08 | Distributed Generation Solutions LLC | Station Name: Abilene Industrial Park TSP Station Code: ABINDUST Load Transformer name: LOAD1 Bus#: 60772 Voltage in kV (Transmission Level): 138kV | Taylor | WEST | 2025-11-26 | OTH | BA | 9.9 |  | 2024-08-15 | Yes
25INR0710 | Cedarvale Gas | 2025-12-03 | RPC Merchant LLC | Station Name: CEDRVALE Load Name: CEDRVL_3 TNMP Transformer Name: Xfmr T-3 (25kV) Bus#: 38145 Transmission Voltage: 138kV Node: 9247 | Ward | WEST | 2026-03-02 | GAS | IC | 9.9 |  | 2025-03-03 | Yes
25INR0715 | Poteet BESS | 2025-03-05 | HEN INFRASTRUCTURE, LLC 1 | TSP Station Name: POTEET SUB TSP Station Code: POTEETS Load Name: POTEE_1 Bus#: 5710 kV: 69 | Atascosa | SOUTH | 2025-12-19 | OTH | BA | 9.95 |  | 2024-08-07 | Yes | 2025-05-07 | 2025-09-09
25INR0717 | Beck_Road BESS1 | 2025-12-10 | Bexar Corrilla LLC | TSP Station Name: Beck Road TSP Station Code: Z0 Load Name / Load Transformer Name: LXFMR3 Bus #: PTI Bus Number: 5035 Voltage (Transmission level kV): 138 Node (associated w/ load/load XFMR in NMMS): 0001 | Bexar | SOUTH | 2026-01-10 | OTH | BA | 9.99 |  | 2025-08-12 | Yes
25INR0718 | Pyote Gas | 2026-01-07 | RPC Merchant LLC | Station Name: PYOTE Load Name: PYOTE_1B TNMP Transformer Name: Xfmr T1-E (25kV) Bus#: 38001 Transmission Voltage: 138kV Node: 8401 | Ward | WEST | 2026-03-02 | GAS | IC | 9.9 |  | 2025-03-03 | Yes
25INR0742 | Gears BESS2 | 2025-11-05 | ESTX-PLD-HOUSTON7, LLC | TSP STATION NAME: GEARS TSP STATION CODE: GEARS/GZ LOAD TRANSFORMER NAME: GZ-TG_BESS BUS#: 45781 VOLTAGE: 138kV NODE: TR2 | Harris | HOUSTON | 2025-12-15 | OTH | BA | 9.95 | COD | 2024-04-30 | Yes
25INR0743 | BERRY BESS1 | 2025-11-05 | ESTX-PLD-HOUSTON8, LLC | TSP STATION NAME: BERRY Substation TSP STATION CODE: BERRY/BY LOAD TRANSFORMER NAME: TR4 BUS#: 45670 VOLTAGE: 138kV NODE: TR4 | Harris | HOUSTON | 2025-12-15 | OTH | BA | 9.95 | COD | 2025-05-23 | Yes
25INR0747 | Knapp BESS | 2025-09-04 | Knapp ESS Assets, LLC | Station Name: KNAPP Station Code: KNAPP Station Bus Number: #1310 Station Transmission Voltage: 138 kV Load/Load Transformer Name: LDLXFMR2 Distribution Voltage: 12.47 kV | Scurry | WEST | 2025-10-31 | OTH | BA | 9.95 |  | 2025-03-13 | Yes
25INR0763 | Alamo Street BESS | 2025-11-05 | Alamo Clean Energy Center, LLC | New DESR on the coordinates above tie at 12.47kV to: TSP Station Name: Alamo TSP Station Code: Alamo_ST Load Name: Alamo_3 Bus #: PTI Bus Number: 38331 Voltage (Transmission level kV): 138kV Node (load/load XFMR in NMMS): 9643 | Pecos | WEST | 2025-12-27 | OTH | BA | 9.99 |  | 2024-12-27 | Yes
25INR0764 | Downtown BESS | 2025-11-05 | Fort Stockton Clean Energy Center, LLC | New DESR on the coordinates above tie at 12.47kV to: TSP Station Name: Downtown TSP Station Code: TNFS Load Name: LOAD2 Bus #: PTI Bus Number: 38360 Voltage (Transmission level kV): 69kV Node (load/load XFMR in NMMS): 0007 | Pecos | WEST | 2025-12-27 | OTH | BA | 9.99 |  | 2024-12-27 | Yes
25INR0765 | Elm Street BESS2 | 2025-11-05 | North Pecos Clean Energy Center, LLC | New DESR on the coordinates above tie at 12.47kV to: TSP Station Name: Elm Street TSP Station Code: ELM_ST Load Name: ELMST_3 Bus #: PTI Bus Number: 38049 Voltage (Transmission level kV): 138kV Node (load/load XFMR in NMMS): 8912 | Reeves | WEST | 2025-12-27 | OTH | BA | 9.99 |  | 2024-12-27 | Yes
25INR0766 | Mesquite BESS2 | 2025-11-05 | Mesquite Clean Energy Center, LLC | New DESR on the coordinates above tie at 12.47kV to: TSP Station Name: Mesquite TSP Station Code: MESQUITE Load Name: LOAD2 Bus #: PTI Bus Number: 8554 Voltage (Transmission level kV): 138kV Node (load/load XFMR in NMMS), Tranformer: #2 | Cameron | COASTAL | 2025-12-27 | OTH | BA | 9.99 |  | 2024-05-23 | Yes
26INR0512 | County Road BESS | 2025-07-02 | County Rd Infra LLC | COUNTY ROAD COUNTY ROAD SUB TNP 138kv CNTYRDS Bus # 38047 Load Name - CNTYRD_1 | Reeves | WEST | 2026-03-06 | OTH | BA | 9.9 |  | 2025-01-01 | Yes
26INR0520 | Highway 6 BESS | 2025-08-06 | Hwy 6 Infra LLC | substation - HWY6 Substation kv - 138 Ercot Lond Name - Highway 6 ERCOT station code - HWY6 ERCOTBus # - 6 ERCOTLoad Name - HWY6_1 NMMS Node #: 3165 | Brazos | NORTH | 2026-03-07 | OTH | BA | 9.9 |  | 2025-01-30 | Yes
26INR0574 | Apple BESS | 2025-10-01 | Apple Infra LLC | Station Name - Apple Oncor 5-digit code - APPLE Oncor XFMR # - 1 ERCOT Bus Name - APPLE_9 ERCOT Bus # 1276 EROCT Load Name - LDLXFMR1 Substation Transmission kV - 138 | Ector | WEST | 2026-05-05 | OTH | BA | 9.9 |  | 2025-04-03 | Yes
26INR0682 | North Edinburg BESS 1 | 2025-10-01 | Edinburg ESS Assets LLC | TSP Station Name: North Edinburg TSP Station Code: NEDIN Load Name / Load Transformer Name: LOAD3 Bus #: PTI Bus Number: 8380 Voltage (Transmission level kV): 138 kV Node (associated w/ load/load XFMR in NMMS): LD03 | Hidalgo | SOUTH | 2026-01-27 | OTH | BA | 9.99 |  | 2025-06-10 | Yes
26INR0691 | Harlingen #1 BESS 1 | 2025-10-01 | Harlingen ESS Assets LLC | TSP Station Name: Harlingen #1 TSP Station Code: HARLIN_1 • Load Name / Load Transformer Name: 69_12_1 Bus #: PTI Bus Number:8321 Voltage (Transmission level kV):69kV Node (associated w/ load/load XFMR in NMMS): Transformer 1 | Cameron | COASTAL | 2025-12-23 | OTH | BA | 9.99 |  | 2025-06-18 | Yes
26INR0699 | Meadow Park BESS | 2025-12-10 | Meadow Park ESS Assets, LLC | Station Name: Meadow Park ¦ Oncor 5-digit code: MDWPK ¦ Oncor XFMR Number: 2 ¦ ERCOT Bus Name: MEADPRK1_8 ¦ ERCOT Bus#: 2039 ¦ ERCOT Load Name: LDLXFMR2 ¦ Substation Transmission kV: 138 kV ¦ ERCOT Node#: CN1 | Tarrant | NORTH | 2026-01-26 | OTH | BA | 9.95 |  | 2023-10-27 | Yes

## GIM Trends
GIM Trends
Reflects all Large Generator projects for which a Security Screening Study has been requested. The third table reflects all Small Generator projects whose GIM applications have been approved.
Excludes projects that have a status of Inactive (status = INA).
Nameplate capacity will change across time due to additional projects, cancelations, expirations, adjustments from study results, and projects being placed into service.
| Year | Month | Total Projects |  |  | Project Count | [5 empty] | Project Capacity (MW)
[6 empty] | GIM milestones | [5 empty] | Fuel Type
|  |  |  | Small Generator Not Model Ready | Small Generator Model Ready | Initial Screening Study | Screening Study Complete | In Full Study | Completed Full Study | Signed Interconnection Agreement | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Battery | Other
| 2022 | Sep | 1192 | 21 | 4 | 56 | 107 | 649 | 58 | 297 | 10 | 22920.32 | 120296.29 | 11551.44 | 0 | 0 | 53 | 74877.41 | 2486.27
| 2022 | Oct | 1205 | 22 | 6 | 60 | 100 | 667 | 49 | 301 | 10 | 23024.78 | 122584.5 | 11513.34 | 0 | 0 | 53 | 75629.54 | 2486.27
| 2022 | Nov | 1214 | 22 | 8 | 56 | 90 | 682 | 52 | 304 | 18 | 23198.34 | 122704.82 | 12277.1 | 0 | 0 | 53 | 78746.39 | 2486.27
| 2022 | Dec | 1254 | 21 | 8 | 40 | 102 | 722 | 53 | 308 | 10 | 23875.87 | 123340.4 | 12935.1 | 0 | 0 | 53 | 82844.41 | 2486.27
| 2023 | Jan | 1298 | 23 | 5 | 51 | 105 | 736 | 63 | 315 | 1 | 24350.74 | 125568.83 | 12542.1 | 0 | 0 | 53 | 88430.16 | 2486.27
| 2023 | Feb | 1334 | 18 | 13 | 48 | 109 | 761 | 68 | 317 | 1 | 24702.44 | 127309.1 | 12542.1 | 0 | 0 | 53 | 91492.71 | 2486.27
| 2023 | Mar | 1373 | 14 | 17 | 39 | 100 | 810 | 73 | 320 | 22 | 25741.94 | 127764.63 | 12544.1 | 0 | 0 | 53 | 96356.26 | 2235.03
| 2023 | Apr | 1385 | 15 | 18 | 33 | 89 | 825 | 80 | 325 | 20 | 23702.82 | 129236.52 | 12984.8 | 0 | 0 | 53 | 96078.43 | 2235.03
| 2023 | May | 1424 | 18 | 20 | 36 | 86 | 843 | 86 | 335 | 19 | 22472.25 | 129506.95 | 13026 | 0 | 0 | 53 | 102825.36 | 2235.03
| 2023 | Jun | 1479 | 28 | 22 | 51 | 83 | 872 | 82 | 341 | 16 | 27151.55 | 130857.4 | 12476.33 | 0 | 0 | 53 | 109379.63 | 2235.03
| 2023 | Jul | 1500 | 25 | 28 | 50 | 76 | 903 | 83 | 335 | 16 | 28615.02 | 133978.64 | 12368.43 | 0 | 0 | 53 | 110408 | 2385.63
| 2023 | Aug | 1537 | 31 | 30 | 45 | 82 | 927 | 85 | 337 | 7 | 32034.48 | 136165.24 | 11841.53 | 0 | 0 | 53 | 111579.02 | 2235.03
| 2023 | Sep | 1580 | 40 | 32 | 43 | 102 | 924 | 93 | 346 | 15 | 31639.72 | 141315.27 | 11383.73 | 0 | 0 | 53 | 114563.15 | 2235.03
| 2023 | Oct | 1628 | 41 | 32 | 49 | 102 | 952 | 99 | 353 | 16 | 31915.72 | 143221.48 | 13637.63 | 0 | 0 | 53 | 120534.12 | 2235.03
| 2023 | Nov | 1656 | 44 | 30 | 55 | 99 | 961 | 92 | 375 | 10 | 32509.57 | 142605.97 | 15457.28 | 0 | 0 | 53 | 124941.16 | 2385.03
| 2023 | Dec | 1671 | 41 | 28 | 39 | 116 | 974 | 92 | 381 | 12 | 34590.95 | 145654.02 | 15482.78 | 0 | 0 | 53 | 127067.73 | 2367
| 2024 | Jan | 1731 | 42 | 29 | 35 | 133 | 1011 | 95 | 386 | 12 | 36260.89 | 148135.32 | 15546.14 | 0 | 0 | 53 | 133592.45 | 2246.85
| 2024 | Feb | 1783 | 43 | 27 | 65 | 132 | 1023 | 102 | 391 | 13 | 37214.97 | 152097.86 | 16022.14 | 0 | 0 | 0 | 140219.15 | 2966.85
| 2024 | Mar | 1775 | 39 | 29 | 80 | 100 | 1035 | 101 | 391 | 64 | 35119.62 | 155272.52 | 15428.85 | 0 | 0 | 0 | 141483.67 | 2331.85
| 2024 | Apr | 1780 | 42 | 33 | 58 | 115 | 1025 | 112 | 395 | 15 | 32956.29 | 152916.51 | 15572.93 | 0 | 0 | 0 | 145000.4 | 2331.85
| 2024 | May | 1813 | 39 | 41 | 48 | 129 | 1023 | 125 | 408 | 9 | 33886.77 | 154225.29 | 15937.93 | 0 | 0 | 0 | 149001.55 | 2331.85
| 2024 | Jun | 1812 | 34 | 44 | 20 | 137 | 1023 | 140 | 414 | 27 | 31452.23 | 152433.39 | 17088.71 | 0 | 0 | 0 | 147743.45 | 2331.85
| 2024 | Jul | 1858 | 31 | 46 | 27 | 136 | 1033 | 158 | 427 | 5 | 33731.45 | 154407.17 | 22159.93 | 0 | 0 | 0 | 151810.97 | 2561.85
| 2024 | Aug | 1886 | 27 | 49 | 24 | 140 | 1057 | 152 | 437 | 8 | 33853.45 | 154770.45 | 25327.99 | 0 | 0 | 0 | 154799.02 | 2561.85
| 2024 | Sep | 1881 | 29 | 48 | 21 | 140 | 1050 | 158 | 435 | 19 | 34838.55 | 153658.25 | 25966.99 | 0 | 0 | 0 | 154264.31 | 2960.85
| 2024 | Oct | 1872 | 35 | 44 | 28 | 127 | 1039 | 159 | 440 | 29 | 33467.14 | 154860.41 | 25953.73 | 0 | 0 | 0 | 152579.89 | 3712.85
| 2024 | Nov | 1903 | 33 | 48 | 21 | 126 | 1070 | 156 | 449 | 11 | 35307.35 | 155675.7 | 27159.53 | 0 | 0 | 0 | 156529.81 | 3113.15
| 2024 | Dec | 1917 | 32 | 46 | 22 | 120 | 1103 | 147 | 447 | 14 | 34449.55 | 154487.12 | 27577.52 | 0 | 0 | 0 | 160043.38 | 2912.85
| 2025 | Jan | 1952 | 30 | 46 | 16 | 119 | 1163 | 133 | 445 | 17 | 38223.03 | 153607.1 | 28773.88 | 0 | 0 | 0 | 165932.71 | 2780.85
| 2025 | Feb | 1987 | 24 | 50 | 19 | 113 | 1200 | 121 | 460 | 16 | 39892.87 | 155989.52 | 32190.19 | 0 | 0 | 0 | 168836 | 2780.85
| 2025 | Mar | 2018 | 26 | 50 | 19 | 113 | 1207 | 112 | 491 | 18 | 39795.14 | 156685.43 | 33578.49 | 600 | 0 | 0 | 171592.01 | 2912.85
| 2025 | Apr | 2037 | 32 | 50 | 29 | 102 | 1212 | 105 | 507 | 38 | 42483.35 | 159425.81 | 33583.05 | 600 | 0 | 0 | 172485.62 | 3062.85
| 2025 | May | 2031 | 31 | 50 | 21 | 89 | 1223 | 106 | 511 | 26 | 40885.47 | 158490.36 | 32489.82 | 600 | 0 | 0 | 173996.86 | 3208.4
| 2025 | Jun | 2054 | 28 | 50 | 27 | 88 | 1237 | 114 | 510 | 17 | 41414.07 | 161676.74 | 35260.07 | 600 | 0 | 0 | 177928.6 | 3501.35
| 2025 | Jul | 2066 | 23 | 52 | 27 | 86 | 1242 | 119 | 517 | 21 | 45048.33 | 162702.67 | 39557.68 | 600 | 0 | 0 | 181393.77 | 3501.35
| 2025 | Aug | 2041 | 23 | 56 | 33 | 82 | 1201 | 111 | 535 | 30 | 44648.55 | 160192 | 39402.77 | 600 | 0 | 0 | 179838.35 | 3501.35
| 2025 | Sep | 2042 | 29 | 54 | 20 | 94 | 1196 | 117 | 532 | 25 | 46093.45 | 159931.82 | 43695.24 | 600 | 0 | 0 | 178052.76 | 3562.45
Note: Other contains all Fuel and Technology Types not in the Solar, Wind, Gas or Battery categories.

## data_GIM Trends_1 (hidden)
| # Signed Interconnect Agreement | # Completed Full Study | # in Full Study | # Screening Study Complete | # Initial Screening study | GW Capacity
Sep-24 | 435 | 158 | 1050 | 140 | 21 | 370.9633
Oct-24 | 440 | 159 | 1039 | 127 | 28 | 369.8282
Nov-24 | 449 | 156 | 1070 | 126 | 21 | 377.0299
Dec-24 | 447 | 147 | 1103 | 120 | 22 | 378.7444
Jan-25 | 445 | 133 | 1163 | 119 | 16 | 388.6158
Feb-25 | 460 | 121 | 1200 | 113 | 19 | 399.0073
Mar-25 | 491 | 112 | 1207 | 113 | 19 | 404.457
Apr-25 | 507 | 105 | 1212 | 102 | 29 | 410.8736
May-25 | 511 | 106 | 1223 | 89 | 21 | 408.9081
Jun-25 | 510 | 114 | 1237 | 88 | 27 | 419.6478
Jul-25 | 517 | 119 | 1242 | 86 | 27 | 432.1004
Aug-25 | 535 | 111 | 1201 | 82 | 33 | 427.4415
Sep-25 | 532 | 117 | 1196 | 94 | 20 | 431.1647

## data_GIM Trends_2 (hidden)
| Natural Gas | Nuclear | Coal | Wind | Solar | Biomass | Battery | Other | Total Project Count | Cancelled Project Count
Sep-24 | 25.967 | 0 | 0 | 34.8385 | 153.6583 | 0 | 154.2643 | 2.9609 | 1881 | 19
Oct-24 | 25.9537 | 0 | 0 | 33.4671 | 154.8604 | 0 | 152.5799 | 3.7128 | 1872 | 29
Nov-24 | 27.1595 | 0 | 0 | 35.3073 | 155.6757 | 0 | 156.5298 | 3.1132 | 1903 | 11
Dec-24 | 27.5775 | 0 | 0 | 34.4496 | 154.4871 | 0 | 160.0434 | 2.9129 | 1917 | 14
Jan-25 | 28.7739 | 0 | 0 | 38.223 | 153.6071 | 0 | 165.9327 | 2.7809 | 1952 | 17
Feb-25 | 32.1902 | 0 | 0 | 39.8929 | 155.9895 | 0 | 168.836 | 2.7809 | 1987 | 16
Mar-25 | 33.5785 | 0.6 | 0 | 39.7951 | 156.6854 | 0 | 171.592 | 2.9129 | 2018 | 18
Apr-25 | 33.5831 | 0.6 | 0 | 42.4834 | 159.4258 | 0 | 172.4856 | 3.0629 | 2037 | 38
May-25 | 32.4898 | 0.6 | 0 | 40.8855 | 158.4904 | 0 | 173.9969 | 3.2084 | 2031 | 26
Jun-25 | 35.2601 | 0.6 | 0 | 41.4141 | 161.6767 | 0 | 177.9286 | 3.5013 | 2054 | 17
Jul-25 | 39.5577 | 0.6 | 0 | 45.0483 | 162.7027 | 0 | 181.3938 | 3.5013 | 2066 | 21
Aug-25 | 39.4028 | 0.6 | 0 | 44.6486 | 160.192 | 0 | 179.8383 | 3.5013 | 2041 | 30
Sep-25 | 43.6952 | 0.6 | 0 | 46.0934 | 159.9318 | 0 | 178.0528 | 3.5625 | 2042 | 25

## data_GIM Trends_3 (hidden)
| # Not Model Ready | # Model Ready | MW Capacity
Sep-24 | 29 | 48 | 725.62
Oct-24 | 35 | 44 | 745.8
Nov-24 | 33 | 48 | 755.62
Dec-24 | 32 | 46 | 726.03
Jan-25 | 30 | 46 | 701.78
Feb-25 | 24 | 50 | 682.08
Mar-25 | 26 | 50 | 706.9
Apr-25 | 32 | 50 | 767.07
May-25 | 31 | 50 | 762.84
Jun-25 | 28 | 50 | 733.06
Jul-25 | 23 | 52 | 703.44
Aug-25 | 23 | 56 | 741.48
Sep-25 | 29 | 54 | 770.99

## data_GIM Trends_4 (hidden)
|  | Gas | Wind | Solar | Battery | Other
COASTAL | 2025 |  | 0.5427 | 1.3744 | 0.921
| 2026 | 0.20471 |  | 1.6594 | 3.8246
| 2027 | 1.8474 | 1.1881 | 4.5145 | 8.211 | 0.41
| 2028 | 2.0162 | 0.1415 | 4.3303 | 5.2295 | 0.499
| 2029 | 0.3514 | 0.5228 | 2.0692 | 0.76206
| 2030 |  | 2.5714 | 0.6036 | 0
| 2031 | 0.6591 |  |  | 0.3036
HOUSTON | 2025 | 0.1717 |  | 1.387 | 0.68274 | 0.05
| 2026 | 0.944 |  |  | 3.6925
| 2027 | 0.7225 |  | 0.40848 | 7.8281
| 2028 | 1.0658 |  | 0.1882 | 1.4567 | 0.05
| 2029 | 0.208 |  |  | 1.1199
| 2030 |  | 1.0294 |  | 0.10305
WEST | 2023 |  | 0.0072 |  | 0
| 2024 |  | 0.4292 |  | 0
| 2025 |  | 1.6485 | 1.3569 | 1.2426 | 0.02985
| 2026 | 0.46779 | 1.4357 | 6.6269 | 4.8531
| 2027 | 2.4794 | 6.1219 | 14.5913 | 14.8421 | 0.492
| 2028 | 3.3842 | 6.0616 | 19.3878 | 19.0867
| 2029 | 1.6761 | 1.8094 | 7.1921 | 3.3461 | 0.6
| 2030 | 1.341 | 0.4413 | 1.4 | 0
| 2031 |  | 1.5 |  | 0
NORTH | 2024 | 0.067 |  |  | 0
| 2025 |  | 1.3005 | 5.0159 | 2.4852 | 0.1
| 2026 | 1.9087 | 0.6537 | 7.2738 | 7.1966
| 2027 | 1.8264 | 1.3675 | 17.011 | 16.1498
| 2028 | 2.5095 | 0.20777 | 11.4724 | 17.6956 | 0.2
| 2029 | 1.7473 | 0.396 | 1.8747 | 3.2986
| 2030 | 0.479 |  |  | 0.2076 | 1.232
PANHANDLE | 2025 |  | 0.1634 | 1.1489 | 0.00999
| 2026 |  | 0.16542 | 1.2149 | 0.50385
| 2027 | 2.21 | 1.2195 | 4.8546 | 3.1195
| 2028 |  | 3.1214 | 3.4142 | 3.1151
| 2029 | 0.573 | 4.1181 | 2.3617 | 0.20696
SOUTH | 2023 | 0.0031 |  | 0.0055 | 0
| 2025 | 0.0407 | 0.91373 | 3.9103 | 1.0335 | 0.3145
| 2026 | 2.7764 | 0.68981 | 4.7058 | 8.0416
| 2027 | 1.2964 | 1.4637 | 10.7429 | 15.2073 | 0.1851
| 2028 | 3.9123 | 3.9585 | 9.8659 | 15.7845
| 2029 | 2.2131 | 0.9036 | 7.1382 | 5.5314
| 2030 | 4.14 |  | 0.83101 | 0.96045
| 2031 | 0.45207 |  |  | 0

## Commissioning Update
Commissioning Approvals during September 2025
Commissioning Category | INR | Size Category | Project Name | Fuel | County | Approval Date * | MW **
Commercial Operation Approved by ERCOT* | 23INR0287 | Large | Avila BESS | Battery Storage | Pecos | 2025-09-09 | 164.28
Commercial Operation Approved by ERCOT* | 24INR0662 | Small | Prairie Creek BESS | Battery Storage | Dallas | 2025-09-10 | 9.95
Commercial Operation Approved by ERCOT* | 22INR0353 | Large | Carina BESS | Battery Storage | Nueces | 2025-09-18 | 154.11
Commercial Operation Approved by ERCOT* | 22INR0388 | Large | Cachi BESS | Battery Storage | Guadalupe | 2025-09-08 | 205.46
Commercial Operation Approved by ERCOT* | 21INR0511 | Large | Wolf Ridge Repower | Wind | Cooke | 2025-09-03 | 9
Commercial Operation Approved by ERCOT* | 24INR0545 | Small | Spencer BESS | Battery Storage | Harris | 2025-09-30 | 9.9
Commercial Operation Approved by ERCOT* | 22INR0511 | Large | Gransolar Texas One | Solar | Milam | 2025-09-12 | 50.8
Commercial Operation Approved by ERCOT* | 26INR0684 | Large | Z5 Southton DGR | Fuel Oil | Bexar | 2025-09-19 | 29
Commercial Operation Approved by ERCOT* | 26INR0674 | Large | X1 MEDINA BASE DGR | Fuel Oil | Bexar | 2025-09-04 | 29
Commercial Operation Approved by ERCOT* | 20INR0230 | Large | Markum Solar | Solar | McLennan | 2025-09-09 | 161.54
Commercial Operation Approved by ERCOT* | 24INR0039 | Large | Jaguar BESS | Battery Storage | McLennan | 2025-09-09 | 157.15
Commercial Operation Approved by ERCOT* | 26INR0666 | Large | P2 HIGHLAND HILLS DGR | Fuel Oil | Bexar | 2025-09-30 | 66
Commercial Operation Approved by ERCOT* | 22INR0525 | Large | St. Gall II Energy Storage | Battery Storage | Pecos | 2025-09-24 | 100.24
Commercial Operation Approved by ERCOT* | 24INR0629 | Large | Jade Storage SLF | Battery Storage | Scurry | 2025-09-29 | 0
Commercial Operation Approved by ERCOT* | 24INR0460 | Large | Evelyn Battery Energy Storage System | Battery Storage | Galveston | 2025-09-22 | 221.3
Synchronization Approved by ERCOT | 23INR0401 | Large | Headcamp Energy Storage Plant | Battery Storage | Pecos | 2025-09-16 | 152.88
Synchronization Approved by ERCOT | 25INR0715 | Small | Poteet BESS | Battery Storage | Atascosa | 2025-09-09 | 9.95
Synchronization Approved by ERCOT | 23INR0494 | Large | Cartwheel BESS 1 | Battery Storage | Hopkins | 2025-09-10 | 154.2
Synchronization Approved by ERCOT | 26INR0676 | Large | Q1 Valley Road DGR | Fuel Oil | Bexar | 2025-09-08 | 29
Synchronization Approved by ERCOT | 26INR0670 | Large | Greyhound Solar - Phase F | Solar | Ector | 2025-09-10 | 101.6
Synchronization Approved by ERCOT | 24INR0315 | Large | Black Springs BESS | Battery Storage | Palo Pinto | 2025-09-16 | 120.68
Synchronization Approved by ERCOT | 26INR0669 | Large | Greyhound Solar - Phase E | Solar | Ector | 2025-09-10 | 150.71
Synchronization Approved by ERCOT | 23INR0351 | Large | Seven Flags BESS | Battery Storage | Webb | 2025-09-30 | 102.7
Synchronization Approved by ERCOT | 24INR0295 | Large | Lucky Bluff BESS SLF | Battery Storage | Erath | 2025-09-17 | 100.8
Energization Approved by ERCOT | 23INR0501 | Large | Soda Lake BESS 1 | Battery Storage | Crane | 2025-09-02 | 203.87
Energization Approved by ERCOT | 26INR0683 | Large | Z0 BECK ROAD DGR | Fuel Oil | Bexar | 2025-09-17 | 60
Energization Approved by ERCOT | 26INR0676 | Large | Q1 Valley Road DGR | Fuel Oil | Bexar | 2025-09-03 | 29
Energization Approved by ERCOT | 23INR0351 | Large | Seven Flags BESS | Battery Storage | Webb | 2025-09-22 | 102.7
Energization Approved by ERCOT | 23INR0790 | Small | DAMON BESS3 | Battery Storage | Brazoria | 2025-09-29 | 9.96
Energization Approved by ERCOT | 25INR0647 | Small | Lantana BESS | Battery Storage | Nueces | 2025-09-12 | 9.99
Energization Approved by ERCOT | 26INR0681 | Large | K2 Nacogdoches DGR | Fuel Oil | Bexar | 2025-09-30 | 58
Energization Approved by ERCOT | 25INR0648 | Small | East Harrison BESS | Battery Storage | Cameron | 2025-09-03 | 9.99
* For projects approved for commercial operations, the approval date is the Resource Commissioning Date defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a
Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative
values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.

## Inactive Projects
Inactive Projects as of end of September 2025*
INR | Size Category | Project Name | Fuel | County | Inactive Date | MW **
13INR0010a | Large | Mariah Del Este Wind | Wind | Parmer | 2019-09-09 10:19 | 152.5
20INR0025 | Large | Spinel Solar | Solar | Medina | 2019-09-10 14:02 | 30
20INR0024 | Large | Fluorite Solar | Solar | Uvalde | 2019-09-11 13:32 | 25
17INR0036 | Large | Grandview 4 Phase A Wind | Wind | Carson | 2019-10-31 10:59 | 200.5
20INR0096 | Large | Desert Rose Solar | Solar | Andrews | 2019-11-12 13:44 | 200
19INR0031 | Large | Bestla Solar | Solar | Winkler | 2020-03-04 16:50 | 180
20INR0023 | Large | Agate Solar | Solar | Ellis | 2020-05-22 15:12 | 60
19INR0101 | Large | Tehuacana Wind | Wind | Limestone | 2020-05-28 10:23 | 600
21INR0503 | Large | Celeste Energy Storage | Battery Storage | Pecos | 2020-06-03 10:35 | 60.89
20INR0299 | Large | Sparkl BESS | Battery Storage | Guadalupe | 2020-09-16 12:30 | 20
19INR0161 | Large | Pierce Wind | Wind | Wharton | 2021-03-16 10:13 | 300
20INR0043 | Large | Gulf Wind 2 | Wind | Kenedy | 2021-04-02 08:54 | 226.5
20INR0267 | Large | Greens Bayou Expansion | Gas | Harris | 2021-04-17 01:08 | 140
18INR0072 | Large | Blue Summit repower | Wind | Wilbarger | 2021-04-28 15:42 | 9.9
20INR0013 | Large | Basalt Solar | Solar | Uvalde | 2021-08-16 09:22 | 20
23INR0152 | Large | Madrone Energy Storage | Battery Storage | Comal | 2021-08-20 09:03 | 102.49
22INR0548 | Large | Fighting Jays Battery | Battery Storage | Fort Bend | 2022-02-25 17:43 | 53.2
19INR0099b | Large | Kontiki 2 Wind (ERNEST) | Wind | Glasscock | 2022-03-10 15:42 | 250.1
19INR0099a | Large | Kontiki 1 Wind (ERIK) | Wind | Glasscock | 2022-03-10 15:46 | 250.1
22INR0266 | Large | Creekfield Solar | Solar | Fort Bend | 2022-03-23 11:25 | 161.34
22INR0379 | Large | Creekfield Storage | Battery Storage | Fort Bend | 2022-03-25 16:59 | 69
23INR0158 | Large | High Chaparral BESS 138kV | Battery Storage | Brazoria | 2022-06-15 15:23 | 51.74
19INR0017 | Large | Tri-County Solar | Solar | Crane | 2022-09-21 15:00 | 177.75
16INR0033 | Large | Hart Wind (Old POI) | Wind | Castro | 2022-10-13 14:42 | 165
20INR0202 | Large | Rueter Solar | Solar | Bosque | 2022-11-01 16:15 | 200
21INR0486 | Large | Pandora Solar | Solar | Wilson | 2022-11-14 14:50 | 252
23INR0210 | Large | Cornwall Solar | Solar | Williamson | 2023-01-19 21:20 | 204.5
23INR0192 | Large | Utica Solar | Solar | Guadalupe | 2023-04-25 09:22 | 204.5
23INR0157 | Large | High Chaparral Solar 138kV | Solar | Brazoria | 2023-05-09 15:54 | 147.63
17INR0022 | Large | MIRAGE | Gas | Harris | 2023-05-31 11:28 | 11
24INR0400 | Large | Bora Bora Solar | Solar | Wichita | 2023-06-05 16:38 | 233.35
25INR0243 | Large | CLUTCH CITY STORAGE I SLF | Battery Storage | Galveston | 2023-06-28 17:51 | 16.63
25INR0332 | Large | Clutch City Storage II SLF | Battery Storage | Brazoria | 2023-06-28 17:51 | 11.3
25INR0095 | Large | Brittlebush BESS | Battery Storage | Henderson | 2023-07-05 22:58 | 597.08
25INR0094 | Large | Brittlebush Solar | Solar | Henderson | 2023-07-05 22:58 | 594.01
25INR0089 | Large | Tempesta | Solar | Kaufman | 2023-08-11 14:22 | 443
25INR0090 | Large | Tempesta BESS | Battery Storage | Kaufman | 2023-08-11 14:23 | 600
22INR0275 | Large | Coleto Creek ESS Addition | Battery Storage | Goliad | 2023-09-18 12:23 | 100.1
24INR0428 | Large | Pioneer Hutt Solar | Solar | Midland | 2023-10-05 23:23 | 116
24INR0241 | Large | Utica BESS | Battery Storage | Guadalupe | 2024-01-23 11:46 | 203.9
24INR0244 | Large | Cornwall BESS | Battery Storage | Williamson | 2024-01-23 11:47 | 203.8
24INR0248 | Large | Half Moon 2 BESS | Battery Storage | Hidalgo | 2024-01-23 11:48 | 102
24INR0292 | Large | Urca Solar | Solar | Live Oak | 2024-01-23 11:50 | 204.1
25INR0234 | Large | Maldives Solar (Oncor POI) | Solar | Scurry | 2024-01-31 14:57 | 184
24INR0290 | Large | Rubicon Echo Wind | Wind | Haskell | 2024-02-05 09:51 | 228.4
28INR0012 | Large | Shamrock II Wind | Wind | Crockett | 2024-02-07 09:24 | 256.62
22INR0362 | Large | Pluto Solar | Solar | Webb | 2024-03-08 09:48 | 228
20INR0135 | Large | Half Moon Battery | Battery Storage | Hidalgo | 2024-03-08 10:09 | 30.2
24INR0402 | Large | Inertia BESS 3 | Battery Storage | Jones | 2024-03-11 11:38 | 108.44
25INR0151 | Large | Academy Wind | Wind | Dickens | 2024-03-12 06:59 | 304.56
21INR0363 | Large | Carol Battery | Battery Storage | Potter | 2024-03-13 09:42 | 168
25INR0179 | Large | Triangle Ranch Charlie | Wind | Cottle | 2024-03-14 10:30 | 200.22
25INR0180 | Large | Triangle Ranch Delta | Wind | Cottle | 2024-03-14 10:31 | 101.52
25INR0181 | Large | Triangle Ranch Echo | Wind | Cottle | 2024-03-14 10:32 | 100.52
25INR0182 | Large | Triangle Ranch Fox | Wind | Cottle | 2024-03-14 10:34 | 100.52
24INR0390 | Large | Long Point Solar II | Solar | Brazoria | 2024-03-21 08:36 | 100.9
24INR0398 | Large | Lake Henry Wind | Wind | Kent | 2024-03-29 12:37 | 305
25INR0398 | Large | Pumpville Ranch 1 | Solar | Val Verde | 2024-04-17 15:33 | 1000
24INR0242 | Large | Stockdale BESS | Battery Storage | Wilson | 2024-04-19 09:08 | 203.9
26INR0100 | Large | Wishbone Storage (SLF) | Battery Storage | Hidalgo | 2024-05-16 12:10 | 90
25INR0012 | Large | Alamosa Solar | Solar | Wilbarger | 2024-05-20 17:03 | 209.48
25INR0022 | Large | Alamosa Storage | Battery Storage | Wilbarger | 2024-05-20 17:03 | 207.21
25INR0079 | Large | Sunlight Solar | Solar | Ector | 2024-06-27 14:12 | 203
23INR0526 | Large | Canyon Wind Alternative | Wind | Scurry | 2024-07-05 09:42 | 311.6
25INR0516 | Large | Collier Ranch Solar | Solar | Motley | 2024-07-05 09:43 | 253
25INR0485 | Large | Diver Energy Storage SLF | Battery Storage | Limestone | 2024-07-05 09:53 | 0
24INR0348 | Large | Best Southwest BESS | Battery Storage | Dallas | 2024-07-15 13:53 | 241.32
21INR0201 | Large | Brandon | Gas | Lubbock | 2024-07-25 16:08 | 21
21INR0202 | Large | R Massengale | Gas | Lubbock | 2024-07-25 16:54 | 58
21INR0506 | Large | Ty Cooke | Gas | Lubbock | 2024-07-25 16:54 | 33
25INR0087 | Large | Capoterra | Solar | Milam | 2024-08-12 15:18 | 598
25INR0088 | Large | Capoterra BESS | Battery Storage | Milam | 2024-08-12 15:18 | 600
24INR0432 | Large | HGP Pacesetter BESS | Battery Storage | Dallas | 2024-08-26 13:39 | 200.83
22INR0238 | Large | Rockefeller Solar | Solar | Schleicher | 2024-09-05 09:05 | 207.48
26INR0316 | Large | Lonesome Dove BESS | Battery Storage | Throckmorton | 2024-09-11 13:41 | 256.1
26INR0282 | Large | Haute Stockage | Battery Storage | Shackelford | 2024-09-19 11:33 | 307.32
26INR0325 | Large | Reynolds Park BESS | Battery Storage | Wichita | 2024-09-19 11:36 | 204.8
26INR0286 | Large | Beaujolais BESS | Battery Storage | Lamar | 2024-09-19 13:50 | 307.2
24INR0259 | Large | Zeissel Storage SLF | Battery Storage | Knox | 2024-09-27 10:22 | 0
26INR0492 | Large | Horse Hollow BESS III SLF | Battery Storage | Nolan | 2024-10-01 11:28 | 0
25INR0049 | Large | Point Mountain Solar | Solar | Upton | 2024-10-07 09:40 | 514
26INR0055 | Large | Point Mountain Storage | Battery Storage | Upton | 2024-10-07 09:41 | 507.2
20INR0146 | Large | Angus Storage | Battery Storage | Bosque | 2024-10-08 10:44 | 63
23INR0193 | Large | Stockdale Solar | Solar | Wilson | 2024-10-17 10:52 | 152.5
27INR0052 | Large | Aquilla Lake 3 Wind (Alternative POI Oncor 138KV) | Wind | Hill | 2024-10-17 15:14 | 225.62
27INR0053 | Large | Aquilla Lake 3 Wind ( Alternative POI Oncor 345kV) | Wind | Hill | 2024-10-18 10:25 | 225.62
23INR0189 | Large | Bayside Solar | Solar | Victoria | 2024-10-18 10:27 | 508.9
23INR0282 | Large | BAYSIDE II SOLAR | Solar | DeWitt | 2024-10-18 10:27 | 252.8
24INR0236 | Large | Bayside 2 BESS | Battery Storage | DeWitt | 2024-10-18 14:30 | 252.3
24INR0237 | Large | Bayside BESS | Battery Storage | Victoria | 2024-10-18 14:30 | 507.8
21INR0274 | Large | Carol Solar | Solar | Potter | 2024-10-21 11:26 | 223.2
23INR0245 | Large | Tiger Storage | Battery Storage | Jones | 2024-10-24 15:35 | 251.04
23INR0155 | Large | Umbra (Stockyard) Solar | Solar | Franklin | 2024-12-03 14:10 | 207.84
23INR0156 | Large | Umbra (Stockyard) BESS | Battery Storage | Franklin | 2024-12-03 14:11 | 72.98
24INR0437 | Large | Umbra Solar II | Solar | Franklin | 2024-12-03 14:11 | 344.66
24INR0439 | Large | Citrus Grove Energy Storage | Battery Storage | Hidalgo | 2024-12-05 09:53 | 204.93
24INR0438 | Large | Umbra BESS II | Battery Storage | Franklin | 2024-12-09 11:32 | 149.64
24INR0075 | Large | Blue Bird Solar | Solar | Johnson | 2024-12-13 11:02 | 1004
19INR0175 | Large | Shifting Gale Wind | Wind | Castro | 2025-01-28 11:14 | 289
20INR0271 | Large | Blue Hills Wind | Wind | Val Verde | 2025-02-05 12:34 | 276
22INR0276 | Large | Trinidad ESS Addition | Battery Storage | Henderson | 2025-02-11 13:20 | 110
24INR0605 | Large | TEXAS GULF SULPHUR REPOWER | Gas | Wharton | 2025-05-02 08:59 | 16.1
24INR0507 | Large | Young Wind II SLF | Wind | Young | 2025-05-08 07:46 | 152.28
23INR0117 | Large | Cantaloupe Storage | Battery Storage | Reeves | 2025-05-08 07:47 | 251.05
25INR0128 | Large | Fiji Solar | Solar | Limestone | 2025-05-08 07:48 | 202.7
28INR0018 | Large | Channing Wind | Wind | Oldham | 2025-05-08 07:48 | 360.5
24INR0245 | Large | Diamondback BESS | Battery Storage | Starr | 2025-05-08 07:49 | 203.8
28INR0033 | Large | Corvette Wind | Wind | Carson | 2025-05-08 07:49 | 1200
22INR0375 | Large | Inertia BESS 2 | Battery Storage | Haskell | 2025-05-08 07:50 | 100.77
26INR0344 | Large | Kendall BESS | Battery Storage | Kendall | 2025-05-08 07:50 | 0
24INR0246 | Large | Sultan BESS | Battery Storage | Bosque | 2025-05-08 07:51 | 203.8
23INR0295 | Large | Sultan Solar | Solar | Bosque | 2025-05-08 07:51 | 206.11
28INR0007 | Large | Tetris Solar (Alternative POI) | Solar | Zapata | 2025-05-08 07:52 | 359
24INR0169 | Large | Yaupon Storage SLF | Battery Storage | Milam | 2025-05-08 07:52 | 0
27INR0065 | Large | Funston Solar (AEP POI) | Solar | Jones | 2025-05-16 14:58 | 355.22
23INR0537 | Large | Wildhorse POD Solar | Solar | Howard | 2025-05-19 10:16 | 9.99
26INR0577 | Large | Pine Forest BESS 2 | Battery Storage | Hopkins | 2025-05-21 13:44 | 201.1
24INR0177 | Large | Mitchell Plant Road Solar | Solar | Pecos | 2025-07-09 15:27 | 201.5
24INR0255 | Large | Mitchell Plant Road Storage | Battery Storage | Pecos | 2025-07-09 15:27 | 201.6
25INR0431 | Large | Millennium Energy Storage | Battery Storage | Martin | 2025-07-18 10:56 | 102.59
25INR0073 | Large | Saltillo Storage | Battery Storage | Bastrop | 2025-07-25 09:47 | 101
26INR0539 | Large | Jade Thunder Storage | Battery Storage | Scurry | 2025-08-13 13:50 | 320
26INR0540 | Large | Andromeda Storage IIB | Battery Storage | Scurry | 2025-08-14 08:58 | 320
26INR0541 | Large | Radian Storage IIB | Battery Storage | Brown | 2025-08-15 11:19 | 320
26INR0178 | Large | Alliance Solar | Solar | Navarro | 2025-08-19 13:30 | 180.25
25INR0171 | Large | Pinewood BESS | Battery Storage | Brazoria | 2025-08-20 17:00 | 100.9
26INR0139 | Large | Weathervane Storage SLF | Battery Storage | Montague | 2025-08-21 13:07 | 32.47
26INR0138 | Large | Weathervane Solar SLF | Solar | Montague | 2025-08-21 13:07 | 160.49
25INR0167 | Large | Padrino BESS | Battery Storage | Hill | 2025-09-18 09:00 | 100.77
25INR0313 | Large | Staked Plains BESS | Battery Storage | Lubbock | 2025-09-18 09:11 | 254.8
27INR0415 | Large | Ulysses Crossing Storage | Battery Storage | Coleman | 2025-09-22 16:45 | 150.8
27INR0370 | Large | Ulysses Crossing Solar | Solar | Coleman | 2025-09-22 16:46 | 405.4
27INR0377 | Large | Vista Bluff Wind 1 | Wind | Upton | 2025-09-23 09:49 | 290.4
28INR0333 | Large | Reunion Storage | Battery Storage | Wilbarger | 2025-09-23 11:26 | 200
28INR0332 | Large | Reunion Solar | Solar | Wilbarger | 2025-09-23 11:26 | 600
26INR0473 | Large | Canyon BESS SLF | Battery Storage | Scurry | 2025-09-25 09:46 | 0
23INR0216 | Large | Venus Mill Storage | Battery Storage | Ellis | 2025-09-25 13:35 | 100.8
* Includes only those projects designated as Inactive by ERCOT or the project developer after the developer makes a Full Interconnection Study (FIS) request, or
in the case of Small Generators, after their Resource Registrations have been approved.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.

## Cancellation Update
Projects Cancelled by the Developer during September 2025*
INR | Size Category | Project Name | Fuel | County | Cancel Date | MW **
22INR0471 | Large | MARATUA SOLAR | Solar | Grimes | 2025-09-02 16:31 | 100
24INR0462 | Large | Ventana Ranch Solar | Solar | Jim Wells | 2025-09-03 07:30 | 502.03
28INR0170 | Large | Kiskadee Trail Solar SLF | Solar | Dimmit | 2025-09-03 16:13 | 406
25INR0471 | Large | Tyler BESS | Battery Storage | Smith | 2025-09-10 09:07 | 305.3
20INR0235 | Large | Knickerbocker Solar SLF | Solar | Tom Green | 2025-09-16 11:12 | 241.26
21INR0446 | Large | Knickerbocker Storage SLF | Battery Storage | Tom Green | 2025-09-16 11:13 | 0
29INR0086 | Large | Winslow Storage | Battery Storage | Hill | 2025-09-17 14:41 | 101
29INR0087 | Large | Glade Storage | Battery Storage | Rains | 2025-09-17 14:41 | 161.5
22INR0444 | Large | Liberty Senate Solar 1 | Solar | Jack | 2025-09-22 13:27 | 202
26INR0014 | Large | Greenwolfe Solar Alt POI | Solar | Hunt | 2025-09-22 18:35 | 274.14
28INR0171 | Large | Kiskadee Trail Storage SLF | Battery Storage | Dimmit | 2025-09-23 14:53 | 406
27INR0280 | Large | Goose Foot Energy Storage | Battery Storage | Scurry | 2025-09-25 10:12 | 305.8
29INR0075 | Large | Southern Star Solar SLF | Solar | Frio | 2025-09-25 10:13 | 115.45
29INR0076 | Large | Southern Star Storage SLF | Battery Storage | Frio | 2025-09-25 10:13 | 51.07
25INR0393 | Large | MICOT BESS | Battery Storage | Montgomery | 2025-09-25 11:24 | 150
24INR0557 | Large | Hovey Energy Storage | Battery Storage | Pecos | 2025-09-29 09:17 | 23
21INR0344 | Large | Lunis Creek Solar SLF | Solar | Jackson | 2025-09-30 11:31 | 617.12
24INR0374 | Large | Farrier Station Energy Storage | Battery Storage | Hopkins | 2025-09-30 15:34 | 409.9
25INR0273 | Large | Horse Wrangler Solar | Solar | Karnes | 2025-09-30 15:44 | 251.33
25INR0274 | Large | Horse Wrangler Storage | Battery Storage | Karnes | 2025-09-30 15:44 | 102.07
25INR0275 | Large | Texas Sage Solar SLF | Solar | Wilson | 2025-09-30 15:44 | 100.7
25INR0276 | Large | Texas Sage Storage SLF | Battery Storage | Wilson | 2025-09-30 15:44 | 0
* Includes only those projects cancelled by the developer after it makes a Full Interconnection Study (FIS) request, or in the case of Small Generators, after the Resource Registrations have been approved.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.