## Contents
GINR Activity: Sep 01, 2020 to Sep 30, 2020
Table of Contents
Disclaimer and References | Disclaimer on the use of this report, and references to associated ERCOT Binding Documents ***Please read***
Acronyms | A list of the various acronyms used throughout the report
Summary | Tables that provide project aggregate counts and megawatt capacities by GINR phase and fuel type
Project Details | A table that lists project details; only includes projects for which a Full Interconnection Study has been requested
GINR Trends | Charts and tables that show historical and projected interconnection study trends
Commissioning Update | A table listing project commissioning approval milestones met for the month: energization, synchronization, and commercial operations approval
Inactive Projects | A table listing Inactive projects
Cancellation Update | A table listing the projects cancelled for the month
Time of Report Run: Oct 1, 2020 9:07:03 AM

## Disclaimer and References
Generator Interconnection Status Report - Disclaimer
FOR PLANNING PURPOSES ONLY
This ERCOT Working Paper has been prepared for specific ERCOT and Market Participant purposes, and has been
developed from data provided by Interconnecting Entities and Transmission Service Providers that has been entered into the online GINR system.
The data may contain errors or be obsolete depending on when the data was entered. ERCOT MAKES NO WARRANTY, EXPRESS
OR IMPLIED,INCLUDING ANY WARRANTY OF MERCHANTABILITY OR FITNESS FOR ANY PARTICULAR PURPOSE,
AND DISCLAIMS ANY AND ALL LIABILITY WITH RESPECT TO THE ACCURACY OF SAME OR THE FITNESS OR
APPROPRIATENESS OF SAME FOR ANY PARTICULAR USE. THIS ERCOT WORKING PAPER IS SUPPLIED WITH ALL FAULTS.
References
The links below provide more information on the ERCOT interconnection process:
http://www.ercot.com/mktrules/guides/planning/current
See the Resource Interconnection Handbook, available on ERCOT’s Resource Integration webpage:
http://www.ercot.com/services/rq/integration

## Acronyms
Acronyms
GINR = Generation Interconnection or Change Request
COD = Commercial Operation Date
SS = Security Screening Study
FIS = Full Interconnection Study
IA = Interconnection Agreement; can be either of the following:
- Standard Generation Interconnection Agreement (SGIA)
- Public financially binding agreement
- An official letter from a Municipally Owned Utility or Electric Cooperative signifying developer intent to build and operate generation facilities and
interconnect with the MOU or EC
POI = Point of lnterconnection
INR = Interconnection Request Number
TSP = Transmission Service Provider
NtP = Notice-to-Proceed given to the TSP for interconnection construction
CDR = Capacity, Demand and Reserves Report
SFS = Sufficient Financial Security provided to the TSP for construction of the interconnection facilities
QSA = Quarterly Stability Assessment
INA = Inactive status
PLN = Planned status
Fuel Types | Technology Types
BIO = Biomass | BA = Battery Energy Storage
COA = Coal | CC = Combined-Cycle
GAS = Gas | CE = Compressed Air Energy Storage
GEO = Geothermal | CP = Concentrated Solar Power
HYD = Hydrogen | EN = Energy Storage
NUC = Nuclear | FC = Fuel Cell
OIL = Fuel Oil | GT = Combustion (gas) Turbine, but not part of a Combined-Cycle
OTH = Other | HY = Hydroelectric Turbine
PET = Petcoke | IC = Internal Combustion Engine, eg. Reciprocating
SOL = Solar | OT = Other
WAT = Water | PV = Photovoltaic Solar
WIN = Wind | ST = Steam Turbine other than Combined-Cycle
WT = Wind Turbine

## Summary
Summary |  |  | Major GINR Milestone Status by Fuel/Technology Type, MW
Currently tracking 633 generation interconnection or change requests as of Sep 30, 2020 |  |  | Includes only those projects for which a Screening Study (SS) has been requested and are not Inactive.
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  |  | Fuel | Technology | SS Started | SS Started | SS Completed | SS Completed | SS Completed | SS Started | SS Started | SS Completed | SS Completed | SS Completed | TOTAL
Includes only those projects for which a Screening Study (SS) has been requested |  |  | Type | Type | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed
and are not Inactive |  |  |  |  | No IA | No IA | No IA | No IA | No IA | IA | IA | IA | IA | IA
Status of SS, FIS, and IA | Project Count | % of Total | Gas | Combined-Cycle | 1350 |  |  | 741 |  |  |  |  | 93 | 375 | 2559
SS Started, FIS Not Started, No IA | 28 | 4.423% | Gas | Combustion Turbine | 84 | 331.68 | 450 | 876.8 | 616.84 |  |  |  | 140 | 1279 | 3778.32
SS Started, FIS Started, No IA | 46 | 7.267% | Gas | Internal Combustion Engine |  |  |  | 143 | [6 empty] | 143
SS Completed, FIS Not Started, No IA | 65 | 10.27% | Gas | Compressed Air Energy Storage |  |  | 324.4 | [7 empty] | 324.4
SS Completed, FIS Started, No IA | 272 | 42.97% | Gas | Steam Turbine | [9 empty] | 14 | 14
SS Completed, FIS Completed, No IA | 40 | 6.319% | Gas | Fuel Cell
SS Started, FIS Not Started, IA | 0 | 0% | Gas | Total gas | 1434 | 331.68 | 774.4 | 1760.8 | 616.84 |  |  |  | 233 | 1668 | 6818.72
SS Started, FIS Started, IA | 0 | 0% | Nuclear | [5 empty] | 13 | [5 empty] | 13
SS Completed, FIS Not Started, IA | 1 | 0.158% | Coal | [5 empty] | 420 | [5 empty] | 420
SS Completed, FIS Started, IA | 55 | 8.689% | Wind |  | 848 | 350 | 1035.5 | 7438.11 | 546 |  |  |  | 5434.11 | 8027.25 | 23678.97
SS Completed, FIS Completed, IA | 126 | 19.91% | Solar |  | 3497.08 | 3072.78 | 10908.76 | 38255.89 | 5331.55 |  |  | 185 | 4694.34 | 11128.36 | 77073.76
Total Interconnection Requests | 633 |  | Biomass
Inactive (since last month) | 4 |  | Other | Battery | 705 | 5788.56 | 2255.2 | 8001.15 | 197.12 |  |  |  | 743.02 | 419.09 | 18109.14
Cancelled (since last month) | 37 |  | Other* |  |  | 50 | 150 | 150 | [6 empty] | 350
| Capacity, MW |  | TOTAL |  | 6484.08 | 9593.02 | 15123.86 | 55605.95 | 7124.51 |  |  | 185 | 11104.47 | 21242.7 | 126463.59
Total Capacity Under Study | 126463.59
Interconnection Agreements Executed | 32532.17
Inactive (since last month) | 576.9
Inactive changed to Planned (since last month) | 50
Inactive changed to Cancelled (since last month) | 257
Cancelled (since last month) | 6939.52
* Other includes petroleum coke (pet coke), hydroelectric, fuel oil, geothermal energy, other miscellaneous fuels reported by developers, and fuel cells that use fuels other than natural gas.

## Project Details
GINR Project Details
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study has been requested are included.
Excludes projects that have a status of Inactive (status = INA).
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GINR system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not been obtained or reported to ERCOT yet.
A developer may split a project into two or more additional projects with different INR numbers during the interconnection request process. Due to current RIOO interface limitations,
the new projects do not inherit certain milestone dates entered for the original project. As a result, dates may be blank even though the milestones have been met.
Project Attributes | [10 empty] | Changes from Last Report | GINR Project Milestone Dates
INR | Project Name | GINR Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  |  | Screening Study Started | Screening Study Complete | FIS Approved | Economic Study Required | IA Signed |  | Air Permit | GHG Permit | Water Availability | Meets Planning | Meets All Planning |  | Construction Start | Construction End | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Change indicators: Proj Name, MW | Approval Date for | [5 empty] | Financial Security |  |  |  | Guide Section 6.9(1) | Guide Section 6.9 | Meets Planning Guide
[11 empty] | Size, COD, SFS/NtP, FIS Request, | Submission of Proof of | [5 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[11 empty] | Status Change INA-to-PLN | Site Control | [5 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[22 empty] | Models | Models
11INR0062 | Shaffer Wind | SS Completed, FIS Completed, IA | Clearway Energy | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2020-10-31 | WIN | WT | 226 | Proj Name COD | 1940-05-16 | 2009-04-23 | 2009-06-16 | 2018-06-13 | No | 2013-07-02 | Yes | Not Required | Not Required | Not Required | 2018-04-18 | 2018-09-28 | 2018-07-31 |  |  | 2019-03-27 | 2019-04-05
12INR0059b | HOVEY (Barilla Solar 1B) | SS Completed, FIS Completed, IA | First Solar | 60385 Solstice 138kV | Pecos | WEST | 2020-04-30 | SOL | PV | 7.4 |  | 1940-05-16 | 2010-12-01 | 2011-02-25 | 2014-01-16 |  | 2013-12-26 | Yes | Not Required | Not Required | Not Required
14INR0009 | WKN Amadeus Wind | SS Completed, FIS Completed, IA | WKN | tap 345kV 11305 Dermott - 60706 Kirchhoff | Fisher | WEST | 2021-01-08 | WIN | WT | 250.12 | COD | 1940-05-16 | 2011-01-24 | 2011-03-18 | 2019-11-01 | No | 2018-03-15 | Yes | Not Required | Not Required | Not Required | 2019-03-07 | 2019-10-28 | 2019-11-01 |  |  | 2020-09-14
15INR0034 | El Algodon Alto W | SS Completed, FIS Started, IA | Eon | tap 345kV 8455 Lon Hill -8606 Goddard | San Patricio | COASTAL | 2021-12-15 | WIN | WT | 201 |  |  | 2013-02-04 | 2013-03-25 |  | No | 2020-04-02 | Yes | Not Required | Not Required | Not Required | 2020-04-17
15INR0044 | Corazon Solar | SS Completed, FIS Started, IA | Corazon Energy, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2021-05-31 | SOL | PV | 202.64 |  | 1940-05-16 | 2013-09-06 | 2013-09-16 |  | No | 2020-01-09 | Yes | Not Required | Not Required | Not Required | 2020-07-11 | 2020-09-28
15INR0059 | Emerald Grove Solar | SS Completed, FIS Started, IA | Emerald Grove Solar, LLC | 76602 Horse Crossing 138kV | Pecos | WEST | 2021-09-15 | SOL | PV | 108 |  | 2013-11-12 | 2013-11-13 | 2013-12-23 |  | No | 2018-06-27 | Yes | Not Required | Not Required | Not Required | Date Not Available | 2019-04-17
15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2020-11-04 | WIN | WT | 162.1 | COD |  | 2013-11-27 | 2014-01-27 | 2017-09-27 | No | 2018-05-30 | Yes | Not Required | Not Required | Not Required | 2018-05-30 | 2018-09-19 | 2019-01-22 |  |  | 2020-02-10 | 2020-05-12
15INR0090 | Pflugerville Solar | SS Completed, FIS Completed, IA | RRE Solar | tap 138kV 7336 Gillie - 3650 Elgin | Travis | SOUTH | 2021-05-31 | SOL | PV | 144 |  | 2015-09-30 | 2015-04-28 | 2015-07-01 | 2020-01-31 | No | 2017-06-13 | Yes | Not Required | Not Required | Not Required | 2020-04-28 | 2020-05-01 | 2020-05-01
16INR0033 | Hart Wind | SS Completed, FIS Started, IA | Orion | 23912 Ogallala 345kV | Castro | PANHANDLE | 2022-12-31 | WIN | WT | 151.5 |  | 2014-10-27 | 2014-02-10 | 2014-03-20 |  | No | 2018-08-06 | No | Not Required | Not Required | Not Required
16INR0049 | Nazareth Solar | SS Completed, FIS Started, IA | Lendlease Energy | 23912 Ogallala 345kV | Castro | PANHANDLE | 2023-06-01 | SOL | PV | 201 | COD | 2014-07-07 | 2014-06-19 | 2014-07-25 |  | No | 2018-05-10 | No | Not Required | Not Required | Not Required
16INR0054 | NA | SS Completed, FIS Completed, IA | NASA | 42970 Nasa 138kV | Harris | HOUSTON | 2018-09-01 | GAS | CC | 12 |  |  | 2015-03-10 | 2015-04-01 | 2016-01-26 | No | 2016-10-27 | Yes | Not Required | Not Required |  | 2016-11-10 | 2018-09-28 |  |  |  |  | 2017-11-27
16INR0081 | Mesteno Wind | SS Completed, FIS Completed, IA | Mesteno Windpower, LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2020-10-31 | WIN | WT | 201.6 |  | 1940-05-16 | 2014-12-30 | 2015-03-09 | 2018-01-29 | No | 2018-04-25 | Yes | Not Required | Not Required | Not Required | 2018-04-25 | 2019-03-28 | 2019-04-01 |  |  | 2019-11-26 | 2019-12-12
16INR0085 | Priddy Wind | SS Completed, FIS Started, IA | ENGIE North America | tap 345kV 1444 Brown – 3422 Killeen | Mills | NORTH | 2021-11-30 | WIN | WT | 300 | COD | 2015-03-06 | 2015-01-14 | 2015-02-10 |  |  | 2020-08-13 | Yes | Not Required | Not Required | Not Required
16INR0086 | Cactus Flats Wind | SS Completed, FIS Completed, IA | Southern Power Company | tap 138kV 6480 SAPS - 6365 Yellow Jacket | Concho | WEST | 2020-11-30 | WIN | WT | 148.4 | COD |  | 2015-02-02 | 2015-03-27 | 2017-10-20 | No | 2017-03-15 | Yes | Not Required | Not Required | Not Required | Date Not Available | 2018-09-05 | 2017-11-01 |  |  | 2018-05-24 | 2018-06-11
16INR0104 | Big Sampson Wind | SS Completed, FIS Completed, IA | Infinity Renewables | 76005 Schneeman Draw 345kV | Crockett | WEST | 2022-09-01 | WIN | WT | 400 | COD |  | 2015-05-11 | 2015-06-17 | 2018-12-11 | No | 2019-11-08 | No | Not Required | Not Required | Not Required
16INR0111 | Venado Wind | SS Completed, FIS Completed, IA | Las Lomas Wind Energy, LLC | 8957 Lopeno 138kV | Starr | SOUTH | 2020-12-01 | WIN | WT | 201.6 |  |  | 2015-05-18 | 2015-06-25 | 2020-05-01 | No | 2018-12-22 | Yes | Not Required | Not Required | Not Required | 2019-01-29 | 2020-05-01 | 2020-05-01
16INR0114 | Upton Solar | SS Completed, FIS Started, IA | Clearway Energy | 76020 SONNE 138-kV | Upton | WEST | 2021-11-01 | SOL | PV | 104.56 |  |  | 2015-05-27 | 2015-07-02 |  |  | 2015-12-04 | Yes | Not Required | Not Required | Not Required | 2018-12-14
17INR0020a | RE Maplewood 2a Solar | SS Completed, FIS Completed, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2021-06-01 | SOL | PV | 222 |  | 2014-10-22 | 2014-10-17 | 2014-12-01 | 2020-07-22 | No | 2019-05-06 | Yes | Not Required | Not Required | Not Required | 2020-08-04 | 2020-08-04 | 2020-08-04
17INR0020b | RE Maplewood 2b Solar | SS Completed, FIS Completed, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2021-03-12 | SOL | PV | 28 |  | 2014-10-22 | 2014-10-17 | 2014-12-01 | 2020-07-22 | No | 2019-05-06 | Yes | Not Required | Not Required | Not Required | 2020-08-04 | 2020-08-04 | 2020-08-04
17INR0022 | MIRAGE | SS Completed, FIS Completed, IA | Net Power | 111161 Mirage 13.8kV | Harris | HOUSTON | 2020-10-15 | GAS | GT | 11 |  |  | 2015-02-17 | 2015-05-01 | 2016-09-13 | No | 2016-08-31 | Yes | 2015-05-08 | Not Required | 2017-10-12 | 2016-10-11 | 2018-09-28 |  |  |  | 2017-02-06
17INR0025 | Reloj Del Sol Wind | SS Completed, FIS Completed, IA | EDP Renewables | 80220 Cenizo 345kV | Zapata | SOUTH | 2020-12-01 | WIN | WT | 209.4 | MW Size | 2015-09-14 | 2015-03-24 | 2015-05-05 | 2020-04-26 | Yes | 2018-12-21 | Yes | Not Required | Not Required | Not Required | 2019-03-04 | 2020-05-01 | 2020-05-01
17INR0027b | Coyote Wind | SS Completed, FIS Completed, IA | Coyote Wind | 11305 Dermott 345kV | Scurry | WEST | 2020-12-14 | WIN | WT | 242.6 |  |  | 2015-04-22 | 2015-05-22 | 2020-01-31 | No | 2016-08-09 | Yes | Not Required | Not Required | Not Required | 2016-08-09 | 2020-01-28 | 2020-01-31 |  |  | 2020-08-24
17INR0031 | Espiritu Wind | SS Completed, FIS Completed, IA | Acciona | 8640 Kelvin 138kV | Cameron | COASTAL | 2020-12-21 | WIN | WT | 25.2 |  |  | 2015-05-19 | 2015-06-22 | 2020-01-21 | No | 2020-01-29 | Yes | Not Required | Not Required | Not Required | 2020-01-29 | 2020-01-29 | 2020-01-29 |  |  | 2020-07-30
17INR0035 | Las Majadas Wind | SS Completed, FIS Completed, IA | EDF Renewable Energy | 8318 Rio Hondo 345kV plus 12.5mi gentie | Willacy | COASTAL | 2020-12-14 | WIN | WT | 272.6 |  | 2015-12-09 | 2015-10-30 | 2015-12-14 | 2020-01-30 | Yes | 2018-04-13 | Yes | Not Required | Not Required | Not Required | 2019-07-22 | 2020-01-30 | 2020-01-30 |  |  | 2020-09-02
17INR0037 | Palmas Altas Wind | SS Completed, FIS Completed, IA | Acciona | 5760 PALMAS 138 kV | Cameron | COASTAL | 2020-09-30 | WIN | WT | 144.9 | COD | 2016-07-20 | 2016-03-24 | 2016-05-06 | 2018-08-07 | No | 2017-11-30 | Yes | Not Required | Not Required | Not Required | 2018-10-04 | 2018-10-04 | 2018-10-04 |  |  | 2019-12-03 | 2019-12-10
17INR0052 | Horse13 CallD repower | SS Completed, FIS Completed, IA | Nextera | 6216 Bluff Creek 138kV | Taylor | WEST | 2020-09-30 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2018-04-10 | No | 2019-05-22 | Yes | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13
17INR0054 | Capricorn I & III repower | SS Completed, FIS Completed, IA | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WEST | 2020-11-30 | WIN | WT | 32 |  | 2017-03-09 | 2017-03-09 | 2017-04-24 | 2018-02-26 | No | 2006-11-14 | No | Not Required | Not Required | Not Required
17INR0061 | Capricorn IV repower | SS Completed, FIS Completed, IA | Nextera |  | Sterling | WEST | 2020-12-31 | WIN | WT | 9 | COD | 2017-08-23 | 2017-08-23 | 2017-09-15 | 2018-02-06 | No | 2008-01-15 | No | Not Required | Not Required | Not Required | 2020-08-28 | 2020-08-28 |  |  |  |  | 2020-08-19
17INR0068 | Sweetwater 2 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2020-10-31 | WIN | WT | 7.3 | COD | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-11-10 | No | 2003-06-27 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2017-12-20
17INR0069 | Trent repower | SS Completed, FIS Completed, IA | Invenergy | 1338 Eskota 138kV | Nolan | WEST | 2020-09-30 | WIN | WT | 6.4 | COD | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2018-03-01 | No | 2018-10-19 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-05-09
17INR0070 | Desert Sky repower | SS Completed, FIS Completed, IA | Invenergy | two LCRA 138kV | Pecos | WEST | 2020-09-30 | WIN | WT | 7.2 | COD | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2018-02-06 | No | 2018-10-18 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-09-06
18INR0016 | RTS 2 Wind | SS Completed, FIS Completed, IA | Heart of Texas Wind, LLC | 76006 Bow Wood 345kV | McCulloch | SOUTH | 2020-10-08 | WIN | WT | 179.91 | COD | 2015-12-31 | 2015-11-02 | 2015-12-07 | 2019-01-16 | No | 2017-11-21 | Yes | Not Required | Not Required | Not Required | 2019-07-11 | 2019-07-11 | 2019-07-11 |  |  | 2020-04-17 | 2020-04-29
18INR0030 | Canyon Wind | SS Completed, FIS Started, IA | TriGlobal | 11319 ScurryCounty 138kV | Scurry | WEST | 2021-09-30 | WIN | WT | 259.44 |  | 2017-03-02 | 2016-05-09 | 2016-07-22 |  | No | 2018-09-20 | Yes | Not Required | Not Required | Not Required | 2020-02-07
18INR0031 | Maryneal Wind | SS Completed, FIS Completed, IA | Maryneal Windpower, LLC | 71050 Bitter Creek 345kV | Nolan | WEST | 2021-07-01 | WIN | WT | 182.4 |  | 2016-07-22 | 2016-05-26 | 2016-07-21 | 2020-01-31 | No | 2020-01-31 | Yes | Not Required | Not Required | Not Required | 2020-01-31 | 2020-01-31 | 2020-01-31
18INR0033 | Oveja Wind | SS Completed, FIS Completed, IA | Invenergy | 76005 Schneeman Draw 345kV | Irion | WEST | 2020-08-30 | WIN | WT | 300 |  |  | 2016-07-12 | 2016-09-07 | 2018-07-11 | No | 2018-07-24 | Yes | Not Required | Not Required | Not Required | 2018-07-30 | 2018-09-28 | 2018-07-30 |  |  | 2019-03-28 | 2019-04-05
18INR0038 | Barrow Ranch | SS Completed, FIS Completed, IA | Engie | 1134 Littman 138kV | Andrews | WEST | 2020-07-31 | WIN | WT | 160 |  |  | 2016-10-02 | 2016-12-12 | 2019-07-30 | No | 2018-06-26 | Yes | Not Required | Not Required | Not Required | 2018-09-04 | 2019-05-01 | 2019-08-01 |  |  | 2020-02-06 | 2020-02-26
18INR0042 | Kaiser Creek Wind | SS Completed, FIS Started, No IA | Calpine | Tap 138kV 6275 Abilene East – 6670 Putnam | Callahan | WEST | 2021-11-30 | WIN | WT | 101.52 |  | 2016-12-05 | 2016-10-12 | 2016-12-01 |  | No |  | No | Not Required | Not Required | Not Required
18INR0043 | Edmondson Ranch Wind | SS Completed, FIS Completed, IA | Wind Tex | 59903 Bearkat 345kV | Glasscock | WEST | 2021-12-01 | WIN | WT | 293.28 |  |  | 2016-10-26 | 2016-12-22 | 2018-01-30 | Yes | 2017-10-04 | Yes | Not Required | Not Required | Not Required | Date Not Available | 2018-09-05 | 2019-09-17
18INR0045 | Misae Solar | SS Completed, FIS Completed, IA | CIP | 60501 Tesla 345kV | Childress | PANHANDLE | 2020-10-01 | SOL | PV | 240.8 | COD | 2016-10-20 | 2016-10-20 | 2017-01-06 | 2019-01-28 | No | 2018-07-18 | Yes | Not Required | Not Required | Not Required | 2019-01-28 | 2019-01-30 | 2019-01-31 |  |  | 2019-08-21 | 2020-01-16
18INR0050 | Mustang Creek Solar | SS Completed, FIS Completed, IA | Sunchase Power | tap 138kV 5523 ETP - 78104 Ricebird new sub Galow | Jackson | SOUTH | 2022-01-01 | SOL | PV | 152.25 | MW Size COD | 2017-03-22 | 2016-11-16 | 2016-12-20 | 2020-08-25 | No | 2019-01-04 | Yes | Not Required | Not Required | Not Required | 2019-10-04 | 2020-03-11
18INR0053 | Fort Bend Solar | SS Completed, FIS Started, IA | Fort Bend Solar LLC | tap 138kV 44541 Orchard - 44190 E Bernard | Fort Bend | HOUSTON | 2021-12-31 | SOL | PV | 240 |  |  | 2016-12-19 | 2017-02-15 |  | No | 2019-06-30 | Yes | Not Required | Not Required | Not Required
18INR0055 | Long Draw Solar | SS Completed, FIS Completed, IA | ENGIE | 59906 Long Draw 138kV | Borden | WEST | 2020-12-21 | SOL | PV | 226.73 | COD |  | 2016-12-15 | 2017-02-02 | 2019-12-19 | No | 2018-08-16 | Yes | Not Required | Not Required | Not Required | 2019-02-28 | 2019-12-31 | 2020-01-31
18INR0056 | Hallmark Solar | SS Completed, FIS Started, No IA | Hallmark Solar, LLC | tap 69kV 1824 Neyland - 1826 Cadmil | Hunt | NORTH | 2023-05-12 | SOL | PV | 43 |  |  | 2016-12-15 | 2017-02-16 |  |  |  | No | Not Required | Not Required | Not Required
18INR0058 | Texana Solar | SS Completed, FIS Started, No IA | Sunchase Power | tap 138kV 8102 El Campo - 8117 Ganado | Wharton | SOUTH | 2022-12-15 | SOL | PV | 152.34 | MW Size | 2017-03-22 | 2016-12-23 | 2017-02-14 |  | No |  | No | Not Required | Not Required | Not Required
18INR0059 | East Raymond Wind | SS Completed, FIS Completed, IA | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2021-01-04 | WIN | WT | 201.6 |  |  | 2017-01-27 | 2017-03-09 | 2019-11-01 | No | 2018-09-18 | Yes | Not Required | Not Required | Not Required | 2018-10-17 | 2019-07-16 | 2019-11-01 |  |  | 2020-09-16
18INR0060 | Brightside Solar | SS Completed, FIS Started, IA | Brightside Solar, LLC | tap 69kV 8198 Beeville - 8400 Three River | Bee | SOUTH | 2021-07-30 | SOL | PV | 50 |  |  | 2017-02-17 | 2017-03-20 |  | No | 2020-06-11 | Yes | Not Required | Not Required | Not Required | 2020-07-01
18INR0062 | Wagyu Solar | SS Completed, FIS Completed, IA | Cypress Creek Renewables | tap 138kV 43380 West Columbia - 44010 WA Parish | Brazoria | COASTAL | 2020-09-25 | SOL | PV | 120 | COD | 2017-02-21 | 2017-02-22 | 2017-04-03 | 2018-11-01 | No | 2019-06-03 | Yes | Not Required | Not Required | Not Required | 2019-10-23 | 2019-10-31 | 2019-10-31 |  |  | 2020-05-14 | 2020-05-22
18INR0064 | Silver Star repower | SS Completed, FIS Completed, IA | Silver Star I Power Partners, LLC | 1642 Flat Creek 138kV | Eastland | NORTH | 2020-09-16 | WIN | WT | -7.2 |  | 2017-07-06 | 2017-04-05 | 2017-05-08 | 2018-04-26 | No | 2018-10-16 | Yes | Not Required | Not Required | Not Required | 2019-10-23 | 2019-10-23 | 2019-10-28 |  |  |  | 2020-07-28
18INR0068 | Loraine Windpark Phase III | SS Completed, FIS Started, IA | Third Planet Wind Power | 181153 Lonewolf 345kV | Mitchell | WEST | 2022-05-06 | WIN | WT | 100 |  | 2017-10-20 | 2017-08-14 | 2017-10-05 |  | No | 2018-04-10 | Yes | Not Required | Not Required | Not Required | 2018-04-12 | 2018-09-12 | 2018-05-01
18INR0069 | Indian Mesa repower | SS Completed, FIS Completed, IA | Nextera | 76019 Indian NWP 138kV | Pecos | WEST | 2020-12-31 | WIN | WT | 0 | COD | 2018-05-22 | 2018-05-22 | Date Not Available | 2018-10-03 | No | 2018-12-04 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2018-11-02
18INR0072 | Blue Summit repower | SS Completed, FIS Started, No IA | Nextera | 61001 Jim Treece 345kV | Wilbarger | WEST | 2021-03-31 | WIN | WT | 9.9 | COD | 2018-01-04 | 2018-01-04 | 2018-01-04 |  | No |  | No | Not Required | Not Required | Not Required
18INR0073 | Sweetwater 1 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2020-10-31 | WIN | WT | 3 | COD | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-12-27 | No | 2002-10-23 | No | Not Required | Not Required | Not Required
18INR0075 | Gulf Wind 1 repower | SS Completed, FIS Completed, IA | Pattern Gulf Wind LLC | 80071 Zorillo 345kV | Kenedy | COASTAL | 2020-12-15 | WIN | WT | 0 |  | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2019-05-29 | No | 2007-08-28 | No | Not Required | Not Required | Not Required | 2019-07-19 | 2019-07-19 | 2019-07-31 |  |  | 2020-03-31 | 2020-07-31
18INR0076 | Wolf Hollow 2 repower | SS Completed, FIS Started, No IA | Exelon | 1877 Mitchell Bend 345kV | Hood | NORTH | 2020-11-01 | GAS | CC | 44 |  | 2018-04-24 | 2018-04-24 | 2018-04-24 |  | No |  | No | Not Required | Not Required |  | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-19
18INR0077 | Colorado Bend 2 repower | SS Completed, FIS Started, IA | Exelon | 44040 Bailey 345kV | Wharton | SOUTH | 2020-11-01 | GAS | CC | 45 |  | 2018-04-24 | 2018-04-24 | 2018-04-24 |  | No | 2015-12-17 | No | Not Required | Not Required |  | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-19
18INR0079 | Woodward I repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2020-12-31 | WIN | WT | 0 | COD | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2019-01-09 | No | 2018-12-12 | No | Not Required | Not Required | Not Required | [5 empty] | 2019-11-07 | 2019-11-13
18INR0080 | Woodward 2 repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2021-02-28 | WIN | WT | 0 | COD | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-11-27 | No | 2018-12-18 | No | Not Required | Not Required | Not Required | [6 empty] | 2018-12-19
19INR0001 | Texas Solar Nova | SS Completed, FIS Started, IA | Clearway Energy | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2022-01-31 | SOL | PV | 252.2 |  | 2016-07-06 | 2015-11-17 | 2015-12-30 |  | No | 2019-07-01 | Yes | Not Required | Not Required | Not Required | 2019-11-08
19INR0006 | Bluebonnet Solar | SS Completed, FIS Started, No IA | One Energy Renewables | tap 138kV 6680 Alamito - 60444 Hayter | Brewster | WEST | 2022-12-31 | SOL | PV | 60.7 |  | 2017-04-05 | 2016-07-18 | 2016-10-07 |  |  |  | No | Not Required | Not Required | Not Required
19INR0014 | Formosa Increase | SS Completed, FIS Completed, IA | Formosa Plastics | 8126 Formosa 138kV | Calhoun | COASTAL | 2020-12-31 | GAS | CC | 240 |  |  | 2016-09-12 | 2016-11-14 | 2019-02-20 | No | 2019-04-30 | Yes | 2017-04-17 | 2017-07-12 | 2019-02-22 | 2019-04-30 | 2019-04-30 | 2019-04-30 |  |  | 2020-02-10 | 2020-03-04
19INR0017 | Tri-County Solar | SS Completed, FIS Started, No IA | First Solar | tap 138kV 1027 Odessa - 1107 Monahans2T | Crane | WEST | 2022-04-30 | SOL | PV | 177.75 |  |  | 2016-10-10 | 2016-11-29 |  | No |  | No | Not Required | Not Required | Not Required
19INR0022 | Monte Alto I | SS Completed, FIS Started, IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2021-12-31 | WIN | WT | 223.8 |  |  | 2016-11-04 | 2017-01-10 |  | No | 2020-02-13 | No | Not Required | Not Required | Not Required
19INR0023 | Monte Alto 2 Wind | SS Completed, FIS Started, No IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2021-12-31 | WIN | WT | 236.9 |  |  | 2016-11-04 | 2017-01-10 |  | No |  | No | Not Required | Not Required | Not Required
19INR0034 | Greasewood Solar | SS Completed, FIS Completed, IA | Concho Bluff, LLC | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Pecos | WEST | 2020-12-23 | SOL | PV | 255 |  |  | 2017-02-22 | 2017-04-17 | 2020-01-31 | No | 2020-01-29 | Yes | Not Required | Not Required | Not Required | 2020-01-29 | 2020-01-29 | 2020-01-31 |  |  | 2020-09-24
19INR0035 | Norton Solar | SS Completed, FIS Started, IA | 8minutenergy | tap 138kV 6325 Chad to 6340 Balg, 10mi from Chad | Runnels | WEST | 2022-04-01 | SOL | PV | 125 |  | 2017-11-08 | 2017-03-06 | 2017-04-20 |  | No | 2019-06-20 | Yes | Not Required | Not Required | Not Required | 2019-07-12
19INR0036 | Oxbow Solar | SS Completed, FIS Started, No IA | ENGIE Long Draw Solar 2 LLC | 59905 Faraday 345kV | Borden | WEST | 2022-06-30 | SOL | PV | 225 |  | 2017-10-10 | 2017-02-28 | 2017-04-13 |  | No |  | No | Not Required | Not Required | Not Required
19INR0038 | High Lonesome W | SS Completed, FIS Completed, IA | Enel | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | WEST | 2020-10-15 | WIN | WT | 449.5 |  | 2017-07-18 | 2017-03-10 | 2017-04-17 | 2019-01-21 | No | 2018-04-17 | Yes | Not Required | Not Required | Not Required | 2019-02-15 | 2019-02-15 | 2019-02-15 |  |  | 2019-11-12 | 2019-11-26
19INR0041 | Myrtle Solar | SS Completed, FIS Completed, IA | Sunchase Power | 42110 Angleton 138kV | Brazoria | COASTAL | 2022-01-01 | SOL | PV | 240 | COD |  | 2017-03-15 | 2017-04-28 | 2019-03-12 | No | 2019-11-13 | Yes | Not Required | Not Required | Not Required | 2019-11-30 | 2020-05-06
19INR0042 | Long Point Solar | SS Completed, FIS Completed, IA | SunChase Power | tap 138kV 44010 WAP - 42981 Nash98 | Brazoria | COASTAL | 2021-12-01 | SOL | PV | 100 |  | 2017-11-02 | 2017-03-15 | 2017-04-20 | 2019-03-12 |  | 2019-10-24 | No | Not Required | Not Required | Not Required
19INR0044 | Lily Solar | SS Completed, FIS Completed, IA | Lily Solar, LLC | tap 138kV 6904 CombinRC - 6908 ScuryRC | Kaufman | NORTH | 2021-06-01 | SOL | PV | 147.63 |  | 1940-05-16 | 2017-03-28 | 2017-04-28 | 2020-07-28 | No | 2019-03-29 | Yes | Not Required | Not Required | Not Required | 2020-07-10 | 2020-07-14 | 2020-07-30
19INR0045 | Rayos Del Sol | SS Completed, FIS Completed, IA | Rayos Del Sol Solar Project, LLC | tap 138kV 8554 Mesquite - 80103 Rangerville | Cameron | COASTAL | 2021-12-31 | SOL | PV | 150 | COD |  | 2017-03-28 | 2017-05-22 | 2020-03-17 | No | 2018-11-06 | Yes | Not Required | Not Required | Not Required | 2019-01-23 | 2020-03-17
19INR0051 | Vera Wind | SS Completed, FIS Completed, IA | Longroad Energy | tap 345kV 60500 EdithC - 60700 Gauss | Knox | WEST | 2020-10-20 | WIN | WT | 208.8 | COD | 2017-06-13 | 2017-04-04 | 2017-05-18 | 2019-03-06 | No | 2018-07-10 | Yes | Not Required | Not Required | Not Required | 2019-08-02 | 2019-08-02 | 2019-08-02 |  |  | 2020-04-30 | 2020-07-21
19INR0052 | TG East Wind | SS Completed, FIS Started, IA | Northrenew | 60722 Coulomb 345kV | Knox | WEST | 2021-12-15 | WIN | WT | 336 |  | 2017-06-13 | 2017-04-04 | 2017-05-18 |  | No | 2018-10-22 | Yes | Not Required | Not Required | Not Required | 2020-04-28
19INR0053 | Hidalgo II Wind | SS Completed, FIS Completed, IA | EDP Renewables | 161705 Mirasole 345kV | Hidalgo | SOUTH | 2020-09-30 | WIN | WT | 51 | COD |  | 2017-04-05 | 2017-05-19 | 2019-04-30 | No | 2019-04-25 | Yes | Not Required | Not Required | Not Required | 2019-04-30 | 2019-04-30 | 2019-04-30 |  |  | 2019-11-27 | 2019-12-10
19INR0056 | Chamon 2 | SS Completed, FIS Completed, IA | Castleman Power | 40260 Chamon 138kV | Harris | HOUSTON | 2021-05-01 | GAS | GT | 100 |  |  | 2017-04-24 | 2017-06-09 | 2019-08-02 | No | 2019-09-20 | No | 2019-03-18 | Not Required
19INR0057 | Old Bloomington Road | SS Completed, FIS Completed, IA | Castleman Power | 8143 Dupont 138kV | Victoria | SOUTH | 2021-05-01 | GAS | GT | 100 |  |  | 2017-04-18 | 2017-05-22 | 2019-03-06 | No | 2020-05-20 | Yes | 2018-08-10 | Not Required | 2020-07-11
19INR0073 | Shakes Solar | SS Completed, FIS Completed, IA | Cypress Creek Renewables | 8283 Asherton 138kV | Zavala | SOUTH | 2021-10-01 | SOL | PV | 206 |  |  | 2017-05-03 | 2017-06-15 | 2019-09-19 | No | 2018-10-26 | Yes | Not Required | Not Required | Not Required | 2019-03-04
19INR0075 | Horseshoe Bend Solar | SS Completed, FIS Started, No IA | Clenera | 1444 Brown 345kV | Brown | NORTH | 2022-12-15 | SOL | PV | 300 | COD | 2018-02-09 | 2017-06-23 | 2017-08-07 |  |  |  | No | Not Required | Not Required | Not Required
19INR0080 | Whitehorse Wind | SS Completed, FIS Completed, IA | Clearway Energy | 68001 Clayton 345kV | Fisher | WEST | 2020-09-30 | WIN | WT | 418.9 | COD |  | 2017-06-23 | 2017-08-07 | 2019-01-22 | No | 2018-12-05 | Yes | Not Required | Not Required | Not Required | 2019-03-12 | 2019-04-02 | 2019-05-01 |  |  | 2019-12-12 | 2019-12-27
19INR0081 | Anson Solar 1 | SS Completed, FIS Completed, IA | Anson Solar Center, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2021-01-19 | SOL | PV | 201.53 | COD | 2018-02-15 | 2017-06-23 | 2017-08-07 | 2020-03-27 | No | 2019-06-05 | Yes | Not Required | Not Required | Not Required | 2019-11-18 | 2020-04-15 | 2020-04-20
19INR0085 | Blue Jay Solar | SS Completed, FIS Completed, No IA | Open Road Renewables | 4 Iola 138kV | Grimes | NORTH | 2021-12-30 | SOL | PV | 210 |  | 2018-02-15 | 2017-05-30 | 2017-08-11 | 2020-06-05 | No |  | No | Not Required | Not Required | Not Required
19INR0088 | Aragorn Solar | SS Completed, FIS Completed, IA | IP Aragorn, LLC | tap 138kV 71097 LCulberson - 7387 Kunitz (71097 LCRA Culberson 138kV) | Culberson | WEST | 2021-06-30 | SOL | PV | 187.2 |  | 2017-08-08 | 2017-05-30 | 2017-07-21 | 2019-12-13 | No | 2018-05-31 | Yes | Not Required | Not Required | Not Required | 2020-03-17 | 2020-07-27 | 2020-07-27
19INR0091 | Phoenix Solar | SS Completed, FIS Completed, IA | G.S.E. ONE LLC | 1808 Bonham 138kV | Fannin | NORTH | 2021-08-10 | SOL | PV | 82.3 |  | 2017-08-09 | 2017-06-23 | 2017-08-23 | 2020-07-27 | No | 2019-10-22 | Yes | Not Required | Not Required | Not Required | 2020-05-06 | 2020-07-15 | 2020-07-16
19INR0093 | Solemio | SS Completed, FIS Started, No IA | SOLEMIO LLC | tap 138kV 1698 Sulphur Springs - 1814 Sulspg | Hopkins | NORTH | 2021-12-31 | SOL | PV | 81.4 |  |  | 2017-06-23 | 2017-08-23 |  | No |  | No | Not Required | Not Required | Not Required
19INR0099a | Kontiki 1 Wind (ERIK) | SS Completed, FIS Started, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2023-03-01 | WIN | WT | 250.1 | MW Size |  | 2017-06-22 | 2017-08-04 |  | No | 2018-05-07 | Yes | Not Required | Not Required | Not Required | 2018-05-07
19INR0099b | Kontiki 2 Wind (ERNEST) | SS Completed, FIS Started, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2023-03-01 | WIN | WT | 250.1 | MW Size |  | 2017-06-22 | 2017-08-04 |  | No | 2018-05-07 | Yes | Not Required | Not Required | Not Required | 2018-05-07
19INR0100 | Prairie Hill Wind | SS Completed, FIS Completed, IA | Prairie Hill LLC | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | McLennan | NORTH | 2020-12-22 | WIN | WT | 300 |  | 2017-06-19 | 2017-06-19 | 2017-08-11 | 2020-04-03 | No | 2018-09-17 | Yes | Not Required | Not Required | Not Required | 2018-11-27 | 2020-04-21 | 2020-04-21
19INR0103 | Rodeo Solar | SS Completed, FIS Started, IA | Core Solar SPV I, LLC | tap 138kV 1134 Littman - 1135 Gasland | Andrews | WEST | 2021-11-01 | SOL | PV | 200 |  | 2018-02-19 | 2017-06-29 | 2017-08-04 |  |  | 2019-08-20 | No | Not Required | Not Required | Not Required
19INR0110 | Angelina Solar | SS Completed, FIS Started, No IA | EDP Renewables | 3349 TMPLinla 138kV | Angelina | NORTH | 2023-06-30 | SOL | PV | 178.89 | COD |  | 2017-07-26 | 2017-09-15 |  | No |  | No | Not Required | Not Required | Not Required
19INR0111 | Tom Green Solar | SS Completed, FIS Started, No IA | EDP Renewables | tap 138kV 6480 SAPS - 60423 Treadwell | Tom Green | WEST | 2021-10-31 | SOL | PV | 150 |  |  | 2017-07-26 | 2017-09-13 |  |  |  | No | Not Required | Not Required | Not Required
19INR0112 | Cranel Wind | SS Completed, FIS Completed, IA | Eon | tap 345kV 8164 Coleto - 8455 Lon Hill | Refugio | COASTAL | 2020-10-15 | WIN | WT | 220 |  |  | 2017-09-12 | 2017-11-01 | 2018-08-30 | No | 2018-10-12 | Yes | Not Required | Not Required | Not Required | 2018-10-12 | 2019-02-27 | 2019-03-26 |  |  | 2020-05-11 | 2020-05-19
19INR0113 | County Line Solar | SS Completed, FIS Started, No IA | S Power | 60385 Solstice 138kV | Pecos | WEST | 2021-12-15 | SOL | PV | 250 |  |  | 2017-08-15 | 2017-11-01 |  |  |  | No | Not Required | Not Required | Not Required
19INR0114 | Rambler Solar | SS Completed, FIS Completed, IA | Rambler Solar | 76009 Twin Buttes 345kV | Tom Green | WEST | 2020-09-18 | SOL | PV | 200 |  | 2018-01-05 | 2017-08-09 | 2017-10-10 | 2019-08-02 | No | 2018-10-11 | Yes | Not Required | Not Required | Not Required | 2019-05-07 | 2019-07-25 | 2019-07-31 |  |  | 2020-01-31 | 2020-04-01
19INR0117 | Roadrunner Crossing Wind | SS Completed, FIS Started, IA | RWE Renewables Development, LLC | tap 345kV 68005 WShack - 68050 Romney | Eastland | NORTH | 2021-12-15 | WIN | WT | 200.2 |  | 2018-03-01 | 2017-09-08 | 2017-11-07 |  | No | 2020-04-17 | Yes | Not Required | Not Required | Not Required | 2020-09-17
19INR0120 | Sherbino II Wind repower | SS Completed, FIS Completed, IA | Sherbino II Wind Farm LLC | 131454 Keo_3 138kV | Pecos | WEST | 2020-10-28 | WIN | WT | -18 |  | 2017-09-21 | 2017-08-18 | 2017-09-28 | 2018-12-04 | No | 2008-02-28 | Yes | Not Required | Not Required | Not Required | 2019-10-28 | 2019-10-28 | 2019-10-28 |  |  |  | 2020-06-09
19INR0121 | Galloway Solar | SS Completed, FIS Completed, IA | 8minutenergy | tap 345kV 76009 Twin Buttes - 1444 Brown | Concho | WEST | 2021-10-01 | SOL | PV | 250 |  | 2017-08-25 | 2017-08-25 | 2017-10-02 | 2020-07-30 |  | 2019-12-20 | Yes | Not Required | Not Required | Not Required | 2020-07-10 | 2020-07-23 | 2020-07-30
19INR0123 | OLD JACKSON SOLAR | SS Completed, FIS Started, No IA | OLD JACKSON SOLAR LLC | tap 138kV 3175 Canton - 3173 Expmtr | Van Zandt | NORTH | 2021-04-23 | SOL | PV | 129.3 |  |  | 2017-09-12 | 2017-11-13 |  | No |  | No | Not Required | Not Required | Not Required
19INR0128 | White Mesa Wind | SS Completed, FIS Started, IA | White Mesa Wind, LLC | 76005 Schneeman Draw 345kV | Crockett | WEST | 2021-07-30 | WIN | WT | 152.3 | MW Size COD |  | 2017-09-08 | 2017-11-20 |  | No | 2018-12-13 | Yes | Not Required | Not Required | Not Required | 2019-06-03
19INR0129 | Flatland Solar | SS Completed, FIS Started, No IA | Sunfinity Renewables | tap 138kV 1032 Morgan - 1064 Sun | Scurry | WEST | 2022-05-31 | SOL | PV | 147 |  | 2018-07-31 | 2017-10-20 | 2017-12-13 |  | No |  | No | Not Required | Not Required | Not Required
19INR0131 | Cutlass Solar | SS Completed, FIS Completed, IA | Cutlass Solar LLC | tap 345kV 44000 WAP - 44200 Hillje, probably | Fort Bend | HOUSTON | 2021-05-31 | SOL | PV | 300 |  | 2018-05-15 | 2017-09-21 | 2017-11-20 | 2020-03-27 | No | 2020-09-23 | No | Not Required | Not Required | Not Required
19INR0134 | Cottonwood Bayou Solar | SS Completed, FIS Completed, IA | Sunchase Power | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2022-01-01 | SOL | PV | 150 | Proj Name COD |  | 2017-09-22 | 2017-11-17 | 2019-03-25 | No | 2019-11-13 | No | Not Required | Not Required | Not Required
19INR0135 | Hill Solar | SS Completed, FIS Started, No IA | Sunchase Power | tap 69kV 3523 Hillsboro - 3532 Itasca | Hill | NORTH | 2022-12-15 | SOL | PV | 80 |  | 2018-05-10 | 2017-09-22 | 2017-11-17 |  |  |  | No | Not Required | Not Required | Not Required
19INR0142 | Bacon Switch Solar | SS Completed, FIS Started, No IA | SunChase Power | tap 345kV 6101 Riley - 1425 Fisher | Wichita | WEST | 2022-06-01 | SOL | PV | 180 |  | 2018-02-15 | 2017-10-11 | 2017-11-08 |  | No |  | No | Not Required | Not Required | Not Required
19INR0145 | Aquilla Lake Wind | SS Completed, FIS Completed, IA | Nextera | 68090 Sam Switch 345 kV | Hill | NORTH | 2021-09-30 | WIN | WT | 202 |  | 2018-07-18 | 2018-07-18 | 2018-09-20 | 2020-01-17 | No | 2020-06-30 | Yes | Not Required | Not Required | Not Required | 2020-07-23
19INR0151 | Impact Solar | SS Completed, FIS Completed, IA | IMPACT SOLAR 1 LLC | tap 345kV 1695 Moses - 1692 Paris | Lamar | NORTH | 2020-12-23 | SOL | PV | 198.55 |  | 2018-05-04 | 2017-12-18 | 2018-02-01 | 2019-09-19 | No | 2019-07-02 | Yes | Not Required | Not Required | Not Required | 2019-09-12 | 2019-10-28 | 2019-10-28 |  |  | 2020-08-10 | 2020-09-02
19INR0155 | Morrow Lake Solar | SS Completed, FIS Completed, IA | Sunchase Power | 5895 Pearsall 138kV | Frio | SOUTH | 2022-04-01 | SOL | PV | 204 |  | 2018-02-15 | 2017-12-05 | 2018-01-15 | 2020-04-15 | No | 2019-08-29 | Yes | Not Required | Not Required | Not Required | 2019-11-18 | 2020-04-15
19INR0156 | Aviator Wind | SS Completed, FIS Completed, IA | Apex Clean | 76090 Divide 345kV | Coke | WEST | 2020-10-01 | WIN | WT | 525 |  | 2018-01-25 | 2017-12-06 | 2018-02-23 | 2019-11-01 | No | 2019-02-14 | Yes | Not Required | Not Required | Not Required | 2019-10-15 | 2019-10-24 | 2019-11-01 |  |  | 2020-06-15 | 2020-06-24
19INR0159 | Reiher Solar | SS Completed, FIS Started, No IA | EnergieKontor US Texas SP 7 LLC | 76597 Robb Sw 138kV | Upton | WEST | 2021-10-31 | SOL | PV | 120 |  | 2018-08-14 | 2018-01-29 | 2018-03-27 |  | No |  | No | Not Required | Not Required | Not Required
19INR0161 | Pierce Wind | SS Completed, FIS Started, No IA | Seventus | 345kV ROW between Hillje & WAP or 345kV Bailey to Hillje | Wharton | SOUTH | 2021-12-31 | WIN | WT | 300 |  |  | 2018-01-03 | 2018-02-16 |  | No |  | No | Not Required | Not Required | Not Required
19INR0163 | Sage Draw Wind | SS Completed, FIS Completed, IA | Lincoln Clean | 23924 Farmland 345kV | Lynn | WEST | 2020-09-13 | WIN | WT | 338 |  |  | 2016-03-14 | 2016-03-23 | 2019-04-17 | No | 2018-01-03 | Yes | Not Required | Not Required | Not Required | 2019-03-22 | 2019-04-30 | 2019-04-30 |  |  | 2019-12-03 | 2019-12-12
19INR0165 | Barranca Wind | SS Completed, FIS Started, No IA | Lincoln Clean Energy, LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2022-01-30 | WIN | WT | 201.6 |  |  | 2018-05-09 | 2018-05-25 |  |  |  | No | Not Required | Not Required | Not Required
19INR0169 | Sun Valley Solar | SS Completed, FIS Completed, IA | Sun Valley Solar LLC | tap 345kV 68090 Sam Sw - 3405 Tradinghouse | Hill | NORTH | 2022-05-31 | SOL | PV | 250 | Proj Name | 2018-11-09 | 2018-03-02 | 2018-04-17 | 2019-12-12 | No | 2020-03-15 | No | Not Required | Not Required | Not Required
19INR0173 | Magnet Wind | SS Completed, FIS Started, No IA | Seventus | 43190 South Lane City 138kV | Wharton | SOUTH | 2021-12-31 | WIN | WT | 125 |  |  | 2018-04-13 | 2018-06-12 |  | No |  | No | Not Required | Not Required | Not Required
19INR0174 | Elbow Creek repower | SS Completed, FIS Completed, IA | NRG | 1058 Longshore 345kV | Howard | WEST | 2019-10-15 | WIN | WT | 0 |  | 2018-07-19 | 2018-05-04 | 2018-05-18 | 2018-09-17 | No | 2007-11-30 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-27
19INR0175 | Shifting Gale Wind | SS Completed, FIS Started, No IA | SEAWAY WIND ENERGY LLC | 23912 Ogallala 345kV | Castro | PANHANDLE | 2024-12-31 | WIN | WT | 289 |  | 2018-12-06 | 2018-04-26 | 2018-06-12 |  | No |  | No | Not Required | Not Required | Not Required
19INR0176 | Roughneck Storage | SS Completed, FIS Started, IA | KCE TX 23, LLC | 43380 W Columbia 138kV | Brazoria | COASTAL | 2021-07-01 | OTH | BA | 50 | Status Change INA-to-PLN | 2018-11-07 | 2018-05-09 | 2018-07-13 |  | No | 2020-05-13 | Yes | Not Required | Not Required | Not Required
19INR0177 | Shanghai Wind | SS Completed, FIS Started, No IA | Seventus | 8104 Lane City PM 138kV | Wharton | SOUTH | 2021-12-31 | WIN | WT | 153.3 |  |  | 2018-05-09 | 2018-06-21 |  | No |  | No | Not Required | Not Required | Not Required
19INR0179 | Barranca Wind II | SS Completed, FIS Started, No IA | Lincoln Clean Energy, LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2021-12-31 | WIN | WT | 201.6 |  |  | 2018-05-15 | 2018-06-01 |  |  |  | No | Not Required | Not Required | Not Required
19INR0184 | Oxy Solar | SS Completed, FIS Completed, IA | Oxy Renewable Energy | 11256 Goldsmith 138kV | Ector | WEST | 2020-09-30 | SOL | PV | 16.2 | COD | 2018-08-07 | 2018-07-18 | 2018-09-20 | 2019-01-30 | No | 2019-01-30 | Yes | Not Required | Not Required | Not Required | 2019-01-30 | 2019-01-30 | 2019-01-31 |  |  | 2019-07-31 | 2019-07-31
19INR0187 | John Paul Jones | SS Completed, FIS Completed, No IA | Dflex Power | 46510 Tomball 138kV | Harris | HOUSTON | 2021-12-31 | GAS | GT | 18.6 |  | 2018-08-02 | 2018-08-02 | 2018-09-28 | 2019-10-03 | No |  | No | 2019-02-14
19INR0189 | SP TX-12B Phase III | SS Completed, FIS Started, No IA | ConEd Development | 76040 Castillo 138kV | Upton | WEST | 2022-12-01 | SOL | PV | 40 |  | 2019-01-29 | 2018-09-12 | 2018-10-03 |  | No |  | No | Not Required | Not Required | Not Required
19INR0203 | Angelo Solar | SS Completed, FIS Started, No IA | ANGELO SOLAR LLC | 76009 Twin Buttes 345kV | Tom Green | WEST | 2022-03-31 | SOL | PV | 195 |  | 2019-01-17 | 2018-11-20 | 2019-02-05 |  | No |  | No |  |  | Not Required
20INR0012 | Lueders Solar | SS Completed, FIS Started, No IA | Innovative Solar | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | WEST | 2022-05-15 | SOL | PV | 40 |  |  | 2017-07-11 | 2017-08-28 |  | No |  | No | Not Required | Not Required | Not Required
20INR0013 | Basalt Solar | SS Completed, FIS Started, No IA | Innovative Solar | tap 138kV 8234 Uvalde - 8241 Razorback | Uvalde | SOUTH | 2022-05-15 | SOL | PV | 20 |  | 2017-10-20 | 2017-07-11 | 2017-09-01 |  | No |  | No | Not Required | Not Required | Not Required
20INR0014 | Obsidian Solar | SS Completed, FIS Started, No IA | Innovative Solar | 6131 Padr 69kV | Cottle | WEST | 2022-05-15 | SOL | PV | 60 |  | 2017-10-20 | 2017-07-11 | 2017-08-28 |  | No |  | No | Not Required | Not Required | Not Required
20INR0015 | Citrine Solar | SS Completed, FIS Completed, No IA | Innovative Solar | Tap 138kV 6135 Paducah Clare - 6117 E Munday | Cottle | WEST | 2022-05-15 | SOL | PV | 45 |  | 2017-10-20 | 2017-07-11 | 2017-08-28 | 2020-08-12 | No |  | No | Not Required | Not Required | Not Required
20INR0016 | Opal Solar | SS Completed, FIS Started, No IA | Innovative Solar | tap 345kV 60501 Tesla - 60500 Edith Clark | Hardeman | WEST | 2022-05-15 | SOL | PV | 45 |  |  | 2017-07-11 | 2017-08-28 |  | No |  | No | Not Required | Not Required | Not Required
20INR0019 | Trinity Hills Wind repower | SS Completed, FIS Completed, IA | Trinity Hills Wind Farm LLC | 150751 & 150752 Trinity Hills 34.5kV | Young | WEST | 2020-09-23 | WIN | WT | -27 |  | 2017-09-21 | 2017-07-20 | 2017-09-08 | 2018-08-02 | No | 2018-10-17 | No | Not Required | Not Required | Not Required | 2019-10-29 | 2019-10-29 | 2019-10-29 |  |  |  | 2020-05-22
20INR0021 | Garnet Solar | SS Completed, FIS Started, IA | Innovative Solar | tap 69kV 3648 Granger - 3649 Taylor | Williamson | SOUTH | 2020-12-18 | SOL | PV | 20 |  |  | 2017-08-10 | 2017-10-10 |  | No | 2019-04-30 | No | Not Required | Not Required | Not Required
20INR0022 | Sandine Solar | SS Completed, FIS Completed, No IA | Innovative Solar | tap 138kV 6135 Paducah - 6320 Tardis | Cottle | WEST | 2022-05-15 | SOL | PV | 30 |  | 2017-10-26 | 2017-08-10 | 2017-10-22 | 2020-06-03 | No |  | No | Not Required | Not Required | Not Required
20INR0029 | Lutum Wind | SS Completed, FIS Started, No IA | EDF Renewable Energy | tap 345kV 6101 Riley - 1730 W Krum | Clay | WEST | 2022-10-01 | WIN | WT | 242 | Proj Name COD |  | 2017-09-12 | 2017-11-07 |  | No |  | No | Not Required | Not Required | Not Required
20INR0031 | Rippey Solar | SS Completed, FIS Completed, IA | BT Cooke Solar, LLC | tap 138kV 1988 ValleyV - 1710 Gainvl | Cooke | NORTH | 2020-12-01 | SOL | PV | 59.8 |  | 2018-02-06 | 2017-10-02 | 2017-11-13 | 2020-01-23 | No | 2019-05-15 | Yes | Not Required | Not Required | Not Required | 2020-05-01 | 2020-05-01 | 2020-05-01
20INR0032 | IP Titan | SS Completed, FIS Completed, IA | IP Titan, LLC | 71097 LCRA Culberson 138kV | Culberson | WEST | 2021-06-30 | SOL | PV | 270 |  | 2018-01-19 | 2017-10-12 | 2017-12-08 | 2019-12-13 | No | 2019-02-04 | Yes | Not Required | Not Required | Not Required | 2020-03-17 | 2020-04-14 | 2020-04-14
20INR0033 | WILDWIND | SS Completed, FIS Completed, IA | Wildcat Creek | tap 345kV 1730 KrumW - 2373 Anna | Cooke | NORTH | 2020-12-15 | WIN | WT | 180.08 |  | 2018-06-14 | 2017-10-18 | 2017-12-11 | 2019-11-25 | No | 2020-02-21 | Yes | Not Required | Not Required | Not Required | 2020-03-23 | 2020-04-30 | 2020-04-30
20INR0035 | Angus Solar | SS Completed, FIS Completed, No IA | Cypress Creek Renewables | tap 138kV 177 Bosque - 181 Cayote | Bosque | NORTH | 2022-05-01 | SOL | PV | 113 |  | 2017-11-13 | 2017-11-13 | 2018-01-02 | 2020-07-20 |  |  | No | Not Required | Not Required | Not Required
20INR0037 | Coniglio Solar | SS Completed, FIS Completed, IA | BT Coniglio Solar, LLC | 1809 Boistret 138kV | Fannin | NORTH | 2021-03-01 | SOL | PV | 125.68 |  | 2018-05-25 | 2017-11-28 | 2018-01-23 | 2019-05-15 | No | 2019-08-03 | Yes | Not Required | Not Required | Not Required | 2020-03-30 | 2020-06-26 | 2020-06-26
20INR0038 | Red Mud Creek | SS Completed, FIS Started, No IA | Eon | tap 345kV 11318 Scurry - 59905 Faraday or 11318-59900 Long Draw | Borden | WEST | 2022-12-15 | WIN | WT | 201 |  |  | 2017-11-29 | 2018-02-05 |  |  |  | No | Not Required | Not Required | Not Required
20INR0040 | Montgomery Ranch Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 60500 EdithC - 60700 Gauss | Foard | WEST | 2022-12-15 | WIN | WT | 200.2 |  | 2018-06-20 | 2017-12-18 | 2018-02-06 |  |  |  | No | Not Required | Not Required | Not Required
20INR0042 | Chalupa Wind | SS Completed, FIS Completed, IA | Acciona | 8640 Kelvin 138kV | Cameron | COASTAL | 2020-12-21 | WIN | WT | 174 |  |  | 2017-12-22 | 2018-02-06 | 2019-08-01 | No | 2018-09-28 | Yes | Not Required | Not Required | Not Required | 2018-10-18 | 2018-12-18 | 2019-10-30 |  |  | 2020-07-30 | 2020-08-10
20INR0043 | Gulf Wind 2 | SS Completed, FIS Started, No IA | TEXAS GULF WIND 2 LLC | 80071 Zorillo 345kV | Kenedy | COASTAL | 2022-07-01 | WIN | WT | 226.5 |  |  | 2018-01-04 | 2018-02-20 |  |  |  | No | Not Required | Not Required | Not Required
20INR0044 | French Goldston Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV 1430 Graham - 1445 Burwick Switch | Young | WEST | 2022-12-15 | SOL | PV | 144 |  | 2018-09-19 | 2018-01-03 | 2018-03-12 |  | No |  | No | Not Required | Not Required | Not Required
20INR0045 | Maverick Creek I W | SS Completed, FIS Completed, IA | Maverick Creek Wind, LLC | 7077 Amos Cr 345kV | Concho | WEST | 2020-12-19 | WIN | WT | 373.2 |  | 2018-03-05 | 2018-01-05 | 2018-02-20 | 2019-04-03 | No | 2018-07-30 | Yes | Not Required | Not Required | Not Required | 2019-10-31 | 2019-10-31 | 2019-10-31 |  |  | 2020-08-11 | 2020-09-01
20INR0046 | Maverick Creek II W | SS Completed, FIS Completed, IA | Maverick Creek Wind, LLC | 7077 Amos Cr 345kV | Concho | WEST | 2021-03-23 | WIN | WT | 118.8 |  | 2018-03-05 | 2018-01-05 | 2018-02-20 | 2020-04-30 | No | 2018-07-30 | Yes | Not Required | Not Required | Not Required | 2020-04-30 | 2020-05-01 | 2020-05-01
20INR0047 | Siete | SS Completed, FIS Started, No IA | Apex Clean | 80219 Lobo 345kV | Webb | SOUTH | 2022-07-31 | WIN | WT | 375.06 | COD | 2019-06-13 | 2018-10-23 | 2018-12-11 |  | No |  | No | Not Required | Not Required | Not Required
20INR0048 | Century Oak Wind | SS Completed, FIS Started, No IA | Engie | 6670 Putnam 138kV | Callahan | WEST | 2022-06-01 | WIN | WT | 126 |  | 2018-05-17 | 2018-01-29 | 2018-02-28 |  |  |  | No | Not Required | Not Required | Not Required
20INR0050 | Castro Solar | SS Completed, FIS Completed, No IA | Oaktree Development | 23912 Ogallala 345kV | Castro | PANHANDLE | 2021-12-15 | SOL | PV | 222.95 |  | 2018-05-15 | 2018-02-08 | 2018-04-09 | 2020-04-23 | No |  | No | Not Required | Not Required | Not Required
20INR0052 | Griffin Trail Wind | SS Completed, FIS Started, IA | Innergex | 60506 AVOGADRO 345 kV | Knox | WEST | 2021-07-09 | WIN | WT | 225.6 | COD |  | 2018-03-05 | 2018-05-04 |  | No | 2019-03-04 | Yes | Not Required | Not Required | Not Required | 2020-06-30
20INR0053 | Bravepost Solar | SS Completed, FIS Started, IA | Recurrent Energy | 6444 Red Creek 345kV | Tom Green | WEST | 2022-05-31 | SOL | PV | 200 |  | 2018-06-07 | 2018-02-22 | 2018-04-13 |  |  | 2019-10-30 | Yes | Not Required | Not Required | Not Required | 2019-11-18
20INR0054 | Taygete Solar | SS Completed, FIS Completed, IA | 7x Energy | 60393 Pig Creek 138kV | Pecos | WEST | 2021-01-28 | SOL | PV | 255.07 | COD |  | 2018-02-26 | 2018-05-04 | 2019-10-29 | No | 2018-10-26 | Yes | Not Required | Not Required | Not Required | 2019-02-05 | 2019-10-29 | 2019-10-29 |  |  | 2020-08-04
20INR0061 | Pflugerville 2 Solar | SS Completed, FIS Started, No IA | RRE Power LLC 1 | tap 138kV 7336 Gillie - 3650 Elgin | Travis | SOUTH | 2021-12-16 | SOL | PV | 120 |  | 2018-10-10 | 2018-03-05 | 2018-04-19 |  | No |  | No | Not Required | Not Required | Not Required
20INR0068 | Blackjack Creek Wind | SS Completed, FIS Started, IA | Eon | 8624 Grissom 345kV | Bee | SOUTH | 2021-08-31 | WIN | WT | 240.5 |  |  | 2018-04-02 | 2018-05-18 |  | No | 2019-10-24 | Yes | Not Required | Not Required | Not Required | 2019-11-24
20INR0069 | Danish Fields Solar | SS Completed, FIS Completed, IA | Sunchase Power | 44200 Hillje 345kV | Wharton | SOUTH | 2022-01-01 | SOL | PV | 201 | COD |  | 2018-04-12 | 2018-06-05 | 2020-01-21 | No | 2020-02-24 | Yes | Not Required | Not Required | Not Required | 2020-03-19
20INR0070 | Monte Bueno | SS Completed, FIS Started, No IA | Terra-Gen | tap 138kV 8392 Bates - 8394 Liston | Hidalgo | SOUTH | 2022-12-31 | WIN | WT | 129.2 |  |  | 2018-04-12 | 2018-05-30 |  | No |  | No | Not Required | Not Required | Not Required
20INR0074 | Pitts Dudik Solar | SS Completed, FIS Completed, No IA | Belltown Power | tap 138kV Hillsoboro 3522- Navarro 3478 | Hill | NORTH | 2022-05-30 | SOL | PV | 50 | COD |  | 2018-04-12 | 2018-05-18 | 2020-02-25 | No |  | No | Not Required | Not Required | Not Required
20INR0075 | Howle Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV 1906 Venus - 68090 Sam Sw | Ellis | NORTH | 2022-12-15 | SOL | PV | 75 |  | 2018-08-09 | 2018-05-15 | 2018-07-02 |  | No |  | No | Not Required | Not Required | Not Required
20INR0080 | Frye Solar | SS Completed, FIS Started, No IA | Hecate Energy | tap 345kV 23912 Ogallala - 23914 Tule Canyon | Swisher | PANHANDLE | 2022-09-30 | SOL | PV | 500 |  | 2018-10-23 | 2018-05-17 | 2018-07-02 |  | No |  | No | Not Required | Not Required | Not Required
20INR0081 | Strategic Solar 1 | SS Completed, FIS Completed, IA | Elm Branch Solar 1, LLC | tap 345kV 2435 Watermill - 68091 Navarro | Ellis | NORTH | 2021-10-31 | SOL | PV | 136.85 |  | 2018-07-18 | 2018-04-26 | 2018-06-05 | 2020-09-25 | No | 2020-01-13 | Yes | Not Required | Not Required | Not Required | 2020-07-10 | 2020-09-29
20INR0082 | Vision Solar 1 | SS Completed, FIS Completed, No IA | Briar Creek Solar 1, LLC | tap 345kV 2428 Watermill - 68091 Navarro | Navarro | NORTH | 2021-10-05 | SOL | PV | 129.24 |  | 2018-05-17 | 2018-04-26 | 2018-06-05 | 2020-09-29 | No |  | Yes | Not Required | Not Required | Not Required
20INR0083 | Baird North Wind | SS Completed, FIS Started, IA | BMP Wind, LLC | 68008 Latimer 345kV | Callahan | WEST | 2021-06-15 | WIN | WT | 331.2 |  |  | 2018-05-04 | 2018-06-12 |  | No | 2019-05-31 | Yes | Not Required | Not Required | Not Required | 2019-07-19
20INR0086 | Arroyo Solar | SS Completed, FIS Started, No IA | Belltown Power | 8318 Rio Hondo 345kV | Cameron | COASTAL | 2021-10-01 | SOL | PV | 180 |  | 2018-10-10 | 2018-05-09 | 2018-07-09 |  | No |  | No | Not Required | Not Required | Not Required
20INR0088 | West Raymond (El Trueno) Wind | SS Completed, FIS Completed, IA | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2021-04-12 | WIN | WT | 239.8 |  |  | 2018-05-14 | 2018-07-09 | 2020-01-31 | No | 2019-05-20 | Yes | Not Required | Not Required | Not Required | 2019-06-06 | 2019-07-30 | 2020-01-31
20INR0089 | Chisholm Grid | SS Completed, FIS Started, IA | Able Grid Energy | 2082 Hicks 138kV | Tarrant | NORTH | 2021-07-09 | OTH | BA | 101.7 |  |  | 2018-05-14 | 2018-06-19 |  | No | 2019-08-16 | Yes | Not Required | Not Required | Not Required | 2019-11-04
20INR0091 | Misae Solar II | SS Completed, FIS Started, IA | Misae Solar Park II | 60501 Tesla 345kV | Childress | PANHANDLE | 2022-12-20 | SOL | PV | 517.35 |  | 2018-05-15 | 2018-05-15 | 2018-07-06 |  | No | 2019-02-21 | Yes | Not Required | Not Required | Not Required
20INR0097 | El Suaz Ranch | SS Completed, FIS Started, No IA | El Sauz Ranch Wind, LLC | 8601 Cebolla 345kV | Willacy | COASTAL | 2022-09-30 | WIN | WT | 301.74 | COD | 2019-02-01 | 2018-06-19 | 2018-08-22 |  |  |  | No | Not Required | Not Required | Not Required
20INR0098 | Danciger Solar | SS Completed, FIS Completed, IA | Brazoria County Solar Project, LLC | tap 138kV 43120 Pledger - 43380 W Columbia | Brazoria | COASTAL | 2022-06-01 | SOL | PV | 203.2 |  | 2018-10-23 | 2018-06-06 | 2018-08-01 | 2020-05-21 | No | 2020-03-20 | No | Not Required | Not Required | Not Required
20INR0101 | Westoria Solar | SS Completed, FIS Completed, IA | Brazoria West Solar Project,LLC | tap 138kV 42980 Nash - 43380 W Columbia | Brazoria | COASTAL | 2021-12-31 | SOL | PV | 203.35 |  | 2018-10-23 | 2018-06-07 | 2018-07-30 | 2020-06-01 | No | 2020-03-20 | Yes | Not Required | Not Required | Not Required | 2020-07-10
20INR0104 | GoodAlta | SS Completed, FIS Completed, IA | Alta Power | tap 138kV 3483 Goodloe - 3127 Trinidad SES | Navarro | NORTH | 2021-04-01 | GAS | GT | 150 |  |  | 2018-07-26 | 2018-09-18 | 2019-08-29 | No | 2020-03-16 | No | 2019-06-13 | Not Required
20INR0106 | Wang Solar | SS Completed, FIS Started, No IA | Fresh Air Energy II, LLC | tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2022-04-30 | SOL | PV | 120 |  | 2018-08-29 | 2018-06-14 | 2018-08-13 |  | No |  | No | Not Required | Not Required | Not Required
20INR0120 | Vortex Wind | SS Completed, FIS Completed, No IA | Tradewind Energy | loop 345kV 60515 Clear Crossing - 1421 WillowCr 345kV | Throckmorton | WEST | 2021-12-31 | WIN | WT | 350 |  | 2019-02-28 | 2018-06-29 | 2018-08-27 | 2020-08-10 | No |  | No | Not Required | Not Required | Not Required
20INR0125 | Alwest | SS Completed, FIS Completed, No IA | Castleman Power | 3114 Paltalco 138kV | Anderson | NORTH | 2022-05-18 | GAS | GT | 200 |  |  | 2018-07-18 | 2018-10-02 | 2020-08-11 | No |  | No | 2019-03-13 | 2019-03-13 | 2020-07-11
20INR0127 | Milam Solar 1 | SS Completed, FIS Started, No IA | Sandow Lakes Ranch Solor I, LLC | tap one 345kV 7040 Austrop - 13429 Sandow line | Milam | SOUTH | 2022-05-26 | SOL | PV | 214 |  | 2019-08-13 | 2018-07-03 | 2018-09-18 |  | No |  | No | Not Required | Not Required | Not Required
20INR0128 | EK Tipton Solar | SS Completed, FIS Started, No IA | EnergieKontor US Texas SP 1 LLC | 6673 Musquiz 138kV | Reeves | WEST | 2021-12-31 | SOL | PV | 120 |  | 2018-09-27 | 2018-09-27 | 2018-11-19 |  | No |  | No | Not Required | Not Required | Not Required
20INR0129 | Foxtrot Wind | SS Completed, FIS Started, IA | Lincoln Clean | tap 345kV 5725 Pawnee – 8606 Goddard | Karnes | SOUTH | 2022-02-01 | WIN | WT | 504 |  |  | 2018-07-26 | 2018-09-14 |  | No | 2020-05-05 | Yes | Not Required | Not Required | Not Required
20INR0130 | Ramsey Solar | SS Completed, FIS Completed, IA | Hecate Energy | 44200 Hillje 345kV | Wharton | SOUTH | 2021-06-01 | SOL | PV | 514 | SFS/NtP | 2018-07-18 | 2018-10-10 | 2018-11-21 | 2020-01-07 | No | 2020-05-29 | Yes | Not Required | Not Required | Not Required
20INR0133 | Thickgrass Solar | SS Completed, FIS Completed, No IA | Origis Energy | 8115 Wadsworth 138kV OR loop into STP - Jones Creek 345-kV line | Matagorda | COASTAL | 2021-12-15 | SOL | PV | 148.7 |  | 2019-03-14 | 2018-07-18 | 2018-10-01 | 2020-07-10 | No |  | No | Not Required | Not Required | Not Required
20INR0134 | Half Moon Solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2022-12-31 | SOL | PV | 151.2 |  |  | 2018-09-13 | 2018-11-09 |  | No |  | No | Not Required | Not Required | Not Required
20INR0135 | Half Moon Battery | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2022-12-31 | OTH | BA | 30.2 |  |  | 2018-09-13 | 2018-11-09 |  | No |  | No | Not Required | Not Required | Not Required
20INR0142 | Ajax Wind | SS Completed, FIS Started, IA | Lincoln Clean | tap 345kV 6101 Riley - 1422 Bowman | Wilbarger | WEST | 2021-08-02 | WIN | WT | 630 | COD |  | 2018-08-14 | 2018-10-19 |  | No | 2020-07-14 | Yes | Not Required | Not Required | Not Required | 2020-08-03
20INR0143 | Soda Lake Solar 2 | SS Completed, FIS Started, IA | Arrington Solar | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | WEST | 2022-05-31 | SOL | PV | 202.99 |  | 2020-09-08 |  | 2016-11-08 |  | No | 2018-08-20 | No | Not Required | Not Required | Not Required
20INR0153 | Tiger Wind | SS Completed, FIS Started, No IA | Nextera | 68000 West Shackelford 345kV | Taylor | WEST | 2022-12-01 | WIN | WT | 300 |  |  | 2018-10-10 | 2018-11-16 |  | No |  | No | Not Required | Not Required | Not Required
20INR0155 | Peyton Creek Wind II | SS Completed, FIS Started, No IA | RWE Renewables Development, LLC | 42400 Refuge 345kV | Matagorda | COASTAL | 2022-12-15 | WIN | WT | 242 |  | 2019-01-30 | 2018-08-21 | 2018-11-02 |  | No |  | No | Not Required | Not Required | Not Required
20INR0162 | Diamondback Solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Starr | SOUTH | 2022-12-31 | SOL | PV | 201.6 |  |  | 2018-09-13 | 2018-12-06 |  | No |  | No | Not Required | Not Required | Not Required
20INR0164 | Files Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV 1907 Venus - 68090 Sam | Hill | NORTH | 2022-05-30 | SOL | PV | 175 | COD |  | 2018-08-29 | 2018-11-08 |  | No |  | No | Not Required | Not Required | Not Required
20INR0202 | Rueter Solar | SS Completed, FIS Completed, No IA | Belltown Power | tap 345kV 68091 Navarro - 68040 Kopperl | Bosque | NORTH | 2022-12-31 | SOL | PV | 200 | COD |  | 2018-09-19 | 2018-10-03 | 2020-02-24 | No |  | No |  |  | Not Required
20INR0203 | Pine Forest Solar | SS Completed, FIS Completed, IA | Telios Corporation | Monticello Switch – Allen Switch 345 kV Line | Hopkins | NORTH | 2022-02-01 | SOL | PV | 284.29 |  | 2019-03-26 | 2018-10-04 | 2018-11-20 | 2020-06-16 | No | 2020-07-29 | No | Not Required | Not Required | Not Required
20INR0204 | BlueBell Solar II | SS Completed, FIS Completed, IA | Bluebell Solar | 76090 Divide 345kV | Sterling | WEST | 2020-12-31 | SOL | PV | 115 |  | 2018-10-23 | 2018-10-23 | 2018-12-13 | 2020-02-06 | No | 2020-03-12 | Yes | Not Required | Not Required | Not Required | 2020-03-12 | 2020-04-20 | 2020-04-20
20INR0205 | Roseland Solar | SS Completed, FIS Completed, No IA | Hecate Energy LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2021-06-01 | SOL | PV | 500 |  | 2018-11-05 | 2018-11-30 | 2019-02-04 | 2020-07-01 | No |  | No |  |  | Not Required
20INR0206 | PES1 | SS Completed, FIS Completed, IA | HO CLARKE GENERATING LLC | 47150 H O Clarke 138kV | Harris | HOUSTON | 2020-12-01 | GAS | GT | 306 |  | 2018-10-23 | 2018-10-23 | 2018-11-16 | 2019-12-02 | No | 2019-12-20 | Yes | 2019-04-10 | Not Required | 2019-12-06 | 2019-12-31 | 2020-03-27 | 2020-03-27
20INR0208 | Signal Ranch | SS Completed, FIS Completed, No IA | Belltown Power Texas, LLC | tap 138kV 6879 Weiland - 6883 Quinlan N | Hunt | NORTH | 2021-11-01 | SOL | PV | 70 |  | 2019-04-02 | 2018-11-07 | 2018-12-20 | 2020-06-17 | No |  | No |  |  | Not Required
20INR0210 | Hopkins Solar | SS Completed, FIS Completed, No IA | GSE Group LLC | tap 345kV 1685 Farmersvl - 1695 Moses (Circuit #2) | Hopkins | NORTH | 2022-05-31 | SOL | PV | 320 | Proj Name | 2019-03-15 | 2018-11-20 | 2019-02-06 | 2020-06-24 | No |  | No |  |  | Not Required
20INR0213 | Brushy Creek Solar | SS Completed, FIS Started, No IA | Brushy Creek Solar LLC | 6444 Red Creek 345kV | Tom Green | WEST | 2023-05-01 | SOL | PV | 177.09 | COD | 2019-03-26 | 2019-01-07 | 2019-03-26 |  | No |  | No | Not Required | Not Required | Not Required
20INR0214 | Noble Solar | SS Completed, FIS Started, No IA | Belltown Power Texas, LLC | 1730 Krum 345kV | Denton | NORTH | 2022-05-30 | SOL | PV | 300 | COD | 2018-11-06 | 2018-11-06 | 2018-12-17 |  | No |  | No |  |  | Not Required
20INR0216 | Starr Solar Ranch | SS Completed, FIS Completed, No IA | Starr Solar Ranch LLC | 8795 Roma 138kV | Starr | SOUTH | 2021-10-01 | SOL | PV | 135.99 |  | 2018-11-07 | 2018-11-07 | 2018-12-14 | 2020-04-01 | No |  | No | Not Required | Not Required | Not Required
20INR0217 | CAROL wind | SS Completed, FIS Completed, IA | Goat Mountain Renewables, LLC | 79504 AJ Swope 345kV | Potter | PANHANDLE | 2021-12-17 | WIN | WT | 169.2 |  | 2019-06-10 | 2018-12-06 | 2019-01-18 | 2020-07-14 | No | 2020-09-11 | No |  |  | Not Required
20INR0219 | Eunice Solar | SS Completed, FIS Completed, IA | 2W Permian Solar LLC | tap 345kV 79650 Clearfork - 79630 Telephone Rd | Andrews | WEST | 2021-01-04 | SOL | PV | 426.7 | COD |  | 2018-12-06 | 2019-01-30 | 2020-05-01 | No | 2019-12-11 | Yes | Not Required | Not Required | Not Required | 2020-02-06 | 2020-04-13 | 2020-05-01
20INR0220 | Eunice Storage | SS Completed, FIS Completed, IA | 2W Permian Solar LLC | tap 345kV 79650 Clearfork - 79630 Telephone Rd | Andrews | WEST | 2021-01-04 | OTH | BA | 40.26 | COD | 2018-12-06 | 2018-12-06 | 2019-01-30 | 2020-05-01 | No | 2019-12-11 | Yes | Not Required | Not Required | Not Required | 2020-02-06 | 2020-05-01 | 2020-05-01
20INR0221 | Braes Power Plant | SS Completed, FIS Completed, No IA | ProEnergy Services LLC | 44650 Smithers 345kV | Fort Bend | HOUSTON | 2022-03-07 | GAS | GT | 398.24 | COD | 2018-12-06 | 2018-12-06 | 2019-01-30 | 2020-09-25 | No |  | No | 2018-12-04 | Not Required
20INR0222 | Tyson Nick Solar | SS Completed, FIS Completed, IA | Tyson Nick Solar Project, LLC | 1700 Toco 138kV | Lamar | NORTH | 2021-12-30 | SOL | PV | 90 | COD | 2019-02-25 | 2018-12-12 | 2019-02-15 | 2020-07-06 | No | 2020-08-28 | No | Not Required | Not Required | Not Required
20INR0226 | Timberwolf POI A Solar | SS Completed, FIS Started, IA | CED Crane Solar 2, LLC | 76635 King Mt 138kV | Upton | WEST | 2022-12-01 | SOL | PV | 152.11 | MW Size | 2019-02-11 | 2018-12-13 | 2019-01-17 |  | No | 2019-12-11 | No | Not Required | Not Required | Not Required
20INR0230 | Markum Solar | SS Completed, FIS Completed, No IA | Glory Leasing | 177 Bosque 138kV | McLennan | NORTH | 2021-12-31 | SOL | PV | 161 |  | 2018-12-17 | 2018-12-18 | 2019-01-03 | 2020-08-24 |  |  | No | Not Required | Not Required | Not Required
20INR0231 | Topaz Power Plant | SS Completed, FIS Completed, IA | Topaz Generating, LLC | 38500 GAF TNP 138kV | Galveston | HOUSTON | 2021-06-01 | GAS | GT | 510 |  | 2019-02-26 | 2019-02-01 | 2019-04-26 | 2020-04-02 | No | 2020-04-28 | Yes | 2019-03-11 | Not Required | 2020-03-16 | 2020-07-10 | 2020-07-10 | 2020-07-10
20INR0232 | Mars Solar | SS Completed, FIS Started, No IA | ABEI ENERGY&INFRASTRUCTURE LLC | 6030 Childress 138kV | Childress | PANHANDLE | 2022-01-10 | SOL | PV | 52.75 |  | 2019-10-21 | 2019-02-06 | 2019-04-29 |  |  |  | No | Not Required | Not Required | Not Required
20INR0233 | Impala Flats Wind | SS Completed, FIS Started, No IA | Antelope Flats Wind, LLC | 79641 Farmland 345kV | Lynn | WEST | 2022-11-01 | WIN | WT | 282 |  | 2019-01-15 | 2019-01-11 | 2019-04-03 |  |  |  | No |  |  | Not Required
20INR0235 | Knickerbocker Solar | SS Completed, FIS Started, No IA | Knickerbocker Solar LLC | Tap 345kV 76003 Big Hill - 76009 Twin Buttes | Tom Green | WEST | 2023-05-01 | SOL | PV | 202.87 | COD | 2019-03-12 | 2019-01-07 | 2019-03-15 |  |  |  | No | Not Required | Not Required | Not Required
20INR0236 | Old Hickory Solar | SS Completed, FIS Started, IA | Old Hickory Solar LLC | tap 345kV 5133 Elmcreek - 5915 STP c2 | Jackson | SOUTH | 2021-05-21 | SOL | PV | 250 |  | 2019-08-27 | 2019-01-25 | 2019-04-19 |  |  | 2020-06-30 | Yes | Not Required | Not Required | Not Required
20INR0238 | Voyager Storage | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2022-12-01 | OTH | BA | 50.14 |  | 2019-04-30 | 2019-01-14 | 2019-03-19 |  |  |  | No | Not Required | Not Required | Not Required
20INR0241 | Crowded Star Solar | SS Completed, FIS Started, IA | Jones City Solar, LLC | tap 345kV 68000 West Shack - 68001 Clayton c2 | Jones | WEST | 2022-12-15 | SOL | PV | 215 |  | 2019-05-23 | 2019-01-21 | 2019-04-19 |  | No | 2019-12-17 | No | Not Required | Not Required | Not Required
20INR0242 | Anson Solar Center, Phase II | SS Completed, FIS Started, No IA | Anson Solar Center, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2021-12-31 | SOL | PV | 200 |  | 2018-02-15 | 2017-06-23 | 2017-08-07 |  |  |  | No | Not Required | Not Required | Not Required
20INR0244 | Montezuma Storage | SS Completed, FIS Started, No IA | Montezuma Storage LLC | 7258 Glidden 138kV | Colorado | SOUTH | 2022-04-15 | OTH | BA | 47.12 |  | 2019-01-08 | 2019-01-15 | 2019-07-02 |  |  |  | No | Not Required | Not Required | Not Required
20INR0245 | Volunteer Storage | SS Completed, FIS Started, No IA | Blackjack Storage LLC | 7216 Lockhart 138kV | Caldwell | SOUTH | 2022-04-01 | OTH | BA | 47.12 |  | 2019-01-16 | 2019-01-15 | 2019-07-02 |  |  |  | No | Not Required | Not Required | Not Required
20INR0246 | Ryan Energy Storage | SS Completed, FIS Completed, No IA | Arrowhead Storage LLC | 37580 TNPancake 69kV | Coryell | NORTH | 2022-04-01 | OTH | BA | 47.12 |  | 2019-02-08 | 2019-01-15 | 2019-04-05 | 2020-08-16 | No |  | No | Not Required | Not Required | Not Required
20INR0247 | Water Valley Wind Energy | SS Completed, FIS Started, No IA | Water Valley Wind Energy, LLC | 76011 Twin Buttes 138kV | Tom Green | WEST | 2021-12-31 | WIN | WT | 150 |  | 2019-01-10 | 2019-01-15 | 2019-03-29 |  |  |  | No |  |  | Not Required
20INR0248 | Second Division Solar | SS Completed, FIS Completed, No IA | TX Gulf Solar 1 LLC | tap 138kV 43120 Pledger - 43380 W Columbia c4 | Brazoria | COASTAL | 2022-05-01 | SOL | PV | 100 |  | 2019-08-06 | 2019-03-28 | 2019-06-18 | 2020-02-06 | No |  | No | Not Required | Not Required | Not Required
20INR0249 | Appaloosa Run Wind_ | SS Completed, FIS Started, No IA | Appaloosa Run, LLC | tap 138kV 60361 Santarita - 76032 NMcCamey | Upton | WEST | 2021-12-31 | WIN | WT | 175 | Proj Name | 2019-02-19 | 2019-01-17 | 2019-04-02 |  |  |  | No |  |  | Not Required
20INR0250 | Aguayo Wind | SS Completed, FIS Completed, No IA | Castle Gap Wind Power | tap 345kV 1444 Brown - 3422 Killeen | Mills | NORTH | 2021-12-31 | WIN | WT | 196 |  | 2019-02-05 | 2019-02-05 | 2019-05-03 | 2020-07-13 |  |  | No |  |  | Not Required
20INR0255 | Dawn Solar | SS Completed, FIS Started, No IA | Renegade Renewable LLC | Tap 345kV 23910 Windmill - 23906 AJ Swope | Deaf Smith | PANHANDLE | 2021-12-21 | SOL | PV | 515.66 |  | 2019-04-01 | 2019-02-26 | 2019-05-17 |  |  |  | No |  |  | Not Required
20INR0256 | Aquilla Lake 2 Wind | SS Completed, FIS Completed, IA | NextEra Energy | 68090 Sam Switch 345 kV | Hill | NORTH | 2021-09-30 | WIN | WT | 100 |  | 2019-03-05 | 2019-05-23 | 2019-08-13 | 2020-01-17 | No | 2020-06-30 | Yes | Not Required | Not Required | Not Required
20INR0257 | Snyder Wind Repower | SS Completed, FIS Started, No IA | Snyder Wind Farm, LLC | 6658 Plainview 69kV | Scurry | WEST | 2021-11-30 | WIN | WT | -15 |  | 2019-12-16 | 2019-03-28 | 2019-06-20 |  |  |  | No |  |  | Not Required
20INR0258 | Snyder BESS | SS Completed, FIS Started, No IA | Snyder Wind Farm, LLC | 6658 Plainview 69kV | Scurry | WEST | 2021-11-30 | OTH | BA | 17.58 |  | 2019-12-18 | 2019-03-28 | 2019-06-20 |  |  |  | No | Not Required | Not Required | Not Required
20INR0259 | San Bernard Solar II | SS Completed, FIS Started, No IA | San Bernard Solar II, LLC | tap 138kV 43012 New Gulf - 43340 Texas Gulf Sulphur | Wharton | SOUTH | 2022-01-01 | SOL | PV | 102 | MW Size COD | 2019-06-12 | 2019-03-25 | 2019-06-12 |  |  |  | No |  |  | Not Required
20INR0261 | Kellam Solar | SS Completed, FIS Completed, IA | BT Kellam Solar, LLC | 6852 Ben Wheeler 138kV | Van Zandt | NORTH | 2020-12-01 | SOL | PV | 59.8 |  | 2019-03-19 | 2019-03-19 | 2019-05-13 | 2019-07-08 | No | 2019-07-30 | Yes | Not Required | Not Required | Not Required | 2020-04-28 | 2020-04-28 | 2020-04-28
20INR0262 | High Lonesome Wind Phase II | SS Completed, FIS Completed, IA | HIGH LONESOME WIND POWER, LLC | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | WEST | 2020-10-15 | WIN | WT | 50.6 |  | 2019-03-28 | 2019-03-25 | 2019-06-20 | 2019-07-31 | No | 2019-07-22 | Yes | Not Required | Not Required | Not Required | 2019-08-02 | 2019-08-02 | 2019-08-02 |  |  | 2020-02-18 | 2020-02-28
20INR0263 | Myrtle Solar II | SS Completed, FIS Completed, No IA | Myrtle Solar II, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2022-01-01 | SOL | PV | 100 | COD |  | 2019-03-25 | 2019-06-03 | 2020-07-19 | No |  | No |  |  | Not Required
20INR0266 | Tres Bahias Solar | SS Completed, FIS Started, IA | Tres Bahias Solar Power LLC | 8140 Joslin 138kV | Calhoun | COASTAL | 2021-12-30 | SOL | PV | 195 |  | 2019-06-03 | 2019-03-26 | 2019-06-11 |  |  | 2020-08-07 | No | Not Required | Not Required | Not Required
20INR0267 | Greens Bayou Expansion | SS Completed, FIS Started, IA | NRG Texas Power | 40715 Greens Bayou 138kV | Harris | HOUSTON | 2021-06-01 | GAS | GT | 140 |  | 2019-04-23 | 2019-04-24 | 2019-07-19 |  | No | 2019-10-31 | No | Not Required | Not Required | 2019-10-28 |  |  | 2019-10-31
20INR0268 | Pyron BESS II | SS Completed, FIS Started, No IA | Pyron Wind Farm, LLC | 1048 Tonkawas 345kV | Nolan | WEST | 2021-04-30 | OTH | BA | 30 |  | 2019-09-09 | 2019-06-03 | 2019-08-30 |  |  |  | No |  |  | Not Required
20INR0269 | Texas Solar Nova 2 | SS Completed, FIS Started, No IA | Texas Solar Nova 1, LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2022-09-30 | SOL | PV | 200.2 |  | 2016-07-06 | 2019-06-24 | 2015-12-30 |  |  |  | No |  |  | Not Required
20INR0274 | SIXTY SIX Solar | SS Completed, FIS Started, No IA | MERIT SI DEVELOPMENT, LLC | 38212 TNMONMNTDC0 138kv | Winkler | WEST | 2021-07-01 | SOL | PV | 3.75 |  | 2019-05-31 | 2019-06-20 | 2019-09-17 |  |  |  | No |  |  | Not Required
20INR0276 | North Fork Energy Storage | SS Completed, FIS Completed, IA | North Fork Energy Storage | 7522 Andice 138kV | Williamson | SOUTH | 2021-05-15 | OTH | BA | 100.49 |  | 2019-05-16 | 2019-05-17 | 2019-08-13 | 2020-06-15 | No | 2020-04-28 | Yes | Not Required | Not Required | Not Required | 2020-07-11
20INR0279 | SHIELD Solar | SS Completed, FIS Started, No IA | MERIT SI DEVELOPMENT, LLC | 60441 OLLIN4A | Crane | WEST | 2021-07-01 | SOL | PV | 1.88 |  | 2019-05-31 | 2019-06-17 | 2019-09-05 |  |  |  | No |  |  | Not Required
20INR0280 | High Lonesome BESS | SS Completed, FIS Started, IA | High Lonesome Storage, LLC | tap 345kV 76002 Bakersfield - 7053 Noelke | Crockett | WEST | 2022-06-01 | OTH | BA | 50 |  | 2019-06-12 | 2019-06-11 | 2019-08-30 |  |  | 2020-08-26 | No | Not Required | Not Required | Not Required
20INR0281 | Queen BESS | SS Completed, FIS Started, IA | Roadrunner Solar Project, LLC | 842 GPL King Mountain 345kV | Upton | WEST | 2022-05-06 | OTH | BA | 50 |  | 2019-06-04 | 2019-06-11 | 2019-10-23 |  |  | 2020-08-06 | No | Not Required | Not Required | Not Required
20INR0282 | Odessa-Ector Unit 2 (Block 2) Uprate Repower | SS Completed, FIS Completed, IA | LA FRONTERA HOLDINGS LLC | 1026 Odessa 345kV | Ector | WEST | 2020-06-15 | GAS | CC | 83 |  |  | 2019-06-18 | 2019-10-23 | 2019-11-01 | No | 2019-11-01 | Yes | 2019-09-30 |  | 2019-10-01 | 2019-11-01 | 2019-11-01 | 2019-11-01
20INR0283 | CITY WEST Solar | SS Completed, FIS Started, No IA | MERIT SI DEVELOPMENT, LLC | 8507 Schottky 69kV | Live Oak | SOUTH | 2021-07-01 | SOL | PV | 4.13 |  | 2019-07-12 | 2019-07-15 | 2019-10-07 |  |  |  | No |  |  | Not Required
20INR0286 | Wise County Power Repower (CT1, CT2) | SS Completed, FIS Completed, IA | Wise County Power Company LLC | 1421 Willow Creek 345kV | Wise | NORTH | 2020-12-01 | GAS | CC | 21 |  | 2019-07-15 | 2019-07-25 | 2019-10-23 | 2019-10-23 | No | 2001-03-19 | Yes | 2020-01-21 |  | 2019-12-05 | 2020-01-22 | 2020-01-27 | 2020-01-27
20INR0287 | STP Unit 1 repower | SS Completed, FIS Completed, No IA | South Texas Electric Generating Station Unit 1 | 5915 STP 345kV | Matagorda | COASTAL | 2020-10-30 | NUC | ST | 13 |  | 2019-10-11 | 2019-07-25 | 2019-10-22 | 2019-10-28 | No |  | Yes | Not Required | Not Required |  | 2019-10-28 | 2019-10-28 | 2019-10-28
20INR0288 | Brazos BESS 2 | SS Completed, FIS Started, No IA | Brazos Wind Ventures, LLC | 1064 Sun 138kV | Borden | WEST | 2022-02-08 | OTH | BA | 50 |  | 2019-09-22 | 2019-08-05 | 2019-10-31 |  |  |  | No |  |  | Not Required
20INR0290 | River Valley Storage 1 | SS Completed, FIS Started, No IA | KCE TX 19, LLC | 3650 Elgin SS 138kV | Williamson | SOUTH | 2021-12-31 | OTH | BA | 52.26 |  | 2019-11-01 | 2019-10-15 | 2020-01-07 |  |  |  | No |  |  | Not Required
20INR0291 | Silicon Hill Storage | SS Completed, FIS Started, IA | KCE TX 12, LLC | 7336 L_GILLCR8_1Y 138kV | Travis | SOUTH | 2021-06-01 | OTH | BA | 104.62 | MW Size COD | 2019-10-29 | 2019-10-15 | 2020-01-07 |  |  | 2020-03-27 | Yes | Not Required | Not Required | Not Required | 2020-04-03 | 2020-07-10
20INR0293 | River Valley Storage 2 | SS Completed, FIS Started, No IA | KCE TX 21, LLC | 3650 Elgin SS 138kV | Williamson | SOUTH | 2021-12-31 | OTH | BA | 52.26 |  | 2019-10-25 | 2019-10-15 | 2020-01-07 |  |  |  | No |  |  | Not Required
20INR0294 | Lily Storage | SS Completed, FIS Completed, IA | Lily Solar, LLC | tap 138kV 6904 CombinRC - 6908 ScuryRC | Kaufman | NORTH | 2021-06-01 | OTH | BA | 51.74 |  | 2020-01-30 | 2019-09-23 | 2019-12-11 | 2020-07-28 |  | 2020-07-14 | Yes | Not Required | Not Required | Not Required | 2020-07-22 | 2020-07-27 | 2020-07-30
20INR0296 | Sand Bluff Wind Repower | SS Completed, FIS Started, No IA | RWE Renewables Development, LLC | 1333 McDonald 138kV | Glasscock | WEST | 2022-12-15 | WIN | WT | 8 |  | 2019-11-27 | 2019-11-27 | 2019-11-27 |  | No |  | No |  |  | Not Required
20INR0305 | Vera Wind V110 | SS Completed, FIS Completed, IA | Longroad Energy | tap 345kV 60500 EdithC - 60700 Gauss (proposed Coloumb substation for 19INR0051) | Knox | WEST | 2020-10-20 | WIN | WT | 34 | COD | 2020-03-24 |  |  | 2019-03-06 | No | 2018-07-10 | Yes | Not Required | Not Required | Not Required | 2019-08-02 | 2019-08-02 | 2019-08-02 |  |  | 2020-04-30 | 2020-07-21
20INR0308 | Gibbons Creek TEERP | SS Completed, FIS Completed, No IA | TEERP Power Station LLC | 967 Gibbons Creek 345kV | Grimes | NORTH | 2020-11-01 | COA | ST | 420 |  | 2020-03-30 | 2020-04-13 | 2020-04-13 | 2020-04-30 | No |  | Yes | 2011-05-31 | Not Required | 2020-03-29 |  |  | 2020-05-01
20INR0312 | Barney Davis IPAC #4 repower | SS Completed, FIS Started, IA | Barney Davis LLC | 8458 Barney Davis 138kV | Nueces | COASTAL | 2020-09-30 | GAS | CC | 48 |  | 2020-07-31 | 2020-06-19 | 2020-09-14 |  | No | 2008-06-18 | No
21INR0005 | Hutt Wind | SS Completed, FIS Started, IA | Pioneer Natural Resources | tap 345kV 11028 Odessa - 59901 Grelton | Midland | WEST | 2021-10-06 | WIN | WT | 336 |  | 2019-04-02 | 2017-09-06 | 2019-08-19 |  |  | 2020-05-26 | No | Not Required | Not Required | Not Required
21INR0006 | Giddings Wind | SS Completed, FIS Started, No IA | Pioneer Natural Resources | 71212 Upton 138kV | Upton | WEST | 2021-12-01 | WIN | WT | 240 |  | 2019-04-02 | 2017-09-06 | 2019-08-19 |  |  |  | No | Not Required | Not Required | Not Required
21INR0008 | Samson Solar | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 | COD |  | 2018-04-12 | 2018-06-12 |  | No |  | No | Not Required | Not Required | Not Required
21INR0012 | Air Products GCA | SS Completed, FIS Completed, IA | Air Products | 39140 TNTxCityMain 69kV (Will be upgraded to 138kV) | Galveston | HOUSTON | 2022-05-15 | GAS | ST | 14 |  | 2019-03-26 | 2018-06-07 | 2018-08-01 | 2020-05-14 |  | 2020-08-07 | Yes | 2019-07-08 | Not Required | 2020-03-31 | 2020-08-21
21INR0016 | Danish Fields II Solar | SS Completed, FIS Completed, IA | Sunchase Power | 44200 Hillje 345kV | Wharton | SOUTH | 2022-01-01 | SOL | PV | 201 | Proj Name COD |  | 2018-05-10 | 2018-07-11 | 2020-01-21 | No | 2020-02-24 | Yes | Not Required | Not Required | Not Required | 2020-03-23
21INR0017 | Danish Fields III Solar | SS Completed, FIS Completed, IA | Sunchase Power | 44200 Hillje 345kV | Wharton | SOUTH | 2022-01-01 | SOL | PV | 201 | Proj Name COD |  | 2018-05-10 | 2018-07-11 | 2020-01-21 | No | 2020-02-24 | Yes | Not Required | Not Required | Not Required | 2020-03-19
21INR0019 | Zier Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 138 kV Pinto Creek (78255) | Kinney | SOUTH | 2022-05-25 | SOL | PV | 160 |  |  | 2018-05-24 | 2018-07-20 |  | No |  | No | Not Required | Not Required | Not Required
21INR0021 | Green Holly Solar | SS Completed, FIS Completed, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2022-05-31 | SOL | PV | 413.6 |  |  | 2018-07-11 | 2018-08-16 | 2020-05-06 | No | 2020-05-19 | No | Not Required | Not Required | Not Required
21INR0022 | Red Holly Solar | SS Completed, FIS Completed, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2022-05-31 | SOL | PV | 260 |  |  | 2018-07-11 | 2018-08-16 | 2020-04-02 | No |  | No | Not Required | Not Required | Not Required
21INR0024 | Samson Solar 2 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 | COD | 2018-10-23 |  | 2018-06-12 |  | No |  | No | Not Required | Not Required | Not Required
21INR0026 | Juno Solar (Phase I) | SS Completed, FIS Completed, IA | IP Juno, LLC | 59906 Long Draw 138 kV | Borden | WEST | 2021-05-15 | SOL | PV | 166.12 |  |  | 2018-08-14 | 2018-10-25 | 2019-12-12 | No | 2018-12-22 | Yes | Not Required | Not Required | Not Required | 2020-03-23 | 2020-04-06 | 2020-04-24
21INR0027 | Zier Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 138 kV Pinto Creek (78255) | Kinney | SOUTH | 2022-05-25 | OTH | BA | 20 |  |  | 2018-05-24 | 2018-07-20 |  | No |  | No | Not Required | Not Required | Not Required
21INR0029 | Green Holly Storage | SS Completed, FIS Completed, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-08-01 | OTH | BA | 50 |  |  | 2018-07-11 | 2018-08-16 | 2020-05-06 | No |  | No | Not Required | Not Required | Not Required
21INR0031 | Indigo Solar | SS Completed, FIS Completed, No IA | Innovative Solar, LLC | tap 345kV 68001 Clayton 345kV - 68000 WShack | Fisher | WEST | 2021-12-15 | SOL | PV | 125 |  | 2019-05-16 | 2018-09-27 | 2018-11-20 | 2020-03-28 | No |  | No | Not Required | Not Required | Not Required
21INR0033 | Red Holly Storage | SS Completed, FIS Completed, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-07-01 | OTH | BA | 50 |  |  | 2018-09-27 | 2018-12-18 | 2020-04-02 | No |  | No | Not Required | Not Required | Not Required
21INR0201 | Brandon | SS Completed, FIS Started, No IA | Lubbock Power and Light | Brandon 69 kV | Lubbock | PANHANDLE | 2021-06-03 | GAS | GT | 21 |  |  | 2018-09-12 | 2018-09-12 |  | No |  | No |  |  | 2020-08-09
21INR0202 | R Massengale | SS Completed, FIS Started, No IA | Lubbock Power and Light | MacKenzie 60 kV | Lubbock | PANHANDLE | 2021-06-03 | GAS | GT | 58 |  |  | 2018-09-12 | 2018-09-12 |  | No |  | No |  |  | 2020-08-09
21INR0203 | Cattlemen Solar Park LLC | SS Completed, FIS Started, No IA | EDP RENEWABLES NORTH AMERICA LLC | tap 345kV 3687 Bell E - 39950 TNP One | Milam | SOUTH | 2023-06-30 | SOL | PV | 238.89 | Proj Name | 2019-04-23 | 2018-10-10 | 2018-12-09 |  | No |  | No |  |  | Not Required
21INR0204 | Lumina Solar | SS Completed, FIS Started, No IA | IP Lumina, LLC | 11305 Dermott 345kV | Scurry | WEST | 2022-06-30 | SOL | PV | 313.2 | Proj Name |  | 2018-09-27 | 2018-11-08 |  | No |  | No |  |  | Not Required
21INR0205 | Radian Solar | SS Completed, FIS Completed, No IA | IP Radian, LLC | 1444 Brown 345kV | Brown | NORTH | 2022-12-31 | SOL | PV | 374.4 | COD |  | 2018-09-27 | 2018-11-08 | 2020-08-03 | No |  | No | Not Required | Not Required | Not Required
21INR0207 | Quantum Solar | SS Completed, FIS Started, No IA | IP Quantum, LLC | tap 60515 Clear Crossing - 6104 Smoky Hill 345kV | Haskell | WEST | 2023-05-31 | SOL | PV | 374.4 | COD | 2018-11-07 | 2018-09-27 | 2018-11-14 |  | No |  | No |  |  | Not Required
21INR0209 | Adamstown Storage | SS Completed, FIS Started, No IA | Adams Creek Solar Project, LLC | tap 345kV 1730 West Krum - 6101 Riley | Wichita | WEST | 2022-12-31 | OTH | BA | 116 |  | 2019-05-22 | 2018-11-20 | 2019-02-04 |  | No |  | No |  |  | Not Required
21INR0210 | Adamstown Solar | SS Completed, FIS Started, No IA | Adams Creek Solar Project, LLC | tap 345kV 1730 West Krum - 6101 Riley | Wichita | WEST | 2022-12-31 | SOL | PV | 250 |  | 2019-05-22 | 2018-11-20 | 2019-02-04 |  | No |  | No |  |  | Not Required
21INR0213 | Vancourt Solar | SS Completed, FIS Started, IA | Rayos Del Sol Solar Project, LLC | tap 138kV 80103 Rangerville - 8554 Mesquite | Cameron | COASTAL | 2021-12-31 | SOL | PV | 50 |  | 2018-11-07 | 2018-11-07 | 2018-12-12 |  | No | 2020-06-11 | Yes | Not Required | Not Required | Not Required | 2020-06-29
21INR0217 | Spectrum Solar | SS Completed, FIS Started, No IA | IP Spectrum, LLC | 1440 Comanche 345kV | Comanche | NORTH | 2023-06-30 | SOL | PV | 400 |  | 2019-02-05 | 2018-11-07 | 2018-12-20 |  | No |  | No |  |  | Not Required
21INR0220 | Maleza Solar | SS Completed, FIS Completed, No IA | Brush Solar LLC | tap 345kV 44200 Hillje - 44040 Bailey | Fort Bend | HOUSTON | 2022-01-01 | SOL | PV | 254.94 | COD | 2019-03-07 | 2018-12-06 | 2019-01-18 | 2020-07-27 | No |  | No |  |  | Not Required
21INR0221 | Delilah Solar 1 | SS Completed, FIS Completed, IA | Samson Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2021-12-31 | SOL | PV | 250 |  | 2019-05-13 | 2018-11-20 | 2019-01-04 | 2020-06-09 | No | 2020-08-26 | No |  |  | Not Required
21INR0223 | Tulsita Solar | SS Completed, FIS Started, No IA | Tulsita Solar LLC | 8590 Tuleta 138kV | Goliad | SOUTH | 2021-05-28 | SOL | PV | 258.35 |  | 2019-05-20 | 2018-12-05 | 2019-02-21 |  | No |  | No | Not Required | Not Required | Not Required
21INR0226 | Equinox Solar 1 | SS Completed, FIS Started, No IA | Invenergy Solar Project Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2023-06-30 | SOL | PV | 200 | COD | 2019-08-14 | 2018-12-11 | 2019-01-23 |  | No |  | No | Not Required | Not Required | Not Required
21INR0227 | Equinox Solar 2 | SS Completed, FIS Started, No IA | Invenergy Solar Project Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2023-06-30 | SOL | PV | 200 |  | 2019-08-05 | 2018-12-11 | 2019-01-31 |  | No |  | No | Not Required | Not Required | Not Required
21INR0228 | Cottonwood Bayou Solar II | SS Completed, FIS Completed, No IA | Cottonwood Bayou Solar II, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2022-01-01 | SOL | PV | 200 | COD | 2019-06-19 | 2018-12-06 | 2019-02-07 | 2020-08-13 | No |  | No | Not Required | Not Required | Not Required
21INR0229 | Prospero Solar II | SS Completed, FIS Completed, IA | Prospero Solar II, LLC | 79650 Clearfork 345kV + 10 mile gen-tie | Andrews | WEST | 2021-07-01 | SOL | PV | 250 |  |  | 2018-11-29 | 2019-02-12 | 2020-01-15 | No | 2020-01-17 | Yes | Not Required | Not Required | Not Required | 2020-05-27
21INR0233 | Taygete II Solar | SS Completed, FIS Completed, IA | Taygete Energy Project II, LLC | 60393 Pig Creek 138kV | Pecos | WEST | 2021-06-01 | SOL | PV | 203.8 |  | 2018-12-06 | 2018-12-17 | 2019-01-15 | 2020-07-24 | No | 2019-03-27 | Yes | Not Required | Not Required | Not Required | 2019-05-06 | 2020-07-29 | 2020-07-30
21INR0237 | Voyager Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2022-05-06 | SOL | PV | 303.9 |  | 2019-04-30 | 2019-01-04 | 2019-03-19 |  |  |  | No | Not Required | Not Required | Not Required
21INR0240 | La Casa Wind | SS Completed, FIS Started, No IA | EC&R development, LLC | tap 138kV 1618 Caddo - 1619 Colony Creek | Stephens | NORTH | 2022-12-15 | WIN | WT | 201 |  |  | 2018-12-28 | 2019-03-12 |  |  |  | No |  |  | Not Required
21INR0244 | Madero Grid | SS Completed, FIS Completed, IA | Madero Grid, LLC | 8824 Railroad 138kV | Hidalgo | SOUTH | 2021-06-01 | OTH | BA | 101.52 | MW Size | 2018-12-19 | 2018-12-20 | 2019-03-12 | 2020-06-09 | No | 2019-12-06 | Yes | Not Required | Not Required | Not Required | 2020-01-13
21INR0247 | Anson Solar Center, Phase III | SS Completed, FIS Started, No IA | Anson Solar Center, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2021-06-01 | SOL | PV | 200 |  | 2018-02-15 | 2017-06-23 | 2017-08-07 |  |  |  | No |  |  | Not Required
21INR0253 | Ulysses Solar | SS Completed, FIS Completed, No IA | Ulysses Solar LLC | tap 345kV 6444 Red Creek - 60040 Bluff Creek | Coke | WEST | 2021-11-01 | SOL | PV | 150 |  | 2019-05-14 | 2019-01-25 | 2019-04-05 | 2020-07-15 |  |  | No | Not Required | Not Required | Not Required
21INR0254 | Blue Cut Solar | SS Completed, FIS Started, No IA | Blue Cut Solar, LLC | tap 138kV 7064 Lampasas - 260 Kempner | Lampasas | NORTH | 2022-06-01 | SOL | PV | 150 |  | 2019-10-10 | 2019-01-30 | 2019-04-12 |  |  |  | No | Not Required | Not Required | Not Required
21INR0256 | Amsterdam Solar | SS Completed, FIS Started, No IA | Cottonwood Bayou Solar II, LLC | tap 345kV 43035 Oasis - 42500 Dow c27 | Brazoria | COASTAL | 2021-11-30 | SOL | PV | 509.88 |  | 2019-10-18 | 2019-02-07 | 2019-04-29 |  |  |  | No | Not Required | Not Required | Not Required
21INR0257 | Mercury Solar | SS Completed, FIS Started, No IA | Mercury Solar, LLC | 68090 Sam Sw 345kV | Hill | NORTH | 2021-12-01 | SOL | PV | 201.6 |  | 2019-02-07 | 2019-02-14 | 2019-05-03 |  |  |  | No | Not Required | Not Required | Not Required
21INR0258 | Mercury Storage | SS Completed, FIS Started, No IA | Mercury Storage, LLC | 68090 Sam Sw 345kV | Hill | NORTH | 2021-12-01 | OTH | BA | 205.9 |  | 2019-02-07 | 2019-02-14 | 2019-05-03 |  |  |  | No | Not Required | Not Required | Not Required
21INR0259 | Sunshine Solar | SS Completed, FIS Started, No IA | Sunshine Energy LLC | tap 138kV 8125 Lolita - 8172 Victoria | Victoria | SOUTH | 2022-07-30 | SOL | PV | 172.83 |  | 2019-02-14 | 2019-02-14 | 2019-03-29 |  |  |  | No |  |  | Not Required
21INR0260 | Chariot Storage | SS Completed, FIS Started, No IA | Chariot Storage LLC | 99 Ben Hur 69kV | Limestone | NORTH | 2022-04-01 | OTH | BA | 47.12 |  | 2019-02-19 | 2019-03-06 | 2019-05-24 |  |  |  | No | Not Required | Not Required | Not Required
21INR0261 | Horizon Solar | SS Completed, FIS Started, IA | First Solar Development, LLC | tap 138kV 5895 Pearsall - 5827 Moore | Frio | SOUTH | 2022-12-31 | SOL | PV | 204.09 | COD | 2019-03-05 | 2019-03-05 | 2019-05-20 |  | No | 2019-07-12 | Yes | Not Required | Not Required | Not Required | 2019-08-09 | 2019-12-09
21INR0262 | Grandfalls Storage | SS Completed, FIS Started, No IA | King Mountain Storage LLC | tap 345kV 11028 Odessa - 76000 North McCamey | Upton | WEST | 2022-12-01 | OTH | BA | 205.9 |  | 2019-02-14 | 2019-03-25 | 2019-06-17 |  |  |  | No |  |  | Not Required
21INR0263 | Monarch Creek Wind | SS Completed, FIS Started, IA | EDF Renewables Development, Inc. | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek Switch (North Circuit) | Throckmorton | WEST | 2021-12-31 | WIN | WT | 349.13 |  | 2019-10-28 | 2019-04-25 | 2019-07-19 |  | No | 2020-08-24 | No | Not Required | Not Required | Not Required
21INR0264 | Monarch Creek Wind (B) | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek Switch (North Circuit) | Haskell | WEST | 2022-12-01 | WIN | WT | 451.5 | COD | 2019-11-20 | 2019-04-25 | 2019-07-19 |  |  |  | No |  |  | Not Required
21INR0265 | Sisters Solar | SS Completed, FIS Started, No IA | Oberon Solar LLC | loop station on double circuit 345kV line 1018 Moss Sw/1029 Odessa Ehv Sw - 11010 Wolf Sw | Ector | WEST | 2021-12-01 | SOL | PV | 610 |  | 2019-02-28 | 2019-02-28 | 2019-03-29 |  | Yes |  | No | Not Required | Not Required | Not Required
21INR0268 | Greyhound Solar | SS Completed, FIS Started, No IA | Rockhound Solar 2, LLC dba "Greyhound Solar" | tap 345kV dbl ckt 11010 Wolf - 1018 Moss and 11008 Wolf - 11028 Odessa | Ector | WEST | 2021-06-30 | SOL | PV | 609 |  | 2019-03-14 | 2019-03-28 | 2019-06-05 |  |  |  | No |  |  | Not Required
21INR0270 | NIGHTINGALE SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY | 1189 Barber 138kV | Mitchell | WEST | 2022-03-04 | SOL | PV | 151.64 |  | 2019-12-13 | 2019-03-26 | 2019-06-10 |  |  |  | No |  |  | Not Required
21INR0271 | TERRANOVA SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY&INFRASTRUCTURE LLC | 6110 East Munday 138kV 345kV Avogadro Station | Knox | WEST | 2022-03-04 | SOL | PV | 152.32 |  | 2019-12-05 | 2019-04-01 | 2019-06-10 |  |  |  | No |  |  | Not Required
21INR0274 | Carol Solar | SS Completed, FIS Completed, IA | Goat Mountain Renewables, LLC | 23906 AJ Swope 345kV | Potter | PANHANDLE | 2021-12-17 | SOL | PV | 223.2 |  | 2019-06-11 | 2019-03-26 | 2019-06-11 | 2020-07-24 | No | 2020-09-11 | No | Not Required | Not Required | Not Required
21INR0276 | Elara Solar | SS Completed, FIS Completed, IA | Elara Energy Project, LLC | 5866 PaloduroSw 138kV | Frio | SOUTH | 2021-09-01 | SOL | PV | 132.4 |  | 2019-03-26 | 2019-03-26 | 2019-06-19 | 2020-07-28 | No | 2019-07-12 | Yes | Not Required | Not Required | Not Required | 2019-09-27 | 2020-08-03
21INR0278 | Fighting Jays Solar | SS Completed, FIS Completed, IA | AP Solar Holdings, LLC | tap 345kV 44000 WA Parish - 44200 Hillje c64 | Fort Bend | HOUSTON | 2022-05-31 | SOL | PV | 356.55 | SFS/NtP | 2019-04-30 | 2019-03-26 | 2019-06-17 | 2020-04-06 | No | 2020-06-22 | Yes |  |  | Not Required
21INR0280 | Edgewater Storage | SS Completed, FIS Started, No IA | Edgewater Battery Storage LLC | 210 Reagor Springs 69kV | Ellis | NORTH | 2022-04-15 | OTH | BA | 47.12 |  | 2019-04-02 | 2019-04-08 | 2019-07-04 |  |  |  | No | Not Required | Not Required | Not Required
21INR0281 | Byrd Ranch Storage | SS Completed, FIS Completed, No IA | Byrd Ranch Storage LLC | 39700 TNSweeny 138kV | Brazoria | COASTAL | 2022-02-01 | OTH | BA | 50 | MW Size COD | 2019-04-02 | 2019-04-08 | 2019-07-04 | 2020-06-17 | No |  | No | Not Required | Not Required | Not Required
21INR0285 | LARISA SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY & INFRASTRUCTURE LLC | Tap 345kV 6235 Mulberry - 6076 Foxtail | Jones | WEST | 2022-03-25 | SOL | PV | 405.09 |  | 2020-01-13 | 2019-04-24 | 2019-07-01 |  |  |  | No |  |  | Not Required
21INR0292 | Slama Solar | SS Completed, FIS Started, No IA | Burkburnett Solar, LLC | Tap 345kV 6101 Riley - 1730 W Krum c1 | Wichita | WEST | 2022-06-01 | SOL | PV | 251.65 |  | 2020-01-15 | 2019-04-18 | 2019-07-03 |  |  |  | No | Not Required | Not Required | Not Required
21INR0293 | Hat Creek Solar | SS Completed, FIS Started, No IA | Hat Creek Solar, LLC | 1464 South Wichita Falls 138kV | Archer | WEST | 2022-06-01 | SOL | PV | 251.67 |  | 2020-01-13 | 2019-04-18 | 2019-06-24 |  |  |  | No | Not Required | Not Required | Not Required
21INR0294 | Brooke Smith Solar | SS Completed, FIS Started, No IA | BN Wind Project LLC | 1444 Brown 345 kV | Brown | NORTH | 2022-05-15 | SOL | PV | 332 |  | 2019-12-11 | 2019-04-16 | 2019-06-11 |  |  |  | No |  |  | Not Required
21INR0295 | Sterling Prairie Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 138kV 8127 Lane City 4A - 8121 Blessings c1 | Matagorda | COASTAL | 2022-03-01 | SOL | PV | 119.91 |  | 2020-01-22 | 2019-04-24 | 2019-07-23 |  |  |  | No |  |  | Not Required
21INR0302 | Ben Milam Solar 1 | SS Completed, FIS Started, No IA | Ben Milam Solar 1 LLC | tap 345kV 3687 Bell E - 39950 TNTNP One, one-third from Bell | Milam | SOUTH | 2023-01-30 | SOL | PV | 203 | COD | 2020-07-15 | 2019-12-19 | 2020-03-12 |  |  |  | No |  |  | Not Required
21INR0303 | James Fannin Solar | SS Completed, FIS Started, No IA | Ben Milam Solar 2 LLC | tap 345kV 3687 Bell E - 39950 TNTNP One, one-half from Bell | Milam | SOUTH | 2023-01-30 | SOL | PV | 254 | COD | 2020-07-15 | 2020-01-22 | 2020-04-13 |  |  |  | No |  |  | Not Required
21INR0304 | James Bowie Solar | SS Completed, FIS Started, No IA | Ben Milam Solar 3 LLC | tap 345kV 3687 Bell E - 39950 TNTNP One, one-fourth from Bell | Bell | NORTH | 2023-01-30 | SOL | PV | 254 | COD | 2020-08-10 | 2020-01-22 | 2020-04-13 |  |  |  | No |  |  | Not Required
21INR0311 | MEISSA SOLAR | SS Completed, FIS Started, No IA | BLUE STONE RENEWABLE VIII LLC | 60417 Tennyson 138kV | Coke | WEST | 2022-03-25 | SOL | PV | 136.37 |  | 2019-12-27 | 2019-04-24 | 2019-07-01 |  |  |  | No |  |  | Not Required
21INR0314 | AQUAMARINE SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY & INFRASTRUCTURE LLC | 6150 Spur 138kV | Dickens | PANHANDLE | 2022-04-25 | SOL | PV | 151.69 |  | 2020-02-13 | 2019-05-10 | 2019-07-31 |  |  |  | No |  |  | Not Required
21INR0320 | Ion Solar | SS Completed, FIS Started, No IA | GSE Group LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2023-05-31 | SOL | PV | 384 |  | 2020-02-03 | 2019-05-17 | 2019-08-01 |  |  |  | No |  |  | Not Required
21INR0321 | Pin Oak Wind | SS Completed, FIS Started, No IA | Limestone Wind Project, LLC | tap 138kV 3515 Hubbard - 213 Haney | Navarro | NORTH | 2022-07-15 | WIN | WT | 99.99 |  | 2020-03-23 | 2019-05-31 | 2019-08-15 |  |  |  | No |  |  | Not Required
21INR0323 | Spanish Crown | SS Completed, FIS Completed, No IA | OCI Alamo 9 LLC | Tap 138kV 3420 Temple Pecan Creek - 3410 Lake Creek | Falls | NORTH | 2022-03-28 | SOL | PV | 103.1 | COD | 2019-05-10 | 2019-05-13 | 2019-07-31 | 2020-05-29 |  |  | No |  |  | Not Required
21INR0324 | Board Creek WP | SS Completed, FIS Started, No IA | Limestone Wind Project, LLC | tap 345kV 68091 Navarro - 46020 Limestone c2 | Navarro | NORTH | 2022-09-01 | WIN | WT | 301 |  | 2019-11-08 | 2019-04-24 | 2019-07-22 |  |  |  | No |  |  | Not Required
21INR0325 | Sheep Creek Wind | SS Completed, FIS Started, No IA | Century Oak Wind Project, LLC | Reata 345kV | Callahan | WEST | 2022-12-15 | WIN | WT | 151.5 |  | 2020-02-05 | 2019-05-30 | 2019-08-15 |  |  |  | No |  |  | Not Required
21INR0326 | Dove Run Solar | SS Completed, FIS Started, No IA | Dove Run Solar Project, LLC | tap 138kV 8510 Falfurrias - 8695 Crestonio | Duval | SOUTH | 2024-12-31 | SOL | PV | 101.25 |  | 2019-05-07 | 2019-05-07 | 2019-07-23 |  |  |  | No |  |  | Not Required
21INR0328 | RIO NOGALES UPGRADE CT2 repower | SS Completed, FIS Completed, IA | CPS Energy | 5392 Rio Nogales 345kV | Guadalupe | SOUTH | 2021-01-14 | GAS | CC | 19 |  | 2019-05-10 | 2019-05-10 | 2019-08-02 | 2020-04-30 |  | 2020-04-18 | No | 2020-03-20 | Not Required | 2020-03-20 | 2020-04-01 | 2020-04-30 | 2020-04-30
21INR0334 | NIGHTFALL SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY & INFRASTRUCTURE LLC | Tap 138kV 8241 Razorback - 8234 Uvalde | Uvalde | SOUTH | 2022-04-25 | SOL | PV | 151.7 |  | 2020-09-24 | 2019-05-10 | 2019-07-31 |  |  |  | No |  |  | Not Required
21INR0341 | Space City Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2022-05-06 | SOL | PV | 609.74 |  | 2019-10-28 | 2019-11-01 | 2020-03-06 |  |  |  | No |  |  | Not Required
21INR0343 | Flag City Solar | SS Completed, FIS Started, No IA | Flag City Solar Project, LLC | tap 138kV 5588 Red Bluff - 5546 Danevang c1 | Jackson | SOUTH | 2023-12-31 | SOL | PV | 150 | Proj Name | 2019-05-07 | 2019-05-07 | 2019-07-29 |  |  |  | No |  |  | Not Required
21INR0344 | Lunis Creek Solar 1 | SS Completed, FIS Started, No IA | Lunis Creek Solar Project, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2023-12-31 | SOL | PV | 202.5 |  | 2019-05-02 | 2019-05-02 | 2019-07-03 |  |  |  | No |  |  | Not Required
21INR0345 | Lunis Creek Storage 1 | SS Completed, FIS Started, No IA | Lunis Creek Solar Project, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2023-12-31 | OTH | BA | 81.2 |  | 2019-05-02 | 2019-05-02 | 2019-07-03 |  |  |  | No |  |  | Not Required
21INR0346 | Lunis Creek Solar 2 | SS Completed, FIS Started, No IA | Lunis Creek Solar Project II, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2023-12-31 | SOL | PV | 202.5 |  | 2019-05-02 | 2019-05-02 | 2019-07-30 |  |  |  | No |  |  | Not Required
21INR0347 | Lunis Creek Storage 2 | SS Completed, FIS Started, No IA | Lunis Creek Solar Project II, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2023-12-31 | OTH | BA | 81.2 |  | 2019-05-02 | 2019-05-02 | 2019-07-30 |  |  |  | No |  |  | Not Required
21INR0349 | Pearl Crescent Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 7640 Rock Island 138kV | Colorado | SOUTH | 2021-12-15 | SOL | PV | 208.35 |  | 2019-06-04 | 2019-05-31 | 2019-08-26 |  |  |  | No |  |  | Not Required
21INR0351 | 7V Solar | SS Completed, FIS Started, IA | 7V Solar Ranch, LLC | tap 138kV 7248 Flatonia - 7274 Plum | Fayette | SOUTH | 2022-09-30 | SOL | PV | 246.3 |  | 2019-10-16 | 2019-04-16 | 2019-07-03 |  |  | 2020-09-01 | No | Not Required | Not Required | Not Required
21INR0352 | YELLOW LIGHT SOLAR | SS Completed, FIS Started, No IA | ABEI ENERGY & INFRASTRUCTURE LLC | 6500 Live Oak 138kV | Schleicher | WEST | 2022-05-07 | SOL | PV | 151.75 |  | 2020-04-07 | 2019-05-21 | 2019-08-13 |  |  |  | No |  |  | Not Required
21INR0353 | Big Elm Solar | SS Completed, FIS Started, No IA | Big Elm Solar, LLC | tap 345kV 3414 Temple - 3409 Lake Creek | Bell | NORTH | 2022-10-31 | SOL | PV | 222.6 |  | 2020-03-25 | 2019-06-27 | 2019-09-23 |  |  |  | No |  |  | Not Required
21INR0354 | Kochab Solar | SS Completed, FIS Started, No IA | Kochab Energy Project, LLC | 8241 Razorback 138kV | Uvalde | SOUTH | 2023-07-01 | SOL | PV | 204 |  | 2019-05-14 | 2019-05-14 | 2019-08-10 |  |  |  | No |  |  | Not Required
21INR0355 | Wilmeth Solar | SS Completed, FIS Started, No IA | Wilmeth Solar, LLC | tap 138kV 8212 Dilley - 8613 Big Well | Frio | SOUTH | 2023-10-31 | SOL | PV | 160 |  | 2020-03-05 | 2019-06-17 | 2019-08-08 |  |  |  | No |  |  | Not Required
21INR0356 | Welder Solar | SS Completed, FIS Started, No IA | Welder Solar, LLC | tap 345kV 8624 Grissom - 8455 Lon Hill | Bee | SOUTH | 2023-10-31 | SOL | PV | 300 |  | 2020-07-08 | 2019-06-18 | 2019-09-13 |  |  |  | No |  |  | Not Required
21INR0357 | SP TX-12B BESS | SS Completed, FIS Completed, IA | CED Upton County BESS, LLC | 132943 SPTX12B 138kV | Upton | WEST | 2021-01-29 | OTH | BA | 22.68 |  | 2019-05-31 | 2019-06-17 | 2019-09-09 | 2020-05-01 | No | 2020-05-01 | Yes | Not Required | Not Required | Not Required | 2020-05-01 | 2020-05-01 | 2020-05-01
21INR0359 | Hickerson Solar | SS Completed, FIS Started, No IA | Belltown Power Texas | tap 345kV 68091 Navarro - 68040 Kopperl | Bosque | NORTH | 2022-05-01 | SOL | PV | 310.4 |  | 2020-05-13 | 2019-05-29 | 2019-08-23 |  |  |  | No |  |  | Not Required
21INR0362 | Oystercatcher Solar | SS Completed, FIS Started, No IA | Oysercatcher Solar LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2022-08-15 | SOL | PV | 220.33 |  | 2020-01-15 | 2019-05-30 | 2019-08-07 |  |  |  | No |  |  | Not Required
21INR0364 | Gambit Batt | SS Completed, FIS Completed, IA | Gambit Energy Storage | 39560 TNAngleton 138kV | Brazoria | COASTAL | 2021-06-01 | OTH | BA | 102.4 | Proj Name | 2019-05-31 | 2019-06-03 | 2019-08-28 | 2020-06-05 | No | 2020-05-28 | Yes | Not Required | Not Required | Not Required | 2020-07-11 | 2020-09-25
21INR0365 | Bat Cave Energy Storage | SS Completed, FIS Started, IA | Bat Cave Energy Storage | 76390 Fort Mason 138kV | Mason | SOUTH | 2021-06-01 | OTH | BA | 100.49 |  | 2019-05-31 | 2019-05-31 | 2019-08-15 |  |  | 2020-02-21 | No | Not Required | Not Required | Not Required
21INR0366 | Brahman Solar | SS Completed, FIS Started, No IA | EC&R Development | tap 345kV 68040 Kopperl - 68091 Navarro | Navarro | NORTH | 2022-06-30 | SOL | PV | 144.01 |  | 2019-12-16 | 2019-07-08 | 2019-10-01 |  |  |  | No |  |  | Not Required
21INR0368 | Eliza Solar | SS Completed, FIS Started, No IA | Ables Springs Solar, LLC | tap 345kV 2478 Royse - 3103 Shamburger | Kaufman | NORTH | 2022-06-01 | SOL | PV | 151.28 | MW Size | 2020-05-04 | 2019-06-21 | 2019-08-30 |  |  |  | No |  |  | Not Required
21INR0371 | Nabatoto Solar 1 | SS Completed, FIS Started, No IA | ConnectGen Operating LLC | tap 345kV 967 Gibbons Creek - 46020 Limestone ckt 18 | Leon | NORTH | 2022-03-31 | SOL | PV | 165 |  | 2019-08-27 | 2019-08-16 | 2019-11-05 |  |  |  | No |  |  | Not Required
21INR0375 | Grizzly Ridge Solar | SS Completed, FIS Started, No IA | Diode Ventures | tap 69kV 273 Gustine - 258 Hamilton | Hamilton | NORTH | 2021-11-01 | SOL | PV | 100 |  | 2019-07-08 | 2019-07-08 | 2019-10-01 |  |  |  | No |  |  | Not Required
21INR0376 | Barranca Wind III | SS Completed, FIS Started, No IA | Barranca Wind Energy, LLC | tap 345kV 80307 Delsol - 80225 Cenizo | Zapata | SOUTH | 2021-12-31 | WIN | WT | 205 |  | 2019-07-12 | 2019-06-26 | 2019-09-23 |  |  |  | No |  |  | Not Required
21INR0377 | Wagon Wheel Solar | SS Completed, FIS Started, No IA | Orion Power Generation, LLC | tap 138kV 60399 WEISS – 6340 Ballinger | Runnels | WEST | 2023-12-31 | SOL | PV | 144.76 |  | 2019-07-22 | 2019-07-17 | 2019-10-08 |  |  |  | No |  |  | Not Required
21INR0378 | Twin Mountain Solar | SS Completed, FIS Started, No IA | Orion Renewable Resources LLC | tap 138kV 1649 Hasse - 290 Shilo | Comanche | NORTH | 2023-12-31 | SOL | PV | 83.86 |  | 2020-02-25 | 2019-07-29 | 2019-10-25 |  |  |  | No |  |  | Not Required
21INR0379 | Ash Creek Solar | SS Completed, FIS Started, No IA | Orion Power Generation, LLC | 68090 SAM SW 345kV | Hill | NORTH | 2021-12-31 | SOL | PV | 408.85 |  |  | 2019-07-29 | 2019-10-25 |  |  |  | No |  |  | Not Required
21INR0380 | Charolais Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 44000 W A Parish - 5915 STP | Matagorda | COASTAL | 2022-12-15 | SOL | PV | 261.63 |  | 2020-05-11 | 2019-08-05 | 2019-10-31 |  |  |  | No |  |  | Not Required
21INR0384 | Concho Valley Solar | SS Completed, FIS Started, IA | MERIT SI, LLC | The crossing of SAPS to Live Oak and SAPS to Yellowjacket 138 kV lines. | Tom Green | WEST | 2022-03-01 | SOL | PV | 159.8 |  | 2019-10-17 | 2019-07-08 | 2019-12-18 |  |  | 2020-09-28 | No |  |  | Not Required
21INR0387 | Anchor Wind | SS Completed, FIS Started, No IA | Ranchland Wind Project,LLC | Tap 345kV 68008 Latimer - 68010 Romney | Eastland | NORTH | 2021-12-24 | WIN | WT | 300 |  | 2019-06-26 | 2019-08-26 | 2019-11-12 |  | No |  | No |  |  | Not Required
21INR0389 | Red-tailed Hawk Solar | SS Completed, FIS Completed, IA | AP Solar 6, LLC | tap 345kV 44200 Hillje - 44000 WA Parish | Wharton | SOUTH | 2021-12-31 | SOL | PV | 355.27 | SFS/NtP | 2019-07-01 | 2019-07-08 | 2019-10-02 | 2020-03-13 |  | 2020-08-28 | Yes | Not Required | Not Required | Not Required | 2020-08-28
21INR0391 | Grandslam Solar | SS Completed, FIS Completed, No IA | Grandslam Solar | 5700 Miracle Lake 138kV | Atascosa | SOUTH | 2021-12-31 | SOL | PV | 228.23 |  | 2019-09-03 | 2019-07-29 | 2019-10-30 | 2020-08-03 |  |  | No |  |  | Not Required
21INR0393 | Talitha Solar | SS Completed, FIS Started, No IA | Talitha Energy Project, LLC | 5660 Orange Grove 138kV | Jim Wells | SOUTH | 2023-02-28 | SOL | PV | 204 | COD | 2019-07-12 | 2019-07-12 | 2019-09-09 |  |  |  | No |  |  | Not Required
21INR0395 | SunRay | SS Completed, FIS Started, No IA | OCI SunRay LLC | tap 138kV 8234 Uvalde - 8241 Razorback | Uvalde | SOUTH | 2022-03-28 | SOL | PV | 200 | COD | 2019-09-13 | 2019-07-17 | 2019-10-14 |  | No |  | No |  |  | Not Required
21INR0398 | MykawaAlta | SS Completed, FIS Started, No IA | Alta Power LLC | tap 138kV 42741 Gulfgate - 43052 Pearland | Harris | HOUSTON | 2021-11-30 | GAS | GT | 300 |  | 2019-08-13 | 2019-08-13 | 2019-11-05 |  |  |  | No
21INR0401 | Young Wind | SS Completed, FIS Started, No IA | Young Wind, LLC | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek | Young | WEST | 2023-10-31 | WIN | WT | 500 |  | 2020-04-13 | 2019-07-29 | 2019-10-25 |  |  |  | No |  |  | Not Required
21INR0403 | Cane Flats Solar | SS Completed, FIS Started, No IA | Cane Flats Solar Project, LLC | 78280 Bevo 138kV | Dimmit | SOUTH | 2023-12-31 | SOL | PV | 127.5 |  | 2019-07-17 | 2019-07-29 | 2019-10-30 |  |  |  | No |  |  | Not Required
21INR0404 | Cane Flats Storage | SS Completed, FIS Started, No IA | Cane Flats Solar Project, LLC | 78280 Bevo 138kV | Dimmit | SOUTH | 2023-12-31 | OTH | BA | 40.6 |  | 2019-07-17 | 2019-07-29 | 2019-10-30 |  |  |  | No |  |  | Not Required
21INR0406 | Old 300 Solar Center | SS Completed, FIS Completed, IA | Lincoln Clean Energy Development | tap 345kV 44200 Hillje - 44000 WA Parish | Fort Bend | HOUSTON | 2021-12-31 | SOL | PV | 400 |  | 2019-08-06 | 2019-08-01 | 2019-10-30 | 2020-09-30 | No | 2020-04-16 | Yes | Not Required | Not Required | Not Required | 2020-05-06
21INR0413 | Big Star Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | Tap 345kV 9074 Lytton - 9073 Holman | Bastrop | SOUTH | 2021-12-15 | SOL | PV | 220.61 |  | 2020-01-02 | 2019-08-27 | 2019-11-08 |  |  |  | No |  |  | Not Required
21INR0414 | Jayhawk Solar | SS Completed, FIS Started, No IA | Renewable Energy Ventures, LLC | tap 345kV 1030 Morgan - 76030 Gasconades | Mitchell | WEST | 2023-02-28 | SOL | PV | 101.5 |  | 2020-06-22 | 2019-08-05 | 2019-10-31 |  |  |  | No |  |  | Not Required
21INR0421 | Armadillo Solar | SS Completed, FIS Started, No IA | Lincoln Clean Energy Development | 3478 Navarro 138kV | Navarro | NORTH | 2022-12-31 | SOL | PV | 204 |  | 2019-09-05 | 2019-08-28 | 2019-11-22 |  |  |  | No |  |  | Not Required
21INR0424 | Tierra Bonita Solar | SS Completed, FIS Started, No IA | Greasewood II, LLC | 844 Nevilesw 345kV | Pecos | WEST | 2022-04-29 | SOL | PV | 309.79 | MW Size | 2020-09-18 | 2019-10-15 | 2020-01-02 |  |  |  | No |  |  | Not Required
21INR0428 | Nabatoto Solar 2 | SS Completed, FIS Started, No IA | ConnectGEN West LLC | tap 345kV 967 Gibbons Creek - 46020 Limestone ckt 50 | Leon | NORTH | 2022-06-30 | SOL | PV | 400 |  | 2019-08-16 | 2019-09-23 | 2019-12-10 |  |  |  | No |  |  | Not Required
21INR0430 | Holstein 2 Energy Storage | SS Completed, FIS Started, No IA | 229HD 8me LLC | 11406 Central Bluff 345kV | Nolan | WEST | 2022-06-01 | OTH | BA | 102.5 |  | 2019-09-16 | 2019-08-26 | 2019-11-12 |  |  |  | No |  |  | Not Required
21INR0431 | Galloway 2 Solar | SS Completed, FIS Started, IA | 224WB 8me LLC | tap 345kV 76009 Twin Buttes - 1444 Brown | Concho | WEST | 2022-04-01 | SOL | PV | 110 |  |  | 2019-08-28 | 2017-10-02 |  |  | 2019-12-20 | Yes | Not Required | Not Required | Not Required | 2020-07-27
21INR0432 | Diversion Wind | SS Completed, FIS Started, No IA | Diversion Wind Development LLC | 6101 Riley 345kV | Baylor | WEST | 2021-12-31 | WIN | WT | 300 |  | 2020-07-15 | 2019-09-10 | 2019-12-04 |  |  |  | No |  |  | Not Required
21INR0434 | Golinda Solar | SS Completed, FIS Started, No IA | OCI SOL LLC | Tap 138kV 3420 Temple Pecan Creek - 3410 Lake Creek | Falls | NORTH | 2022-03-28 | SOL | PV | 103.1 | COD | 2019-08-26 | 2019-09-23 | 2019-12-10 |  |  |  | No |  |  | Not Required
21INR0440 | Wren Solar | SS Completed, FIS Started, No IA | Wren Solar, LLC | 8601 Cebolla 345kV | Willacy | COASTAL | 2023-12-29 | SOL | PV | 170 |  |  | 2019-10-15 | 2020-01-02 |  |  |  | No |  |  | Not Required
21INR0442 | Myrtle Storage | SS Completed, FIS Started, No IA | Myrtle Storage, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2022-01-01 | OTH | BA | 150.83 | COD | 2020-08-03 | 2019-11-04 | 2020-02-07 |  |  |  | No |  |  | Not Required
21INR0443 | Cottonwood Bayou Storage | SS Completed, FIS Started, No IA | Cottonwood Bayou Storage, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2022-01-01 | OTH | BA | 150.83 | COD | 2020-07-20 | 2019-10-31 | 2020-01-23 |  |  |  | No |  |  | Not Required
21INR0444 | Long Point Storage | SS Completed, FIS Started, No IA | Long Point Storage, LLC | tap 138kV 44010 WAP - 42980 Nash. | Brazoria | COASTAL | 2021-12-01 | OTH | BA | 100 | FIS Request | 2020-09-17 | 2019-11-01 | 2020-02-05 |  |  |  | No |  |  | Not Required
21INR0445 | Brushy Creek Storage | SS Completed, FIS Started, No IA | Brushy Creek Solar LLC | 6444 Red Creek 345kV | Tom Green | WEST | 2023-05-01 | OTH | BA | 25.14 | COD | 2019-12-16 | 2019-12-12 | 2020-03-05 |  |  |  | No |  |  | Not Required
21INR0446 | Knickerbocker Storage | SS Completed, FIS Started, No IA | Knickerbocker Solar LLC | Tap 345kV 76003 Big Hill - 76009 Twin Buttes | Tom Green | WEST | 2023-05-01 | OTH | BA | 25 | COD | 2020-01-10 | 2019-12-19 | 2020-03-06 |  |  |  | No |  |  | Not Required
21INR0449 | Panther Creek III Repower | SS Completed, FIS Completed, IA | Panther Creek Wind Farm Three, LLC | 1058 Longshore 345kV | Howard | WEST | 2021-02-02 | WIN | WT | 15.96 |  | 2019-12-02 | 2019-11-27 | 2020-02-14 | 2020-04-24 | No | 2009-03-19 | No |  |  | Not Required | 2020-08-03 | 2020-08-03 | 2020-08-03
21INR0450 | Danish Fields Storage | SS Completed, FIS Started, No IA | Danish Fields Storage, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2022-01-01 | OTH | BA | 150.83 | COD | 2020-07-20 | 2019-10-31 | 2020-01-24 |  |  |  | No |  |  | Not Required
21INR0454 | Racetrack Solar | SS Completed, FIS Started, No IA | Innergex Renewables USA, LLC | tap 138kV 8234 Uvalde - 8236 West Batesville | Uvalde | SOUTH | 2022-05-01 | SOL | PV | 120 |  | 2020-09-08 | 2019-11-18 | 2020-01-28 |  |  |  | No |  |  | Not Required
21INR0455 | Independence Trail Storage | SS Completed, FIS Started, No IA | KCE TX 16, LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2021-08-01 | OTH | BA | 100 |  | 2019-11-11 | 2019-12-03 | 2020-02-24 |  |  |  | No |  |  | Not Required
21INR0456 | Maleza Storage | SS Completed, FIS Started, No IA | Brush Storage, LLC | tap 345kV 44200 Hillje - 44040 Bailey | Wharton | SOUTH | 2021-12-01 | OTH | BA | 150.83 | MW Size | 2020-08-24 | 2019-10-31 | 2020-01-24 |  |  |  | No |  |  | Not Required
21INR0458 | Porter Solar | SS Completed, FIS Started, No IA | Lantana Solar, LLC | tap 345kv 1429 Jacksboro - 1730 Krum West | Denton | NORTH | 2023-04-13 | SOL | PV | 276.7 |  | 2020-08-24 | 2020-01-30 | 2020-04-17 |  |  |  | No |  |  | Not Required
21INR0459 | DeCordova BESS addition | SS Completed, FIS Started, No IA | Luminant Generation Company LLC | 1891 Decordova 138kV | Hood | NORTH | 2021-02-28 | OTH | BA | 263.3 |  | 2019-11-11 | 2019-11-18 | 2020-01-31 |  |  |  | No |  |  | Not Required
21INR0460 | Republic Road Storage | SS Completed, FIS Started, No IA | KCE TX 11, LLC | 35 Hearne 138kV | Robertson | NORTH | 2021-06-01 | OTH | BA | 50 |  | 2020-01-16 | 2019-12-06 | 2020-02-25 |  | No |  | No |  |  | Not Required
21INR0465 | San Bernard Storage | SS Completed, FIS Started, No IA | San Bernard Storage, LLC | tap 138kV 43012 New Gulf - 43340 Texas Gulf Sulphur | Wharton | SOUTH | 2022-06-01 | OTH | BA | 100 | FIS Request | 2020-09-21 | 2019-11-27 | 2020-02-11 |  |  |  | No |  |  | Not Required
21INR0467 | Apogee Wind | SS Completed, FIS Started, IA | EDF Renewables Development, Inc. | Tap 345kV 6235 Mulberry - 6076 Foxtail | Haskell | WEST | 2021-12-31 | WIN | WT | 393.24 |  | 2019-11-27 | 2019-12-03 | 2020-03-08 |  | No | 2020-03-10 | Yes | Not Required | Not Required | Not Required | 2020-03-27
21INR0469 | Big Star Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | Tap 345kV 9074 Lytton - 9073 Holman | Bastrop | SOUTH | 2022-04-04 | OTH | BA | 90 |  |  | 2020-01-02 | 2020-03-26 |  |  |  | No |  |  | Not Required
21INR0470 | Pearl Crescent Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 7640 Rock Island 138kV | Colorado | SOUTH | 2021-12-15 | OTH | BA | 50.26 | MW Size | 2020-09-18 | 2019-12-20 | 2020-03-12 |  |  |  | No |  |  | Not Required
21INR0473 | Vortex BESS | SS Completed, FIS Started, No IA | AZURE SKY WIND STORAGE LLC | loop 345kV 60515 Clear Crossing - 1421 WillowCr 345kV | Throckmorton | WEST | 2021-12-31 | OTH | BA | 121.83 |  | 2019-11-27 | 2019-12-03 | 2020-03-08 |  |  |  | No |  |  | Not Required
21INR0474 | Anchor BESS | SS Completed, FIS Started, No IA | Ranchland Wind Project,LLC | Tap 345kV 68008 Latimer - 68010 Romney | Eastland | NORTH | 2021-12-24 | OTH | BA | 100.76 | MW Size COD | 2019-11-27 | 2019-12-03 | 2020-02-25 |  |  |  | No |  |  | Not Required
21INR0476 | Azure Sky BESS | SS Completed, FIS Started, IA | Azure Sky Solar Project, LLC | 60515 Clear Crossing 345kV | Haskell | WEST | 2021-06-01 | OTH | BA | 77.6 |  | 2019-12-27 | 2019-12-12 | 2020-03-05 |  | No | 2020-04-01 | Yes | Not Required | Not Required | Not Required | 2020-04-14
21INR0477 | Azure Sky Solar | SS Completed, FIS Started, IA | Azure Sky Solar Project, LLC | 60515 Clear Crossing 345kV | Haskell | WEST | 2021-06-01 | SOL | PV | 228.4 |  | 2020-01-31 | 2019-12-12 | 2020-03-05 |  | No | 2020-04-01 | Yes | Not Required | Not Required | Not Required | 2020-04-15
21INR0479 | Endurance Park Storage | SS Completed, FIS Started, No IA | KCE TX 13, LLC | 11306 Dermott 138kV | Scurry | WEST | 2022-01-17 | OTH | BA | 52.25 |  | 2019-12-03 | 2019-11-27 | 2020-02-14 |  |  |  | No |  |  | Not Required
21INR0480 | Juanita Hill Storage | SS Completed, FIS Started, No IA | KCE TX 20, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2021-12-01 | OTH | BA | 208.96 |  | 2019-12-03 | 2019-11-27 | 2020-02-12 |  | No |  | No |  |  | Not Required
21INR0481 | Lunar Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 5133 Elm Creek - 5915 STP (CKT 1) | Wharton | SOUTH | 2022-05-06 | SOL | PV | 609.74 | SFS/NtP | 2020-03-30 | 2019-12-17 | 2020-03-11 |  |  |  | Yes |  |  | Not Required
21INR0482 | Sisters Storage | SS Completed, FIS Started, No IA | Oberon Solar | loop station on double circuit 345kV line 1018 Moss Sw/1029 Odessa Ehv Sw - 11010 Wolf Sw | Ector | WEST | 2021-12-01 | OTH | BA | 504.44 |  | 2020-03-30 | 2019-12-18 | 2020-03-11 |  |  |  | No |  |  | Not Required
21INR0484 | Mustang Creek Storage | SS Completed, FIS Started, No IA | Ganado Storage, LLC | tap 138kV 5523 ETP - 78104 Ricebird new sub Galow | Jackson | SOUTH | 2022-01-01 | OTH | BA | 150 | FIS Request | 2020-09-22 | 2020-01-02 | 2020-03-23 |  |  |  | No |  |  | Not Required
21INR0485 | Texana Storage | SS Completed, FIS Started, No IA | Louise Storage, LLC | tap 138kV 8102 El Campo - 8117 Ganado | Wharton | SOUTH | 2022-12-15 | OTH | BA | 150 | FIS Request | 2020-09-04 | 2019-12-16 | 2020-03-11 |  |  |  | No |  |  | Not Required
21INR0486 | Pandora Solar | SS Completed, FIS Started, No IA | Pandora | Tap 345kV 5915 STP - 5133 Elm Creek, c1 | Wilson | SOUTH | 2023-12-01 | SOL | PV | 252 |  |  | 2020-01-03 | 2020-03-23 |  |  |  | No |  |  | Not Required
21INR0487 | Nickel Prairie Storage | SS Completed, FIS Started, No IA | KCE TX 17, LLC | 44600 Rosharon 138kV | Brazoria | COASTAL | 2021-12-31 | OTH | BA | 208.96 |  | 2020-01-15 | 2019-12-23 | 2020-03-13 |  | No |  | No |  |  | Not Required
21INR0488 | Cottage Meadow Storage | SS Completed, FIS Started, No IA | KCE TX 18, LLC | 8319 Rio Hondo 138kV | Cameron | COASTAL | 2021-10-31 | OTH | BA | 208.96 |  | 2020-01-17 | 2020-01-14 | 2020-04-07 |  | No |  | No |  |  | Not Required
21INR0490 | Delilah Solar 1A | SS Completed, FIS Completed, IA | Samson Solar Energy II LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 |  | 2020-01-14 | 2020-01-13 | 2019-01-04 | 2020-06-09 |  | 2020-08-27 | No |  |  | Not Required
21INR0491 | Delilah Solar 1B | SS Completed, FIS Completed, IA | Samson Solar Energy III LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2021-12-31 | SOL | PV | 250 |  | 2020-01-14 | 2020-01-13 | 2019-01-04 | 2020-06-09 |  | 2020-08-27 | No |  |  | Not Required
21INR0492 | Stockyard Grid | SS Completed, FIS Started, No IA | Stockyard Grid, LLC | 2082 Hicks 138kV | Tarrant | NORTH | 2021-11-01 | OTH | BA | 101.7 |  | 2020-02-05 | 2020-01-13 | 2020-03-30 |  |  |  | No |  |  | Not Required
21INR0493 | Ellis Solar | SS Completed, FIS Started, No IA | Ellis Solar, LLC | tap 138kV 2303 KEMPRNCH_8 - 2305 AIRPRD_T8 | Ellis | NORTH | 2021-11-01 | SOL | PV | 81 |  | 2020-02-26 | 2020-01-30 | 2020-03-03 |  |  |  | No |  |  | Not Required
21INR0495 | Belding 2 | SS Completed, FIS Started, No IA | Triple Butte II LLC | 38490 TNBelding 69kV | Pecos | WEST | 2021-06-30 | OTH | BA | 51.48 |  | 2020-05-20 | 2020-03-26 | 2020-06-11 |  |  |  | No |  |  | Not Required
21INR0496 | Flower Valley II Batt | SS Completed, FIS Started, No IA | Flower Valley II, LLC | 38069 TN Flat Top 138kV | Reeves | WEST | 2021-06-30 | OTH | BA | 100.98 | Proj Name | 2020-05-20 | 2020-03-26 | 2020-06-11 |  |  |  | No |  |  | Not Required
21INR0497 | Swoose II | SS Completed, FIS Started, No IA | Swoose II, LLC | 38001 TNPyote 138kV | Ward | WEST | 2021-06-30 | OTH | BA | 100.98 |  | 2020-05-20 | 2020-03-26 | 2020-06-11 |  |  |  | No |  |  | Not Required
21INR0498 | Baird North II | SS Completed, FIS Started, No IA | BMP Wind LLC | 68008 Latimer 345kV | Callahan | WEST | 2021-09-15 | WIN | WT | 20 |  | 2020-08-24 | 2020-05-01 | 2020-07-30 |  |  |  | No |  |  | Not Required
21INR0499 | Neptune Solar | SS Completed, FIS Started, No IA | Matagorda Solar LLC | 8126 Formosa 138kV | Jackson | SOUTH | 2021-09-20 | SOL | PV | 204.65 |  | 2020-04-16 | 2020-04-13 | 2020-07-07 |  |  |  | No |  |  | Not Required
21INR0500 | SkySealy | SS Completed, FIS Started, No IA | Sky Global Power Two, LLC | 44700 Gebhardt 138kV | Austin | SOUTH | 2021-12-21 | GAS | IC | 143 |  | 2020-06-19 | 2020-05-01 | 2020-07-15 |  |  |  | No | 2020-04-15
21INR0501 | Juno Solar (Phase II) | SS Completed, FIS Completed, IA | IP Juno, LLC | 59906 Long Draw 138 kV | Borden | WEST | 2021-08-15 | SOL | PV | 147.09 |  |  | 2020-03-23 | 2018-10-25 | 2019-12-12 |  | 2018-12-22 | Yes | Not Required | Not Required | Not Required | 2020-03-23 | 2020-04-06 | 2020-04-24
21INR0502 | LUND STORAGE | SS Completed, FIS Started, No IA | RRE POWER STORAGE 1 LLC | tap 138kV 7336 Gillie - 3650 Elgin | Travis | SOUTH | 2022-11-15 | OTH | BA | 60 |  | 2020-08-18 | 2020-05-01 | 2020-07-15 |  |  |  | No |  |  | Not Required
21INR0506 | Ty Cooke | SS Started, FIS Started, No IA | Lubbock Power and Light | 59166 LP Holly 69kV | Lubbock | PANHANDLE | 2021-07-31 | GAS | GT | 33 |  |  | 2020-08-21 |  |  |  |  | No | Not Required
21INR0508 | Angels Creek | SS Completed, FIS Started, No IA | Angels Creek LLC | 5888 Bruni 69kV | Webb | SOUTH | 2021-05-31 | OTH | BA | 30 |  | 2020-07-27 | 2020-06-03 | 2020-08-18 |  |  |  | No |  |  | Not Required
21INR0510 | Crossett Power | SS Completed, FIS Started, IA | Crossett Power Management LLC | 76026 Soda Lake 138kV | Crane | WEST | 2021-07-15 | OTH | BA | 208.61 |  | 2020-06-09 | 2020-06-03 | 2020-08-18 |  |  | 2020-08-05 | No |  |  | Not Required
21INR0515 | Roadrunner Crossing Wind II | SS Completed, FIS Started, No IA | RWE Renewables Development, LLC | tap 345kV 68005 WShack - 68050 Romney | Eastland | NORTH | 2021-12-15 | WIN | WT | 105.6 |  |  | 2020-07-02 | 2020-09-14 |  |  |  | No |  |  | Not Required
21INR0516 | Cone Mountain Batt | SS Started, FIS Started, No IA | Ramsay Draw LLC | 6666 Alpine 69kV | Brewster | WEST | 2021-10-01 | OTH | BA | 102.96 | Proj Name |  | 2020-09-02 |  |  |  |  | No |  |  | Not Required
21INR0517 | Tidwell Prairie Storage 1 | SS Started, FIS Started, No IA | Tidwell Prairie LLC | 39950 TNP ONE PLANT 345kV | Robertson | NORTH | 2022-03-01 | OTH | BA | 304.78 | COD | 2020-07-23 | 2020-07-24 |  |  |  |  | No |  |  | Not Required
21INR0519 | Egret Hill Storage | SS Started, FIS Started, No IA | Coyote Crossing LLC | 837 DentSw 138kV | Hunt | NORTH | 2021-10-01 | OTH | BA | 205.63 |  | 2020-09-03 | 2020-09-02 |  |  |  |  | No |  |  | Not Required
22INR0001 | Samson Solar 3 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 | COD | 2018-10-23 |  | 2018-06-12 |  | No |  | No | Not Required | Not Required | Not Required
22INR0202 | Delilah Solar 2 | SS Completed, FIS Completed, No IA | Delilah Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2022-06-01 | SOL | PV | 300 |  | 2019-05-13 | 2018-11-20 | 2019-01-03 | 2020-06-09 | No |  | No | Not Required | Not Required | Not Required
22INR0203 | Delilah Solar 3 | SS Completed, FIS Completed, No IA | Delilah Solar Energy II LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2023-06-30 | SOL | PV | 310 |  | 2019-05-13 | 2018-11-20 | 2019-01-03 | 2020-06-09 | No |  | No | Not Required | Not Required | Not Required
22INR0205 | Sbranch Solar | SS Completed, FIS Completed, IA | CG Wharton County LLC | Tap 138kV 44190 East Bernard - 44130 Caney | Wharton | SOUTH | 2022-04-01 | SOL | PV | 154 | Proj Name | 2019-04-01 | 2019-01-03 | 2019-03-13 | 2020-05-01 | No | 2020-07-26 | Yes | Not Required | Not Required | Not Required
22INR0209 | Crescent Solar | SS Completed, FIS Started, No IA | Crescent Solar | 6101 Riley 345kV | Wilbarger | WEST | 2022-12-31 | SOL | PV | 253.68 |  | 2019-09-23 | 2019-01-17 | 2019-04-02 |  |  |  | No | Not Required | Not Required | Not Required
22INR0211 | Schoolhouse Solar | SS Completed, FIS Started, No IA | Schoolhouse Solar, LLC | tap 345kV 7040 Austrop - 13429 Sandow | Lee | SOUTH | 2022-06-01 | SOL | PV | 150.84 |  | 2019-10-08 | 2019-01-30 | 2019-04-09 |  |  |  | No | Not Required | Not Required | Not Required
22INR0213 | Dexter Solar | SS Completed, FIS Started, No IA | 241BB 8me LLC | tap 345kV 60040 Bluff Creek - 6444 Red Creek | Runnels | WEST | 2023-05-02 | SOL | PV | 330.12 |  |  | 2019-03-05 | 2019-05-28 |  |  |  | No | Not Required | Not Required | Not Required
22INR0215 | TEXAS SOLAR NOVA 3 | SS Completed, FIS Started, No IA | Texas Solar Nova 1, LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2023-01-31 | SOL | PV | 200.2 |  | 2019-05-28 | 2019-06-24 | 2015-12-30 |  |  |  | No |  |  | Not Required
22INR0218 | Greyhound Solar 2 | SS Completed, FIS Started, No IA | Greyhound Solar 2 | tap 345kV dbl ckt 11010 Wolf - 1018 Moss and 11008 Wolf - 11028 Odessa | Ector | WEST | 2022-12-15 | SOL | PV | 500 |  | 2019-05-23 | 2019-05-14 | 2019-08-05 |  |  |  | No |  |  | Not Required
22INR0220 | Lamkin Solar | SS Completed, FIS Started, No IA | Commanche Solar I, LLC | tap 69kV 258 Hamilton - 273 Gustine | Comanche | NORTH | 2022-12-31 | SOL | PV | 101.5 |  | 2020-05-11 | 2019-06-24 | 2019-09-18 |  |  |  | No |  |  | Not Required
22INR0223 | Eiffel Solar | SS Completed, FIS Completed, No IA | Paris Farm Solar, LLC | Tap 138kV 1693 Paris Switch - 1769 Paris East Tap | Lamar | NORTH | 2022-03-25 | SOL | PV | 200 |  | 2019-08-26 | 2019-07-11 | 2019-09-05 | 2020-08-26 | No |  | No |  |  | Not Required
22INR0236 | Point Mountain Solar | SS Completed, FIS Started, No IA | Hecate Energy Point Mountain LLC | 76000 North McCamey 345kV | Crane | WEST | 2022-07-01 | SOL | PV | 514 | MW Size | 2019-08-13 | 2019-08-26 | 2019-11-08 |  |  |  | No |  |  | Not Required
22INR0237 | Dragan Solar | SS Completed, FIS Started, No IA | Hecate Comanche Solar LLC | 1440 Comanche 345kV | Comanche | NORTH | 2022-05-01 | SOL | PV | 411 |  | 2019-11-11 | 2019-11-11 | 2020-02-17 |  |  |  | No |  |  | Not Required
22INR0238 | Rockefeller Solar | SS Completed, FIS Started, No IA | Photosol US Renewable Energy LLC | 76003 Big Hill 345kV | Schleicher | WEST | 2022-12-01 | SOL | PV | 207.48 |  | 2020-08-20 | 2019-10-31 | 2020-01-24 |  |  |  | No |  |  | Not Required
22INR0239 | Rockefeller Storage | SS Completed, FIS Started, No IA | Photosol US Renewable Energy LLC | 76003 Big Hill 345kV | Schleicher | WEST | 2022-12-01 | OTH | BA | 207.48 |  | 2020-08-20 | 2019-10-31 | 2020-01-24 |  |  |  | No |  |  | Not Required
22INR0242 | Bright Arrow Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 1685 Farmersville - 1695 Monticello ckt 2 | Hopkins | NORTH | 2022-12-15 | SOL | PV | 330.67 | COD | 2020-03-09 | 2020-02-12 | 2020-05-01 |  |  |  | No |  |  | Not Required
22INR0244 | Razorbill Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP to 44200 Hillje 345kV Ckt 64 | Matagorda | COASTAL | 2022-12-15 | SOL | PV | 240 | FIS Request |  | 2020-01-02 | 2020-03-26 |  |  |  | No |  |  | Not Required
22INR0251 | Shaula I Solar | SS Completed, FIS Started, No IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5915 STP | DeWitt | SOUTH | 2022-08-01 | SOL | PV | 205.2 | COD | 2019-11-27 | 2019-12-03 | 2020-03-08 |  |  |  | No |  |  | Not Required
22INR0254 | Pisgah Ridge Solar | SS Completed, FIS Started, No IA | Duke Energy Renewables Solar, LLC | tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2022-12-31 | SOL | PV | 253.85 |  | 2019-11-01 | 2019-11-01 | 2020-02-07 |  |  |  | No |  |  | Not Required
22INR0257 | Corazon Solar Phase II | SS Completed, FIS Started, IA | BAYWA R.E. SOLAR PROJECTS | 80219 Lobo 345kV | Webb | SOUTH | 2022-05-31 | SOL | PV | 203.9 |  | 2019-12-16 | 2019-12-19 | 2020-03-12 |  | No | 2020-08-04 | No | Not Required | Not Required | Not Required
22INR0260 | Eliza Storage | SS Completed, FIS Started, No IA | Ables Springs Storage, LLC | tap 345kV 2478 Royse - 3103 Shamburger | Kaufman | NORTH | 2022-06-01 | OTH | BA | 100.62 |  | 2020-08-21 | 2019-12-03 | 2020-02-25 |  |  |  | No |  |  | Not Required
22INR0261 | Dorado Solar | SS Completed, FIS Started, No IA | Eldorado Solar Power LLC | 345kV 68051 REATA | Callahan | WEST | 2023-01-01 | SOL | PV | 406.25 | MW Size | 2020-09-02 | 2020-01-09 | 2020-03-30 |  |  |  | No |  |  | Not Required
22INR0262 | Deville Solar | SS Completed, FIS Started, No IA | Deville Solar LLC | 345kV 68051 REATA | Callahan | WEST | 2023-01-01 | SOL | PV | 556.25 | MW Size | 2020-09-02 | 2020-01-22 | 2020-04-08 |  |  |  | No |  |  | Not Required
22INR0267 | Shaula II Solar | SS Completed, FIS Started, No IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5915 STP | DeWitt | SOUTH | 2023-05-15 | SOL | PV | 205.2 | COD | 2019-12-27 | 2019-12-18 | 2020-03-12 |  |  |  | No |  |  | Not Required
22INR0269 | Shinnery Hill Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 6111 Riley7B - 1730 W Krum | Wichita | WEST | 2022-12-01 | SOL | PV | 502.54 | COD | 2020-04-23 | 2019-12-17 | 2020-03-06 |  |  |  | No |  |  | Not Required
22INR0270 | Brass Fork Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 60703 Gauss7D - 60515 Clear Crossing | Haskell | WEST | 2022-12-01 | SOL | PV | 513.19 | Proj Name COD | 2020-08-27 | 2019-12-17 | 2020-03-06 |  |  |  | No |  |  | Not Required
22INR0271 | Bronze Fork Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek | Haskell | WEST | 2022-12-01 | SOL | PV | 515.89 | Proj Name COD | 2020-08-27 | 2019-12-17 | 2020-03-06 |  |  |  | No |  |  | Not Required
22INR0272 | Brinton Fork Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 60791 Perigee Station | Haskell | WEST | 2022-12-01 | SOL | PV | 513.5 | Proj Name COD | 2020-08-27 | 2019-12-17 | 2020-03-10 |  |  |  | No |  |  | Not Required
22INR0275 | Coleto Creek ESS Addition | SS Completed, FIS Started, No IA | COLETO CREEK POWER LLC | 8162 Coleto Creek 138kV | Goliad | SOUTH | 2022-03-14 | OTH | BA | 100.1 | FIS Request |  | 2019-12-11 | 2020-03-05 |  |  |  | No |  |  | Not Required
22INR0276 | Trinidad ESS Addition | SS Completed, FIS Started, No IA | LUMINANT GENERATION COMPANY LLC | 3127 Trinidad 138kV | Henderson | NORTH | 2022-03-15 | OTH | BA | 100.1 | FIS Request |  | 2019-12-11 | 2020-03-06 |  |  |  | No |  |  | Not Required
22INR0279 | Clutch City Solar | SS Completed, FIS Started, No IA | HZ Solar I | tap 138kV 42960 Mustang Bayou – 42100 Hudson | Brazoria | COASTAL | 2022-12-31 | SOL | PV | 204.17 |  | 2020-03-16 | 2020-01-22 | 2020-04-08 |  |  |  | No |  |  | Not Required
22INR0280 | Roseland Storage | SS Completed, FIS Started, No IA | Hecate Energy Roseland Storage 1 LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2022-12-31 | OTH | BA | 100 |  | 2020-01-17 | 2019-12-26 | 2020-03-24 |  |  |  | No |  |  | Not Required
22INR0283 | SP Peregrine Solar | SS Completed, FIS Started, No IA | SP-PeregrineSolar LLC | tap 345kV 8624 Grissom – 8164 Coleto Creek | Goliad | SOUTH | 2023-03-31 | SOL | PV | 300 |  | 2020-07-29 | 2020-01-07 | 2020-03-30 |  |  |  | No |  |  | Not Required
22INR0295 | Coral Solar | SS Completed, FIS Started, No IA | Copperhead Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2022-06-01 | SOL | PV | 203 |  | 2020-08-17 | 2020-06-03 | 2020-06-16 |  |  |  | No |  |  | Not Required
22INR0322 | BRP Paleo BESS | SS Completed, FIS Started, No IA | BRP Paleo BESS LLC | 345 kV Blackwater Draw Switch (formerly 23920 Abernathy 345kV) | Hale | PANHANDLE | 2022-09-30 | OTH | BA | 202.4 |  | 2020-04-09 | 2020-04-13 | 2020-06-25 |  |  |  | No |  |  | Not Required
22INR0324 | Endurance Park Storage 2 | SS Completed, FIS Started, No IA | KCE TX 22, LLC | 11306 Dermott 138kV | Scurry | WEST | 2022-04-30 | OTH | BA | 52.25 |  | 2020-05-21 | 2020-04-13 | 2020-06-25 |  |  |  | No |  |  | Not Required
22INR0325 | BRP Dickens BESS | SS Completed, FIS Started, No IA | BRP Dickens BESS LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2022-09-30 | OTH | BA | 202.41 |  | 2020-04-16 | 2020-04-22 | 2020-07-09 |  |  |  | No |  |  | Not Required
22INR0326 | Inertia Wind | SS Started, FIS Started, No IA | Inertia Wind Project, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2022-07-01 | WIN | WT | 350 |  | 2020-08-31 | 2020-06-03 |  |  |  |  | No |  |  | Not Required
22INR0327 | Hummingbird Storage | SS Completed, FIS Started, No IA | KCE TX 10, LLC | 1730 Krum 345kV | Denton | NORTH | 2022-05-11 | OTH | BA | 104.62 |  | 2020-05-29 | 2020-05-20 | 2020-07-30 |  |  |  | No |  |  | Not Required
22INR0328 | Inertia BESS | SS Started, FIS Started, No IA | Inertia Wind Project, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2022-07-01 | OTH | BA | 121.45 |  | 2020-08-24 | 2020-06-03 |  |  |  |  | No |  |  | Not Required
22INR0330 | Old Aqueduct Batt | SS Completed, FIS Started, No IA | Old Aqueduct LLC | 23920 Abernathy 345kV | Hale | PANHANDLE | 2021-09-30 | OTH | BA | 300 | Proj Name | 2020-07-24 | 2020-05-01 | 2020-07-13 |  |  |  | No |  |  | Not Required
22INR0335 | Estonian Solar Farm | SS Completed, FIS Started, No IA | 249RD 8ME | tap 138kV 1801 Paris Pump Tap – 17011 LKCRK_P8 | Delta | NORTH | 2022-12-01 | SOL | PV | 204.47 |  | 2020-01-17 | 2020-04-22 | 2020-06-29 |  |  |  | No |  |  | Not Required
22INR0336 | Estonian Energy Storage | SS Completed, FIS Started, No IA | 249RD 8ME | tap 138kV 1801 Paris Pump Tap – 17011 LKCRK_P8 | Delta | NORTH | 2022-12-01 | OTH | BA | 102.5 |  | 2020-02-26 | 2020-04-22 | 2020-06-29 |  |  |  | No |  |  | Not Required
22INR0337 | Skylab Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 5915 STP - 8249 Angstrom | Wharton | SOUTH | 2022-05-31 | SOL | PV | 609.74 |  | 2020-08-10 | 2020-06-03 | 2020-08-11 |  |  |  | No |  |  | Not Required
22INR0338 | Limousin Oak Storage | SS Completed, FIS Started, No IA | KCE TX 15, LLC | 44645 Singleton 345kV | Grimes | NORTH | 2022-05-30 | OTH | BA | 104.62 | COD | 2020-05-14 | 2020-05-20 | 2020-07-30 |  |  |  | No |  |  | Not Required
22INR0346 | Clybourn Solar | SS Completed, FIS Started, No IA | Leeward Renewable Energy Development, LLC | 8121 Blessing 138kV + 14 mile gen-tie | Matagorda | COASTAL | 2022-12-31 | SOL | PV | 201.5 |  | 2020-07-20 | 2020-05-20 | 2020-07-30 |  |  |  | No |  |  | Not Required
22INR0347 | BRP Crater BESS | SS Completed, FIS Started, No IA | BRP Crater BESS LLC | tap 345kV 1025 Falcon Seaboard - 1021 Midland East | Howard | WEST | 2022-11-30 | OTH | BA | 303.53 |  | 2020-05-18 | 2020-05-20 | 2020-07-30 |  |  |  | No |  |  | Not Required
22INR0348 | Barrel Summit Storage | SS Completed, FIS Started, No IA | KCE TX 14, LLC | 221 Trumbull 138kV | Ellis | NORTH | 2022-03-31 | OTH | BA | 104.62 |  |  | 2020-06-09 | 2020-08-18 |  |  |  | No |  |  | Not Required
22INR0349 | BRP Antlia BESS | SS Completed, FIS Started, No IA | BRP Antlia BESS LLC | tap 138kV 8998 Maxwell – 8261 Whiting | Val Verde | WEST | 2022-10-30 | OTH | BA | 70.95 |  | 2020-06-18 | 2020-06-03 | 2020-08-11 |  |  |  | No |  |  | Not Required
22INR0350 | Milam Solar 2 | SS Started, FIS Started, No IA | Sandow Lakes Ranch Solar II, LLC | tap one 345kV 7040 Austrop - 13429 Sandow line | Milam | SOUTH | 2023-05-16 | SOL | PV | 290.21 | COD | 2020-08-24 | 2020-09-11 |  |  |  |  | No |  |  | Not Required
22INR0351 | Elston Solar | SS Completed, FIS Started, No IA | Leeward Renewable Energy Development, LLC | tap 345kV 44000 WAP - 5915 STP | Matagorda | COASTAL | 2022-12-31 | SOL | PV | 402.6 |  | 2020-07-20 | 2020-05-20 | 2020-07-30 |  |  |  | No |  |  | Not Required
22INR0352 | Sparta Solar | SS Completed, FIS Started, IA | Sparta Solar | tap 345kV 5725 Pawnee – 8606 Goddard | Bee | SOUTH | 2022-04-01 | SOL | PV | 256 |  | 2020-06-25 | 2020-05-20 | 2020-07-30 |  |  | 2020-08-14 | Yes | Not Required | Not Required | Not Required | 2020-08-17
22INR0353 | BRP Carina BESS | SS Completed, FIS Started, No IA | BRP Carina BESS LLC | 8479 Clarkwood 138kV | Nueces | COASTAL | 2022-10-30 | OTH | BA | 151.85 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 |  |  |  | No |  |  | Not Required
22INR0357 | Loma Pinta Solar | SS Completed, FIS Started, No IA | Loma Pinta Wind Energy, LLC | 5705 Fowlerton 138kV | La Salle | SOUTH | 2022-12-01 | SOL | PV | 203.06 |  | 2020-09-08 | 2020-06-03 | 2020-08-18 |  |  |  | No |  |  | Not Required
22INR0360 | Jade Solar | SS Completed, FIS Started, No IA | IP RENEWABLE ENERGY HOLDINGS LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Scurry | WEST | 2022-12-31 | SOL | PV | 374.4 |  | 2020-07-15 | 2020-06-26 | 2020-09-14 |  |  |  | No |  |  | Not Required
22INR0361 | Sibyl Power Station | SS Started, FIS Started, No IA | Sibyl Generating, LLC | Tap 138kV 43261 Southwyck - 44552 Telview | Fort Bend | HOUSTON | 2022-07-01 | GAS | GT | 298.68 |  | 2020-08-26 | 2020-09-02 |  |  |  |  | No
22INR0362 | Pluto Solar | SS Completed, FIS Started, No IA | Pluto Solar, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2022-11-30 | SOL | PV | 252.8 |  | 2020-07-28 | 2020-06-26 | 2020-09-14 |  |  |  | No |  |  | Not Required
22INR0363 | Hayhurst Texas Solar | SS Started, FIS Started, No IA | CHEVRON USA, INC. | 1090 Screwbean 138kV | Culberson | WEST | 2022-08-31 | SOL | PV | 45 |  |  | 2020-08-21 |  |  |  |  | No |  |  | Not Required
22INR0365 | BRP Mensa BESS | SS Completed, FIS Started, No IA | BRP Mensa BESS LLC | 60718 Pecos Valley 138kV | Pecos | WEST | 2022-12-30 | OTH | BA | 202.79 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 |  |  |  | No |  |  | Not Required
22INR0366 | BRP Libra BESS | SS Completed, FIS Started, No IA | BRP Libra BESS LLC | 5133 Elm Creek 345kV | Guadalupe | SOUTH | 2022-11-30 | OTH | BA | 202.38 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 |  |  |  | No |  |  | Not Required
22INR0367 | BRP Lyra BESS | SS Completed, FIS Started, No IA | BRP Lyra BESS LLC | 60718 Pecos Valley 138kV | Pecos | WEST | 2022-11-30 | OTH | BA | 202.79 | MW Size | 2020-07-03 | 2020-06-26 | 2020-09-14 |  |  |  | No |  |  | Not Required
22INR0368 | Padua Grid BESS | SS Completed, FIS Started, No IA | Padua Grid, LLC | 5395 O.W Sommers 138kV | Bexar | SOUTH | 2022-06-01 | OTH | BA | 202.6 |  | 2020-07-23 | 2020-07-10 | 2020-09-28 |  |  |  | No |  |  | Not Required
22INR0369 | Mark One Power Station | SS Completed, FIS Started, No IA | Mark One Generating, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2022-06-01 | GAS | GT | 497.8 |  | 2020-07-20 | 2020-07-10 | 2020-09-28 |  |  |  | No
22INR0371 | PES 2 Power Station | SS Completed, FIS Completed, IA | HO CLARKE GENERATING LLC | 47150 H.O. Clarke 138kV | Harris | HOUSTON | 2021-07-01 | GAS | GT | 102 | MW Size SFS/NtP | 2020-07-21 | 2020-07-24 |  | 2020-07-31 |  | 2019-12-17 | Yes
22INR0372 | BRP Hydra BESS | SS Started, FIS Started, No IA | BRP Hydra BESS LLC | 76002 Bakersfield 345kV | Pecos | WEST | 2022-10-30 | OTH | BA | 202.46 | MW Size | 2020-07-27 | 2020-07-24 |  |  |  |  | No |  |  | Not Required
22INR0383 | BRP Musca BESS | SS Started, FIS Started, No IA | BRP Musca BESS LLC | 60361 Santa Rita 138kV | Reagan | WEST | 2022-11-30 | OTH | BA | 101.28 |  | 2020-08-13 | 2020-07-24 |  |  |  |  | No |  |  | Not Required
22INR0384 | BRP Pavo BESS | SS Started, FIS Started, No IA | BRP Pavo BESS LLC | 38430 TN White Baker 138kV | Pecos | WEST | 2022-11-30 | OTH | BA | 177.13 |  | 2020-08-19 | 2020-07-24 |  |  |  |  | No |  |  | Not Required
22INR0385 | BRP Pictor BESS | SS Started, FIS Started, No IA | BRP Pictor BESS LLC | 60400 Lynx 138kV | Crane | WEST | 2022-12-30 | OTH | BA | 202.7 |  | 2020-08-13 | 2020-07-24 |  |  |  |  | No |  |  | Not Required
22INR0386 | BRP Octans BESS | SS Started, FIS Started, No IA | BRP OCTANS BESS LLC | 6671 Tombstone 138kV | Pecos | WEST | 2022-11-30 | OTH | BA | 126.63 |  | 2020-08-13 | 2020-07-24 |  |  |  |  | No |  |  | Not Required
22INR0387 | Val Vista Grid BESS | SS Started, FIS Started, No IA | Val Vista Grid, LLC | 8380 North Edinburg 138kV | Hidalgo | SOUTH | 2022-05-31 | OTH | BA | 202.85 |  | 2020-08-04 | 2020-08-04 |  |  |  |  | No |  |  | Not Required
22INR0388 | BRP Cachi BESS | SS Started, FIS Started, No IA | BRP Cachi BESS LLC | 7680 Clear Springs 138kV | Guadalupe | SOUTH | 2022-12-30 | OTH | BA | 202.46 |  |  | 2020-08-21 |  |  |  |  | No |  |  | Not Required
22INR0390 | BRP Perseus BESS | SS Started, FIS Started, No IA | BRP Perseus BESS LLC | 8452 Lon Hill 138kV | Nueces | COASTAL | 2022-12-30 | OTH | BA | 202.5 |  | 2020-08-19 | 2020-08-21 |  |  |  |  | No |  |  | Not Required
22INR0397 | Buckeye Corpus Fuels Solar | SS Started, FIS Started, No IA | Corpus Fuels, LLC | 8858 McKenzie 138kV | Nueces | COASTAL | 2022-09-01 | SOL | PV | 57.59 |  |  | 2020-08-21 |  |  |  |  | No |  |  | Not Required
22INR0400 | Dragan Storage | SS Started, FIS Started, No IA | Hecate Grid Dragan Storage LLC | 1440 Comanche 345kV | Comanche | NORTH | 2022-05-31 | OTH | BA | 408.3 |  |  | 2020-08-21 |  |  |  |  | No |  |  | Not Required
22INR0402 | Frye Storage | SS Started, FIS Started, No IA | Hecate Grid Frye Storage LLC | tap 345kV 23912 Ogallala - 23914 Tule Canyon c2 | Swisher | PANHANDLE | 2022-08-31 | OTH | BA | 510 | MW Size | 2020-08-26 | 2020-09-02 |  |  |  |  | No |  |  | Not Required
22INR0408 | BRP Pular BESS | SS Started, FIS Started, No IA | BRP Pular BESS LLC | 8380 North Edinburg 138kV | Hidalgo | SOUTH | 2022-10-30 | OTH | BA | 233.13 | FIS Request | 2020-09-02 | 2020-09-11 |  |  |  |  | No |  |  | Not Required
22INR0412 | Andromeda Solar | SS Started, FIS Started, No IA | IP Renewable Energy Holdings LLC | Tap 345kV 11305 Dermott - 60706 Kirchhoff C | Scurry | WEST | 2022-12-31 | SOL | PV | 374.4 | FIS Request | 2020-09-22 | 2020-09-11 |  |  |  |  | No |  |  | Not Required
22INR0423 | BRP Quela BESS | SS Started, FIS Started, No IA | BRP Quela BESS LLC | Tap 138kV 5110 J.T. Deely - 5294 Martinez | Bexar | SOUTH | 2022-12-30 | OTH | BA | 303.74 | FIS Request | 2020-09-25 | 2020-09-25 |  |  |  |  | No |  |  | Not Required
22INR0424 | BRP Denali BESS | SS Started, FIS Started, No IA | BRP Denali BESS LLC | Tap 138kV 5395 Sommers - 5030 Braunig East | Bexar | SOUTH | 2022-11-30 | OTH | BA | 258.41 | FIS Request | 2020-09-25 | 2020-09-25 |  |  |  |  | No |  |  | Not Required
22INR0427 | BRP Kabru BESS | SS Started, FIS Started, No IA | BRP Kabru BESS LLC | 1284 Shafter Lake 138kV | Andrews | WEST | 2023-03-30 | OTH | BA | 202.45 | FIS Request | 2020-09-28 | [5 empty] | No |  |  | Not Required
23INR0007 | Outpost Solar | SS Completed, FIS Started, No IA | Hecate Energy Outpost Solar LLC | Tap 345kV 80219 Lobo - 5709 Fowlerton | Webb | SOUTH | 2023-05-01 | SOL | PV | 513.7 |  | 2020-02-11 | 2019-12-06 | 2020-02-25 |  |  |  | No |  |  | Not Required
23INR0008 | Harley Hand Solar | SS Completed, FIS Started, No IA | Hecate Energy Harley Hand LLC | 11420 Sweetwater East 345kV | Nolan | WEST | 2023-05-01 | SOL | PV | 513.7 |  | 2019-12-12 | 2019-12-16 | 2020-03-11 |  |  |  | No |  |  | Not Required
23INR0009 | Shaula III Solar | SS Completed, FIS Started, No IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5915 STP | DeWitt | SOUTH | 2023-07-04 | SOL | PV | 205.2 | COD | 2020-01-13 | 2019-12-18 | 2020-03-11 |  |  |  | No |  |  | Not Required
23INR0010 | Plateau Solar | SS Completed, FIS Started, No IA | Innovative Solar 206, LLC | tap 345kV 68000 West Shackelford - 68001 Claytonville | Jones | WEST | 2023-04-13 | SOL | PV | 300 |  | 2020-09-04 | 2019-12-06 | 2020-02-25 |  |  |  | No |  |  | Not Required
23INR0013 | Nolan Solar | SS Completed, FIS Started, No IA | Tenaska Solar XVII, LLC | 1338 Eskota 138kV | Nolan | WEST | 2023-06-01 | SOL | PV | 150 | FIS Request |  | 2020-01-02 | 2020-03-20 |  |  |  | No |  |  | Not Required
23INR0014 | Hedgehog Solar | SS Completed, FIS Started, No IA | Innovative Solar 408, LLC | tap 138kV 8234 Uvalde - 8241 Razorback | Medina | SOUTH | 2023-04-20 | SOL | PV | 85 |  | 2020-09-16 | 2019-12-11 | 2020-03-06 |  |  |  | No |  |  | Not Required
23INR0015 | Scarlet Solar | SS Completed, FIS Started, No IA | Innovative Solar 416, LLC | tap 345kV 23912 Ogallala - 23910 Windmill | Castro | PANHANDLE | 2023-04-20 | SOL | PV | 180 |  | 2020-09-16 | 2019-12-11 | 2020-03-06 |  |  |  | No |  |  | Not Required
23INR0021 | Hornet Solar | SS Completed, FIS Started, No IA | Hornet Solar LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala | Swisher | PANHANDLE | 2023-06-01 | SOL | PV | 503.21 |  | 2020-05-15 | 2020-02-04 | 2020-04-29 |  |  |  | No |  |  | Not Required
23INR0025 | Blue Sky Solar | SS Completed, FIS Started, No IA | Blue Sky Solar | 6562 Friend Ranch 138kV | Crockett | WEST | 2022-12-15 | SOL | PV | 65 |  |  | 2020-02-26 | 2020-06-02 |  |  |  | No |  |  | Not Required
23INR0026 | Baker Branch Solar | SS Completed, FIS Started, No IA | Mockingbird Solar Center, LLC | tap 345kV 1692 Paris - 1690 Valley | Lamar | NORTH | 2023-02-28 | SOL | PV | 400 |  | 2020-04-09 | 2020-03-26 | 2020-06-04 |  |  |  | No |  |  | Not Required
23INR0027 | Cachena Solar | SS Completed, FIS Started, No IA | 247CT 8ME | Tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Lavaca | SOUTH | 2023-06-01 | SOL | PV | 400 |  | 2020-08-19 | 2020-05-01 | 2020-07-13 |  |  |  | No |  |  | Not Required
23INR0029 | Cedar Bayou5 | SS Completed, FIS Started, No IA | NRG Cedar Bayou 5 LLC | 40000 Cedar Bayou 345kV | Chambers | HOUSTON | 2023-06-01 | GAS | CC | 697 |  | 2020-03-31 | 2020-03-26 | 2020-06-04 |  |  |  | No
23INR0031 | Solace Solar | SS Completed, FIS Started, No IA | IP QUANTUM, LLC. | tap 345kV 1430 Graham - 1048 Tonkawas | Haskell | WEST | 2022-12-31 | SOL | PV | 374.4 |  | 2020-04-21 | 2020-04-22 | 2020-07-09 |  |  |  | No |  |  | Not Required
23INR0042 | Delilah Solar 2A | SS Completed, FIS Completed, No IA | Invenergy Solar Development North America LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2023-06-30 | SOL | PV | 200 |  | 2019-05-13 | 2020-06-03 | 2018-01-03 | 2020-06-09 |  |  | No |  |  | Not Required
23INR0044 | Parliament Solar | SS Completed, FIS Started, No IA | AP Solar 8, LLC | Tap 345kV 44900 Zenith - 44645 Singleton | Waller | HOUSTON | 2023-05-31 | SOL | PV | 410 |  | 2020-08-03 | 2020-06-19 | 2020-09-08 |  |  |  | No |  |  | Not Required
23INR0047 | Charger Solar | SS Completed, FIS Started, No IA | AP Solar 4, LLC | tap 345kV 8249 Angstrom – 5915 STP | Refugio | COASTAL | 2023-03-31 | SOL | PV | 407.84 |  | 2020-07-29 | 2020-06-19 | 2020-09-08 |  |  |  | No |  |  | Not Required
23INR0055 | Tabor Solar | SS Started, FIS Started, No IA | Quanah Solar LLC | tap 345kV 60501 Tesla - 6111 Riley | Hardeman | WEST | 2023-05-15 | SOL | PV | 506.4 |  | 2020-08-31 | 2020-09-02 |  |  |  |  | No |  |  | Not Required
23INR0056 | Caliche Mound Solar | SS Completed, FIS Started, No IA | Tierra Blanco Solar LLC | 23910 Windmill 345kV | Deaf Smith | PANHANDLE | 2023-05-15 | SOL | PV | 405.74 |  | 2020-08-27 | 2020-07-24 | 2020-09-08 |  |  |  | No |  |  | Not Required
23INR0060 | Delilah Solar 3A | SS Completed, FIS Completed, No IA | Invenergy Solar Development North America LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2023-06-30 | SOL | PV | 90 |  | 2019-05-13 |  | 2019-01-03 | 2020-06-09 |  |  | No | Not Required | Not Required | Not Required
23INR0067 | Wekiva Grid | SS Started, FIS Started, No IA | Wekiva Grid, LLC | 5925 East DC Tie 345kV | Titus | NORTH | 2022-05-31 | OTH | BA | 202.61 |  | 2020-08-12 | 2020-08-21 |  |  |  |  | No |  |  | Not Required
23INR0069 | Corbin Grid Batt | SS Started, FIS Started, No IA | Corbin Grid, LLC | 44510 Obrien 138kV | Fort Bend | HOUSTON | 2023-05-31 | OTH | BA | 202.76 | Proj Name COD | 2020-08-28 | 2020-08-04 |  |  |  |  | No |  |  | Not Required
23INR0070 | Chillingham Solar | SS Started, FIS Started, No IA | 250LB 8me | 3687 Bell County East 345kV | Bell | NORTH | 2023-06-01 | SOL | PV | 359.37 |  | 2020-09-02 | 2020-08-04 |  |  |  |  | No |  |  | Not Required
23INR0071 | BRP Volans BESS | SS Started, FIS Started, No IA | BRP Volans BESS LLC | 11074 Orbison Tap 138kV | Winkler | WEST | 2023-03-31 | OTH | BA | 202.47 |  | 2020-08-26 | 2020-08-04 |  |  |  |  | No |  |  | Not Required
23INR0072 | BRP Tortolas BESS | SS Started, FIS Started, No IA | BRP Tortolas BESS LLC | 39030 Alvin 138kV | Brazoria | COASTAL | 2023-03-31 | OTH | BA | 50.7 |  | 2020-08-27 | 2020-08-04 |  |  |  |  | No |  |  | Not Required
23INR0073 | BRP Galan BESS | SS Started, FIS Started, No IA | BRP Galan BESS LLC | 5007 Alamo One 138kV | Bexar | SOUTH | 2023-03-31 | OTH | BA | 75.97 |  | 2020-08-20 | 2020-08-04 |  |  |  |  | No |  |  | Not Required
23INR0074 | BRP Ampato BESS | SS Started, FIS Started, No IA | BRP Ampato BESS LLC | 10002 NS Crane Switch 138kV | Crane | WEST | 2023-03-31 | OTH | BA | 121.56 | MW Size | 2020-08-26 | 2020-08-04 |  |  |  |  | No |  |  | Not Required
23INR0075 | BRP Pisces BESS | SS Started, FIS Started, No IA | BRP Pisces BESS LLC | Tap 345kV 11188 QUARRYFLD - 11010 WOLF | Ward | WEST | 2023-03-31 | OTH | BA | 202.47 | FIS Request | 2020-09-22 | 2020-08-04 |  |  |  |  | No |  |  | Not Required
23INR0076 | Cannon Solar | SS Started, FIS Started, No IA | Duke Energy Renewables Solar, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2023-12-31 | SOL | PV | 152.5 | FIS Request | 2020-09-21 | 2020-09-11 |  |  |  |  | No |  |  | Not Required
23INR0077 | Cachena Storage | SS Started, FIS Started, No IA | 247CT 8ME | Tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Lavaca | SOUTH | 2023-06-01 | OTH | BA | 102.5 | MW Size | 2020-08-21 | 2020-08-21 |  |  |  |  | No |  |  | Not Required
23INR0079 | Chillingham Storage | SS Started, FIS Started, No IA | 250LB 8me | 3687 Bell County East 345kV | Bell | NORTH | 2023-06-01 | OTH | BA | 153.75 | FIS Request | 2020-09-04 | 2020-09-11 |  |  |  |  | No |  |  | Not Required
23INR0080 | Soda Lake Solar 1 | SS Started, FIS Started, No IA | Crane Solar Generating 2 | 76026 Soda Lake 138kV | Crane | WEST | 2023-05-22 | SOL | PV | 202.59 | FIS Request | 2020-09-08 | 2020-09-11 |  |  |  |  | No |  |  | Not Required
23INR0088 | Nockenut Springs Solar 1 | SS Started, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP | Guadalupe | SOUTH | 2023-12-31 | SOL | PV | 203.17 | FIS Request | 2020-09-23 | 2020-09-25 |  |  |  |  | No |  |  | Not Required
23INR0089 | Donegal Solar | SS Started, FIS Started, No IA | HE-Cottonwood Solar, LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2023-09-30 | SOL | PV | 218.4 | FIS Request | [6 empty] | No |  |  | Not Required
23INR0093 | Alila Solar | SS Started, FIS Started, No IA | Electra Energy Project, LLC | 8249 Angstrom 345kV | San Patricio | COASTAL | 2023-05-05 | SOL | PV | 256.5 | FIS Request | [6 empty] | No |  |  | Not Required
23INR0094 | BRP Pyxis BESS | SS Started, FIS Started, No IA | BRP Pyxis BESS LLC | tap 138kV 1009 Yucca - 11197 Sand Tank Pod | Ward | WEST | 2023-03-01 | OTH | BA | 202.45 | FIS Request | 2020-09-23 | 2020-09-25 |  |  |  |  | No |  |  | Not Required
23INR0104 | BRP Kamet BESS | SS Started, FIS Started, No IA | BRP Kamet BESS LLC | 1167 Mustang 138kV | Andrews | WEST | 2023-04-30 | OTH | BA | 202.46 | FIS Request | 2020-09-28 | [5 empty] | No |  |  | Not Required
24INR0007 | Nockenut Springs Solar 2 | SS Started, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP | Guadalupe | SOUTH | 2024-12-31 | SOL | PV | 203.26 | FIS Request | 2020-09-23 | 2020-09-25 |  |  |  |  | No |  |  | Not Required
25INR0002 | Barcelona TxHSR TPSS HN-4 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 45885 HocklyC - 46220 Peters | Harris | HOUSTON | 2026-04-30 | OTH | OT | 50 |  | 2019-10-11 | 2019-01-30 | 2019-04-17 |  | No |  | No | Not Required | Not Required
25INR0005 | Tokyo TxHSR TPSS EW-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2241 Ennis W - 2321 Waxahachie | Ellis | NORTH | 2026-04-30 | OTH | OT | 50 |  | 2019-09-13 | 2019-01-30 | 2019-04-17 |  |  |  | No | Not Required | Not Required
25INR0006 | Atlanta TxHSR TPSS DS-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2429 Watermill E - 3083 Wilmer | Dallas | NORTH | 2026-04-30 | OTH | OT | 50 |  | 2019-10-11 | 2019-01-30 | 2019-04-17 |  |  |  | No | Not Required | Not Required
25INR0010 | Nockenut Springs Solar 3 | SS Started, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP | Gonzales | SOUTH | 2025-12-31 | SOL | PV | 203.39 | FIS Request | 2020-09-23 | 2020-09-25 |  |  |  |  | No |  |  | Not Required
26INR0001 | Turin TxHSR TPSS HN-6 | SS Started, FIS Started, No IA | Texas Central Rail Holdings, LLC | 8 Crutchfield 138kV | Grimes | NORTH | 2026-04-30 | OTH | OT | 50 |  | 2019-10-22 | [5 empty] | No

## GINR Trends
GINR Trends
Reflects all projects for which a Security Screening Study has been requested.
Excludes projects that have a status of Inactive (status = INA).
Nameplate capacity will change across time due to additional projects, cancelations, expirations, adjustments from study results, and projects being placed into service.
| Year | Month | Total Projects | Project Count | [5 empty] | Project Capacity (MW)
|  |  |  | GINR milestones | [5 empty] | Fuel Type
|  |  |  | Initial Screening Study | Screening Study Complete | In Full Study | Completed Full Study | Signed Interconnection Agreement | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Battery | Other
| 2017 | Sep | 336 | 35 | 60 | 157 | 5 | 79 | 18 | 29915 | 24089 | 12001 | 0 | 0 | 0 | 0 | 0
| 2017 | Oct | 339 | 25 | 66 | 163 | 9 | 76 | 6 | 30090 | 24729 | 14201 | 0 | 0 | 0 | 0 | 0
| 2017 | Nov | 340 | 14 | 64 | 172 | 15 | 75 | 17 | 29882 | 24893 | 13747 | 0 | 0 | 0 | 0 | 0
| 2017 | Dec | 337 | 7 | 57 | 166 | 19 | 73 | 8 | 30198 | 24123 | 13969 | 0 | 0 | 0 | 30 | 0
| 2018 | Jan | 335 | 15 | 56 | 169 | 21 | 74 | 17 | 31420 | 22739 | 12768 | 0 | 0 | 0 | 0 | 0
| 2018 | Feb | 334 | 11 | 46 | 177 | 27 | 73 | 9 | 32258 | 22413 | 12727 | 0 | 0 | 0 | 0 | 0
| 2018 | Mar | 340 | 14 | 41 | 179 | 27 | 79 | 8 | 32897 | 23515 | 12065 | 0 | 0 | 0 | 0 | 0
| 2018 | Apr | 349 | 18 | 48 | 172 | 30 | 81 | 4 | 33427 | 24709 | 13484 | 0 | 0 | 0 | 0 | 0
| 2018 | May | 369 | 33 | 36 | 180 | 34 | 86 | 13 | 33799 | 27766 | 13442 | 0 | 0 | 0 | 200 | 0
| 2018 | Jun | 379 | 32 | 42 | 190 | 27 | 88 | 6 | 34376 | 28448 | 13674 | 0 | 0 | 0 | 522 | 0
| 2018 | Jul | 404 | 34 | 60 | 197 | 25 | 88 | 6 | 37708 | 30518 | 11668 | 0 | 0 | 0 | 522 | 0
| 2018 | Aug | 417 | 26 | 57 | 220 | 26 | 88 | 11 | 40851 | 29649 | 10814 | 0 | 0 | 0 | 2177 | 0
| 2018 | Sep | 426 | 30 | 67 | 212 | 26 | 91 | 15 | 40327.45 | 31655.3 | 8589.6 | 0 | 0 | 0 | 1889 | 0
| 2018 | Oct | 429 | 26 | 60 | 221 | 24 | 98 | 4 | 40237.59 | 32248.91 | 9073.6 | 0 | 0 | 0 | 1889 | 0
| 2018 | Nov | 443 | 23 | 59 | 235 | 26 | 100 | 7 | 40283.09 | 36682.4 | 7503.4 | 0 | 0 | 0 | 2048.35 | 0
| 2018 | Dec | 465 | 31 | 67 | 237 | 27 | 103 | 9 | 39596.45 | 40732.49 | 9249.4 | 0 | 0 | 0 | 2342.82 | 0
| 2019 | Jan | 489 | 43 | 69 | 244 | 26 | 107 | 20 | 39222.25 | 43504.49 | 10824.6 | 0 | 45 | 0 | 3147.38 | 0
| 2019 | Feb | 493 | 38 | 70 | 246 | 24 | 115 | 12 | 37419.7 | 47140.55 | 10528.6 | 0 | 45 | 0 | 3011.92 | 300
| 2019 | Mar | 505 | 42 | 68 | 247 | 33 | 115 | 18 | 35555.28 | 50999.9 | 10536.6 | 0 | 45 | 0 | 3265.2 | 441.8
| 2019 | Apr | 527 | 38 | 79 | 260 | 30 | 120 | 9 | 35644.28 | 54655.45 | 10102.6 | 0 | 45 | 0 | 3501.24 | 300
| 2019 | May | 563 | 60 | 68 | 279 | 26 | 130 | 11 | 35689.38 | 58579.47 | 9736.6 | 0 | 45 | 0 | 4120.39 | 300
| 2019 | Jun | 568 | 53 | 68 | 285 | 27 | 135 | 19 | 35739.18 | 59160.69 | 9739.6 | 0 | 0 | 0 | 3956.79 | 300
| 2019 | Jul | 586 | 36 | 87 | 295 | 25 | 143 | 11 | 36048.46 | 62356.08 | 9282.6 | 13 | 0 | 0 | 3970.39 | 300
| 2019 | Aug | 583 | 30 | 91 | 303 | 27 | 132 | 12 | 35275.72 | 64579.48 | 8206.8 | 13 | 0 | 0 | 4199.79 | 340.6
| 2019 | Sep | 575 | 30 | 91 | 298 | 26 | 130 | 15 | 34553.51 | 64343.73 | 7405.2 | 13 | 0 | 0 | 4452.39 | 300
| 2019 | Oct | 582 | 36 | 88 | 294 | 29 | 135 | 16 | 31683.23 | 64789.75 | 7445.5 | 13 | 0 | 0 | 5627.39 | 350
| 2019 | Nov | 589 | 38 | 89 | 300 | 29 | 133 | 11 | 32252.73 | 64664.04 | 5898 | 13 | 0 | 0 | 7214.39 | 350
| 2019 | Dec | 584 | 31 | 78 | 325 | 21 | 129 | 19 | 30173.96 | 67807.94 | 5607 | 13 | 0 | 0 | 7790.29 | 350
| 2020 | Jan | 613 | 47 | 78 | 333 | 23 | 132 | 3 | 30573.34 | 73636.8 | 5607 | 13 | 0 | 0 | 8965.62 | 558.96
| 2020 | Feb | 633 | 48 | 87 | 334 | 27 | 137 | 1 | 30514.72 | 77699.12 | 5507 | 13 | 0 | 0 | 9978.58 | 350
| 2020 | Mar | 621 | 35 | 101 | 320 | 21 | 144 | 21 | 28888.4 | 76238.17 | 5749 | 13 | 493 | 0 | 10381.08 | 350
| 2020 | Apr | 619 | 15 | 117 | 304 | 26 | 157 | 6 | 27779.79 | 76252.21 | 5083.8 | 13 | 493 | 0 | 10899.04 | 350
| 2020 | May | 595 | 20 | 89 | 300 | 27 | 159 | 40 | 25958.39 | 72191.13 | 5083.8 | 13 | 420 | 0 | 12380.59 | 480.95
| 2020 | Jun | 602 | 30 | 84 | 295 | 38 | 155 | 20 | 26271.99 | 73655.09 | 5416.8 | 13 | 420 | 0 | 13041.64 | 410
| 2020 | Jul | 615 | 27 | 84 | 298 | 48 | 158 | 9 | 25477.63 | 75322.06 | 5373.88 | 13 | 420 | 0 | 14475.7 | 350
| 2020 | Aug | 644 | 25 | 83 | 316 | 54 | 166 | 5 | 25886.17 | 76960.74 | 7024.02 | 13 | 420 | 0 | 17436.1 | 350
| 2020 | Sep | 633 | 28 | 65 | 318 | 40 | 182 | 37 | 23678.97 | 77073.76 | 6818.72 | 13 | 420 | 0 | 18109.14 | 350
Note: Other contains all Fuel and Technology Types not in the Solar, Wind, Gas or Battery categories.

## data_GINR Trends_1 (hidden)
| # Signed Interconnect Agreement | # Completed Full Study | # in Full Study | # Screening Study Complete | # Initial Screening study | GW Capacity
Sep-19 | 130 | 26 | 298 | 91 | 30 | 111.0678
Oct-19 | 135 | 29 | 294 | 88 | 36 | 109.9089
Nov-19 | 133 | 29 | 300 | 89 | 38 | 110.3922
Dec-19 | 129 | 21 | 325 | 78 | 31 | 112.1498
Jan-20 | 132 | 23 | 333 | 78 | 47 | 119.3547
Feb-20 | 137 | 27 | 334 | 87 | 48 | 124.0624
Mar-20 | 144 | 21 | 320 | 101 | 35 | 121.6196
Apr-20 | 157 | 26 | 304 | 117 | 15 | 120.8708
May-20 | 159 | 27 | 300 | 89 | 20 | 116.5279
Jun-20 | 155 | 38 | 295 | 84 | 30 | 119.2285
Jul-20 | 158 | 48 | 298 | 84 | 27 | 121.4323
Aug-20 | 166 | 54 | 316 | 83 | 25 | 128.09
Sep-20 | 182 | 40 | 318 | 65 | 28 | 126.4636

## data_GINR Trends_2 (hidden)
| Natural Gas | Nuclear | Coal | Wind | Solar | Biomass | Battery | Other | Total Project Count | Cancelled Project Count
Sep-19 | 7.4052 | 0.013 | 0 | 34.5535 | 64.3437 | 0 | 4.4524 | 0.3 | 575 | 15
Oct-19 | 7.4455 | 0.013 | 0 | 31.6832 | 64.7897 | 0 | 5.6274 | 0.35 | 582 | 16
Nov-19 | 5.898 | 0.013 | 0 | 32.2527 | 64.664 | 0 | 7.2144 | 0.35 | 589 | 11
Dec-19 | 5.607 | 0.013 | 0 | 30.174 | 67.8079 | 0 | 7.7903 | 0.35 | 584 | 19
Jan-20 | 5.607 | 0.013 | 0 | 30.5733 | 73.6368 | 0 | 8.9656 | 0.55896 | 613 | 3
Feb-20 | 5.507 | 0.013 | 0 | 30.5147 | 77.6991 | 0 | 9.9786 | 0.35 | 633 | 1
Mar-20 | 5.749 | 0.013 | 0.493 | 28.8884 | 76.2382 | 0 | 10.3811 | 0.35 | 621 | 21
Apr-20 | 5.0838 | 0.013 | 0.493 | 27.7798 | 76.2522 | 0 | 10.899 | 0.35 | 619 | 6
May-20 | 5.0838 | 0.013 | 0.42 | 25.9584 | 72.1911 | 0 | 12.3806 | 0.48095 | 595 | 40
Jun-20 | 5.4168 | 0.013 | 0.42 | 26.272 | 73.6551 | 0 | 13.0416 | 0.41 | 602 | 20
Jul-20 | 5.3739 | 0.013 | 0.42 | 25.4776 | 75.3221 | 0 | 14.4757 | 0.35 | 615 | 9
Aug-20 | 7.024 | 0.013 | 0.42 | 25.8862 | 76.9607 | 0 | 17.4361 | 0.35 | 644 | 5
Sep-20 | 6.8187 | 0.013 | 0.42 | 23.679 | 77.0738 | 0 | 18.1091 | 0.35 | 633 | 37

## data_GINR Trends_3 (hidden)
|  | Gas | Wind | Solar | Battery | Other
COASTAL | 2020 | 0.288 | 1.0627 | 0.12 |  | 0.013
| 2021 |  | 1.1031 | 1.5369 | 0.85032
| 2022 | 0.4978 | 0.77024 | 3.4871 | 0.90601
| 2023 |  |  | 2.4793 | 0.2007
| 2024 |  |  | 0.10208
HOUSTON | 2018 | 0.012
| 2020 | 0.317
| 2021 | 1.1706 |  | 0.94
| 2022 | 0.71092 | 0.4 | 0.80949
| 2023 | 0.697 |  | 0.458 | 0.20276
| 2025 |  |  |  |  | 0.05
| 2026 |  |  |  |  | 0.05
WEST | 2019 |  | 0
| 2020 | 0.083 | 3.475 | 0.82033
| 2021 |  | 5.5529 | 5.7881 | 1.4794
| 2022 |  | 3.0762 | 11.5922 | 2.8381
| 2023 | 0.45 | 1.0002 | 5.757 | 1.184
| 2025 | 1.35
NORTH | 2020 | 0.065 | 0.47288 | 0.31815 |  | 0.42
| 2021 | 0.15 | 1.5253 | 3.1549 | 1.0807
| 2022 | 0.2 | 0.85199 | 11.5925 | 2.8992
| 2023 |  | 0.5 | 6.1773 | 0.15375
| 2024 | 0.3244 |  |  | 0.1001
| 2025 |  |  |  |  | 0.1
| 2026 |  |  |  |  | 0.15
PANHANDLE | 2020 |  |  | 0.2408
| 2021 | 0.112 | 0.1692 | 0.96181 | 0.4
| 2022 |  | 0.1515 | 1.2218 | 0.91481
| 2023 |  |  | 1.5084
| 2024 |  | 0.289 | 0.345
SOUTH | 2020 | 0.045 | 0.84351 | 0.02
| 2021 | 0.346 | 1.2254 | 3.2346 | 1.1517
| 2022 |  | 1.2099 | 7.6742 | 3.2661
| 2023 |  |  | 6.2259 | 0.48147
| 2024 |  |  | 0.30451
| 2025 |  |  | 0.20339

## Commissioning Update
Commissioning Approvals during September 2020
Commissioning Category | INR | Project Name | Fuel | County | Approval Date * | MW **
Synchronization Approved by ERCOT | 20INR0045 | Maverick Creek I W | Wind | Concho | 2020-09-01 | 373.2
Synchronization Approved by ERCOT | 19INR0151 | Impact Solar | Solar | Lamar | 2020-09-02 | 198.55
Energization Approved by ERCOT | 17INR0035 | Las Majadas Wind | Wind | Willacy | 2020-09-02 | 272.6
Energization Approved by ERCOT | 18INR0059 | East Raymond Wind | Wind | Willacy | 2020-09-16 | 201.6
Energization Approved by ERCOT | 19INR0034 | Greasewood Solar | Solar | Pecos | 2020-09-24 | 255
Energization Approved by ERCOT | 14INR0009 | WKN Amadeus Wind | Wind | Fisher | 2020-09-14 | 250.12
* For projects approved for commercial operations, the approval date is the Resource Commissioning Date defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a
Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative
values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.

## Inactive Projects
Inactive Projects as of end of September 2020*
INR | Project Name | Fuel | County | Inactive Date | MW **
16INR0044 | Halyard Wharton | Gas | Wharton | 2019-08-30 13:26 | 484
17INR0053 | HHGT repower Horse13+CallD | Wind | Taylor | 2019-08-30 13:32 | 44
13INR0025 | Northdraw Wind | Wind | Randall | 2019-08-30 13:38 | 150
16INR0014b | Cattleman Wind B | Wind | Castro | 2019-08-30 13:40 | 201.6
17INR0010 | FGE Texas 2 Gas | Gas | Mitchell | 2019-08-30 13:41 | 742.9
16INR0112 | Loma Pinta Wind | Wind | La Salle | 2019-08-30 13:44 | 200
16INR0014 | Cattleman Wind A | Wind | Castro | 2019-08-30 13:48 | 201.6
16INR0099 | Hecate Solar | Solar | Brewster | 2019-08-30 14:57 | 33
16INR0101 | Chatee Solar | Solar | Pecos | 2019-08-30 14:59 | 57
16INR0102 | Owego Solar | Solar | Pecos | 2019-08-30 15:01 | 74
13INR0010a | Mariah Del Este Wind | Wind | Parmer | 2019-09-09 10:19 | 152.5
20INR0025 | Spinel Solar | Solar | Medina | 2019-09-10 14:02 | 30
20INR0024 | Fluorite Solar | Solar | Uvalde | 2019-09-11 13:32 | 25
14INR0030c | Panhandle Wind 3 | Wind | Carson | 2019-09-24 09:41 | 248
19INR0055 | Monte Cristo 2 Wind | Wind | Hidalgo | 2019-10-24 18:00 | 236.9
19INR0133 | La Joya II Wind | Wind | Hidalgo | 2019-10-24 18:05 | 236.9
17INR0036 | Grandview 4 Phase A Wind | Wind | Carson | 2019-10-31 10:59 | 200.5
20INR0096 | Desert Rose Solar | Solar | Andrews | 2019-11-12 13:44 | 200
15INR0051 | Tierra Blanca W | Wind | Randall | 2019-11-12 14:45 | 200
18INR0009 | Eagle Pines Gas | Gas | Cherokee | 2019-11-19 10:20 | 1173.5
21INR0363 | Carol Battery | Other | Potter | 2019-11-25 16:33 | 168
13INR0038 | Wildrose Wind | Wind | Swisher | 2019-12-20 13:53 | 302.5
16INR0117 | Tecovas 1 W | Wind | Briscoe | 2020-03-02 12:48 | 200
19INR0031 | Bestla Solar | Solar | Winkler | 2020-03-04 16:50 | 180
08INR0019b | Grandview 5 W | Wind | Gray | 2020-03-09 16:21 | 249
16INR0012 | Stella 2 Wind | Wind | Kenedy | 2020-03-09 16:22 | 201
19INR0002 | Grandfalls Solar | Solar | Upton | 2020-04-01 11:39 | 350
17INR0033 | Tecovas 2 W | Wind | Briscoe | 2020-04-20 11:19 | 200
19INR0054 | Monte Cristo 1 W | Wind | Hidalgo | 2020-04-28 17:01 | 236.9
19INR0132 | La Joya I Wind | Wind | Hidalgo | 2020-04-28 17:06 | 236.9
20INR0146 | Angus Storage | Other | Bosque | 2020-05-04 11:36 | 63
19INR0150 | Millhouse Solar | Solar | Jim Wells | 2020-05-04 11:37 | 75
19INR0188 | Millhouse Storage | Other | Jim Wells | 2020-05-04 11:37 | 38
22INR0329 | Girasol | Solar | Zavala | 2020-05-22 08:29 | 200
20INR0023 | Agate Solar | Solar | Ellis | 2020-05-22 15:12 | 60
19INR0101 | Tehuacana Wind | Wind | Limestone | 2020-05-28 10:23 | 600
21INR0503 | Celeste Energy Storage | Other | Pecos | 2020-06-03 10:35 | 60.89
19INR0030 | San Bernard Solar | Solar | Wharton | 2020-06-18 11:51 | 100
16INR0074 | Chocolate Bayou W | Wind | Brazoria | 2020-06-19 09:49 | 149.5
20INR0026 | Longbow Solar | Solar | Brazoria | 2020-06-30 07:33 | 70
17INR0043 | Vaquero 1 Wind | Wind | Zapata | 2020-07-01 18:45 | 400
21INR0015 | Arroyo Del Bisonte Solar | Solar | Wharton | 2020-07-06 16:03 | 300
14INR0033 | Goodnight Wind | Wind | Armstrong | 2020-07-12 19:57 | 504.4
20INR0112 | Walstrom | Gas | Austin | 2020-07-24 10:38 | 200
20INR0271 | Blue Hills Wind | Wind | Val Verde | 2020-08-04 17:42 | 253.8
19INR0026 | Holstein 2 Solar | Solar | Nolan | 2020-09-14 19:21 | 100
20INR0299 | Sparkl BESS | Other | Guadalupe | 2020-09-16 12:30 | 20
21INR0305 | Frio Flat Wind | Wind | Deaf Smith | 2020-09-16 16:12 | 305
19INR0115 | Blackwater Draw Solar | Solar | Dawson | 2020-09-25 22:44 | 151.9
* Includes only those projects designated as Inactive by ERCOT or the project developer after the developer makes a Full Interconnection Study (FIS) request.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.

## Cancellation Update
Projects Cancelled by the Developer during September 2020*
INR | Project Name | Fuel | County | Cancel Date | MW **
21INR0020 | El Zorro Solar | Solar | Webb | 2020-09-01 10:48 | 253.3
21INR0028 | El Zorro Storage | Other | Webb | 2020-09-01 10:48 | 126.65
19INR0070 | Trevino Solar | Solar | Maverick | 2020-09-01 18:32 | 216
21INR0312 | Nereida Solar | Solar | Jones | 2020-09-02 05:23 | 77.62
21INR0266 | BLACKBIRD SOLAR | Solar | Mitchell | 2020-09-02 08:38 | 151.55
21INR0035 | Elmer Battery | Other | Tarrant | 2020-09-03 11:30 | 100
19INR0048 | Buenos Aires 1 Wind | Wind | Hidalgo | 2020-09-08 11:47 | 222.5
19INR0049 | Buenos Aires 2 W | Wind | Hidalgo | 2020-09-08 11:47 | 236.9
19INR0166 | Loma Pinta II | Wind | La Salle | 2020-09-08 11:54 | 201.6
19INR0167 | Gold Creek Solar | Solar | Dawson | 2020-09-10 11:25 | 140
20INR0265 | Karankawa 2 Expansion | Wind | San Patricio | 2020-09-15 20:42 | 98.3
18INR0065 | Goodranch Solar | Solar | Borden | 2020-09-16 17:59 | 200
21INR0289 | Saturn 1 Wind | Wind | Zapata | 2020-09-22 08:40 | 300
21INR0448 | Ennis-Tractebel (Config 1) Repower | Gas | Ellis | 2020-09-22 08:56 | 40.3
21INR0291 | Saturn 2 Wind | Wind | Zapata | 2020-09-22 12:30 | 150
22INR0247 | Pradera Solar | Solar | Webb | 2020-09-25 18:00 | 300
21INR0405 | CullenAlta | Gas | Harris | 2020-09-25 18:07 | 300
19INR0180 | Friendswood II | Gas | Brazoria | 2020-09-25 22:02 | 117
20INR0102 | Atascosa I Solar | Solar | Dawson | 2020-09-28 14:16 | 126.6
* Includes only those projects cancelled after the developer makes a Full Interconnection Study (FIS) request.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.